## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | INF-HSEQ CC0375-ITP-007 Open Drains & Checklist - Rev.6 | itp |  |  |  | Yes | INF-HSEQ CC0375-ITP-007 Open Drains & Checklist - Rev.6
section | 1.0 Preliminaries
checkpoint | 1.1 - Documentation
label | Ref docs - Issued drawings / Site copy drawings
label | Acceptance Criteria - Check that you have the latest site and engineering drawings BEFORE starting each task/set of tasks.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 1.2 - Determine lot size
label | Ref docs - Spec. 0161 Quality [Cl 7.3]
label | Acceptance Criteria - Lots to be broken up accordingly and outlined on a lot of map
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Lot map
checkpoint | 1.3 - Concrete Mix Design
label | Ref docs - Spec. 1121 Open Drains [Cl 3.1]
label | Acceptance Criteria - Submission of Mix Design and compliance certificates for concrete constituents
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Material conformance certificate
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Materials
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 3.0]
label | Acceptance Criteria - Submission of compliance certificates for joint fillers and sealants, proprietary products, wire mattresses, gabions, rock fill, and geotextile.
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Material conformance certificate
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Underlying Lot Conformance
label | Ref docs - Underlying Lot ITP
label | Acceptance Criteria - Underlying services and/or assets have been installed prior to commencing works over and/or above.
label | ○ Refer underlying lot ITP(s)
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 1.6 - Survey set out
label | Ref docs - Drawings
label | Acceptance Criteria - Has the set-out alignment been reviewed by the Superintendent?
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
section | 2.0 Open drain
checkpoint | 2.1 - Excavation
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.1]
label | Acceptance Criteria - Excavate to dimensions shown on drawings or where not shown to a depth of 300mm and minimum water way area of 0.2m2
label | ○ Cross section: V-shaped or trapezoidal unless otherwise shown on drawings
label | ○ Batter slope: Not steeper than 2:1 (H: V)
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 2.2 - Unsuitable material
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.1]
label | Acceptance Criteria - Notify the Superintendent of any unsuitable material and seek direction for removal. Dispose and replace material as directed.
label | WITNESS POINT
label | Notice: Progressive
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - W
label | SHL Key - W
checkpoint | 2.3 - Embankment
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.1]
label | Acceptance Criteria - Construct embankment in compacted layers of max. depth 150mm.
label | ○ Revegetate the embankment after completion if necessary
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 2.4 - Embankment compaction
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.1]
label | Acceptance Criteria - Compact to a density equal to the naturally occurring material or alternatively to 95% standard compaction
label | WITNESS POINT
label | Notice: Progressive
button | Acceptance | Yes,No,N/A
label | Key - W
label | UGL Key - W
label | SHL Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test report
checkpoint | 2.5 - Open Drain Construction
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.1]
label | Acceptance Criteria - Ensure free flow of water and minimum grade of 0.5%. Discharge into natural depressions, culverts or pits
label | ○ Compact any surface to be lined to 90% relative compaction
label | WITNESS POINT
label | Notice: Progressive
button | Acceptance | Yes,No,N/A
label | Key - W
label | UGL Key - W
label | SHL Key - W
checkpoint | 2.6 - Open Drain Lining
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.2]
label | Acceptance Criteria - Unless shown otherwise on the drawings use the following linings:
label | – Organic fibre mat and vegetation for grades 1-5%
label | – Concrete for grades <1% or >5%
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 2.7 - Proprietary Channel Linings
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.2]
label | Acceptance Criteria - Install as per manufacturer’s instructions
label | WITNESS POINT
button | Acceptance | Yes,No,N/A
label | Key - W
label | UGL Key - W
label | SHL Key - W
checkpoint | 2.8 - Concrete Lining Construction
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.2]
label | Acceptance Criteria - Minimum thickness of 100mm or as per design drawings. Free of humps or irregularities
button | Acceptance | Yes,No,N/A
label | Key - W
label | UGL Key - W
label | SHL Key - W
checkpoint | 2.9 - Concrete Lining Weepholes
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.2]
label | Acceptance Criteria - As per design drawings or at 2m spacing in non-horizontal elements
label | WITNESS POINT
button | Acceptance | Yes,No,N/A
label | Key - W
label | UGL Key - W
label | SHL Key - W
checkpoint | 2.10 - Concrete supply and placement
label | Ref docs - Spec. 0319 Minor Concrete Works [Cl 4.8, 4.9, 4.10, 4.11] Drawings
label | Acceptance Criteria - Check docket to ensure strength and slump is as per design requirements
label | ○ Ensure the temperature of freshly mixed concrete is maintained in between 5°C and 35°C. Ensure elapsed time between batching and discharge of the mix complies with the below table.
label | – – – – – – – – – – – – – – – –
label | Concrete temperature at time of discharge (C) ¦¦ Maximum elapsed time (hours)
label | – – – – – – – – – – – – – – – –
label | 10 - 24 ¦¦ 2.00
label | 24 - 27 ¦¦ 1.50
label | 27 - 30 ¦¦ 1.00
label | 30 - 32 ¦¦ 0.75
label | – – – – – – – – – – – – – – – –
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Delivery dockets
checkpoint | 2.11 - Concrete sampling
label | Ref docs - Spec. 0319 Minor Concrete Works [Cl 4.2]
label | Acceptance Criteria - The nominal rate of sampling shall be taken as:
label | (a) Compressive strength: See table below
label | – – – – – – – – – – – – – – – –
label | Number of batches for each type and grade of concrete per day ¦¦ Minimum number of samples
label | – – – – – – – – – – – – – – – –
label | 1 ¦¦ 1
label | 2-5 ¦¦ 2
label | 6-10 ¦¦ 3
label | 11-20 ¦¦ 4
label | each additional 10 ¦¦ 1 additional
label | – – – – – – – – – – – – – – – –
label | Slump: One per batch of concrete
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Concrete pour record
checkpoint | 2.12 - Concrete testing
label | Ref docs - Drawings
label | Acceptance Criteria - Average compressive strength at 28 days meets minimum design requirements
label | ○ Slump within tolerances specified in AS 1379
label | – – – – – – – – – – – – – – – –
label | Table 5.1 Permissible Tolerance on Slump
label | – – – – – – – – – – – – – – – –
label | Specified slump, mm ¦¦ Tolerance, mm
label | – – – – – – – – – – – – – – – –
label | <60 ¦¦ ±10
label | ≥60 ≤80 ¦¦ ±15
label | >80 ≤110 ¦¦ ±20
label | >110 ≤150 ¦¦ ±30
label | >150 ¦¦ ±40
label | – – – – – – – – – – – – – – – –
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
checkpoint | 2.13 - Joints - Contraction
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.3]
label | Acceptance Criteria - Contraction joints to conform to the following:
label | – Width: 5mm min.
label | – Depth: 20mm
label | – Intervals: every 3m
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 2.14 - Joints – Expansion
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.3]
label | Acceptance Criteria - Expansion joints to conform to the following:
label | – Width: 15mm
label | – Depth: Full thickness
label | – Intervals: Max interval 15m
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
section | 3.0 Rock Mattresses and Gabions
checkpoint | 3.1 - Foundation
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.5]
label | Acceptance Criteria - Shape and compact foundation material to 95% standard compaction
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
checkpoint | 3.2 - Geotextile
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.5]
label | Acceptance Criteria - Place geotextile between the foundation and any wire cages
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 3.3 - Assembly
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.5]
label | Acceptance Criteria - Assemble and lace the rock mattress or gabion cage as per manufacturer’s instructions.
label | ○ Secure the end of a new cage to completed works or with galvanised star pickets driven in to the ground.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 3.4 - Filling
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.5]
label | Acceptance Criteria - Fill boxes whilst under tension and only release tension once fully laced. Ensure cages are fully filled and uniform.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 3.5 - Completion
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.5]
label | Acceptance Criteria - Inspect rock filled mattresses or gabions upon completion
button | Acceptance | Yes,No,N/A
label | Key - W
label | UGL Key - W
label | SHL Key - W
section | 4.0 Conformance check
checkpoint | 4.1 - Survey Report
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.6]
label | Acceptance Criteria - Survey report verifying open drains have been constructed within tolerance:
label | ○ Finish levels of channel/gutter surface: within ± 10mm of design level.
label | ○ Surface deviation of kerb face and channel surface: ±5 mm from edge of a 3m straight edge, except at laybacks, grade changes or curves, or at gully pits requiring channel/gutter depression.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Survey report
checkpoint | 4.2 - Acceptance and closure of non-conforming items
label | Ref docs - Spec. 0161 Quality [Cl 3.8]
label | Acceptance Criteria - NCRs to be opened for non-conforming items and closed prior to closing construction lot.
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
holdpoint | AUTHORITY HOLDPOINT