## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CS-4044 - Roundabout Kerb Construction Record | [5 empty] | CS-4044 - Roundabout Kerb Construction Record
section | DETAILS
checkpoint-no-status | DETAILS
textbox | Project No:
textbox | Description of Pour:
textbox | Concrete Qty:
textbox | Kerb Type & Dimensions:
textbox | Concrete Grade: |  |  | Mpa
textbox | Weather conditions:
textbox | Dwg No/Rev:
section | Formwork Mould
checkpoint | 1. Cleaned and oiled
textbox | Initials:
date | Date:
checkpoint | 2. Correct profile/dimensions for Kerb Type
textbox | Initials:
date | Date:
section | Subgrade
checkpoint | 3. Ensure subgrade construction is complete and suitable for kerb
textbox | Initials:
date | Date:
checkpoint | 4. Cesspit protection in place
textbox | Initials:
date | Date:
section | Survey set out
checkpoint | 5. Check survey set out
textbox | Initials:
date | Date:
checkpoint | 6. Check subcontractors string lines for machine
textbox | Initials:
date | Date:
checkpoint | 7. Check crossfall from RAB collar to kerb lip using a tape and level every 5m before kerb is poured
textbox | Initials:
date | Date:
checkpoint | 8. Vertical levels correct to design +/-5mm vertical tolerance
textbox | Initials:
date | Date:
checkpoint | 9. Horizontal alignment correct to design. +/-30mm profile tolerance but the width between parallel kerbs +/-20mm
textbox | Initials:
date | Date:
checkpoint | 10. Crossings / kerb transitions set out
textbox | Initials:
date | Date:
checkpoint | 11. Engineer to mark kerb types at crossings and kerb transitions
textbox | Initials:
date | Date:
checkpoint | 12. Ensure channels fall towards catchpit locations
textbox | Initials:
date | Date:
section | Miscellaneous
checkpoint | 13. Construction joint roughened & clean
textbox | Initials:
date | Date:
checkpoint | 14. Correct mix ordered
textbox | Initials:
date | Date:
checkpoint | Pre-pour check – HOLD POINT
textbox | Site Engineer - Name:
date | Site Engineer - Date:
textbox | Design Engineer - Name:
date | Design Engineer - Date:
holdpoint | Sign:
section | Concrete Checks
checkpoint | 15. Correct mix delivered?
textbox | Initials:
date | Date:
checkpoint | 16. Correct slump (within tolerances)?
textbox | Initials:
date | Date:
checkpoint | 17. Concrete Supply Dockets collected?
textbox | Initials:
date | Date:
checkpoint | 18. Batching Plant Records received?
textbox | Initials:
date | Date:
checkpoint | 19. Kerb meters completed in m
textbox | Completed: |  |  | m
textbox | Initials:
date | Date:
section | DURING CONCRETE POUR INSPECTION
checkpoint | 20. Check height between base prep & kerb lip is consistent with #7 during kerb pouring
textbox | Initials:
date | Date:
checkpoint | 21. Ensure correct kerb type is being installed in the correct location(s)
textbox | Initials:
date | Date:
checkpoint | 22. Constantly check levels and line to ensure kerb is within design tolerances
textbox | Initials:
date | Date:
checkpoint | 23. Ensure protruded kerb has U4 finish
textbox | Initials:
date | Date:
checkpoint | 24. Ensure Expansion joints are installed
textbox | Initials:
date | Date:
section | CONCRETE INFILL ISLANDS
checkpoint | 25. ENSURE F3 FINISH AND THE CONCRETE LEVEL IS NO HIGHER THAN THE TOP OF THE KERB THAT FORMS THE MEDIAN/ISLAND
textbox | Initials:
date | Date:
section | TIE INS TO PRE-CAST ELEMENTS
checkpoint | 26. Aprons to be formed around pre-cast elements
textbox | Initials:
date | Date:
textbox | Pour Start Time:
textbox | Pour Complete Time:
textbox | Volume Placed:
section | PROTECTION
checkpoint | 27. Warning tape to be placed over kerb to prevent any damage
textbox | Initials:
date | Date:
checkpoint | 28. Backfilling to commence after 72 hours curing time
textbox | Initials:
date | Date:
section | POST CONCRETE INSPECTION
checkpoint | 29. Complete #7 again after pouring using actual kerb lip
textbox | Initials:
date | Date:
checkpoint | 30. Surface Finish and levels acceptable
textbox | Initials:
date | Date:
checkpoint | 31. Expansion joints satisfactorily completed
textbox | Initials:
date | Date:
checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
textbox | Site Engineer - Name:
date | Site Engineer - Date:
textbox | Design Engineer - Name:
date | Design Engineer - Date:
holdpoint | Sign: