## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CS-4048 - ITS Duct Installation | [5 empty] | CS-4048 - ITS Duct Installation
section | DETAILS
checkpoint-no-status | DETAILS
textbox | Project No.
textbox | Drawing No (& Rev No):
textbox | CH Start:
textbox | CH Finish:
section | Inspection
checkpoint | Pull Pit/ intermediate line points set out by surveyor
textbox | Initials:
date | Date:
label | Comments: Survey Receipt
checkpoint | All existing services exposed and identified before trenching
textbox | Initials:
date | Date:
checkpoint | Trench must be made safe before any person may enter the trench
textbox | Initials:
date | Date:
label | Comments: Trench depth > 1.5m must be shored or battered.
checkpoint | Base of trench is clean and inspected by engineer
textbox | Initials:
date | Date:
label | Comments: Base to be as flat as possible
checkpoint | Bedding material to be placed in layers 100mm thick
textbox | Initials:
date | Date:
label | Comments: Lab test 85% of MDD (CIV=8) or 95% of MDD under carriageway, Frequency 1/20m
checkpoint | Glue ducts together and lower carefully into trench.
textbox | Initials:
date | Date:
label | Comments: All open ends shall be taped up to prevent material entering
checkpoint | Guide wire installed in ducts before lowered into the trench
textbox | Initials:
date | Date:
checkpoint | As built survey every 20m
textbox | Initials:
date | Date:
label | Comments: Must pick up all changes in direction
checkpoint | Ensure 50mm gap between ducts sitting in the base of trench
textbox | Initials:
date | Date:
label | Comments: Check gaps before backfilling
checkpoint | Ensure backfill material is suitable and un-contaminated. Compacted and tested in 200mm lifts
textbox | Initials:
date | Date:
label | Comments: Footpath/Berm - Backfill with excavated material. CIV 8 required.
label | ○ Carriageway – Hardfill (GAP65) 95% of MDD
checkpoint | Warning Tape to be installed 200mm above the top ducts
textbox | Initials:
date | Date:
checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
textbox | Name:
textbox | Position:
date | Date:
holdpoint | Sign:
checkpoint-no-status | Trench Cross Section
textbox | H |  |  | (m)
textbox | L |  |  | (m)
textbox | Backfill: Warning Tape 200mm above top of duct
textbox | Backfill Material Type & Source
textbox | Bedding layer Material Type & Source