## General
SECTION 1 – GENERAL DETAILS
Project Name: | SP1 NZTA Ohakea Weigh Right | [5 empty] | Inspection Key |  | Responsibilities
Project Number: | 558020 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Waka Kotahi | [5 empty] | B | Report by Breach | CM | Construction Manager | Christopher Colman | CC
Contract Number: | 7456 | [5 empty] | C | Check | CR | Cust. Representative (WSP Engineers) | Mark Frampton & Alex Brown | MF / AB
Area/ Sub-System: | CVSC - Kerb& Channel and Footpath |  |  | Lot ID Number: |  |  | D | Dimension Inspection | IP | Inspection Personnel | N/A
[7 empty] | E | Examine | MC | Material Controller | N/A
ITP Number: | 558020-DOW-ITP-PC-0025 |  |  | Version: | 2 |  | H | Hold Point | OP | Operations Manager | N/A
ITP Description: | This ITP comprehensively encompasses the critical aspects related to incoming materials and processes associated with Kerb& Channel and Footpath . | [5 empty] | I | Inspection | PM | Project Manager | Krishna Marangat | KM
Discipline: | Earthwork, Concrete, Pavement | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | Gavin Hosnell | GH
Specification: | Technical Specification, Construction Drawings, NZTA T/1 | [5 empty] | O | Operation | SE | QA Manager | Steve Darby | SD
[7 empty] | R | Review | SP | Site Engineer | Ribin Jose | RJ
Drawings: | Waka Kotahi NZ Transport Agency SH3 & Pukenui Rd Intersection, Ohakea Weigh Right Programme. Civil - For Construction | [5 empty] | S | Subcontractor | SP | Supervisor | Gavin Hosnell (Civil) & Gareth Mclellan (Drainage) | GH / GM
[7 empty] | V | Visual Verification | ST | Superintendent | N/A
Prepared By: | Ribin Jose |  |  | Date: | 2023-11-16 |  | W | Witness Point | SV | Surveyor | Stefan Killian | SK
Quality Specified: | [8 empty] | WS | Welding Supervisor | N/A
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: | Ribin Jose |  |  | Signature: |  |  |  |  | Date: | 2024-04-08
Downer Approval |  | Name: | Krishna Marangat |  |  | Signature: |  |  |  |  | Date: | 2024-04-08
Customer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS
Item No. | Activity/ Task Description | Standard / Specification | Acceptance Criteria | Verifying Document | Frequency | Inspection Type | Inspection |  | Signature | Date
[7 empty] | Key | By
3.1 | General Preliminary
3.1.1 | Survey Setout | Downer | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Survey Records | Prior to Works | Document review | H | SV
3.1.2 | Service Location | Downer | Complete the on site check to identify, locate and protect all services. | Service location documents | Prior to Works | Document review | R | SE
3.1.3 | Internal Permits | Downer | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Internal Permits | Prior to Excavation | Document review | R | SE
3.1.4 | External Permits | Downer | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | External Permits | Prior to Excavation | Document review | R | SE
3.1.5 | Approved Construction Drawings | Downer | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | IFC Drawings | Prior to works start | Document review | R | SE
3.2 | Receiving Materials/Parts - Kerb & Channel/Nib
3.2.1 | Concrete mix design | Pre-construction | 20Mpa concrete as per design notes Drawing/Notes Sheet No :C 5110 | Mix design | Per type of mix | Document review | H | SE,CR
3.3 | Receiving Materials/Parts - Footpath
3.3.1 | Concrete mix design | Pre-construction | 20Mpa concrete as per Civil Technical Spec Section 5.3 | Mix design | Per type of mix | Document review | H | SE,CR
3.3.2 | Steel reinforcement | Pre-construction | As per Civil Technical Spec Section 5.3 | Material Certificate/Docket, Photos | Per Delivery/Batch | Visual, Document review | R | SE

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS
Item No. | Activity/ Task Description | Specification | Acceptance Criteria | Verifying Document | Frequency | Inspection Type | Inspection |  | Signature | Date
[7 empty] | Key | By
4.1 | Kerb & Channel/Nib
4.1.1 | Service Location | As per TDS | As per project specification locate on site 4 weeks prior to construction | ITP Sign Off/Photos | Prior to the works starting | Visual Inspection | V | SP
4.1.2 | Kerb/Nib Location | As per design | Surveyor to set-out location of kerb & channel for foundation preparation | ITP Sign off | Prior to constructing foundation | Survey Setout | D | SV
4.1.3 | Subgrade Testing | Construction Drawings Sheet No: C-5110 | Clegg testing at 10m intervals Subgrade CBR ≥ 7% | Clegg Hammer Result Sheet | 10m Intervals | Subgrade Compaction Testing | H | SE
4.1.4 | Foundation Preparation and Asbuilt Survey | Civil Technical Specification Section 4.3 | 300mm of AP65 or cement modified basecourse | Photos & Asbuilt Survey | 10m Cross Sections | Dimension Inspection | D | SV
4.1.5 | Foundation Testing | Civil Technical Specification Section 4.3 | Compacted to a minimum dry density of 2100kg/m3 In accordance with NZS 4407: NZ Heavy Compaction Results provided to Engineer to proceed | IANZ Accredited Laboratory Report | 10m Intervals | NDM Compaction Testing | H | SE
4.1.6 | Kerb/Nib Setout | As per design & Construction Drawings Sheet No: C-5110 | Surveyor to set-out stringline of kerb and channel. Dimensions as per standard detail in Construction Drawings Sheet No: C-5110 | ITP Sign Off | Straight: 10m Intervals Curve: 2m Intervals Survey every tangent | Survey Setout | D | SV
4.1.7 | Heavy Duty Vehicle Crossing | Construction Drawings Sheet No: C-5110 | Construct heavy duty vehicle crossing including reinforcing steel as per standard detail in Construction Drawings Sheet No: C-5110 | ITP Sign Off/Photos | Prior to pouring the concrete | Visual Inspection | V | SE
4.1.8 | Pre-Pour Inspection | As per TDS | Stringline Check, Concrete Pour Inspection Checksheet completed, and Written approval from Engineer to proceed | Checksheet: DN-QC-04 & Written Approval from Engineer | Prior to pouring the concrete | Pre-pour Inspection | H | SE
4.1.9 | Supply and Installation of Concrete | Civil Technical Specification Section 4.3 | 20MPa at 28 Days. Concrete strength & slump testing certificates obtained from concrete plant and submitted to Engineer. | Mix Design Certificate | 1 Test per batch/delivery 1 Sample @ 28days. | Concrete Strength & Slump Testing | R | SE
4.1.10 | Concrete Testing | Civil Technical Specification Section 4.4.1 | In accordance with NZS 3109 and NZS 3112 Part 2 Section 9 | IANZ Accredited Laboratory Report | Minimum of 1 every 50m centres | Core Compressive Strength Testing | R | SE
4.1.11 | Concrete Surface Finish | Civil Technical Specification Section 4.2 | In accordance with NZS 3114 | ITP Sign Off/Photos | Every Pour | Visual Inspection | V | SP
4.1.12 | Construction Joints | Civil Technical Specification Section 4.3 | Construction joints shall be installed in all kerbs and channels at 5m centres | ITP Sign Off/Photos | 1 every 5m centres | Visual Inspection | V | SP
4.1.13 | Concrete Docket Tally | As per TDS | All concrete dockets to be collected on a daily basis and provided to the Site Engineer | Dockets | Daily | Check | C | SE
4.1.14 | Asbuilt Survey | Civil Technical Specification Section 4.3 | No discrepancies of greater than 6mm in line or level in any 3m length | Asbuilt Drawings | Straight: 10m Intervals Curve: 2m Intervals Survey every tangent | Survey Asbuilt | R | SV
4.2 | Footpath
4.2.1 | Service Location | As per TDS | As per project specification locate on site 4 weeks prior to construction | ITP Sign Off/Photos | Prior to the works starting | Visual Inspection | V | SP
4.2.2 | Footpath Location | As per design & Construction Drawings Sheet No: C-5111 | Surveyor to set-out location of footpath for boxing and prepping. Dimensions as per standard detail in Construction Drawings Sheet No. C-5111: Height 100mm, Width 1.5m, Slope 2% | ITP Sign off | Prior to constructing foundation | Survey Setout | D | SV
4.2.3 | Accessible Ramp Location | Construction Drawings Sheet No: C-5111 | Surveyor to set-out location of footpath for boxing and prepping. Dimensions as per standard detail in Construction Drawings Sheet No. C-5111:Slope 10% | ITP Sign Off | Prior to constructing foundation | Survey Setout | D | SV
4.2.4 | Subgrade Testing | Construction Drawings Sheet No: C-5111 | Clegg testing at 10m intervals Subgrade CBR ≥ 6% | Clegg Hammer Result Sheet | 10m intervals | Subgrade Compaction Testing | H | SE
4.2.5 | Foundation Preparation and Asbuilt Survey | As per design & Construction Drawings Sheet No: C-5111 | Minimum 100mm of M/4 AP40 Basecourse | Photos & Asbuilt Survey | 10m Cross Sections | Dimension Inspection | D | SV
4.2.6 | Foundation Testing | Civil Technical Specification Section 5.5.1 | NDM testing to be carried out by IANZ accredited laboratory. Site plan to be provided to Engineer showing every test point. Minimum acceptable result shall be 95% of the suppliers specification as per approved JMF. | IANZ Accredited Laboratory Report | 10m intervals | NDM Compaction Testing | H | SE
4.2.7 | Foundation Testing | Civil Technical Specification Section 5.5.1 | NDM testing carried out by approved user within Downer (with approval from Waka Kotahi) Min. Acceptable Compaction ≥ 95% of Target MDD | IANZ Accredited Laboratory Report | 10m intervals with surveyed test point locations | NDM Compaction Testing | H | SE
4.2.8 | Foundation Testing | Civil Technical Specification Section 5.5.2, NZTA T/1 | Deflection testing shall be carried prior to kerb and channel being formed. Allowable deflections are as follows: - 95% of readings < 2.0mm - Maximum reading of 2.5mm | IANZ Accredited Laboratory Report | 10m intervals with surveyed test point locations | Benkelman Beaming | H | SE
4.2.9 | Formwork | Civil Technical Specification Section 5.3 | In accordance with NZS 3109. Finished level of formwork shall be within +-10mm of design. The line of the formwork shall be straight with the maximum deviation from a 3m straight edge along the face of 5mm with a cumulative total of all visible gaps of not more than 10mm | ITP Sign off | Prior to pouring the concrete | Survey Setout | D | SV
4.2.10 | Reinforcing Steel | Civil Technical Specification Section 5.2 | Reinforcing steel in accordance with AS/NZS 4671 Grade 500E Steel Welded wire fabric in accordance with AS/NZS 4671 Class E smooth | Dockets & Photos | Per batch/delivery | Check | C | SE
4.2.11 | Pre-Pour Inspection | As per TDS | Boxing Check, Concrete Pour Inspection Checksheet completed, and Written approval from Engineer to proceed | Checksheet: DN-QC-04 & Written Approval from Engineer | Prior to pouring the concrete | Pre-pour Inspection | H | SE
4.2.12 | Supply and Installation of Concrete | Civil Technical Specification Section 5.3 | 20MPa at 28 Days. Concrete strength & slump testing certificates obtained from concrete plant and submitted to Engineer. | Mix Design Certificate | 1 Test per batch/delivery 1 Sample @ 28days. | Concrete Strength & Slump Testing | R | SE
4.2.13 | Concrete Surface Finish | Civil Technical Specification Section 5.3 | U5 finish in accordance with NZS 3114 | ITP Sign Off/Photos | Every Pour | Visual Inspection | V | SP
4.2.14 | Saw Cutting | Civil Technical Specification Section 5.3 | Grooves to be between 1/4 and 1/3 of specified depth of slab, and any convenient width greater than 3mm. Max spacing of saw cuts shall be 3m. | ITP Sign Off/Photos | No more than 3m Intervals | Visual Inspection | V | SP
4.2.15 | Concrete Docket Tally | As per TDS | All concrete dockets to be collected on a daily basis and provided to the Site Engineer | Dockets | Daily | Check | C | SE
4.2.16 | Asbuilt Survey | Civil Technical Specification Section 5.1 | In accordance with requirements of the TA Minimum cossfall of 1% | Asbuilt Drawings | Appropriate intervals to represent asbuilt footpath | Survey Asbuilt | R | SV

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type | Inspection |  | Inspection Point/Signature & Date
[7 empty] | Key | By | Downer Signature | Date | Customer Requirements Verification Records/Location
5.1 | Construction Record Compilation | Upon completion of works | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Closed-out NCR/Defects | Post construction | Review | R | SE
5.2 | As-built Survey | Upon completion of works | Ensure all items have been surveyed and records are assembled for asbuilting | As built survey record completed | Post construction | Review | R | SV
5.3 | Red-line As-built Drawings | Upon completion of works | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar | Signed As-built Drawings | Post construction | Review | R | SE,SV
5.4 | Defect, Snag and Punch List | Upon completion of works | Update the project Defect, Snag and Punch List Register | Register | Post construction | Review | R | PE
5.5 | All QA documentation collated & signed-off | Upon completion of works | All signed and closed out | Signed off Documents | Post construction | Review | R | QM