## General
SECTION 1 – GENERAL DETAILS
Project Name: | SP1 NZTA Ohakea Weigh Right | [5 empty] | Inspection Key |  | Responsibilities
Project Number: | 558020 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Waka Kotahi | [5 empty] | B | Report by Breach | CM | Construction Manager | Christopher Colman | CC
Contract Number: | 7456 | [5 empty] | C | Check | CR | Cust. Representative (WSP Engineers) | Mark Frampton & Alex Brown | MF / AB
Area/ Sub-System: | Variable Messaging Sign (VMS) Site |  |  | Lot ID Number: |  |  | D | Dimension Inspection | IP | Inspection Personnel | N/A
[7 empty] | E | Examine | MC | Material Controller | N/A
ITP Number: | DG-OWR-VMS-ITP-001 |  |  | Version: | 2 |  | H | Hold Point | OP | Operations Manager | N/A
ITP Description: | Cover the foundation work, shoulder widening, and guardrail installation at the VIM site | [5 empty] | I | Inspection | PM | Project Manager | Krishna Marangat | KM
Discipline: | Earthwork, Concrete, Pavement, Guardrail Installation | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | Gavin Hosnell | GH
Specification: | NZTA B/2, NZTA M/1, NZTA M/3, NZTA M/4, NZTA M/6, , NZTA M/23, NZTA Q/5 | [5 empty] | O | Operation | QM | QA Manager | Steve Darby | SD
[7 empty] | R | Review | SE | Site Engineer | Ribin Jose | RJ
Drawings: | Waka Kotahi NZ Transport Agency SH3 & Pukenui Rd Intersection, Ohakea Weigh Right Programme. Civil - For Construction | [5 empty] | S | Subcontractor | SP | Supervisor | Gavin Hosnell (Civil) & Gareth Mclellan (Drainage) | GH / GM
[7 empty] | V | Visual Verification | ST | Superintendent | N/A
Prepared By: | Ribin Jose |  |  | Date: | 2023-11-15 |  | W | Witness Point | SV | Surveyor | Stefan Killian | SK
Quality Specified: | [8 empty] | WS | Welding Supervisor | N/A
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: | Ribin Jose |  |  | Signature: |  |  |  |  | Date: | 2024-04-08
Downer Approval |  | Name: | Krishna Marangat |  |  | Signature: |  |  |  |  | Date: | 2024-04-08
Customer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS
Item No. | Activity/ Task Description | Standard / Specification | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Signature | Date
[7 empty] | Key | By (Role Key)
3.1 | General Preliminary
3.1.1 | Survey Setout | Downer | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Survey Records | Prior to Works | Document review | H | SV
3.1.2 | Service Location | Downer | Complete the on site check to identify, locate and protect all services. | Service location documents | Prior to Works | Document review | R | SE
3.1.3 | Internal Permits | Downer | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Internal Permits | Prior to Excavation | Document review | R | SE
3.1.4 | External Permits | Downer | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | External Permits | Prior to Excavation | Document review | R | SE
3.1.5 | Approved Construction Drawings | Downer | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | IFC Drawings | Prior to works start | Document review | R | SE
3.2 | Receiving Materials/Parts - VMS Foundation with Plinth and cabinet pad
3.2.1 | Concrete mix design | 30Mpa Structural Concrete | Concrete Mix design for each mix comply with the requirements of the Project Specification | Concrete supplier mix designs | Submitted to Client Engineer for approval before construction | Document review | H | CR
3.2.2 | Reinforcement | As per Design Specification | Reinforcing bars and mesh shall comply with AS/NZS4671:2001. | Mill Certs | Each Lot | Document review | R | SE
3.3 | Receiving Materials/Parts - Shoulder Widening and Sealing
3.3.1 | AP65 - Source Property Tests and Sampling | TNZ M/3 Notes : 1986 TNZ M/4: 2006 NZS 4407 : 1991 NZS 4402 : 1986 | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio. | IANZ Lab Reports | 10,000m3 | Document review | H | CR
3.3.2 | AP65 - Production Property Tests and Sampling | TNZ M/3 Notes : 1986 TNZ M/4: 2006 NZS 4407 : 1991 | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Permeability, and Particle Size Distribution. | IANZ Lab Reports | 3 per source initially, then 1/1000m³ | Document review | H | CR
3.3.3 | AP65 - Testing for Layer Compaction - MDD | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). | IANZ Lab Reports | 5,000m2 | Document review | H | CR
3.3.4 | AP40 - Source Property Tests and Sampling | TNZ M/4: 2006 - 3 NZS 4407 : 1991 NZS 4402 : 1986 | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio. | IANZ Lab Reports | 10,000m4 | Document review | H | CR
3.3.5 | AP40 - Production Property Tests and Sampling | TNZ M/4: 2006 - 4 NZS 4407 : 1991 | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per M/4 Figure 1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control. | IANZ Lab Reports | 3 per source initially, then 1/1000m³ | Document review | H | CR
3.3.6 | AP40 - Testing for Layer Compaction - MDD | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). | IANZ Lab Reports | 5,000m2 | Document review | H | CR
3.3.7 | Sealing Chip - Source Property Tests and Sampling | TNZ M/6: 2019 - 4 | The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV | IANZ Lab Reports | Before Supply and Every 10,000m3 Thereafter | Document review | H | CR
3.3.8 | Sealing Chip - Production Property Test Sampling | TNZ M/6: 2019 - 5 | The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6 | IANZ Lab Reports | Every 500m3 | Document review | H | CR
3.3.9 | Bitumen - Quality Testing | NZTA M01: 2022 - 6 | The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01. | IANZ Lab Reports | One test per grade supplied | Document review | H | CR
3.3.10 | Bitumen - Supply Testing | NZTA Q05: 2022 - 6.2 | The binder shall have benchmark parameter testing completed complying with the requirements of NZTA Q05. | IANZ Lab Reports | Every 200 tonnes supplied. | Document review | H | CR
3.4 | Receiving Materials/Parts - Safety Barrier
3.4.1 | Barrier Mill Certs | NZTA M23 AS/NZS 3845 | Compliance documentation | Mill Certs | Prior to commencement of works | Document review | R | SE
3.4.2 | Concrete mix design | As per Design Specification | Concrete Mix design for each mix comply with the requirements of the Project Specification | Concrete supplier mix designs | Submitted to Client Engineer for approval before construction | Document review | H | CR

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS
Item No. | Activity/ Task Description | Spectification | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Signature | Date
[7 empty] | Key | By (Role Key)
4.1 | VMS Foundation with Plinth and cabinet pad - Construction
4.1.1 | Construction Location | Design Location | Proposed location of construction to be staked out to the engineer for review prior to construction | Approval letter, Photos | Prior to each foundation build | Visual Inspection | V | CR
4.1.2 | Ground Compaction Test | Downer Standard | Compaction shall achieve a minimum Clegg Impact Value (CIV) of 20 on the first layer and 25 on subsequent layers | Test reults, Location of Test | For each Foundation | Check | C | SE
4.1.3 | Reinforcement and Hold Down Bolt Inspection | As per Design Specification | Handling, Fabrication, Placing and Fixing shall be inspected prior to pouring concrete. | Pre pour, Photos | Prior to each foundation pour | Visual Inspection, Dimensional Inspection | H | CR,SE
4.1.4 | Electrical & Comms Ducts Placement | As per Design Specification | Compliant with the construction drawings | Pre pour, Photos | Prior to each foundation pour | Visual Inspection | H | CR,SE
4.1.5 | Pre-Pour Inspection | Downer Standard | Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area. | Pre pour, Photos | Prior to each foundation pour | Visual Inspection | H | CR,SE
4.1.6 | Delivery Dockets | Downer Standard | The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size. | Dockets | Each Pour | Review | R | SE
4.1.7 | Compression Testing | As per Design Specification | One specimen from each pour shall be tested at 28 days. | Test Results | one test per 50m³/per pour | Review | R | SE
4.1.8 | Post Pour Inspection | Downer Standard | Following the concrete pour, the concrete shall be inspected for Size, Shape, Features, inserts, reliefs, and Finish against the drawings. | Post Pour, Photos | Each Pour | Visual Inspection | R | SE
4.1.9 | Defective Concrete Finishes | Downer Standard | Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer. | NCR | Prior to minor repair | Review | A | SE
4.2 | Shoulder Widening and Sealing - Construction
4.2.1 | Material Placement | Downer Standard | The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored thoughout | Survey / Level Checks | Continuous monitoring. | Check | C | SV,PS
4.2.2 | Pavement Shoulder Widening | Design Specification, Appendix E, Section 2.1.4 | Pavement sholder widening treatment will be confirmed with Engineer on site | Approval letter, Photos | Prior to construction | Visual Inspection | V | CR
4.2.3 | Sub-basecourse Pavement Layer Compaction (NDM) | TNZ B/02: 2005 - 7.6 | Mean Value ≥ 95 % of MDD Minimum Value ≥ 92 of MDD | NDM Report | 1/10m | Check | H | SE
4.2.4 | Sub-basecourse Layer thickness | TNZ B/02: 2005 - 5.1 | The Sub-basecourse shall be monitured for Layer thickness. –25 mm +5 mm | Survey / Level Checks | 1/20m Full width | Dimensional Inspection | D | SV or SE
4.2.5 | Basecourse Pavement Layer Compaction | TNZ B/02: 2005 - 7.6 | Mean Value ≥ 98 % of MDD Minimum Value ≥ 95 of MDD | NDM Report | 1/10m | Check | H | SE
4.2.6 | Basecourse Layer thickness. | TNZ B/02: 2005 - 5.1 | The Sub-basecourse shall be monitured for Layer thickness. –5 mm +15 mm | Survey / Level Checks | 1/20m Full width | Dimensional Inspection | D | SV or SE
4.2.7 | Surface Shape | TNZ B/02: 2005 - 7.7 | The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual.. | Survey / Straight edge Report | 1/20m Full width prior to sealing | Dimensional Inspection | D | SV
4.2.8 | Surface Finish post sweeping | TNZ B/02: 2005 - 7.8 | The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept. | Photos | Prior to sealing | Visual Inspection | V | SE
4.2.9 | Preselling Requirements | TNZ B/02: 2005 - 12 | The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 80%. | NDM Report | 1/10m | Check | C | SE
4.2.10 | PreSeal inspection | TNZ P3 TNZ B02 | The road shall be reasonably dry before the binder is applied, and no spraying with asphaltic binder shall be carried out when the air temperature measured within the confines of the sealing course is below 10oC in the shade. The Engineer shall be given the opportunity to inspect the site. | Hold point Release, ITP Sign off | Prior to sealing | Check | H | SE
4.2.11 | Spray Temperature | TNZ P3 | The emulsified asphalt may be sprayed at the temperature at which it is received from the manufacturing plant except that no emulsified asphalt shall be sprayed at a temperature in excess of 90oC or below 20oC. | Sealing statement | Prior to sealing | Check | I | SE
4.2.12 | Chip Application | TNZ P3 | All binder sprayed shall be covered with chips across the full sprayed width, apart from necessary longitudinal laps, within five minutes of spraying. | Sealing statement | For every spray run | Check | I | SE
4.2.13 | Post Seal Inspections | TNZ P3 | The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed. | Engineers Acceptance | Prior to TM Removal and After Final Sweeping | Visual Inspection | H | SE,CR
4.2.14 | Chipseal Repairs | TNZ P3 | The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used. | Approved Repair Methodology | Prior to Repairs | Review | A | SE
4.3 | Guardrail - Installation
4.3.1 | Guard rails - Location | Design Specification, Appendix E, Section 2.1.3 | The Contractor will set out the guardrail location with the Engineer on site. | Approval letter, Photos | Prior to construction | Visual Inspection | V | CR
4.3.2 | Guard rails - Installation & Checklist | As per design specification | To complete the check list along with the guard rail installer after the construction | Check Sheet DN-QC-06 Photos | For each site | Visual Inspection | V | SE

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type | Inspection |  | Inspection Point/Signature & Date
[7 empty] | Key | By | Downer Signature | Date | Customer Requirements Verification Records/Location
5.1 | Construction Record Compilation | Upon completion of works | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Closed-out NCR/Defects | Post construction | Review | R | SE
5.2 | As-built Survey | Upon completion of works | Ensure all items have been surveyed and records are assembled for asbuilting | As built survey record completed | Post construction | Review | R | SV
5.3 | Red-line As-built Drawings | Upon completion of works | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar | Signed As-built Drawings | Post construction | Review | R | SE,SV
5.4 | Defect, Snag and Punch List | Upon completion of works | Update the project Defect, Snag and Punch List Register | Register | Post construction | Review | R | PE
5.5 | All QA documentation collated & signed-off | Upon completion of works | All signed and closed out | Signed off Documents | Post construction | Review | R | QM