## General
SECTION 1 – GENERAL DETAILS
Project Name: | SP1 NZTA Ohakea Weigh Right | [5 empty] | Inspection Key |  | Responsibilities
Project Number: | 558020 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Waka Kotahi | [5 empty] | B | Report by Breach | CM | Construction Manager | Christopher Colman | CC
Contract Number: | 7456 | [5 empty] | C | Check | CR | Cust. Representative (WSP Engineers) | Mark Frampton & Alex Brown | MF / AB
Area/ Sub-System: | Signs and Street Furniture |  |  | Lot ID Number: |  |  | D | Dimension Inspection | IP | Inspection Personnel | N/A
[7 empty] | E | Examine | MC | Material Controller | N/A
ITP Number: | 558020-DOW-ITP-PC-0030 |  |  | Version: | 1 |  | H | Hold Point | OP | Operations Manager | N/A
ITP Description: | This ITP comprehensively encompasses the critical aspects related to incoming materials and processes associated with earthwork. | [5 empty] | I | Inspection | PM | Project Manager | Krishna Marangat | KM
Discipline: | Earthwork | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | Gavin Hosnell | GH
Specification: | NZTA P/30, IFC Drawings | [5 empty] | O | Operation | QM | QA Manager | Steve Darby | SD
[7 empty] | R | Review | SE | Site Engineer | Ribin Jose | RJ
Drawings: | Waka Kotahi NZ Transport Agency SH3 & Pukenui Rd Intersection, Ohakea Weigh Right Programme. Civil - For Construction | [5 empty] | S | Subcontractor | SP | Supervisor | Gavin Hosnell (Civil) & Gareth Mclellan (Drainage) | GH / GM
[7 empty] | V | Visual Verification | ST | Superintendent | N/A
Prepared By: | Steve Darby |  |  | Date: | 2024-03-14 |  | W | Witness Point | SV | Surveyor | Stefan Killian | SK
Quality Specified: | [8 empty] | WS | Welding Supervisor | N/A
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: | Ribin Jose |  |  | Signature: |  |  |  |  | Date: | 2024-04-05
Downer Approval |  | Name: | Krishna Marangat |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS
Item No. | Activity/ Task Description | Standards/Specification | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Signature | Date
[7 empty] | Key | By (Role Key)
3.1 | General Preliminary
3.1.1 | Survey Setout | Downer Standard | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Survey Records | Prior to Works | Document review | H | SV
3.1.2 | Service Location | Downer Standard | Complete the on site check to identify, locate and protect all services. | Service location documents | Prior to Works | Document review | R | SE
3.1.3 | Internal Permits | Downer Standard | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Internal Permits | Prior to Excavation | Document review | R | SE
3.1.4 | External Permits | Downer Standard | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | External Permits | Prior to Excavation | Document review | R | SE
3.1.5 | ESCP | As per contracts | Prior to starting works, Ensure that ESCP plan an approved ESCP by counsil is in place and valid | Approved ESCP plan | Prior to Works | Document review | R | SE
3.1.6 | Approved Construction Drawings | Downer Standard | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | IFC Drawings | Prior to works start | Document review | R | SE
3.2 | Signage - Incoming Materials
3.2.1 | General | NZTA manuals, NZTA P/30 | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | IFC Drawings, Sheet No. C-2510 | All | Document review | R | SE

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS
Item No. | Activity/ Task Description | Specification | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Signature | Date
[7 empty] | Key | By (Role Key)
4.1 | Signage and Marking - General Notes
4.1.1 | General | IFC Drawings, Sheet No. C-0300 | All signs and markings are to comply with MOTSAM | Photos | All | Visual | V | SE
4.1.2 |  | IFC Drawings, Sheet No. C-0300 | Sign positions are to be agreed with the Engineer on site | Photos | All | Visual | V | SE
4.1.3 |  | IFC Drawings, Sheet No. C-0300 | All redundant road markings to be removed by water blasting. Residue from the water blasting is tobe removed by the contractor. | Photos | All | Visual | V | SE
4.1.4 |  | IFC Drawings, Sheet No. C-0300 | Unless otherwise indicated, all signs and bollards are to have a minimum of 500mm clearance from the kerb face to the edge of the sign/bollard. | Photos | All | Visual | V | SE
4.1.5 |  | IFC Drawings, Sheet No. C-0300 | All road markings are to be a minimum of 300mm from the kerb | Photos | All | Visual | V | SE
4.1.6 |  | IFC Drawings, Sheet No. C-0300 | All existing remaining road markings disturbed by the works are to be reinstated. | Photos | All | Visual | V | SE
4.1.7 |  | IFC Drawings, Sheet No. C-0300 | All existing pavement markings to be reinstated unless approved by principles representative. | Photos | All | Visual | V | SE
4.1.8 |  | IFC Drawings, Sheet No. C-0300 | New line markings to join neatly to existing line marking at limit of works. | Photos | All | Visual | V | SE
4.2 | Signage and Marking - Southbound Approach WIM Site
4.2.1 | Signs and Markings | NZTA Manuals, NZTA P/30, IFC Drawings, Sheet No. C-2510 | Manual of Traffic Signs and Markings. - Part 1: Signs - Part 2: Markings | Photos | All | Dimension Inspection Visual | D,V | SV, SE
4.2.2 | Reflectorised Markings | NZTA Manuals, NZTA P/30, IFC Drawings, Sheet No. C-2510 | Refer to IFC drawings | Photos | All | Dimension Inspection Visual | D,V | SV, SE
4.2.3 | Raised Pavement Markers | MOTSAM, IFC Drawings, Sheet No. C-2510 | Refer to IFC drawings | Photos | All | Dimension Inspection Visual | D,V | SV, SE
4.2.4 | No Cycling Signage | NZTA Manuals, NZTA P/30, IFC Drawings, Sheet No. C-2510 | Relocate existing RG24 no bicycles symbol sign | Photos | All | Dimension Inspection Visual | D,V | SV, SE
4.2.5 | Sign Poles | NZTA Manual of Traffic Signs, Project Specification, Section 5.4 | All poles must be fluted alluminium | Photos | All | Visual | V | SE
4.3 | Signage and Marking - Southbound Approach VMS Site
4.3.1 | Signs and Markings | NZTA Manuals, NZTA P/30, IFC Drawings, Sheet No. C-2510 | Manual of Traffic Signs and Markings. - Part 1: Signs - Part 2: Markings | Photos | All | Dimension Inspection Visual | D,V | SV, SE
4.3.2 | Reflectorised Markings | NZTA Manuals, NZTA P/30, IFC Drawings, Sheet No. C-2510 | Refer to IFC drawings | Photos | All | Dimension Inspection Visual | D,V | SV, SE
4.3.3 | Raised Pavement Markers | MOTSAM, IFC Drawings, Sheet No. C-2510 | Refer to IFC drawings | Photos | All | Dimension Inspection Visual | D,V | SV, SE
4.3.4 | Sign Poles | NZTA Manual of Traffic Signs, Project Specification, Section 5.4 | All poles must be fluted alluminium | Photos | All | Visual | V | SE
4.4 | Signage and Marking - Northbound Approach WIM Site
4.4.1 | Signs and Markings | NZTA Manuals, NZTA P/30, IFC Drawings, Sheet No. C-2510 | Manual of Traffic Signs and Markings. - Part 1: Signs - Part 2: Markings | Photos | All | Dimension Inspection Visual | D,V | SV, SE
4.4.2 | Reflectorised Markings | NZTA Manuals, NZTA P/30, IFC Drawings, Sheet No. C-2510 | Refer to IFC drawings | Photos | All | Dimension Inspection Visual | D,V | SV, SE
4.4.3 | Raised Pavement Markers | MOTSAM, IFC Drawings, Sheet No. C-2510 | Refer to IFC drawings | Photos | All | Dimension Inspection Visual | D,V | SV, SE
4.4.4 | Sign Poles | NZTA Manual of Traffic Signs, Project Specification, Section 5.4 | All poles must be fluted alluminium | Photos | All | Visual | V | SE
4.5 | Signage and Marking - Static Signage
4.5.1 | During Roundabout Construction | IFC Drawings, Sheet No. C-7000 | Refer to IFC drawing to reference the sign and marking details during the construction of the roundabout. | Photos | All | Dimension Inspection Visual | D,V | SV, SE
4.5.2 | After Roundabout Construction | IFC Drawings, Sheet No. C-7001 | Refer to IFC drawing to reference the sign and marking details after the construction of the roundabout. | Photos | All | Dimension Inspection Visual | D,V | SV, SE
4.6 | Signage and Marking - Commercial Vehicle Safety Centre (CVSC)
4.6.1 | CVSC - Detailed Plan | IFC Drawings, Sheet No. C-7011 | Refer to IFC drawing to reference the sign and marking details for the CVSC facility. All dimensions and requirements are listed within the Legend of the drawing. | Photos | All | Visual | V | SE
4.6.2 |  | IFC Drawings, Sheet No. C-7012 | Refer to IFC drawing to reference the sign and marking details for the CVSC facility. All dimensions and requirements are listed within the Legend of the drawing. | Photos | All | Dimension Inspection Visual | D,V | SV, SE
4.6.3 | Sign Details and Dimensions | IFC Drawings, Sheet No. C-7100 & C-7101 | - Legend is series E 125 unless stated otherwise - Contractor to organise for shop drawings of traffic signs to be in accordance with the Traffic Control Devices manual and manual of Traffic Signs and Road Markings - Traffic sign posts to be in accordance with RSMA - All measurements are in millimeters unless otherwise stated | Photos | All | Dimension Inspection Visual | D,V | SV, SE

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type | Inspection |  | Inspection Point/Signature & Date
[7 empty] | Key | By | Downer Signature | Date | Customer Requirements Verification Records/Location
5.1 | Construction Record Compilation | Upon completion of works | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Closed-out NCR/Defects | Post construction | Review | R | SE
5.2 | As-built Survey | Upon completion of works | Ensure all items have been surveyed and records are assembled for asbuilting | As built survey record completed | Post construction | Review | R | SV
5.3 | Red-line As-built Drawings | Upon completion of works | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar | Signed As-built Drawings | Post construction | Review | R | SE,SV
5.4 | Defect, Snag and Punch List | Upon completion of works | Update the project Defect, Snag and Punch List Register | Register | Post construction | Review | R | PE
5.5 | All QA documentation collated & signed-off | Upon completion of works | All signed and closed out | Signed off Documents | Post construction | Review | R | QM