## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 558020-DOW-ITP-PC-0025 (Kerb and Channel Footpath for CVSC) | itp |  |  |  |  | 558020-DOW-ITP-PC-0025 (Kerb and Channel Footpath for CVSC)
section | 3.1 General Preliminary
checkpoint | 3.1.1 - Survey Setout
label | Standard/Specification - Downer
label | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - SV
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Service Location
label | Standard/Specification - Downer
label | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
label | Verifying Document - Service location documents
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.3 - Internal Permits
label | Standard/Specification - Downer
label | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.4 - External Permits
label | Standard/Specification - Downer
label | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.5 - Approved Construction Drawings
label | Standard/Specification - Downer
label | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
section | 3.2 Receiving Materials/Parts - Kerb & Channel/Nib
checkpoint | 3.2.1 - Concrete mix design
label | Standard/Specification - Pre-construction
label | Acceptance Criteria - 20Mpa concrete as per design notes, Drawing/Notes Sheet No :C 5110
label | Verifying Document - Mix design
label | Frequency - Per type of mix
label | Inspection Type - Document review
label | Inspection: Key - H
label | Inspection: By - SE, CR
holdpoint | AUTHORITY HOLDPOINT
section | 3.3 Receiving Materials/Parts - Footpath
checkpoint | 3.3.1 - Concrete mix design
label | Standard/Specification - Pre-construction
label | Acceptance Criteria - 20Mpa concrete as per Civil Technical Spec Section 5.3
label | Verifying Document - Mix design
label | Frequency - Per type of mix
label | Inspection Type - Document review
label | Inspection: Key - H
label | Inspection: By - SE, CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.2 - Steel reinforcement
label | Standard/Specification - Pre-construction
label | Acceptance Criteria - As per Civil Technical Spec Section 5.3
label | Verifying Document - Material Certificate/Docket, Photos
label | Frequency - Per Delivery/Batch
label | Inspection Type - Visual, Document review
label | Inspection: Key - R
label | Inspection: By - SE
section | 4.1 Kerb & Channel/Nib
checkpoint | 4.1.1 - Service Location
label | Standard/Specification - As per TDS
label | Acceptance Criteria - As per project specification locate on site 4 weeks prior to construction
label | Verifying Document - ITP Sign Off/Photos
label | Frequency - Prior to the works starting
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SP
checkpoint | 4.1.2 - Kerb/Nib Location
label | Standard/Specification - As per design
label | Acceptance Criteria - Surveyor to set-out location of kerb & channel for foundation preparation
label | Verifying Document - ITP Sign off
label | Frequency - Prior to constructing foundation
label | Inspection Type (Visual, other) - Survey Setout
label | Inspection: Key - D
label | Inspection: By - SV
checkpoint | 4.1.3 - Subgrade Testing
label | Standard/Specification - Construction Drawings Sheet No: C-5110
label | Acceptance Criteria - Clegg testing at 10m intervals
label | ○ Subgrade CBR ≥ 7%
label | Verifying Document - Clegg Hammer Result Sheet
label | Frequency - 10m Intervals
label | Inspection Type (Visual, other) - Subgrade Compaction Testing
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.4 - Foundation Preparation and Asbuilt Survey
label | Standard/Specification - Civil Technical Specification Section 4.3
label | Acceptance Criteria - 300mm of AP65 or cement modified basecourse
label | Verifying Document - Photos & Asbuilt Survey
label | Frequency - 10m Cross Sections
label | Inspection Type (Visual, other) - Dimension Inspection
label | Inspection: Key - D
label | Inspection: By - SV
checkpoint | 4.1.5 - Foundation Testing
label | Standard/Specification - Civil Technical Specification Section 4.3
label | Acceptance Criteria - Compacted to a minimum dry density of 2100kg/m3
label | ○ In accordance with NZS 4407: NZ Heavy Compaction
label | ○ Results provided to Engineer to proceed
label | Verifying Document - IANZ Accredited Laboratory Report
label | Frequency - 10m Intervals
label | Inspection Type (Visual, other) - NDM Compaction Testing
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.6 - Kerb/Nib Setout
label | Standard/Specification - As per design & Construction Drawings Sheet No: C-5110
label | Acceptance Criteria - Surveyor to set-out stringline of kerb and channel.
label | ○ Dimensions as per standard detail in Construction Drawings Sheet No: C-5110
label | Verifying Document - ITP Sign Off
label | Frequency - Straight: 10m Intervals
label | ○ Curve: 2m Intervals
label | ○ Survey every tangent
label | Inspection Type (Visual, other) - Survey Setout
label | Inspection: Key - D
label | Inspection: By - SV
checkpoint | 4.1.7 - Heavy Duty Vehicle Crossing
label | Standard/Specification - Construction Drawings Sheet No: C-5110
label | Acceptance Criteria - Construct heavy duty vehicle crossing including reinforcing steel as per standard detail in Construction Drawings Sheet No: C-5110
label | Verifying Document - ITP Sign Off/Photos
label | Frequency - Prior to pouring the concrete
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.1.8 - Pre-Pour Inspection
label | Standard/Specification - As per TDS
label | Acceptance Criteria - Stringline Check, Concrete Pour Inspection Checksheet completed, and Written approval from Engineer to proceed
label | Verifying Document - Checksheet: DN-QC-04 & Written Approval from Engineer
label | Frequency - Prior to pouring the concrete
label | Inspection Type (Visual, other) - Pre-pour Inspection
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.9 - Supply and Installation of Concrete
label | Standard/Specification - Civil Technical Specification Section 4.3
label | Acceptance Criteria - 20MPa at 28 Days. Concrete strength & slump testing certificates obtained from concrete plant and submitted to Engineer.
label | Verifying Document - Mix Design Certificate
label | Frequency - 1 Test per batch/delivery, 1 Sample @ 28days.
label | Inspection Type (Visual, other) - Concrete Strength & Slump Testing
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 4.1.10 - Concrete Testing
label | Standard/Specification - Civil Technical Specification Section 4.4.1
label | Acceptance Criteria - In accordance with NZS 3109 and NZS 3112 Part 2 Section 9
label | Verifying Document - IANZ Accredited Laboratory Report
label | Frequency - Minimum of 1 every 50m centres
label | Inspection Type (Visual, other) - Core Compressive Strength Testing
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 4.1.11 - Concrete Surface Finish
label | Standard/Specification - Civil Technical Specification Section 4.2
label | Acceptance Criteria - In accordance with NZS 3114
label | Verifying Document - ITP Sign Off/Photos
label | Frequency - Every Pour
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SP
checkpoint | 4.1.12 - Construction Joints
label | Standard/Specification - Civil Technical Specification Section 4.3
label | Acceptance Criteria - Construction joints shall be installed in all kerbs and channels at 5m centres
label | Verifying Document - ITP Sign Off/Photos
label | Frequency - 1 every 5m centres
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SP
checkpoint | 4.1.13 - Concrete Docket Tally
label | Standard/Specification - As per TDS
label | Acceptance Criteria - All concrete dockets to be collected on a daily basis and provided to the Site Engineer
label | Verifying Document - Dockets
label | Frequency - Daily
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.1.14 - Asbuilt Survey
label | Standard/Specification - Civil Technical Specification Section 4.3
label | Acceptance Criteria - No discrepancies of greater than 6mm in line or level in any 3m length
label | Verifying Document - Asbuilt Drawings
label | Frequency - Straight: 10m Intervals
label | ○ Curve: 2m Intervals
label | ○ Survey every tangent
label | Inspection Type (Visual, other) - Survey Asbuilt
label | Inspection: Key - R
label | Inspection: By - SV
section | 4.2 Footpath
checkpoint | 4.2.1 - Service Location
label | Standard/Specification - As per TDS
label | Acceptance Criteria - As per project specification locate on site 4 weeks prior to construction
label | Verifying Document - ITP Sign Off/Photos
label | Frequency - Prior to the works starting
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SP
checkpoint | 4.2.2 - Footpath Location
label | Standard/Specification - As per design & Construction Drawings Sheet No: C-5111
label | Acceptance Criteria - Surveyor to set-out location of footpath for boxing and prepping.
label | ○ Dimensions as per standard detail in Construction Drawings Sheet No. C-5111: Height 100mm, Width 1.5m, Slope 2%
label | Verifying Document - ITP Sign off
label | Frequency - Prior to constructing foundation
label | Inspection Type (Visual, other) - Survey Setout
label | Inspection: Key - D
label | Inspection: By - SV
checkpoint | 4.2.3 - Accessible Ramp Location
label | Standard/Specification - Construction Drawings Sheet No: C-5111
label | Acceptance Criteria - Surveyor to set-out location of footpath for boxing and prepping.
label | ○ Dimensions as per standard detail in Construction Drawings Sheet No. C-5111:Slope 10%
label | Verifying Document - ITP Sign Off
label | Frequency - Prior to constructing foundation
label | Inspection Type (Visual, other) - Survey Setout
label | Inspection: Key - D
label | Inspection: By - SV
checkpoint | 4.2.4 - Subgrade Testing
label | Standard/Specification - Construction Drawings Sheet No: C-5111
label | Acceptance Criteria - Clegg testing at 10m intervals
label | ○ Subgrade CBR ≥ 6%
label | Verifying Document - Clegg Hammer Result Sheet
label | Frequency - 10m intervals
label | Inspection Type (Visual, other) - Subgrade Compaction Testing
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.5 - Foundation Preparation and Asbuilt Survey
label | Standard/Specification - As per design & Construction Drawings Sheet No: C-5111
label | Acceptance Criteria - Minimum 100mm of M/4 AP40 Basecourse
label | Verifying Document - Photos & Asbuilt Survey
label | Frequency - 10m Cross Sections
label | Inspection Type (Visual, other) - Dimension Inspection
label | Inspection: Key - D
label | Inspection: By - SV
checkpoint | 4.2.6 - Foundation Testing
label | Standard/Specification - Civil Technical Specification Section 5.5.1
label | Acceptance Criteria - NDM testing to be carried out by IANZ accredited laboratory. Site plan to be provided to Engineer showing every test point. Minimum acceptable result shall be 95% of the suppliers specification as per approved JMF.
label | Verifying Document - IANZ Accredited Laboratory Report
label | Frequency - 10m intervals
label | Inspection Type (Visual, other) - NDM Compaction Testing
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.7 - Foundation Testing
label | Standard/Specification - Civil Technical Specification Section 5.5.1
label | Acceptance Criteria - NDM testing carried out by approved user within Downer (with approval from Waka Kotahi) Min. Acceptable Compaction ≥ 95% of Target MDD
label | Verifying Document - IANZ Accredited Laboratory Report
label | Frequency - 10m intervals with surveyed test point locations
label | Inspection Type (Visual, other) - NDM Compaction Testing
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.8 - Foundation Testing
label | Standard/Specification - Civil Technical Specification Section 5.5.2, NZTA T/1
label | Acceptance Criteria - Deflection testing shall be carried prior to kerb and channel being formed.
label | Allowable deflections are as follows:
label | ○ 95% of readings < 2.0mm
label | ○ Maximum reading of 2.5mm
label | Verifying Document - IANZ Accredited Laboratory Report
label | Frequency - 10m intervals with surveyed test point locations
label | Inspection Type (Visual, other) - Benkelman Beaming
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.9 - Formwork
label | Standard/Specification - Civil Technical Specification Section 5.3
label | Acceptance Criteria - In accordance with NZS 3109. Finished level of formwork shall be within +-10mm of design. The line of the formwork shall be straight with the maximum deviation from a 3m straight edge along the face of 5mm with a cumulative total of all visible gaps of not more than 10mm
label | Verifying Document - ITP Sign off
label | Frequency - Prior to pouring the concrete
label | Inspection Type (Visual, other) - Survey Setout
label | Inspection: Key - D
label | Inspection: By - SV
checkpoint | 4.2.10 - Reinforcing Steel
label | Standard/Specification - Civil Technical Specification Section 5.2
label | Acceptance Criteria - Reinforcing steel in accordance with AS/NZS 4671 Grade 500E Steel Welded wire fabric in accordance with AS/NZS 4671 Class E smooth
label | Verifying Document - Dockets & Photos
label | Frequency - Per batch/delivery
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.2.11 - Pre-Pour Inspection
label | Standard/Specification - As per TDS
label | Acceptance Criteria - Boxing Check, Concrete Pour Inspection Checksheet completed, and Written approval from Engineer to proceed
label | Verifying Document - Checksheet: DN-QC-04 & Written Approval from Engineer
label | Frequency - Prior to pouring the concrete
label | Inspection Type (Visual, other) - Pre-pour Inspection
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.12 - Supply and Installation of Concrete
label | Standard/Specification - Civil Technical Specification Section 5.3
label | Acceptance Criteria - 20MPa at 28 Days. Concrete strength & slump testing certificates obtained from concrete plant and submitted to Engineer.
label | Verifying Document - Mix Design Certificate
label | Frequency - 1 Test per batch/delivery, 1 Sample @ 28days.
label | Inspection Type (Visual, other) - Concrete Strength & Slump Testing
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 4.2.13 - Concrete Surface Finish
label | Standard/Specification - Civil Technical Specification Section 5.3
label | Acceptance Criteria - U5 finish in accordance with NZS 3114
label | Verifying Document - ITP Sign Off/Photos
label | Frequency - Every Pour
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SP
checkpoint | 4.2.14 - Saw Cutting
label | Standard/Specification - Civil Technical Specification Section 5.3
label | Acceptance Criteria - Grooves to be between 1/4 and 1/3 of specified depth of slab, and any convenient width greater than 3mm. Max spacing of saw cuts shall be 3m.
label | Verifying Document - ITP Sign Off/Photos
label | Frequency - No more than 3m Intervals
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SP
checkpoint | 4.2.15 - Concrete Docket Tally
label | Standard/Specification - As per TDS
label | Acceptance Criteria - All concrete dockets to be collected on a daily basis and provided to the Site Engineer
label | Verifying Document - Dockets
label | Frequency - Daily
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.2.16 - Asbuilt Survey
label | Standard/Specification - Civil Technical Specification Section 5.1
label | Acceptance Criteria - In accordance with requirements of the TA Minimum cossfall of 1%
label | Verifying Document - Asbuilt Drawings
label | Frequency - Appropriate intervals to represent asbuilt footpath
label | Inspection Type (Visual, other) - Survey Asbuilt
label | Inspection: Key - R
label | Inspection: By - SV
section | FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - Construction Record Compilation
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Verifying Document - Closed-out NCR/Defects
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 5.2 - As-built Survey
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Verifying Document - As built survey record completed
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SV
checkpoint | 5.3 - Red-line As-built Drawings
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
label | Verifying Document - Signed As-built Drawings
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE, SV
checkpoint | 5.4 - Defect, Snag and Punch List
label | Inspection Point: Quality Control Activity - Defect, Snag and Punch List
label | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
label | Verifying Document - Register
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - PE
checkpoint | 5.5 - All QA documentation collated & signed-off
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - All signed and closed out
label | Verifying Document - Signed off Documents
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - QM
checklist | 558020-DOW-ITP-PC-0026_v2 (Earthworks -CVSC) | itp |  |  |  |  | 558020-DOW-ITP-PC-0026_v2 (Earthworks -CVSC)
section | 3.1 General Preliminary
checkpoint | 3.1.1 - Survey Setout
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - SV
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Service Location
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
label | Verifying Document - Service location documents
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.3 - Internal Permits
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.4 - External Permits
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.5 - ESCP
label | Standard/Specification - As per contracts
label | Acceptance Criteria - Prior to starting works, Ensure that ESCP plan an approved ESCP by council is in place and valid
label | Verifying Document - Approved ESCP plan
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.6 - Approved Construction Drawings
label | Standard/Specification - Issued by Client
label | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
section | 3.2 Earthwork - Incoming Materials
checkpoint | 3.2.1 - Imported Fill (AP65) and Structural Fill Sources
label | Standard/Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | Acceptance Criteria - Max Dry Density (Standard) and Optimum Water Content
label | ○ Natural moisture content
label | ○ Plasticity index
label | ○ Particle size distribution
label | Verifying Document - 1 set for each fill material and source (each 5000m3 thereafter)
label | Frequency - Porior to works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - CR/SE
checkpoint | 3.2.2 - Cut to Fill Material
label | Standard/Specification - NZS 4402:1986
label | Acceptance Criteria - Max Dry Density (Heavy) and Optimum Water Content
label | ○ Natural moisture content
label | ○ Plasticity index
label | ○ Particle size distribution
label | Verifying Document - 1 set for each fill material and source (each 5000m3 thereafter)
label | Frequency - Porior to works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - CR/SE
checkpoint | 3.2.3 - Geotextile
label | Standard/Specification - NZTA F/7
label | Acceptance Criteria - Non-woven filtration class 1 and Geotextile strenght class C.
label | ○ Confirm the above grade from the Manufacturer's Certificate of Compliance with IANZ endorsed or equivalent test documents.
label | Verifying Document - Product data sheet, Docket
label | Frequency - Each lot
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - Inspection
label | Inspection: By - SE
checkpoint | 3.2.4 - Geogrid
label | Standard/Specification - As per project specification, Section 2.15
label | Acceptance Criteria - Prior to placement of the geogrid, verification of the grade, length, orientation and layout is required against the drawings.
label | Verifying Document - Product data sheet, Photos, As-built
label | Frequency - each application
label | Inspection Type (Visual, other) - Action
label | Inspection: Key - W
label | Inspection: By - SE
section | 4.1 Earthwork - Construction
checkpoint | 4.1.1 - Site clearance
label | Standard/Specification - As per project specification, Section 2.3
label | Acceptance Criteria - Clearing shall include the complete removal of stumps, trees, logs, scrub and coarse vegetation and disposal by burning, or dumping and burying in accordance with any particular requirements of the contract documents
label | Verifying Document - Photos, Checklist as per requirements
label | Frequency - Prior to topsoil removal
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.1.2 - Top soil strip
label | Standard/Specification - As per project specification (200mm), Section 2.9
label | Acceptance Criteria - Topsoil shall be removed within the limits of the earthworks. Care shall be taken during the removal to avoid contamination of the topsoil.
label | Verifying Document - Photos, As-built
label | Frequency - All
label | Inspection Type (Visual, other) - Dimension Inspection, Visual
label | Inspection: Key - D,V
label | Inspection: By - SV, SE
checkpoint | 4.1.3 - Subgrade Suitability Testing - Scala Penetrometer Testing
label | Standard/Specification - As per project specification, Section 2.18.2
label | Acceptance Criteria - The Subgrade must be tested by Scala penetrometer or Shear Vane to confrim suitiablity. 3 blows per 100mm.
label | Verifying Document - Shear vane/scala checksheet
label | Frequency - Whole area by 20x20m Intervals
label | Inspection Type (Visual, other) - Inspection
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.4 - Subgrade Proof Rolling and Suitability Inspection
label | Standard/Specification - As per project specification, Section 2.10 and NZTA F/1, 10.5.1
label | Acceptance Criteria - The subgrade shall be proof rolled to verify the subgrade stiffness and consistency. "Indents" left in the compacte layer shoiuld be no more than 7mm for bulk fill and 5mm for subgrade fill.
label | ○ The RL and area of proof rolling will be surveyed.
label | Verifying Document - Proof Rolling Sheet, Photos, Survey area
label | Frequency - Prior to the placement of any filling, Whole area
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - H
label | Inspection: By - CR, SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.5 - Imported & Onsite Fill (Gap65/AP65) Compaction Testing (NDM)
label | Standard/Specification - As per project specification, Sections 2.13 & 2.18
label | Acceptance Criteria - Bulk fill shall be tested by NDM with a minimum Dry Density of 95% MDD
label | Cohesive soils shall be compacted at OWC (moisture limits are 4% below OWC to 2% above OWC)
label | Minimum acceptable dry density for AP65 is 2100 kg/m3 , a minimum dry density of 95% must be achieved (moisture limits are 4% below OWC to 2% below OWC)
label | Verifying Document - Test Results
label | Frequency - 10m x 10m grid
label | Inspection Type (Visual, other) - Inspection
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.6 - Geotextile Installation and Lap Length
label | Standard/Specification - As per project specification, Section 2.15
label | Acceptance Criteria - All geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets.
label | Verifying Document - Photos, As-built
label | Frequency - each application
label | Inspection Type (Visual, other) - Action
label | Inspection: Key - W
label | Inspection: By - SE
section | 4.2 Landscaping
checkpoint | 4.2.1 - General
label | Standard/Specification - NZTA P/39
label | Acceptance Criteria - Planting and grassing shall be in accordance with NZTA P/39.
label | This includes, but is not necessarily limited to:
label | ○ Site preparation for planting
label | ○ Topsoil placement
label | ○ Planting of grass and trees
label | ○ Trimming existing garden beds
label | ○ Replacing trees
label | ○ Supply and spread mulch
label | ○ Watering
label | ○ Weed control
label | ○ Maintenance
label | Verifying Document - Photos, as builts
label | Frequency - All
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.2.2 - Topsoil - Depths
label | Standard/Specification - As per project specification, Section 6.3
label | Acceptance Criteria - New grassed areas shall have a minimum of 200mm depth New garden areas shall have a minimum depth of 300mm. Where required top soil areas shall tie into existing levels with a minimum depth of 150mm of topsoil and at a maximum grade of 1V:5H.
label | Verifying Document - Photos, as builts
label | Frequency - All
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.2.3 - Topsoil - Quality
label | Standard/Specification - As per project specification, Section 6.3
label | Acceptance Criteria - Topsoil shall contain less than 5% by dry weight of solid detritus and debris and stone content shll be less than 10% by dry mass. The topsoil shall not contain any object larger than 30mm in diameter in the largest direction.
label | Verifying Document - Photos, as builts
label | Frequency - All
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.2.4 - Grass - Fertilization
label | Standard/Specification - As per project specification, Section 6.4
label | Acceptance Criteria - Superphosphate fertilizer shall be applied at 20 grams/m2 at grass seeding.
label | ○ Three weeks after seeding, slow release fertilizer shall be applied at a rate of 15 grams/m2
label | ○ The fertilizer shall be 3-2-1 NPK plus trace elements mix. Hydroseeding is acceptable.
label | Verifying Document - Photos, as builts
label | Frequency - All
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.2.5 - Grass - Coverage
label | Standard/Specification - As per project specification, Section 6.4
label | Acceptance Criteria - At least 90% of the ground surface shall be covered with no bare area greater than 30mm diameter.
label | ○ The grass sward shall be maintained at no less than 90% weed free (i.e have less than 10% of it's area in non-specific grasses and weeds).
label | Verifying Document - Photos, as builts
label | Frequency - All
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.2.6 - Grass - Seeding Conditions
label | Standard/Specification - As per project specification, Section 6.4
label | Acceptance Criteria - Work shall only be undertaken when the weather is suitable i.e mild, dull and moist, and when the ground is moist and workable. All planting and grassing operations shall be suspended during periods of severe frosts, drought, water logging or persistant drying winds.
label | Verifying Document - Photos, as builts
label | Frequency - All
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.2.7 - Mulch to Garden Beds - General
label | Standard/Specification - As per project specification, Section 6.5
label | Acceptance Criteria - The Contractor is to supply and install organic mulch to all garden bed and planted areas. Mulch shall be clean, dry and weed free.
label | Verifying Document - Photos, as builts
label | Frequency - All
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.2.8 - Mulch to Garden Beds - Depth
label | Standard/Specification - As per project specification, Section 6.5
label | Acceptance Criteria - Ensure mulch is kept a minimum of 50mm clear of plant stems to avoid stem rot.
label | ○ Mulch depth shall be maintained to a minimum consolidated depth of 100mm.
label | Verifying Document - Photos, as builts
label | Frequency - All
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.2.9 - Mulch to Garden Beds - Surface Height
label | Standard/Specification - As per project specification, Section 6.5
label | Acceptance Criteria - The surface of the mulch shall be flush with or no more than 25mm below the surrounding ground surface, kerb, path or other formed surface and shall be even and free of hollows.
label | Verifying Document - Photos, as builts
label | Frequency - All
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
section | FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - Construction Record Compilation
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Verifying Document - Closed-out NCR/Defects
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 5.2 - As-built Survey
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Verifying Document - As built survey record completed
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SV
checkpoint | 5.3 - Red-line As-built Drawings
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
label | Verifying Document - Signed As-built Drawings
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE, SV
checkpoint | 5.4 - Defect, Snag and Punch List
label | Inspection Point: Quality Control Activity - Defect, Snag and Punch List
label | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
label | Verifying Document - Register
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - PE
checkpoint | 5.5 - All QA documentation collated & signed-off
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - All signed and closed out
label | Verifying Document - Signed off Documents
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - QM
checklist | 558020-DOW-ITP-PC-0027_v3 (Pavement - CVSC) | itp |  |  |  |  | 558020-DOW-ITP-PC-0027_v3 (Pavement - CVSC)
section | 3.1 General Preliminary
checkpoint | 3.1.1 - Survey Setout
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - SV
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Service Location
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
label | Verifying Document - Service location documents
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.3 - Internal Permits
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.4 - External Permits
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.5 - ESCP
label | Standard/Specification - As per contracts
label | Acceptance Criteria - Prior to starting works, Ensure that ESCP plan an approved ESCP by counsil is in place and valid
label | Verifying Document - Approved ESCP plan
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.6 - Approved Construction Drawings
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
section | 3.2 Pavement Materials
checkpoint | 3.2.1 - AP65 - Source Property Tests and Sampling
label | Standard/Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2006, NZS 4407 : 1991, NZS 4402 : 1986
label | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 per source
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.2 - AP65 - Production Property Tests and Sampling
label | Standard/Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2006, NZS 4407 : 1991
label | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Permeability, and Particle Size Distribution.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 3 per source initially, then 1/1000m³ (stockpile sample)
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.3 - AP65 - Testing for Layer Compaction - MDD
label | Standard/Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 per material source (stockpile sample)
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.4 - AP40 - Source Property Tests and Sampling
label | Standard/Specification - TNZ M/4: 2006 - 3 NZS 4407 : 1991 NZS 4402 : 1986
label | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 per source initially, then 1/1000m³ (stockpile sample)
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.5 - AP40 - Production Property Tests and Sampling
label | Standard/Specification - TNZ M/4: 2006 - 4 NZS 4407 : 1991
label | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per M/4 Figure 1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 3 per source initially, then 1/1000m³ (stockpile sample)
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.6 - AP40 - Testing for Layer Compaction - MDD
label | Standard/Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
label | Verifying Document - IANZ Lab Reports
label | Frequency - 5,000m2
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.7 - Sealing Chip - Source Property Tests and Sampling
label | Standard/Specification - TNZ M/6: 2019 - 4
label | Acceptance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV
label | Verifying Document - IANZ Lab Reports
label | Frequency - Before Supply and Every 10,000m3 Thereafter
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.8 - Sealing Chip - Production Property Test Sampling
label | Standard/Specification - TNZ M/6: 2019 - 5
label | Acceptance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6
label | Verifying Document - IANZ Lab Reports
label | Frequency - Every 500m3
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.9 - Bitumen - Quality Testing
label | Standard/Specification - NZTA M01: 2022 - 6
label | Acceptance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01.
label | Verifying Document - IANZ Lab Reports
label | Frequency - One test per grade supplied
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.10 - Bitumen - Supply Testing
label | Standard/Specification - NZTA Q05: 2022 - 6.2
label | Acceptance Criteria - The binder shall have benchmark parameter testing completed complying with the requirements of NZTA Q05.
label | Verifying Document - IANZ Lab Reports
label | Frequency - Every 200 tonnes supplied.
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
section | 3.3 Cement Treated Basecourse
checkpoint | 3.3.1 - Cement
label | Standard/Specification - NZS3112
label | Acceptance Criteria - General purpose Portland cement, type GP, shall be used unless otherwise specified in the Contract documents.
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By (Role Key) - CR
holdpoint | AUTHORITY HOLDPOINT
section | 3.4 Asphalt
checkpoint | 3.4.1 - AC14
label | Standard/Specification - Pre-construction
label | Acceptance Criteria - As per NZTA M/10 specification
label | Verifying Document - Mix Design, Production Test report or Volumetric properties
label | Frequency - Per Mix
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By (Role Key) - CR
holdpoint | AUTHORITY HOLDPOINT
section | 3.5 Geotextile and Geogrid
checkpoint | 3.5.1 - Geotextile
label | Standard/Specification - Class C as per design spec
label | Acceptance Criteria - The Contractor shall submit to the Engineer for approval the details of the filter fabric they propose to use at least two weeks prior to commencement of works, including compliance certificates.
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By (Role Key) - SE
checkpoint | 3.5.2 - Geogrid
label | Standard/Specification - TENSAR TRIAX TX160 as per desig spec
label | Acceptance Criteria - The geogrid shall be manufactured in accordance with a management system that complies with BS EN ISO 9001 and BS 14001.
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By (Role Key) - SE
section | 4.1 Unbound Pavement Construction
checkpoint | 4.1.1 - Top Subgrade CBR
label | Standard/Specification - Project Specification CVSC Pvmt Type C Detail on Bartley Dwg TD002
label | Acceptance Criteria - Minimum CBR 3.5% to be achieved failed to achieve the above need to carry with the contingency details as per Project Specification CVSC Pvmt Type C Detail on Bartley Dwg TD002
label | Verifying Document - Test Report
label | Frequency - Before starting Subbase layer, whole lot in 20x20 centers
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - H
label | Inspection: By - SE, CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.2 - Geotextile
label | Standard/Specification - NZTA F/7
label | Acceptance Criteria - All geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets.
label | Verifying Document - Photos
label | Frequency - Each roll out and overlaps
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SP
checkpoint | 4.1.3 - Geogrid
label | Standard/Specification - Project Specification CVSC Pvmt Type C Detail on Bartley Dwg TD002
label | Acceptance Criteria - Prior to placement of the geogrid, verification of the grade, length, orientation and layout is required against the drawings.
label | ○ A minimum overlap of 500mm is required between sheets.
label | Verifying Document - Photos
label | Frequency - Each roll out and overlaps
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SP
checkpoint | 4.1.4 - Material Placement
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - The uniformity, contamination and segregation shall be Continuous monitored thoughout
label | Verifying Document - Photos
label | Frequency - Continuous monitoring.
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - PS
checkpoint | 4.1.5 - Plateau Density Tests (Sub-basecourse)
label | Standard/Specification - TNZ B/02: 2005 - 7.5
label | Acceptance Criteria - The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC.
label | Verifying Document - Plateau test results confirmance
label | Frequency - Continuous monitoring.
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.1.6 - Sub-basecourse Pavement Layer Compaction (NDM)
label | Standard/Specification - TNZ B/02: 2005 - 7.6
label | Acceptance Criteria - Mean Value ≥ 95 % of MDD Minimum Value ≥ 92 of MDD
label | Verifying Document - NDM Report
label | Frequency - 1/10m each layer not exceeding 200mm. If no clear lanes then 1 test per 50m2.
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.7 - Sub-basecourse Layer thickness
label | Standard/Specification - TNZ B/02: 2005 - 5.1
label | Acceptance Criteria - The Sub-basecourse shall be monitured for Layer thickness. –25 mm +5 mm
label | Verifying Document - Survey / Level Checks
label | Frequency - 1/20m Full width
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - D
label | Inspection: By - SV or SE
checkpoint | 4.1.8 - Benkelman Beaming on Subbase
label | Standard/Specification - Contract Specification, Section 3.5.5 & Appendix F
label | Acceptance Criteria - 90th percentile deflection ≤ 1.3mm.
label | ○ No single deflection > 1.4mm.
label | Verifying Document - Test report, delivered weekly
label | Frequency - 1 per 10m each traffic lane (alternating wheel paths) or 1 test /50m2 if no clear lane
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.1.9 - Plateau Density Tests (Pre stabilise Basecourse)
label | Standard/Specification - TNZ B/02: 2005 - 7.5
label | Acceptance Criteria - The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC.
label | Verifying Document - Plateau test results confirmance
label | Frequency - Continuous monitoring.
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.1.10 - Basecourse Pavement Layer Compaction (Pre stabilise Basecourse)
label | Standard/Specification - TNZ B/02: 2005 - 7.6
label | Acceptance Criteria - Mean Value ≥ 98 % of MDD Minimum Value ≥ 95 of MDD
label | Verifying Document - NDM Report
label | Frequency - 1/10m each layer not exceeding 200mm. If no clear lanes then 1 test per 50m2.
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.11 - Basecourse Layer thickness. (Pre stabilise Basecourse)
label | Standard/Specification - TNZ B/02: 2005 - 5.1
label | Acceptance Criteria - The Sub-basecourse shall be monitured for Layer thickness. –5 mm +15 mm
label | Verifying Document - Survey / Level Checks
label | Frequency - 1/20m Full width
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - D
label | Inspection: By - SV or SE
section | 4.2 CTB (Cement Treated Basecourse)
checkpoint | 4.2.1 - Pre-Stab check
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Check the temperature (between 5 °C or and 30 ºC), Wind (not exceeds 25km/hr), Rain, Time limitations(Primary compaction within 2 hr and the final trimming compaction within 4 hrs)
label | Verifying Document - Checklsit
label | Frequency - Befoore the stabilisation
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.2.2 - Mat testing
label | Standard/Specification - NZTA B/5: 2008 - 7.3
label | Acceptance Criteria - Every 400 m2 complete a Mat test using a 1m2 cancas. The ammount of Stabilising Agent on the canvas shall be within ±0.5 kg/m2 of the specified rate.
label | Verifying Document - Test Results/Photos
label | Frequency - Every 400 m2
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - D
label | Inspection: By - SE
checkpoint | 4.2.3 - Average usage test
label | Standard/Specification - NZTA B/5: 2008 - 7.3
label | Acceptance Criteria - Upon emptying the spreader and bulk tanker, Compare tonnes of Stabilising Agent used (from delivery docket) with measured area. Usagese shall be within ±2.5 % of the specified rate
label | Verifying Document - Calculation with Dockets and Weights
label | Frequency - Upon emptying the spreader and bulk tanker
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - D
label | Inspection: By - SE
checkpoint | 4.2.4 - Water content during compaction
label | Standard/Specification - NZTA B/5: 2008 - 7.5
label | Acceptance Criteria - The water content during compaction shall be in the range of 90% to 100% of the material’s optimum water content. The water content tests taken prior to stabilising and the water consumed per cut shall be recorded in the production plan records.
label | Verifying Document - NDM Results, delivered weekly
label | Frequency - 5 tests per 1000m2
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.2.5 - Control of cut depth
label | Standard/Specification - NZTA B/5: 2008 - 7.6.1
label | Acceptance Criteria - The actual depth of the cut shall be physically measured at both ends of the stabilising drum at least once every 200 m along the cut length. Maximum variation from the specified depth of cut is –0 mm and +20 mm. Unless specifically allowed in the project specification, the depth of cut shall not intrude into a subgrade layer.
label | Verifying Document - Site Records/Photos
label | Frequency - Each Cut
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.2.6 - Overlap on longitudinal joints
label | Standard/Specification - NZTA B/5: 2008 - 7.6.2
label | Acceptance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by minimum of 200 mm or half the layer thickness, whichever is the greater.
label | Verifying Document - Site Records/Photos
label | Frequency - Each Cut
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.2.7 - Continuity of stabilised layer
label | Standard/Specification - NZTA B/5: 2008 - 7.6.3
label | Acceptance Criteria - The exact location of the end of the cut shall be carefully marked. This mark shall coincide with the position of the centre of the mixing drum at the point at which the supply of the stabilising agent ceased. To ensure continuity of the stabilised layer, the next successive cut shall be started 1 m behind this mark.
label | Verifying Document - Site Records/Photos
label | Frequency - Each Cut
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.2.8 - Plateau Density tests
label | Standard/Specification - NZTA B/5: 2008 - 7.7
label | Acceptance Criteria - At the outset of compaction the contractor shall undertake plateau density tests for the purpose of determining the practicality of both the OWC and the MDD mix design targets, the minimum, and possibly the maximum, number and type of roller passes required to achieve the MDD for the proposed compaction plant and stiffness of lower pavement ‘anvil’ beneath the layer to be compacted.
label | Verifying Document - Plateau Density test
label | Frequency - Continuous monitoring.
label | Inspection Type (Visual, other) - Inspection
label | Inspection: Key - I
label | Inspection: By - SE
checkpoint | 4.2.9 - Compaction testing
label | Standard/Specification - NZTA B/5: 2008 - 7.7.1
label | Acceptance Criteria - The Degree of Compaction for Cement Treated Subbase shall have a Mean Dry Density of ≥ 98 % and a Minimum Dry Density of ≥ 95%. Compaction testing during construction of the stabilised pavement layers shall be carried out in lots.The area of a lot shall not exceed 1000 m2
label | Verifying Document - NDM Results
label | Frequency - 5 tests per Lot
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.2.10 - ITS Testing
label | Standard/Specification - NZTA T/19, Contract Specification, Section 3.6.5, Appendix F
label | Acceptance Criteria - ITS testing shall be carried out in accordance with NZTA T/19. The maximum time between mixing and compaction shall be 2 hours. The ITS test ranges shall be as follows:
label | ○ Dry: 150kPa - 350 kPa
label | ○ Soaked: 100kPa - 300kPa
label | – The Tensile Strength Retained (TSR) shall be no less than 75%
label | – If results are below the target strengths then notify the Engineer immediately.
label | Verifying Document - Test Results, delivered weekly
label | Frequency - 2 ITS (dry) and 2 ITS (soaked) for behind the hoe sampled each day of stabilisation. Samples are to be taken from seperate locations.
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.2.11 - Benkelman Beaming on Basecourse (cement modified)
label | Standard/Specification - Contract Specification, Section 3.5.5 & Appendix F
label | Acceptance Criteria - 90th percentile deflection ≤ 1.0mm.
label | ○ No single deflection > 1.1mm.
label | Verifying Document - Test report, delivered weekly
label | Frequency - 1 per 10m each traffic lane (alternating wheel paths) or 1 test /50m2 if no clear lane
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.2.12 - Construction Tolerances
label | Standard/Specification - TNZ B/5: 2008 - 7.8
label | Acceptance Criteria - Basecourse where asphalt surfacing with concrete channel
label | (i) at or close to the lip of channel –5 +5 mm
label | (ii) at other locations on pavement –15 +5 mm
label | (iii) at other locations on pavement –5 +15 mm
label | Verifying Document - Survey Records
label | Frequency - On final layer
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - C
label | Inspection: By - SV
checkpoint | 4.2.13 - Surface Finish post sweeping
label | Standard/Specification - TNZ B/02: 2005 - 7.8
label | Acceptance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
label | Verifying Document - Photos
label | Frequency - Prior to sealing
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
section | 4.3 Grade 3/5 Chip Sealing
checkpoint | 4.3.1 - Presealing Requirements
label | Standard/Specification - TNZ B/02: 2005 - 12, Contract Specification, Section 3.6.7
label | Acceptance Criteria - The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 70%.
label | Verifying Document - NDM Report
label | Frequency - 1/10m
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.3.2 - Benkelman Beaming on Basecouse (on AP40 CTB)
label | Standard/Specification - Contract Specification, Section 3.5.5 & Appendix F
label | Acceptance Criteria - 90th percentile deflection ≤ 1.0mm.
label | ○ No single deflection > 1.1mm.
label | Verifying Document - Test report, delivered weekly
label | Frequency - 1 per 10m each traffic lane (alternating wheel paths) or 1 test /50m2 if no clear lane
label | Inspection Type (Visual, other) - Inspection
label | Inspection: Key - I
label | Inspection: By - SE
checkpoint | 4.3.3 - Preseal inspection/ Subbase/Basecourse check
label | Standard/Specification - TNZ P3 TNZ B02
label | Acceptance Criteria - The road shall be reasonably dry before the binder is applied, and no spraying with asphaltic binder shall be carried out when the air temperature measured within the confines of the sealing course is below 10oC in the shade.
label | ○ Visual inspection by engineer's representative
label | Verifying Document - Hold point Release, ITP Sign off
label | Frequency - Prior to sealing
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - I
label | Inspection: By - SE
checkpoint | 4.3.4 - Spray Temperature
label | Standard/Specification - TNZ P3
label | Acceptance Criteria - The emulsified asphalt may be sprayed at the temperature at which it is received from the manufacturing plant except that no emulsified asphalt shall be sprayed at a temperature in excess of 90oC or below 20oC.
label | Verifying Document - Sealing statement
label | Frequency - Prior to sealing
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - I
label | Inspection: By - SE
checkpoint | 4.3.5 - Chip Application
label | Standard/Specification - TNZ P3
label | Acceptance Criteria - All binder sprayed shall be covered with chips across the full sprayed width, apart from necessary longitudinal laps, within five minutes of spraying.
label | Verifying Document - Sealing statement
label | Frequency - For every spray run
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - I
label | Inspection: By - SE
checkpoint | 4.3.6 - Post Seal Inspections
label | Standard/Specification - TNZ P3
label | Acceptance Criteria - The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed.
label | Verifying Document - Engineers Acceptance
label | Frequency - After Final Sweeping
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - H
label | Inspection: By - SE, CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3.7 - Chipseal Repairs
label | Standard/Specification - TNZ P3
label | Acceptance Criteria - The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used.
label | Verifying Document - Approved Repair Methodology
label | Frequency - Prior to Repairs
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - A
label | Inspection: By - SE
section | 4.4 Asphaltic Concrete (AC14)
checkpoint | 4.4.1 - Preparation of Area to be Paved
label | Standard/Specification - NZTA M27:2020 - 9
label | Acceptance Criteria - The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping. All fatty and unsuitable patches shall be removed. Depressions and other irregularities shall be patched or corrected.
label | Verifying Document - Site Notes/Photos
label | Frequency - Pre Seal
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - PS
checkpoint | 4.4.2 - Ambient Conditions for Placing
label | Standard/Specification - NZTA M27:2020 - 9
label | Acceptance Criteria - Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C,
label | Verifying Document - Site Notes/ Weather report
label | Frequency - Pre Seal
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - R
label | Inspection: By - PS
checkpoint | 4.4.3 - Seal surface check prior to asphalt
label | Standard/Specification - as per project specification 3.7.7
label | Acceptance Criteria - Visual inspection by engineer's representative
label | Verifying Document - ITP Sign off
label | Frequency - All
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4.4 - Heavy Tack & Blind
label | Standard/Specification - Minimum Residual Bitumen of 1.2 L/m2 As per project based pavement specification
label | Acceptance Criteria - Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. The use of a hand lance shall be minimised to ensure an even application of the tack coat. Where SMA is to be spread over clean, freshly placed asphalt, the Engineer can direct the Contractor to omit the tack coat.
label | Verifying Document - Run sheet, QA from Sub
label | Frequency - Entire length of pavement
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.4.5 - Asphaltic Concrete - Surfacing
label | Standard/Specification - NZTA M10 & M27, Contract Specification 3.7.15, Appendix F, Section 10.15
label | Acceptance Criteria - 55mm of AC14
label | ○ Asphalt layers less than or equal to 55mm shall be +/- 5mm from the specified design thickness.
label | ○ The combined thickness of all asphalt layers should not be less than the specified total asphalt depth.
label | Verifying Document - Run sheet, QA from Sub
label | Frequency - Entire length of pavement
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - D
label | Inspection: By - SE
checkpoint | 4.4.6 - Thickness
label | Standard/Specification - Contract Specification, Section 3.7.15
label | Acceptance Criteria - Thickness as per design lift with +/-10mm (AC14)
label | Verifying Document - ITP Sign off
label | Frequency - Continuos
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.4.7 - Finished surface at joints
label | Standard/Specification - Contract Specification, Section 3.7.16
label | Acceptance Criteria - No more than 5 mm variation under a 3 m stright edge
label | Verifying Document - ITP Sign off
label | Frequency - Continuos
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.4.8 - Air Voids
label | Standard/Specification - NZTA M/10
label | Acceptance Criteria - The maximum and minimum air voids for each core shall be +3%/-2% from the mix design air voids.
label | Verifying Document - Test results, delivered weekly
label | Frequency - Continuos
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.4.9 - Level checks
label | Standard/Specification - Survey
label | Acceptance Criteria - Thickness as per design lift with +/-10mm (AC20)
label | ○ Thickness of 40mm with +/-5mm (SMA10)
label | Verifying Document - As-built drawing
label | Frequency - 1/20m full width
label | Inspection Type (Visual, other) - As-built
label | Inspection: Key - D
label | Inspection: By - SV
checkpoint | 4.4.10 - Line marking
label | Standard/Specification - Set out
label | Acceptance Criteria - As per NZTA standard/ design drawings
label | Verifying Document - ITP sign off/ Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
section | FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - Construction Record Compilation
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Verifying Document - Closed-out NCR/Defects
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 5.2 - As-built Survey
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Verifying Document - As built survey record completed
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SV
checkpoint | 5.3 - Red-line As-built Drawings
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
label | Verifying Document - Signed As-built Drawings
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE, SV
checkpoint | 5.4 - Defect, Snag and Punch List
label | Inspection Point: Quality Control Activity - Defect, Snag and Punch List
label | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
label | Verifying Document - Register
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - PE
checkpoint | 5.5 - All QA documentation collated & signed-off
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - All signed and closed out
label | Verifying Document - Signed off Documents
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - QM
checklist | 558020-DOW-ITP-PC-0028_v2 (3 Waters - CVSC) | itp |  |  |  |  | 558020-DOW-ITP-PC-0028_v2 (3 Waters - CVSC)
section | 3.1 General Preliminary
checkpoint | 3.1.1 - Survey Setout
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - SV
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Service Location
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
label | Verifying Document - Service location documents
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.3 - Internal Permits
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.4 - External Permits
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.5 - ESCP
label | Standard/Specification - As per contracts
label | Acceptance Criteria - Prior to starting works, Ensure that ESCP plan an approved ESCP by counsil is in place and valid
label | Verifying Document - Approved ESCP plan
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.6 - Approved Construction Drawings
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
section | 3.2 Stormwater and Wastewater - Materials
checkpoint | 3.2.1 - Sand
label | Standard/Specification - As per project specification (Stormwater Swales, 3.1.2)
label | Acceptance Criteria - Sieve analysis NZS 4402 Test 4.2.8.2
label | – – – – – – – – – – – – – –
label | Grading criteria:
label | – – – – – – – – – – – – – –
label | Sieve Size ¦¦ % Passing
label | 9.5mm ¦¦ 100
label | 5.4mm ¦¦ 70 - 100
label | 2.36mm ¦¦ 50 - 70
label | 0.6mm ¦¦ 15 - 35
label | 0.3mm ¦¦ 5 - 15
label | 0.075mm ¦¦ 2
label | – – – – – – – – – – – – – –
label | Verifying Document - Test result
label | Frequency - 1 per 200m³
label | Inspection Type (Visual, other) - Visual Inspection, Document Review
label | Inspection: Key - R
label | Inspection: By (Role Key) - SE/PS
checkpoint | 3.2.2 - Drainage Media
label | Standard/Specification - As per project specification (Stormwater Swales, 3.1.3)
label | Acceptance Criteria - Single size angular stone chip no larger than 9.5mm
label | – – – – – – – – – – – – – –
label | Grading criteria:
label | – – – – – – – – – – – – – –
label | Sieve Size ¦¦ % Passing
label | 9.5mm ¦¦ 80 - 100
label | 2.4mm ¦¦ 0 - 20
label | 0.6mm ¦¦ <2%
label | – – – – – – – – – – – – – –
label | Verifying Document - Test result
label | Frequency - 1 per 200m³
label | Inspection Type (Visual, other) - Visual Inspection, Document Review
label | Inspection: Key - R
label | Inspection: By (Role Key) - SE/PS
checkpoint | 3.2.3 - Soil Media
label | Standard/Specification - As per project specification (Stormwater Swales, 3.1.5)
label | Acceptance Criteria - The media must consist of material that has:
label | ○ 5% clean organic compost from a consistent source. The source of clean organic material must have been provided to the Engineer for acceptance prior to supply.
label | ○ Locally sourced topsoil (free of weeds or contamination)
label | ○ No obvious seeds, weeds, any contamination and material > 25mm in nominal diameter
label | ○ < or = to 50% coarse sand from a consistent source to improve permeability and structure.
label | ○ < 3% clay (particles < 0.002mm)
label | ○ < 5% by volume of particles exceeding 4.75mm nominal diameter.
label | ○ A pH rangeof 7.5 - 5.5
label | ○ Well graded particle size from 0.075mm through to 4.75mm with no gaps in the grading.
label | ○ Compacted hydraulic conductivity of at least 50mm/hr and nort exceeding 400mm/hr based on the ASTM F1815-069 methodology.
label | ○ Total Phosphorus < 100mg/kg
label | ○ Total Nitrogen < 1000mg/kg
label | Verifying Document - Test result
label | Frequency - 1 per 200m³
label | Inspection Type (Visual, other) - Visual Inspection, Document Review
label | Inspection: Key - R
label | Inspection: By (Role Key) - SE/PS
checkpoint | 3.2.4 - Concrete Pipes
label | Standard/Specification - As per project specification (Pipeline Supply, 2.4.4)
label | Acceptance Criteria - Concrete pipes must be reinforced concrete rubber ring jointed pipe complying with AS/NZS 4058.
label | Verifying Document - Data Sheet
label | Frequency - Per delivery/Item
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.2.5 - PVC-U Pipes
label | Standard/Specification - As per project specification (Pipeline Supply, 2.4.2)
label | Acceptance Criteria - PVC-U pipes and fittings for gravity stormwater must be plain wall construction rubber ring jointed and must comply with AS/NZS 1254.
label | ○ All PVC pipes must have factory fitted, composite rings; loose Z type rings must not be used.
label | ○ PVC-U pipe diameters shown on the Drawings are the nominal diameters unless shown otherwise. Pipe classes are to be as shown on the Drawings
label | Verifying Document - Concrete pipes must be reinforced concrete rubber ring jointed pipe complying with AS/NZS 4058.
label | Frequency - Per delivery/Item
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.2.6 - PE & PP Pipes
label | Standard/Specification - As per project specification (Pipeline Supply, 2.4.3)
label | Acceptance Criteria - PE & PP pipe must comply with AS/NZS 5065.
label | Verifying Document - Data Sheet
label | Frequency - Per delivery/Item
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.7 - Precast Concrete Manholes
label | Standard/Specification - As per project specification (Pipeline Supply, 2.5.1)
label | Acceptance Criteria - Unless shown otherwise on the Drawings, manholes (and manhole components) must be circular precast reinforced concrete manholes manufactured in accordance with AS/NZS 4058 with cast in base manufactured to NZ5 3109.
label | Verifying Document - Data Sheet
label | Frequency - Per delivery/Item
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.2.8 - Manhole Lids
label | Standard/Specification - As per project specification (Pipeline Supply, 2.5.2)
label | Acceptance Criteria - Manhole lids must be precast reinforced concrete manufactured in accordance with NZS 5109 rated heavy duty (HD60) or HN-H0-72 as specified on the Drawings or as required by the local authority
label | Verifying Document - Data Sheet
label | Frequency - Per delivery/Item
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.2.9 - Frame and Covers
label | Standard/Specification - As per project specification (Pipeline Supply, 2.5.3)
label | Acceptance Criteria - Manhole lids must be precast reinforced concrete manufactured in accordance with NZS 5109 rated heavy duty (HD60) or HN-H0-72 as specified on the Drawings or as required by the local authority
label | Verifying Document - Data Sheet
label | Frequency - Per delivery/Item
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.2.10 - Catchpits and Grates
label | Standard/Specification - As per project specification (Pipeline Supply, 2.6)
label | Acceptance Criteria - Use precast single or double catchpits manufactured from reinforced concrete complying with NZS 3101 and NZ 3109. Each single catchpit must have minimum internal dimensions of 450 mm by 675 mm.
label | ○ Use grates rated to class D complying with As 3996 with
label | Verifying Document - Data Sheet
label | Frequency - Per delivery/Item
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.2.11 - Subsoil
label | Standard/Specification - As per project specification (Pipeline Supply, 2.7)
label | Acceptance Criteria - Unless shown otherwise on the Drawings, subsoil drains must be DN110 perforated corrugated plastic pipe complying with AS 2439.1-2007 Perforated plastics and drainage and effluent pipe and fittings, Part 1: Perforated drainage pipe and associated fittings, and be minimum SN 4
label | Verifying Document - Data Sheet
label | Frequency - Per delivery/Item
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.2.12 - Materials - general
label | Standard/Specification - As per project specification T-WES 00012, Section 4.8
label | Acceptance Criteria - Do not change the source of supply of materials without written approval from the Engineer - refer Section 2.1
label | Verifying Document - Approved list Verification / Datasheet
label | Frequency - Prior to use
label | Inspection Type (Visual, other) - Visual Inspection, Document Review
label | Inspection: Key - R
label | Inspection: By - SE/CR
section | 3.3 Receiving Materials/Parts - Portable water
checkpoint | 3.3.1 - Water Pipes
label | Standard/Specification - As per project specification refer T-WES 00013, 2.4
label | Acceptance Criteria - All fittings shall be of the material, grade, diameter and pressure class shown on the Drawings/specifications and be on the approved material list
label | Verifying Document - Approved list Verification / Datasheet
label | Frequency - Prior to use
label | Inspection Type (Visual, other) - Document Review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.3.2 - Water Fittings
label | Standard/Specification - As per project specification refer T-WES 00014, 2.5
label | Acceptance Criteria - All fittings shall be of the material, grade, diameter and pressure class shown on the Drawings/specifications and be on the approved material list
label | Verifying Document - Approved list Verification / Datasheet
label | Frequency - Prior to use
label | Inspection Type (Visual, other) - Document Review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.3.3 - Joints
label | Standard/Specification - As per project specification refer T-WES 00014, 2.6
label | Acceptance Criteria - All Joints shall be of the material, grade and size shown on the Drawings/specifications and be on the approved material list
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Inspection Type (Visual, other) - Document Review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.3.4 - Fire hydrant and Valve Covers
label | Standard/Specification - As per project specification refer T-WES 00014, 2.7
label | Acceptance Criteria - All surface boxes and covers over buried valves and hydrants must be rated to AS 3996 Class B (footpaths and non-trafficable areas) or Class D (trafficable areas).
label | ○ Use PVC risers and/or or concrete frames as necessary to provide access to the valves or hydrants.
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Inspection Type (Visual, other) - Document Review
label | Inspection: Key - R
label | Inspection: By - SE/PS
section | 3.4 General
checkpoint | 3.2.13 - Embedment Materials (1)
label | Standard/Specification - As per project specification (Pipeline Supply, 2.8)
label | Acceptance Criteria - For flexible pipes, well graded processed AP20 complying with AS/NZS 2566.2 section 54.2. Any proposed alternative bedding material must meet the requirements of AS/NZS 2566.2 section 5.4.2.1 note 3 and may only be used if approved by the Engineer in writing.
label | ○ Where low-fines embedment material is specified on the Drawings, the material must be a graded AP20 with none passing the 2.36 mm sieve size (no fines material) that has the consistency and moisture content suitable for placement without segregation. Screened in-situ materials may be used for embedment
label | ○ Pea metal may not be used
label | Verifying Document - Test result
label | Frequency - 1 per 200m³
label | Inspection Type (Visual, other) - Visual Inspection, Document Review
label | Inspection: Key - R
label | Inspection: By (Role Key) - SE/PS
checkpoint | 3.2.13 - Embedment Materials (2)
label | Standard/Specification - As per project specification (Pipeline Supply, 2.8)
label | Acceptance Criteria - For concrete pipes, Material with grading limits in accordance with As/NZS 3725 and the CPAA Engineering Guideline Selecting Materials for Bedding Steel Reinforced Concrete Pipe available from the CPAA website.
label | ○ Where low-fines embedment material is specified on the Drawings, the material must be a gradec AP20 with none passing the 2.36 mm sieve size (no fines material) that has the consistency and moisture content suitable for placement without segregation It is expected that screened in-situ materials will be used for embedment. The material used is to have a Compaction Fraction (CF) of 0.1 or less as defined below
label | Verifying Document - Test result
label | Frequency - 2 per 200m³
label | Inspection Type (Visual, other) - Visual Inspection, Document Review
label | Inspection: Key - R
label | Inspection: By (Role Key) - SE/PS
checkpoint | 3.2.14 - Trench Fill Material
label | Standard/Specification - As per project specification
label | Acceptance Criteria - Before construction commences establish the maximum dry density using NZS 4402 Test 4.1.3 New Zealand vibrating hammer compaction test. Submit results to the Engineer one week before importing trench fill material.
label | Verifying Document - Test result
label | Frequency - Prior to imoport material
label | Inspection Type (Visual, other) - Document Review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.15 - Concrete
label | Standard/Specification - As per project specification (Minor Concrete Works, 2.1)
label | Acceptance Criteria - Normal concrete witht the requirements of NZS 3104 and strength shown on the drawings. Where the strength us not shown, use 25 Mpa normal concrete
label | Verifying Document - Mix Design
label | Frequency - Per mix
label | Inspection Type (Visual, other) - Document Review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.2.4 - Geotextile
label | Standard/Specification - As per project specification (Earthworks, 2.15)
label | Acceptance Criteria - Geotextile to be the grade and standards on the drawings and be on the Approved materials list.
label | ○ Non-Woven Filtration Class 1 and Geotextile Strength Class C
label | Verifying Document - Data Sheet
label | Frequency - Per delivery/Item
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE/PS
section | 4.1 Soakage swale - Construction
checkpoint | 4.1.1 - Swale - Formation and Levels
label | Standard/Specification - As per design height
label | Acceptance Criteria - Ensure the excavation is clear of roots, projections, or obstructions. If overexcavation occurs, bring the bottom back to grade using excavated material, lightly compacting it. Do not leave loose soil. Notify the Engineer if the swale contains low-permeability soils; they will assess and advise on additional excavation if needed.
label | Verifying Document - As-built check, photos
label | Frequency - Before instal the drainage media
label | Inspection Type (Visual, other) - Survey, Visual
label | Inspection: Key - V
label | Inspection: By - SV, SE
checkpoint | 4.1.2 - Drainage Media
label | Standard/Specification - As per three water specification Section 3.3.2
label | Acceptance Criteria - Carefully position drainage media in a clean, excavated area free of contaminants after removing materials. Use the media as embedment around the subsoil pipe, ensuring it is lightly tamped in the bedding zone without mechanical compaction. Avoid placing or lightly compacting drainage media in flooded excavations or saturated in-situ soils.
label | Verifying Document - Photo
label | Frequency - As progress
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - V
label | Inspection: By - SE/PS
checkpoint | 4.1.3 - Subsoil Installation
label | Standard/Specification - As per three water specification Section 3.3.3
label | Acceptance Criteria - Position subsoil pipes centrally in the drainage media layer per specifications and drawings. Avoid laying pipes in flooded or saturated soils; no filter sleeves for perforated pipes. Install pipes parallel to bedding, avoiding ponded water in the swale. Carefully place a minimum of 50 mm of drainage media around the pipe, using it as embedment material without mechanical compaction.
label | Verifying Document - Checksheet,Asbuilt and Photo
label | Frequency - As progress
label | Inspection Type (Visual, other) - Witness,Visual
label | Inspection: Key - V
label | Inspection: By - SE/PS
checkpoint | 4.1.4 - Sand Layer
label | Standard/Specification - As per three water specification Section 3.3.4
label | Acceptance Criteria - Place a 400 mm thick layer of uncompacted sand over the Drainage Media, avoiding compaction with construction equipment. Ensure the subsoil drain is undisturbed, and rake the sand for a level finish.
label | Verifying Document - Photo
label | Frequency - As progress
label | Inspection Type (Visual, other) - Visual, Dimensional
label | Inspection: Key - V,D
label | Inspection: By - SE/PS
checkpoint | 4.1.5 - Soil Media
label | Standard/Specification - As per three water specification Section 3.3.5
label | Acceptance Criteria - Place soil media in a single lift up to 50 mm above the Construction Drawings' finished level for post-construction consolidation. Ensure a smooth, uniform surface, lightly consolidate the soil, and avoid disturbing the subsoil drain. Rectify sediment blinding as directed by the Engineer. Do not exceed 30% moisture content to prevent poor performance. Notify the Engineer for approval; upon acceptance, commence grass sowing within seven days.
label | Verifying Document - Photo
label | Frequency - As progress
label | Inspection Type (Visual, other) - Visual, Dimensional
label | Inspection: Key - V,D
label | Inspection: By - SE/PS
checkpoint | 4.1.6 - Grass Sowing
label | Standard/Specification - As per grass sowing mix
label | ○ Pernnial ryegrass 70%
label | ○ Chewing fescue 25%
label | ○ Brown top 5%
label | Acceptance Criteria - Sow an approved bird-repellent coated grass seed mix at 1 kg/30 m² and fertilize with diammonium phosphate at a minimum rate of 1 kg per 50 m². Aim for a 90% grass strike by the end of the Defects Notification Period, promptly fixing any surface depressions.
label | Verifying Document - Photo, Docket, Mix design
label | Frequency - Per application
label | Inspection Type (Visual, other) - Visual Inspection, Document Review
label | Inspection: Key - R,V
label | Inspection: By - SE/PS
checkpoint | 4.1.7 - In-situ Infiltration Test
label | Standard/Specification - Double ring infiltrometer Test Method
label | Acceptance Criteria - Test reslt > 50 mm/hr as per project spec Test to complete as per project's three water specification Section 3.5.1
label | Verifying Document - Test result, Witness Engineer
label | Frequency - Two test per stormwater swale
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - W
label | Inspection: By - CR, SE/PS
section | 4.2 Subsoil Drain - Installation
checkpoint | 4.2.1 - Subsoil Drain Installation
label | Specification - Downer Standard
label | Acceptance Criteria - Subsoil drains shall be constructed to the lines, levels and dimensions shown on the construction drawings and fully comply with the dimesnional and drawing specifications
label | Verifying Document - Checksheet, Asbuilt and Photo
label | Frequency - Each subsoil drain
label | Inspection Type (Visual, other) - Witness, Visual
label | Inspection: Key - V
label | Inspection: By (Role Key) - SE/PS
section | 4.3 Drainge Pipe - Installation
checkpoint | 4.3.1 - Length of Open Trench
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - The length of open trench shall not exceed the greater of one manhole length or 50m and when offsite this open trench shall be reduced to a maximum length of not more than 10 metres.
label | Verifying Document - Checksheet, Photo
label | Frequency - As progress
label | Inspection Type (Visual, other) - Visual, Dimensional
label | Inspection: Key - V,D
label | Inspection: By - SE/PS
checkpoint | 4.3.2 - Trench Width
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - The minimum trench width shall be 300mm wider than the external diameter of the collar of the pipe being laid, providing the haunching metal is compacted under and at the sides of the pipe.
label | Verifying Document - Checksheet, Photo
label | Frequency - As progress
label | Inspection Type (Visual, other) - Visual, Dimensional
label | Inspection: Key - V,D
label | Inspection: By - SE/PS
checkpoint | 4.3.3 - Trench Subgrade
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Complete Scala testing on the trench Subgrade to a depth of 1m every 10m and when the subgrade changes appearance.
label | Verifying Document - Scala Results
label | Frequency - Every 20 m
label | Inspection Type (Visual, other) - Inspection
label | Inspection: Key - V,D
label | Inspection: By - SE/PS
checkpoint | 4.3.4 - Line and Level
label | Standard/Specification - Project Specification
label | Acceptance Criteria - Pipe inverts shall be laid to ±10mm of the design vertical alignment. Pipes shall be individually aligned to grade. Gravity pipes shall not be laid at a negative grade. Pipe alignments shall be positioned horizontally within the greater of 50mm or 5% of the pipe diameter from the location specified.
label | Verifying Document - Checksheet
label | Frequency - Before backfill
label | Inspection Type (Visual, other) - Visual,Dimensional
label | Inspection: Key - V,D
label | Inspection: By - SE/PS
checkpoint | 4.3.5 - Backfill Placement
label | Standard/Specification - Project Specification
label | Acceptance Criteria - Backfill shall be placed and compacted in layers not exceeding 200mm to 95% of MDD.
label | Verifying Document - NDM Report
label | Frequency - One test every two layers per 50 m
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE/PS
section | 4.4 Manhole - Installation
checkpoint | 4.4.1 - Alignment
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Structures shall be positioned within 50mm horizontally of the location specified. All structures shall be watertight.
label | Verifying Document - Checksheet, Survey
label | Frequency - Each Manhole
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE/PS
checkpoint | 4.4.2 - Drainage Structure Foundation
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Complete Scala test on the subgrade underneath each structure to a depth of 1m
label | Verifying Document - Checksheet,Scala
label | Frequency - Each Structure
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE/PS
checkpoint | 4.4.3 - Drainage Structure Bedding
label | Standard/Specification - Project Specification
label | Acceptance Criteria - Unless specified otherwise, all catchpits, manholes and other stormwater structures shall be founded on a minimum 75 mm bedding.
label | Verifying Document - Checksheet,Photos
label | Frequency - Each Structure
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE/PS
checkpoint | 4.4.4 - Structure Backfill Testing
label | Standard/Specification - Project Specification
label | Acceptance Criteria - Backfill shall be placed and compacted in layers not exceeding 200mm to 95% of MDD.
label | Verifying Document - NDM Report
label | Frequency - One test every two layers per manhole
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE/PS
checkpoint | 4.4.5 - Pipe Penetrations
label | Standard/Specification - Project Specification
label | Acceptance Criteria - Drill holes around the intended cut line before removing the section to create pipe penetrations. Ensure that the diameter of the cutout does not exceed 100 mm beyond the outer diameter of the pipe.
label | Verifying Document - Photo
label | Frequency - Each Structure
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - I
label | Inspection: By - SE/PS
checkpoint | 4.4.6 - Benching
label | Standard/Specification - Project Specification
label | Acceptance Criteria - Construct manhole benching and channelling using 25 MPa concrete. Cast and trowel manhole benching to shape, sloping towards the channel at minimum 1:12 with a U2 finish.
label | Verifying Document - Photo
label | Frequency - Each Structure
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - I
label | Inspection: By - SE/PS
checkpoint | 4.4.7 - Corbels
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Pipes shall be haunched and surrounded with concrete to a minimum distance of 200mm from the outside of the manhole in accordance with the drawings.
label | Verifying Document - Photo
label | Frequency - Each Pipe Entry
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - I
label | Inspection: By - SE/PS
checkpoint | 4.4.8 - Pipe ends
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Pipe ends shall finish approximately 50mm beyond the inside wall and be plastered with cement mortar or encased in benching concrete in accordance with the drawings.
label | Verifying Document - Photo
label | Frequency - Each Pipe Entry
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - I
label | Inspection: By - SE/PS
checkpoint | 4.4.9 - Dewatering
label | Standard/Specification - Project Specification T-WES 00011, Section 3.5
label | Acceptance Criteria - Provide a method statement for controlling water in trenches or dewatering for the Engineers acceptance five days before construction, including:
label | ○ Reasons why the proposed de-watering system has been chosen.
label | ○ Proposed location and details of any well points/spears.
label | ○ Details of back-up power supplies in case there is a power failure.
label | ○ Details of discharging (location(s), volume and flow rate) including environmental controls.
label | ○ A rsk assessment with respect to dewatering affecting adjacent structures.
label | ○ Detrails of how niose standards will be met.
label | Verifying Document - Approved Verification
label | Frequency - Prior to installation
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By - CR/SE
holdpoint | AUTHORITY HOLDPOINT
section | 4.5 Acceptance Testing and Commissioning
checkpoint | 4.5.1 - Pipeline Testing - Acceptance Criteria
label | Standard/Specification - Project Specification, T-WES 00012, Section 4.6.3
label | Acceptance Criteria - Pipelines including laterals shall be tested in accordance with one of the following methods as detailed in AS/NZS 2566.2 Section 6.4:
label | ○ Low Pressure Air Testing
label | ○ Hydrostatic Testing
label | ○ Vacuum Testing
label | Verifying Document - Test Report
label | Frequency - Each Pipline
label | Inspection Type (Visual, other) - Check, Visual
label | Inspection: Key - H
label | Inspection: By - CR, SE/PS
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5.2 - Pipeline Testing - Testing Record Requirements
label | Standard/Specification - Project Specification, T-WES 00012, Section 4.6.4
label | Acceptance Criteria - The Test must be witnessed by the Engineer or their representative. A record of all tests shall be made and forwarded to the Engineer within 24 hours of test completion.
label | (a) Date
label | (b) Full description of section of pipeline being tested, including pipe length, pipe diameter, class and manufacture.
label | (c) Number of sump connections or laterals on the section being tested.
label | (d) Test pressure and acceptance criteria
label | (e) The start time of the test
label | (f) The pressure at the start time
label | (g) Time taken to drop pressure by 2 kPa
label | (h) Minimum and maximum pressure in the test section and water loss over 30 minutes
label | (i) Whether the pipeline passed the test
label | (j) The name and signature of the Contractors personnel responsible for the test
label | (k) The name and signature of the Engineers nominated personnel who witnessed the test
label | Verifying Document - Test Report
label | Frequency - Each Pipline
label | Inspection Type (Visual, other) - Check, Visual
label | Inspection: Key - H
label | Inspection: By - CR, SE/PS
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5.3 - Flexible Pipe Ovality Test
label | Standard/Specification - Project Specification
label | Acceptance Criteria - An ovality test shall be carried out on gravity pipelines in accordance with clause 6.5 of AS/NZS 2566.2 “Buried flexible pipelines – Installation”. The test shall be carried out at least seven days after the pipe surround is laid.
label | Verifying Document - Test Report
label | Frequency - Each Pipline
label | Inspection Type (Visual, other) - Check, Visual
label | Inspection: Key - H
label | Inspection: By - CR, SE/PS
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5.4 - CCTV Inspection
label | Standard/Specification - Project Specification, T-WES 00012, Section 4.6.7
label | Acceptance Criteria - All completed pipelines (excluding laterals and sump connections) are to be inspected using CCTV after backfilling and leak testing is successfully completed, but prior to final surface restoration.
label | ○ The specific requirements for the CCTV inspection are found within clauses (a) to (f)
label | Verifying Document - Test Report
label | Frequency - Each Pipline
label | Inspection Type (Visual, other) - Check, Visual
label | Inspection: Key - H
label | Inspection: By - CR, SE/PS
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5.5 - Manhole Testing
label | Standard/Specification - Project Specification
label | Acceptance Criteria - All manholes (new and refurbished) shall be water tested. Manhole watertightness testing must be witnessed by the Engineer or their representative. A record of all tests shall be made and forwarded to the Engineer within 24 hours of test completion.
label | Verifying Document - Test Report
label | Frequency - Each Pipline
label | Inspection Type (Visual, other) - Check, Visual
label | Inspection: Key - H
label | Inspection: By - CR, SE/PS
holdpoint | AUTHORITY HOLDPOINT
section | 4.6 Portable Water - Installation
checkpoint | 4.6.1 - Trench Foundation
label | Standard/Specification - Project Specification
label | Acceptance Criteria - Shape the foundation for uniform pipe support and alignment. Alert the Engineer if unsuitable trench floor material and await instructions before proceeding with additional work.
label | Verifying Document - Scala Results
label | Frequency - Every 50 m
label | Inspection Type (Visual, other) - Inspection
label | Inspection: Key - V,D
label | Inspection: By - SE/PS
checkpoint | 4.6.2 - Soft Ground faft Foundation
label | Standard/Specification - Project Specification
label | Acceptance Criteria - Refer engineers advise where the foundation fails to meet the design requirments.
label | Verifying Document - Checksheet
label | Frequency - for each event/as required
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - R,V
label | Inspection: By - SE
checkpoint | 4.6.3 - Geotextile
label | Standard/Specification - Project Specification
label | Acceptance Criteria - Geotextiles shall fully wrap raft foundations, in accordance with the manufacturer’s specification, where rafts are required.
label | Verifying Document - Checksheet
label | Frequency - for each event/as required
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 4.6.4 - Embedment Construction
label | Standard/Specification - Project Specification T-WES 00013, 3.1.5
label | Acceptance Criteria - Place and compact all filling materials in layers not exceeding 200 mm compacted thickness. For pipe embedment at least 90% of the maximum dry density (MDD)
label | Verifying Document - NDM Report
label | Frequency - NDM Every 50 m per 200mm of fill
label | Inspection Type (Visual, other) - Inspection
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 4.6.5 - Laying and Jointing of Pipes (1)
label | Specification - Project Specification T-WES 00013, 3.1.6
label | Acceptance Criteria - Lay in straight lines, beginning at the lower end of the line (unless agreed otherwise in writing with the Engineer), and complete each joint before another pipe is laid.
label | ○ Lay all pipe with manufacturing codes and class markings facing upwards.
label | Verifying Document - Checksheet
label | Frequency - Each Pipline
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - Check
label | Inspection: By (Role Key) - SE/PS
checkpoint | 4.6.5 - Laying and Jointing of Pipes (2)
label | Specification - General, Project Specification T-WES 00013, 3.1.1
label | Acceptance Criteria - Submit the proposed methodology for pipe laying, concrete work, jointing and backfilling to the Engineer and obtain acceptance before starting pipe installation.
label | Verifying Document - Approved Verification
label | Frequency - Prior to installation
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By (Role Key) - CR/SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6.6 - Thrust Blocks
label | Specification - Project Specification T-WES 00013, 3.1.12
label | Acceptance Criteria - Unreinforced Concrete Thrust Blocks Precast concrete thrust blocks can only be used where approved by the local authority. Arrange for the Engineer to inspect the first completed thrust block.
label | Verifying Document - Checksheet, concrete test result
label | Frequency - On the first completed thrust block
label | Inspection Type (Visual, other) - Inspection
label | Inspection: Key - H
label | Inspection: By (Role Key) - CR/SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6.7 - Thrust Blocks
label | Specification - Project Specification T-WES 00013, 3.1.13
label | Acceptance Criteria - Reinforced Concrete Thrust Walls / Thrust Blocks
label | ○ All thrust wall steel reinforcement must comply with AS/NZS 4671. Have the Engineer inspect the thrust wall reinforcing and puddle pipe arrangement prior to pouring concrete.
label | Verifying Document - Checksheet, concrete test result
label | Frequency - for each set of blocks pouring
label | Inspection Type (Visual, other) - Inspection
label | Inspection: Key - H
label | Inspection: By (Role Key) - CR/SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6.8 - Flanges
label | Standard/Specification - Project Specification T-WES 00013, 3.1.14
label | Acceptance Criteria - Complete the flange bolting procedure as per project spec and check sheet
label | ○ Have the Engineer witness the first flanged joint completed on the PE 100 pipeline
label | Verifying Document - Check sheet, photo
label | Frequency - First flanged joint completed on the PE 100 pipeline
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By - CR/SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6.9 - Backfill
label | Standard/Specification - Project Specification
label | Acceptance Criteria - AP65 backfill shall be compacted in 200mm loose layers to at least 95% of the maximum dry density (MDD) every 50m.
label | Verifying Document - NDM Report
label | Frequency - NDM Every 50 m per 200mm of fill
label | Inspection Type (Visual, other) - Inspection
label | Inspection: Key - R
label | Inspection: By - SE/PS
section | 4.7 Portable Water - Testing and Commissioning
checkpoint | 4.7.1 - Pressure Test
label | Specification - Project Specification, T-WES 00013, Section 4.5.7.2
label | Acceptance Criteria - Complete the pressure test in accordance with the project specification and the check sheet for pressure test.
label | ○ The system test Pressure (STP) is 1,000 kPa.
label | Verifying Document - Check sheet, photo
label | Frequency - Each major pipelines
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE/PS
checkpoint | 4.7.2 - Pressure Test
label | Specification - Project Specification, T-WES 00013, Section 4.5.3
label | Acceptance Criteria - Before commencing any pressure acceptance test:
label | ○ Give the Engineer at least two working days notice.
label | ○ Provide the Engineer with a detailed work method statement (WMS) with details of how the pressure testing will be carried out at least 10 working days prior to the test, including but not limited to:
label | ○ Proposed equipment to be used, including pump/s, water meters, logging pressure gauge/s, check pressure gauge/s
label | ○ Proposed fill rate, noting the bulk fill must not be greater than the discharge capacity of any air valves and any local authority constraints relating to the supply of water
label | ○ Calibration certificates for meters and pressure gauges
label | ○ Details of qualified personnel who will be carrying out the tests
label | ○ Source/s of water proposed to be used
label | ○ Provision for backflow prevention
label | ○ Location of the pressure test rig and the proposed test pressure at that location if the elevation of the test rig is higher than the lowest part of the test section
label | ○ The test lengths proposed that will ensure that no pipes are over pressurised or inadequately tested
label | ○ Pressure test report template
label | ○ Health and safety risks and mitigation measures
label | Verifying Document - Check sheet, (WMS)
label | Frequency - Prior to pressure testing
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - R
label | Inspection: By (Role Key) - CR/SE
checkpoint | 4.7.3 - Water Main Disinfection
label | Specification - Project Specification, T-WES 00013, Section 5
label | Acceptance Criteria - A resolution with a remaining free available chlorine (FAC) level ranging from 15 to 20 mg/L (ppm). By the conclusion of the disinfection period, the water expelled from the pipelines should retain a minimum FAC concentration of 5 mg/L.
label | Prepare to submit a WMS for disinfection of potable water pipelines to the Engineer for acceptance before commencing disinfection work. The WMS must include (at least) details of:
label | ○ Swabbing all potable water pipes, valves, and other fittings (> DN 63)
label | ○ How the disinfection solution will be introduced with the initial fill water for pressure acceptance testing, if done, Note that this will be at the Contractors risk
label | ○ How the disinfection solution will be prepared and delivered reliably into the pipeline. Include calculations of dosing and flow rates, strength of the proposed liquid or powered form of hypochlorite as well as methods for checking that the required FAC is being achieved
label | ○ How it is proposed to ensure that all watermains, service pipes, valves and fittings will receive nthe disinfection solution
label | ○ How measurement of the FAC during and at the end of the disinfection process will be achieved to ensure that the system has been fully disinfected
label | ○ How the disinfection solution is to be disposed of safely at the end
label | ○ Identified health and safety risks and proposed mitigation measures
label | Verifying Document - Checksheet, (WMS)
label | Frequency - Before commissioning
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - R
label | Inspection: By (Role Key) - SE/PS
checkpoint | 4.7.4 - Flushing of Reconnection
label | Specification - Downer Standard
label | Acceptance Criteria - The Contractor shall open the front outside hose tap, if available, before the supply is reinstated to any premises. Wherever possible, the owner shall be notified prior to this work.
label | Verifying Document - Checksheet
label | Frequency - Each Connection
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - R
label | Inspection: By (Role Key) - SE
section | FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - Construction Record Compilation
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Verifying Document - Closed-out NCR/Defects
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 5.2 - As-built Survey
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Verifying Document - As built survey record completed
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SV
checkpoint | 5.3 - Red-line As-built Drawings
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
label | Verifying Document - Signed As-built Drawings
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE, SV
checkpoint | 5.4 - Defect, Snag and Punch List
label | Inspection Point: Quality Control Activity - Defect, Snag and Punch List
label | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
label | Verifying Document - Register
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - PE
checkpoint | 5.5 - All QA documentation collated & signed-off
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - All signed and closed out
label | Verifying Document - Signed off Documents
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - QM
checklist | 558020-DOW-ITP-PC-0029_v2 (VMS Site) | itp |  |  |  |  | 558020-DOW-ITP-PC-0029_v2 (VMS Site)
section | 3.1 General Preliminary
checkpoint | 3.1.1 - Survey Setout
label | Standard/Specification - Downer
label | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - SV
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Service Location
label | Standard/Specification - Downer
label | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
label | Verifying Document - Service location documents
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.3 - Internal Permits
label | Standard/Specification - Downer
label | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.4 - External Permits
label | Standard/Specification - Downer
label | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.5 - Approved Construction Drawings
label | Standard/Specification - Downer
label | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
section | 3.2 Receiving Materials/Parts - VMS Foundation with Plinth and cabinet pad
checkpoint | 3.2.1 - Concrete mix design
label | Standard/Specification - 30Mpa Structural Concrete
label | Acceptance Criteria - Concrete Mix design for each mix comply with the requirements of the Project Specification
label | Verifying Document - Concrete supplier mix designs
label | Frequency - Submitted to Client Engineer for approval before construction
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.2 - Reinforcement
label | Standard/Specification - As per Design Specification
label | Acceptance Criteria - Reinforcing bars and mesh shall comply with AS/NZS4671:2001.
label | Verifying Document - Mill Certs
label | Frequency - Each Lot
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
section | 3.3 Receiving Materials/Parts - Shoulder Widening and Sealing
checkpoint | 3.3.1 - AP65 - Source Property Tests and Sampling
label | Standard/Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2006, NZS 4407 : 1991, NZS 4402 : 1986
label | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 10,000m3
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.2 - AP65 - Production Property Tests and Sampling
label | Standard/Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2006, NZS 4407 : 1991
label | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Permeability, and Particle Size Distribution.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 3 per source initially, then 1/1000m³
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.3 - AP65 - Testing for Layer Compaction - MDD
label | Standard/Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
label | Verifying Document - IANZ Lab Reports
label | Frequency - 5,000m2
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.4 - AP40 - Source Property Tests and Sampling
label | Standard/Specification - TNZ M/4: 2006 - 3 NZS 4407 : 1991, NZS 4402 : 1986
label | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 10,000m4
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.5 - AP40 - Production Property Tests and Sampling
label | Standard/Specification - TNZ M/4: 2006 - 4 NZS 4407 : 1991
label | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per M/4 Figure 1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 3 per source initially, then 1/1000m³
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.6 - AP40 - Testing for Layer Compaction - MDD
label | Standard/Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
label | Verifying Document - IANZ Lab Reports
label | Frequency - 5,000m2
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.7 - Sealing Chip - Source Property Tests and Sampling
label | Standard/Specification - TNZ M/6: 2019 - 4
label | Acceptance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV
label | Verifying Document - IANZ Lab Reports
label | Frequency - Before Supply and Every 10,000m3 Thereafter
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.8 - Sealing Chip - Production Property Test Sampling
label | Standard/Specification - TNZ M/6: 2019 - 5
label | Acceptance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6
label | Verifying Document - IANZ Lab Reports
label | Frequency - Every 500m3
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.9 - Bitumen - Quality Testing
label | Standard/Specification - NZTA M01: 2022 - 6
label | Acceptance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01.
label | Verifying Document - IANZ Lab Reports
label | Frequency - One test per grade supplied
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.10 - Bitumen - Supply Testing
label | Standard/Specification - NZTA Q05: 2022 - 6.2
label | Acceptance Criteria - The binder shall have benchmark parameter testing completed complying with the requirements of NZTA Q05.
label | Verifying Document - IANZ Lab Reports
label | Frequency - Every 200 tonnes supplied.
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
section | 3.4 Receiving Materials/Parts - Safety Barrier
checkpoint | 3.4.1 - Barrier Mill Certs
label | Standard/Specification - NZTA M23 AS/NZS 3845
label | Acceptance Criteria - Compliance documentation
label | Verifying Document - Mill Certs
label | Frequency - Prior to commencement of works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.4.2 - Concrete mix design
label | Standard/Specification - As per Design Specification
label | Acceptance Criteria - Concrete Mix design for each mix comply with the requirements of the Project Specification
label | Verifying Document - Concrete supplier mix designs
label | Frequency - Submitted to Client Engineer for approval before construction
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
section | 4.1 VMS Foundation with Plinth and cabinet pad - Construction
checkpoint | 4.1.1 - Construction Location
label | Standard/Specification - Design Location
label | Acceptance Criteria - Proposed location of construction to be staked out to the engineer for review prior to construction
label | Verifying Document - Approval letter, Photos
label | Frequency - Prior to each foundation build
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - CR
checkpoint | 4.1.2 - Ground Compaction Test
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Compaction shall achieve a minimum Clegg Impact Value (CIV) of 20 on the first layer and 25 on subsequent layers
label | Verifying Document - Test reults, Location of Test
label | Frequency - For each Foundation
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.1.3 - Reinforcement and Hold Down Bolt Inspection
label | Standard/Specification - As per Design Specification
label | Acceptance Criteria - Handling, Fabrication, Placing and Fixing shall be inspected prior to pouring concrete.
label | Verifying Document - Pre pour, Photos
label | Frequency - Prior to each foundation pour
label | Inspection Type (Visual, other) - Visual Inspection, Dimensional Inspection
label | Inspection: Key - H
label | Inspection: By - CR, SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.4 - Electrical & Comms Ducts Placement
label | Standard/Specification - As per Design Specification
label | Acceptance Criteria - Compliant with the construction drawings
label | Verifying Document - Pre pour, Photos
label | Frequency - Prior to each foundation pour
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - H
label | Inspection: By - CR, SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.5 - Pre-Pour Inspection
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area.
label | Verifying Document - Pre pour, Photos
label | Frequency - Prior to each foundation pour
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - H
label | Inspection: By - CR, SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.6 - Delivery Dockets
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
label | Verifying Document - Dockets
label | Frequency - Each Pour
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 4.1.7 - Compression Testing
label | Standard/Specification - As per Design Specification
label | Acceptance Criteria - One specimen from each pour shall be tested at 28 days.
label | Verifying Document - Test Results
label | Frequency - one test per 50m³/per pour
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 4.1.8 - Post Pour Inspection
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Following the concrete pour, the concrete shall be inspected for Size, Shape, Features, inserts, reliefs, and Finish against the drawings.
label | Verifying Document - Post Pour, Photos
label | Frequency - Each Pour
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 4.1.9 - Defective Concrete Finishes
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer.
label | Verifying Document - NCR
label | Frequency - Prior to minor repair
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - A
label | Inspection: By - SE
section | 4.2 Shoulder Widening and Sealing - Construction
checkpoint | 4.2.1 - Material Placement
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored thoughout
label | Verifying Document - Survey / Level Checks
label | Frequency - Continuous monitoring.
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SV, PS
checkpoint | 4.2.2 - Pavement Shoulder Widening
label | Standard/Specification - Design Specification, Appendix E, Section 2.1.4
label | Acceptance Criteria - Pavement sholder widening treatment will be confirmed with Engineer on site
label | Verifying Document - Approval letter, Photos
label | Frequency - Prior to construction
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - CR
checkpoint | 4.2.3 - Sub-basecourse Pavement Layer Compaction (NDM)
label | Standard/Specification - TNZ B/02: 2005 - 7.6
label | Acceptance Criteria - Mean Value ≥ 95 % of MDD Minimum Value ≥ 92 of MDD
label | Verifying Document - NDM Report
label | Frequency - 1/10m
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.4 - Sub-basecourse Layer thickness
label | Standard/Specification - TNZ B/02: 2005 - 5.1
label | Acceptance Criteria - The Sub-basecourse shall be monitured for Layer thickness. –25 mm +5 mm
label | Verifying Document - Survey / Level Checks
label | Frequency - 1/20m Full width
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - D
label | Inspection: By - SV or SE
checkpoint | 4.2.5 - Basecourse Pavement Layer Compaction
label | Standard/Specification - TNZ B/02: 2005 - 7.6
label | Acceptance Criteria - Mean Value ≥ 98 % of MDD Minimum Value ≥ 95 of MDD
label | Verifying Document - NDM Report
label | Frequency - 1/10m
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.6 - Basecourse Layer thickness.
label | Standard/Specification - TNZ B/02: 2005 - 5.1
label | Acceptance Criteria - The Sub-basecourse shall be monitured for Layer thickness. –5 mm +15 mm
label | Verifying Document - Survey / Level Checks
label | Frequency - 1/20m Full width
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - D
label | Inspection: By - SV or SE
checkpoint | 4.2.7 - Surface Shape
label | Standard/Specification - TNZ B/02: 2005 - 7.7
label | Acceptance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual..
label | Verifying Document - Survey / Straight edge Report
label | Frequency - 1/20m Full width prior to sealing
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - D
label | Inspection: By - SV
checkpoint | 4.2.8 - Surface Finish post sweeping
label | Standard/Specification - TNZ B/02: 2005 - 7.8
label | Acceptance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
label | Verifying Document - Photos
label | Frequency - Prior to sealing
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.2.9 - Preselling Requirements
label | Standard/Specification - TNZ B/02: 2005 - 12
label | Acceptance Criteria - The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 80%.
label | Verifying Document - NDM Report
label | Frequency - 1/10m
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.2.10 - PreSeal inspection
label | Standard/Specification - TNZ P3 TNZ B02
label | Acceptance Criteria - The road shall be reasonably dry before the binder is applied, and no spraying with asphaltic binder shall be carried out when the air temperature measured within the confines of the sealing course is below 10oC in the shade. The Engineer shall be given the opportunity to inspect the site.
label | Verifying Document - Hold point Release, ITP Sign off
label | Frequency - Prior to sealing
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.11 - Spray Temperature
label | Standard/Specification - TNZ P3
label | Acceptance Criteria - The emulsified asphalt may be sprayed at the temperature at which it is received from the manufacturing plant except that no emulsified asphalt shall be sprayed at a temperature in excess of 90oC or below 20oC.
label | Verifying Document - Sealing statement
label | Frequency - Prior to sealing
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - I
label | Inspection: By - SE
checkpoint | 4.2.12 - Chip Application
label | Standard/Specification - TNZ P3
label | Acceptance Criteria - All binder sprayed shall be covered with chips across the full sprayed width, apart from necessary longitudinal laps, within five minutes of spraying.
label | Verifying Document - Sealing statement
label | Frequency - For every spray run
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - I
label | Inspection: By - SE
checkpoint | 4.2.13 - Post Seal Inspections
label | Standard/Specification - TNZ P3
label | Acceptance Criteria - The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed.
label | Verifying Document - Engineers Acceptance
label | Frequency - Prior to TM Removal and After Final Sweeping
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - H
label | Inspection: By - SE, CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.14 - Chipseal Repairs
label | Standard/Specification - TNZ P3
label | Acceptance Criteria - The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used.
label | Verifying Document - Approved Repair Methodology
label | Frequency - Prior to Repairs
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - A
label | Inspection: By - SE
section | 4.3 Guardrail - Installation
checkpoint | 4.3.1 - Guard rails - Location
label | Standard/Specification - Design Specification, Appendix E, Section 2.1.3
label | Acceptance Criteria - The Contractor will set out the guardrail location with the Engineer on site.
label | Verifying Document - Approval letter, Photos
label | Frequency - Prior to construction
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - CR
checkpoint | 4.3.2 - Guard rails - Installation & Checklist
label | Standard/Specification - As per design specification
label | Acceptance Criteria - To complete the check list along with the guard rail installer after the construction
label | Verifying Document - Check Sheet DN-QC-06 Photos
label | Frequency - For each site
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
section | FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - Construction Record Compilation
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Verifying Document - Closed-out NCR/Defects
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 5.2 - As-built Survey
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Verifying Document - As built survey record completed
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SV
checkpoint | 5.3 - Red-line As-built Drawings
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
label | Verifying Document - Signed As-built Drawings
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE, SV
checkpoint | 5.4 - Defect, Snag and Punch List
label | Inspection Point: Quality Control Activity - Defect, Snag and Punch List
label | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
label | Verifying Document - Register
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - PE
checkpoint | 5.5 - All QA documentation collated & signed-off
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - All signed and closed out
label | Verifying Document - Signed off Documents
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - QM
checklist | 558020-DOW-ITP-PC-0030_v1 (Signs and Furniture ITPs) | itp |  |  |  |  | 558020-DOW-ITP-PC-0030_v1 (Signs and Furniture ITPs)
section | 3.1 General Preliminary
checkpoint | 3.1.1 - Survey Setout
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - SV
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Service Location
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
label | Verifying Document - Service location documents
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.3 - Internal Permits
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.4 - External Permits
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.5 - ESCP
label | Standard/Specification - As per contracts
label | Acceptance Criteria - Prior to starting works, Ensure that ESCP plan an approved ESCP by counsil is in place and valid
label | Verifying Document - Approved ESCP plan
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.6 - Approved Construction Drawings
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
section | 3.2 Signage - Incoming Materials
checkpoint | 3.2.1 - General
label | Standard/Specification - NZTA manuals, NZTA P/30
label | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Verifying Document - IFC Drawings, Sheet No. C-2510
label | Frequency - All
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By (Role Key) - SE
section | 4.1 Signage and Marking - General Notes
checkpoint | 4.1.1 - General
label | Standard/Specification - IFC Drawings, Sheet No. C-0300
label | Acceptance Criteria - All signs and markings are to comply with MOTSAM
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.1.2 - General
label | Standard/Specification - IFC Drawings, Sheet No. C-0300
label | Acceptance Criteria - Sign positions are to be agreed with the Engineer on site
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.1.3 - General
label | Standard/Specification - IFC Drawings, Sheet No. C-0300
label | Acceptance Criteria - All redundant road markings to be removed by water blasting. Residue from the water blasting is tobe removed by the contractor.
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.1.4 - General
label | Standard/Specification - IFC Drawings, Sheet No. C-0300
label | Acceptance Criteria - Unless otherwise indicated, all signs and bollards are to have a minimum of 500mm clearance from the kerb face to the edge of the sign/bollard.
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.1.5 - General
label | Standard/Specification - IFC Drawings, Sheet No. C-0300
label | Acceptance Criteria - All road markings are to be a minimum of 300mm from the kerb
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.1.6 - General
label | Standard/Specification - IFC Drawings, Sheet No. C-0300
label | Acceptance Criteria - All existing remaining road markings disturbed by the works are to be reinstated.
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.1.7 - General
label | Standard/Specification - IFC Drawings, Sheet No. C-0300
label | Acceptance Criteria - All existing pavement markings to be reinstated unless approved by principles representative.
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.1.8 - General
label | Standard/Specification - IFC Drawings, Sheet No. C-0300
label | Acceptance Criteria - New line markings to join neatly to existing line marking at limit of works.
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - V
label | Inspection: By - SE
section | 4.2 Signage and Marking - Southbound Approach WIM Site
checkpoint | 4.2.1 - Signs and Markings
label | Standard/Specification - NZTA Manuals, NZTA P/30, IFC Drawings, Sheet No. C-2510
label | Acceptance Criteria - Manual of Traffic Signs and Markings.
label | ○ Part 1: Signs
label | ○ Part 2: Markings
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Dimension Inspection, Visual
label | Inspection: Key - D,V
label | Inspection: By - SV, SE
checkpoint | 4.2.2 - Reflectorised Markings
label | Standard/Specification - NZTA Manuals, NZTA P/30, IFC Drawings, Sheet No. C-2510
label | Acceptance Criteria - Refer to IFC drawings
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Dimension Inspection, Visual
label | Inspection: Key - D,V
label | Inspection: By - SV, SE
checkpoint | 4.2.3 - Raised Pavement Markers
label | Standard/Specification - MOTSAM, IFC Drawings, Sheet No. C-2510
label | Acceptance Criteria - Refer to IFC drawings
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Dimension Inspection, Visual
label | Inspection: Key - D,V
label | Inspection: By - SV, SE
checkpoint | 4.2.4 - No Cycling Signage
label | Standard/Specification - NZTA Manuals, NZTA P/30, IFC Drawings, Sheet No. C-2510
label | Acceptance Criteria - Relocate existing RG24 no bicycles symbol sign
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Dimension Inspection, Visual
label | Inspection: Key - D,V
label | Inspection: By - SV, SE
checkpoint | 4.2.5 - Sign Poles
label | Standard/Specification - NZTA Manual of Traffic Signs, Project Specification, Section 5.4
label | Acceptance Criteria - All poles must be fluted alluminium
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - V
label | Inspection: By - SE
section | 4.3 Signage and Marking - Southbound Approach VMS Site
checkpoint | 4.3.1 - Signs and Markings
label | Standard/Specification - NZTA Manuals, NZTA P/30, IFC Drawings, Sheet No. C-2510
label | Acceptance Criteria - Manual of Traffic Signs and Markings.
label | ○ Part 1: Signs
label | ○ Part 2: Markings
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Dimension Inspection, Visual
label | Inspection: Key - D,V
label | Inspection: By - SV, SE
checkpoint | 4.3.2 - Reflectorised Markings
label | Standard/Specification - NZTA Manuals, NZTA P/30, IFC Drawings, Sheet No. C-2510
label | Acceptance Criteria - Refer to IFC drawings
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Dimension Inspection, Visual
label | Inspection: Key - D,V
label | Inspection: By - SV, SE
checkpoint | 4.3.3 - Raised Pavement Markers
label | Standard/Specification - MOTSAM, IFC Drawings, Sheet No. C-2510
label | Acceptance Criteria - Refer to IFC drawings
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Dimension Inspection, Visual
label | Inspection: Key - D,V
label | Inspection: By - SV, SE
checkpoint | 4.3.4 - Sign Poles
label | Standard/Specification - NZTA Manual of Traffic Signs, Project Specification, Section 5.4
label | Acceptance Criteria - All poles must be fluted alluminium
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - V
label | Inspection: By - SE
section | 4.4 Signage and Marking - Northbound Approach WIM Site
checkpoint | 4.4.1 - Signs and Markings
label | Standard/Specification - NZTA Manuals, NZTA P/30, IFC Drawings, Sheet No. C-2510
label | Acceptance Criteria - Manual of Traffic Signs and Markings.
label | ○ Part 1: Signs
label | ○ Part 2: Markings
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Dimension Inspection, Visual
label | Inspection: Key - D,V
label | Inspection: By - SV, SE
checkpoint | 4.4.2 - Reflectorised Markings
label | Standard/Specification - NZTA Manuals, NZTA P/30, IFC Drawings, Sheet No. C-2510
label | Acceptance Criteria - Refer to IFC drawings
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Dimension Inspection Visual
label | Inspection: Key - D,V
label | Inspection: By - SV, SE
checkpoint | 4.4.3 - Raised Pavement Markers
label | Standard/Specification - MOTSAM, IFC Drawings, Sheet No. C-2510
label | Acceptance Criteria - Refer to IFC drawings
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Dimension Inspection, Visual
label | Inspection: Key - D,V
label | Inspection: By - SV, SE
checkpoint | 4.4.4 - Sign Poles
label | Standard/Specification - NZTA Manual of Traffic Signs, Project Specification, Section 5.4
label | Acceptance Criteria - All poles must be fluted alluminium
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - V
label | Inspection: By - SE
section | 4.5 Signage and Marking - Static Signage
checkpoint | 4.5.1 - During Roundabout Construction
label | Standard/Specification - IFC Drawings, Sheet No. C-7000
label | Acceptance Criteria - Refer to IFC drawing to reference the sign and marking details during the construction of the roundabout.
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Dimension Inspection, Visual
label | Inspection: Key - D,V
label | Inspection: By - SV, SE
checkpoint | 4.5.2 - After Roundabout Construction
label | Standard/Specification - IFC Drawings, Sheet No. C-7001
label | Acceptance Criteria - Refer to IFC drawing to reference the sign and marking details after the construction of the roundabout.
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Dimension Inspection, Visual
label | Inspection: Key - D,V
label | Inspection: By - SV, SE
section | 4.6 Signage and Marking - Commercial Vehicle Safety Centre (CVSC)
checkpoint | 4.6.1 - CVSC - Detailed Plan
label | Standard/Specification - IFC Drawings, Sheet No. C-7011
label | Acceptance Criteria - Refer to IFC drawing to reference the sign and marking details for the CVSC facility.
label | ○ All dimensions and requirements are listed within the Legend of the drawing.
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.6.2 - CVSC - Detailed Plan
label | Standard/Specification - IFC Drawings, Sheet No. C-7012
label | Acceptance Criteria - Refer to IFC drawing to reference the sign and marking details for the CVSC facility.
label | ○ All dimensions and requirements are listed within the Legend of the drawing.
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Dimension Inspection, Visual
label | Inspection: Key - D,V
label | Inspection: By - SV, SE
checkpoint | 4.6.3 - Sign Details and Dimensions
label | Standard/Specification - IFC Drawings, Sheet No. C-7100 and C-7101
label | Acceptance Criteria - - Legend is series E 125 unless stated otherwise
label | ○ Contractor to organise for shop drawings of traffic signs to be in accordance with the Traffic Control Devices manual and manual of Traffic Signs and Road Markings
label | ○ Traffic sign posts to be in accordance with RSMA
label | ○ All measurements are in millimeters unless otherwise stated
label | Verifying Document - Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Dimension Inspection, Visual
label | Inspection: Key - D,V
label | Inspection: By - SV, SE
section | FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - Construction Record Compilation
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Verifying Document - Closed-out NCR/Defects
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 5.2 - As-built Survey
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Verifying Document - As built survey record completed
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SV
checkpoint | 5.3 - Red-line As-built Drawings
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
label | Verifying Document - Signed As-built Drawings
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE, SV
checkpoint | 5.4 - Defect, Snag and Punch List
label | Inspection Point: Quality Control Activity - Defect, Snag and Punch List
label | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
label | Verifying Document - Register
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - PE
checkpoint | 5.5 - All QA documentation collated & signed-off
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - All signed and closed out
label | Verifying Document - Signed off Documents
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - QM