## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | ITP-001
Revision : 1
Client: |  | Department of Transport and Planning |  | Construction Process: Pre-commencement of Works |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Ballarat-Carngham RD & Dyson Drive Intersection Upgrade |  | Specifications: VicRoads Standard Section 160, 166, 167, 168, 176 & IFC Drawings 928RD-06 Rev. 1 04.09.23 |  | Name: | Rakib Hossain | Name: | Hugh Burns |  | Name: | Andrew Cotter
Contract No: |  | Job No. 7FB2020 |  | Structure / Component: Not Applicable |  | Signed : | R.H | Signed : | H.B |  | Signed : | A.C
Date: |  |  |  | Location: Dyson Drive, Alfredton |  | Date : |  | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item No. | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
|  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Construction - General
1.1 | Design Drawings |  | Prior to commencing any activity | Ensure that the most recent copy of the design drawings are used and have been Issued for Construction (IFC). | IFC Drawings | Visual inspection | ITP Signed | IHP | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Service Locating / Permits |  | Prior to commencing any activity | Lodge DBYD application prior to works commence and obtain any relevant permits applicable to the works. DBYD to be renewed every 30 days. All nominated/aﬀected services from the DBYD application must be located/potholed prior to commencement of works. Works identified within the vicinity of the powerlines to ensure distance exclusions are followed & spotter used, if required. | DBYD Information | Visual inspection | ITP Signed | IHP | Site Engineer / Site Foreman | N/A |  | N/A
1.3 | Commencement of work |  | Prior to commencing any activity | The Contractor shall not commence work on site before the following documents have been submitted to the Superintendent and the Superintendent has authorised release of the Hold Point: (a) Public Liability and WorkSafe insurance conforming with the requirements of the General Conditions of Contract (b) Health and Safety Co-ordination Plan (c) Environmental Management Plan for initial works (d) Project Management Plan (e) Quality Management Plan (f) Safety Management Plan | VicRoads Standard Section 160, 166, 167, 168 & 176 | Visual Inspection | ITP Signed | HP | Site Engineer |  |  | N/A
2 | Traffic Management
2.1 | Submission of the TMP to the Superintendent |  | Prior to commencing any activity | The Traffic Management Plan shall not be implemented as a Traffic Guidance Scheme until the Superintendent has completed the review of the final Traffic Management Plan and released this Hold Point. | TMP VicRoads Standard Section 166.08 | Visual Inspection | ITP Signed | HP | Site Engineer |  |  | N/A
2.2 | Detours and Side Tracks (a) Side Tracks (b) Detours |  | Prior to commencing any activity | Traffic shall not be diverted on to any side track until permission to use such side track has been given by the Superintendent. - Permission has been given by the Superintendent and Ballarat City Council. Where VicRoads as well as the Contractor has some responsibility for the restoration of any detours or sidetracks, the Contractor shall not commence any restoration work until the Contractor has submitted details of the work to be undertaken to the Superintendent for review. | VicRoads Standard Section 166.17 (a) & (b) | Inspection | ITP Signed | HP | Site Engineer |  |  | N/A
2.3 | Traffic Management Documentation |  | Prior to commencing any activity | Ensure all TGS plans have been reviewed and deemed acceptable for the project. Obtain MoA approval for any road impacts or closures. | VicRoads Standard Section 166 | Visual Inspection | ITP Signed | IHP | Site Engineer / Site Foreman | N/A |  | N/A
3 | Health and Safety
3.1 | Occupational Health & Safety Management Implementation |  | Prior to commencing any activity | Signed Safe Work Method Statement (SWMS) in place. All personnel including Subcontractors must complete Site Induction prior to arriving on site. | Site Specific SWMS | Inspection | ITP Signed SWMS | IHP | Site Engineer / Site Foreman | N/A |  | N/A
3.2 | Health and Safety Co-ordination Plan and Declaration |  | Prior to commencing any activity | The Contractor shall, not less than 5 working days prior to commencing work, submit to the Superintendent: (a) a reviewed Health and Safety Co-ordination Plan; and (b) a signed HSCP Declaration by an OH&S consultant/advisor that the HSCP meets all the necessary requirements. The Declaration shall be in accordance with the proforma included in the appendices of this Specification. (c) a completed VicRoads HSCP Checklist with Contractor’s responses for each checklist item requirement. | VicRoads Standard Section 168.05 (c) | Submission | ITP Signed Safety Management Plan | HP | Site Engineer |  |  | N/A
4 | Environmental Management
4.1 | Environmental Impacts, Aspects & Risk Assessment Implementation |  | Prior to commencing any activity | All environmental controls implemented in accordance with the Contract Environmental Impacts, Aspects & Risk Assessment. | EMP & A&I | Visual Inspection | ITP Signed | IHP | Site Engineer / Site Foreman | N/A |  | N/A
4.2 | Environmental Management Plans |  | Prior to commencing any activity | The Contractor shall submit to the Superintendent for review an Environmental Management Plan not less than 2 weeks prior to the commencement of work. Work shall not commence until: - the Superintendent is satisfied that the Plan meets the requirements of this specification; and - the controls detailed in the Plan are implemented; and - the Superintendent has authorised release of the Hold Point. - Limit of works identified in applicable SWMS. | VicRoads Standard Section 176.A3 VicRoads Standard Section 177.A3 | Submission | EMP ITP Signed | HP | Site Engineer/Superintendent |  |  | N/A
4.3 | Flora and Fauna |  | Prior to commencing any activity | Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the Superintendent and other relevant authorities to conﬁrm and clearly identify and mark trees, vegetation or habitat to be removed. Any removal shall be consistent with the Contract drawings and any relevant permits and shall fence and sign all sites nominated as No-Go Zones. | VicRoads Standard Section 176.I1 VicRoads Standard Section 177.I1(c) | Visual Inspection | ITP Signed Relevant permits No Go Zone Signage | HP | Site Engineer |  |  | N/A
4.4 | Erosion and Sediment Control |  | Prior to commencing any activity if applicable | The Contractor shall provide the necessary environmental controls as nominated on the approved Environmental Management Plan and identified on site. | VicRoads Standard Section 177.D1(c) | Visual Inspection | ITP Signed | IHP | Site Engineer / Site Foreman | N/A |  | N/A
5 | Stakeholder and Community Engagement
5.1 | Residents have been informed |  | Prior to commencing any activity | Residents impacted by construction works are to be notified by letter drop of the construction taking place, the timeframe of the works and information on how the works will affect them. | Letterdrop | Visual Inspection | ITP Signed | HP* | Site Engineer | N/A |  | N/A
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
IHP | Internal Hold Point | Work shall not proceed past the IHP until released by Fulton Hogan |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent