## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | FC - R - Scaffold Drop Checklist |  |  |  |  | Yes | FC - R - Scaffold Drop Checklist | 001bbbe1-4fc6-45fc-aabc-d9773f411f9f
checkpoint-group |  |  | section | Brickwork
checkpoint-status |  |  | checkpoint | Weep holes installed.
checkpoint-status |  |  | checkpoint | Weep holes clean of mortar.
checkpoint-status |  |  | checkpoint | Vent holes installed.
checkpoint-status |  |  | checkpoint | Vent holes clear of mortar.
checkpoint-status |  |  | checkpoint | Mortar finish acceptable – no holes.
checkpoint-status |  |  | checkpoint | Mortar acceptable around vents.
checkpoint-status |  |  | checkpoint | Clean Lintel Cavity.
checkpoint-status |  |  | checkpoint | Vent holes full brick.
checkpoint-status |  |  | checkpoint | No damage to bricks.
checkpoint-status |  |  | checkpoint | Seals completed Nib / Brick. Soffit / Brick.
checkpoint-group |  |  | section | Sto
checkpoint-status |  |  | checkpoint | Seals completed Nib / Brick.
checkpoint-status |  |  | checkpoint | Sto finish good ( not damaged.)
checkpoint-status |  |  | checkpoint | Paint standard acceptable
checkpoint-status |  |  | checkpoint | Soffits complete
checkpoint-group |  |  | section | Windows
checkpoint-status |  |  | checkpoint | Windows are clean
checkpoint-status |  |  | checkpoint | Railside's sealed (good seal)
checkpoint-status |  |  | checkpoint | Transom rubber caps installed (not loose)
checkpoint-group |  |  | section | Misc
checkpoint-status |  |  | checkpoint | Downpipes installed
checkpoint-status |  |  | checkpoint | Roof capped & fascia installed
holdpoint |  |  | signoff | Raise remedial / Request Sign Off
checklist-flat |  |  | checklist | CST - R - Fitout Consent |  |  |  |  | Yes | CST - R - Fitout Consent | 0186fa23-ba08-4aa3-a69e-2bc31ff3e538
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP records
checkpoint-status |  |  | checkpoint | Waterproofing
boolean | d5d06565-4e2c-59cc-bf4d-c116e6d91e74 |  | tickbox | Producer Statement Construction(PS3): Waterproofing Membrane
boolean | 63d2ad78-0ec8-5882-9aa4-41970ba30692 |  | tickbox | Manufacturer's warranty for waterproofing membrane
checkpoint-status |  |  | checkpoint | Surface Coatings
boolean | 06dff091-821c-5db3-9d18-f5b95756ce7d |  | tickbox | Producer Statement Construction(PS3): surface finishes complying with (material categories 1-3 – NZBC clause C3.4(a)
boolean | 36668b04-7f44-5bec-b2cc-c4ebd920bc72 |  | tickbox | Producer Statement Construction(PS3): floor surface materials complying with (NZBC clause C3.4(b))
checkpoint-status |  |  | checkpoint | Acoustic testing
boolean | 8d09252a-b301-56fa-90ff-fcb10201b438 |  | tickbox | Report/Test certificates from council approved acoustic engineer confirming compliance with NZBC G6
checkpoint-status |  |  | checkpoint | Balustrades
boolean | 55e65961-9434-5c6a-8363-97a6868de9ea |  | tickbox | Producer Statement Construction(PS3) for balustrade installation
checkpoint-status |  |  | checkpoint | Producer Statement Construction(PS3) for proprietary products
checklist-flat |  |  | checklist | PRE - R - Fire Penetration |  |  |  |  | Yes | PRE - R - Fire Penetration | 0246ad21-2668-45d7-8599-0a3c686eca25
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Edge Beams Installation completed and acceptable
checklist-flat |  |  | checklist | ITP - R - On Grade Slab Foundation Construction (per area) |  |  |  |  | Yes | ITP - R - On Grade Slab Foundation Construction (per area) | 0a32e2c6-1506-43f9-9aad-fd4431b5ae0f
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Survey set out (height, location, setout) - confirmation attached.
checkpoint-status |  |  | checkpoint | Underground services installation completed
checkpoint-status |  |  | checkpoint | Backfilling completed
checkpoint-status |  |  | checkpoint | Waterproofing completed
checkpoint-status |  |  | checkpoint | DPM overlapping/taping with no tears or perforations. Council requirement
checkpoint-status |  |  | checkpoint | Reinforcing completed
checkpoint-status |  |  | checkpoint | Engineer sign off completed and approved for pour
button | f0e66d2f-6c11-564b-8f11-569b9ff3c253 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved for pour
button | d8ef7d6c-0c8f-57ba-8561-fa3002b8db5e |  | button | Note remedial work needed | None, Minor, Major
text | 66bb35c3-7f65-5d66-b8a9-7190d0da855a |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checklist-flat |  |  | checklist | ST - R - Precast Edge Beams Installation |  |  |  |  | Yes | ST - R - Precast Edge Beams Installation | 0a8bb564-ff5b-4f8e-a92a-3095414d854f
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Edge Beams Installation completed and acceptable
checklist-sectioned |  |  | checklist | ITP - R - Apartment Pre Cast, Timber, Insuti , Blockwork Element Installation (per area/level) |  |  |  |  | Yes | ITP - R - Apartment Pre Cast, Timber, Insitu, Blockwork Element Installation (per area/level) | 0b1e3b8e-2156-40c7-ae67-40454310f4c3
checkpoint-group |  |  | section | Pre-Cast Elements
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Pre-cast elements inspected upon delivery and accepted for lifting.
checkpoint-status |  |  | checkpoint | Installed vertically / aligment tolerances complies with specification (components below)
checkpoint-status |  |  | checkpoint | Stairs
checkpoint-status |  |  | checkpoint | Spandrels
checkpoint-status |  |  | checkpoint | Pre-cast panels
checkpoint-status |  |  | checkpoint | Columns
checkpoint-status |  |  | checkpoint | Stitch joints
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 1be11c07-fc66-5036-a9ab-8631b9978ad1 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 7af388fc-1735-52d1-87b4-bb2af3386446 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 27913cd9-d72a-56ca-befa-93480d7ca3c7 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Timber Framing Elements
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Timber Framing installed
button | 94d35135-5c6c-50c8-a39d-643ae044a465 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 18b10817-9fc8-52e0-be30-2b4418d43303 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | a24bed06-d99a-5bc7-9c19-a687099b735e |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 4cb407e1-1596-552d-9d03-52fd4e4b164a |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Insuti Pour Elements
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Stitch joints - meets specification
checkpoint-status |  |  | checkpoint | Beams - meets specification
checkpoint-status |  |  | checkpoint | Panels - meets specification
checkpoint-status |  |  | checkpoint | Columns - meets specification
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 5a5a1af9-8dbb-5e7f-8e5b-2de010aa20b3 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 4331304e-8f0f-55ca-83f2-da8085bae5c1 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 6683db46-9251-557c-81b8-2bdbabfc00c7 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Reinforced Blockwork Elements
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Blockwork - meets specification
checkpoint-status |  |  | checkpoint | Reinforcing - meets specification
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 509e1a56-82f5-5412-8902-317a796d986e |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 61ac4ede-547d-5254-abec-c697a69a3a62 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | b6587f4d-d2d5-56ce-84b7-1bd7f76f2907 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Testing
checkpoint-status |  |  | checkpoint | Chemical anchor testing completed. Upload report
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
text | 537115b4-d16d-59bc-b593-c9945f0c4b1f |  | textbox | Record sample size
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Concrete Documentation
checkpoint-status |  |  | checkpoint | Concrete pour planning completed with subcontractor
text | f372b153-3461-5295-80b7-f04dee50d16b |  | textbox | Date of pour
text | 99d0ff77-242b-56f8-9369-b7700e2f739d |  | textbox | Specified concrete strength:
text | 2e8b0361-c987-5b52-91f1-f2f8e2b8b16a |  | textbox | Concrete strength ordered:
text | fccbda79-00f8-59e2-b5ba-33e1e92f8f19 |  | textbox | Concrete quantity ordered:
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checklist-flat | bcdbac8d-7406-48ab-abd8-3229b6ed3878 |  | checklist | Code of Compliance (CCC) - |  |  |  |  | Yes | Add Council CCC Upload Checklist | 0da7c982-54b4-4d43-a8df-9cf541d44c9e
checkpoint-status | 5b3bfeed-466c-4aa7-bc3d-b9ce0b73251e |  | checkpoint | Final CCC (approved & attached)
checklist-flat |  |  | checklist | FC - R - Soffits |  |  |  |  | Yes | FC - R - Soffits | 122328f8-2ca4-44d8-9dc5-79bb10da2f93
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Soffit works completed and acceptable
checklist-flat |  |  | checklist | FC - R - Flashing installation |  |  |  |  | Yes | FC - R - Flashing installation | 12c9619e-3630-49cb-b3fe-092d56757783
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Flashing installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - Exterior Tiling |  |  |  |  | Yes | FC - R - Exterior Tiling | 130bc84b-74c8-4228-9dd6-97c1fa568cf3
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Exterior Tiling works completed and acceptable
checklist-sectioned |  |  | checklist | ITP - R - Pipe Laying (Mains Water, Storm and Waste) |  |  |  |  | Yes | ITP - R - Pipe Laying (Mains Water, Storm and Waste) | 166963db-ad86-4c37-a0b5-58307137fa95
checkpoint-group |  |  | section | Main Water
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Set-out completed
checkpoint-status |  |  | checkpoint | Excavation
checkpoint-status |  |  | checkpoint | Ground conditions
checkpoint-status |  |  | checkpoint | Bedding
checkpoint-status |  |  | checkpoint | Pipework
checkpoint-status |  |  | checkpoint | Levels and Gradients
checkpoint-status |  |  | checkpoint | Backfill
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 9dda8b15-fd32-590f-bead-b95461d59402 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 8dda2b4b-1bf4-5286-9fef-d2d29e1f6d57 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | ad657497-3a7d-5ec3-898b-4ccaeee8d170 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Storm Water
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Set-out completed
checkpoint-status |  |  | checkpoint | Excavation
checkpoint-status |  |  | checkpoint | Ground conditions
checkpoint-status |  |  | checkpoint | Bedding
checkpoint-status |  |  | checkpoint | Pipework
checkpoint-status |  |  | checkpoint | Levels and Gradients
checkpoint-status |  |  | checkpoint | Backfill
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 7473ba5e-bc33-5a58-8506-b47d2f520a62 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | b4993fd4-2513-596b-a8a1-a63c7e16f83b |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | a7a0c72a-785e-5d40-a698-642ab867c330 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Waste Water
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Set-out completed
checkpoint-status |  |  | checkpoint | Excavation
checkpoint-status |  |  | checkpoint | Ground conditions
checkpoint-status |  |  | checkpoint | Bedding
checkpoint-status |  |  | checkpoint | Pipework
checkpoint-status |  |  | checkpoint | Levels and Gradients
checkpoint-status |  |  | checkpoint | Backfill
checkpoint-status |  |  | checkpoint | Air/water test completed
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | d1a07d63-28fb-55e1-8da4-1f39e5a9c049 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 661741df-b159-51f5-9da7-a31684aeefd7 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | c6386f50-d06e-50e7-98d8-ee440839eb73 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-flat |  |  | checklist | CST - R - Structural Consent |  |  |  |  | Yes | CST - R - Structural Consent | 16f749d1-02f5-4328-9273-87dbc0786708
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Pre-cast concrete
boolean | 868d39fc-77a6-5231-8237-2e56c06ddd1d |  | tickbox | Producer Statement Design(PS1): Prestressed beams, walls, stairs, columns and floor units
boolean | ae759039-6410-5e4b-a24e-d410225fe1a0 |  | tickbox | Producer Statement Construction(PS3): Prestressed beams, walls, stairs, columns and floor units
boolean | 6ea6f50a-c605-509e-9c39-9ee19d94ead4 |  | tickbox | Producer Statement Review(PS4): Prestressed beams, walls, stairs, columns and floor units
checkpoint-status |  |  | checkpoint | Structural Steel
boolean | 96744209-dae4-5455-a495-5a35071cca77 |  | tickbox | Producer Statement Construction(PS3): Corrosion Protection
boolean | 7c7e8ee7-9322-59a3-862c-b13546dd60bc |  | tickbox | ITPs approved by structural engineer
boolean | cd0daadf-c20f-55c2-b82b-d46a18c00807 |  | tickbox | weld inspection and test records
checkpoint-status |  |  | checkpoint | Fire rated (Intumescent) Coatings to Structural Steel
boolean | 25e31d9e-6aac-51a7-838f-7edbf2815023 |  | tickbox | Producer Statement Construction(PS3 - AC2334): Intumescent coatings to structural steel from approved applicator
boolean | be7be6e9-ec44-580c-b6c3-bdffa7f72aed |  | tickbox | Suppliers material schedule - products used and thicknesses applied
boolean | c8118423-c591-504d-8472-693b91cd9b96 |  | tickbox | Floor plan of intumescent coating locations
checkpoint-status |  |  | checkpoint | Trusses
boolean | ab8a391a-4435-58a0-aca6-1027513b3ea0 |  | tickbox | Producer Statement Design(PS1): Layout Plan for timber roof trusses
boolean | 751a3579-9bdc-5beb-b2e1-3bc25caffbbb |  | tickbox | Producer Statement Construction(PS3): for timber roof trusses
checkpoint-status |  |  | checkpoint | Construction Review (Structural)
boolean | af8014ab-2439-5e93-8c06-46c3adcf4e94 |  | tickbox | Producer Statement Construction Review(PS4): Certification of work in accordance with design, drawings, specifications and material codes
boolean | e7189543-3fd9-5cb0-8f94-3add17c170f4 |  | tickbox | Producer Statement Construction Review(PS4): excavation near boundary and site observation notes
boolean | e2a1ee2b-7de2-531f-ae9c-28ae12d40f0b |  | tickbox | Producer Statement Construction Review(PS4): Raft slab and site observation notes
boolean | f7f86804-aba7-578a-a0f7-ab0c125bde84 |  | tickbox | Producer Statement Construction Review(PS4): Swimming pool and site observation notes
boolean | 1d264176-d393-5853-9f70-942b9fdebe5f |  | tickbox | Producer Statement Construction Review(PS4): Type A or B masonry and site observation notes
boolean | 034155fa-2c91-57b8-83ec-44b7b7abc495 |  | tickbox | Producer Statement Construction Review(PS4): Underpinning and site observation notes
boolean | f6d51be8-4f0d-5bc2-8fee-49404127d2a5 |  | tickbox | Producer Statement Construction Review(PS4): Structural steel including connections and site observation notes
boolean | cdaaac0e-5c49-5883-8e34-876a704387e7 |  | tickbox | Producer Statement Construction Review(PS4): Timber pole retaining wall and site observation notes
boolean | b8018783-9ff7-5baa-8a83-1fb31614deb4 |  | tickbox | Producer Statement Construction Review(PS4): reinforced concrete foundations and site observation notes
boolean | 46a2cf41-67f7-5853-a1e6-80999d083920 |  | tickbox | Producer Statement Construction Review(PS4): Suspended concrete slab and site observation notes
boolean | 6169310d-652c-5ed1-947b-492f71846d2f |  | tickbox | Producer Statement Construction Review(PS4): Precast elements and site observation notes
boolean | bb82bb78-0ac5-5eae-b937-73f6abf52b1d |  | tickbox | Structural engineer's variations and contractor advice notes
checkpoint-status |  |  | checkpoint | Surveyor certificate for finished floor levels
checklist-flat |  |  | checklist | C - R - Connection to public systems |  |  |  |  | Yes | C - R - Connection to public systems | 17f416ab-1f9b-4e73-8231-3a3ea66faee6
checkpoint-status |  |  | checkpoint | Approval to connect given by relevant Authority (AC, Watercare, Vector, etc)
checkpoint-status |  |  | checkpoint | Area signed off by engineer
checkpoint-status |  |  | checkpoint | Pipe line connected in accordance with requirements, checked and accurate
checklist-flat |  |  | checklist | ST - R - Precast beam installation |  |  |  |  | Yes | ST - R - Precast beam installation | 186a67c3-b70b-4de6-aa65-d8098b770ac3
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Anchor point installation completed and acceptable
checklist-sectioned |  |  | checklist | ITP - R - Apartment Pre Cast Floor Structure and Concrete Pour (per level/area) |  |  |  |  | Yes | ITP - R - Apartment Pre Cast Floor Structure and Concrete Pour (per level/area) | 233f26e1-b5ae-4027-b587-7b808e236e35
checkpoint-group |  |  | section | Pre Commencement
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
button | 01b368c9-d59a-5f01-a7d7-b04b61ece147 |  | button | Confirm construction method | Double T's, Rib & Infill, Post Tensioned, Other
text | b3c589b1-91b6-5962-b314-91756795b0bf |  | textbox | Other details:
button | 96551a32-4a52-5816-ab6c-ce4decc964aa |  | button | Propping layout confirmed as "issued for construction" | Yes, N/A
checkpoint-status |  |  | checkpoint | Propping/Falseworks Confirmed and Accepted. Evidence required.
button | 1e933e1e-a262-5e9a-9c38-6db0304eb6a4 |  | button | Floor area cleared for propping to be erected | Yes, N/A
checkpoint-status |  |  | checkpoint | Hogging of panels within design tolerances. Installed in accordance with suppliers recommendations.
checkpoint-status |  |  | checkpoint | Adequate identification, cast date and verification of inspection marked on precast element.
checkpoint-group |  |  | section | Pre Cast Element Installation
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Hogging of panels within design tolerances. Installed in accordance with suppliers recommendations.
checkpoint-status |  |  | checkpoint | Adequate identification, cast date and verification of inspection marked on precast element.
checkpoint-status |  |  | checkpoint | Pre-cast elements inspected upon delivery and accepted for lifting.
checkpoint-status |  |  | checkpoint | Floor structure elements landed as per layout
checkpoint-status |  |  | checkpoint | If Rib and Infill, Ryman SOP followed where applicable. (Reference the document name / version)
checkpoint-status |  |  | checkpoint | Reinforcing laid as per specification
checkpoint-status |  |  | checkpoint | Service penetrations present as per specification
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved for pour
button | 5033e767-dc08-5637-b710-7b46aafea2db |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | b83c2f48-5b8b-5d61-af0c-237979cb07f7 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Post Tensioned Floor Construction
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Stressing access correct
checkpoint-status |  |  | checkpoint | Tensioning strands quantity, length, and size correct.
checkpoint-status |  |  | checkpoint | Tendons quantity, size, and spacing correct
checkpoint-status |  |  | checkpoint | Tendon profiles (highs and lows and edges) correct
checkpoint-status |  |  | checkpoint | Antiburst are located at the correct position on the tendon
checkpoint-status |  |  | checkpoint | Grout Tubes height above concrete surface, quantity, and location correct
checkpoint-status |  |  | checkpoint | Pans and pan trimmers, anchorages, antiburst
checkpoint-status |  |  | checkpoint | Reinforcing laid as per specification
checkpoint-status |  |  | checkpoint | Service penetrations present as per specification
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved for pour
button | c47c3013-b46b-5808-8982-37b9378dd13e |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 827c8e6d-667a-58ab-aa5d-a20cae6732ec |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Pre Pour Planning
checkpoint-status |  |  | checkpoint | Concrete pour planning completed with subcontractor
text | 1db40d47-2ee8-5cff-adcc-8a1fe85134e3 |  | textbox | Date of pour
text | 3ac7fb2d-09e1-5c14-84fb-7e49623f22f8 |  | textbox | Specified concrete strength:
text | 64d8a3f5-5b7c-52eb-94ca-a530e0ca5adb |  | textbox | Concrete strength ordered:
text | f0efaa14-61b3-500d-a7ba-803ed32e0353 |  | textbox | Concrete quantity ordered:
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | fb2a5c94-f501-5e4a-ba98-1d2e126fba54 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Request to pour received and approved
checkpoint-status |  |  | checkpoint | Reinforcing meets specification
checkpoint-status |  |  | checkpoint | Service penetrations present and correct
checkpoint-status |  |  | checkpoint | Waterproofing elements present and correct
checkpoint-status |  |  | checkpoint | Couplers present and correct
checkpoint-status |  |  | checkpoint | Control joints/ stop ends installed accurately and correctly braced
checkpoint-status |  |  | checkpoint | Engineer Inspection conducted and passed
button | 1e2d7b35-c04a-529e-8ade-a35ad1f37e75 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | d25d0665-ca5d-5838-9745-09d7d43a4d72 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Post Pour (Post Tensioned Floor Only)
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Initial Tension applied [when concrete strength 9MPa (min) initial stress- 21% of UTS]
checkpoint-status |  |  | checkpoint | Final Tension applied [when concrete strength 22MPa (min) final stress- 80% of UTS]
checkpoint-status |  |  | checkpoint | Cutting of strands and sealing of pockets completed
checkpoint-status |  |  | checkpoint | Grouting completed as per specification and tubes clear
checkpoint-status |  |  | checkpoint | Engineer Inspection conducted and passed
button | f36bc263-ef2e-56f1-91de-f642284e6d1b |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | f4b3f6cf-a296-5f95-8c29-d25db0a47bd8 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-flat |  |  | checklist | F - R - Crane Piling |  |  |  |  | Yes | F - R - Crane Piling | 244259de-4e4b-4d7c-b3e2-c541473fa7ef
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Crane Piling completed and acceptable
checklist-sectioned |  |  | checklist | Pour: |  |  |  |  | Yes | ST - R - Concrete Pour - Ryman Owned | 24bdefac-513f-4e97-b3ab-058f7c154dda
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour details entered
text | ccea959f-390a-5fe6-b67d-81eb598410e3 |  | textbox | Area to be poured:
text | 2bb5f321-af14-5085-a5db-d04d2fe4e2b9 |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork and Embedded Items
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
checkpoint-status |  |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
boolean | 16d0cab2-e481-5e4c-9a60-57dd8cbfe5f4 |  | tickbox | Appointment with the engineers confirmed (Enter date & time of the appointment)
boolean | 96b8fcdd-055e-5065-824d-5116631380c0 |  | tickbox | Reidbar – coupler and flange nut installations are inspected by the MV Engineer
checkpoint-status |  |  | checkpoint | IMBMS couplers testing carried out for Village Podiums in the form of tensile testing in accordance with NZS3101.1.2006 and results acceptable
checkpoint-status |  |  | checkpoint | All starter bars are installed correctly (location, size and spacing )
checkpoint-status |  |  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Welding certificates sited and attached
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Relevant service requirements completed (locations checked and accurate)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint-status |  |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-status |  |  | checkpoint | Concrete Supplier details entered
text | c3745c52-3681-5218-b504-7947e2f3a105 |  | textbox | Supplier Name:
text | aedf8736-35a7-52ca-908c-eba11f56f52d |  | textbox | Specified concrete strength: |  |  | mPA
text | 102f9ce8-61a8-5faf-9081-b99038e92b75 |  | textbox | Concrete strength ordered: |  |  | mPA
text | 97b5575a-eb72-50fc-b6da-9f6445097f6b |  | textbox | Concrete quantity ordered: |  |  | m3
button | 5d1c1f4c-70bf-5ccd-bbdd-372f3bc5179f |  | button | Test blocks booked | Yes, No, N/A
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-group |  |  | section | Placement Method
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint-status |  |  | checkpoint | Heights and falls checked/confirmed before placement
button | 189271a5-0c08-5312-af24-8f8996168f83 |  | button | Is the cover correct to specification | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise remedial/ Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist-sectioned |  |  | checklist | ST - R - Rib & Infill Installation |  |  |  |  | Yes | ST - R - Rib & Infill Installation | 25002141-12f4-41e0-a87d-8e32eec7ffc5
checkpoint-group |  |  | section | Pre-commencement
checkpoint-status |  |  | checkpoint | Rib lifting plan confirmed, correct chains and hooks verified.
checkpoint-status |  |  | checkpoint | Propping layout confirmed as "issued for construction" with contractor and attached.
checkpoint-status |  |  | checkpoint | Floor area cleared for propping to be erected.
checkpoint-status |  |  | checkpoint | Rib grid layout confirmed with contractor and drawing attached.
checkpoint-status |  |  | checkpoint | Ryman Infill Installation SOP obtained and reviewed. Record version number below. Click PASS to confirm
text | c6c7fa82-7e9c-5c68-b9d4-d2bce98c216c |  | textbox | Version number
checkpoint-status |  |  | checkpoint | Subcontractor SWMS obtained and reviewed against Ryman SOP.
checkpoint-status |  |  | checkpoint | Variations to the SOP are proactively assessed and managed with the subcontractor accordingly. Record personnel involved below. Respond N/A if no variation to Ryman SOP is identified.
text | c7575ae4-5eab-5fea-8b8f-67c8efe3a785 |  | textbox | Name/s of personnel
checkpoint-status |  |  | checkpoint | Upload a copy of the subcontractor SWMS document. PASS this checkpoint when uploaded.
checkpoint-status |  |  | checkpoint | Approval to proceed given.
checkpoint-group |  |  | section | Rib Installation
checkpoint-status |  |  | checkpoint | Rib inspection results received from the contractor
checkpoint-status |  |  | checkpoint | Ribs placed as per layout.
checkpoint-status |  |  | checkpoint | All ribs visually supported as per plan, no visual damage. Ready for infill panels.
checkpoint-group |  |  | section | Infill Panel Installation
checkpoint-status |  |  | checkpoint | Infill panel inspection results received from the contractor
checkpoint-status |  |  | checkpoint | Infill boards constructed as panels, including 'backbone', 6 to 10 boards in length and fitted tightly between the ribs
checkpoint-status |  |  | checkpoint | Infill panel adjacent ends are joined, locked with timber blocks to prevent lateral movement, and secured to wall supports
checkpoint-status |  |  | checkpoint | Handrails installed on all edges (top of slab)
checkpoint-status |  |  | checkpoint | All penetrations closed or exclusions in place
checkpoint-status |  |  | checkpoint | Pass to indicate agreement to proceed to lay reinforcing.
checkpoint-status |  |  | checkpoint | No obvious visual defects on infill boards, no knots, no cracks or other weakness across 25% of the width.
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | All propping below timber infill complete
checklist-flat |  |  | checklist | FC - R - Balconies |  |  |  |  | Yes | FC - R - Balconies | 26d1516d-dd2d-4da7-9813-cd76c604a6ad
checkpoint-status |  |  | checkpoint | Waterproofing and flashing checked and acceptable
checkpoint-status |  |  | checkpoint | All screed to nib and deck falls checked and accurate
checkpoint-status |  |  | checkpoint | Soffit Checked and accurate
checkpoint-status |  |  | checkpoint | Flood test completed and acceptable
checkpoint-status |  |  | checkpoint | Installation of deck tiles completed and acceptable
checkpoint-status |  |  | checkpoint | All works on balcony are completed to required specification.
checklist-flat | 1351b651-cc0c-426d-b23b-e141606d0668 |  | checklist | Minor Variation - |  |  |  |  | Yes | Add Council Minor Variation Checklist | 282a1e14-6837-4dd6-998f-5bfef416fc39
checkpoint-status | 4a44e985-0c05-48b5-9b22-fa7edcd9ffe7 |  | checkpoint | Minor variation status (Pass once approved & all information is attached including observations, correspondence & close out evidence)
label | d83c76ad-c2c4-422a-b3d0-5e46ac4be24f |  | note | PASS above checkpoint when variation is approved
label | ab21c4bc-c773-43ee-88d7-f338c674ee92 |  | note | If minor variation is a FAIL - document why below and follow appropriate corrective actions
text | e716f58a-4420-4e11-91ae-f4fef0f7ba87 |  | textbox | Date of application
text | 6931f74e-964b-42b5-905c-440c2ce0001a |  | textbox | Reason for application
text | 4ce69a81-cba4-4eac-b963-ff28392bbaf5 |  | textbox | Date of approval / acceptance
text | 78d9159e-0896-4188-a542-fa6b1bf43aaa |  | textbox | Inspection Type Code (If applicable e.g. Site meeting IME)
boolean | d24858c1-85f5-44b8-99c0-818a707a7f19 |  | tickbox | Council approval of minor variation attached
checklist-flat |  |  | checklist | C - R - Demolition |  |  |  |  | Yes | C - R - Demolition | 28ec2cc8-e8a0-42e6-a5eb-640f5cb47e81
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Demolition completed and acceptable
checklist-sectioned |  |  | checklist | I - C - MV Consultant Site Visit Report |  |  |  |  | Yes | I - C - MV Consultant Site Visit Report | 29ae9a15-9dc9-4f87-9c07-6732236c9289
checkpoint-group |  |  | section | Site Inspection Details
checkpoint-status |  |  | checkpoint | All Site Details Inputted Below
text | 906501af-763a-572d-81e5-f8afe387fba4 |  | textbox | Building Consent No.
text | fa9a8e41-0db7-53b2-8b07-4396f30bf660 |  | textbox | Date site visit occurred
text | c714a644-f383-5698-a9e8-a257c65823d6 |  | textbox | Time on site (include start and end times)
text | b1ccbe67-8226-5b0e-b2e9-8c4097b0040a |  | textbox | Report prepared by - Engineer's name
text | ea672b01-08dd-56a1-83b1-33e3c1afdaed |  | textbox | Additional personnel accompanying engineer
button | 6ee27010-0e1f-5248-bdf8-1b0eed5463ab |  | button | Has contractors pre-inspection QA been reviewed? | Yes, No
label | 5be78f87-783d-5b53-83a0-d5b8fca376f1 |  | note | Select "Yes" if pre-inspection QC/QA has been viewed & detail below / attach examples
label | dc67e295-80b7-5963-8929-c6d3452a5f88 |  | note | Select "No" detail why no QC/QA has been viewed/referenced below
checkpoint-group |  |  | section | Inspection Specifics
checkpoint-status |  |  | checkpoint | Consented drawings have been followed
checkpoint-status |  |  | checkpoint | General comments, photos and observations during inspection
checkpoint-group |  |  | section | Site Report Summary/Closeout
checkpoint-status |  |  | checkpoint | Works accepted and may proceed (select Pass) or reinspection required to defective elements (select Fail - Works Cannot Proceed)
text | 31674f03-6b8d-5fde-9082-952ea968b818 |  | textbox | Remedial(s) - Recorded and Closed Out
holdpoint |  |  | signoff | RAISE REMEDIAL / REQUEST SIGNOFF
checklist-flat |  |  | checklist | ST - R - Precast Balcony Installation |  |  |  |  | Yes | ST - R - Precast Balcony Installation | 2f534a4e-ff1b-4be0-84ba-55d2aebda402
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Joints grouted with Sika 212 and PEF rod.
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Balcony Installation completed and acceptable
checklist-flat |  |  | checklist | ST - R - Concrete Pour |  |  |  |  | Yes | ST - R - Concrete Pour | 32f9b0e2-e670-4ba4-856a-725d978f3a93
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Correct size and grade of the propping timbers
checkpoint-status |  |  | checkpoint | Correct size and grade of the props
checkpoint-status |  |  | checkpoint | Props placed in the correct location as indicated on the propping plan
checkpoint-status |  |  | checkpoint | Temporary anchors and fixings installed
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Concrete pour completed and acceptable
checklist-flat | 71d4341d-f64b-418b-a1c6-9bc46c6d9f30 |  | checklist | Council Inspection - |  |  |  |  | Yes | Add Council Inspection Checklist | 3532b7f2-6347-4d06-928b-e79d9017d2f5
checkpoint-status | 5c21e63c-7951-4e59-91dd-9909fc0c4b0a |  | checkpoint | Inspection completed, attached and any relevant observations closed out (Pass once all information is attached including observations with evidence of closeout)
text | e716f58a-4420-4e11-91ae-f4fef0f7ba87 |  | textbox | Date of inspection:
text | 78d9159e-0896-4188-a542-fa6b1bf43aaa |  | textbox | Inspection Type Code:
text | 6931f74e-964b-42b5-905c-440c2ce0001a |  | textbox | Area inspection relates to
select | ca58c4ad-f5b3-41c0-ae49-ce6c1c3289f9 |  | dropdown | Inspection Outcome | Pass,Fail,Partial Pass,N/A
boolean | d24858c1-85f5-44b8-99c0-818a707a7f19 |  | tickbox | Council inspection attached
holdpoint | f8fb688c-8db0-40be-bdfd-8214d2bb948a |  | signoff | Raise Remedial / Request Signoff
checkpoint-status | 7d244954-2fa5-4f9e-9553-4854758292f3 |  | checkpoint | All Relevant Observation Closeout evidence attached here if applicable (Pass once completed)
text | 659f0de8-c7a9-45fe-9851-606ecd798dd2 |  | textbox | Outstanding Information Required
checklist-flat |  |  | checklist | Handover |  |  |  |  | Yes | H - R - Handover | 35717cba-2e9b-41fd-8477-1f1c8aacc5d9
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | Bathroom completed and signed off.
checkpoint-status |  |  | checkpoint | Open living room area completed and signed off.
checkpoint-status |  |  | checkpoint | Kitchen area completed and signed off.
checkpoint-status |  |  | checkpoint | Toilet completed and signed off.
checkpoint-status |  |  | checkpoint | Bedroom 1 (1st clockwise from front door) completed and signed off.
checkpoint-status |  |  | checkpoint | Bedroom 2 (2nd clockwise from front door) completed and signed off.
checkpoint-status |  |  | checkpoint | Bedroom 3 (3rd clockwise from front door) completed and signed off.
checkpoint-status |  |  | checkpoint | Walk in/through wardrobe area completed and signed off.
checkpoint-status |  |  | checkpoint | Hall (and closets) completed and signed off.
checkpoint-status |  |  | checkpoint | Laundry area completed and signed off.
checkpoint-status |  |  | checkpoint | Garage completed and signed off.
checkpoint-status |  |  | checkpoint | Cleanliness and general items completed and signed off.
checkpoint-status |  |  | checkpoint | External and Hardscape completed and signed off.
checkpoint-status |  |  | checkpoint | Client extras / other unit specific items completed and signed off.
checkpoint-status |  |  | checkpoint | Upload Related Ryman Fitout quality inspection record (QT-012)
checklist-flat |  |  | checklist | I - C - MV Compliance Documents |  |  |  |  | Yes | I - C - MV Compliance Documents | 35c7345d-d311-47d9-a339-2b66a02f5d82
checkpoint-status |  |  | checkpoint | Compliance Documents
boolean | ff339850-e362-502e-a087-559542144cbd |  | tickbox | LBP Memorandum
boolean | ff806bf6-41dc-576a-8d81-040245144ee7 |  | tickbox | Mill Certificates
boolean | 1c16f7b3-ee2b-52af-8280-67deca12d2cb |  | tickbox | Concrete Dockets
boolean | 79ba0ecf-d41e-5740-a93d-0b2113fed022 |  | tickbox | Concrete Strength Test Results
checkpoint-status |  |  | checkpoint | Mitchell Vranjes PS4 Attached
checklist-sectioned |  |  | checklist | ITP - R - Ancillary Building Build (per ancillary building unit) |  |  |  |  | Yes | ITP - R - Ancillary Building Build (per ancillary building unit) | 37a57181-7e59-44ac-83c4-9d985ca6148c
checkpoint-group |  |  | section | Structure/Framing
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Framing system installed, square and plumb
checkpoint-status |  |  | checkpoint | Council pre-clad inspection completed and approved. Note date of inspection in comments
button | 6ee000ed-35bf-5298-a246-bf53f7cde3b9 |  | button | Note remedial work needed | None, Minor, Major
text | e49d9bad-aa00-537d-b364-aea97cc318f1 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Roofing
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Verify materials supplied to site (material and fixings) are as specified or approved samples
checkpoint-status |  |  | checkpoint | Construction complies with specifications
checkpoint-status |  |  | checkpoint | Obtain and upload all performance and authority certificates as required by specification or statutory regulations.
checkpoint-status |  |  | checkpoint | Council Pre-Roof Inspection completed and passed
button | f9ffe183-de7c-57d3-85f4-00dcbf1fdab2 |  | button | Note remedial work needed | None, Minor, Major
text | 9ca5437f-67e4-50e3-86a5-8f0f1ca666d4 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Façade
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Envelope/Watertightness Completed (requirements below)
checkpoint-status |  |  | checkpoint | Ecoply Board installed
checkpoint-status |  |  | checkpoint | Lintels installed
checkpoint-status |  |  | checkpoint | Tapes and VaproShield installed.
checkpoint-status |  |  | checkpoint | Windows and Sliders installed
checkpoint-status |  |  | checkpoint | Flashing installed
checkpoint-status |  |  | checkpoint | Envelope Penetrations completed
checkpoint-status |  |  | checkpoint | Council pre-wrap inspection completed and passed
button | 91df0477-d971-57d7-886c-0fbaa15a277a |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Council brickwork 'half-high' inspection completed and acceptable
button | ba88765d-4739-541c-b2e2-75da8e1e831f |  | button | Note remedial work needed | None, Minor, Major
text | a9d0c492-2db4-550c-a604-cb60fcd65a32 |  | textbox | Describe cladding type:
button | f399324c-1667-5f4f-91d0-38542f2aa823 |  | button | Brick Works completed | Yes, Reworked, N/A
button | 016d6ad6-71cf-54e5-b50f-ed29102b45ef |  | button | STO Poly Plaster completed | Yes, Reworked, N/A
text | 3164f10d-f627-5ad2-beba-3d03e676880a |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Pre-Line
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Pre-line completed
checkpoint-status |  |  | checkpoint | Framing system installation completed and acceptable
checkpoint-status |  |  | checkpoint | Nogs Installed as below and comply
checkpoint-status |  |  | checkpoint | Electrical First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Plumbing First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Insulation installation completed and acceptable
checkpoint-status |  |  | checkpoint | Security, Comms and Data First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | HVAC First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Fire Security First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Under floor heating First Fix (including screeding and soundproofing of the bathrooms/ wc) completed and acceptable
checkpoint-status |  |  | checkpoint | Kitchen extract First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Passive fire installation completed and acceptable
checkpoint-status |  |  | checkpoint | Suspended ceiling grids installation completed and acceptable
checkpoint-status |  |  | checkpoint | Pre-line plumbing external inspections completed and uploaded. Any remedial work signed off.
button | ffb7e1b0-cb0c-5425-bf86-15572047dc0d |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Pre-line building external inspections completed and uploaded. Any remedial work signed off.
button | 3f8eef86-a4fa-5cc1-9973-36838eb9891e |  | button | Note remedial work needed | None, Minor, Major
text | 19618504-abfd-5646-aa91-e3f445962b66 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Post-Line GIB
checkpoint-status |  |  | checkpoint | GIB installation correct, screw types, pattern, etc..
checkpoint-status |  |  | checkpoint | Fire rated GIB installed to adjoining unit walls & garage, correct thickness.
checkpoint-status |  |  | checkpoint | Post Line Council Inspection completed and acceptable. GIB stopping to proceed
button | 6dc2dc7f-6bde-51cc-8ea0-211635c34e3a |  | button | Note remedial work needed | None, Minor, Major
checklist-flat |  |  | checklist | FC - R - Air conditioning |  |  |  |  | Yes | FC - R - Air conditioning | 381db72f-1d4c-4831-aa65-620eadadab70
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Air conditioning works completed and acceptable
checklist-flat |  |  | checklist | ST - R - Timber Framing |  |  |  |  | Yes | ST - R - Timber Framing | 39a14607-70c2-40d0-856b-76db0a718e4b
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Timber frame installation completed and acceptable
checklist-flat |  |  | checklist | CST - R - Restricted Building Works Consent |  |  |  |  | Yes | CST - R - Restricted Building Works Consent | 3f9ecc32-610f-45f4-a20e-785e217b226f
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Record of works
boolean | 9f2eeb3d-17e5-555a-bc69-c510220f067e |  | tickbox | Foundations
boolean | 2d094933-26e2-5519-b7d9-1175adb0fccd |  | tickbox | Slab or subfloor framing
boolean | cf171014-ebbc-5159-9e88-a09c970fecaa |  | tickbox | Blockwork
boolean | 52426a22-7542-54db-ad5f-177e166ee322 |  | tickbox | Walls
boolean | 3eb4c939-3d53-574a-81aa-a8cc0da94d7f |  | tickbox | Roof
boolean | 1d4edd10-aee8-511e-9294-140d5bd477b3 |  | tickbox | Columns and Beams
boolean | f59cf385-da58-57bf-bb76-73ab2646bf86 |  | tickbox | Bracing
boolean | ed26012b-7e20-53aa-9b95-890670e632f8 |  | tickbox | Damp proofing
boolean | 94fce1cf-2f06-5bb1-a794-37b26f981aca |  | tickbox | Roof cladding or roof cladding system
boolean | e4d97a99-0478-5577-ad84-a9f9d8c354eb |  | tickbox | Ventilation system
boolean | 8b42fc3d-baf3-5f83-a3e8-a5f759ce971e |  | tickbox | Wall cladding or wall cladding system
boolean | 9cd4b417-1cb5-5ea4-ad50-a65897f5158b |  | tickbox | Waterproofing
checkpoint-status |  |  | checkpoint | Record of warranties
checklist-flat |  |  | checklist | F - R - Survey Certificates |  |  |  |  | Yes | F - R - Survey Certificates | 3fbcca83-520d-44b8-ad88-7f22cd6c9224
checkpoint-status |  |  | checkpoint | survey certificates for correct building height/location/setout attached
checklist-flat |  |  | checklist | ST - R - Structural Steel Installation |  |  |  |  | Yes | ST - R - Structural Steel Installation | 40f02781-0c1a-4ce7-a287-8d3016b2f950
checkpoint-status |  |  | checkpoint | Chemical anchor proof tests conducted on the sample selected by the MV Engineer
boolean | 3cf707d3-4fb0-5b16-ae96-b59f6dd75332 |  | tickbox | Chemical anchors are tested to 0.7xdesign load
boolean | 337ffcf5-dc45-5dfd-b530-4e935efa50f4 |  | tickbox | The test load of the bar is provided by the MV Engineer
boolean | c53003c8-8420-50e4-ac3c-e18db497b62c |  | tickbox | Proof load tests maintained for a minimum of 30 seconds
boolean | ff6d5f58-606c-5e66-bdc7-73b97b078f34 |  | tickbox | The load did not drop more than 10% during the testing
checkpoint-status |  |  | checkpoint | If the proof of tests show failure of the anchors, installation of anchors should stop, cause of failure investigated and installation methodology should be reviewed. If failure is recorded, the minimum test sample shall be increased to 6 specimens or 5% of the total relevant anchor population, whichever is greater.
checkpoint-status |  |  | checkpoint | Mechanical anchor testing conducted on the sample selected by the MV Engineer and witnessed by the MV Engineer
boolean | 58b7151f-1d2c-58cb-94c5-42ab2d6c79a6 |  | tickbox | For trubolt or similar anchors the maximum tightening torque is reviewed
checkpoint-status |  |  | checkpoint | If the proof of tests show failure of the anchors, installation of anchors should stop, cause of failure investigated and installation methodology should be reviewed. If failure is recorded, the minimum test sample shall be increased to 6 specimens or 5% of the total relevant anchor population, whichever is greater.
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All structural steel correctly installed in respective area and acceptable
checklist-flat |  |  | checklist | ST - R - Precast Flat Slab Installation |  |  |  |  | Yes | ST - R - Precast Flat Slab Installation | 42fc89cf-6d68-47cc-ab1f-bcb6098ba81d
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Flat Slab Installation completed and acceptable
checklist-flat | d6376554-0d23-419d-8455-38261bf13cdd |  | checklist | Inspection - |  |  |  |  | Yes | Add Consultant Inspection Checklist | 43ccb7b6-2831-4cb7-8d7e-ef3dbc4246ac
checkpoint-status | 97c16fd0-68a3-477a-9516-e8e2bc204f6f |  | checkpoint | Inspection completed, attached and any relevant observations closed out
text | e716f58a-4420-4e11-91ae-f4fef0f7ba87 |  | textbox | Date of Inspection:
text | 78d9159e-0896-4188-a542-fa6b1bf43aaa |  | textbox | Type of Inspection:
text | 534f8c4f-3a28-4d0b-8e31-2e870fe2cb87 |  | textbox | Area inspection relates to
boolean | d24858c1-85f5-44b8-99c0-818a707a7f19 |  | tickbox | Inspection attached
holdpoint | d9f7a544-63f6-4d76-a1c6-5167468bb030 |  | signoff | Raise Remedial / Request Signoff
checkpoint-status | 1e86ca02-3120-46d0-8c5e-2bf0ae3e421d |  | checkpoint | All Relevant Observation Closeout evidence attached here if applicable (Pass once completed)
text | b4ff21c8-e458-474a-a19a-1cbce0361c6d |  | textbox | Corrective Actions Required
checklist-flat |  |  | checklist | FC - R - Windows and Sliders |  |  |  |  | Yes | FC - R - Windows and Sliders | 44652711-401b-41e1-84b4-43d5e01e8185
checkpoint-status |  |  | checkpoint | Check clearance around opening min 6mm/ max 18mm
checkpoint-status |  |  | checkpoint | Packers to be correctly used and set back to allow continuous air seal
checkpoint-status |  |  | checkpoint | Check air seal is provided at the rear of the window reveal
holdpoint |  |  | signoff | Raise remedial/ request signoff
checkpoint-status |  |  | checkpoint | Window and slider installation completed and acceptable
checklist-flat |  |  | checklist | F - R - Piling |  |  |  |  | Yes | F - R - Piling | 44b5eb36-2faa-4a0e-8f65-27f7128e276e
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Subcontractor piling card reviewed and meets requirements
checkpoint-status |  |  | checkpoint | Piles set out, surveyed, and marked.
checkpoint-status |  |  | checkpoint | Site condition acceptable for piling rig
checkpoint-status |  |  | checkpoint | Piles meet set out, heights, and correct within tolerances.
checkpoint-status |  |  | checkpoint | All piling cards received, filed, and meet requirements.
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 2e1d650f-9403-555c-9660-65690d4a00b8 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | ce93d03f-bfcc-5118-b357-1ba8846e7f42 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | d99af092-9879-551c-837c-bd5bba847c1e |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-flat |  |  | checklist | C - R - Service Trenches - Common Service Trenches |  |  |  |  | Yes | C - R - Service Trenches - Common Service Trenches | 459c569f-7e6d-4288-8057-c2bbf336c897
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Common service trench works completed as per the specifications
checklist-flat |  |  | checklist | F - R - Underground services |  |  |  |  | Yes | F - R - Underground services | 45f05fdd-2866-409f-99e6-c78d4ceb2e70
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All underground services installation completed as per the specifications
checklist-flat |  |  | checklist | I - C - Woods Survey Set-Out Checklist |  |  |  |  | Yes | I - C - Woods Survey Set-Out Checklist | 495df63d-35b4-40fc-b48d-123adf582f34
checkpoint-status |  |  | checkpoint | All Site Details Inputted Below
text | cd3ab313-9446-5e98-953d-47dd1d7fda5f |  | textbox | Survey works completed by - (enter name)
text | bd9a8dea-670f-55e0-9501-b66dbea674e2 |  | textbox | Additional personnel accompanying surveyor
text | 5d49f91a-682a-545c-8ef1-f514ca072577 |  | textbox | Building/Area to Setout
checkpoint-status |  |  | checkpoint | Received CAD drawing of building grids or outline
boolean | 9a9fe967-ad5e-5a52-9eb3-f40ba82a9825 |  | tickbox | Office calculations
boolean | 3b25de42-b58b-5bcb-b8cb-0d4b6c0f857c |  | tickbox | Set out platform using offset stake
boolean | a08d8007-3e87-5f4f-979f-9cc246ce0afc |  | tickbox | Mark level of top of platform
boolean | 8c540cce-4e39-5ea7-8aa5-3e0b152fb8da |  | tickbox | Provide diagram of set out to contractor
checkpoint-status |  |  | checkpoint | Check level of platform is correct
boolean | 51e75bc6-4255-5ab3-ae0a-f4caa913ca68 |  | tickbox | Set out grids on profiles installed by contractor
checkpoint-status |  |  | checkpoint | Setting out certificate or Building Location Certificate before concrete pour
boolean | f8312ba0-d761-5ddc-9ca3-d06ed1248f0b |  | tickbox | Copy of Setting out or Building Location Certificate
boolean | 2e138d47-2f36-5f24-80a6-ceb7a80ddb1d |  | tickbox | Upper floor setout (if required)
boolean | 7496ac16-24e2-5030-8d97-810418ec739d |  | tickbox | Receive instruction from Rymans
boolean | 1db7ef79-257e-510e-9e22-1710b62a4ece |  | tickbox | Set out service locations on upper floors
boolean | e0d278cf-5671-5749-b349-f0fcad8ae81e |  | tickbox | Diagram provided to contractor
checkpoint-status |  |  | checkpoint | Setout / Surveying works completed and report sent to relevant parties
checklist-flat |  |  | checklist | FC - R - Lintels |  |  |  |  | Yes | FC - R - Lintels | 4d16bc8c-840b-4134-b9fa-4189736bbe35
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Lintels completed and acceptable
checklist-sectioned |  |  | checklist | ITP - R - B01 Fitout/Services (per area/room) |  |  |  |  | Yes | ITP - R - B01 Fitout/Services (per area/room) | 4d7b497d-294d-4ef5-b88d-ddf64a477345
checkpoint-group |  |  | section | All areas/rooms
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
button | 483755c2-425f-5ce6-b5cd-388c24d102f6 |  | button | Sanitary areas completed and signed off | Yes, Reworked, N/A
button | 710475fa-91ce-516d-ac84-84ba570bf7bb |  | button | Service areas completed and signed off. | Yes, Reworked, N/A
button | 4093b5f3-11b0-5525-99ec-985d16da000f |  | button | Public/personal areas completed and signed off. | Yes, Reworked, N/A
button | 6a1be99a-18b4-52dc-b82b-d0d4e785e31a |  | button | Cleanliness and general items completed and signed off. | Yes, Reworked, N/A
button | bdc6e428-f9ff-58e6-93ec-4a96d16ae926 |  | button | Client extras / other unit specific items completed and signed off. | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Upload Related Ryman Fitout quality inspection record (QT-012)
checkpoint-group |  |  | section | ALS/Care unit services
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Systems completed and acceptable.
checkpoint-status |  |  | checkpoint | Fire - Alarm, Hydrant & Sprinkler completed and acceptable.
checkpoint-status |  |  | checkpoint | Nurse Call, Security, Data and Communications completed and acceptable.
checkpoint-status |  |  | checkpoint | Hydraulic completed and acceptable.
checkpoint-status |  |  | checkpoint | Electrical completed and acceptable.
checkpoint-status |  |  | checkpoint | Mechanical completed and acceptable.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | b8f21c8f-392a-59d8-aa2c-40488d0e7a53 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Common, Recreational & Service Areas services
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Specified systems completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Hydrant, Fire Alarms, Sprinklers completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Alarms, Manual/Automatic completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Gas Detection completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Nurse Call completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Access Controlled Doors completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Interfaced Fire/Smoke Doors/Windows/Security completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Hydraulic completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Lifts completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Mechanical, fresh air and duct extract system completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Mechanical, kitchen extract + air conditioning system completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Smoke Curtains completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Essential Power Supply completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Emergency Signage + Exits & Emergency Lighting completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Swimming Pool - Plant completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Fire Engineer inspection completed and approved
button | 65bbb793-ca5e-5dda-bd20-c23a52a59bf5 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Electrical Engineer inspection completed and approved
button | 6f7f6519-78fe-59c1-acf4-e4ccc9659f01 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Mechanical / Hydraulic Engineer inspection completed and approved
button | 1c1d3181-a0bf-51cd-b61e-925dc2bfd459 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 18e99d0e-ad84-5747-9905-ce7e25960611 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checklist-flat |  |  | checklist | CST - R - Council Inspection |  |  |  |  | Yes | CST - R - Council Inspection | 53078f38-ac04-4dd7-8c11-f4dd79d5ec55
checkpoint-no-status |  |  | checkpoint | Inspection Details:
text | b626a201-950d-59ee-a452-afcdb738aece |  | textbox | Date of Inspection
text | df8b6f70-e90d-5175-b8de-b830033b6374 |  | textbox | Type of Inspection
text | 4d8808e7-c702-5274-827e-56a1eda3a2bf |  | textbox | Area Inspection relates to
select | cf1dd3c2-5aa0-5958-b8e5-811d6d0c5a99 |  | dropdown | Inspection outcome | Pass, Partial Pass, Fail
boolean | 4aab5bdc-2992-5d36-ae18-df25f4b03c56 |  | tickbox | Council inspection attached
checkpoint-status |  |  | checkpoint | Relevant Observation Closeout evidence attached below if applicable (pass once completed)
text | 4b2c95c9-476c-5b35-af6d-e6ac4482b655 |  | textbox | Failed comments and Required Action
checklist-flat |  |  | checklist | ST - R - Intumescent Painting |  |  |  |  | Yes | ST - R - Intumescent Painting | 532f12bd-aeee-48f6-a64d-e36672ca38c5
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Intumescent Painting completed and acceptable
checklist-flat |  |  | checklist | Balustrades |  |  |  |  | Yes | FC - R - Balustrades Installation | 5513c1b9-520e-402a-8627-d027f8bf799e
checkpoint-status |  |  | checkpoint | Chemset bolt pull testings completed and passed. Test results received and confirmed.
label | b5cad389-1c18-569b-9921-18e597d765af |  | note | Record sample size (%)
checkpoint-status |  |  | checkpoint | Lateral load pull testings completed and passed. Test results received and confirmed.
label | 652adcab-a8c1-5428-b89a-9ed6814feea7 |  | note | Record sample size (%)
text | 66323d32-399b-52dd-baa9-6b3cfeac0225 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checklist-flat |  |  | checklist | ST - R - Roof structure - Steel |  |  |  |  | Yes | ST - R - Roof structure - Steel | 55847a63-2f1d-4e99-8a91-375d91f11ef3
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All structural steel correctly installed in respective area and acceptable
checklist-flat |  |  | checklist | FC - R - Water Test |  |  |  |  | Yes | FC - R - Water Test | 5b0f3fc1-486e-4525-8c56-400eea9028f1
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Water Test completed and acceptable
checklist-flat |  |  | checklist | S - R - firewalls (must be completed prior to internal wall commencement) |  |  |  |  | Yes | S - R - firewalls (must be completed prior to internal wall commencement) | 5b5ee5a3-93ac-40ab-ac2a-dc32a2620546
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Pre-line completed
button | a060375e-5f23-5821-8bc4-4caa0b44a696 |  | button | Framing system installation completed and acceptable | Yes, Reworked, N/A
button | 16a6f4a5-5664-5d05-b7e8-30a7cf2d180f |  | button | Passive fire installation completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 251a128c-dd30-5952-b049-cdb93b671ff8 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | GIB installation correct, screw types, pattern, etc..
checkpoint-status |  |  | checkpoint | Fire rated GIB installed
checkpoint-status |  |  | checkpoint | All preline services & passive fire (where required) completed, area accessible and substrate acceptable
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Consider bracing, adhesive/sealant & lining layer(s) requirements (including fire stopping between layers)
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Services/penetrations, correctly formed & located (consider cut-out tolerances where applicable)
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Correct fixing pattern/sealant (including fire)/adhesive/layers installed to align with consented design and specifications
checkpoint-status |  |  | checkpoint | All lining(s) completed correctly to specification & level of finish acceptable in respective area(s)
checkpoint-status |  |  | checkpoint | Post Line Council Inspection completed and acceptable. GIB stopping to proceed
button | a0efae5b-fef2-5de8-bb6e-633c0b3d5a81 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checklist-flat |  |  | checklist | I - C - T+T Vibration Monitoring Report |  |  |  |  | Yes | I - C - T+T Vibration Monitoring Report | 5db804c1-2c37-4f85-861c-5594f7b4f23d
checkpoint-status |  |  | checkpoint | General comments, photos and observations during inspection & report attached
checklist-flat |  |  | checklist | F - R - Backfilling |  |  |  |  | Yes | F - R - Backfilling | 5ed1f271-8033-4cc3-8d40-3c45958aacc5
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Backfilling completed as per the specifications
checklist-flat |  |  | checklist | CST - R - Façade Consent |  |  |  |  | Yes | CST - R - Façade Consent | 5f04a322-05f4-40f5-951b-2ebe5f9267f2
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Exterior
boolean | 03e4bd14-37ba-50de-845a-b04ff7dba645 |  | tickbox | Producer Statement Construction(PS3): Plaster system and manufacturer's product warranty
boolean | eddbc1bd-ff57-5e62-80df-024057336705 |  | tickbox | Producer Statement Construction(PS3): Brick work and manufacturer's product warranty
checkpoint-status |  |  | checkpoint | Glazing and external joinery
boolean | bd6ce909-a1d7-5483-a2c8-84c8fd79f59b |  | tickbox | Producer statement for aluminium joinery complying with NZS4211:2008
boolean | e8bfc2b6-80f8-5b98-91fa-b506e44ff80e |  | tickbox | Producer Statement Construction(PS3): safety glazing in compliance with NZS4211:2008
boolean | e8d59ba1-eb87-5d7d-bb4f-c55c46af5a7e |  | tickbox | Producer Statement Design(PS1) from joinery manufacturer
boolean | 97db3c96-5d86-5042-a8b3-5e512e13e803 |  | tickbox | Producer statement for fire rated windows confirming compliance with NZS4232
checkpoint-status |  |  | checkpoint | Waterproofing
boolean | e9704193-0d5a-5ad2-a586-7a4abf7479f9 |  | tickbox | Producer Statement Construction(PS3): Roof membrane and Manufacturer's product warranty
boolean | ef762e23-8425-52ad-bd94-21c475fb5a50 |  | tickbox | Producer Statement Construction(PS3): Deck Membrane and manufacturer's product warranty
boolean | ffacbed3-4f21-57c8-8888-20bc6252bd8a |  | tickbox | Producer Statement Construction(PS3): Tanking membrane and manufacturer's product warranty
checkpoint-status |  |  | checkpoint | Roof abseil and fall arrest system
boolean | eb9c2c43-fe8f-5a28-a123-e9ba33026137 |  | tickbox | Producer Statement Design(PS1): installation of roof abseil and/or fall arrest system
boolean | 79acd052-cf84-521c-b497-5560e0e8df9f |  | tickbox | Producer Statement Construction(PS3): installation of roof abseil and/or fall arrest system
boolean | 4c7230c8-952c-55af-b77a-eafb2b9e3d08 |  | tickbox | Producer Statement Review(PS4): installation of roof abseil and/or fall arrest system
checkpoint-status |  |  | checkpoint | Balustrades
boolean | 91d01526-651f-5bbd-911f-72a880511a66 |  | tickbox | Producer Statement Construction (PS3) for the balustrade installation
checkpoint-status |  |  | checkpoint | Façade systems
boolean | 3ff99901-4bb7-5fe2-8d77-f058b8575496 |  | tickbox | Producer Statement Review(PS4): from council approved façade engineer for façade system
boolean | fc7d35dd-6842-561b-bae5-3fff80d0cd31 |  | tickbox | Written report from council approved façade engineer for façade system (supporting the PS4)
boolean | 43092eae-611f-50a3-a046-d5a694743d0b |  | tickbox | Producer Statement Construction(PS3): installation of the façade system
boolean | 8e5be20e-764b-5e56-9779-d8628d6b9bd9 |  | tickbox | Façade System Maintenance Manual
boolean | 52a897f1-75ce-5bed-b5d2-178ab72ff01e |  | tickbox | Warranties/Guarantees from main and sub-contractors
checklist-flat | 585953ec-b603-48d9-8636-d27849f65506 |  | checklist | Building Consent - |  |  |  |  | Yes | Add Council BC Upload Checklist | 6064715c-2fc6-457f-9577-a5531cb93f8c
checkpoint-status | 6ec0afe6-58c3-4b58-86bf-56de34fccee2 |  | checkpoint | Latest building consent attached (superseded and attached as required)
checklist-flat |  |  | checklist | F - R - Underslab plumbing |  |  |  |  | Yes | F - R - Underslab plumbing | 627ec13a-3a1f-4c59-99cf-063a6f05fef6
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All underslab plumbing installation completed as per the specifications
checklist-flat |  |  | checklist | ST - R - Precast Shell Beam Lintel Installation |  |  |  |  | Yes | ST - R - Precast Shell Beam Lintel Installation | 62a937b9-1b6b-4760-94b2-689d10a7b8c5
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Shell Beam Lintel Installation completed and acceptable
checklist-sectioned |  |  | checklist | ITP - R - Apartment Pre & Post Line (per area/grid/Location) |  |  |  |  | Yes | ITP - R - Apartment Pre & Post Line (per area/grid/Location) | 63a5e4de-7246-4952-b7f3-065ed006b0ea
checkpoint-group |  |  | section | Pre-Line
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Pre-line completed
checkpoint-status |  |  | checkpoint | Framing system installation completed and acceptable
checkpoint-status |  |  | checkpoint | Nogs Installed and comply
checkpoint-status |  |  | checkpoint | Electrical First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Plumbing First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Insulation installation completed and acceptable
checkpoint-status |  |  | checkpoint | Security, Comms and Data First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | HVAC First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Fire Security First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Underfloor heating First Fix (including screeding and soundproofing of the bathrooms/ wc) completed and acceptable
checkpoint-status |  |  | checkpoint | Kitchen extract First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Passive fire installation completed and acceptable
checkpoint-status |  |  | checkpoint | Suspended ceiling grids installation completed and acceptable
checkpoint-status |  |  | checkpoint | Pre-line plumbing external inspections completed and uploaded. Any remedial work signed off.
button | fae2056d-ec08-5f1d-94eb-b58ac77f5e98 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Pre-line building external inspections completed and uploaded. Any remedial work signed off.
button | 992b7ecd-5cd9-5750-bcec-2fc777c36a2a |  | button | Note remedial work needed | None, Minor, Major
text | 2279a9e3-a073-5971-916a-5aad71bfe931 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Post-Line GIB
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | GIB installation correct, screw types, pattern, etc..
checkpoint-status |  |  | checkpoint | Fire rated GIB installed
checkpoint-status |  |  | checkpoint | All preline services & passive fire (where required) completed, area accessible and substrate acceptable
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Consider bracing, adhesive/sealant & lining layer(s) requirements (including fire stopping between layers)
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Services/penetrations, correctly formed & located (consider cut-out tolerances where applicable)
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Correct fixing pattern/sealant (including fire)/adhesive/layers installed to align with consented design and specifications
checkpoint-status |  |  | checkpoint | All lining(s) completed correctly to specification & level of finish acceptable in respective area(s)
checkpoint-status |  |  | checkpoint | Post Line Council Inspection completed and acceptable. GIB stopping to proceed
button | 6f506f96-dd1c-5674-9908-1304586bacdf |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checklist-flat |  |  | checklist | I - C - Woods Consultant Remedial Item Checklist |  |  |  |  | Yes | I - C - Woods Consultant Remedial Item Checklist | 64127878-2a8e-4232-909b-346093ad03df
checkpoint-status |  |  | checkpoint | Remedial Status (Woods to "Pass" once satisfied)
text | 6c7cb984-2651-57dc-93db-13c332b173aa |  | textbox | Location of Remedial
text | 8a7e6514-42a4-5982-aeb2-84e4684d899c |  | textbox | Remedial Description
text | 073491fe-f446-56f9-a74e-aa4957f21204 |  | textbox | Action Required
holdpoint |  |  | signoff | Request Woods Signoff on Remedial
checklist-flat |  |  | checklist | CST - R - Hydraulic Consent |  |  |  |  | Yes | CST - R - Hydraulic Consent | 65932275-6d4d-406a-9eca-0186f9b10f81
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Plumbing
boolean | d8f5a650-be8d-527a-b51f-a2972339dd4c |  | tickbox | Producer Statement Construction (PS3): Plumbing
boolean | 8bb75427-fee1-58c1-a82e-414956519b18 |  | tickbox | Confirmation of water saving devices
boolean | e9cf4362-d9b0-5199-86f2-12a2bed98573 |  | tickbox | Plumbing under slab as built plan
boolean | 725d0bdb-87a1-5953-90d7-95da54a343a0 |  | tickbox | Producer Statement Review(PS4): hydraulic systems of the building from a council approved engineer
checkpoint-status |  |  | checkpoint | Gas-fitting Work Certificate
checkpoint-status |  |  | checkpoint | Automatic Backflow Preventers Connected to Potable Water supply
boolean | 9dc41d37-9573-5a52-a2cd-3b21842d41d8 |  | tickbox | Backflow prevention - PS3 and test certificates showing location and type of devices
checkpoint-status |  |  | checkpoint | Application for compliance schedule (AC2102)
checkpoint-status |  |  | checkpoint | Confirmation of performance standards for specified systems (AC2150)
checklist-sectioned |  |  | checklist | ITP - R - Townhouse Block Build (per townhouse block) |  |  |  |  | Yes | ITP - R - Townhouse Block Build (per townhouse block) | 66877a85-3f58-495f-9a3a-faa2c1c9b323
checkpoint-group |  |  | section | Structure/Framing
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Framing system installed, square and plumb
checkpoint-status |  |  | checkpoint | Council pre-clad inspection completed and approved. Note date of inspection in comments
button | 27faa8b1-dd46-58ad-8728-d58486f32a29 |  | button | Note remedial work needed | None, Minor, Major
text | 8f14baec-f433-553e-bb7f-8bbfacf8dc9f |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Roofing
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Verify materials supplied to site (material and fixings) are as specified or approved samples
checkpoint-status |  |  | checkpoint | Construction complies with specifications
checkpoint-status |  |  | checkpoint | Obtain and upload all performance and authority certificates as required by specification or statutory regulations.
checkpoint-status |  |  | checkpoint | Council Pre-Roof Inspection completed and passed
button | b9c5cc42-26e9-5362-b517-f5fba14fc70f |  | button | Note remedial work needed | None, Minor, Major
text | 36e74a07-3a90-5142-98c4-bc310f25ca82 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Façade
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Envelope/Watertightness Completed (requirements below)
checkpoint-status |  |  | checkpoint | Ecoply Board installed
checkpoint-status |  |  | checkpoint | Lintels installed
checkpoint-status |  |  | checkpoint | Tapes and VaproShield installed.
checkpoint-status |  |  | checkpoint | Windows and Sliders installed
checkpoint-status |  |  | checkpoint | Flashing installed
checkpoint-status |  |  | checkpoint | Envelope Penetrations completed
checkpoint-status |  |  | checkpoint | Council pre-wrap inspection completed and passed
button | 0202192f-ad54-5366-a4ab-a33e4328365a |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Council brickwork 'half-high' inspection completed and acceptable
button | 3f9c3a8d-62c0-57a7-b30d-784d226b0fd2 |  | button | Note remedial work needed | None, Minor, Major
text | 8a4c7ef7-d2e7-510a-8940-2573fcf26099 |  | textbox | Describe cladding type:
button | e97ed044-d1b7-5f24-8351-f2ea596b02ed |  | button | Brick Works completed | Yes, Reworked, N/A
button | 50a97605-61af-5d90-b5e2-4fd6114c2ba5 |  | button | STO Poly Plaster completed | Yes, Reworked, N/A
text | a34cf2d0-3759-5bc4-a704-3d92e6d05fe3 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Pre-Line
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Pre-line completed
checkpoint-status |  |  | checkpoint | Framing system installation completed and acceptable
checkpoint-status |  |  | checkpoint | Nogs Installed as below and comply
button | f3fb0469-ffea-5ac9-bce4-b1a49f251a92 |  | button | Steel Stud frame installation completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Electrical First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Plumbing First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Insulation installation completed and acceptable
checkpoint-status |  |  | checkpoint | Security, Comms and Data First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | HVAC First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Fire Security First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Under floor heating First Fix (including screeding and soundproofing of the bathrooms/ wc) completed and acceptable
checkpoint-status |  |  | checkpoint | Kitchen extract First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Passive fire installation completed and acceptable
checkpoint-status |  |  | checkpoint | Suspended ceiling grids installation completed and acceptable
checkpoint-status |  |  | checkpoint | Pre-line plumbing external inspections completed and uploaded. Any remedial work signed off.
button | 1646b053-33b5-5d8a-9f0d-60cabc9ec81c |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Pre-line building external inspections completed and uploaded. Any remedial work signed off.
button | d801e561-d775-5c97-9034-4149c912da90 |  | button | Note remedial work needed | None, Minor, Major
text | 3ffddc7b-7c41-54e2-bb3e-8472ccf139b3 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Post-Line GIB
checkpoint-status |  |  | checkpoint | GIB installation correct, screw types, pattern, etc..
checkpoint-status |  |  | checkpoint | Fire rated GIB installed to adjoining unit walls & garage, correct thickness.
checkpoint-status |  |  | checkpoint | Post Line Council Inspection completed and acceptable. GIB stopping to proceed
button | 09de849a-f722-542d-b894-0eb2a7be1536 |  | button | Note remedial work needed | None, Minor, Major
checklist-sectioned |  |  | checklist | Concrete Planning and Pour |  |  |  |  | Yes | ITP - R - Concrete - Planning and Pour (per townhouse block) | 6747a608-b945-4a7d-b6f5-189e13d9158c
checkpoint-group |  |  | section | Pre Pour Planning
checkpoint-status |  |  | checkpoint | Concrete pour planning completed with subcontractor
text | db2338b3-5bdf-5c4c-bcaa-8464eb98fccf |  | textbox | Date of pour
text | f52f28f7-c4e2-5f00-a7bc-0240ec30b3df |  | textbox | Specified concrete strength:
text | ad1c72e5-b11b-5865-a0c6-e23823bddb72 |  | textbox | Concrete strength ordered:
text | 46fb1be3-0ff9-53ef-8ebd-ae2736c68ec0 |  | textbox | Concrete quantity ordered:
text | 7519cb09-6860-5767-af18-335f175a47e4 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | Request to pour received and approved
button | e085eb6e-4cc6-55fe-930b-c55304caef15 |  | button | Reinforcing meets specification | Yes, Reworked, N/A
button | 4c13c8e5-a933-5bab-86cb-ef5ccefaa1a2 |  | button | Service penetrations present and correct | Yes, Reworked, N/A
button | 78b72fe9-9885-5905-9a8d-9813a1fd1c35 |  | button | Waterproofing elements present and correct | Yes, Reworked, N/A
button | b8e0fde6-e1c2-5de3-9881-56504ac81247 |  | button | Couples present and correct | Yes, Reworked, N/A
button | 731196ed-f679-556a-a244-0761f760b3ea |  | button | Control joints/ stop ends installed accurately and correctly braced | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Engineer Inspection conducted and passed
button | e7d349ab-5eec-5ce2-aa3c-aafa0f2b7cc0 |  | button | Note remedial work needed | None, Minor, Major
text | 5afe31a7-4aae-519b-894b-a5af25ccaab0 |  | textbox | Inspected by and date:
checklist-flat |  |  | checklist | FC - R - Anchor Points - Static line installation |  |  |  |  | Yes | FC - R - Anchor Points - Static line installation | 6b233561-835b-4e4f-9b67-aff042261a28
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Static line installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - Cladding Sealant |  |  |  |  | Yes | FC - R - Cladding Sealant | 6bf62695-5317-4cbf-9b31-3a80da01b792
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Cladding sealant completed and acceptable
checklist-flat |  |  | checklist | FC - R - Tapes and VaproShield |  |  |  |  | Yes | FC - R - Tapes and VaproShield | 707cedcb-3190-44db-b6b8-ceea2ba2c273
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Tapes/VaproShield works completed and acceptable
checklist-flat |  |  | checklist | FC - R - Roofing |  |  |  |  | Yes | FC - R - Roofing | 7090e4ec-008e-4700-ab6d-3ab9550941ee
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Roofing installation completed and acceptable
checklist-flat |  |  | checklist | ST - R - Double T Installation |  |  |  |  | Yes | ST - R - Double T Installation | 71729e53-4e5d-437a-8e62-d9376dfeec2c
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | Inspected on arrival & damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Shoreload completed
checkpoint-status |  |  | checkpoint | Double T install complete and acceptable (checked location and level)
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 7521f97f-881a-56bf-9cf4-d872f9f2cb41 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-flat |  |  | checklist | FC - R - External Plaster - Nibs & Beams |  |  |  |  | Yes | FC - R - External Plaster - Nibs & Beams | 72ce8d3a-62bd-46f6-985e-25e343347ea6
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | External Plaster works for Nibs & Beams completed and acceptable
checklist-sectioned |  |  | checklist | I - C - T+T Consultant Site Visit Report |  |  |  |  | Yes | I - C - T+T Consultant Site Visit Report | 742c7c51-ad60-40d7-b5b8-ec20dda636d0
checkpoint-group |  |  | section | Site Visit Details
checkpoint-status |  |  | checkpoint | All site visit details have been captured
text | 1a47e2c0-ac66-58bc-8d77-a11f1d3317b8 |  | textbox | Date
text | 544987de-0ba9-5c27-a2b3-d763c8d2d47a |  | textbox | Time
text | e483ed0e-d168-5433-944f-84dcc4dc44ba |  | textbox | Weather Conditions:
text | f6699b02-8aac-5fab-997d-7c82d067e59a |  | textbox | Site Conditions:
text | b4f8f3a6-d45f-5ad5-8eb2-76ba8870139e |  | textbox | Sub-contractors:
text | bb4a8f14-3031-5ac7-99c7-00e46c8aad93 |  | textbox | On-site contact with:
text | 9ae2e913-4d59-57bc-bae1-89724420a0ec |  | textbox | Plant/Equipment on site:
text | d468926a-fa90-5009-999e-80a67af8ae3d |  | textbox | Materials on site:
checkpoint-status |  |  | checkpoint | General progress recorded
checkpoint-group |  |  | section | Health and Safety
checkpoint-status |  |  | checkpoint | Health and safety - All details inputted and any closeout completed
boolean | 7ecaa7f4-371f-5fa9-837d-750b087d5beb |  | tickbox | Contractors induction/Hazard IT sighted
boolean | ac0b42b0-6da8-5a7a-9e5b-a98c19b13cf2 |  | tickbox | T+T's JSA/Hazard ID signed
boolean | 67db92fa-d478-5d79-9d92-765fcb16a67b |  | tickbox | Double take completed
text | f1ab5f9d-61d8-568b-8cb7-240313dbd9da |  | textbox | Comments:
text | 85be7aa7-5277-5067-9596-b12ec29342f6 |  | textbox | Actions:
text | ba3a5656-9544-5144-ac34-1f4d57573cfc |  | textbox | Follow up:
checkpoint-group |  |  | section | Inspection Details/Closeout
checkpoint-status |  |  | checkpoint | All Inspection Details Inputted Below
text | b0bc537c-0e64-5067-a43b-51ec294b1266 |  | textbox | WORK ELEMENT BEING MONITORED:
button | d0b720b3-3d6e-5d4f-8f68-7e210a4b95bd |  | button | HAS CONTRACTOR PRE-INSPECTION QA CHECK BEEN VIEWED | Yes,No
text | c98b32fd-81a7-56a2-af71-26bc60479bf3 |  | textbox | If "Yes" what QC/QA has been viewed
text | 1d0ffbe2-b3f2-5025-b4ca-7f6a4ee87c4c |  | textbox | If "No" detail why no QC/QA has been viewed/referenced
checkpoint-status |  |  | checkpoint | DRAWING REFERENCE:
checkpoint-status |  |  | checkpoint | Works may proceed
label | 02c4afad-029e-58fe-87eb-6b5b90ca94e3 |  | note | "FAIL" if reinspection is required to defective elements (If Failed - Works Cannot Proceed without T+T approval)
label | ace6ca73-11b5-503c-84bb-f3575ece9c25 |  | note | Photographic evidence to close out remedial items is required prior to pouring concrete or completing works. Proceeding without the engineer’s approval is at the Contractor’s risk
text | 6201f85e-f9ab-57a4-9efe-7536857db0be |  | textbox | Reported By:
text | 1ec30646-e91c-5140-9566-8d5ff79e8fb9 |  | textbox | Reviewed By:
holdpoint |  |  | signoff | RAISE REMEDIAL / REQUEST SIGNOFF
checklist-flat |  |  | checklist | Fascia/Gutter |  |  |  |  | Yes | FC - R - Fascia/Gutter | 779abb99-10fe-4473-ab79-34829368b1da
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Fascia/Gutter installation completed and acceptable
checklist-flat |  |  | checklist | POST - R - Grab Rail Load Testing (per stage) |  |  |  |  | Yes | POST - R - Grab Rail Load Testing (per stage) | 77ca4b53-b98f-4d42-b1df-90d836e02a13
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Load testing to NZS 4121:2001 completed and passed. Test results received and confirmed.
text | c80b943e-a5a8-5bce-8588-ef56aead231a |  | textbox | Record quantity tested
text | c7b22539-b9ef-5200-b6e1-0fe5277d621c |  | textbox | Record sample size (%)
text | 532fbfe6-ba1d-565b-9134-d36e2d7b7848 |  | textbox | Record Apartment No's tested
text | e6627a18-cfff-5006-ad82-c9d09e8f2e4a |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checklist-flat |  |  | checklist | Punch Windows Frames (unglazed) |  |  |  |  | Yes | FC - R - Punch Windows Frames (unglazed) | 7b226aed-1b6e-47b9-acbd-db5a5cad06c6
checkpoint-no-status |  |  | checkpoint | Window # / Elevation / Level
text | 4f4afde1-2876-5096-8b62-4b785e8ff7c8 |  | textbox | Window # / Elevation / Level
checkpoint-status |  |  | checkpoint | Installation (By others) completed as per detail Y/N
checkpoint-status |  |  | checkpoint | Check the joinery is free from damage
checkpoint-status |  |  | checkpoint | All glazing beads attached to Frame PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Check Frame number PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Inspection of Backing rubber - no damage and continuous around perimeter
checkpoint-status |  |  | checkpoint | Glazing Blocks inserted correctly PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Correct Glass units installed (Glass sticker) PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Glazing Beads fitted correctly PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Correct Wedge Rubber installed and rubbered off as per WGANZ guidelines
checkpoint-status |  |  | checkpoint | Glass Stickers removed
checkpoint-status |  |  | checkpoint | Trade Clean
checkpoint-status |  |  | checkpoint | Final Inspection PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Glazing complete for handover to Ryman Healthcare
holdpoint |  |  | signoff | Raise Remedial
checklist-flat |  |  | checklist | ST - R - Stair Installation |  |  |  |  | Yes | ST - R - Stair Installation | 805ed2e7-17bb-456f-a8ca-a846dda7e475
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Stair Installation completed and acceptable
checklist-flat |  |  | checklist | ST - R - Blockwork |  |  |  |  | Yes | ST - R - Blockwork | 813139e0-b80a-4e6a-bc8d-8b8009d1e04d
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Blockwork walls completed and acceptable
checklist-flat |  |  | checklist | CST - R - Foundation Consent |  |  |  |  | Yes | CST - R - Foundation Consent | 828529dc-b47e-4edd-b7d5-227bc77ba4a7
checkpoint-status |  |  | checkpoint | Record of title
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Pre-cast concrete
boolean | d7ac7709-7c14-51d9-bb11-f9d6eeab950d |  | tickbox | Producer Statement Design(PS1): Prestressed concrete beams and floor units
boolean | 34a83e1f-c9b3-54d0-ac4b-d6c15cb2cce1 |  | tickbox | Producer Statement Construction(PS3): Prestressed concrete beams and floor units
boolean | e370969b-5ca7-52a8-ba5e-bf9d6c742505 |  | tickbox | Producer Statement Review(PS4): Prestressed concrete beams and floor units
boolean | 6c227c8b-0f23-5cec-9a5b-bc2fd8f7f4e8 |  | tickbox | Shop drawings for concrete beams and floor units
checkpoint-status |  |  | checkpoint | Producer Statement Construction(PS3): sub-soil drainage
checkpoint-status |  |  | checkpoint | Waterproofing
boolean | 276c1d7f-f3ce-5d4d-aed5-39c7516b95c4 |  | tickbox | Producer Statement Construction(PS3): Waterproofing Membrane
boolean | 5c264c89-6e73-5634-9ce8-606decb868cd |  | tickbox | Manufacturer's warranty for waterproofing membrane
checkpoint-status |  |  | checkpoint | Mill certificates
checkpoint-status |  |  | checkpoint | Concrete dockets
checkpoint-status |  |  | checkpoint | Producer Statement Review(PS4): Engineer's observation
checkpoint-status |  |  | checkpoint | Surveyor certificate for siting
checklist-flat |  |  | checklist | FC - R - Anchor Points - Intermediate, Corner and End Plate Installation |  |  |  |  | Yes | FC - R - Anchor Points - Intermediate, Corner and End Plate Installation | 848b3fd5-2f7a-4823-b3d5-55c57e44276f
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Intermediate, Corner and End Plate installation completed and acceptable
checklist-flat |  |  | checklist | CST - R - Piling Consent |  |  |  |  | Yes | CST - R - Piling Consent | 85aa18e5-1b03-4b32-9875-0dc489941f74
checkpoint-status |  |  | checkpoint | Record of Title
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Construction Review
boolean | ca3db4a7-859e-5871-88b9-c794bdf62a24 |  | tickbox | Producer Statement Review(PS4): Geotechnical
boolean | f0fbf83a-02e6-54c0-866d-88a0f1f2b635 |  | tickbox | Producer Statement Review(PS4): Compaction of hardfill
boolean | 03e8c0a2-5236-58aa-9288-fa50ca832142 |  | tickbox | Producer Statement Review(PS4): Drain Bridging
boolean | 095f6b8c-e5ab-514e-91dc-5aa2997f75d2 |  | tickbox | Producer Statement Review(PS4): Engineer's observation
checkpoint-status |  |  | checkpoint | Producer Statement Construction(PS3): Piling
checkpoint-status |  |  | checkpoint | Pile records and cards
checkpoint-status |  |  | checkpoint | Surveyor certificate for siting
checkpoint-status |  |  | checkpoint | Mill certificates
checkpoint-status |  |  | checkpoint | Concrete dockets
checklist-flat |  |  | checklist | I - C - MV Remedial Item Checklist |  |  |  |  | Yes | I - C - MV Remedial Item Checklist | 86c05298-d796-4455-98d5-8c119b46652f
checkpoint-status |  |  | checkpoint | Remedial Status (MV to "Pass" once satisfied)
text | e3f6208b-dc65-5e02-b084-d3ef97306407 |  | textbox | Location of Remedial
text | d1c22686-2863-592e-9004-e232dad5ed0b |  | textbox | Remedial Description
text | b65d491e-2590-5d9e-a0be-de78c084a544 |  | textbox | Action Required
holdpoint |  |  | signoff | Request MV Signoff on Remedial
checklist-flat |  |  | checklist | C - R - Detailed Excavation |  |  |  |  | Yes | C - R - Detailed Excavation | 87a63050-dfa1-40a3-aede-3fe983b0369b
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Excavation completed - Correct locations and RL's achieved
checklist-flat |  |  | checklist | ST - R - Precast Wall Panel Installation |  |  |  |  | Yes | ST - R - Precast Wall Panel Installation | 88322a4e-b069-4906-a4ba-c082465992e0
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Wall Panel Installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - Exterior Timber Framing |  |  |  |  | Yes | FC - R - Exterior Timber Framing | 88ed059d-6715-46c3-a62f-3f06d18aada1
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Exterior Timber Framing works completed and acceptable
checklist-flat |  |  | checklist | FC - R - STO Poly Plaster |  |  |  |  | Yes | FC - R - STO Poly Plaster | 8b7d6620-e229-4439-b6ed-5677223bfd58
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | STO Poly Plaster works completed and acceptable
checklist-flat |  |  | checklist | C - R - Lift Pit Installation |  |  |  |  | Yes | C - R - Lift Pit Installation | 8d5385bf-2029-4987-8674-ea796f660132
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Lift Pit installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - Envelope Penetrations |  |  |  |  | Yes | FC - R - Envelope Penetrations | 8f773312-5be6-4397-9a31-a2d16e525e36
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Envelope Penetrations completed and acceptable
checklist-flat |  |  | checklist | FC - R - Ecoply Board |  |  |  |  | Yes | FC - R - Ecoply Board | 926d7fbf-5445-4749-a401-4dca4151e94d
checkpoint-status |  |  | checkpoint | Fixing and spacings checked in accordance with manufacturers specs.
checkpoint-status |  |  | checkpoint | Bracing checked and accurate
checkpoint-status |  |  | checkpoint | Penetrations and punctures sealed with flashing tape
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Ecoply board installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - Eyebrow - Canopy |  |  |  |  | Yes | FC - R - Eyebrow - Canopy | 929a9ce8-8d1b-400d-bb3b-2fd5b01516b2
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Eyebrow - Canopy works completed and acceptable
checklist-sectioned |  |  | checklist | ITP - R - Detention Tank Installation (Per Tank) |  |  |  |  | Yes | ITP - R - Detention Tank Installation (Per Tank) | 937ec8bb-4c75-4fb1-b13f-685395be4ec8
checkpoint-group |  |  | section | ITP - R - Detailed Excavation
checkpoint-status |  |  | checkpoint | Grids/profiles/set out completed, clearly marked and accurate
checkpoint-status |  |  | checkpoint | Excavation depths and locations confirmed prior to detailed excavation commencing
checkpoint-status |  |  | checkpoint | Services (overhead / below ground) identified, isolated where required before excavation commences
checkpoint-status |  |  | checkpoint | Approval given to commence detailed excavation
checkpoint-status |  |  | checkpoint | Excavation checked, correct and approved
button | ccdefa56-d077-5260-89cc-977aec3c59f6 |  | button | Location accurate | Yes, Reworked, N/A
button | 3586ef1b-e219-588a-965f-875fedaa72df |  | button | Depth correct (allow for site concrete if required) | Yes, Reworked, N/A
button | ec4bab1b-f1b6-52b5-be89-0ff58fcc6f26 |  | button | Width correct (allow for boxing if required) | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Placement of Geotextile (2 photos required)
checkpoint-status |  |  | checkpoint | Placement of hardfill
checkpoint-status |  |  | checkpoint | Placement of Geogrid (2 photos)
checkpoint-status |  |  | checkpoint | NDM test and report (supporting documents incl. photos)
checkpoint-status |  |  | checkpoint | Completed level of hardfill (completion NDM test with report and supporting documents (incl. photos) and uploaded into QA system)
checkpoint-status |  |  | checkpoint | Any additional layer of hardfill (300mm) requires an NDM test (report and supporting documents (incl. photos) sent uploaded into QA system
holdpoint |  |  | signoff | Sand blinding and check final RL. (completion required to handover to the next stage-townhouses only)
checkpoint-status |  |  | checkpoint | Excavation for services is completed and accurate
checkpoint-status |  |  | checkpoint | Excess material cleaned up and removed as required
checkpoint-status |  |  | checkpoint | Detailed excavation completed, reviewed and approved
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checkpoint-group |  |  | section | Underground Detention Chambers
checkpoint-status |  |  | checkpoint | Geotextile laid as specified
checkpoint-status |  |  | checkpoint | Underdrain laid as per the specifications
checkpoint-status |  |  | checkpoint | Angular stone laid as specified pre-installation of chambers
checkpoint-status |  |  | checkpoint | Chambers installed as per the specifications
checkpoint-status |  |  | checkpoint | DIA riser, ring, cover and concrete collar installed as per the specifications
checkpoint-status |  |  | checkpoint | Connections to manholes completed and approved
checkpoint-status |  |  | checkpoint | Angular stone laid as specified post installation of chambers
checkpoint-status |  |  | checkpoint | Pipe laying completed as per the specifications
checkpoint-status |  |  | checkpoint | Backfill completed & compacted as per the specifications
checkpoint-status |  |  | checkpoint | Scour protection sheet base installed as per the specifications
checkpoint-status |  |  | checkpoint | 3 layers of Duragrid (or other specified product) on top of subgrade as per the specifications
checkpoint-status |  |  | checkpoint | Confirmation of inspection port with Engineer prior to installation
checkpoint-status |  |  | checkpoint | Inspection port installed as per specification and location agreement with Engineer
checkpoint-status |  |  | checkpoint | Coil installation as per specification
checkpoint-status |  |  | checkpoint | Chambers completed, reviewed, and approved
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - R - Precast Spandrel Panel Installation |  |  |  |  | Yes | ST - R - Precast Spandrel Panel Installation | 9584bc60-7e29-4ffe-b086-c6493f918ee3
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Spandrel Panel Installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - Passive fire |  |  |  |  | Yes | FC - R - Passive fire | 973c3731-df3b-4da7-bc67-4d5fe14b099c
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Passive Fire works completed and acceptable
checklist-flat |  |  | checklist | C - R - Service Trenches - Pulling Pits |  |  |  |  | Yes | C - R - Service Trenches - Pulling Pits | 97657517-3efa-44b9-bbd1-b5ea91471072
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Pulling Pits trench works completed as per the specifications
checklist-flat |  |  | checklist | Add Photos/Files |  |  |  |  | Yes | Add Photos/Files | 9bc45907-b43b-48d6-9e6a-f7ff92a27020
checkpoint-no-status |  |  | checkpoint | Add Photos/Files here
checklist-flat |  |  | checklist | ST - R - Roof structure - Timber Trusses |  |  |  |  | Yes | ST - R - Roof structure - Timber Trusses | 9c03b785-fb4a-480b-bf7b-de746b113c03
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All timber trusses correctly installed in respective area and acceptable
checklist-flat |  |  | checklist | F - R - Sheet Piling |  |  |  |  | Yes | F - R - Sheet Piling | a0b7c765-c7a1-472e-9d8b-d57b319424cd
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Sheet pile installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - RAB Board |  |  |  |  | Yes | FC - R - RAB Board | a1d8d403-96ba-4af6-a3e1-c08e8298c5d1
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | RAB Board works completed and acceptable
checklist-flat |  |  | checklist | CST - R - Demolition Consent |  |  |  |  | Yes | CST - R - Demolition Consent | a30cbad0-01dd-44dc-a927-c09162c250b7
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection passed
checkpoint-status |  |  | checkpoint | Summary Sheet - Site inspection records
checkpoint-status |  |  | checkpoint | Summary Sheet - LBP Records
checkpoint-status |  |  | checkpoint | Asbestos - Asbestos Clearance Certificates & PS3
checkpoint-status |  |  | checkpoint | Demolition - PS3
checklist-flat |  |  | checklist | PRE - R - PRE-line |  |  |  |  | Yes | PRE - R - PRE-line | a8c6cf57-910e-42ca-8602-7283b1c39cd7
checkpoint-status |  |  | checkpoint | PRE-line works completed and acceptable. Trades QA received, reviewed, attached and approved for all pre-line trades. Approved to line the area.
checkpoint-status |  |  | checkpoint | Timber frame installation completed and acceptable
checkpoint-status |  |  | checkpoint | Steel Stud frame installation completed and acceptable
checkpoint-status |  |  | checkpoint | Electrical First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Plumbing First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Security, Comms and Data First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | HVAC First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Fire Security First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Underfloor heating First Fix (including screeding and soundproofing of the bathrooms/ wc) completed and acceptable
checkpoint-status |  |  | checkpoint | Kitchen extract First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Insulation installation completed and acceptable
checkpoint-status |  |  | checkpoint | Passive fire installation completed and acceptable
checkpoint-status |  |  | checkpoint | Suspended ceiling grids installation completed and acceptable
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checklist-flat |  |  | checklist | ITP - R - Fitout (per unit) |  |  |  |  | Yes | ITP - R - Fitout (per unit) | a9cdf1d2-4f65-4403-b309-1bfcf65abc78
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | Bathroom completed and signed off.
checkpoint-status |  |  | checkpoint | Open living room area completed and signed off.
checkpoint-status |  |  | checkpoint | Kitchen area completed and signed off.
checkpoint-status |  |  | checkpoint | Toilet completed and signed off.
checkpoint-status |  |  | checkpoint | Bedroom 1 (1st clockwise from front door) completed and signed off.
checkpoint-status |  |  | checkpoint | Bedroom 2 (2nd clockwise from front door) completed and signed off.
checkpoint-status |  |  | checkpoint | Bedroom 3 (3rd clockwise from front door) completed and signed off.
checkpoint-status |  |  | checkpoint | Walk in/through wardrobe area completed and signed off.
checkpoint-status |  |  | checkpoint | Hall (and closets) completed and signed off.
checkpoint-status |  |  | checkpoint | Laundry area completed and signed off.
checkpoint-status |  |  | checkpoint | Garage completed and signed off.
checkpoint-status |  |  | checkpoint | Cleanliness and general items completed and signed off.
checkpoint-status |  |  | checkpoint | External and Hardscape completed and signed off.
checkpoint-status |  |  | checkpoint | Client extras / other unit specific items completed and signed off.
checkpoint-status |  |  | checkpoint | Upload Related Ryman Fitout quality inspection record (QT-012)
checklist-flat |  |  | checklist | C - R - Bulk Excavation |  |  |  |  | Yes | C - R - Bulk Excavation | ab266035-317a-4536-be0d-4f756f4fa8e1
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Excavation completed - Correct locations and RL's achieved
checklist-sectioned |  |  | checklist | ITP - R - Apartment Facade (per elevation/grid) |  |  |  |  | Yes | ITP - R - Apartment Facade (per elevation/grid) | abc941f5-7fc5-4bbf-8968-cf73c4f6e9a5
checkpoint-group |  |  | section | Façade
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | All Envelope/Watertightness Completed (requirements below)
checkpoint-status |  |  | checkpoint | Ecoply Board installed
checkpoint-status |  |  | checkpoint | Lintels installed
checkpoint-status |  |  | checkpoint | Tapes and VaproShield installed.
checkpoint-status |  |  | checkpoint | Windows and Sliders installed
checkpoint-status |  |  | checkpoint | Flashing installed
checkpoint-status |  |  | checkpoint | Envelope Penetrations completed
checkpoint-status |  |  | checkpoint | Balcony waterproofing completed
checkpoint-status |  |  | checkpoint | Council pre-wrap inspection completed and passed
checkpoint-status |  |  | checkpoint | Water tightness test performed. No leaks. Witnessed by Ryman. Record name of contractor who conducted the test in the comments section.
button | 61d53c6f-f9b0-5ac1-938b-5ccf31ea00b1 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council brickwork 'half-high' inspection completed and acceptable
button | adc5007d-d48e-51f5-9cd3-8ccb5cf00be6 |  | button | Note remedial work needed | None, Minor, Major
text | f016c7a2-ebc5-5144-97d9-eb6104827917 |  | textbox | Describe cladding type:
button | 77186810-676c-5e09-985c-b9f31873fd22 |  | button | Brick Works completed | Yes, Reworked, N/A
button | 9c1e396f-7021-58b9-aa73-c21846dccf16 |  | button | STO Poly Plaster completed | Yes, Reworked, N/A
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Installed horizontal fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed vertical fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Eyebrow and soffit fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Boss Bulkhead Batt fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Gutter fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Concrete Panels (under roof) fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Hatches fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Consultant Inspections Completed and Passed
button | 49269d68-3ad5-5d2e-b32e-882217f17795 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 9926c7d5-86ef-5508-8ac1-4b26e2fc8206 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Balustrade Testing
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Balustrade Anchor Bolt Pull Testing
label | d9afd45d-fc2d-581d-8525-2d19fd591450 |  | note | Test results to be uploaded
checkpoint-status |  |  | checkpoint | Balustrade Lateral Load Testing
label | 4efad0ca-fb3f-5320-8f58-02412040bc3a |  | note | Test results to be uploaded
checkpoint-status |  |  | checkpoint | Consultant Inspections Completed and Passed
button | f2a31249-a68f-5181-bd61-1e901d90fbdb |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 3480d9fc-ceb0-544d-9ccb-73fcccddfb0c |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-flat |  |  | checklist | CST - R - Mechanical Constant |  |  |  |  | Yes | CST - R - Mechanical Constant | ac93d8ff-a51c-4432-b662-469826693c40
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Electrical
boolean | db3c1dab-0890-5db4-8b10-7b5b0e472cf2 |  | tickbox | Electrical compliance and safety certificate
boolean | cf64e129-c047-5f6d-b5ed-b13f86983f8f |  | tickbox | record of inspections for high risk works
checkpoint-status |  |  | checkpoint | Automatic doors
boolean | 639b5b76-8084-5bba-b066-49cbb0acac18 |  | tickbox | Producer Statement Construction(PS3): automatic door installation and failsafe override
boolean | 16259294-39e1-5e55-930c-544ba1b01883 |  | tickbox | As built documentation; plans, operation and maintenance manual
checkpoint-status |  |  | checkpoint | Access controlled doors
boolean | d7f9205a-be40-565c-a41e-044d3d112f50 |  | tickbox | Producer Statement Construction(PS3): installation of access control to doors and failsafe override
boolean | a8702d7d-a7d8-5a3a-9299-43123494adef |  | tickbox | As built documentation; location of systems, the make of the systems and operation manuals
checkpoint-status |  |  | checkpoint | Escape route pressurization systems
boolean | a3833fb7-f141-589c-a536-178e902673e6 |  | tickbox | Producer Statement Construction(PS3): Installation of escape route pressurization systems from approved mechanical contractor
boolean | ede9cf4a-5d8e-518d-8431-41acd889176c |  | tickbox | Producer Statement Review(PS4): Installation of escape route pressurization systems from approved mechanical contractor
boolean | 83a17516-53ad-514d-b72e-51e9fd3a9dcb |  | tickbox | test/commissioning results verifying measured airflow rates meet design and interface with alarm system
boolean | a76c96bd-996c-5a59-bb3c-b3c904e27c7c |  | tickbox | As built documentation; equipment schedules and make of systems, operation and maintenance manuals
boolean | 64d062de-eca5-5c40-8765-d5197fa2541c |  | tickbox | Electrical work certificate
checkpoint-status |  |  | checkpoint | Passenger Carrying Lifts
boolean | 2cf04f70-0cd6-59d5-9c52-d8dda758a1e9 |  | tickbox | Codemark construction certification and inspection/maintenance sheets
checkpoint-status |  |  | checkpoint | Mechanical ventilation or air conditioning system
boolean | 1e8cc167-8b4b-5cf9-8599-bca9b835e458 |  | tickbox | Producer Statement Construction(PS3): Kitchen extract system (compliance with NZBC G4)
boolean | 26b7a7a9-74b2-589a-9873-28bdc2a2e9c1 |  | tickbox | Producer Statement Construction(PS3): Confirmation from mechanical contractor the systems comply with NZBC G4
boolean | 753666d4-8c4d-5e70-893e-7b3a1fe30c87 |  | tickbox | Producer Statement Review(PS4): Confirmation from council approved mechanical engineer that the systems comply with NZBC G4
boolean | 457b29ff-55e0-566f-bbf0-763d0e8af7bf |  | tickbox | Producer Statement Review(PS4): Installation of seismic restraints in accordance with NZS 4219:2009:"Seismic Performance of Engineering Systems in Buildings"
boolean | 8ff6a3d3-ef05-5ed3-995d-cf07f9c4a4d2 |  | tickbox | test/commissioning results verifying measured airflow rates meet design and interface with alarm system
boolean | 8a2174e9-417d-5493-a9df-c6ae6439e541 |  | tickbox | As built documentation; equipment schedules and make of systems, operation and maintenance manuals
checkpoint-status |  |  | checkpoint | Application for compliance schedule (AC2102)
checkpoint-status |  |  | checkpoint | Confirmation of performance standards for specified systems (AC2150)
checklist-flat |  |  | checklist | FC - R - Symonite Alucobond Cladding System |  |  |  |  | Yes | FC - R - Symonite Alucobond Cladding System | af1752ed-38ad-4a21-98fe-ab4393a7540c
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Exterior Tiling works completed and acceptable
checklist-flat |  |  | checklist | I - C - T+T Remedial Item Checklist |  |  |  |  | Yes | I - C - T+T Remedial Item Checklist | afa45f86-2ed2-4b2a-9cc1-5300f2d2e1bb
checkpoint-status |  |  | checkpoint | Remedial Status (T+T to "Pass" once satisfied)
text | 19e241f0-7ae3-5d48-987a-4354c817e187 |  | textbox | Location of Remedial
text | e5e99f5a-d736-55a1-a642-e735130d19f8 |  | textbox | Remedial Description
text | 5c3f7bf5-68c3-5dc7-9059-a60f0be3b001 |  | textbox | Action Required
holdpoint |  |  | signoff | Request T+T Signoff on Remedial
checklist-flat |  |  | checklist | ST - R - Monier Tiled Roof Installation |  |  |  |  | Yes | ST - R - Monier Tiled Roof Installation | b0e21eda-978a-4078-9137-b51bc6f0c0e6
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Monier Installation Guide Confirmed with Contractor
checkpoint-status |  |  | checkpoint | Subcontractor QA completed and passed
checkpoint-status |  |  | checkpoint | Fall Arrest Anchor Point Fixings in place
checkpoint-status |  |  | checkpoint | Producer Statement Construction (PS3) received and attached for installation of roof abseil and/or fall arrest system
checkpoint-status |  |  | checkpoint | Battens - jointing and fixing.
checkpoint-status |  |  | checkpoint | Sarking/Underlay
checkpoint-status |  |  | checkpoint | Tiles Laid and Secured
checkpoint-status |  |  | checkpoint | Hip and Ridge Tile Bedding and Pointing
checkpoint-status |  |  | checkpoint | Gable ends / Barge Boards - Finish
checkpoint-status |  |  | checkpoint | Fire Wall/Internal Separating Walls
checkpoint-status |  |  | checkpoint | Fire Consultant inspection completed and approved
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
text | d75d99bb-7679-5cbc-a8b2-57d8aede25b5 |  | textbox | Note remedial work needed
holdpoint |  |  | signoff | Raise remedial as required.
checklist-sectioned |  |  | checklist | POST - R - Stair Well Guard and Hand Rail Testing (per stage) |  |  |  |  | Yes | POST - R - Stair Well Guard and Hand Rail Testing (per stage) | b6a71ba0-6af3-48a8-8135-0627c3040029
checkpoint-group |  |  | section | Guard Rail Pull and Load Testing
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Bolt pull testing completed and passed. Test results received and confirmed.
text | f6dea486-6b4b-55da-8cc6-2a7a72e81c9c |  | textbox | Record quantity tested
text | 96754e52-cf36-563f-9ce3-73f1fd37a600 |  | textbox | Record sample size (%)
checkpoint-status |  |  | checkpoint | Lateral load pull testing completed and passed. Test results received and confirmed.
text | 21413bb5-2624-5baf-80b6-ba7889dd55cd |  | textbox | Record quantity tested
text | f6a2da7c-8e0c-565d-b0bb-5d245d00ad48 |  | textbox | Record sample size (%)
text | e37fd4f2-ac9c-5cb5-ad7a-c0bd285947c7 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Handrail Load Testing
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Load testing to NZS 4121:2001 completed and passed. Test results received and confirmed.
text | cb742394-7bde-5471-b09a-2a1365e05da9 |  | textbox | Record quantity tested
text | 7c6824a0-014d-5ac9-9830-f481f2bd8f48 |  | textbox | Record sample size (%)
text | 64131531-0b6f-5a57-a339-08aa0ac7745c |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checklist-flat |  |  | checklist | ITP - R - Hardscaping (per area/location) |  |  |  |  | Yes | ITP - R - Hardscaping (per area/location) | bb2dc9c7-2363-4a1c-b1fe-52e36db0dad7
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Photograph the drawing number and revision of the drawing being implemented.
checkpoint-status |  |  | checkpoint | Street Lighting - locations.
checkpoint-status |  |  | checkpoint | Bollard Lighting - locations.
checkpoint-status |  |  | checkpoint | Letterbox - locations.
checkpoint-status |  |  | checkpoint | Letterbox - materials and colour.
checkpoint-status |  |  | checkpoint | EV charger - location/s.
checkpoint-status |  |  | checkpoint | Main footpath/s - material and finish.
checkpoint-status |  |  | checkpoint | Main footpath/s - Pipework ducting installed prior to pour
checkpoint-status |  |  | checkpoint | Townhouse footpath/s - material and finish.
checkpoint-status |  |  | checkpoint | Main footpath/s - layouts and gradients.
checkpoint-status |  |  | checkpoint | Townhouse footpath/s - layouts and gradients.
checkpoint-status |  |  | checkpoint | Townhouse footpath/s - Pipework ducting installed prior to pour
checkpoint-status |  |  | checkpoint | All pathways - edging.
checkpoint-status |  |  | checkpoint | Raised pedestrian crossing/s - material and finish.
checkpoint-status |  |  | checkpoint | Flush pedestrian crossing/s - material and finish.
checkpoint-status |  |  | checkpoint | Paved area/s - materials, pattern, and edging.
checkpoint-status |  |  | checkpoint | Driveways - materials and finish.
checkpoint-status |  |  | checkpoint | Driveways - Pipework ducting installed prior to pour
checkpoint-status |  |  | checkpoint | Brick wall - materials and finish.
checkpoint-status |  |  | checkpoint | Brick wall - pipework ducting installed
checkpoint-status |  |  | checkpoint | Aluminium fencing/rails/hand rails installed - materials and finish.
button | b15305fe-ce59-5278-b618-8b9be4d3720b |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checklist-flat |  |  | checklist | ITP - R - Landscaping (per area/location) |  |  |  |  | Yes | ITP - R - Landscaping (per area/location) | bb4bdae4-e9b0-426e-bcd6-f1c6f7f56867
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Verify all dimensions, boundaries, and underground services before commencement of work
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Photograph the drawing number and revision of the drawing/s being implemented.
checkpoint-status |  |  | checkpoint | Lawn and garden beds meets landscaping layout plan dimensions
checkpoint-status |  |  | checkpoint | Lawn and planting bed areas meets landscape preparation specification
checkpoint-status |  |  | checkpoint | Plants laid out and planted as per plan
checkpoint-status |  |  | checkpoint | Trees and hedging laid out and planted as per plan
checkpoint-status |  |  | checkpoint | Root guards installed as required.
checklist-sectioned |  |  | checklist | ITP - R - Services |  |  |  |  | Yes | ITP - R - Services | bb7c9818-11bc-424f-9558-6d9384332cb8
checkpoint-group |  |  | section | Residential Apartment/Townhouse Unit
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Fire - Alarm, Hydrant & Sprinkler completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Nurse Call, Security, Data and Communications completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Hydraulic completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Electrical completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Mechanical completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 17a299a6-0803-59a3-866a-ce17ac25475d |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Common, Recreational & Service Areas
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Specified Systems - Hydrant, Fire Alarms, Sprinklers completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Alarms, Manual/Automatic completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Gas Detection completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Nurse Call completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Access Controlled Doors completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Interfaced Fire/Smoke Doors/Windows/Security completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Hydraulic completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Lifts completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Mechanical, fresh air and duct extract system completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Mechanical, kitchen extract + air conditioning system completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Smoke Curtains completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Essential Power Supply completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Emergency Signage + Exits & Emergency Lighting completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Swimming Pool - Plant completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Fire Engineer inspection completed and approved
button | fd810e48-d1c4-56cc-a4f6-e86f69ac2cbf |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Electrical Engineer inspection completed and approved
button | 4fb16691-6f68-5a9a-9433-8da80e9bfd40 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Mechanical / Hydraulic Engineer inspection completed and approved
button | 1807fe0d-ba7a-5fc0-8a08-487c87c64f15 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | ca1fa69c-a8fe-5421-9709-7f650358cfe6 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checklist-flat |  |  | checklist | CST - R - Fire Consent |  |  |  |  | Yes | CST - R - Fire Consent | bcdd4ec2-eb37-4ff9-b951-8c92d1e044c4
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Electrical
boolean | e70af78d-7199-58e7-86c1-12bcfb5abd89 |  | tickbox | Electrical compliance and safety certificate
boolean | eb0b74a8-08e2-5f3f-a5fb-a30b3d81160a |  | tickbox | record of inspections for high risk works
checkpoint-status |  |  | checkpoint | Fire rated (Intumescent) Coatings to Structural Steel
boolean | 53b40ba8-f599-588a-aee8-764f5e18a718 |  | tickbox | Producer Statement Construction(PS3 - AC2334): Intumescent coatings to structural steel from approved applicator
boolean | 61afa040-031a-5ef8-a646-99c49abf74e1 |  | tickbox | Suppliers material schedule - products used and thicknesses applied
boolean | 2bd1f2cc-07b3-5f58-9cc0-32910ff9d311 |  | tickbox | Floor plan of intumescent coating locations
checkpoint-status |  |  | checkpoint | Fire Rated and Stopping Systems
boolean | 8bca4be1-bb49-5139-a954-dec53c3805c4 |  | tickbox | Producer Statement Construction(PS3): Fire stopping of penetrations(collars, wraps, sealants) for Plumbing, Mechanical, Ventilation and Communication services
boolean | bbdbd87d-1515-54b0-a33c-373564f58e74 |  | tickbox | Fire rated penetration Schedule: Plumbing, Mechanical, Ventilation and Communication Services
boolean | 7c8ae495-6676-536b-a49c-620b1db709dd |  | tickbox | As built plans: penetrations
boolean | b2d34ba2-3995-5d00-a638-bf92ec45f87f |  | tickbox | Producer Statement Construction(PS3): Installed fire rated constructions; fire rated walls, partitions, floors and ceilings to show fire rating
boolean | 66656b75-6265-59aa-8b86-2938d70dadd0 |  | tickbox | Fire door declaration documentation and register of door sets by the manufacturer (refer NZS4520: 2010 clause 6.4.3
checkpoint-status |  |  | checkpoint | Sprinkler systems
boolean | 67bdc5af-c9a4-56c4-ab9e-5f1c5d16607d |  | tickbox | Producer Statement Construction(PS3): Automatic sprinkler system (in compliance with NZS4514:2013)
boolean | d360c4d4-b4da-5320-9339-03017f974a98 |  | tickbox | Accredited inspection company's automatic sprinkler system certification confirming compliance with NZS4514:2013
boolean | 92675bee-0d5b-5980-948a-6794732bb5c0 |  | tickbox | As built documentation; sprinkler block plan, equipment manufacture register
checkpoint-status |  |  | checkpoint | Manual and Automatic fire alarms
boolean | da6cde41-8f62-5838-9ced-a58a3bacf88c |  | tickbox | Producer Statement construction(PS3): Manual/automatic fire alarm in compliance with NZS4512:2010
boolean | d613f967-763f-5e57-be8c-5f7066c96424 |  | tickbox | Accredited inspection company's fire alarm certification confirming compliance with NZS4512:2010 (new system)
boolean | 70fa70a2-8e61-58af-b386-72ebea659def |  | tickbox | As built documentation; zone index plan, operation manual and maintenance manual
checkpoint-status |  |  | checkpoint | Riser Mains for use by fire services
boolean | 589b5b13-3863-589e-af13-d283b66e2a8f |  | tickbox | Producer Statement Construction(PS3): fire hydrant riser confirming compliance with NZS4510:2008
boolean | 20eaf32f-8926-5073-b2d4-3cd7d1556867 |  | tickbox | Certificate of Compliance or Verification Report for fire hydrant riser confirming compliance with NZS4510:2008
boolean | 76cda403-3aaf-5cab-956a-f6e51707ac84 |  | tickbox | As built documentation; fire hydrant schematic as built
checkpoint-status |  |  | checkpoint | Emergency Lighting systems
boolean | 21cc874e-11f7-5800-a80d-c13bbff77f1d |  | tickbox | Producer Statement Construction(PS3): Emergency lighting from electrical contractor confirming compliance with NZBC F6
boolean | b0442266-ccfa-5a63-ad5c-f5d1e00d0335 |  | tickbox | Producer Statement Review(PS4): Emergency Lighting from council approved electrical engineer confirming compliance with NZBC F6
boolean | 965071e2-f2f0-56b4-91cc-5b8d3c7b5e3b |  | tickbox | Duration test results for emergency light fitting from electrical contractor or IQP
boolean | a6030d50-feb4-5f23-8487-9e00e9d134ed |  | tickbox | Lux test results for the emergency lighting system
boolean | 49f66d48-14a5-5c07-96e9-141a2f36d766 |  | tickbox | As built plan with model of systems installed
boolean | 11df21be-ae66-50b2-b889-28208f2faf35 |  | tickbox | Electrical work certificate
checkpoint-status |  |  | checkpoint | Fire separation that forms part of the means of escape from fire
boolean | 938ed61d-fabd-597e-b09a-1002fc759c07 |  | tickbox | As built plans confirming final location of Fire separation that forms part of the means of escape from fire
checkpoint-status |  |  | checkpoint | Smoke separation that forms part of the means of escape from fire
boolean | 1740d87c-97ae-597a-864d-9f0a63d26b71 |  | tickbox | As built plans confirming final location of walls forming a protected path in a building, smoke resistant lift lobby, smoke stop door, smoke cell
checkpoint-status |  |  | checkpoint | interfaced fire or smoke doors on windows
boolean | d81ec07b-b4ab-5915-9638-deb1f96ad8da |  | tickbox | Producer Statement Construction(PS3): installation of magnetic door holders
boolean | 3d53718d-1d22-5e9d-b5e4-a5bcbfb61234 |  | tickbox | As built documentation; location of systems, the make of the systems, operation manuals and maintenance manuals
checkpoint-status |  |  | checkpoint | final exits
boolean | 1c2cccdd-f3d7-5b1d-b686-78e7cd565adc |  | tickbox | as built plans confirming location of final exit (include info on if any doors are automatic or access controlled)
checkpoint-status |  |  | checkpoint | Signs for all systems
boolean | 938047d5-d98f-591d-b48f-126777f2c371 |  | tickbox | SS 1/1: Sign showing maximum storage heights
boolean | c8fb06e7-4e6f-56a4-98d5-9c7b01b1f90c |  | tickbox | SS 2/1: Sign showing how to operate a fire alarm call point
boolean | 8929b91e-eda9-509b-b35e-25739ab3b8e2 |  | tickbox | SS 3/1: Sign showing location of accessible automatic
boolean | 0d860d00-ec76-5c54-8a8b-f3628fc04567 |  | tickbox | SS 3/2: Sign showing and automatic closing fire or smoke door
boolean | b54010f6-4e8a-55e5-8b8b-804955441075 |  | tickbox | SS 3/2: Sign showing location of an emergency door release on access control doors
boolean | 75b825bc-f164-554c-bcff-383140b6ae48 |  | tickbox | SS 8/1: Sign showing location of accessible lift
boolean | 17956630-6eff-5da5-ad38-74d5d764d3fc |  | tickbox | Sign showing not to use the lift in event of fire
boolean | 30d1bb34-7d43-5183-aa8c-032a06852a87 |  | tickbox | Sign showing lift load ratings
boolean | 575d7683-d78e-504f-b148-8861e44bfc23 |  | tickbox | SS 8/3: Sign showing hazards to escalators and moving walks
checkpoint-status |  |  | checkpoint | Fire safety construction review
boolean | 449328db-ccf8-5643-923b-b543cd0101d2 |  | tickbox | Producer Statement Review(PS4): council approved fire engineer to confirm systems conform with the relevant NZBC clauses and fire reports
checkpoint-status |  |  | checkpoint | Application for compliance schedule (AC2102)
checkpoint-status |  |  | checkpoint | Confirmation of performance standards for specified systems (AC2150)
checklist-flat |  |  | checklist | C - R - Pipe Laying |  |  |  |  | Yes | C - R - Pipe Laying - Stormwater | c6e125dc-6c59-4652-9b43-28979728a3fc
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Wastewater pipe laying completed as per the specifications
checklist-flat |  |  | checklist | FC - R - Brick Works |  |  |  |  | Yes | FC - R - Brick Works | cd7784ee-db34-4219-948e-4cc3eecc25b9
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Brick works completed and acceptable
checklist-sectioned |  |  | checklist | I - C - Woods Consultant Site Visit Report |  |  |  |  | Yes | I - C - Woods Consultant Site Visit Report | d2ab6bba-42d4-4a1c-8620-16e7846216bb
checkpoint-group |  |  | section | Site Details & Inspection Specifics
checkpoint-status |  |  | checkpoint | All Site Details Inputted Below
text | c7666fe1-eea7-5229-ab18-1a7b4b445a5b |  | textbox | SVR#
text | bc8a1d48-39f8-568b-99f6-df6b60fc55aa |  | textbox | Area of site visited
text | acd88094-541c-551a-b3ae-02fef8aefcbd |  | textbox | Purpose of visit
text | f4c1a790-ba51-5254-8b06-2686aecdd159 |  | textbox | Date site visit occurred
text | ba1e7dd7-5b96-501a-94c5-634b864b2e90 |  | textbox | Time on site (Include start & end time)
text | 3bf08613-de5a-5598-bb1a-0d3406ba005a |  | textbox | Weather
text | 140932da-3b53-589b-8a3e-3e349b066440 |  | textbox | Report prepared by - Engineer's name
text | d072b9d0-b14c-5dda-be76-836258584420 |  | textbox | Additional personnel accompanying engineer
checkpoint-status |  |  | checkpoint | Health and Safety Observations recorded/photos attached
checkpoint-status |  |  | checkpoint | Dust / Erosion and Sediment Control Observations recorded / photos attached
checkpoint-status |  |  | checkpoint | Consented drawings have been followed
text | fbce4287-8f04-5858-84a7-dfe98e44993e |  | textbox | Drawing & Revision Number(s)
checkpoint-status |  |  | checkpoint | General comments, photos and observations during inspection
label | 28f8de27-f01c-557d-ac69-826c3b16657b |  | note | Capture relevant photos specific to this site visit report
button | 1764163c-23aa-53eb-8514-7d3a9b606401 |  | button | Has contractors pre-inspection QA been reviewed? | Yes, No
label | 3c005344-0f64-55a8-b66c-6e2b18802847 |  | note | Select "Yes" if pre-inspection QC/QA has been viewed & detail below / attach examples
label | 722781b5-f93b-58c1-8ed6-ccd5b419127e |  | note | Select "No" detail why no QC/QA has been viewed/referenced below
checkpoint-status |  |  | checkpoint | Works accepted and may proceed (select Pass) or re inspection required to defective elements (select Fail - Works Cannot Proceed)
select | cbd4ea9c-da73-55c4-8d34-75fbabd23c4a |  | dropdown | Select appropriate outcome | PASS - no remedial work, PASS - Remedial action needed to proceed, FAIL - Stop works (fail checkpoint).
label | 46338132-3fed-509d-a52e-20793055c102 |  | note | Photographic evidence to close out remedial items is required prior to pouring concrete or completing works. Proceeding without the engineer’s approval is at the Contractor’s risk
checkpoint-status |  |  | checkpoint | Remedials raised against Main Contractor
holdpoint |  |  | signoff | Raise Remedial Request
checklist-flat |  |  | checklist | FC - R - Anchor Points - Anchor Point Installation |  |  |  |  | Yes | FC - R - Anchor Points - Anchor Point Installation | d34e89cc-6712-4863-bc08-84d181879d47
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Anchor point installation completed and acceptable
checklist-flat |  |  | checklist | CST - R - Site Inspection Details |  |  |  |  | Yes | CST - R - Site Inspection Details | d7985c5d-c6be-4639-af07-3fc08a181728
checkpoint-status |  |  | checkpoint | Specific site works location
checkpoint-status |  |  | checkpoint | Contractor QA reviewed and approved
checkpoint-status |  |  | checkpoint | Have the consented drawings been followed?
checkpoint-status |  |  | checkpoint | General comments, photos, and observations during inspection
checkpoint-status |  |  | checkpoint | Works completed to required specifications - Engineer signoff
checklist-flat |  |  | checklist | C - R - Manhole Installation |  |  |  |  | Yes | C - R - Manhole Installation | d9776d83-1fcb-48fc-966b-172f1f6f8d41
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Manhole Installation completed as per the specifications
checklist-sectioned |  |  | checklist | ST - R - Concrete Pour Inspection |  |  |  |  | Yes | ST - R - Concrete Pour Inspection | da07336f-2cf9-4599-a417-ab8759ee2931
checkpoint-group |  |  | section | IMMEDIATELY PRIOR TO POUR
checkpoint-no-status |  |  | checkpoint | IMMEDIATELY PRIOR TO POUR
text | 584f5b77-8f97-5a2d-916b-4fd2aeeefcf2 |  | textbox | Confirm temperature on site is within allowable range to pour (Deg C)
boolean | 878f70ca-a3d2-559f-9a21-2dbaa781f3ac |  | tickbox | If air temp > 32°C then confirm aliphatic alcohol to be applied.
boolean | f969a60a-34b8-5455-a222-9e75f53428df |  | tickbox | Rain forecast?
checkpoint-status |  |  | checkpoint | Confirm concrete tester is onsite to take samples (slump & cylinder) as per approved testing rate
checkpoint-status |  |  | checkpoint | Confirm agreed concrete truck turn around times and supply rate with supplier
checkpoint-status |  |  | checkpoint | Confirm maximum waiting time with concrete supplier
checkpoint-status |  |  | checkpoint | Confirm positioning of pump is adequate to place concrete in a safe and timely manner
checkpoint-status |  |  | checkpoint | Confirm all required access permits, traffic control and the like are in place for movements of concrete trucks and pumps
checkpoint-status |  |  | checkpoint | Reinforcement installed as per structural design
checkpoint-group |  |  | section | DURING CONCRETE POUR
checkpoint-status |  |  | checkpoint | Concrete dockets - attach photo of each docket to this item
checkpoint-status |  |  | checkpoint | Confirm delivery docket complies with mix design prior to dispatching concrete, check for MPA, slump tolerance, max. time from plant to discharge.
checkpoint-status |  |  | checkpoint | Location of each batch of concrete marked up on pour plan
checkpoint-status |  |  | checkpoint | Ensure no water is added to the concrete mix (whether pump or truck).
checkpoint-status |  |  | checkpoint | Confirm vibrator use, rubber tipped vibrator used at regular intervals and penetrate vertically approx. 50mm into previous layer.
checkpoint-status |  |  | checkpoint | Confirm levels, as per drawings, confirm correct cover, falls and flatness tolerances achieved.
checkpoint-status |  |  | checkpoint | Confirm jointing as per drawings, do not relocate, eliminate or make other construction joints.
checkpoint-status |  |  | checkpoint | Confirm Finishing - As per drawings, confirm finish requirements achieved (sufficient to receive nominated floor coverings) - Steel trowel finish to carpet & vinyl areas, wood
checkpoint-group |  |  | section | IMMEDIATELY AFTER POUR
checkpoint-no-status |  |  | checkpoint | IMMEDIATELY AFTER POUR
text | 6583e3b6-30a5-5980-978f-e0274394859d |  | textbox | Approved Curing Method (nominate)
checkpoint-status |  |  | checkpoint | Check cured when bleed water stops and able to access slab without marking and also amount used complies
checkpoint-status |  |  | checkpoint | Curing commenced and will continue from completion of finish - Fully enclosed internal surfaces/Early age concrete: 3 days - Other concrete surfaces: 7 days. Prevent rapid drying out at the end of the curing period.
checkpoint-status |  |  | checkpoint | Foreman Sign off to receive inspection results - concrete pour inspections completed by subcontractor. Pass this checkpoint once signed.
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO PROJECT MANAGER TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | F - R - Waterproofing |  |  |  |  | Yes | F - R - Waterproofing | de2f93be-c4ae-4a11-9647-efd88f55543c
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All waterproofing works completed as per the specifications
checklist-flat |  |  | checklist | CST - R - Civil Consent |  |  |  |  | Yes | CST - R - Civil Consent | e8473ff7-a12c-4bdd-94e2-0396e5a84e2e
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Drainage
boolean | e91b748f-6469-576c-a62b-506641d891a0 |  | tickbox | Producer Statement Construction(PS3): sub-soil drains
boolean | 61bdc9a8-a40d-5adf-bbbe-53978c6f74e6 |  | tickbox | Producer Statement Construction(PS3): drainage
boolean | 3c882b8a-d044-59ab-bbde-3329f21f232d |  | tickbox | Drainage as built plan
boolean | 8ef53d08-5c57-5853-a5f6-035df787a62f |  | tickbox | Producer Statement Construction(PS3): Stormwater Management
boolean | 79716dd1-6b4c-5380-971c-2a99dcd90178 |  | tickbox | Producer Statement Review(PS4): Stormwater management approved by council Engineer
boolean | 5481c65a-02ef-5330-9b8e-3eb44bfc3f1b |  | tickbox | Operations and Maintenance manual for stormwater management systems
boolean | 2b1dbc8c-7f1f-5985-8dce-6d28ac9f6d4b |  | tickbox | Backflow test Certificate | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Drainage Pump Systems
boolean | 91ba26f7-a615-5b52-8b89-81e395297edb |  | tickbox | Producer Statement Construction(PS3): installation of drainage pump system
boolean | 93a58f73-28de-5ae6-b271-5bf92f71ff64 |  | tickbox | Manufacturer's warranty for pump system
boolean | ba3f110c-0e87-5e14-8992-42e205219b05 |  | tickbox | Maintenance agreement for pump system
checkpoint-status |  |  | checkpoint | On-Site wastewater Systems
boolean | a842e7b7-0ddc-5709-a74a-6dd34cd07b54 |  | tickbox | Producer Statement Construction(PS3): wastewater treatment and disposal system
boolean | e994a161-31f9-5b39-8de4-34d2455f226e |  | tickbox | Plan showing location of treatment and disposal of systems
boolean | 87c9e481-71b0-5ece-9bd8-3bd9bd15dbf2 |  | tickbox | Producer Statement Review(PS4): System of onsite treatment and disposal of wastewater
boolean | d11fec75-a9d7-5a6c-9d8a-f611e994c136 |  | tickbox | Maintenance agreement for on-site wastewater treatment and disposal system
checkpoint-status |  |  | checkpoint | Development Engineering
boolean | bad51351-41e5-5e8c-badd-18384848dcc3 |  | tickbox | Written approval of works completed within 2m of public waste water drainage
boolean | 568fc932-3c34-5b7d-b5a9-1d183422a499 |  | tickbox | Engineering Approval Completion Certificate for ENG
checkpoint-status |  |  | checkpoint | Watercare Services/Viola Approval
boolean | 29378e81-4f59-569d-8583-7512c3c1540b |  | tickbox | Certificate of connection for both incoming and outgoing water to the public system
boolean | 111a1c55-f8bb-597c-8e64-cadd4db95498 |  | tickbox | Written approval of completed works
checklist-flat |  |  | checklist | ITP - R - Contractor Allocation |  |  |  |  | Yes | ITP - R - Contractor Allocation (Use at stage level for each subcontractor on the stage) | eb2a5a53-97ce-44d9-a186-3858b6516644
checkpoint-status |  |  | checkpoint | Contractor Allocated
text | c6a29304-64c7-5741-815b-6364a93a5413 |  | textbox | Record Subcontractor Company Name
text | ffcd552e-f5b4-561e-bf64-12f89246a7a8 |  | textbox | Record scope of works
checkpoint-status |  |  | checkpoint | Specifications confirmed with subcontractor management
checkpoint-status |  |  | checkpoint | Programme milestones confirmed with subcontractor management
checkpoint-status |  |  | checkpoint | All subcontractor ITPs (inspection test plans) attached and agreed.
checkpoint-status |  |  | checkpoint | Quality expectations and requirements discussed and confirmed as understood.
holdpoint |  |  | signoff | Escalate concerns to QA Advisor
checklist-flat |  |  | checklist | FC - R - Louvres Installation |  |  |  |  | Yes | FC - R - Louvres Installation | eee24c17-b175-4d41-89e1-8345572b66ee
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Balustrades installation completed and acceptable
checklist-sectioned |  |  | checklist | ITP - R - Concrete - Planning and Pour (per area) |  |  |  |  | Yes | ITP - R - Concrete - Planning and Pour (per area) | ef0a3747-990c-4439-88a1-116674cc2dde
checkpoint-group |  |  | section | Pre Pour Planning
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Concrete pour planning completed with subcontractor
text | 04630f2d-f941-579d-a88f-3c40be842119 |  | textbox | Date of pour
text | 49b0b947-bf37-506b-9426-5b4f5a61be7f |  | textbox | Specified concrete strength:
text | 21b8a1df-3283-5fbf-9f64-3ba5c70b3b64 |  | textbox | Concrete strength ordered:
text | e0bd549f-9a94-5cbd-970a-a666837faf2b |  | textbox | Concrete quantity ordered:
text | ba461f26-409f-51f6-a98b-4ca225685424 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | Request to pour received and approved
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
button | 326cdf3d-0dc6-5a4a-8dbf-a04a073e1fef |  | button | Reinforcing meets specification | Yes, Reworked, N/A
button | 45204f1a-08bf-5549-88a9-2a62c80af145 |  | button | Service penetrations present and correct | Yes, Reworked, N/A
button | 7e92140f-c386-5f6e-9b0f-e53457ec0c6b |  | button | Waterproofing elements present and correct | Yes, Reworked, N/A
button | a5e4fa80-7b7e-5fb2-a5e7-db7c66ad5db2 |  | button | Couples present and correct | Yes, Reworked, N/A
button | 457381e1-2368-51ff-9130-207740fb531d |  | button | Control joints/ stop ends installed accurately and correctly braced | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Engineer Inspection conducted and passed
button | 7c1a1695-59ac-5975-834c-de7a6668904d |  | button | Note remedial work needed | None, Minor, Major
text | 5c0b49a6-f22a-5cad-a2a6-787ac9002cc5 |  | textbox | Inspected by and date:
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Documentation
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checklist-flat |  |  | checklist | F - R - Shell Beam Installation |  |  |  |  | Yes | F - R - Shell Beam Installation | f2513cb6-506b-4467-95d7-769f42cc7901
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Shell Beam installation completed as per the specifications
checklist-sectioned |  |  | checklist | Rib & Infill Installation |  |  |  |  | Yes | ST - R - Rib & Infill Installation (old) | f49617f7-11da-4634-8d8b-891ddd04741b
checkpoint-group |  |  | section | Pre-commencement
checkpoint-status |  |  | checkpoint | Rib lifting plan confirmed, correct chains and hooks verified.
checkpoint-status |  |  | checkpoint | Propping layout confirmed as "issued for construction" with contractor and attached.
checkpoint-status |  |  | checkpoint | Floor area cleared for propping to be erected.
checkpoint-status |  |  | checkpoint | Rib grid layout confirmed with contractor and drawing attached.
checkpoint-group |  |  | section | Rib Installation
checkpoint-status |  |  | checkpoint | Rib inspection results received from the contractor
checkpoint-status |  |  | checkpoint | Ribs placed as per layout.
checkpoint-status |  |  | checkpoint | All ribs visually supported as per plan, no visual damage. Ready for infill panels.
checkpoint-group |  |  | section | Infill Panel Installation
checkpoint-status |  |  | checkpoint | Infill panel inspection results received from the contractor
checkpoint-status |  |  | checkpoint | Infill boards constructed as panels, including 'backbone', 6 to 10 boards in length and fitted tightly between the ribs
checkpoint-status |  |  | checkpoint | Infill panel adjacent ends are joined, locked with timber blocks to prevent lateral movement, and secured to wall supports
checkpoint-status |  |  | checkpoint | No obvious visual defects on infill boards, no knots, no cracks or other weakness across 25% of the width.
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | All propping below timber infill complete
checkpoint-status |  |  | checkpoint | Handrails installed on all edges (top of slab)
checkpoint-status |  |  | checkpoint | All penetrations closed or exclusions in place
checkpoint-status |  |  | checkpoint | Pass to indicate agreement to proceed to lay reinforcing.
holdpoint |  |  | signoff | Raise Remedial if failed
checklist-flat |  |  | checklist | ITP - R - B01 Area Inspection signoff |  |  |  |  | Yes | ITP - R - B01 Area Inspection signoff | f686fd24-3091-4a9d-8d08-3c31e82620ff
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Fire Engineer inspection completed and approved
button | f033ec81-0cc1-53fe-b922-646b1f590003 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Electrical Engineer inspection completed and approved
button | 3db90c6f-41a0-5e84-b668-04e09c6ed733 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Mechanical / Hydraulic Engineer inspection completed and approved
button | 0f7f8986-c500-5d3f-984c-3c369cccb9f7 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Specified Systems - Hydrant, Fire Alarms, Sprinklers - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Alarms, Manual/Automatic completed - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Gas Detection - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Nurse Call - As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Access Controlled Doors - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Interfaced Fire/Smoke Doors/Windows/Security - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Hydraulic - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Lifts - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Mechanical, fresh air and duct extract system - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Mechanical, kitchen extract + air conditioning system - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Smoke Curtains - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Essential Power Supply - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Emergency Signage + Exits & Emergency Lighting - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Electrical - PS3 and As Builts supplied
checkpoint-status |  |  | checkpoint | Swimming Pool - Plant completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 4df82751-09c2-5817-930c-67166e821e3d |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checklist-sectioned |  |  | checklist | Site Visit Report: |  |  |  |  | Yes | I - C - Site Visit Report | f7e8120b-0a19-42ed-ae3a-3381ed7a6830
checkpoint-group |  |  | section | Site Visit Details
checkpoint-no-status |  |  | checkpoint | Site Details
text | 947a5245-0dd4-53b8-ac7e-2ab009dacb7b |  | textbox | Area of site visited:
text | 3d158043-d558-5e89-8dbc-5a0e38ece70c |  | textbox | Work element monitored / purpose of visit:
text | 2716d84e-974a-5bd2-84bd-0d6a2ef7f104 |  | textbox | Date of site visit:
text | 7182283d-a290-58ab-af5c-b19ad81fec4c |  | textbox | Time on site (include start and end times):
text | 87183c95-91f7-51a2-81a5-2bf3e68ef2e1 |  | textbox | Weather conditions:
text | 93fd509e-611b-5196-835b-012c3221a77a |  | textbox | Report prepared by:
text | 50ae9c54-0c7f-5484-a395-a3c224492b3f |  | textbox | Additional personnel accompanying:
checkpoint-status |  |  | checkpoint | Consented drawings have been followed
text | c83ecee0-fd12-5fb6-893d-89d9021b20c0 |  | textbox | Building Consent Number:
text | 55575cbe-8d47-54f1-9d44-213bb6c813a0 |  | textbox | Drawing & Revision Number(s):
checkpoint-status |  |  | checkpoint | Health and Safety acceptable
checkpoint-group |  |  | section | Site Report Summary/Closeout
checkpoint-status |  |  | checkpoint | Works accepted and may proceed
label | 8245739f-e02d-57bf-aab6-aaeabe002041 |  | note | Select Pass if works accepted or Fail if reinspection required to defective elements
boolean | f84965f7-db6d-5f2d-9240-a6973104b4ce |  | tickbox | Report attached or remedials summarised below
text | 84f6e550-e121-5c95-933f-e6ddb932f9a5 |  | textbox | Remedial(s)
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | C - R - Asbestos Removal |  |  |  |  | Yes | C - R - Asbestos Removal | f8c28650-ea7d-4251-9ba7-252419146b05
checkpoint-status |  |  | checkpoint | Demolition Survey reviewed and attached
checkpoint-status |  |  | checkpoint | Asbestos Removal Control Plan (ARCP) reviewed and attached
checkpoint-status |  |  | checkpoint | Background Air Monitoring Results (BGAM) reviewed and attached
checkpoint-status |  |  | checkpoint | Clearance Certificates reviewed and attached
checkpoint-status |  |  | checkpoint | All asbestos removed and approval given to progress with work
checklist-flat |  |  | checklist | ST - R - Precast Wall Bracket Installation |  |  |  |  | Yes | ST - R - Precast Wall Bracket Installation | fdfa7c37-33e5-4afa-9876-1d6795518be1
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Wall Bracket Installation completed and acceptable