## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ITP - R - Fitout (per unit) |  |  |  |  | Yes | ITP - R - Fitout (per unit) | 069a21ad-5e18-4fee-98fa-0e7238d0c98c
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | Bathroom completed and signed off.
checkpoint-status |  |  | checkpoint | Open living room area completed and signed off.
checkpoint-status |  |  | checkpoint | Kitchen area completed and signed off.
checkpoint-status |  |  | checkpoint | Toilet completed and signed off.
checkpoint-status |  |  | checkpoint | Bedroom 1 (1st clockwise from front door) completed and signed off.
checkpoint-status |  |  | checkpoint | Bedroom 2 (2nd clockwise from front door) completed and signed off.
checkpoint-status |  |  | checkpoint | Bedroom 3 (3rd clockwise from front door) completed and signed off.
checkpoint-status |  |  | checkpoint | Walk in/through wardrobe area completed and signed off.
checkpoint-status |  |  | checkpoint | Hall (and closets) completed and signed off.
checkpoint-status |  |  | checkpoint | Laundry area completed and signed off.
checkpoint-status |  |  | checkpoint | Garage completed and signed off.
checkpoint-status |  |  | checkpoint | Cleanliness and general items completed and signed off.
checkpoint-status |  |  | checkpoint | External and Hardscape completed and signed off.
checkpoint-status |  |  | checkpoint | Client extras / other unit specific items completed and signed off.
checkpoint-status |  |  | checkpoint | Upload Related Ryman Fitout quality inspection record (QT-012)
checklist-sectioned |  |  | checklist | ITP - R - B01 Fitout/Services (per area/room) |  |  |  |  | Yes | ITP - R - B01 Fitout/Services (per area/room) | 20abce34-94ff-49ae-a27f-6d527e20edf5
checkpoint-group |  |  | section | All areas/rooms
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
button | ae280d08-5e54-54d4-bf4e-4af927bc1ad5 |  | button | Sanitary areas completed and signed off | Yes, Reworked, N/A
button | d98251ab-25dd-5a08-9110-00b23fe2694f |  | button | Service areas completed and signed off. | Yes, Reworked, N/A
button | 4e39953d-9ad5-590c-989f-39f4d8ccd672 |  | button | Public/personal areas completed and signed off. | Yes, Reworked, N/A
button | e436c9cc-267d-5684-ba32-fdb99b3bd42f |  | button | Cleanliness and general items completed and signed off. | Yes, Reworked, N/A
button | 273cbcdf-fea9-5325-a749-9cc8829a230d |  | button | Client extras / other unit specific items completed and signed off. | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Upload Related Ryman Fitout quality inspection record (QT-012)
checkpoint-group |  |  | section | ALS/Care unit services
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Systems completed and acceptable.
checkpoint-status |  |  | checkpoint | Fire - Alarm, Hydrant & Sprinkler completed and acceptable.
checkpoint-status |  |  | checkpoint | Nurse Call, Security, Data and Communications completed and acceptable.
checkpoint-status |  |  | checkpoint | Hydraulic completed and acceptable.
checkpoint-status |  |  | checkpoint | Electrical completed and acceptable.
checkpoint-status |  |  | checkpoint | Mechanical completed and acceptable.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | d9ee62e9-f7e6-5e97-9eaf-7a864d41f155 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Common, Recreational & Service Areas services
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Specified systems completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Hydrant, Fire Alarms, Sprinklers completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Alarms, Manual/Automatic completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Gas Detection completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Nurse Call completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Access Controlled Doors completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Interfaced Fire/Smoke Doors/Windows/Security completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Hydraulic completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Lifts completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Mechanical, fresh air and duct extract system completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Mechanical, kitchen extract + air conditioning system completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Smoke Curtains completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Essential Power Supply completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Emergency Signage + Exits & Emergency Lighting completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Swimming Pool - Plant completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Fire Engineer inspection completed and approved
button | 5d816fe9-9254-5813-961d-4e4743e72b2c |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Electrical Engineer inspection completed and approved
button | 0c88acf7-5c02-52b0-9920-f9e1808208be |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Mechanical / Hydraulic Engineer inspection completed and approved
button | 1c09f110-48ad-50c9-b6ac-36f519397d23 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | b3443fec-1433-5f04-a606-24fdc70c2be7 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checklist-sectioned |  |  | checklist | ITP - R - Apartment Pre & Post Line (per area/grid/Location) |  |  |  |  | Yes | ITP - R - Apartment Pre & Post Line (per area/grid/Location) | 2273868e-59ae-4f24-a4ba-c909d33411a9
checkpoint-group |  |  | section | Pre-Line
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Pre-line completed
checkpoint-status |  |  | checkpoint | Framing system installation completed and acceptable
checkpoint-status |  |  | checkpoint | Nogs Installed and comply
checkpoint-status |  |  | checkpoint | Electrical First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Plumbing First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Insulation installation completed and acceptable
checkpoint-status |  |  | checkpoint | Security, Comms and Data First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | HVAC First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Fire Security First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Underfloor heating First Fix (including screeding and soundproofing of the bathrooms/ wc) completed and acceptable
checkpoint-status |  |  | checkpoint | Kitchen extract First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Passive fire installation completed and acceptable
checkpoint-status |  |  | checkpoint | Suspended ceiling grids installation completed and acceptable
checkpoint-status |  |  | checkpoint | Pre-line plumbing external inspections completed and uploaded. Any remedial work signed off.
button | 855ab6e9-54bb-59f8-8e43-e8791a5dc8c0 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Pre-line building external inspections completed and uploaded. Any remedial work signed off.
button | b63cb695-f002-5f78-b7c3-4c2a80374bff |  | button | Note remedial work needed | None, Minor, Major
text | 46885387-8286-588c-9ee3-423cdae26b70 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Post-Line GIB
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | GIB installation correct, screw types, pattern, etc..
checkpoint-status |  |  | checkpoint | Fire rated GIB installed
checkpoint-status |  |  | checkpoint | All preline services & passive fire (where required) completed, area accessible and substrate acceptable
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Consider bracing, adhesive/sealant & lining layer(s) requirements (including fire stopping between layers)
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Services/penetrations, correctly formed & located (consider cut-out tolerances where applicable)
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Correct fixing pattern/sealant (including fire)/adhesive/layers installed to align with consented design and specifications
checkpoint-status |  |  | checkpoint | All lining(s) completed correctly to specification & level of finish acceptable in respective area(s)
checkpoint-status |  |  | checkpoint | Post Line Council Inspection completed and acceptable. GIB stopping to proceed
button | f412061a-0f38-5b68-b4b3-0311319af26d |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checklist-sectioned |  |  | checklist | T+T Consultant Site Visit Report |  |  |  |  | Yes | I - C - T+T Consultant Site Visit Report | 2d2a3516-e823-4da6-8e88-04f7e3c7848b
checkpoint-group |  |  | section | Site Visit Details
checkpoint-status |  |  | checkpoint | All site visit details have been captured
text | 4f426398-6e05-5335-acd8-0559dfe0d420 |  | textbox | Date
text | b7ad38d7-3932-5cc2-9731-d766dcd3f922 |  | textbox | Time
text | bb785de2-f015-5618-a764-0f223454ac42 |  | textbox | Weather Conditions:
text | 6e879818-c4d2-584c-ba2f-e9feda61ac69 |  | textbox | Site Conditions:
text | 5e3ff8be-d72f-5a3d-a0b8-ba245dd30144 |  | textbox | Sub-contractors:
text | dbf3a3db-ba09-5e89-84ad-d6dc0975e82c |  | textbox | On-site contact with:
text | 562d5fba-b40b-586f-8b34-5adb2457e5dc |  | textbox | Plant/Equipment on site:
text | e37e1062-23d5-5560-a0a1-8c469ed4c8f7 |  | textbox | Materials on site:
checkpoint-status |  |  | checkpoint | General progress recorded
checkpoint-group |  |  | section | Health and Safety
checkpoint-status |  |  | checkpoint | Health and safety - All details inputted and any closeout completed
boolean | b8f868eb-2726-5dbc-bb3c-43655fb00bed |  | tickbox | Contractors induction/Hazard IT sighted
boolean | 91a7a74b-4992-598f-9ebe-e9b17aa933c8 |  | tickbox | T+T's JSA/Hazard ID signed
boolean | fba974f3-cfdc-5ff9-843f-5f7b53810340 |  | tickbox | Double take completed
text | 3f10e384-1db5-5a4d-9f97-b0f067b0cd18 |  | textbox | Comments:
text | bcc13e80-7b54-58fb-afae-c8baef67af38 |  | textbox | Actions:
text | d85ed0ab-07f7-5657-96da-91bb4deddc68 |  | textbox | Follow up:
checkpoint-group |  |  | section | Inspection Details/Closeout
checkpoint-status |  |  | checkpoint | All Inspection Details Inputted Below
text | e286f9b9-9244-5ac8-a18e-a353ea03eb41 |  | textbox | WORK ELEMENT BEING MONITORED:
button | 4a54ef98-157d-5237-baa0-c92fd4b962d7 |  | button | HAS CONTRACTOR PRE-INSPECTION QA CHECK BEEN VIEWED | Yes,No
text | d633003b-ab90-5c99-8d1c-f308a85440e2 |  | textbox | If "Yes" what QC/QA has been viewed
text | 18db7113-cbc8-5f13-bc67-be40e8823a34 |  | textbox | If "No" detail why no QC/QA has been viewed/referenced
checkpoint-status |  |  | checkpoint | DRAWING REFERENCE:
checkpoint-status |  |  | checkpoint | Works may proceed
label | c2edcf6b-0f66-5a10-8342-68f5e292c6e5 |  | note | "FAIL" if reinspection is required to defective elements (If Failed - Works Cannot Proceed without T+T approval)
label | 98e812a4-d2fa-5bb7-a703-f8d08e541194 |  | note | Photographic evidence to close out remedial items is required prior to pouring concrete or completing works. Proceeding without the engineer’s approval is at the Contractor’s risk
text | 2112eb49-01ba-59d0-a8db-c4d39f78aa3a |  | textbox | Reported By:
text | 9edd2320-8aee-5bba-b14e-8913243e94aa |  | textbox | Reviewed By:
holdpoint |  |  | signoff | RAISE REMEDIAL / REQUEST SIGNOFF
checklist-sectioned |  |  | checklist | Concrete Planning and Pour |  |  |  |  | Yes | ITP - R - Concrete - Planning and Pour (per townhouse block) | 2fd582e2-0c3c-46d3-af6a-c547067c4dbc
checkpoint-group |  |  | section | Pre Pour Planning
checkpoint-status |  |  | checkpoint | Concrete pour planning completed with subcontractor
text | a566bafd-d8d5-5924-8c1b-18bebc9f8ca9 |  | textbox | Date of pour
text | 7a6d99a1-3423-5b59-9e58-84dfa3ac1e08 |  | textbox | Specified concrete strength:
text | 3cacc034-5dbf-50e4-af5e-e30943362526 |  | textbox | Concrete strength ordered:
text | efcbbbe0-f4ee-5425-aca3-bec378f10bf0 |  | textbox | Concrete quantity ordered:
text | 6f530bfc-72bd-5efc-9cf0-c10ed7217234 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | Request to pour received and approved
button | e49e18c0-1f0f-5d55-97a7-225987e945f9 |  | button | Reinforcing meets specification | Yes, Reworked, N/A
button | 219c4d9f-601b-5d05-a5dc-6a2bbe9ba902 |  | button | Service penetrations present and correct | Yes, Reworked, N/A
button | 136fe8a8-f346-5359-9200-c15f91cc1972 |  | button | Waterproofing elements present and correct | Yes, Reworked, N/A
button | 6a7010f5-8edd-5aa2-ad8e-fdf2749d52b4 |  | button | Couples present and correct | Yes, Reworked, N/A
button | 5783fa31-8dfe-525b-8996-24ec71381f8a |  | button | Control joints/ stop ends installed accurately and correctly braced | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Engineer Inspection conducted and passed
button | a4c39795-223b-51a0-b54a-ff01fb46dc4e |  | button | Note remedial work needed | None, Minor, Major
text | 3b1508ed-e658-54a6-8413-967f24504f75 |  | textbox | Inspected by and date:
checklist-flat |  |  | checklist | S - R - firewalls (must be completed prior to internal wall commencement) |  |  |  |  | Yes | S - R - firewalls (must be completed prior to internal wall commencement) | 31587136-a313-4d84-ad0f-cdd31725549b
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Pre-line completed
button | bc90ab62-9c45-5e9a-b214-e0370153b21d |  | button | Framing system installation completed and acceptable | Yes, Reworked, N/A
button | f2eebdc9-b09f-5f75-a96d-30ad9c472502 |  | button | Passive fire installation completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 9a7b8216-a687-5eab-a185-9540b6d74963 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | GIB installation correct, screw types, pattern, etc..
checkpoint-status |  |  | checkpoint | Fire rated GIB installed
checkpoint-status |  |  | checkpoint | All preline services & passive fire (where required) completed, area accessible and substrate acceptable
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Consider bracing, adhesive/sealant & lining layer(s) requirements (including fire stopping between layers)
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Services/penetrations, correctly formed & located (consider cut-out tolerances where applicable)
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Correct fixing pattern/sealant (including fire)/adhesive/layers installed to align with consented design and specifications
checkpoint-status |  |  | checkpoint | All lining(s) completed correctly to specification & level of finish acceptable in respective area(s)
checkpoint-status |  |  | checkpoint | Post Line Council Inspection completed and acceptable. GIB stopping to proceed
button | bc71374a-cd60-5555-a6e9-d7c3faa15d0f |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checklist-sectioned |  |  | checklist | Site Visit Report: |  |  |  |  | Yes | I - C - S&H Consultant Site Visit Report | 31d96830-30a4-4e01-a956-7fc9edfc7782
checkpoint-group |  |  | section | Site Visit Details
checkpoint-status |  |  | checkpoint | Site Details
text | b09f2fb2-8972-5cd7-8a42-eaa69a3327f3 |  | textbox | Area of site visited:
text | 96fa103c-67b3-5773-9f19-6cdd1259583c |  | textbox | Work element monitored / purpose of visit:
text | afdf8881-b47c-5a91-8889-8319081b441a |  | textbox | Date of site visit:
text | c2b776ec-8646-543a-bc48-f3d8994ddc76 |  | textbox | Time on site (include start and end times):
text | 8a1d14ac-bfdf-5554-9f2a-6500408ec389 |  | textbox | Weather conditions:
text | 0250dce3-cb61-568a-8dd4-1183d3e1c112 |  | textbox | Report prepared by:
text | 176df8f1-eddf-57c0-8798-f62f95acdb09 |  | textbox | Additional personnel accompanying:
checkpoint-status |  |  | checkpoint | Consented drawings have been followed
text | 6cc6b6a8-4edd-5cdf-afef-0e96f471cfab |  | textbox | Building Consent Number:
text | 9359917c-617c-5852-8b8b-bc80213cbc0c |  | textbox | Drawing & Revision Number(s):
checkpoint-status |  |  | checkpoint | Health and Safety acceptable
checkpoint-group |  |  | section | Site Report Summary/Closeout
checkpoint-status |  |  | checkpoint | Works accepted and may proceed
label | 51b0fe12-a859-5f07-bb3d-a2845d27af56 |  | note | Select Pass if works accepted or Fail if reinspection required to defective elements
boolean | fad115be-aafc-5640-ba17-74e52265c609 |  | tickbox | Report attached or remedials summarised below
text | 9f14e762-f961-5c86-b0ab-8833d320cfda |  | textbox | Remedial(s)
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Handover |  |  |  |  | Yes | H - R - Handover | 37ab1f1e-2110-4651-a1ce-a2247e19ff48
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | Bathroom completed and signed off.
checkpoint-status |  |  | checkpoint | Open living room area completed and signed off.
checkpoint-status |  |  | checkpoint | Kitchen area completed and signed off.
checkpoint-status |  |  | checkpoint | Toilet completed and signed off.
checkpoint-status |  |  | checkpoint | Bedroom 1 (1st clockwise from front door) completed and signed off.
checkpoint-status |  |  | checkpoint | Bedroom 2 (2nd clockwise from front door) completed and signed off.
checkpoint-status |  |  | checkpoint | Bedroom 3 (3rd clockwise from front door) completed and signed off.
checkpoint-status |  |  | checkpoint | Walk in/through wardrobe area completed and signed off.
checkpoint-status |  |  | checkpoint | Hall (and closets) completed and signed off.
checkpoint-status |  |  | checkpoint | Laundry area completed and signed off.
checkpoint-status |  |  | checkpoint | Garage completed and signed off.
checkpoint-status |  |  | checkpoint | Cleanliness and general items completed and signed off.
checkpoint-status |  |  | checkpoint | External and Hardscape completed and signed off.
checkpoint-status |  |  | checkpoint | Client extras / other unit specific items completed and signed off.
checkpoint-status |  |  | checkpoint | Upload Related Ryman Fitout quality inspection record (QT-012)
checklist-flat |  |  | checklist | Woods Consultant Remedial Item Checklist |  |  |  |  | Yes | I - C - Woods Consultant Remedial Item Checklist | 3f3f015c-8b3b-4b75-942f-82edced5c2de
checkpoint-status |  |  | checkpoint | Remedial Status (Woods to "Pass" once satisfied)
text | 7f5e05d2-8527-537a-bd79-e3c8ee3cd47e |  | textbox | Location of Remedial
text | 6fe9dda4-92a9-5e59-9b3f-fb6662f2149f |  | textbox | Remedial Description
text | 58a72199-e107-5218-af69-27383d881ece |  | textbox | Action Required
holdpoint |  |  | signoff | Request Woods Signoff on Remedial
checklist-flat |  |  | checklist | ITP - R - Landscaping (per area/location) |  |  |  |  | Yes | ITP - R - Landscaping (per area/location) | 51ff4087-438c-4c79-870a-7ba14f944d73
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Verify all dimensions, boundaries, and underground services before commencement of work
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Photograph the drawing number and revision of the drawing/s being implemented.
checkpoint-status |  |  | checkpoint | Lawn and garden beds meets landscaping layout plan dimensions
checkpoint-status |  |  | checkpoint | Lawn and planting bed areas meets landscape preparation specification
checkpoint-status |  |  | checkpoint | Plants laid out and planted as per plan
checkpoint-status |  |  | checkpoint | Trees and hedging laid out and planted as per plan
checkpoint-status |  |  | checkpoint | Root guards installed as required.
checklist-sectioned |  |  | checklist | ST - R - Rib & Infill Installation |  |  |  |  | Yes | ST - R - Rib & Infill Installation | 5753f0ca-ed4a-460c-95d8-ff81e9bb7b72
checkpoint-group |  |  | section | Pre-commencement
checkpoint-status |  |  | checkpoint | Rib lifting plan confirmed, correct chains and hooks verified.
checkpoint-status |  |  | checkpoint | Propping layout confirmed as "issued for construction" with contractor and attached.
checkpoint-status |  |  | checkpoint | Floor area cleared for propping to be erected.
checkpoint-status |  |  | checkpoint | Rib grid layout confirmed with contractor and drawing attached.
checkpoint-status |  |  | checkpoint | Ryman Infill Installation SOP obtained and reviewed. Record version number below. Click PASS to confirm
text | fc2d3aae-dda9-5c4a-9e07-bb29f891050d |  | textbox | Version number
checkpoint-status |  |  | checkpoint | Subcontractor SWMS obtained and reviewed against Ryman SOP.
checkpoint-status |  |  | checkpoint | Variations to the SOP are proactively assessed and managed with the subcontractor accordingly. Record personnel involved below. Respond N/A if no variation to Ryman SOP is identified.
text | 67cd97b3-acb1-5291-9729-b36e6cbcc5f3 |  | textbox | Name/s of personnel
checkpoint-status |  |  | checkpoint | Upload a copy of the subcontractor SWMS document. PASS this checkpoint when uploaded.
checkpoint-status |  |  | checkpoint | Approval to proceed given.
checkpoint-group |  |  | section | Rib Installation
checkpoint-status |  |  | checkpoint | Rib inspection results received from the contractor
checkpoint-status |  |  | checkpoint | Ribs placed as per layout.
checkpoint-status |  |  | checkpoint | All ribs visually supported as per plan, no visual damage. Ready for infill panels.
checkpoint-group |  |  | section | Infill Panel Installation
checkpoint-status |  |  | checkpoint | Infill panel inspection results received from the contractor
checkpoint-status |  |  | checkpoint | Infill boards constructed as panels, including 'backbone', 6 to 10 boards in length and fitted tightly between the ribs
checkpoint-status |  |  | checkpoint | Infill panel adjacent ends are joined, locked with timber blocks to prevent lateral movement, and secured to wall supports
checkpoint-status |  |  | checkpoint | No obvious visual defects on infill boards, no knots, no cracks or other weakness across 25% of the width.
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | All propping below timber infill complete
checkpoint-status |  |  | checkpoint | Handrails installed on all edges (top of slab)
checkpoint-status |  |  | checkpoint | All penetrations closed or exclusions in place
checkpoint-status |  |  | checkpoint | Pass to indicate agreement to proceed to lay reinforcing.
checklist-sectioned |  |  | checklist | ITP - R - Detention Tank Installation (Per Tank) |  |  |  |  | Yes | ITP - R - Detention Tank Installation (Per Tank) | 5cb9511b-1a76-4338-a9d4-d48cd3d394ce
checkpoint-group |  |  | section | ITP - R - Detailed Excavation
checkpoint-status |  |  | checkpoint | Grids/profiles/set out completed, clearly marked and accurate
checkpoint-status |  |  | checkpoint | Excavation depths and locations confirmed prior to detailed excavation commencing
checkpoint-status |  |  | checkpoint | Services (overhead / below ground) identified, isolated where required before excavation commences
checkpoint-status |  |  | checkpoint | Approval given to commence detailed excavation
checkpoint-status |  |  | checkpoint | Excavation checked, correct and approved
button | ccdefa56-d077-5260-89cc-977aec3c59f6 |  | button | Location accurate | Yes, Reworked, N/A
button | 3586ef1b-e219-588a-965f-875fedaa72df |  | button | Depth correct (allow for site concrete if required) | Yes, Reworked, N/A
button | ec4bab1b-f1b6-52b5-be89-0ff58fcc6f26 |  | button | Width correct (allow for boxing if required) | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Placement of Geotextile (2 photos required)
checkpoint-status |  |  | checkpoint | Placement of hardfill
checkpoint-status |  |  | checkpoint | Placement of Geogrid (2 photos)
checkpoint-status |  |  | checkpoint | NDM test and report (supporting documents incl. photos)
checkpoint-status |  |  | checkpoint | Completed level of hardfill (completion NDM test with report and supporting documents (incl. photos) and uploaded into QA system)
checkpoint-status |  |  | checkpoint | Any additional layer of hardfill (300mm) requires an NDM test (report and supporting documents (incl. photos) sent uploaded into QA system
holdpoint |  |  | signoff | Sand blinding and check final RL. (completion required to handover to the next stage-townhouses only)
checkpoint-status |  |  | checkpoint | Excavation for services is completed and accurate
checkpoint-status |  |  | checkpoint | Excess material cleaned up and removed as required
checkpoint-status |  |  | checkpoint | Detailed excavation completed, reviewed and approved
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checkpoint-group |  |  | section | Underground Detention Chambers
checkpoint-status |  |  | checkpoint | Geotextile laid as specified
checkpoint-status |  |  | checkpoint | Underdrain laid as per the specifications
checkpoint-status |  |  | checkpoint | Angular stone laid as specified pre-installation of chambers
checkpoint-status |  |  | checkpoint | Chambers installed as per the specifications
checkpoint-status |  |  | checkpoint | DIA riser, ring, cover and concrete collar installed as per the specifications
checkpoint-status |  |  | checkpoint | Connections to manholes completed and approved
checkpoint-status |  |  | checkpoint | Angular stone laid as specified post installation of chambers
checkpoint-status |  |  | checkpoint | Pipe laying completed as per the specifications
checkpoint-status |  |  | checkpoint | Backfill completed & compacted as per the specifications
checkpoint-status |  |  | checkpoint | Scour protection sheet base installed as per the specifications
checkpoint-status |  |  | checkpoint | 3 layers of Duragrid (or other specified product) on top of subgrade as per the specifications
checkpoint-status |  |  | checkpoint | Confirmation of inspection port with Engineer prior to installation
checkpoint-status |  |  | checkpoint | Inspection port installed as per specification and location agreement with Engineer
checkpoint-status |  |  | checkpoint | Coil installation as per specification
checkpoint-status |  |  | checkpoint | Chambers completed, reviewed, and approved
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | T+T Vibration Monitoring Report |  |  |  |  | Yes | I - C - T+T Vibration Monitoring Report | 615b497b-5d33-4b3b-8738-3886a579476a
checkpoint-status |  |  | checkpoint | General comments, photos and observations during inspection & report attached
checklist-sectioned |  |  | checklist | ITP - R - Ancillary Building Build (per ancillary building unit) |  |  |  |  | Yes | ITP - R - Ancillary Building Build (per ancillary building unit) | 69eff62b-bc67-4d28-8dec-6e4852bb9e30
checkpoint-group |  |  | section | Structure/Framing
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Framing system installed, square and plumb
checkpoint-status |  |  | checkpoint | Council pre-clad inspection completed and approved. Note date of inspection in comments
button | d7f6fc26-507e-5b3f-b3d8-d29b477e8b0f |  | button | Note remedial work needed | None, Minor, Major
text | 89350a46-23a0-5257-8752-500272639eab |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Roofing
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Verify materials supplied to site (material and fixings) are as specified or approved samples
checkpoint-status |  |  | checkpoint | Construction complies with specifications
checkpoint-status |  |  | checkpoint | Obtain and upload all performance and authority certificates as required by specification or statutory regulations.
checkpoint-status |  |  | checkpoint | Council Pre-Roof Inspection completed and passed
button | db6b5a6a-9df0-54c9-9b2b-b5a760627c32 |  | button | Note remedial work needed | None, Minor, Major
text | 87f94d2d-a485-5bcc-933a-8d283fdf409b |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Façade
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Envelope/Watertightness Completed (requirements below)
checkpoint-status |  |  | checkpoint | Ecoply Board installed
checkpoint-status |  |  | checkpoint | Lintels installed
checkpoint-status |  |  | checkpoint | Tapes and VaproShield installed.
checkpoint-status |  |  | checkpoint | Windows and Sliders installed
checkpoint-status |  |  | checkpoint | Flashing installed
checkpoint-status |  |  | checkpoint | Envelope Penetrations completed
checkpoint-status |  |  | checkpoint | Council pre-wrap inspection completed and passed
button | 6d7f4332-e6b8-5f9b-986c-ec8697cc166d |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Council brickwork 'half-high' inspection completed and acceptable
button | 52e74ba8-4362-5638-8a7b-7d68247eaed7 |  | button | Note remedial work needed | None, Minor, Major
text | b23d283a-f340-562b-b03b-2ce37bbc4384 |  | textbox | Describe cladding type:
button | 17ae56f4-4b80-5343-989b-77e4fb864d76 |  | button | Brick Works completed | Yes, Reworked, N/A
button | e82bf9c2-0b42-5a4e-8e18-e798bf8925c9 |  | button | STO Poly Plaster completed | Yes, Reworked, N/A
text | 793108c8-73a6-52d9-9cb9-38f5d9ce9e73 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Pre-Line
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Pre-line completed
checkpoint-status |  |  | checkpoint | Framing system installation completed and acceptable
checkpoint-status |  |  | checkpoint | Nogs Installed as below and comply
checkpoint-status |  |  | checkpoint | Electrical First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Plumbing First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Insulation installation completed and acceptable
checkpoint-status |  |  | checkpoint | Security, Comms and Data First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | HVAC First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Fire Security First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Under floor heating First Fix (including screeding and soundproofing of the bathrooms/ wc) completed and acceptable
checkpoint-status |  |  | checkpoint | Kitchen extract First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Passive fire installation completed and acceptable
checkpoint-status |  |  | checkpoint | Suspended ceiling grids installation completed and acceptable
checkpoint-status |  |  | checkpoint | Pre-line plumbing external inspections completed and uploaded. Any remedial work signed off.
button | 8880890c-efe1-5bc0-bc0a-f122e9c014c0 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Pre-line building external inspections completed and uploaded. Any remedial work signed off.
button | 8478e887-0d1b-5833-9a51-5bac0926199a |  | button | Note remedial work needed | None, Minor, Major
text | 0c0b415b-b778-53ab-9c27-2f70793834c2 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Post-Line GIB
checkpoint-status |  |  | checkpoint | GIB installation correct, screw types, pattern, etc..
checkpoint-status |  |  | checkpoint | Fire rated GIB installed to adjoining unit walls & garage, correct thickness.
checkpoint-status |  |  | checkpoint | Post Line Council Inspection completed and acceptable. GIB stopping to proceed
button | ece10140-35a1-579f-a05d-aa1d8fb1f7ee |  | button | Note remedial work needed | None, Minor, Major
checklist-flat |  |  | checklist | ITP - R - On Grade Slab Foundation Construction (per area) |  |  |  |  | Yes | ITP - R - On Grade Slab Foundation Construction (per area) | 73a07f3c-d056-4c56-be74-66bb2d774532
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Survey set out (height, location, setout) - confirmation attached.
checkpoint-status |  |  | checkpoint | Underground services installation completed
checkpoint-status |  |  | checkpoint | Backfilling completed
checkpoint-status |  |  | checkpoint | Waterproofing completed
checkpoint-status |  |  | checkpoint | DPM overlapping/taping with no tears or perforations. Council requirement
checkpoint-status |  |  | checkpoint | Reinforcing completed
checkpoint-status |  |  | checkpoint | Engineer sign off completed and approved for pour
button | 3f5aed11-8262-5156-829d-5bce3f078128 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved for pour
button | 9b9c3485-26c7-5911-ad82-da6aec4347f9 |  | button | Note remedial work needed | None, Minor, Major
text | 3c10f3c6-3aed-505a-83de-a13eb6dcd8be |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checklist-flat |  |  | checklist | ITP - R - Contractor Allocation |  |  |  |  | Yes | ITP - R - Contractor Allocation (Use at stage level for each subcontractor on the stage) | 7ad5c926-bfc9-4782-b9fd-9814ed3bf2a8
checkpoint-status |  |  | checkpoint | Contractor Allocated
text | c6a29304-64c7-5741-815b-6364a93a5413 |  | textbox | Record Subcontractor Company Name
text | ffcd552e-f5b4-561e-bf64-12f89246a7a8 |  | textbox | Record scope of works
checkpoint-status |  |  | checkpoint | Specifications confirmed with subcontractor management
checkpoint-status |  |  | checkpoint | Programme milestones confirmed with subcontractor management
checkpoint-status |  |  | checkpoint | All subcontractor ITPs (inspection test plans) attached and agreed.
checkpoint-status |  |  | checkpoint | Quality expectations and requirements discussed and confirmed as understood.
holdpoint |  |  | signoff | Escalate concerns to QA Advisor
checklist-flat |  |  | checklist | T+T Remedial Item Checklist |  |  |  |  | Yes | I - C - T+T Remedial Item Checklist | 8288ccd3-4f4a-4f5e-8e6e-3f30cf929688
checkpoint-status |  |  | checkpoint | Remedial Status (T+T to "Pass" once satisfied)
text | ab61d8d9-adb4-5449-a7bf-e8a522e407d0 |  | textbox | Location of Remedial
text | 871adada-11a4-58e2-97ee-46af68e47f17 |  | textbox | Remedial Description
text | 110ae150-083f-504a-9dc8-a1e2a809a892 |  | textbox | Action Required
holdpoint |  |  | signoff | Request T+T Signoff on Remedial
checklist-flat |  |  | checklist | ST - R - Monier Tiled Roof Installation |  |  |  |  | Yes | ST - R - Monier Tiled Roof Installation | 8559b731-141d-4fe2-8236-338bd46a2e26
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Monier Installation Guide Confirmed with Contractor
checkpoint-status |  |  | checkpoint | Subcontractor QA completed and passed
checkpoint-status |  |  | checkpoint | Fall Arrest Anchor Point Fixings in place
checkpoint-status |  |  | checkpoint | Producer Statement Construction (PS3) received and attached for installation of roof abseil and/or fall arrest system
checkpoint-status |  |  | checkpoint | Battens - jointing and fixing.
checkpoint-status |  |  | checkpoint | Sarking/Underlay
checkpoint-status |  |  | checkpoint | Tiles Laid and Secured
checkpoint-status |  |  | checkpoint | Hip and Ridge Tile Bedding and Pointing
checkpoint-status |  |  | checkpoint | Gable ends / Barge Boards - Finish
checkpoint-status |  |  | checkpoint | Fire Wall/Internal Separating Walls
checkpoint-status |  |  | checkpoint | Fire Consultant inspection completed and approved
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
text | 630de155-80e3-5b2d-bc63-8055bf6840e1 |  | textbox | Note remedial work needed
holdpoint |  |  | signoff | Raise remedial as required.
checklist-sectioned |  |  | checklist | ITP - R - Concrete - Planning and Pour (per area) |  |  |  |  | Yes | ITP - R - Concrete - Planning and Pour (per area) | 8cd42c09-8da3-4793-bc75-69e8517bba0b
checkpoint-group |  |  | section | Pre Pour Planning
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Concrete pour planning completed with subcontractor
text | 13d43c4a-ecdf-5b36-9074-862bd207357a |  | textbox | Date of pour
text | 313c28ba-0be7-5d44-8949-76e7489842ac |  | textbox | Specified concrete strength:
text | 1283ab0e-12d5-5844-a20c-d1791872a01b |  | textbox | Concrete strength ordered:
text | a0347221-f196-5183-a334-a62ac4bec742 |  | textbox | Concrete quantity ordered:
text | 2a8dadf8-47e9-502e-9382-393ced1385c1 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | Request to pour received and approved
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
button | d6b2d4d0-aa4e-54db-893b-c9c37068ec82 |  | button | Reinforcing meets specification | Yes, Reworked, N/A
button | fe8a66e0-692d-505c-b501-e7883888ce84 |  | button | Service penetrations present and correct | Yes, Reworked, N/A
button | 951902ab-e3bb-5e4f-a9d5-45ce256744ce |  | button | Waterproofing elements present and correct | Yes, Reworked, N/A
button | 1e003843-2f24-5852-8654-d12ff3d612d1 |  | button | Couples present and correct | Yes, Reworked, N/A
button | c2bbb1c0-eaed-5e63-a199-964270f88655 |  | button | Control joints/ stop ends installed accurately and correctly braced | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Engineer Inspection conducted and passed
button | 0f0d28bf-0300-569a-a4c7-8861a9ed7155 |  | button | Note remedial work needed | None, Minor, Major
text | 1a647ad7-fb64-5c18-bc39-ed1a71db1c9e |  | textbox | Inspected by and date:
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Documentation
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checklist-sectioned |  |  | checklist | ITP - R - Townhouse Block Build (per townhouse block) |  |  |  |  | Yes | ITP - R - Townhouse Block Build (per townhouse block) | 915d034c-c3c4-4c98-a82e-c90ecd551fac
checkpoint-group |  |  | section | Structure/Framing
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Framing system installed, square and plumb
checkpoint-status |  |  | checkpoint | Council pre-clad inspection completed and approved. Note date of inspection in comments
button | 7a498ba2-9b10-5265-86e7-007eda886d61 |  | button | Note remedial work needed | None, Minor, Major
text | 11f2f944-8776-5652-a13e-bef3f2c30d62 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Roofing
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Verify materials supplied to site (material and fixings) are as specified or approved samples
checkpoint-status |  |  | checkpoint | Construction complies with specifications
checkpoint-status |  |  | checkpoint | Obtain and upload all performance and authority certificates as required by specification or statutory regulations.
checkpoint-status |  |  | checkpoint | Council Pre-Roof Inspection completed and passed
button | 5c10281a-2f33-5a72-91ec-4cf16e373cfe |  | button | Note remedial work needed | None, Minor, Major
text | 212721fe-a3da-508f-a896-31a95dc93660 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Façade
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Envelope/Watertightness Completed (requirements below)
checkpoint-status |  |  | checkpoint | Ecoply Board installed
checkpoint-status |  |  | checkpoint | Lintels installed
checkpoint-status |  |  | checkpoint | Tapes and VaproShield installed.
checkpoint-status |  |  | checkpoint | Windows and Sliders installed
checkpoint-status |  |  | checkpoint | Flashing installed
checkpoint-status |  |  | checkpoint | Envelope Penetrations completed
checkpoint-status |  |  | checkpoint | Council pre-wrap inspection completed and passed
button | 514dd05b-8685-5b27-99be-47aca0ecea0c |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Council brickwork 'half-high' inspection completed and acceptable
button | 557bb178-b83d-560a-8441-a13c52de5bb1 |  | button | Note remedial work needed | None, Minor, Major
text | 6221bfb4-2177-50e0-bc39-4457778c6e5e |  | textbox | Describe cladding type:
button | 1c758f27-7021-5b87-977b-dda315b67d43 |  | button | Brick Works completed | Yes, Reworked, N/A
button | d6774b44-a5d1-58ee-9161-e0907bdcfaf0 |  | button | STO Poly Plaster completed | Yes, Reworked, N/A
text | 3db974d4-d2c8-5120-9c26-ae4d9a8558ef |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Pre-Line
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Pre-line completed
checkpoint-status |  |  | checkpoint | Framing system installation completed and acceptable
checkpoint-status |  |  | checkpoint | Nogs Installed as below and comply
button | 3ecd629f-3cff-5a5b-a862-5e80c6ce7708 |  | button | Steel Stud frame installation completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Electrical First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Plumbing First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Insulation installation completed and acceptable
checkpoint-status |  |  | checkpoint | Security, Comms and Data First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | HVAC First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Fire Security First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Under floor heating First Fix (including screeding and soundproofing of the bathrooms/ wc) completed and acceptable
checkpoint-status |  |  | checkpoint | Kitchen extract First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Passive fire installation completed and acceptable
checkpoint-status |  |  | checkpoint | Suspended ceiling grids installation completed and acceptable
checkpoint-status |  |  | checkpoint | Pre-line plumbing external inspections completed and uploaded. Any remedial work signed off.
button | d813e039-8f79-53be-97a2-399c1057711f |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Pre-line building external inspections completed and uploaded. Any remedial work signed off.
button | 65746682-7cd8-52d4-aee6-d9a5258e8be5 |  | button | Note remedial work needed | None, Minor, Major
text | f2cc99a5-cd70-51eb-a3a8-a8dda4171e14 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Post-Line GIB
checkpoint-status |  |  | checkpoint | GIB installation correct, screw types, pattern, etc..
checkpoint-status |  |  | checkpoint | Fire rated GIB installed to adjoining unit walls & garage, correct thickness.
checkpoint-status |  |  | checkpoint | Post Line Council Inspection completed and acceptable. GIB stopping to proceed
button | 3ff6994c-3904-59e0-9001-6ab5bba15cc9 |  | button | Note remedial work needed | None, Minor, Major
checklist-sectioned |  |  | checklist | ITP - R - Pipe Laying (Mains Water, Storm and Waste) |  |  |  |  | Yes | ITP - R - Pipe Laying (Mains Water, Storm and Waste) | 91cdf93d-3f3a-40ff-9e53-eb04dba8536a
checkpoint-group |  |  | section | Main Water
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Set-out completed
checkpoint-status |  |  | checkpoint | Excavation
checkpoint-status |  |  | checkpoint | Ground conditions
checkpoint-status |  |  | checkpoint | Bedding
checkpoint-status |  |  | checkpoint | Pipework
checkpoint-status |  |  | checkpoint | Levels and Gradients
checkpoint-status |  |  | checkpoint | Backfill
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 39afa771-3aff-5a09-89c7-98580c92a49b |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 7238ef8c-0838-5c24-a6f9-4472cc97ba2e |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 196cd4a2-c7f3-5472-88d3-420686b4ba58 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Storm Water
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Set-out completed
checkpoint-status |  |  | checkpoint | Excavation
checkpoint-status |  |  | checkpoint | Ground conditions
checkpoint-status |  |  | checkpoint | Bedding
checkpoint-status |  |  | checkpoint | Pipework
checkpoint-status |  |  | checkpoint | Levels and Gradients
checkpoint-status |  |  | checkpoint | Backfill
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 4e4bea62-bd74-57cf-80e1-ad7de3cad2e5 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | c81f12cf-a579-51c6-b2ab-8ff97085c281 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | f507952e-5f03-5017-8826-c69cb9082500 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Waste Water
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Set-out completed
checkpoint-status |  |  | checkpoint | Excavation
checkpoint-status |  |  | checkpoint | Ground conditions
checkpoint-status |  |  | checkpoint | Bedding
checkpoint-status |  |  | checkpoint | Pipework
checkpoint-status |  |  | checkpoint | Levels and Gradients
checkpoint-status |  |  | checkpoint | Backfill
checkpoint-status |  |  | checkpoint | Air/water test completed
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | bd49c02e-99fc-5c59-a72d-d906f469d6ee |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | ca7cb3e4-51e0-5212-9074-8f1e84652e13 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 13134261-c750-52a2-9030-b9d5acdae13b |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-sectioned |  |  | checklist | ITP - R - Apartment Pre Cast, Timber, Insuti , Blockwork Element Installation (per area/level) |  |  |  |  | Yes | ITP - R - Apartment Pre Cast, Timber, Insitu, Blockwork Element Installation (per area/level) | 9dd18c59-13f4-4a06-b44f-3a2793baad73
checkpoint-group |  |  | section | Pre-Cast Elements
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Pre-cast elements inspected upon delivery and accepted for lifting.
checkpoint-status |  |  | checkpoint | Installed vertically / aligment tolerances complies with specification (components below)
checkpoint-status |  |  | checkpoint | Stairs
checkpoint-status |  |  | checkpoint | Spandrels
checkpoint-status |  |  | checkpoint | Pre-cast panels
checkpoint-status |  |  | checkpoint | Columns
checkpoint-status |  |  | checkpoint | Stitch joints
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 3a40dd67-90a2-5517-839b-ac4a75ca58d7 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | bf73d49a-37f5-5f72-937d-3c647ca12c0f |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | aa51a282-90b5-5aa5-aec1-07b17de217e0 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Timber Framing Elements
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Timber Framing installed
button | 4852c1dc-9fef-5af9-8e26-21c69a0e6ad5 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 202e9ddc-b14e-5d9a-8258-fe3af9328820 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | ce86213a-d5c4-5ba9-ba36-086a33b1a096 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 06971275-6386-5475-961d-d9ce94f8806c |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Insuti Pour Elements
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Stitch joints - meets specification
checkpoint-status |  |  | checkpoint | Beams - meets specification
checkpoint-status |  |  | checkpoint | Panels - meets specification
checkpoint-status |  |  | checkpoint | Columns - meets specification
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 8208ff85-0cac-52ff-a381-8aa327576eff |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | c9f88748-5e33-5f42-9872-6fba21b514ad |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 45828b6c-2aea-56e2-bd21-0af89e34a9ee |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Reinforced Blockwork Elements
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Blockwork - meets specification
checkpoint-status |  |  | checkpoint | Reinforcing - meets specification
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 1352c890-15eb-575a-bd41-20a296621262 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 40b39b8f-fbcd-5f46-8317-920b63563bcc |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 37b863c8-3288-5581-9ffb-be8bbf0bf926 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Testing
checkpoint-status |  |  | checkpoint | Chemical anchor testing completed. Upload report
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
text | 9c47c708-82ce-55c2-b888-2685ae084e9f |  | textbox | Record sample size
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Concrete Documentation
checkpoint-status |  |  | checkpoint | Concrete pour planning completed with subcontractor
text | 4a083c16-4523-5ddd-9bee-86006f25e0aa |  | textbox | Date of pour
text | f6c10cf6-d7e6-5143-a8c6-ab517775ccd6 |  | textbox | Specified concrete strength:
text | 983396ee-c6a0-5bd1-a912-aad2a0ce0fc4 |  | textbox | Concrete strength ordered:
text | 19f576d5-89ea-5201-a11b-889bd002c0bf |  | textbox | Concrete quantity ordered:
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checklist-flat |  |  | checklist | PRE - R - PRE-line |  |  |  |  | Yes | PRE - R - PRE-line | 9e67b155-e078-4769-8489-38c70eefbd6b
checkpoint-status |  |  | checkpoint | PRE-line works completed and acceptable. Trades QA received, reviewed, attached and approved for all pre-line trades. Approved to line the area.
checkpoint-status |  |  | checkpoint | Timber frame installation completed and acceptable
checkpoint-status |  |  | checkpoint | Steel Stud frame installation completed and acceptable
checkpoint-status |  |  | checkpoint | Electrical First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Plumbing First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Security, Comms and Data First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | HVAC First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Fire Security First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Underfloor heating First Fix (including screeding and soundproofing of the bathrooms/ wc) completed and acceptable
checkpoint-status |  |  | checkpoint | Kitchen extract First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Insulation installation completed and acceptable
checkpoint-status |  |  | checkpoint | Passive fire installation completed and acceptable
checkpoint-status |  |  | checkpoint | Suspended ceiling grids installation completed and acceptable
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checklist-flat |  |  | checklist | Woods Survey Set-Out Checklist |  |  |  |  | Yes | I - C - Woods Survey Set-Out Checklist | a18595c0-c90c-4073-8ba5-e5e65451f946
checkpoint-status |  |  | checkpoint | All Site Details Inputted Below
text | 2a7dc799-7c91-5f78-97cc-327eafc32966 |  | textbox | Survey works completed by - (enter name)
text | ca984a9f-f4ec-54a5-bb57-6f5d1f7ddc61 |  | textbox | Additional personnel accompanying surveyor
text | 1b8f0eb9-1b6e-55af-b933-60ca3d201099 |  | textbox | Building/Area to Setout
checkpoint-status |  |  | checkpoint | Received CAD drawing of building grids or outline
boolean | 7d4983b5-ea77-56fc-8e82-22cc498b7acd |  | tickbox | Office calculations
boolean | 73fad50f-29ec-575c-ba89-502380b83882 |  | tickbox | Set out platform using offset stake
boolean | 6b88bb0f-9e12-5081-93a8-6233f8bf0dc4 |  | tickbox | Mark level of top of platform
boolean | 593ed0ac-1dd2-5b39-b80d-49c66714b791 |  | tickbox | Provide diagram of set out to contractor
checkpoint-status |  |  | checkpoint | Check level of platform is correct
boolean | 978b01d2-1898-5be6-83dc-4cd32728b4df |  | tickbox | Set out grids on profiles installed by contractor
checkpoint-status |  |  | checkpoint | Setting out certificate or Building Location Certificate before concrete pour
boolean | 2228dae0-fdd1-53be-9a91-66f75607f49a |  | tickbox | Copy of Setting out or Building Location Certificate
boolean | 2168316d-d679-5ae7-8791-42b5f353fdfd |  | tickbox | Upper floor setout (if required)
boolean | 240ff477-1fce-5966-93d0-e365f1ff7a72 |  | tickbox | Receive instruction from Rymans
boolean | 83061db0-570a-53dc-8e90-4de941c3dbc0 |  | tickbox | Set out service locations on upper floors
boolean | cd7179fa-f601-5538-8d48-bec4ad4881bf |  | tickbox | Diagram provided to contractor
checkpoint-status |  |  | checkpoint | Setout / Surveying works completed and report sent to relevant parties
checklist-sectioned |  |  | checklist | ITP - R - Services |  |  |  |  | Yes | ITP - R - Services | a578df0b-2e5e-466c-8db6-e1300a2eb98c
checkpoint-group |  |  | section | Residential Apartment/Townhouse Unit
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Fire - Alarm, Hydrant & Sprinkler completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Nurse Call, Security, Data and Communications completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Hydraulic completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Electrical completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Mechanical completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 56e1b5e6-6036-5b78-a527-181a8520ebf9 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Common, Recreational & Service Areas
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Specified Systems - Hydrant, Fire Alarms, Sprinklers completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Alarms, Manual/Automatic completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Gas Detection completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Nurse Call completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Access Controlled Doors completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Interfaced Fire/Smoke Doors/Windows/Security completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Hydraulic completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Lifts completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Mechanical, fresh air and duct extract system completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Mechanical, kitchen extract + air conditioning system completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Smoke Curtains completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Essential Power Supply completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Emergency Signage + Exits & Emergency Lighting completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Swimming Pool - Plant completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Fire Engineer inspection completed and approved
button | d9e6975b-a286-5ba1-b248-b48cb23daa7e |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Electrical Engineer inspection completed and approved
button | dec2c850-1321-546c-9b61-c19ef4d9728b |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Mechanical / Hydraulic Engineer inspection completed and approved
button | 24716e16-a440-57a5-8171-803289c11416 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | e8d53e07-ebb6-5ae3-8700-c67dd3223910 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checklist-flat |  |  | checklist | POST - R - Grab Rail Load Testing (per stage) |  |  |  |  | Yes | POST - R - Grab Rail Load Testing (per stage) | a60e3d1f-8548-4bc4-b07a-38fea343d06c
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Load testing to NZS 4121:2001 completed and passed. Test results received and confirmed.
text | df8e0893-a09e-595e-b364-fa0503888ebc |  | textbox | Record quantity tested
text | 4fa99306-9d9c-5831-90a7-ce8eb9cce022 |  | textbox | Record sample size (%)
text | da6a685b-75a6-56b2-ada0-53ac7f54d648 |  | textbox | Record Apartment No's tested
text | 15135b72-9f4e-5cb7-9101-277578c35236 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checklist-flat |  |  | checklist | Punch Windows Frames (unglazed) |  |  |  |  | Yes | FC - R - Punch Windows Frames (unglazed) | a982193a-38dd-4fa6-ad7a-d89612bf58dd
checkpoint-no-status |  |  | checkpoint | Window # / Elevation / Level
text | 12f06f9d-851f-586f-b79f-934e897cacb0 |  | textbox | Window # / Elevation / Level
checkpoint-status |  |  | checkpoint | Installation (By others) completed as per detail Y/N
checkpoint-status |  |  | checkpoint | Check the joinery is free from damage
checkpoint-status |  |  | checkpoint | All glazing beads attached to Frame PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Check Frame number PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Inspection of Backing rubber - no damage and continuous around perimeter
checkpoint-status |  |  | checkpoint | Glazing Blocks inserted correctly PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Correct Glass units installed (Glass sticker) PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Glazing Beads fitted correctly PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Correct Wedge Rubber installed and rubbered off as per WGANZ guidelines
checkpoint-status |  |  | checkpoint | Glass Stickers removed
checkpoint-status |  |  | checkpoint | Trade Clean
checkpoint-status |  |  | checkpoint | Final Inspection PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Glazing complete for handover to Ryman Healthcare
holdpoint |  |  | signoff | Raise Remedial
checklist-flat |  |  | checklist | ST - R - Double T Installation |  |  |  |  | Yes | ST - R - Double T Installation | b7d480d2-3a29-437c-90c3-3fdfc3921223
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | Inspected on arrival & damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Shoreload completed
checkpoint-status |  |  | checkpoint | Double T install complete and acceptable (checked location and level)
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 60546f6c-4cfe-5f2c-811c-8de408253aa2 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-sectioned |  |  | checklist | ITP - R - Apartment Pre Cast Floor Structure and Concrete Pour (per level/area) |  |  |  |  | Yes | ITP - R - Apartment Pre Cast Floor Structure and Concrete Pour (per level/area) | c541be33-5366-44af-854d-f76a6a7acb74
checkpoint-group |  |  | section | Pre Commencement
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
button | 80790564-6a7e-5b2f-80cb-987bd964a6d7 |  | button | Confirm construction method | Double T's, Rib & Infill, Post Tensioned, Other
text | 131a7a15-eaab-56ac-9f75-8bc678e87f2b |  | textbox | Other details:
button | bab3e96a-5484-53c6-8c42-a1f48fb8be13 |  | button | Propping layout confirmed as "issued for construction" | Yes, N/A
checkpoint-status |  |  | checkpoint | Propping/Falseworks Confirmed and Accepted. Evidence required.
button | 08bba02f-6748-5d04-81f3-16f10d1b359d |  | button | Floor area cleared for propping to be erected | Yes, N/A
checkpoint-status |  |  | checkpoint | Hogging of panels within design tolerances. Installed in accordance with suppliers recommendations.
checkpoint-status |  |  | checkpoint | Adequate identification, cast date and verification of inspection marked on precast element.
checkpoint-group |  |  | section | Pre Cast Element Installation
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Hogging of panels within design tolerances. Installed in accordance with suppliers recommendations.
checkpoint-status |  |  | checkpoint | Adequate identification, cast date and verification of inspection marked on precast element.
checkpoint-status |  |  | checkpoint | Pre-cast elements inspected upon delivery and accepted for lifting.
checkpoint-status |  |  | checkpoint | Floor structure elements landed as per layout
checkpoint-status |  |  | checkpoint | If Rib and Infill, Ryman SOP followed where applicable. (Reference the document name / version)
checkpoint-status |  |  | checkpoint | Reinforcing laid as per specification
checkpoint-status |  |  | checkpoint | Service penetrations present as per specification
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved for pour
button | d4b9f19e-73c6-5146-8561-7315feaf59c7 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 6adfcd41-2262-5506-b5df-fe2de28a1d13 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Post Tensioned Floor Construction
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Stressing access correct
checkpoint-status |  |  | checkpoint | Tensioning strands quantity, length, and size correct.
checkpoint-status |  |  | checkpoint | Tendons quantity, size, and spacing correct
checkpoint-status |  |  | checkpoint | Tendon profiles (highs and lows and edges) correct
checkpoint-status |  |  | checkpoint | Antiburst are located at the correct position on the tendon
checkpoint-status |  |  | checkpoint | Grout Tubes height above concrete surface, quantity, and location correct
checkpoint-status |  |  | checkpoint | Pans and pan trimmers, anchorages, antiburst
checkpoint-status |  |  | checkpoint | Reinforcing laid as per specification
checkpoint-status |  |  | checkpoint | Service penetrations present as per specification
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved for pour
button | a206c6d6-2029-59b3-8c44-a92f1caaf489 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 0cbd16cb-1930-59c6-96a3-f282aa3fa69c |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Pre Pour Planning
checkpoint-status |  |  | checkpoint | Concrete pour planning completed with subcontractor
text | 212b9ed4-5520-5aa8-8eb5-f12a7e7f909e |  | textbox | Date of pour
text | f6e603fa-b318-5e19-9853-c21e5f016ff2 |  | textbox | Specified concrete strength:
text | 0b1fcce8-24e3-51c3-b039-5167676628e4 |  | textbox | Concrete strength ordered:
text | 4603a51e-16ef-552a-9056-ca94d23b2915 |  | textbox | Concrete quantity ordered:
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | a36c43a8-bd24-5c00-a8a5-694d8f7b08e9 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Request to pour received and approved
checkpoint-status |  |  | checkpoint | Reinforcing meets specification
checkpoint-status |  |  | checkpoint | Service penetrations present and correct
checkpoint-status |  |  | checkpoint | Waterproofing elements present and correct
checkpoint-status |  |  | checkpoint | Couplers present and correct
checkpoint-status |  |  | checkpoint | Control joints/ stop ends installed accurately and correctly braced
checkpoint-status |  |  | checkpoint | Engineer Inspection conducted and passed
button | 36c2831e-2215-5a5c-b06a-2591e4357ea1 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 2a34daaf-92e4-5a98-8423-c0b00ce505ba |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Post Pour (Post Tensioned Floor Only)
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Initial Tension applied [when concrete strength 9MPa (min) initial stress- 21% of UTS]
checkpoint-status |  |  | checkpoint | Final Tension applied [when concrete strength 22MPa (min) final stress- 80% of UTS]
checkpoint-status |  |  | checkpoint | Cutting of strands and sealing of pockets completed
checkpoint-status |  |  | checkpoint | Grouting completed as per specification and tubes clear
checkpoint-status |  |  | checkpoint | Engineer Inspection conducted and passed
button | 95a3b152-3317-56c7-85b1-ab8f19b9429e |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 740a26a4-a100-5d2a-a61f-8cb1514ea6fd |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-sectioned |  |  | checklist | Woods Consultant Site Visit Report |  |  |  |  | Yes | I - C - Woods Consultant Site Visit Report | c999a420-682d-48c7-8026-6f7c87d38e88
checkpoint-group |  |  | section | Site Details & Inspection Specifics
checkpoint-status |  |  | checkpoint | All Site Details Inputted Below
text | d9885644-11ad-5600-9c72-692ff238b160 |  | textbox | SVR#
text | 155066c2-e395-5735-86dd-af91b26e3e2f |  | textbox | Area of site visited
text | fc9a85a8-d30a-5492-83b5-fef2b4cf1ca6 |  | textbox | Purpose of visit
text | 5a8e908b-a6cf-5a67-bbc5-7870c9a43883 |  | textbox | Date site visit occurred
text | 485c34d9-ccab-53b0-82ba-8cacd8a53ed3 |  | textbox | Time on site (Include start & end time)
text | 5842bc30-fe54-5a6d-8488-291aa695db33 |  | textbox | Weather
text | 158f91af-950a-54d3-8aee-d4a22501a518 |  | textbox | Report prepared by - Engineer's name
text | 372d9276-3631-54e4-83e2-1270a1e1fa46 |  | textbox | Additional personnel accompanying engineer
checkpoint-status |  |  | checkpoint | Health and Safety Observations recorded/photos attached
checkpoint-status |  |  | checkpoint | Dust / Erosion and Sediment Control Observations recorded / photos attached
checkpoint-status |  |  | checkpoint | Consented drawings have been followed
text | d1ffa4b1-b5e4-5b53-a677-6a4c1a5ce98c |  | textbox | Drawing & Revision Number(s)
checkpoint-status |  |  | checkpoint | General comments, photos and observations during inspection
label | 1ef147bb-75bb-5b0f-af12-a839676d624e |  | note | Capture relevant photos specific to this site visit report
button | fd364f62-116f-566b-b72a-5b9dfc909f64 |  | button | Has contractors pre-inspection QA been reviewed? | Yes, No
label | 195cf81d-f8f4-50b0-96b1-711af26773b6 |  | note | Select "Yes" if pre-inspection QC/QA has been viewed & detail below / attach examples
label | bd078291-6596-57f7-9156-3f684fc8c503 |  | note | Select "No" detail why no QC/QA has been viewed/referenced below
checkpoint-status |  |  | checkpoint | Works accepted and may proceed (select Pass) or re inspection required to defective elements (select Fail - Works Cannot Proceed)
select | ea506436-65c7-5625-98fd-f93f862c014d |  | dropdown | Select appropriate outcome | PASS - no remedial work, PASS - Remedial action needed to proceed, FAIL - Stop works (fail checkpoint).
label | 1634ec0c-7988-576f-a4fb-ec316edca116 |  | note | Photographic evidence to close out remedial items is required prior to pouring concrete or completing works. Proceeding without the engineer’s approval is at the Contractor’s risk
checkpoint-status |  |  | checkpoint | Remedials raised against Main Contractor
holdpoint |  |  | signoff | Raise Remedial Request
checklist-sectioned |  |  | checklist | POST - R - Stair Well Guard and Hand Rail Testing (per stage) |  |  |  |  | Yes | POST - R - Stair Well Guard and Hand Rail Testing (per stage) | d15f947d-8ecb-4dd7-876d-65c7855b4b77
checkpoint-group |  |  | section | Guard Rail Pull and Load Testing
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Bolt pull testing completed and passed. Test results received and confirmed.
text | a9c32f84-9c7d-58fa-bf98-f00809305437 |  | textbox | Record quantity tested
text | ecffe705-a20e-5d14-a610-c667a52f9586 |  | textbox | Record sample size (%)
checkpoint-status |  |  | checkpoint | Lateral load pull testing completed and passed. Test results received and confirmed.
text | bf5af4b6-5363-56e6-bb96-6bdb2c0219a9 |  | textbox | Record quantity tested
text | b2e46a61-8dd2-557d-a372-6cff9ce18f0b |  | textbox | Record sample size (%)
text | a35e5c12-3ab6-557e-b0be-e25ed145389e |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Handrail Load Testing
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Load testing to NZS 4121:2001 completed and passed. Test results received and confirmed.
text | 070cc95a-3b40-57eb-973f-832ec068db1c |  | textbox | Record quantity tested
text | cdacd5c6-d579-563d-8c04-b2575233242c |  | textbox | Record sample size (%)
text | c7d10804-50c8-5931-879d-3c3cca6e6228 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checklist-flat |  |  | checklist | ITP - R - B01 Area Inspection signoff |  |  |  |  | Yes | ITP - R - B01 Area Inspection signoff | d61681a2-3121-4c59-bb7a-d28f9c4638b8
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Fire Engineer inspection completed and approved
button | 4c673bac-b017-5c9b-a75f-eac0c7ea60c0 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Electrical Engineer inspection completed and approved
button | 5c2ffe1c-4b14-5d6e-b20d-63dbc94866dd |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Mechanical / Hydraulic Engineer inspection completed and approved
button | e074c372-2608-535c-bbd0-ee886eded5a7 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Specified Systems - Hydrant, Fire Alarms, Sprinklers - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Alarms, Manual/Automatic completed - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Gas Detection - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Nurse Call - As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Access Controlled Doors - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Interfaced Fire/Smoke Doors/Windows/Security - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Hydraulic - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Lifts - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Mechanical, fresh air and duct extract system - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Mechanical, kitchen extract + air conditioning system - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Smoke Curtains - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Essential Power Supply - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Emergency Signage + Exits & Emergency Lighting - PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Electrical - PS3 and As Builts supplied
checkpoint-status |  |  | checkpoint | Swimming Pool - Plant completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | f520cbec-c0a4-5679-a221-ca4d8b31bcf6 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checklist-flat |  |  | checklist | ITP - R - Hardscaping (per area/location) |  |  |  |  | Yes | ITP - R - Hardscaping (per area/location) | dc120ec3-5113-4aa3-a14e-af1f16352e1b
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Photograph the drawing number and revision of the drawing being implemented.
checkpoint-status |  |  | checkpoint | Street Lighting - locations.
checkpoint-status |  |  | checkpoint | Bollard Lighting - locations.
checkpoint-status |  |  | checkpoint | Letterbox - locations.
checkpoint-status |  |  | checkpoint | Letterbox - materials and colour.
checkpoint-status |  |  | checkpoint | EV charger - location/s.
checkpoint-status |  |  | checkpoint | Main footpath/s - material and finish.
checkpoint-status |  |  | checkpoint | Main footpath/s - Pipework ducting installed prior to pour
checkpoint-status |  |  | checkpoint | Townhouse footpath/s - material and finish.
checkpoint-status |  |  | checkpoint | Main footpath/s - layouts and gradients.
checkpoint-status |  |  | checkpoint | Townhouse footpath/s - layouts and gradients.
checkpoint-status |  |  | checkpoint | Townhouse footpath/s - Pipework ducting installed prior to pour
checkpoint-status |  |  | checkpoint | All pathways - edging.
checkpoint-status |  |  | checkpoint | Raised pedestrian crossing/s - material and finish.
checkpoint-status |  |  | checkpoint | Flush pedestrian crossing/s - material and finish.
checkpoint-status |  |  | checkpoint | Paved area/s - materials, pattern, and edging.
checkpoint-status |  |  | checkpoint | Driveways - materials and finish.
checkpoint-status |  |  | checkpoint | Driveways - Pipework ducting installed prior to pour
checkpoint-status |  |  | checkpoint | Brick wall - materials and finish.
checkpoint-status |  |  | checkpoint | Brick wall - pipework ducting installed
checkpoint-status |  |  | checkpoint | Aluminium fencing/rails/hand rails installed - materials and finish.
button | ab62b7cd-337a-5d69-8ab3-f50bbf85df9e |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checklist-sectioned |  |  | checklist | MV Consultant Site Visit Report |  |  |  |  | Yes | I - C - MV Consultant Site Visit Report | e1f8f4f1-0cd9-4991-8878-055de13e1fa1
checkpoint-group |  |  | section | Site Inspection Details
checkpoint-status |  |  | checkpoint | All Site Details Inputted Below
text | f796cdf6-1cc3-5115-ba07-0ff76c522012 |  | textbox | Building Consent No.
text | b1f81a58-c4c1-508f-ab59-dd5f5ed361db |  | textbox | Date site visit occurred
text | 994ac6a0-7d23-574f-a4d4-e47bdca59313 |  | textbox | Time on site (include start and end times)
text | 83b47e99-3880-5633-9ae4-f04bbdbc9c37 |  | textbox | Report prepared by - Engineer's name
text | c4ea4f5a-79ee-5484-8b83-c0646a5c3768 |  | textbox | Additional personnel accompanying engineer
button | 4b04de9f-01a0-5e66-9c4b-f5793be2d3cc |  | button | Has contractors pre-inspection QA been reviewed? | Yes, No
label | 7d400e33-ea35-515e-8c54-69a5c61b7ef6 |  | note | Select "Yes" if pre-inspection QC/QA has been viewed & detail below / attach examples
label | 6085d91a-80c4-5cec-942e-7d4773633e9f |  | note | Select "No" detail why no QC/QA has been viewed/referenced below
checkpoint-group |  |  | section | Inspection Specifics
checkpoint-status |  |  | checkpoint | Consented drawings have been followed
checkpoint-status |  |  | checkpoint | General comments, photos and observations during inspection
checkpoint-group |  |  | section | Site Report Summary/Closeout
checkpoint-status |  |  | checkpoint | Works accepted and may proceed (select Pass) or reinspection required to defective elements (select Fail - Works Cannot Proceed)
text | 7db14ead-a8b3-5898-b7a0-2c5bb5d83e29 |  | textbox | Remedial(s) - Recorded and Closed Out
holdpoint |  |  | signoff | RAISE REMEDIAL / REQUEST SIGNOFF
checklist-flat |  |  | checklist | MV Compliance Documents |  |  |  |  | Yes | I - C - MV Compliance Documents | e3f813ab-5f92-4f5a-9651-5e3962463348
checkpoint-status |  |  | checkpoint | Compliance Documents
boolean | 60dac8a3-1b67-5ba5-b9ad-257afa937dc7 |  | tickbox | LBP Memorandum
boolean | d2841a9d-e45b-5290-a4a7-5e3023301ca0 |  | tickbox | Mill Certificates
boolean | 238e917e-0f97-5308-912c-81de20c3461f |  | tickbox | Concrete Dockets
boolean | 8abcf8b5-a6ad-53de-8b31-f80a00e8cf3c |  | tickbox | Concrete Strength Test Results
checkpoint-status |  |  | checkpoint | Mitchell Vranjes PS4 Attached
checklist-flat |  |  | checklist | MV Remedial Item Checklist |  |  |  |  | Yes | I - C - MV Remedial Item Checklist | ea801be6-4450-4b35-a9d9-1ba7a14ac0e8
checkpoint-status |  |  | checkpoint | Remedial Status (MV to "Pass" once satisfied)
text | 104edfc1-4fc5-5fc9-99a4-4baf090eddac |  | textbox | Location of Remedial
text | cca059f4-64ec-598f-a24b-f0e12f3e03c7 |  | textbox | Remedial Description
text | f44ee69a-58ec-5993-a234-1057564fd340 |  | textbox | Action Required
holdpoint |  |  | signoff | Request MV Signoff on Remedial
checklist-sectioned |  |  | checklist | ITP - R - Apartment Facade (per elevation/grid) |  |  |  |  | Yes | ITP - R - Apartment Facade (per elevation/grid) | f0aefd9c-285a-4f00-939a-29d023285e5c
checkpoint-group |  |  | section | Façade
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | All Envelope/Watertightness Completed (requirements below)
checkpoint-status |  |  | checkpoint | Ecoply Board installed
checkpoint-status |  |  | checkpoint | Lintels installed
checkpoint-status |  |  | checkpoint | Tapes and VaproShield installed.
checkpoint-status |  |  | checkpoint | Windows and Sliders installed
checkpoint-status |  |  | checkpoint | Flashing installed
checkpoint-status |  |  | checkpoint | Envelope Penetrations completed
checkpoint-status |  |  | checkpoint | Balcony waterproofing completed
checkpoint-status |  |  | checkpoint | Council pre-wrap inspection completed and passed
checkpoint-status |  |  | checkpoint | Water tightness test performed. No leaks. Witnessed by Ryman. Record name of contractor who conducted the test in the comments section.
button | cd84d4fa-e963-5758-9e19-5b68c8b3582e |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council brickwork 'half-high' inspection completed and acceptable
button | f2bdb921-0c4a-588b-bbc8-f7e6b3315dd5 |  | button | Note remedial work needed | None, Minor, Major
text | b0f2acaf-2c2e-5506-8075-4bd39c33ceea |  | textbox | Describe cladding type:
button | 7aad5ee9-bd20-5db3-b885-10e0ae1527da |  | button | Brick Works completed | Yes, Reworked, N/A
button | c9918813-5762-546f-b84a-aeb4c71c24eb |  | button | STO Poly Plaster completed | Yes, Reworked, N/A
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Installed horizontal fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed vertical fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Eyebrow and soffit fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Boss Bulkhead Batt fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Gutter fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Concrete Panels (under roof) fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Hatches fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Consultant Inspections Completed and Passed
button | af686545-3a19-5f40-ba35-501be6bbe82c |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 1134170a-dea4-558c-9a67-32561870084b |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Balustrade Testing
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Balustrade Anchor Bolt Pull Testing
label | c1b9c7e4-3b75-5af3-9b3f-aa4ec3795eab |  | note | Test results to be uploaded
checkpoint-status |  |  | checkpoint | Balustrade Lateral Load Testing
label | 0f10de72-87d0-58c3-a90d-7bb598f82b88 |  | note | Test results to be uploaded
checkpoint-status |  |  | checkpoint | Consultant Inspections Completed and Passed
button | c1d6b214-7e3f-589a-94f4-73c13a2c5613 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 06a7f5dd-3b83-57dc-a079-ff1eafdfb1e1 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-flat |  |  | checklist | ITP - R - Foundation Piling |  |  |  |  | Yes | ITP - R - Foundation Piling | fd8bfa98-03b4-4fb1-b9a7-9749abd74278
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Subcontractor piling card reviewed and meets requirements
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Piles set out, surveyed, and marked.
checkpoint-status |  |  | checkpoint | Site condition acceptable for piling rig
checkpoint-status |  |  | checkpoint | Piles meet set out, heights, and correct within tolerances.
checkpoint-status |  |  | checkpoint | All piling cards received, filed, and meet requirements.
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 90e992bd-9811-5319-a099-827576b386dc |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 3350005c-b524-5dd9-a3cb-d169926e0be5 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 90f3059a-da4c-5ca5-9611-094b834e5123 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)