## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP - R - Detention Tank Installation (Per Tank) |  |  |  |  | Yes | ITP - R - Detention Tank Installation (Per Tank) | 01b5fbca-9190-48e0-b785-ab286bcbb0a5
checkpoint-group |  |  | section | ITP - R - Detailed Excavation
checkpoint-status |  |  | checkpoint | Grids/profiles/set out completed, clearly marked and accurate
checkpoint-status |  |  | checkpoint | Excavation depths and locations confirmed prior to detailed excavation commencing
checkpoint-status |  |  | checkpoint | Services (overhead / below ground) identified, isolated where required before excavation commences
checkpoint-status |  |  | checkpoint | Approval given to commence detailed excavation
checkpoint-status |  |  | checkpoint | Excavation checked, correct and approved
button | ccdefa56-d077-5260-89cc-977aec3c59f6 |  | button | Location accurate | Yes, Reworked, N/A
button | 3586ef1b-e219-588a-965f-875fedaa72df |  | button | Depth correct (allow for site concrete if required) | Yes, Reworked, N/A
button | ec4bab1b-f1b6-52b5-be89-0ff58fcc6f26 |  | button | Width correct (allow for boxing if required) | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Placement of Geotextile (2 photos required)
checkpoint-status |  |  | checkpoint | Placement of hardfill
checkpoint-status |  |  | checkpoint | Placement of Geogrid (2 photos)
checkpoint-status |  |  | checkpoint | NDM test and report (supporting documents incl. photos)
checkpoint-status |  |  | checkpoint | Completed level of hardfill (completion NDM test with report and supporting documents (incl. photos) and uploaded into QA system)
checkpoint-status |  |  | checkpoint | Any additional layer of hardfill (300mm) requires an NDM test (report and supporting documents (incl. photos) sent uploaded into QA system
holdpoint |  |  | signoff | Sand blinding and check final RL. (completion required to handover to the next stage-townhouses only)
checkpoint-status |  |  | checkpoint | Excavation for services is completed and accurate
checkpoint-status |  |  | checkpoint | Excess material cleaned up and removed as required
checkpoint-status |  |  | checkpoint | Detailed excavation completed, reviewed and approved
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checkpoint-group |  |  | section | Underground Detention Chambers
checkpoint-status |  |  | checkpoint | Geotextile laid as specified
checkpoint-status |  |  | checkpoint | Underdrain laid as per the specifications
checkpoint-status |  |  | checkpoint | Angular stone laid as specified pre-installation of chambers
checkpoint-status |  |  | checkpoint | Chambers installed as per the specifications
checkpoint-status |  |  | checkpoint | DIA riser, ring, cover and concrete collar installed as per the specifications
checkpoint-status |  |  | checkpoint | Connections to manholes completed and approved
checkpoint-status |  |  | checkpoint | Angular stone laid as specified post installation of chambers
checkpoint-status |  |  | checkpoint | Pipe laying completed as per the specifications
checkpoint-status |  |  | checkpoint | Backfill completed & compacted as per the specifications
checkpoint-status |  |  | checkpoint | Scour protection sheet base installed as per the specifications
checkpoint-status |  |  | checkpoint | 3 layers of Duragrid (or other specified product) on top of subgrade as per the specifications
checkpoint-status |  |  | checkpoint | Confirmation of inspection port with Engineer prior to installation
checkpoint-status |  |  | checkpoint | Inspection port installed as per specification and location agreement with Engineer
checkpoint-status |  |  | checkpoint | Coil installation as per specification
checkpoint-status |  |  | checkpoint | Chambers completed, reviewed, and approved
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Mandatory photos/files example |  |  |  |  | Yes | Mandatory photos/files example | 126daddd-0ca0-4e03-a7db-235e2086c8d7
checkpoint-status |  |  | checkpoint | Checkpoint with mandatory photo/file upload requirement
checkpoint-status |  |  | checkpoint | Works completed
checklist-sectioned |  |  | checklist | ITP - R - Pipe Laying (Mains Water, Storm and Waste) |  |  |  |  | Yes | ITP - R - Pipe Laying (Mains Water, Storm and Waste) | 298841dc-9d31-44ba-8b63-ae48697d51fa
checkpoint-group |  |  | section | Main Water
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Set-out completed
checkpoint-status |  |  | checkpoint | Excavation
checkpoint-status |  |  | checkpoint | Ground conditions
checkpoint-status |  |  | checkpoint | Bedding
checkpoint-status |  |  | checkpoint | Pipework
checkpoint-status |  |  | checkpoint | Levels and Gradients
checkpoint-status |  |  | checkpoint | Backfill
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | fbe335a4-528e-5f8a-b902-69ba2d927266 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | fce92ce7-7e6a-5c0d-930e-bdde8e301572 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | fe391469-7926-5f38-85c9-2c03f3433b0d |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Storm Water
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Set-out completed
checkpoint-status |  |  | checkpoint | Excavation
checkpoint-status |  |  | checkpoint | Ground conditions
checkpoint-status |  |  | checkpoint | Bedding
checkpoint-status |  |  | checkpoint | Pipework
checkpoint-status |  |  | checkpoint | Levels and Gradients
checkpoint-status |  |  | checkpoint | Backfill
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 75b069aa-58d5-5d91-86b7-4bb994120e47 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | e5794366-770a-5b75-ad1d-c64d1354ee7a |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 7f2873bd-facc-5651-9f39-a1878c790a92 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Waste Water
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Set-out completed
checkpoint-status |  |  | checkpoint | Excavation
checkpoint-status |  |  | checkpoint | Ground conditions
checkpoint-status |  |  | checkpoint | Bedding
checkpoint-status |  |  | checkpoint | Pipework
checkpoint-status |  |  | checkpoint | Levels and Gradients
checkpoint-status |  |  | checkpoint | Backfill
checkpoint-status |  |  | checkpoint | Air/water test completed
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | bea100d0-72c4-5253-b19d-e37f180ad02b |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 41e6a3fa-fc18-5d37-8a50-df482c5ef52e |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | d97addfc-0cb0-5905-b6f4-c151f62df231 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-sectioned |  |  | checklist | ITP - R - Fitout/Services (per area/room) |  |  |  |  | Yes | ITP - R - Fitout/Services (per area/room) | 2c579054-0e58-446e-9713-97f84acb43b5
checkpoint-group |  |  | section | Fitout/Services Checks
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | Sanitary areas completed and signed off
checkpoint-status |  |  | checkpoint | Service areas completed and signed off.
checkpoint-status |  |  | checkpoint | Public/personal areas completed and signed off.
checkpoint-status |  |  | checkpoint | Cleanliness and general items completed and signed off.
checkpoint-status |  |  | checkpoint | Client extras / other unit specific items completed and signed off.
checkpoint-status |  |  | checkpoint | Upload Related Ryman Fitout quality inspection record (QT-012)
checkpoint-group |  |  | section | ALS/Care Unit Services
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Systems completed and acceptable. PS3 and As Builts supplied
button | ffe0d37f-662f-5256-a48a-9140fe19b52b |  | button | Fire - Alarm, Hydrant & Sprinkler completed and acceptable. PS3 and As Builts supplied. | Yes, No
button | 72c5a78e-38df-5c89-8f62-aeb0ec042463 |  | button | Nurse Call, Security, Data and Communications completed and acceptable. PS3 and As Builts supplied. | Yes, No
button | ef152f94-cdc4-5d21-82b4-b78076c42160 |  | button | Hydraulic completed and acceptable. PS3 and As Builts supplied. | Yes, No
button | 08298853-abf3-53dd-ad7d-bf58a7900c4e |  | button | Electrical completed and acceptable. PS3 and As Builts supplied. | Yes, No
button | a68dded6-5d3b-5878-8829-e83f96270bda |  | button | Mechanical completed and acceptable. PS3 and As Builts supplied. | Yes, No
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 21098399-e1cd-5fb1-91f2-bec613d83b03 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Common, Recreational & Service Areas services
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Specified systems completed and acceptable. PS3 and As Builts supplied
button | 9c5f138d-b49f-55a1-885a-343aaa4aa622 |  | button | Specified Systems - Hydrant, Fire Alarms, Sprinklers completed and acceptable. PS3 and As Builts supplied. | Yes, No
button | 60ffd8bc-17a2-5675-9e08-febf71fea6b0 |  | button | Specified Systems - Alarms, Manual/Automatic completed and acceptable. PS3 and As Builts supplied. | Yes, No
button | bd400150-d7f4-5c64-b317-67757b80e17b |  | button | Specified Systems - Gas Detection completed and acceptable. PS3 and As Builts supplied. | Yes, No
button | f74d43e7-fb3f-5949-b697-87cac3b873d8 |  | button | Specified Systems - Nurse Call completed and acceptable. PS3 and As Builts supplied. | Yes, No
button | 490ed256-9adb-586a-9beb-c66fac179fc6 |  | button | Specified Systems - Access Controlled Doors completed and acceptable. PS3 and As Builts supplied. | Yes, No
button | d4d5a6a0-23ac-5af4-bf49-dd77d488317b |  | button | Specified Systems - Interfaced Fire/Smoke Doors/Windows/Security completed and acceptable. PS3 and As Builts supplied. | Yes, No
button | 48e02d57-8484-547d-a23b-ecc4f7efe80c |  | button | Specified Systems - Hydraulic completed and acceptable. PS3 and As Builts supplied. | Yes, No
button | d13d7d38-14ac-54d9-a750-8b7871b51522 |  | button | Specified Systems - Lifts completed and acceptable. PS3 and As Builts supplied. | Yes, No
button | 13e34554-a4ad-5be4-b377-2cdac032f7cf |  | button | Specified Systems - Mechanical, fresh air and duct extract system completed and acceptable. PS3 and As Builts supplied. | Yes, No
button | dd227483-df27-5157-bb22-cacbd96272f5 |  | button | Specified Systems - Mechanical, kitchen extract + air conditioning system completed and acceptable. PS3 and As Builts supplied. | Yes, No
button | 8ac6db2e-f916-5781-b3d8-1804139d085c |  | button | Specified Systems - Smoke Curtains completed and acceptable. PS3 and As Builts supplied. | Yes, No
button | a2f0f360-c041-5a88-a299-9984644c4c86 |  | button | Specified Systems - Essential Power Supply completed and acceptable. PS3 and As Builts supplied. | Yes, No
button | 68f62cf0-e2e1-5083-8f91-c4490377e301 |  | button | Specified Systems - Emergency Signage + Exits & Emergency Lighting completed and acceptable. PS3 and As Builts supplied. | Yes, No
button | 98c44123-27ee-55b4-8a46-dc46b661804b |  | button | Swimming Pool - Plant completed and acceptable. PS3 and As Builts supplied. | Yes, No
checkpoint-status |  |  | checkpoint | Fire Engineer inspection completed and approved
button | 40c740eb-537a-59fc-b738-efc2ddcc1181 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Electrical Engineer inspection completed and approved
button | 73038354-6f27-5187-8dc4-2c947b8a6cf8 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Mechanical / Hydraulic Engineer inspection completed and approved
button | 77ffd7d6-8660-5337-b80d-d84dba4bd0c8 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 5a5eaf5c-5786-58dc-bbb2-6dd501ca2447 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checklist-sectioned |  |  | checklist | ITP - R - Service Trenches (Common and Pulling Pits) |  |  |  |  | Yes | ITP - R - Service Trenches (Common and Pulling Pits) | 2d5c3b42-565a-4515-b4bb-a511062eec1c
checkpoint-group |  |  | section | Common Service Trenches
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Excavation
checkpoint-status |  |  | checkpoint | Bedding
checkpoint-status |  |  | checkpoint | Power Ducts and Comms Ducts
checkpoint-status |  |  | checkpoint | Mag slab installed
checkpoint-status |  |  | checkpoint | Backfill
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 93610e50-bab5-5b2e-806f-c5278844a7fa |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 0dc05c28-6bd4-5ce7-8f9c-e9b9cbd85156 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 4e2f39f4-a5db-5264-a669-34763a80e18b |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Pulling Pits
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Excavation
checkpoint-status |  |  | checkpoint | Bedding
checkpoint-status |  |  | checkpoint | Power Ducts and Comms Ducts
checkpoint-status |  |  | checkpoint | Draw cords
checkpoint-status |  |  | checkpoint | Backfill
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 9d3aaf32-be2d-5e2e-918c-f71e67ff7974 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | b6c9ff15-6c6d-50f3-a77d-cf8db6786be9 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 3a715be8-6730-592a-b9f0-3ac11b5b326c |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-sectioned |  |  | checklist | ITP - R - Apartment Pre Cast Floor Structure and Concrete Pour (per level/area) |  |  |  |  | Yes | ITP - R - Apartment Pre Cast Floor Structure and Concrete Pour (per level/area) | 4146e617-68ac-47bd-aef3-f0da5ca4c5dc
checkpoint-group |  |  | section | Pre Commencement
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
button | 0e2d13e2-baf6-584b-8e1e-254042247b7c |  | button | Confirm construction method | Double T's, Rib & Infill, Post Tensioned, Other
text | 0f2eff38-eef3-53f5-8694-ce2d6831693b |  | textbox | Other details:
button | 1fa4b08c-4f28-51ab-9cb2-e7a9258ae2cb |  | button | Propping layout confirmed as "issued for construction" | Yes, N/A
checkpoint-status |  |  | checkpoint | Propping/Falseworks Confirmed and Accepted. Evidence required.
button | ddb67c1a-117a-5a31-96c3-286058f3a8aa |  | button | Floor area cleared for propping to be erected | Yes, N/A
checkpoint-status |  |  | checkpoint | Hogging of panels within design tolerances. Installed in accordance with suppliers recommendations.
checkpoint-status |  |  | checkpoint | Adequate identification, cast date and verification of inspection marked on precast element.
checkpoint-group |  |  | section | Pre Cast Element Installation
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Hogging of panels within design tolerances. Installed in accordance with suppliers recommendations.
checkpoint-status |  |  | checkpoint | Adequate identification, cast date and verification of inspection marked on precast element.
checkpoint-status |  |  | checkpoint | Pre-cast elements inspected upon delivery and accepted for lifting.
checkpoint-status |  |  | checkpoint | Floor structure elements landed as per layout
checkpoint-status |  |  | checkpoint | If Rib and Infill, Ryman SOP followed where applicable. (Reference the document name / version)
checkpoint-status |  |  | checkpoint | Reinforcing laid as per specification
checkpoint-status |  |  | checkpoint | Service penetrations present as per specification
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved for pour
button | c049eb70-2f3c-56e1-b749-9c5aa4ef82b1 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 5a93ced9-0eed-5f31-a88e-d0b1d8f9c5eb |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Post Tensioned Floor Construction
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Stressing access correct
checkpoint-status |  |  | checkpoint | Tensioning strands quantity, length, and size correct.
checkpoint-status |  |  | checkpoint | Tendons quantity, size, and spacing correct
checkpoint-status |  |  | checkpoint | Tendon profiles (highs and lows and edges) correct
checkpoint-status |  |  | checkpoint | Antiburst are located at the correct position on the tendon
checkpoint-status |  |  | checkpoint | Grout Tubes height above concrete surface, quantity, and location correct
checkpoint-status |  |  | checkpoint | Pans and pan trimmers, anchorages, antiburst
checkpoint-status |  |  | checkpoint | Reinforcing laid as per specification
checkpoint-status |  |  | checkpoint | Service penetrations present as per specification
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved for pour
button | 57aec42b-57e9-5639-8b2b-9ca1b8454d08 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | b58c88cb-2bcf-50dd-a601-a74e17ffb5b4 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Pre Pour Planning
checkpoint-status |  |  | checkpoint | Concrete pour planning completed with subcontractor
text | f5dba30d-8e2b-56dc-b85f-0a037c144bfa |  | textbox | Date of pour
text | d1603a35-e911-5adc-9eb5-d974c21fd603 |  | textbox | Specified concrete strength:
text | 0ba7f7a3-18b2-595e-a6d8-66ff4806c8c6 |  | textbox | Concrete strength ordered:
text | a6f7c2af-d74a-51ad-bbc6-82769f1a494f |  | textbox | Concrete quantity ordered:
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | bb348a35-2567-5ce2-8a12-84b118f77a36 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Request to pour received and approved
checkpoint-status |  |  | checkpoint | Reinforcing meets specification
checkpoint-status |  |  | checkpoint | Service penetrations present and correct
checkpoint-status |  |  | checkpoint | Waterproofing elements present and correct
checkpoint-status |  |  | checkpoint | Couplers present and correct
checkpoint-status |  |  | checkpoint | Control joints/ stop ends installed accurately and correctly braced
checkpoint-status |  |  | checkpoint | Engineer Inspection conducted and passed
button | 08a6c430-bdcb-53fd-8cf7-6d1d32721410 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 83bad5b3-62b1-5559-b443-0e7f3bcb421a |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Post Pour (Post Tensioned Floor Only)
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Initial Tension applied [when concrete strength 9MPa (min) initial stress- 21% of UTS]
checkpoint-status |  |  | checkpoint | Final Tension applied [when concrete strength 22MPa (min) final stress- 80% of UTS]
checkpoint-status |  |  | checkpoint | Cutting of strands and sealing of pockets completed
checkpoint-status |  |  | checkpoint | Grouting completed as per specification and tubes clear
checkpoint-status |  |  | checkpoint | Engineer Inspection conducted and passed
button | 77861068-0775-5bea-a8e5-0adf9e8058f7 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 44d3168c-a429-5423-9657-675384ef2781 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-flat |  |  | checklist | ITP - R - Tanking/Waterproofing |  |  |  |  | Yes | ITP - R - Tanking/Waterproofing | 44d1b75b-7daf-44f6-82d8-5c75b0a21499
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Verify application of waterproofing, joint laps, thickness and number of layers as is specified.
checkpoint-status |  |  | checkpoint | Monitor installation and adequacy of protective linings during backfilling operations
checkpoint-status |  |  | checkpoint | Subcontractor to provide photo evidence of applied membranes
checkpoint-status |  |  | checkpoint | Sign off completed areas as per the agreed method PRIOR TO follow-on trades commencing their work.
checkpoint-status |  |  | checkpoint | Flood test conducted
checkpoint-status |  |  | checkpoint | PS3 received from subcontractor confirming application of membrane is in accordance with manufacturers recommendations
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | cd98d4df-fd66-5da7-a898-2ca9f1a34ef0 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | a869495d-7f94-5892-b5f0-7b1ca0f514cd |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 23b00c48-e5ff-5b60-8280-d6dfe82920c4 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-sectioned |  |  | checklist | ITP - R - Apartment Pre Cast, Timber, Insitu, Blockwork Element Installation (per area/level) |  |  |  |  | Yes | ITP - R - Apartment Pre Cast, Timber, Insitu, Blockwork Element Installation (per area/level) | 4a8e490f-7bff-45c6-a3e8-b36cf5d818bd
checkpoint-group |  |  | section | Pre-Cast Elements
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Pre-cast elements inspected upon delivery and accepted for lifting.
checkpoint-status |  |  | checkpoint | Installed vertically / aligment tolerances complies with specification (components below)
checkpoint-status |  |  | checkpoint | Stairs
checkpoint-status |  |  | checkpoint | Spandrels
checkpoint-status |  |  | checkpoint | Pre-cast panels
checkpoint-status |  |  | checkpoint | Columns
checkpoint-status |  |  | checkpoint | Stitch joints
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 76271607-48a5-5a8e-88ef-ccb1cdedf3e3 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 6bbdff9e-2f20-54c6-b4fa-341422afbd1a |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | b5599891-a4ea-5506-a13c-a876f0623340 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Timber Framing Elements
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Timber Framing installed
button | 64f20f95-88dc-5063-bec8-414da73bf4dc |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | ff64e989-187c-55e8-863c-53d3814dae10 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 9589e50a-f42b-5df4-b3f7-73626f0ead4d |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 819c88f5-0d5a-55ab-895d-5203cf8717c9 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Insuti Pour Elements
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Stitch joints - meets specification
checkpoint-status |  |  | checkpoint | Beams - meets specification
checkpoint-status |  |  | checkpoint | Panels - meets specification
checkpoint-status |  |  | checkpoint | Columns - meets specification
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 8a4f4846-e23e-55fd-a30c-22609fdef068 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | e800df17-1847-5733-abdf-3d97653417d6 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 3764ab2d-3592-5df5-984f-792825b44efa |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Reinforced Blockwork Elements
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Blockwork - meets specification
checkpoint-status |  |  | checkpoint | Reinforcing - meets specification
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | c9973922-58cb-5fa0-89b1-26aff15bf36d |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | eda03503-92d8-51b7-8c2b-5b21ba07abf8 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 6e54ae2c-6cbd-58b7-a842-152a1493f07b |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Testing
checkpoint-status |  |  | checkpoint | Chemical anchor testing completed. Upload report
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
text | 622e7c57-22c1-5a6c-8d7b-16ba6550f1e9 |  | textbox | Record sample size
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Concrete Documentation
checkpoint-status |  |  | checkpoint | Concrete pour planning completed with subcontractor
text | d773aeef-cedf-558d-904f-12373a85c91e |  | textbox | Date of pour
text | 0ba46e84-70c6-50fd-8268-6ad27b70b79c |  | textbox | Specified concrete strength:
text | 97cad03f-c189-5d51-b6d7-7217fb45a55e |  | textbox | Concrete strength ordered:
text | db5620b7-3a40-5d54-b82e-9767f0445fd1 |  | textbox | Concrete quantity ordered:
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checklist-sectioned |  |  | checklist | ITP - R - Apartment Structural Steel (per area/level) |  |  |  |  | Yes | ITP - R - Apartment Structural Steel (per area/level) | 545c64cb-7553-4443-bbac-05a22a6be6e3
checkpoint-group |  |  | section | SFC and Non SFC Accredited Contractors
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Accreditation confirmed as below.
button | 3346e514-9d49-5dd7-8f51-4651205cd305 |  | button | Confirm Steel Contractor's SFC Accreditation | SFC Accredited, Non-SFC Accredited
checkpoint-status |  |  | checkpoint | Subcontractor SFC certification (n/a response if non-SFC)
checkpoint-status |  |  | checkpoint | Steel source list and declaration of conformity
checkpoint-status |  |  | checkpoint | Detail of proposed markings if members and/or connections are to exposed to view. (only applicable for Architecturally Exposed Structural Steel, AESS)
checkpoint-status |  |  | checkpoint | Structural Steel installed, test results uploaded and attached. Meets specification
button | cbf52c58-b256-5b3b-bb80-a3cee7eb4cc3 |  | button | Chemical anchor tests conducted and documented | Yes, Reworked, N/A
button | c0382b40-29ba-50eb-93ec-1f7a14d91561 |  | button | Mechanical anchor tests conducted and documented | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Bolting requirements confirmed against design requirements.
checkpoint-status |  |  | checkpoint | Welding conforms to design requirements.
checkpoint-status |  |  | checkpoint | Engineer Inspection conducted and passed
button | 543c61be-8ed3-5a2a-aad5-33c616f58202 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 25880649-fa87-5737-a2d0-13b755e45c8d |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Mandatory Completion for Non SFC Accredited Contractors ONLY
checkpoint-status |  |  | checkpoint | Non SFC only: Independent preparation, assembly and fabrication inspection report received and issued to subsubcontractor
checkpoint-status |  |  | checkpoint | Non SFC only: Independent welding inspection report received and issued to subcontractor
checkpoint-status |  |  | checkpoint | Non SFC only: Independent surface treatment inspection report received and issued to subcontractor
checkpoint-status |  |  | checkpoint | Non SFC only: Independent paint coatings inspection report received and issued to subcontractor
checkpoint-status |  |  | checkpoint | Non SFC only: Independent galvanised coating inspection report received and issued to subcontractor
checkpoint-status |  |  | checkpoint | Non SFC only: Final weld inspector compliance certificate received
checkpoint-status |  |  | checkpoint | Non SFC only: Final surface preparation inspector compliance certificate received
checkpoint-status |  |  | checkpoint | Non SFC only: Final paint coating inspector compliance certificate received
checkpoint-status |  |  | checkpoint | Non SFC only: Final galvanising inspector compliance certificate received
holdpoint |  |  | signoff | Raise remedial as required.
checklist-sectioned |  |  | checklist | I - C - Site Visit Report |  |  |  |  | Yes | I - C - Site Visit Report | 5779b536-3753-445e-8b36-56ba53a149d7
checkpoint-group |  |  | section | Site Visit Details
checkpoint-no-status |  |  | checkpoint | Site Details
text | 65f69954-f3b8-5edb-b70f-4c9c3bc6f4bf |  | textbox | Area of site visited:
text | 28fb2723-f954-5448-b5f3-15a2ed6fbf76 |  | textbox | Work element monitored / purpose of visit:
text | 79957183-cf05-58ad-9f30-4bed4a660696 |  | textbox | Date of site visit:
text | 794afb11-5e80-5ffe-9e06-3876e75a9113 |  | textbox | Time on site (include start and end times):
text | cc14af9d-af85-5325-8d3c-e9bcfca84cc5 |  | textbox | Weather conditions:
text | c2ac2bea-f740-58ab-bfbe-b6ecaec5d4b8 |  | textbox | Report prepared by:
text | 86db574d-ccd1-576e-9835-1d648074c737 |  | textbox | Additional personnel accompanying:
checkpoint-status |  |  | checkpoint | Consented drawings have been followed
text | 33b8ea75-bc69-541d-90c7-18202965cbf0 |  | textbox | Building Consent Number:
text | 3ffa0431-a775-5a1c-95df-e12c8869530f |  | textbox | Drawing & Revision Number(s):
checkpoint-status |  |  | checkpoint | Health and Safety acceptable
checkpoint-group |  |  | section | Site Report Summary/Closeout
checkpoint-status |  |  | checkpoint | Works accepted and may proceed
label | b6d62539-2b6a-5000-984d-a253406a195f |  | note | Select Pass if works accepted or Fail if reinspection required to defective elements
boolean | 285401b8-ea10-52ea-95e4-ca08e0d36c0f |  | tickbox | Report attached or remedials summarised below
text | 56d4d7ed-2866-502a-98af-3a8c37ec5c38 |  | textbox | Remedial(s)
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | ITP - R - Foundation Piling |  |  |  |  | Yes | ITP - R - Foundation Piling | 5bdc1c5d-0a79-4ea7-989b-551b6005d9a7
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Subcontractor piling card reviewed and meets requirements
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Piles set out, surveyed, and marked.
checkpoint-status |  |  | checkpoint | Site condition acceptable for piling rig
checkpoint-status |  |  | checkpoint | Piles meet set out, heights, and correct within tolerances.
checkpoint-status |  |  | checkpoint | All piling cards received, filed, and meet requirements.
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 3bb95f66-bb97-5417-a569-80601acc6526 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 28f53f3d-b5a0-5c50-ad49-2bee8fffb9fc |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | bb370923-70c7-529c-a8b0-d4ee2b306cb0 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-sectioned |  |  | checklist | ITP - R - Ancillary Building Build (per ancillary building unit) |  |  |  |  | Yes | ITP - R - Ancillary Building Build (per ancillary building unit) | 614b82c9-db23-44b1-8cde-1820ca001118
checkpoint-group |  |  | section | Structure/Framing
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Framing system installed, square and plumb
checkpoint-status |  |  | checkpoint | Council pre-clad inspection completed and approved. Note date of inspection in comments
button | 3a600380-d481-5850-bfe7-6b7ca67915e0 |  | button | Note remedial work needed | None, Minor, Major
text | 873e9b74-4d0d-549c-87fb-e5d7347f4b98 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Roofing
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Verify materials supplied to site (material and fixings) are as specified or approved samples
checkpoint-status |  |  | checkpoint | Construction complies with specifications
checkpoint-status |  |  | checkpoint | Obtain and upload all performance and authority certificates as required by specification or statutory regulations.
checkpoint-status |  |  | checkpoint | Council Pre-Roof Inspection completed and passed
button | 149573b0-1406-564c-904b-736843dead2d |  | button | Note remedial work needed | None, Minor, Major
text | 0ee790db-b4d0-58cd-80f8-62a3255a3438 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Façade
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Envelope/Watertightness Completed (requirements below)
checkpoint-status |  |  | checkpoint | Ecoply Board installed
checkpoint-status |  |  | checkpoint | Lintels installed
checkpoint-status |  |  | checkpoint | Tapes and VaproShield installed.
checkpoint-status |  |  | checkpoint | Windows and Sliders installed
checkpoint-status |  |  | checkpoint | Flashing installed
checkpoint-status |  |  | checkpoint | Envelope Penetrations completed
checkpoint-status |  |  | checkpoint | Council pre-wrap inspection completed and passed
button | eaded4ce-37b2-59ab-bcdc-6417e3c2feb5 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Council brickwork 'half-high' inspection completed and acceptable
button | 98bc0078-03f5-5b02-81e8-e9ad38483ade |  | button | Note remedial work needed | None, Minor, Major
text | a8cde1c8-d019-5a72-bc37-08f930d22b60 |  | textbox | Describe cladding type:
button | 12200d47-533d-5508-affb-86dba0bb571e |  | button | Brick Works completed | Yes, Reworked, N/A
button | bce96f4f-a729-52c7-83f2-8019204476d7 |  | button | STO Poly Plaster completed | Yes, Reworked, N/A
text | 6d4e2d0e-d7c5-5a3d-a6e2-129385fe1d65 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Pre-Line
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Pre-line completed
checkpoint-status |  |  | checkpoint | Framing system installation completed and acceptable
checkpoint-status |  |  | checkpoint | Nogs Installed as below and comply
checkpoint-status |  |  | checkpoint | Electrical First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Plumbing First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Insulation installation completed and acceptable
checkpoint-status |  |  | checkpoint | Security, Comms and Data First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | HVAC First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Fire Security First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Under floor heating First Fix (including screeding and soundproofing of the bathrooms/ wc) completed and acceptable
checkpoint-status |  |  | checkpoint | Kitchen extract First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Passive fire installation completed and acceptable
checkpoint-status |  |  | checkpoint | Suspended ceiling grids installation completed and acceptable
checkpoint-status |  |  | checkpoint | Pre-line plumbing external inspections completed and uploaded. Any remedial work signed off.
button | 8adfd648-206a-5e3e-9693-c252365b77c3 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Pre-line building external inspections completed and uploaded. Any remedial work signed off.
button | 754cd2d3-3364-59b5-9805-795f5cb813a4 |  | button | Note remedial work needed | None, Minor, Major
text | cb26f1de-975b-509f-8bab-0c169617f561 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Post-Line GIB
checkpoint-status |  |  | checkpoint | GIB installation correct, screw types, pattern, etc..
checkpoint-status |  |  | checkpoint | Fire rated GIB installed to adjoining unit walls & garage, correct thickness.
checkpoint-status |  |  | checkpoint | Post Line Council Inspection completed and acceptable. GIB stopping to proceed
button | 050b0d60-7f3c-5f4b-b569-5b9f48284d2f |  | button | Note remedial work needed | None, Minor, Major
checklist-flat |  |  | checklist | ITP - R - Apartment Roofing (per area) |  |  |  |  | Yes | ITP - R - Apartment Roofing (per area) | 704da179-d617-468d-95ab-12eebc483c6f
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Verify materials supplied to site (material and fixings) are as specified or approved samples
checkpoint-status |  |  | checkpoint | Producer Statement Construction (PS3) received and attached for installation of roof abseil and/or fall arrest system
checkpoint-status |  |  | checkpoint | Construction complies with specifications
checkpoint-status |  |  | checkpoint | Obtain and upload all performance and authority certificates as required by specification or statutory regulations.
checkpoint-status |  |  | checkpoint | Council Pre-Roof Inspection completed and passed
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | a266ace1-2241-5fa6-96c0-df1b757d17fa |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 4ca069e1-25e9-52f7-8d90-e16040a2e7b8 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 75824e7b-c1d8-5ec4-bc39-dc1ad85c2a7b |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-sectioned |  |  | checklist | ITP - R - Services |  |  |  |  | Yes | ITP - R - Services | 753c3917-1f8e-449b-bf5a-572d063683e6
checkpoint-group |  |  | section | Residential Apartment/Townhouse Unit
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Fire - Alarm, Hydrant & Sprinkler completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Nurse Call, Security, Data and Communications completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Hydraulic completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Electrical completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Mechanical completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | c6609324-cbe7-511e-ad0c-c055080a3dd7 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Common, Recreational & Service Areas
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Specified Systems - Hydrant, Fire Alarms, Sprinklers completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Alarms, Manual/Automatic completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Gas Detection completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Nurse Call completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Access Controlled Doors completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Interfaced Fire/Smoke Doors/Windows/Security completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Hydraulic completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Lifts completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Mechanical, fresh air and duct extract system completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Mechanical, kitchen extract + air conditioning system completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Smoke Curtains completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Essential Power Supply completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Emergency Signage + Exits & Emergency Lighting completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Swimming Pool - Plant completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Fire Engineer inspection completed and approved
button | 53d8f7a2-c2fe-53e5-80f4-7a7361c6321e |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Electrical Engineer inspection completed and approved
button | 2169ac48-ca39-5628-b59e-b9fcd5519abd |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Mechanical / Hydraulic Engineer inspection completed and approved
button | 6793f66d-0883-5e5e-840c-ec087e6a62a6 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | b80d075b-df5e-5459-a4f0-93a0c3ea2674 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checklist-flat |  |  | checklist | ST - R - Double T Installation |  |  |  |  | Yes | ST - R - Double T Installation | 78592b56-9c3a-402f-9464-e5a4aad4ee60
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | Inspected on arrival & damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Shoreload completed
checkpoint-status |  |  | checkpoint | Double T install complete and acceptable (checked location and level)
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | a6896be1-3425-5c95-9276-797cb5eb7915 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-sectioned |  |  | checklist | ITP - R - Concrete - Planning and Pour (per area) |  |  |  |  | Yes | ITP - R - Concrete - Planning and Pour (per area) | 8c43561d-36b9-410f-8d49-69a38c201a23
checkpoint-group |  |  | section | Pre Pour Planning
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Concrete pour planning completed with subcontractor
text | ce76300b-58fb-51c7-884e-b2dcb5f40180 |  | textbox | Date of pour
text | f14e3375-b746-5d6f-b105-5c3e1ab6654c |  | textbox | Specified concrete strength:
text | 0e5763f3-d9e7-59ee-8731-f463cf1fdacf |  | textbox | Concrete strength ordered:
text | 0cd28008-b13a-5574-9116-dcba7c190315 |  | textbox | Concrete quantity ordered:
text | a5373b52-461d-5f10-8d60-714e8d20fd6f |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | Request to pour received and approved
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
button | cbf10e25-e111-5432-a1c6-3dad547bf3b8 |  | button | Reinforcing meets specification | Yes, Reworked, N/A
button | 7dc4bbaa-2598-5473-9251-e873db78f0b1 |  | button | Service penetrations present and correct | Yes, Reworked, N/A
button | 105fa59e-ba9b-5289-9bf1-d9fec698d571 |  | button | Waterproofing elements present and correct | Yes, Reworked, N/A
button | 38151330-c8d8-5d35-8c3c-ff2c23982f6c |  | button | Couples present and correct | Yes, Reworked, N/A
button | b5660acb-7c5d-5d58-9766-dbe216a1738a |  | button | Control joints/ stop ends installed accurately and correctly braced | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Engineer Inspection conducted and passed
button | 3e913e7c-cd3f-5833-8b42-52cfdc796f7c |  | button | Note remedial work needed | None, Minor, Major
text | 74063451-c06b-50a2-8c55-162ae127afe7 |  | textbox | Inspected by and date:
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Documentation
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checklist-sectioned |  |  | checklist | ITP - R - Apartment Pre & Post Line (per area/grid/Location) |  |  |  |  | Yes | ITP - R - Apartment Pre & Post Line (per area/grid/Location) | 978140cc-7ff9-40ec-bfbd-469c3ceb5d6b
checkpoint-group |  |  | section | Pre-Line
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Pre-line completed
button | a501abe1-bd28-5d0f-8f77-59bf1fa23452 |  | button | Framing system installation completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Nogs Installed and comply
button | 25c42aa5-869e-5023-be40-fefe7276f3bd |  | button | Electrical First Fix completed and acceptable | Yes, Reworked, N/A
button | 2a94a86f-b91f-5236-9460-d03077a4dae5 |  | button | Plumbing First Fix completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Insulation installation completed and acceptable
checkpoint-status |  |  | checkpoint | Security, Comms and Data First Fix completed and acceptable
button | 10c14555-a5f6-5c8c-95d2-08a604d4d63f |  | button | HVAC First Fix completed and acceptable | Yes, Reworked, N/A
button | 6d2d186f-eb11-59b5-8500-43447fb0e175 |  | button | Fire Security First Fix completed and acceptable | Yes, Reworked, N/A
button | c353c53d-95f4-5642-962a-f01d76bdfbd8 |  | button | Underfloor heating First Fix (including screeding and soundproofing of the bathrooms/ wc) completed and acceptable | Yes, Reworked, N/A
button | e602039b-499a-5ed8-8267-eb125119d1a8 |  | button | Kitchen extract First Fix completed and acceptable | Yes, Reworked, N/A
button | 5b130390-ce1b-52db-b862-f52544fe7003 |  | button | Passive fire installation completed and acceptable | Yes, Reworked, N/A
button | cd8f1f1f-d00b-5e8e-bd3d-abccffa7c038 |  | button | Suspended ceiling grids installation completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Pre-line plumbing external inspections completed and uploaded. Any remedial work signed off.
button | 7fcdd295-288d-57cc-84a7-bfe97e432b53 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Pre-line building external inspections completed and uploaded. Any remedial work signed off.
button | 772c7c59-3389-5ddb-b4fd-4a59cdbd7863 |  | button | Note remedial work needed | None, Minor, Major
text | 1c00d616-7f31-5abf-b500-3a9d47914e77 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Post-Line GIB
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | GIB installation correct, screw types, pattern, etc..
checkpoint-status |  |  | checkpoint | Fire rated GIB installed
checkpoint-status |  |  | checkpoint | All preline services & passive fire (where required) completed, area accessible and substrate acceptable
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Consider bracing, adhesive/sealant & lining layer(s) requirements (including fire stopping between layers)
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Services/penetrations, correctly formed & located (consider cut-out tolerances where applicable)
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Correct fixing pattern/sealant (including fire)/adhesive/layers installed to align with consented design and specifications
checkpoint-status |  |  | checkpoint | All lining(s) completed correctly to specification & level of finish acceptable in respective area(s)
checkpoint-status |  |  | checkpoint | Post Line Council Inspection completed and acceptable. GIB stopping to proceed
button | 85a32b19-0db8-5072-87cb-ee5cb7474001 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checklist-flat |  |  | checklist | ITP - R - Unit Benchmarking (Use at stage level) |  |  |  |  | Yes | ITP - R - Unit Benchmarking (Use at stage level) | a297da8b-e781-41d4-adee-26c91035ec87
checkpoint-status |  |  | checkpoint | Benchmark standard agreed as per Quality Management Plan
button | 7dcff55c-54e5-556c-a319-ee9e504daaaf |  | button | Project Manager or delegate present | Yes, No, N/A
button | a5cf7ab6-239d-58f9-a212-2e326c067a7b |  | button | Sales representative or delegate present | Yes, No, N/A
button | b78cfb06-b4d8-5373-8ac2-5bf5a72d3a4d |  | button | QA Advisor or delegate present | Yes, No, N/A
button | a3b541fd-612b-571e-89bd-50c2fee293ca |  | button | Design representative or delegate present | Yes, No, N/A
text | 729ef6b5-c1bd-5cfa-a7e7-0dcfc2f060a5 |  | textbox | Benchmark details (e.g. apartment number or explanation)
text | 5a9de39d-f159-51fd-9320-0edd7a4c2b36 |  | textbox | Record benchmark date
checklist-sectioned |  |  | checklist | ITP - R - B01 Fitout/Services (per area/room) |  |  |  |  | Yes | ITP - R - B01 Fitout/Services (per area/room) | b3bc9012-58b7-423c-addd-1253b5af1f49
checkpoint-group |  |  | section | All areas/rooms
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
button | 5a04e2c2-217d-5a2c-ac38-2373fd48d4e9 |  | button | Sanitary areas completed and signed off | Yes, Reworked, N/A
button | 6456c8c6-88f6-5494-a636-fa60cb2e7808 |  | button | Service areas completed and signed off. | Yes, Reworked, N/A
button | e29497c9-d65e-569b-b409-75f4f3977b56 |  | button | Public/personal areas completed and signed off. | Yes, Reworked, N/A
button | 8c38843a-c09c-599a-8082-979567146395 |  | button | Cleanliness and general items completed and signed off. | Yes, Reworked, N/A
button | 3c9ba01d-f26d-58ba-b211-b21148889430 |  | button | Client extras / other unit specific items completed and signed off. | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Upload Related Ryman Fitout quality inspection record (QT-012)
checkpoint-group |  |  | section | ALS/Care unit services
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Systems completed and acceptable.
checkpoint-status |  |  | checkpoint | Fire - Alarm, Hydrant & Sprinkler completed and acceptable.
checkpoint-status |  |  | checkpoint | Nurse Call, Security, Data and Communications completed and acceptable.
checkpoint-status |  |  | checkpoint | Hydraulic completed and acceptable.
checkpoint-status |  |  | checkpoint | Electrical completed and acceptable.
checkpoint-status |  |  | checkpoint | Mechanical completed and acceptable.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | d4afabc1-fee1-5bab-aa27-4e95bca63f7d |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Common, Recreational & Service Areas services
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Specified systems completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Hydrant, Fire Alarms, Sprinklers completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Alarms, Manual/Automatic completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Gas Detection completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Nurse Call completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Access Controlled Doors completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Interfaced Fire/Smoke Doors/Windows/Security completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Hydraulic completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Lifts completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Mechanical, fresh air and duct extract system completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Mechanical, kitchen extract + air conditioning system completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Smoke Curtains completed and acceptable.
checkpoint-status |  |  | checkpoint | Specified Systems - Essential Power Supply completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Specified Systems - Emergency Signage + Exits & Emergency Lighting completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Swimming Pool - Plant completed and acceptable. PS3 and As Builts supplied.
checkpoint-status |  |  | checkpoint | Fire Engineer inspection completed and approved
button | 6522e292-4e6c-5b1e-ba32-a027d32e5d5b |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Electrical Engineer inspection completed and approved
button | 75b10400-86c5-5bd8-af99-60b8d7638f5e |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Mechanical / Hydraulic Engineer inspection completed and approved
button | e0a6aa0d-f8a6-55ef-ac27-055b6c5c2e5a |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | d2777205-30b8-5c84-95f0-327a0edb7eae |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checklist-sectioned |  |  | checklist | ITP - R - Apartment Build (per area/level) |  |  |  |  | Yes | ITP - R - Apartment Build (per area/level) | b6f4ed07-4d3a-42dd-aed1-d4d39980355a
checkpoint-group |  |  | section | Façade
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Envelope/Watertightness Completed (requirements below)
button | 2e00bf3e-9e79-54dc-bf0f-c4ed59b8a9a5 |  | button | Ecoply Board installed | Yes, Reworked, N/A
button | cd096575-f498-5702-b719-52c7555748d6 |  | button | Lintels installed | Yes, Reworked, N/A
button | dc02fea6-15f5-5dfe-9e90-504459a16ca0 |  | button | Tapes and VaproShield installed. | Yes, Reworked, N/A
button | 9e36a586-63b7-5d41-ad54-582d678d94cd |  | button | Windows and Sliders installed | Yes, Reworked, N/A
button | cd4697f4-3749-5eb3-bf11-02c47ed04b6f |  | button | Flashing installed | Yes, Reworked, N/A
button | b1ac6243-3ef7-57e9-a344-1a2b077615dd |  | button | Envelope Penetrations completed | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Council pre-wrap inspection completed and passed
button | 21c8ccf6-40ac-506f-be87-b9706b0699a7 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council brickwork 'half-high' inspection completed and acceptable
button | a94cc7d8-96d3-5b0d-b0f3-a4c1671acaa9 |  | button | Note remedial work needed | None, Minor, Major
text | 1168a2d5-41d4-587a-a6cb-1459296f7252 |  | textbox | Describe cladding type:
button | 00e19b42-661e-5295-969b-37454114ad6b |  | button | Brick Works completed | Yes, Reworked, N/A
button | 8b50e452-301f-5307-92db-103cdb17fc06 |  | button | STO Poly Plaster completed | Yes, Reworked, N/A
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Installed horizontal fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed vertical fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Eyebrow and soffit fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Boss Bulkhead Batt fire barriers as per sepecifications
checkpoint-status |  |  | checkpoint | Installed Gutter fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Concrete Pannels (under roof) fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Hatches fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Consultant Inspections Completed and Passed
button | c503cd9b-bdf8-5b4a-a0a1-fb7f7dcd8485 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 8b48d9c1-f389-52f7-a816-37b7ba5ada89 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Pre-Line
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Pre-line completed
button | 5e895fc4-ebfa-558c-a9aa-ef0d5fd4ba24 |  | button | Framing system installation completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Nogs Installed as below and comply
button | 534967c5-3b81-5f7c-a437-a2279e611df8 |  | button | Electrical First Fix completed and acceptable | Yes, Reworked, N/A
button | 854b9f9c-58f4-5290-a483-250f5b651ca0 |  | button | Plumbing First Fix completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Insulation installation completed and acceptable
checkpoint-status |  |  | checkpoint | Security, Comms and Data First Fix completed and acceptable
button | 009e3528-c44f-50bb-98a1-b0f60223445c |  | button | HVAC First Fix completed and acceptable | Yes, Reworked, N/A
button | 5536a335-0515-5aaf-949a-a842e72dcad9 |  | button | Fire Security First Fix completed and acceptable | Yes, Reworked, N/A
button | 561cce7a-be35-5b71-b915-af56cd9888bc |  | button | Under floor heating First Fix (including screeding and soundproofing of the bathrooms/ wc) completed and acceptable | Yes, Reworked, N/A
button | 803d79e3-434f-5adc-8e98-05fe1d326658 |  | button | Kitchen extract First Fix completed and acceptable | Yes, Reworked, N/A
button | c19f6d9c-62a7-58a1-be71-0d222f9c2ab8 |  | button | Passive fire installation completed and acceptable | Yes, Reworked, N/A
button | 1a41dc37-2099-5b55-987d-d7b820c602b7 |  | button | Suspended ceiling grids installation completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Pre-line plumbing external inspections completed and uploaded. Any remedial work signed off.
button | 0760d416-0a2e-5fa0-8b45-2110281f8d6c |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Pre-line building external inspections completed and uploaded. Any remedial work signed off.
button | c2a8ce51-2f6c-54d1-9596-0c99f53ff357 |  | button | Note remedial work needed | None, Minor, Major
text | 795a7829-2a20-5379-80c0-193a56cc5b77 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Post-Line GIB
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | GIB installation correct, screw types, pattern, etc..
checkpoint-status |  |  | checkpoint | Fire rated GIB installed
checkpoint-status |  |  | checkpoint | All preline services & passive fire (where required) completed, area accessible and substrate acceptable
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Consider bracing, adhesive/sealant & lining layer(s) requirements (including fire stopping between layers)
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Services/penetrations, correctly formed & located (consider cut-out tolerances where applicable)
checkpoint-status |  |  | checkpoint | Ceilings and Walls: Correct fixing pattern/sealant (including fire)/adhesive/layers installed to align with consented design and specifications
checkpoint-status |  |  | checkpoint | All lining(s) completed correctly to specification & level of finish acceptable in respective area(s)
checkpoint-status |  |  | checkpoint | Post Line Council Inspection completed and acceptable. GIB stopping to proceed
button | 5c809249-d8e6-5fbe-8a72-5609bcc72c3f |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-group |  |  | section | Balustrade Testing
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Balustrade Anchor Bolt Pull Testing
label | a4998ce2-b6b2-596c-9df2-8afad11a0d7d |  | note | Test results to be uploaded
checkpoint-status |  |  | checkpoint | Balustrade Lateral Load Testing
label | 8bc53c51-1b9a-5b0d-bbbd-221d4618f49a |  | note | Test results to be uploaded
checkpoint-status |  |  | checkpoint | Consultant Inspections Completed and Passed
button | c786f264-4b46-5419-8663-e4ece162af5e |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 80c07156-fba1-52e2-a304-b5ea821ca7c7 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-flat |  |  | checklist | ITP - R - Fitout (per unit) |  |  |  |  | Yes | ITP - R - Fitout (per unit) | bc1193c8-c5d2-4733-ac7f-324863b03203
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Finishing completed, meets benchmark standard. Refer separate checklist. Full response to the items below needed.
button | a40f588e-7c14-511c-b2ce-40e7c7cce575 |  | button | Hardware/Fittings | Yes, Reworked, N/A
button | 38f4c701-6b1a-50a8-bfe3-8285b324bca8 |  | button | Plumbing completed and acceptable | Yes, Reworked, N/A
button | 9dbd4ca4-4471-58b3-8eab-99bb094b3420 |  | button | Electrical completed and acceptable | Yes, Reworked, N/A
button | 1e99b54e-80b0-51d5-9dd4-9ecc98bf51c1 |  | button | Joinery/Doors completed and acceptable | Yes, Reworked, N/A
button | 4aa23148-5785-52df-8175-71113c008c88 |  | button | Decorating completed and acceptable | Yes, Reworked, N/A
button | a21546ac-9859-5289-baa6-4c0f1a0648b7 |  | button | Flooring completed and acceptable | Yes, Reworked, N/A
button | 1f8ad32d-0898-5965-95be-6ddd4069e8c3 |  | button | Other works completed (inc. client extras) and acceptable, state below. | Yes, Reworked, N/A
text | b26a1316-e447-54d5-b8cf-4c5e11efe3e6 |  | textbox | Details:
checkpoint-status |  |  | checkpoint | Upload Related Ryman Fitout quality inspection record (QT-012)
holdpoint |  |  | signoff | Raise remedial as required.
checklist-flat |  |  | checklist | ITP - R - Project Manager Handover to Operations (per unit) |  |  |  |  | Yes | ITP - R - Project Manager Handover to Operations (per unit) | c14c0cfd-32b1-48f8-bef9-85f2f434ef1c
checkpoint-status |  |  | checkpoint | No outstanding defects/snag list items
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Chattels confirmed as operational
checkpoint-status |  |  | checkpoint | Chattel manuals provided.
checkpoint-status |  |  | checkpoint | Unit meets benchmark standards and expectations
checkpoint-status |  |  | checkpoint | Resident "Welcome Letter" completed by PM and left in property.
checkpoint-status |  |  | checkpoint | Formal handover to Sales/Operations conducted by PM.
checklist-flat |  |  | checklist | ITP - R - Contractor Allocation (Use at stage level for each subcontractor on the stage) |  |  |  |  | Yes | ITP - R - Contractor Allocation (Use at stage level for each subcontractor on the stage) | c9977c85-e60f-4973-90e7-9acf5057e187
checkpoint-status |  |  | checkpoint | Contractor Allocated
text | 9cf79b80-2033-536e-9388-fea1d7d80f31 |  | textbox | Record Subcontractor Company Name
text | f7cc3f41-a2ed-52f2-8fa3-e9d03845de34 |  | textbox | Record scope of works
checkpoint-status |  |  | checkpoint | Specifications confirmed with subcontractor management
checkpoint-status |  |  | checkpoint | Programme milestones confirmed with subcontractor management
checkpoint-status |  |  | checkpoint | All subcontractor ITPs (inspection test plans) attached and agreed.
checkpoint-status |  |  | checkpoint | Quality expectations and requirements discussed and confirmed as understood.
holdpoint |  |  | signoff | Escalate concerns to QA Advisor
checklist-sectioned |  |  | checklist | ITP - R - Townhouse Block Build (per townhouse block) |  |  |  |  | Yes | ITP - R - Townhouse Block Build (per townhouse block) | c9cca8f2-0011-430f-8464-692397bb61b8
checkpoint-group |  |  | section | Structure/Framing
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Framing system installed, square and plumb
checkpoint-status |  |  | checkpoint | Council pre-clad inspection completed and approved. Note date of inspection in comments
button | 3c8d9f20-0f72-564f-aaf0-6cdad64dd5a7 |  | button | Note remedial work needed | None, Minor, Major
text | ff419c58-3551-57ad-949e-885bd1de27d7 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Roofing
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Verify materials supplied to site (material and fixings) are as specified or approved samples
checkpoint-status |  |  | checkpoint | Construction complies with specifications
checkpoint-status |  |  | checkpoint | Obtain and upload all performance and authority certificates as required by specification or statutory regulations.
checkpoint-status |  |  | checkpoint | Council Pre-Roof Inspection completed and passed
button | ae862b33-8ff8-53f6-94df-e63117f37f9b |  | button | Note remedial work needed | None, Minor, Major
text | 230a9e24-5105-5f22-bf82-6961380e30c6 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Façade
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Envelope/Watertightness Completed (requirements below)
checkpoint-status |  |  | checkpoint | Ecoply Board installed
checkpoint-status |  |  | checkpoint | Lintels installed
checkpoint-status |  |  | checkpoint | Tapes and VaproShield installed.
checkpoint-status |  |  | checkpoint | Windows and Sliders installed
checkpoint-status |  |  | checkpoint | Flashing installed
checkpoint-status |  |  | checkpoint | Envelope Penetrations completed
checkpoint-status |  |  | checkpoint | Council pre-wrap inspection completed and passed
button | 7699b8a2-7c3e-541f-9509-cd73b78a63c4 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Council brickwork 'half-high' inspection completed and acceptable
button | 0eb1d965-98ba-5393-92f5-013c144a142c |  | button | Note remedial work needed | None, Minor, Major
text | e547a3fc-1eb7-5f36-a234-393298603938 |  | textbox | Describe cladding type:
button | 75d979e6-8b6f-5978-98bb-ed397a1944e4 |  | button | Brick Works completed | Yes, Reworked, N/A
button | c1398f65-7e18-5fe7-a677-bc4a69ca24bb |  | button | STO Poly Plaster completed | Yes, Reworked, N/A
text | aa22a4dd-7cef-5d7d-be4d-c078fa44952d |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Pre-Line
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Pre-line completed
checkpoint-status |  |  | checkpoint | Framing system installation completed and acceptable
checkpoint-status |  |  | checkpoint | Nogs Installed as below and comply
button | d8d9dff7-f25d-5336-9983-b6b94ae2f357 |  | button | Steel Stud frame installation completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Electrical First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Plumbing First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Insulation installation completed and acceptable
checkpoint-status |  |  | checkpoint | Security, Comms and Data First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | HVAC First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Fire Security First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Under floor heating First Fix (including screeding and soundproofing of the bathrooms/ wc) completed and acceptable
checkpoint-status |  |  | checkpoint | Kitchen extract First Fix completed and acceptable
checkpoint-status |  |  | checkpoint | Passive fire installation completed and acceptable
checkpoint-status |  |  | checkpoint | Suspended ceiling grids installation completed and acceptable
checkpoint-status |  |  | checkpoint | Pre-line plumbing external inspections completed and uploaded. Any remedial work signed off.
button | 62090abd-b8e4-5826-8a81-c132b2b5c686 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Pre-line building external inspections completed and uploaded. Any remedial work signed off.
button | 656baa1d-9283-56ca-8137-f52e53f75931 |  | button | Note remedial work needed | None, Minor, Major
text | 75968acd-b611-5676-9b79-7dcc8f50da96 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Post-Line GIB
checkpoint-status |  |  | checkpoint | GIB installation correct, screw types, pattern, etc..
checkpoint-status |  |  | checkpoint | Fire rated GIB installed to adjoining unit walls & garage, correct thickness.
checkpoint-status |  |  | checkpoint | Post Line Council Inspection completed and acceptable. GIB stopping to proceed
button | 626f01f9-99cd-5955-8746-735c76e98ecb |  | button | Note remedial work needed | None, Minor, Major
checklist-sectioned |  |  | checklist | ITP - R - Apartment Facade (per elevation/grid) |  |  |  |  | Yes | ITP - R - Apartment Facade (per elevation/grid) | d1822e91-ba91-494e-86c4-4beb4747853d
checkpoint-group |  |  | section | Façade
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Envelope/Watertightness Completed (requirements below)
button | 7b799de5-d89b-56cc-a8dc-06e12ad10315 |  | button | Ecoply Board installed | Yes, Reworked, N/A
button | c96066df-1aa8-5d88-adbd-1bcf356b71c3 |  | button | Lintels installed | Yes, Reworked, N/A
button | 83d815ee-6b20-5f6e-b649-92436370d28e |  | button | Tapes and VaproShield installed. | Yes, Reworked, N/A
button | ffc3214f-b1a9-56d5-835f-42e553945671 |  | button | Windows and Sliders installed | Yes, Reworked, N/A
button | ad9270cf-ae3f-5edf-b170-a49568ac6217 |  | button | Flashing installed | Yes, Reworked, N/A
button | 910e571c-721e-58c0-b6cf-9aefb6c97b58 |  | button | Envelope Penetrations completed | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Balcony waterproofing completed
checkpoint-status |  |  | checkpoint | Council pre-wrap inspection completed and passed
button | 4d958e1d-4ccd-5059-a668-9a9b829ea32a |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council brickwork 'half-high' inspection completed and acceptable
button | 7e8b29b8-28b5-5c5f-baa2-cac8b2b3c3e5 |  | button | Note remedial work needed | None, Minor, Major
text | fa68311c-3bf5-5ec6-8096-23417aec4d84 |  | textbox | Describe cladding type:
button | 605d7c71-7285-5cea-96a9-fffa90c07de4 |  | button | Brick Works completed | Yes, Reworked, N/A
button | b7690567-0714-5626-ade9-8c805f6dc0a4 |  | button | STO Poly Plaster completed | Yes, Reworked, N/A
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Installed horizontal fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed vertical fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Eyebrow and soffit fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Boss Bulkhead Batt fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Gutter fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Concrete Panels (under roof) fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Installed Hatches fire barriers as per specifications
checkpoint-status |  |  | checkpoint | Consultant Inspections Completed and Passed
button | 9ba6d9e0-d2db-58ff-a06e-493869ea2eec |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | cbf6dbad-c8d8-5682-9a08-4327c172bdd3 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Balustrade Testing
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Balustrade Anchor Bolt Pull Testing
label | e84ba05c-e2c5-56b0-9762-50cbb23ce730 |  | note | Test results to be uploaded
checkpoint-status |  |  | checkpoint | Balustrade Lateral Load Testing
label | d4cccf75-1aae-5869-abd4-235697bce50c |  | note | Test results to be uploaded
checkpoint-status |  |  | checkpoint | Consultant Inspections Completed and Passed
button | fde709d8-07b9-54c5-9b0e-e84b20dfe1dd |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 00089dff-358a-57df-bc84-e5cce1685a64 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-flat |  |  | checklist | ITP - R - On Grade Slab Pre-Pour (per area) |  |  |  |  | Yes | ITP - R - On Grade Slab Pre-Pour (per area) | d252a718-88ef-4bfe-91a1-9878753d4592
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Survey set out (height, location, setout) - confirmation attached.
checkpoint-status |  |  | checkpoint | Underground services installation completed
checkpoint-status |  |  | checkpoint | Backfilling completed
checkpoint-status |  |  | checkpoint | Waterproofing completed
checkpoint-status |  |  | checkpoint | DPM overlapping/taping with no tears or perforations. Council requirement
checkpoint-status |  |  | checkpoint | Reinforcing completed
checkpoint-status |  |  | checkpoint | Engineer sign off completed and approved for pour
button | bca8c1db-ef6c-54dd-84c1-37aa05e75aec |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved for pour
button | 1a631bb3-4eb6-5947-88ba-eb9f1085e170 |  | button | Note remedial work needed | None, Minor, Major
text | 4fd31eab-46c8-5290-a5a0-a76115c1dd8a |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checklist-sectioned |  |  | checklist | ITP - R - Excavation (Bulk and Detailed) |  |  |  |  | Yes | ITP - R - Excavation (Bulk and Detailed) | d665c164-2aa0-4ac7-9611-3e26bda44e97
checkpoint-group |  |  | section | Bulk Excavation
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Excavation depth determined using appropriate RL's (Check relevant drawings and revisions)
checkpoint-status |  |  | checkpoint | Confirm location and isolation of relevant services
checkpoint-status |  |  | checkpoint | Batters formed correctly
checkpoint-status |  |  | checkpoint | Trenches/ pits / hazardous areas appropriately isolated
checkpoint-status |  |  | checkpoint | Soft spots identified and appropriate remedial completed
checkpoint-status |  |  | checkpoint | Hardfill/ blinding installed correctly to required specification
checkpoint-status |  |  | checkpoint | Static Rolled (2 photos required)
checkpoint-status |  |  | checkpoint | Scala Test and results upload (including supporting documents)
checkpoint-status |  |  | checkpoint | Excavation completed - Correct locations and RL's achieved
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 70f69d1d-9ae2-5bb4-a2ec-bfd63bc829b0 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | 653319eb-b1bd-5686-b23f-5f5533664789 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 4b376fd3-ff2d-5a9d-bfdc-29c02aeda003 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group |  |  | section | Detailed Excavation
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Grids/profiles/set out completed, clearly marked and accurate
checkpoint-status |  |  | checkpoint | Excavation depths and locations confirmed prior to detailed excavation commencing
checkpoint-status |  |  | checkpoint | Services (overhead / below ground) considered and isolated where required before excavation commences
checkpoint-status |  |  | checkpoint | Placement of Geotextile (2 photos required)
checkpoint-status |  |  | checkpoint | Placement of hardfill
checkpoint-status |  |  | checkpoint | Placement of Geo-grid (2 photos)
checkpoint-status |  |  | checkpoint | NDM test and report (supporting documents incl. photos)
checkpoint-status |  |  | checkpoint | Completed level of hardfill (completion NDM test with report and supporting documents (incl. photos) and uploaded into QA system)
checkpoint-status |  |  | checkpoint | Sand blinding and check final RL. (completion required to handover to the next stage-townhouses only)
checkpoint-status |  |  | checkpoint | Excavation for services is completed and accurate
checkpoint-status |  |  | checkpoint | Excess material cleaned up and removed as required
checkpoint-status |  |  | checkpoint | Engineer inspection completed and approved
button | 9d658784-a89a-56cf-bc9c-8cd0cfe3fd52 |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Council inspection completed and approved
button | db2fe806-e034-5b8a-a213-1780b192a1ec |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | 5702aacb-95c7-506b-9ef2-94789ab3fef5 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)