## zres_siteapp
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ITP - R - Landscaping (per area/location) |  |  |  |  | Yes | ITP - R - Landscaping (per area/location) | df356e28-6088-425f-91dd-3e1476abb027
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Verify all dimensions, boundaries, and underground services before commencement of work
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Photograph the drawing number and revision of the drawing/s being implemented.
checkpoint-status |  |  | checkpoint | Lawn and garden beds meets landscaping layout plan dimensions
checkpoint-status |  |  | checkpoint | Lawn and planting bed areas meets landscape preparation specification
checkpoint-status |  |  | checkpoint | Plants laid out and planted as per plan
checkpoint-status |  |  | checkpoint | Trees and hedging laid out and planted as per plan
checkpoint-status |  |  | checkpoint | Root guards installed as required.
checkpoint-status |  |  | checkpoint | Irrigation system installed as per plan and working correctly
button |  |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.
checklist-flat |  |  | checklist | ITP - R - Hardscaping (per area/location) |  |  |  |  | Yes | ITP - R - Hardscaping (per area/location) | 0f5372d6-8e09-4343-8132-5c2a6bea156b
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | PASS to confirm work has started.
checkpoint-status |  |  | checkpoint | PASS to confirm expectations have been set for all contractors.
checkpoint-status |  |  | checkpoint | Photograph the drawing number and revision of the drawing being implemented.
checkpoint-status |  |  | checkpoint | Street Lighting - locations.
checkpoint-status |  |  | checkpoint | Bollard Lighting - locations.
checkpoint-status |  |  | checkpoint | Letterbox - locations.
checkpoint-status |  |  | checkpoint | Letterbox - materials and colour.
checkpoint-status |  |  | checkpoint | EV charger - location/s.
checkpoint-status |  |  | checkpoint | Main footpath/s - material and finish.
checkpoint-status |  |  | checkpoint | Main footpath/s - Pipework ducting installed prior to pour
checkpoint-status |  |  | checkpoint | Townhouse footpath/s - material and finish.
checkpoint-status |  |  | checkpoint | Main footpath/s - layouts and gradients.
checkpoint-status |  |  | checkpoint | Townhouse footpath/s - layouts and gradients.
checkpoint-status |  |  | checkpoint | Townhouse footpath/s - Pipework ducting installed prior to pour
checkpoint-status |  |  | checkpoint | All pathways - edging.
checkpoint-status |  |  | checkpoint | Raised pedestrian crossing/s - material and finish.
checkpoint-status |  |  | checkpoint | Flush pedestrian crossing/s - material and finish.
checkpoint-status |  |  | checkpoint | Paved area/s - materials, pattern, and edging.
checkpoint-status |  |  | checkpoint | Driveways - materials and finish.
checkpoint-status |  |  | checkpoint | Driveways - Pipework ducting installed prior to pour
checkpoint-status |  |  | checkpoint | Brick wall - materials and finish.
checkpoint-status |  |  | checkpoint | Brick wall - pipework ducting installed
checkpoint-status |  |  | checkpoint | Non-consented retaining wall has been built to engineers specification
checkpoint-status |  |  | checkpoint | Aluminium fencing/rails/hand rails installed - materials and finish.
checkpoint-status |  |  | checkpoint | Consultant inspection completed and passed
button |  |  | button | Note remedial work needed | None, Minor, Major
holdpoint |  |  | signoff | Raise remedial as required.