## Asphalt - Surfacing
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | B1101A - Te Ngarue Bridge |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Asphalt - Surfacing |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
Lot No: B1101A - Te Ngarue Bridge |  |  |  | Corresponding Work Instruction: |  | https://trecnz.sharepoint.com/:f:/s/ZONEB-SH2SOUTHHAWKESBAY/Ev4wrE48H99GjthARCOzmRYBgYRCbqlHsP6YVUo2EPmPWg?e=7oCCTg |  | Compliance with Work Instructions and Specifications
Detailed Location: SH2 RS 626 RP 0.009
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Milling Operations
1.1 | Survey Setout - Milling | W | Confirm site extents by checking what’s marked on the road matches the job sheet / Design Report | Prior to commencement | Visual inspection, Survey | Mark out on site, confirmed by CPS Engineer | Survey, Photos, COR | Site Engineer
1.2 | Milling Existing AC | M | Milling undertaken to correct depth of 50mm ±5mm nominal thickness | During operation | Dip checks | Design Report, depth of milling confirmed by CPS | QA Records, Photos | Site Engineer
1.3 | Waterproofing Exposed Layer | M | Exposed Basecourse waterproofed / levelled | Post milling, before asphalt | Visual Inspection |  | QA Records, Photos | Site Engineer
2 | Material Compliance
2.1 | Binder Penetration Grade | W | To comply with NZTA M01: 2020 - Table 6.1 and TNZ P11: 2007 - Table 5.2 Lab Mix | Prior to commencement | Property Test | NZTA M01: 2020 - Table 6.1 TNZ P11: 2007 - Table 5.2 Lab Mix Design Volumetric and Physical requirements | IANZ Report | Site Engineer
2.2 | Coarse Aggregate Source | W | To comply with TNZ P11: 2007 | 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009) | Property Test | 230kN minimum Crushing Resistance AA or BA Weathering Quality Index | IANZ Report | Site Engineer
2.3 | Coarse Aggregate Production | W | To comply with SPC-21711902a-PVT-PV3006-H-01 + TNZ P11:2007 and RPT-21711902a-PVT-PV310-H01 | Prior to commencement | Property Test | PSV: ≥ 58. (At least 85% by mass of minimum PSV) Table 3.13 for various sites | IANZ Report | Site Engineer
2.4 | Fine Aggregate Source | W | To comply with TNZ P11: 2007 | 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009) | Property Test | 130kN minimum Crushing Resistance | IANZ Report | Site Engineer
2.5 | Blended Coarse Aggregate Production | W | To comply with TNZ P11: 2007 | 1/500m³ (Section6 of RNZ 9805:2009) | Property Test | 2.25 Max Particle Shape 98% Broken Faces Report Value-5 minimum Cleanness Value | IANZ Report | Site Engineer
2.6 | Asphalt Mix Design | W | Mix Design approved including peer review to comply with TNZ P11: 2007 | 10 days minimum prior to paving | Lab Testing | TNZ P11: 2007 Table 5.1 Mix Envelop & 5.2 Lab Mix Design Volumetric and Physical requirements | IANZ Report, Mix Design | Site Engineer
3 | Construction
3.1 | Survey Setout - Paving | W | Determine paving run start/stop locations | Prior to commencement | Survey, Visual Inspection | Ensure accurate survey setting out is in place. | Survey Record | Site Engineer
3.2 | Weather Check | W | Ensure weather conditions are acceptable for work to proceed | Prior to commencement | Weather Forecast | Not foggy or raining or wet surface. Base Temp ≥ 7ºC (25 – 75mm layers) | Forecast Records, QA Records | Site Engineer
3.3 | Surface Preparation | W | Ensure previous layer is broomed clean. | Prior to commencement | Visual inspection | Truck broom to have been used and surface approved by CPS Engineer | QA Records, COR | Site Engineer
3.4 | Tack Coat | W | Apply tack coat | Prior to asphalt | Spray sheet, QA records | TNZ M/10 2020 - Section 9.3.1 | Spray sheet, QA records | Site Engineer
3.5 | Production Property Test - Grading | W | To comply with SPC-2171902a-PVT-PV3006-H-01 | 1/>30mimutes production run and 2/>5 hours production run | Property Test | Approved JMF + Table 7.1 - Mix Control Tolerance Note: ±0.4% rolling ave of four | IANZ Report, QA Records | Site Engineer
3.6 | Production Property Test - Binder Content | W | To comply with SPC-2171902a-PVT-PV3006-H-01 | 1/>30mimutes production run and 2/>5 hours production run | Property Test | Approved JMF + Table 7.1 - Mix Control Tolerance Note: ±0.4% rolling ave of four | IANZ Report, QA Records | Site Engineer
3.7 | Production Property Test - Maximum Specific Gravity | W | To comply with TNZ TM6002:2006 | 1/>30mimutes production run and 2/>5 hours production run | Property Test | TNZ TM6002:2006 Report Value | IANZ Report, QA Records | Site Engineer
3.8 | Production Property Test - Avg Temperature | W | Check temperature of Asphalt for every truck entering the paver. | Any truck load | Temperature Check | TNZ P11: 2007 ±10 oC from recommended mixing temperature | IANZ Report, QA Records | Site Engineer
3.9 | Asphalt Construction - Layer Thickness | M | Ensure asphalt is laid at correct thickness of 50mm to comply with SPC-2171902a-PVT-PV3006-H-01. | During paving operation | Survey | ±5mm nominal thickness as shown in the Drawings, Plans and/or Specifications | IANZ Report, QA Records | Site Engineer
3.1 | Asphalt Construction - Surface Shape | M | Ensure asphalt is laid to correct shape to comply with SPC-2171902a-PVT-PV3006-H-01. | During paving operation | 5m straight edge | SPC-2171902a-PVT-PV3006-H-01. ≤5mm (Visual Inspection) | QA Records | Site Engineer
3.11 | Asphalt Construction - Surface Texture | M | To comply with NZTA M10: 2023 | Every 10 metres | Laser Profilometer | NZTA M10: 2023 Table 3 | IANZ Report, QA Records | Site Engineer
3.12 | Asphalt Construction - Compaction | W | To comply with NZTA M10: 2023 | One test per 50m2 | NDM for Quality Control Only | NZTA M/10: 2020 - section 9.9.3 | IANZ Report, QA Records | Site Engineer
3.13 | Ride quality | M | Upon 100% completion of OGPA layer and at expiry of defects liability period | Prior to Opening to Traffic | NAASRA | 10. Appendices to Principal's Requirement: 50 NAASRA count as a 95%tile for every 100m rolling section | IANZ Report, QA Records | Site Engineer
3.14 | Surface finish visual inspection | H | Site walk over | Post Construction | Visual Inspection | No visible cracks, No obvious defect related to poorly constructed joins, No areas where water can pool; No part of all pavement surfaces deviate more than 5mm from a 2m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline. | QA Records, COR | Site Engineer | CPS Engineer
4 | Post-Construction Closeout
4.1 | Final Walkover (Snags) | H | The final walkover must be scheduled at least one week before the site's completion or demobilisation. | At the completion of the Lot of work | Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out) | Completed report | Snag List signed by attendees | Site Engineer | CPS Engineer
4.2 | Survey As-builts | H | Red pen mark-up drawings are to be included in the QA file. A survey as-built of completed work must be provided | At the completion of the CWP of work | Drawings Survey as-built | All RFI, NCRs and site changes must be recorded. Signed and dated | As-built Drawings. Redline Markups | Quality Manager
4.3 | Quality Assurance Deliverables | W | Redline mark-up drawings are to be reviewed and accepted by CPS. All NCRs and RFIs are closed and included with the Handover QA file. | At the completion of the CWP | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Quality Manager
4.4 | Final Approvals | H | Signoffs by Project Manager, Quality Manager and CPS Manager | At the completion of the CWP | Document Review | Ensure all parties have signed and approved ITP | Signatures | Project Manager, Quality Manager, CPS Manager