## Master Captain's Culvert
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | B1401A - Captain's Culvert Inlet Remediation |  | CPS Approver | Quality Approver | CPS Eng. | David Hooker
|  |  |  | Procedure: | Master ITP |  | Name / Signature | Name / Signature | Engineer | Josin Francis
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng. | Dharminder Singh
Lot No: B1401A |  |  |  | Corresponding Work Instruction: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location: SH 05 RS220 RP 3.3
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Debris Clearance | H | Need to inspected by the engineer to determine whether rip rap reinforcing is required around the inlet. | After clearing debris | Visual inspection | Confirmation from the Engineer | Site visits,emails | Site Engineer | CPS Engineer
2 | Stream and Bank Regrade | H | Location and extent of bund is to be confirmed on-site with the engineer. | After clearing debris | Visual inspection | Confirmation from the Engineer | Site visits,Photos emails | Site Engineer | CPS Engineer
3 | Stream training | H | Stream training is required at the mouth of the gorge with the extent to be confirmed onsite with the engineer. | After clearing debris | Visual inspection | Confirmation from the Engineer | Site visits,emails | Site Engineer | CPS Engineer
4 | Gabion basket installation |  | separate ITP provided
5 | Rock Armourt installation |  | separate ITP provided
6 | Subsoil Drain |  | separate ITP provided
7 | Parking bay construction |  | separate ITP provided
8 | Kerb and Channel |  | separate ITP provided
9 | GuardRail |  | separate ITP provided
10 | Swale Inspection | H | The Engineer needs to inspect and adjust the transition and swale if needed. | Once the swale is set out. | Visual inspection | Engineer acceptance | Site visits, emails | Site Engineer | CPS Engineer
11 | Berm Demolising | H | Final inspection to be done before berm demolision | Before Diverting back the River | Visual inspection | Engineer acceptance | Site visits, emails | Site Engineer | CPS Engineer
12 | Planting Process | H | The Engineer shall be notified of any key stages throughout the planting process and afforded the opportunity to inspect and adjust as necessary. | During planting | Visual inspection | Engineer acceptance | Site visits, emails | Site Engineer | CPS Engineer
Post-Construction Closeout
13 | Final Walkover (Snags) | H | The final walkover must be scheduled at least one week before the site's completion or demobilisation. | At the completion of the Lot of work | Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out) | Completed report | Snag List signed by attendees | Quality
14 | Survey As-builts | H | Red pen mark-up drawings are to be included in the QA file. A survey as-built of completed work must be provided | At the completion of the CWP of work | Drawings Survey as-built | All RFI, NCRs and site changes must be recorded. Signed and dated | As-built Drawings. Redline Markups | Site Engineer
15 | Quality Assurance Deliverables | W | Redline mark-up drawings are to be reviewed and accepted by CPS. All NCRs and RFIs are closed and included with the Handover QA file. | At the completion of the CWP | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer