## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP - B1101A - Te Ngarue Bridge - Scours Asphalt | itp |  |  |  | Yes | ITP - B1101A - Te Ngarue Bridge - Scours Asphalt | 0d04d2e0-3ff5-4777-b70f-a37f59f54c15
checkpoint-group |  |  | section | 1 - Milling Operations
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 09847663-c7ce-550d-aa98-915a297dea66 |  | textbox | CPS Eng.
text | c98707ff-ff0d-50c4-933a-def70ee9f98f |  | textbox | Site Engineer
text | 6f381376-03f4-5f3e-afa4-2b31c1a0409c |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Survey Setout - Milling
label | 8a7c79a5-54e2-5e0f-a89e-50ebc0da92f6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8ffb1962-c0f3-59ff-bea4-1044bb714c06 |  | note | Detail - Confirm site extents by checking what’s marked on the road matches the job sheet / Design Report
label | 4fdb9593-e254-5efb-82a8-122988265e0c |  | note | Frequency - Prior to commencement
label | d80184c7-a931-5978-bdb5-e991654a535a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, Survey
label | 8d3585c0-54ad-5f99-a02c-b0f6e234657a |  | note | Conformance Criteria - Mark out on site, confirmed by CPS Engineer
label | 3d797218-ec2c-5885-b7ef-7ea7531bf6c1 |  | note | Records - Survey, Photos, COR
checkpoint-status |  |  | checkpoint | 1.2 - Milling Existing AC
label | 4dc67849-b8a1-5b65-bc5e-54f8aaeac922 |  | note | ACTION (Hold, Monitor, Witness) - M
label | b51d0aab-aa44-5dc4-9af2-25031329b373 |  | note | Detail - Milling undertaken to correct depth of 50mm ±5mm nominal thickness
label | ea25c596-38b4-57b3-8f8a-cf17d8b68f11 |  | note | Frequency - During operation
label | 02d59097-f7cd-58c8-9d09-9cc7334a8601 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Dip checks
label | dd200693-df6d-5e07-8c09-25fa8fb7ecfe |  | note | Conformance Criteria - Design Report, depth of milling confirmed by CPS
label | 0c35b98f-6820-514a-bd59-86d6928e7838 |  | note | Records - QA Records, Photos
checkpoint-status |  |  | checkpoint | 1.3 - Waterproofing Exposed Layer
label | 039256cb-f33e-54cc-a77f-606b4bad7bac |  | note | ACTION (Hold, Monitor, Witness) - M
label | f8c3518f-cbe8-5aa9-a10c-d48dd6d5f98f |  | note | Detail - Exposed Basecourse waterproofed / levelled
label | d8a9ecac-d131-5894-a9ce-aa111d36e463 |  | note | Frequency - Post milling, before asphalt
label | 76395e77-537d-58bd-b258-10b4e91215d9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 2d5faa86-2eb1-541b-85e8-2282c54fec88 |  | note | Conformance Criteria -
label | 8ba4302e-0d01-5735-92b2-454be6fef092 |  | note | Records - QA Records, Photos
checkpoint-group |  |  | section | 2 - Material Compliance
checkpoint-status |  |  | checkpoint | 2.1 - Binder Penetration Grade
label | 5aa3e481-84bd-592c-ba00-1b944b5622a2 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ea5ea0ac-e4a5-5369-9b92-ea4d44a251c3 |  | note | Detail - To comply with NZTA M01: 2020 - Table 6.1 and TNZ P11: 2007 - Table 5.2 Lab Mix
label | d12bbd47-e97e-568c-be51-8920f9d6d9a2 |  | note | Frequency - Prior to commencement
label | 5e92a0d7-19d8-5f3c-b42d-31663e067f48 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | 14b1ded4-c378-586f-8d42-0fbc99471c56 |  | note | Conformance Criteria - NZTA M01: 2020 - Table 6.1 TNZ P11: 2007 - Table 5.2 Lab Mix Design Volumetric and Physical requirements
label | 21c96e78-fd28-510e-89a0-058061c93a33 |  | note | Records - IANZ Report
checkpoint-status |  |  | checkpoint | 2.2 - Coarse Aggregate Source
label | 77d9a518-4e51-55f4-b752-39b99dbb72f1 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0c2c20bf-a395-560d-aab6-0db8b8f3d016 |  | note | Detail - To comply with TNZ P11: 2007
label | 8bb7e16c-45e9-5adb-b42b-232d8915c114 |  | note | Frequency - 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009)
label | 876a5cc3-809a-58f3-8999-5ab4d350ac32 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | 88fe4985-4c75-5c1a-af51-d584abd9c05c |  | note | Conformance Criteria - 230kN minimum Crushing Resistance, AA or BA Weathering Quality Index
label | 277234d7-d7c3-543e-95c0-09e0e4fae9b5 |  | note | Records - IANZ Report
checkpoint-status |  |  | checkpoint | 2.3 - Coarse Aggregate Production
label | 32e4718e-2ca3-5a51-ba72-ce315d459553 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d073c1f3-abe9-538a-9ade-2f8f8c12bd59 |  | note | Detail - To comply with SPC-21711902a-PVT-PV3006-H-01 + TNZ P11:2007 and RPT-21711902a-PVT-PV310-H01
label | 89760bec-b341-5210-b1ab-41dd1c331f2c |  | note | Frequency - Prior to commencement
label | d63a7974-8670-58da-b222-8183a46c2bd7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | af7c9e60-9692-5588-af5a-56f80baf0868 |  | note | Conformance Criteria - PSV: ≥ 58. (At least 85% by mass of minimum PSV) Table 3.13 for various sites
label | 354409f5-6d3c-5b11-8bb3-68227fc468a6 |  | note | Records - IANZ Report
checkpoint-status |  |  | checkpoint | 2.4 - Fine Aggregate Source
label | 0e99430c-be38-5b5c-95b5-3f1853e8d410 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 57515e84-bec6-5fd7-bd91-23eab047e8e7 |  | note | Detail - To comply with TNZ P11: 2007
label | bea7d6cb-fc75-56fa-9bb2-9662e1daeac5 |  | note | Frequency - 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009)
label | 59af343b-5c2b-5bba-a6ee-8a58150d9f1a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | a6673a07-edcd-5f04-a743-e80b45b713a0 |  | note | Conformance Criteria - 130kN minimum Crushing Resistance
label | 221522fd-3edc-502f-a4e9-ba3d7f9e2fb7 |  | note | Records - IANZ Report
checkpoint-status |  |  | checkpoint | 2.5 - Blended Coarse Aggregate Production
label | b453b16b-8f9f-5837-b2be-3c9ce670a20d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9db91e05-3e9c-5a3b-9330-2e5a93e148d9 |  | note | Detail - To comply with TNZ P11: 2007
label | ef4d5b3f-7801-5250-83ed-b32d885acb41 |  | note | Frequency - 1/500m³ (Section6 of RNZ 9805:2009)
label | e05ed9cd-1dac-5438-aaa0-183867640e34 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | 689f9682-88f8-557a-9dda-c696defeac6a |  | note | Conformance Criteria - 2.25 Max Particle Shape
label | cd3e9658-6798-596d-af4a-9d53f969e0e3 |  | note | ○ 98% Broken Faces
label | 3887d104-f285-5a8b-93a3-c300f94e8743 |  | note | ○ Report Value - 5 minimum Cleanness Value
label | 13661301-2f5b-5c6b-900e-2452bfdc29e4 |  | note | Records - IANZ Report
checkpoint-status |  |  | checkpoint | 2.6 - Asphalt Mix Design
label | d75aa424-d085-5ae6-90c6-d73c044d1ec0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | fc7ca3c4-bd18-54c9-9310-18723992137f |  | note | Detail - Mix Design approved including peer review to comply with TNZ P11: 2007
label | ff2b588b-f229-57f5-b8e7-3400009a07b3 |  | note | Frequency - 10 days minimum prior to paving
label | c2659c6a-7e5e-58af-8a65-3486c32876b4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 9047101d-c58b-5701-a04b-506067af0458 |  | note | Conformance Criteria - TNZ P11: 2007 Table 5.1 Mix Envelop & 5.2 Lab Mix Design Volumetric and Physical requirements
label | f070fe00-1eda-53df-b073-27c30a861061 |  | note | Records - IANZ Report, Mix Design
checkpoint-group |  |  | section | 3 - Construction
checkpoint-status |  |  | checkpoint | 3.1 - Survey Setout - Paving
label | c7ee423e-e9f6-5f32-b18c-183b993bc79a |  | note | ACTION (Hold, Monitor, Witness) - W
label | d048bb33-fdf6-5d05-8e39-3ed3c94d4214 |  | note | Detail - Determine paving run start/stop locations
label | 38014465-bc27-52d5-b591-adad74ffcf7b |  | note | Frequency - Prior to commencement
label | 9081a92c-89cc-58bc-8d26-2984d07fae0b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Visual Inspection
label | 9aec2b6f-1a3a-597e-9dca-e112c90b4477 |  | note | Conformance Criteria - Ensure accurate survey setting out is in place.
label | 9281ffe8-3e6a-510a-959d-ed825e9a9afd |  | note | Records - Survey Record
checkpoint-status |  |  | checkpoint | 3.2 - Weather Check
label | 7b509b82-c3df-5430-8602-de7763a80d45 |  | note | ACTION (Hold, Monitor, Witness) - W
label | eca038b6-61d4-56e5-a4d7-bbaf562ab0e6 |  | note | Detail - Ensure weather conditions are acceptable for work to proceed
label | fc2ed29f-0bbe-5d72-bd85-6ced7ebd93dc |  | note | Frequency - Prior to commencement
label | efb6aedd-b033-5bf1-84fa-c775a0ba17a6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Weather Forecast
label | d0dd1508-c956-50fc-8fd9-6bef159aa6f1 |  | note | Conformance Criteria - Not foggy or raining or wet surface. Base Temp ≥ 7ºC (25 – 75mm layers)
label | 0e491b82-b99a-5df4-9670-ce8df7ff76fd |  | note | Records - Forecast Records, QA Records
checkpoint-status |  |  | checkpoint | 3.3 - Surface Preparation
label | f8839a99-e277-548c-847f-547fbb084818 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4e9c65ae-94c4-5376-a112-0e8f6ec4bd34 |  | note | Detail - Ensure previous layer is broomed clean.
label | 3b8f844e-479d-5e75-ae4f-b3d69e0f0d1c |  | note | Frequency - Prior to commencement
label | 08b850fb-343f-5ecb-8f66-85ec31c55820 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 6548f8c4-c3a2-5f12-af89-8afeee21c140 |  | note | Conformance Criteria - Truck broom to have been used and surface approved by CPS Engineer
label | d94a0a6f-b5fd-5450-b754-27575a915d62 |  | note | Records - QA Records, COR
checkpoint-status |  |  | checkpoint | 3.4 - Tack Coat
label | 61e99cce-bbed-5713-b59e-556837dddaf0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | de96aae3-fa74-5321-b644-152adf7f0cc6 |  | note | Detail - Apply tack coat
label | f1e82e9c-9921-5fc0-987b-a3e4b94f61c1 |  | note | Frequency - Prior to asphalt
label | 65c166ff-da05-5192-a3be-d745c0bd3b09 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Spray sheet, QA records
label | dfdfa26e-31c2-5362-a2cd-01b22ab5fef2 |  | note | Conformance Criteria - TNZ M/10 2020 - Section 9.3.1
label | fdd832de-a714-5dc5-a3eb-86e8a3680632 |  | note | Records - Spray sheet, QA records
checkpoint-status |  |  | checkpoint | 3.5 - Production Property Test - Grading
label | 460b1db4-451c-52d0-a8d5-64c6598c86ea |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3b47d7c4-1ab0-5743-97a0-bad139d2db17 |  | note | Detail - To comply with SPC-2171902a-PVT-PV3006-H-01
label | 5ed5061c-9a5c-574d-ad1a-7cee4ee59e11 |  | note | Frequency - 1/>30mimutes production run and 2/>5 hours production run
label | 69188654-6cdf-5801-b103-4e91f57b3c0c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | 40405b4f-f7c8-5799-9c04-9b8ae7bdd815 |  | note | Conformance Criteria - Approved JMF + Table 7.1 - Mix Control Tolerance Note: ±0.4% rolling ave of four
label | d927f8d2-c27b-5d38-949f-f95d2d247769 |  | note | Records - IANZ Report, QA Records
checkpoint-status |  |  | checkpoint | 3.6 - Production Property Test - Binder Content
label | 1b217baf-8640-5742-921b-1c62f796a86a |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9315ba01-b05b-5934-9195-294fa842c24a |  | note | Detail - To comply with SPC-2171902a-PVT-PV3006-H-01
label | 7785ef8b-c4be-58e6-bd82-3ccd5f785a51 |  | note | Frequency - 1/>30mimutes production run and 2/>5 hours production run
label | 01fc5ef8-7080-5254-9cd7-4c105a763d6e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | 93a201a6-5879-5ecb-a0c9-73fdf47c6611 |  | note | Conformance Criteria - Approved JMF + Table 7.1 - Mix Control Tolerance Note: ±0.4% rolling ave of four
label | 772cb7a2-982e-584a-9cae-d20a142abbdf |  | note | Records - IANZ Report, QA Records
checkpoint-status |  |  | checkpoint | 3.7 - Production Property Test - Maximum Specific Gravity
label | 9f4aff70-cb52-549f-b15c-729c99910425 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 09a98b0c-d2d0-5a6c-9d32-38932ae6ca70 |  | note | Detail - To comply with TNZ TM6002:2006
label | f7041634-f276-57bb-9336-7dd37bf3e112 |  | note | Frequency - 1/>30mimutes production run and 2/>5 hours production run
label | b69e76b1-a03f-53c0-a0a5-ba95fe060831 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | 6c26b0d8-a29a-5697-b2b5-39e220600720 |  | note | Conformance Criteria - TNZ TM6002:2006 Report Value
label | 3e0a5524-83d2-5e17-8e02-2ed048084278 |  | note | Records - IANZ Report, QA Records
checkpoint-status |  |  | checkpoint | 3.8 - Production Property Test - Avg Temperature
label | 7285886a-23c7-5b06-8019-341f7d9f2549 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 071cf91d-0303-599f-8614-2eea761c2604 |  | note | Detail - Check temperature of Asphalt for every truck entering the paver.
label | ad454e0f-28d1-58e8-ae3b-084911c8619f |  | note | Frequency - Any truck load
label | 482f5eb4-6cb6-5017-9ae6-593105364fd1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Temperature Check
label | f1624867-e727-57f1-9ca8-bc089b67f30e |  | note | Conformance Criteria - TNZ P11: 2007
label | ecb1893f-5395-5832-9697-820727c0a134 |  | note | ○ ±10 oC from recommended mixing temperature
label | dbc24c32-dd06-5fee-9497-482c322b1588 |  | note | Records - IANZ Report, QA Records
checkpoint-status |  |  | checkpoint | 3.9 - Asphalt Construction - Layer Thickness
label | 6cfaba1f-3e66-555f-81ce-0e2fc6792d5b |  | note | ACTION (Hold, Monitor, Witness) - M
label | 585f5061-23e6-51cb-bca4-0b20dafd395d |  | note | Detail - Ensure asphalt is laid at correct thickness of 50mm to comply with SPC-2171902a-PVT-PV3006-H-01.
label | 45dac390-6fe2-553b-ac9b-8269f239aad8 |  | note | Frequency - During paving operation
label | 81e6e95a-984a-574b-849f-3504a363d89f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 70f7684d-2449-52e2-9cda-4b27a63954bc |  | note | Conformance Criteria - ±5mm nominal thickness as shown in the Drawings, Plans and/or Specifications
label | b3f69ae2-8794-5ce5-8765-ac832f2fc42a |  | note | Records - IANZ Report, QA Records
checkpoint-status |  |  | checkpoint | 3.1 - Asphalt Construction - Surface Shape
label | 1e4be2b2-893c-56e7-9614-72c8febcd205 |  | note | ACTION (Hold, Monitor, Witness) - M
label | cea514f0-ba0a-5a12-ac4a-ff1c545dd3ed |  | note | Detail - Ensure asphalt is laid to correct shape to comply with SPC-2171902a-PVT-PV3006-H-01.
label | 2ab70f32-be8d-5b54-b588-66479e6a9217 |  | note | Frequency - During paving operation
label | 546ad15e-ca84-5a41-a134-3b42d0a2793e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - 5m straight edge
label | 09c0133d-5215-5d74-ab8c-bf4668ee3d50 |  | note | Conformance Criteria - SPC-2171902a-PVT-PV3006-H-01.
label | 9b20401c-7f25-5d12-bc7d-aa26c24e0c22 |  | note | ○ ≤5mm (Visual Inspection)
label | 54f3d20b-c13a-5a2b-8f46-f4c90e4106f8 |  | note | Records - QA Records
checkpoint-status |  |  | checkpoint | 3.11 - Asphalt Construction - Surface Texture
label | 8ad24679-0c9c-5e0f-9d09-d1034ce5df3b |  | note | ACTION (Hold, Monitor, Witness) - M
label | a3279356-20ae-54f5-abd5-cbd4114c181d |  | note | Detail - To comply with NZTA M10: 2023
label | fe225e84-b5e9-58a2-8da9-3f93e84440b2 |  | note | Frequency - Every 10 metres
label | 031bf56b-4f26-5ba8-af09-4a2ce482aace |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Laser Profilometer
label | ea40e03e-8111-5aa2-9534-1a41850f0d58 |  | note | Conformance Criteria - NZTA M10: 2023 Table 3
label | 4e2d037e-57a1-5ab4-b01e-6cd696e847f8 |  | note | Records - IANZ Report, QA Records
checkpoint-status |  |  | checkpoint | 3.12 - Asphalt Construction - Compaction
label | 9c3cbf70-c9f4-5fca-aff2-e0f663181a94 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a0c28b5a-6321-5940-9113-395c06e3841e |  | note | Detail - To comply with NZTA M10: 2023
label | 1cbbd1be-4191-56ae-9f3b-62035bbf9580 |  | note | Frequency - One test per 50m2
label | 1d012bbb-6c57-58c6-97ce-731d2bcb9b55 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM for Quality Control Only
label | 49aa3f1f-f1c4-5ee9-b4d6-8db005a3e3a3 |  | note | Conformance Criteria - NZTA M/10: 2020 - section 9.9.3
label | b32916b0-aa67-5421-a675-62a7288764e1 |  | note | Records - IANZ Report, QA Records
checkpoint-status |  |  | checkpoint | 3.13 - Ride quality
label | 4c56552a-b278-5bf6-ac67-3d89353d8886 |  | note | ACTION (Hold, Monitor, Witness) - M
label | df688d69-3d61-55a2-8a07-5f0b68fe0038 |  | note | Detail - Upon 100% completion of OGPA layer and at expiry of defects liability period
label | a0020189-3bd1-5874-99c4-0c5c3a733952 |  | note | Frequency - Prior to Opening to Traffic
label | acfabbe7-930e-5123-b8a0-5547a8ca41b1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NAASRA
label | 61e7df59-39e5-5267-954b-7051e4659e86 |  | note | Conformance Criteria - 10. Appendices to Principal's Requirement: 50 NAASRA count as a 95%tile for every 100m rolling section
label | efd6a033-fb1d-5300-af67-de15267f4fbf |  | note | Records - IANZ Report, QA Records
checkpoint-status |  |  | checkpoint | 3.14 - Surface finish visual inspection
label | 275baf9c-ba1c-58ea-9782-b31e6ab8fc72 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 76ac8f13-0a6c-555a-b4dc-b97c0b80f10a |  | note | Detail - Site walk over
label | 00b0b2cc-fdde-5d88-b5df-6abc93dcb144 |  | note | Frequency - Post Construction
label | 841ab86d-af8b-5e57-952a-56ad7440fa92 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | bd6ca1c9-d1e9-51fa-a621-4b0d0d42e874 |  | note | Conformance Criteria - No visible cracks, No obvious defect related to poorly constructed joins, No areas where water can pool; No part of all pavement surfaces deviate more than 5mm from a 2m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline.
label | 4c8626cc-52a1-5dc3-ad27-d5be7f89754c |  | note | Records - QA Records, COR
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4 - Post-Construction Closeout
checkpoint-status |  |  | checkpoint | 4.1 - Final Walkover (Snags)
label | c9fb9d67-ed81-5ed4-b221-a9fb396f8b71 |  | note | ACTION (Hold, Monitor, Witness) - H
label | df72ad0b-a682-5c8a-ad64-e59f77f521a0 |  | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | f77a8488-2e2c-5789-9d7d-ea718c4ee5cf |  | note | Frequency - At the completion of the Lot of work
label | 47f0a676-274d-5552-a003-dd7caf8af0a2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | 14dd018f-d376-53a6-9fea-ab165ef2b0e1 |  | note | Conformance Criteria - Completed report
label | 1d430b0b-f558-51c1-96ae-4bc039c62156 |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Survey As-builts
label | 892ca46f-8eae-540e-8bdd-1a144e23129e |  | note | ACTION (Hold, Monitor, Witness) - H
label | fe301b49-c8ec-51ee-a30d-c6a3018e6bd2 |  | note | Detail - Red pen mark-up drawings are to be included in the QA file.
label | 0e111037-d804-5a11-a283-6c256202e9da |  | note | ○ A survey as-built of completed work must be provided
label | 6e615034-34df-54fb-b6bc-86d9bf83d4f0 |  | note | Frequency - At the completion of the CWP of work
label | 1747552d-a5c9-54b4-9584-4ae1a00ccc21 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | 86fc6063-ebe4-5a9d-b40c-98078203d58a |  | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | e281ea92-70c8-524d-b5cd-8ae6f8bc2d1a |  | note | Records - As-built Drawings. Redline Markups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - Quality Assurance Deliverables
label | 502b8a9c-d2fe-5102-adc6-3cf1adb98691 |  | note | ACTION (Hold, Monitor, Witness) - W
label | f5835484-1943-59a5-82aa-9fd5e7d135cd |  | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | 7b84dfe1-fded-57a8-ac56-2eebb67f908b |  | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | fd74244b-b5c5-56e1-9990-fc4b81ff3c93 |  | note | Frequency - At the completion of the CWP
label | 35417a3c-39f2-57db-8fed-d59b4fd6cf71 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 35185a1c-995d-51ad-a0e7-c11a9d331cf4 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | d97d1df7-263c-5d1f-b3b2-7a575914ebde |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 4.4 - Final Approvals
label | d1e93a99-0ffb-5bc8-acc6-6829e48a6872 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 28e41e73-2310-57b7-b3b3-d469a6d060ad |  | note | Detail - Signoffs by Project Manager, Quality Manager and CPS Manager
label | 211dcfba-4e22-5804-9254-d36f4d7f509c |  | note | Frequency - At the completion of the CWP
label | d772f37d-07d0-50bb-b465-6af7182dd533 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 2ed54d51-0bc2-5b90-85ae-5592662976cf |  | note | Conformance Criteria - Ensure all parties have signed and approved ITP
label | 42446ec0-d601-5d93-8a77-55642f34c129 |  | note | Records - Signatures
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - E1401A - Captain's Culvert Inlet Remediation - Master ITP | itp |  |  |  | Yes | ITP - E1401A - Captain's Culvert Inlet Remediation - Master ITP V2 | 0fb9dcb8-e398-4018-a935-65ebe47e4c8d
checkpoint-group |  |  | section | Master ITP
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 45a7ccc8-e61d-549f-8435-0bea0ee8046a |  | textbox | CPS Eng.
text | a13a82e2-0df4-5be7-bee5-d69fd66c5ed6 |  | textbox | Engineer
text | c40e70d9-166d-5e14-825f-753d2c701b14 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Debris Clearance
label | 34a13748-e9dd-5aec-8529-a7af52c5958c |  | note | ACTION (Hold, Monitor, Witness) - H
label | b0cac6cb-db32-5c11-9c04-1d4d87147de2 |  | note | Detail - Need to inspected by the engineer to determine whether rip rap reinforcing is required around the inlet.
label | 53d2a460-a098-571a-9018-319a9fe8b356 |  | note | Frequency - After clearing debris
label | e17b2271-9c8f-5568-a32d-e0194d7cfb33 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 0065ae33-7499-591b-9ad1-ea14aafadabe |  | note | Conformance Criteria - Confirmation from the Engineer
label | f9e9b8ea-3244-5bfe-87aa-4cc9077c4b0f |  | note | Records - Site visits, emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Stream and Bank Regrade
label | 3db1529c-5502-53c7-89ca-4b8593b40c74 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ceaf7680-c884-5f9d-9712-07fa4ae8da5f |  | note | Detail - Location and extent of bund is to be confirmed on-site with the engineer.
label | 91f55be9-565b-5e2b-a4cb-71b3b192b7a9 |  | note | Frequency - After clearing debris
label | a4b29d48-debf-5806-a3ae-cd555777f84c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 1dd1de15-2bd9-50f4-be1c-6315b95a4f61 |  | note | Conformance Criteria - Confirmation from the Engineer
label | e76f5034-3e14-5c26-874e-3568bb414d3f |  | note | Records - Site visits,Photos emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Stream training
label | ad3be08b-f60f-5d73-8c25-831576cf9f00 |  | note | ACTION (Hold, Monitor, Witness) - H
label | e09c1d36-cdc7-5374-90a7-7a00a6458f68 |  | note | Detail - Stream training is required at the mouth of the gorge with the extent to be confirmed onsite with the engineer.
label | 24011bd8-ac24-579e-9f11-299401e9fa11 |  | note | Frequency - After clearing debris
label | f00a3093-db58-5a2c-a070-7860fd62523c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 2d278b0b-50e2-5944-aa25-0a20bc4bd2e0 |  | note | Conformance Criteria - Confirmation from the Engineer
label | d1e511f1-c589-5627-91bf-42d6aacd3ea1 |  | note | Records - Site visits, emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Gabion basket installation
label | f3306661-b424-5bc0-a9f5-26859b912fc7 |  | note | ACTION (Hold, Monitor, Witness) -
label | 4322dedb-e00f-5081-b746-53dafa4fba06 |  | note | Detail - separate ITP provided
label | 8dfeec16-2c05-5cec-ac6c-0cfd8ae47012 |  | note | Frequency -
label | 8dfc4d70-0f77-51f2-98bd-371de36c2a78 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review -
label | 13d545da-5c39-5fbb-b4a1-b24b5cda390f |  | note | Conformance Criteria -
label | d51cb77f-eeaa-59d1-886a-5bb1c3a8ce54 |  | note | Records -
checkpoint-status |  |  | checkpoint | 5 - Rock Armourt installation
label | 8f9b3a8f-1b95-5744-870d-3d0891788598 |  | note | ACTION (Hold, Monitor, Witness) -
label | 5cfd2908-c6b3-5c66-9918-9febcddab383 |  | note | Detail - separate ITP provided
label | 69fcd58f-0aa4-5e51-811c-f0a6217f0c7e |  | note | Frequency -
label | 8d74b5a5-84e5-5c09-9b8c-2da113568787 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review -
label | e744d34d-b824-5a97-b378-d3c4fe327ff1 |  | note | Conformance Criteria -
label | d11308c6-4a15-593d-8278-3a5362c66e05 |  | note | Records -
checkpoint-status |  |  | checkpoint | 6 - Subsoil Drain
label | dbce5a0c-8afb-5ec4-9cc0-9e73b64b20b8 |  | note | ACTION (Hold, Monitor, Witness) -
label | f086a508-53c0-569c-a844-1ae6550120cf |  | note | Detail - separate ITP provided
label | 8d3b951e-3093-50ae-b1b7-9521c4cfe67b |  | note | Frequency -
label | 834e62f6-8567-5d65-a133-bbb27ae0996c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review -
label | 773af2ca-74cc-55d9-aa13-2d19b6927962 |  | note | Conformance Criteria -
label | f588f401-3bbe-5d22-8bf6-e3e8ae629b3d |  | note | Records -
checkpoint-status |  |  | checkpoint | 7 - Parking bay construction
label | e9a88361-1958-5b9b-aee2-7da9756c7f6c |  | note | ACTION (Hold, Monitor, Witness) -
label | 2d48dcce-af3d-5dc0-9ae6-220724e56ccd |  | note | Detail - separate ITP provided
label | eae8a39c-8eb7-5bf0-8e2b-209a79231a42 |  | note | Frequency -
label | a8010d11-9a07-5945-af4a-3364d70fbcc7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review -
label | 9c90cd21-674d-5dcf-8509-9e015fe623e8 |  | note | Conformance Criteria -
label | 1849c986-8d46-5dc4-a8f0-4823de2b47fb |  | note | Records -
checkpoint-status |  |  | checkpoint | 8 - Kerb and Channel
label | c919f4eb-1865-52d7-ac18-c43bac6d60ff |  | note | ACTION (Hold, Monitor, Witness) -
label | ab6a7419-90ff-5f08-a0c5-0b4b3b3514da |  | note | Detail - separate ITP provided
label | 047b0d76-826a-5f88-9c11-31b311ba5df1 |  | note | Frequency -
label | f7be5fe0-7516-56d3-9c74-82a7137114c2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review -
label | f7857ebf-34f6-5f78-989b-71a572f041f6 |  | note | Conformance Criteria -
label | f12b247d-fec9-5632-8f80-b0eec7ed40ad |  | note | Records -
checkpoint-status |  |  | checkpoint | 9 - GuardRail
label | 491578a8-d276-5757-9b71-f2e08c266ea8 |  | note | ACTION (Hold, Monitor, Witness) -
label | b42ff3ce-92f2-516d-8e28-fda0423d2bc0 |  | note | Detail - separate ITP provided
label | e6a32fa4-8156-5337-874c-67d2de2fe214 |  | note | Frequency -
label | bda2f8d0-0c58-58b2-9a75-d9bc8d8aa459 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review -
label | 2f53dc5d-55fc-5e59-a342-d6fac4a4f33c |  | note | Conformance Criteria -
label | 56199acb-f451-5149-9f19-68d9deb08d6c |  | note | Records -
checkpoint-status |  |  | checkpoint | 10 - Swale Inspection
label | 58427056-b1c9-53cc-8252-fc3ac1322b25 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2c85c73d-40a6-5b9e-ba14-6fe08f888c5d |  | note | Detail - The Engineer needs to inspect and adjust the transition and swale if needed.
label | 3b969a28-2e3a-5c6f-97df-d8e398f18ae8 |  | note | Frequency - Once the swale is set out.
label | 96b02e05-c5d5-53ce-a910-376a1f9927b7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 33b542f6-8179-50cb-9b16-9fed5ae2aba1 |  | note | Conformance Criteria - Engineer acceptance
label | f6ff9854-0160-54f8-a197-6ecf150c644b |  | note | Records - Site visits, emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Berm Demolising
label | f63ef5a4-4981-551d-93d0-865e678bc212 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f9e8d03f-6361-5abc-ab4e-3429c64dff48 |  | note | Detail - Final inspection to be done before berm demolision
label | 0966a4a2-a3f8-59f5-8e4d-1bd4e4ae869e |  | note | Frequency - Before Diverting back the River
label | 415febc2-d024-5d0d-b909-56cbffa84e46 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 32582daa-5490-58bd-9430-1379218e8636 |  | note | Conformance Criteria - Engineer acceptance
label | 10710ceb-3e27-5866-a9b3-f51294bde6bc |  | note | Records - Site visits, emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 - Planting Process
label | 88bddaa5-f0e5-5e1d-b0f9-9670a9ef730f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 31ae583e-7788-54fd-9eb4-a9cbc5342828 |  | note | Detail - The Engineer shall be notified of any key stages throughout the planting process and afforded the opportunity to inspect and adjust as necessary.
label | 4cb43045-4cda-5f40-b09c-d38faadbf05d |  | note | Frequency - During planting
label | d78f73a2-b03b-5402-a6a2-74ba5b048caa |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | f6935acb-2c6b-5075-868d-b82c7a9aefec |  | note | Conformance Criteria - Engineer acceptance
label | 128af767-6a43-598a-b706-0a814d5d9fbb |  | note | Records - Site visits, emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Post-Construction Closeout
checkpoint-status |  |  | checkpoint | 13 - Final Walkover (Snags)
label | ac506f7a-c09e-5d42-b8cb-99db25075e56 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d55501f9-002f-5288-aac5-736fdde3d96d |  | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | 66451397-1198-5a56-a429-d1b189b62343 |  | note | Frequency - At the completion of the Lot of work
label | d30b7d07-baba-512a-a4c3-0d0bc5833df5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | 3865c2f9-4239-50a5-8357-9031551568a6 |  | note | Conformance Criteria - Completed report
label | f08ad7a9-a41b-53c8-818c-3bd940022a1f |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 14 - Survey As-builts
label | 7bacf22e-e052-54ee-86d5-08feb7b1e49f |  | note | ACTION (Hold, Monitor, Witness) - H
label | af013ef9-f970-5c7a-9936-9a7455ff8887 |  | note | Detail - Red pen mark-up drawings are to be included in the QA file.
label | 87f683e1-f808-506c-9291-c002a7f6cd96 |  | note | ○ A survey as-built of completed work must be provided
label | 7651c91d-6e6a-5ea2-b009-27b7ce3e5ba8 |  | note | Frequency - At the completion of the CWP of work
label | ff1bb492-ec96-59f6-a8ba-cfd7f1c96018 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | 2f87e3a4-7e5d-5056-a9e8-273f520e431f |  | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated
label | 40f02686-eee3-5af3-9282-c9c31a4e5d90 |  | note | Records - As-built Drawings. Redline Markups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 15 - Quality Assurance Deliverables
label | f3894fda-17bb-5aca-b4d8-4d79b9a28722 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3eda4559-5a0f-54b4-815a-71c2c89497b4 |  | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | 990cc14a-7e38-5fe4-a7cf-d23bde764fa4 |  | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | 7c839158-0c67-56cb-ad43-34e431040a77 |  | note | Frequency - At the completion of the CWP
label | c3eb1ad8-5c89-5917-a846-72c76eeed2a9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 68eb9c51-618f-53fb-b1d5-cc83fe6a848d |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 57d559f2-69c2-550c-8abf-a265b16543ea |  | note | Records - As-builts, NCR's and RFI's