## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - E1401A - Captain's Culvert Inlet Remediation - Master ITP | itp |  |  |  |  | ITP - E1401A - Captain's Culvert Inlet Remediation - Master ITP V2 | 0fb9dcb8-e398-4018-a935-65ebe47e4c8d
section | Master ITP
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Engineer
textbox | Quality Eng.
checkpoint | 1 - Debris Clearance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Need to inspected by the engineer to determine whether rip rap reinforcing is required around the inlet.
label | Frequency - After clearing debris
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Confirmation from the Engineer
label | Records - Site visits, emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Stream and Bank Regrade
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Location and extent of bund is to be confirmed on-site with the engineer.
label | Frequency - After clearing debris
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Confirmation from the Engineer
label | Records - Site visits,Photos emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Stream training
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Stream training is required at the mouth of the gorge with the extent to be confirmed onsite with the engineer.
label | Frequency - After clearing debris
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Confirmation from the Engineer
label | Records - Site visits, emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Gabion basket installation
label | ACTION (Hold, Monitor, Witness) -
label | Detail - separate ITP provided
label | Frequency -
label | Inspection / Test Method submission, visual inspection, testing, measure, review -
label | Conformance Criteria -
label | Records -
checkpoint | 5 - Rock Armourt installation
label | ACTION (Hold, Monitor, Witness) -
label | Detail - separate ITP provided
label | Frequency -
label | Inspection / Test Method submission, visual inspection, testing, measure, review -
label | Conformance Criteria -
label | Records -
checkpoint | 6 - Subsoil Drain
label | ACTION (Hold, Monitor, Witness) -
label | Detail - separate ITP provided
label | Frequency -
label | Inspection / Test Method submission, visual inspection, testing, measure, review -
label | Conformance Criteria -
label | Records -
checkpoint | 7 - Parking bay construction
label | ACTION (Hold, Monitor, Witness) -
label | Detail - separate ITP provided
label | Frequency -
label | Inspection / Test Method submission, visual inspection, testing, measure, review -
label | Conformance Criteria -
label | Records -
checkpoint | 8 - Kerb and Channel
label | ACTION (Hold, Monitor, Witness) -
label | Detail - separate ITP provided
label | Frequency -
label | Inspection / Test Method submission, visual inspection, testing, measure, review -
label | Conformance Criteria -
label | Records -
checkpoint | 9 - GuardRail
label | ACTION (Hold, Monitor, Witness) -
label | Detail - separate ITP provided
label | Frequency -
label | Inspection / Test Method submission, visual inspection, testing, measure, review -
label | Conformance Criteria -
label | Records -
checkpoint | 10 - Swale Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The Engineer needs to inspect and adjust the transition and swale if needed.
label | Frequency - Once the swale is set out.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Engineer acceptance
label | Records - Site visits, emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Berm Demolising
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Final inspection to be done before berm demolision
label | Frequency - Before Diverting back the River
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Engineer acceptance
label | Records - Site visits, emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Planting Process
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The Engineer shall be notified of any key stages throughout the planting process and afforded the opportunity to inspect and adjust as necessary.
label | Frequency - During planting
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Engineer acceptance
label | Records - Site visits, emails
holdpoint | AUTHORITY HOLDPOINT
section | Post-Construction Closeout
checkpoint | 13 - Final Walkover (Snags)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | Conformance Criteria - Completed report
label | Records - Snag List signed by attendees
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Survey As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark-up drawings are to be included in the QA file.
label | ○ A survey as-built of completed work must be provided
label | Frequency - At the completion of the CWP of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated
label | Records - As-built Drawings. Redline Markups
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 - Quality Assurance Deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | Frequency - At the completion of the CWP
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checklist | ITP - B1101A - Te Ngarue Bridge - Scours Asphalt | itp |  |  |  |  | ITP - B1101A - Te Ngarue Bridge - Scours Asphalt V2 | 0d04d2e0-3ff5-4777-b70f-a37f59f54c15
section | 1 - Milling Operations
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1.1 - Survey Setout - Milling
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Confirm site extents by checking what’s marked on the road matches the job sheet / Design Report
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, Survey
label | Conformance Criteria - Mark out on site, confirmed by CPS Engineer
label | Records - Survey, Photos, COR
checkpoint | 1.2 - Milling Existing AC
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Milling undertaken to correct depth of 50mm ±5mm nominal thickness
label | Frequency - During operation
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Dip checks
label | Conformance Criteria - Design Report, depth of milling confirmed by CPS
label | Records - QA Records, Photos
checkpoint | 1.3 - Waterproofing Exposed Layer
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Exposed Basecourse waterproofed / levelled
label | Frequency - Post milling, before asphalt
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria -
label | Records - QA Records, Photos
section | 2 - Material Compliance
checkpoint | 2.1 - Binder Penetration Grade
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - To comply with NZTA M01: 2020 - Table 6.1 and TNZ P11: 2007 - Table 5.2 Lab Mix
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | Conformance Criteria - NZTA M01: 2020 - Table 6.1 TNZ P11: 2007 - Table 5.2 Lab Mix Design Volumetric and Physical requirements
label | Records - IANZ Report
checkpoint | 2.2 - Coarse Aggregate Source
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - To comply with TNZ P11: 2007
label | Frequency - 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009)
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | Conformance Criteria - 230kN minimum Crushing Resistance, AA or BA Weathering Quality Index
label | Records - IANZ Report
checkpoint | 2.3 - Coarse Aggregate Production
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - To comply with SPC-21711902a-PVT-PV3006-H-01 + TNZ P11:2007 and RPT-21711902a-PVT-PV310-H01
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | Conformance Criteria - PSV: ≥ 58. (At least 85% by mass of minimum PSV) Table 3.13 for various sites
label | Records - IANZ Report
checkpoint | 2.4 - Fine Aggregate Source
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - To comply with TNZ P11: 2007
label | Frequency - 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009)
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | Conformance Criteria - 130kN minimum Crushing Resistance
label | Records - IANZ Report
checkpoint | 2.5 - Blended Coarse Aggregate Production
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - To comply with TNZ P11: 2007
label | Frequency - 1/500m³ (Section6 of RNZ 9805:2009)
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | Conformance Criteria - 2.25 Max Particle Shape
label | ○ 98% Broken Faces
label | ○ Report Value - 5 minimum Cleanness Value
label | Records - IANZ Report
checkpoint | 2.6 - Asphalt Mix Design
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Mix Design approved including peer review to comply with TNZ P11: 2007
label | Frequency - 10 days minimum prior to paving
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - TNZ P11: 2007 Table 5.1 Mix Envelop & 5.2 Lab Mix Design Volumetric and Physical requirements
label | Records - IANZ Report, Mix Design
section | 3 - Construction
checkpoint | 3.1 - Survey Setout - Paving
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Determine paving run start/stop locations
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Visual Inspection
label | Conformance Criteria - Ensure accurate survey setting out is in place.
label | Records - Survey Record
checkpoint | 3.2 - Weather Check
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure weather conditions are acceptable for work to proceed
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Weather Forecast
label | Conformance Criteria - Not foggy or raining or wet surface. Base Temp ≥ 7ºC (25 – 75mm layers)
label | Records - Forecast Records, QA Records
checkpoint | 3.3 - Surface Preparation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure previous layer is broomed clean.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Truck broom to have been used and surface approved by CPS Engineer
label | Records - QA Records, COR
checkpoint | 3.4 - Tack Coat
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Apply tack coat
label | Frequency - Prior to asphalt
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Spray sheet, QA records
label | Conformance Criteria - TNZ M/10 2020 - Section 9.3.1
label | Records - Spray sheet, QA records
checkpoint | 3.5 - Production Property Test - Grading
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - To comply with SPC-2171902a-PVT-PV3006-H-01
label | Frequency - 1/>30mimutes production run and 2/>5 hours production run
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | Conformance Criteria - Approved JMF + Table 7.1 - Mix Control Tolerance Note: ±0.4% rolling ave of four
label | Records - IANZ Report, QA Records
checkpoint | 3.6 - Production Property Test - Binder Content
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - To comply with SPC-2171902a-PVT-PV3006-H-01
label | Frequency - 1/>30mimutes production run and 2/>5 hours production run
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | Conformance Criteria - Approved JMF + Table 7.1 - Mix Control Tolerance Note: ±0.4% rolling ave of four
label | Records - IANZ Report, QA Records
checkpoint | 3.7 - Production Property Test - Maximum Specific Gravity
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - To comply with TNZ TM6002:2006
label | Frequency - 1/>30mimutes production run and 2/>5 hours production run
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | Conformance Criteria - TNZ TM6002:2006 Report Value
label | Records - IANZ Report, QA Records
checkpoint | 3.8 - Production Property Test - Avg Temperature
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Check temperature of Asphalt for every truck entering the paver.
label | Frequency - Any truck load
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Temperature Check
label | Conformance Criteria - TNZ P11: 2007
label | ○ ±10 oC from recommended mixing temperature
label | Records - IANZ Report, QA Records
checkpoint | 3.9 - Asphalt Construction - Layer Thickness
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Ensure asphalt is laid at correct thickness of 50mm to comply with SPC-2171902a-PVT-PV3006-H-01.
label | Frequency - During paving operation
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - ±5mm nominal thickness as shown in the Drawings, Plans and/or Specifications
label | Records - IANZ Report, QA Records
checkpoint | 3.1 - Asphalt Construction - Surface Shape
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Ensure asphalt is laid to correct shape to comply with SPC-2171902a-PVT-PV3006-H-01.
label | Frequency - During paving operation
label | Inspection / Test Method submission, visual inspection, testing, measure, review - 5m straight edge
label | Conformance Criteria - SPC-2171902a-PVT-PV3006-H-01.
label | ○ ≤5mm (Visual Inspection)
label | Records - QA Records
checkpoint | 3.11 - Asphalt Construction - Surface Texture
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - To comply with NZTA M10: 2023
label | Frequency - Every 10 metres
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Laser Profilometer
label | Conformance Criteria - NZTA M10: 2023 Table 3
label | Records - IANZ Report, QA Records
checkpoint | 3.12 - Asphalt Construction - Compaction
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - To comply with NZTA M10: 2023
label | Frequency - One test per 50m2
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM for Quality Control Only
label | Conformance Criteria - NZTA M/10: 2020 - section 9.9.3
label | Records - IANZ Report, QA Records
checkpoint | 3.13 - Ride quality
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Upon 100% completion of OGPA layer and at expiry of defects liability period
label | Frequency - Prior to Opening to Traffic
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NAASRA
label | Conformance Criteria - 10. Appendices to Principal's Requirement: 50 NAASRA count as a 95%tile for every 100m rolling section
label | Records - IANZ Report, QA Records
checkpoint | 3.14 - Surface finish visual inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Site walk over
label | Frequency - Post Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - No visible cracks, No obvious defect related to poorly constructed joins, No areas where water can pool; No part of all pavement surfaces deviate more than 5mm from a 2m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline.
label | Records - QA Records, COR
holdpoint | AUTHORITY HOLDPOINT
section | 4 - Post-Construction Closeout
checkpoint | 4.1 - Final Walkover (Snags)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | Conformance Criteria - Completed report
label | Records - Snag List signed by attendees
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Survey As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark-up drawings are to be included in the QA file.
label | ○ A survey as-built of completed work must be provided
label | Frequency - At the completion of the CWP of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | Records - As-built Drawings. Redline Markups
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Quality Assurance Deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | Frequency - At the completion of the CWP
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 4.4 - Final Approvals
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Signoffs by Project Manager, Quality Manager and CPS Manager
label | Frequency - At the completion of the CWP
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all parties have signed and approved ITP
label | Records - Signatures
holdpoint | AUTHORITY HOLDPOINT