## Sheet1
4.6.1 | CVSC - Detailed Plan | IFC Drawings, Sheet No. C-7011 | Refer to IFC drawing to reference the sign and marking details for the CVSC facility. All dimensions and requirements are listed within the Legend of the drawing. | Photos | All | Visual | V | SE | 4.6.1 - CVSC - Detailed Plan | Standard/Specification - IFC Drawings, Sheet No. C-7011 | Acceptance Criteria - Refer to IFC drawing to reference the sign and marking details for the CVSC facility. All dimensions and requirements are listed within the Legend of the drawing. | Verifying Document - Photos | Frequency - All | Inspection Type (Visual, other) - Visual | Inspection: Key - V | Inspection: By - SE | 4.6.1 - CVSC - Detailed Plan | - | Inspection Point: Quality Control Activity - | Acceptance Criteria - | Verifying Document - | Frequency - | Inspection Type - | Inspection: Key - | Inspection: By - | -
4.6.2 | CVSC - Detailed Plan | IFC Drawings, Sheet No. C-7012 | Refer to IFC drawing to reference the sign and marking details for the CVSC facility. All dimensions and requirements are listed within the Legend of the drawing. | Photos | All | Dimension Inspection Visual | D,V | SV, SE | 4.6.2 - CVSC - Detailed Plan | Standard/Specification - IFC Drawings, Sheet No. C-7012 | Acceptance Criteria - Refer to IFC drawing to reference the sign and marking details for the CVSC facility. All dimensions and requirements are listed within the Legend of the drawing. | Verifying Document - Photos | Frequency - All | Inspection Type (Visual, other) - Dimension Inspection Visual | Inspection: Key - D,V | Inspection: By - SV, SE | Standard/Specification - IFC Drawings, Sheet No. C-7011 | - | Inspection Point: Quality Control Activity - | Acceptance Criteria - | Verifying Document - | Frequency - | Inspection Type - | Inspection: Key - | Inspection: By - | Inspection Point: Quality Control Activity -
4.6.3 | Sign Details and Dimensions | IFC Drawings, Sheet No. C-7100 and C-7101 | - Legend is series E 125 unless stated otherwise - Contractor to organise for shop drawings of traffic signs to be in accordance with the Traffic Control Devices manual and manual of Traffic Signs and Road Markings - Traffic sign posts to be in accordance with RSMA - All measurements are in millimeters unless otherwise stated | Photos | All | Dimension Inspection Visual | D,V | SV, SE | 4.6.3 - Sign Details and Dimensions | Standard/Specification - IFC Drawings, Sheet No. C-7100 and C-7101 | Acceptance Criteria - - Legend is series E 125 unless stated otherwise - Contractor to organise for shop drawings of traffic signs to be in accordance with the Traffic Control Devices manual and manual of Traffic Signs and Road Markings - Traffic sign posts to be in accordance with RSMA - All measurements are in millimeters unless otherwise stated | Verifying Document - Photos | Frequency - All | Inspection Type (Visual, other) - Dimension Inspection Visual | Inspection: Key - D,V | Inspection: By - SV, SE | Acceptance Criteria - Refer to IFC drawing to reference the sign and marking details for the CVSC facility. All dimensions and requirements are listed within the Legend of the drawing. | - | Inspection Point: Quality Control Activity - | Acceptance Criteria - | Verifying Document - | Frequency - | Inspection Type - | Inspection: Key - | Inspection: By - | Acceptance Criteria -
[17 empty] | Verifying Document - Photos | - | Inspection Point: Quality Control Activity - | Acceptance Criteria - | Verifying Document - | Frequency - | Inspection Type - | Inspection: Key - | Inspection: By - | Verifying Document -
[17 empty] | Frequency - All | - | Inspection Point: Quality Control Activity - | Acceptance Criteria - | Verifying Document - | Frequency - | Inspection Type - | Inspection: Key - | Inspection: By - | Frequency -
[17 empty] | Inspection Type (Visual, other) - Visual | [8 empty] | Inspection Type -
[17 empty] | Inspection: Key - V | [8 empty] | Inspection: Key -
[17 empty] | Inspection: By - SE | [8 empty] | Inspection: By -
[17 empty] | 4.6.2 - CVSC - Detailed Plan | [8 empty] | -
[17 empty] | Standard/Specification - IFC Drawings, Sheet No. C-7012 | [8 empty] | Inspection Point: Quality Control Activity -
[17 empty] | Acceptance Criteria - Refer to IFC drawing to reference the sign and marking details for the CVSC facility. All dimensions and requirements are listed within the Legend of the drawing. | [8 empty] | Acceptance Criteria -
[17 empty] | Verifying Document - Photos | [8 empty] | Verifying Document -
[17 empty] | Frequency - All | [8 empty] | Frequency -
[17 empty] | Inspection Type (Visual, other) - Dimension Inspection Visual | [8 empty] | Inspection Type -
[17 empty] | Inspection: Key - D,V | [8 empty] | Inspection: Key -
[17 empty] | Inspection: By - SV, SE | [8 empty] | Inspection: By -
[17 empty] | 4.6.3 - Sign Details and Dimensions | [8 empty] | -
[17 empty] | Standard/Specification - IFC Drawings, Sheet No. C-7100 and C-7101 | [8 empty] | Inspection Point: Quality Control Activity -
[17 empty] | Acceptance Criteria - - Legend is series E 125 unless stated otherwise - Contractor to organise for shop drawings of traffic signs to be in accordance with the Traffic Control Devices manual and manual of Traffic Signs and Road Markings - Traffic sign posts to be in accordance with RSMA - All measurements are in millimeters unless otherwise stated | [8 empty] | Acceptance Criteria -
[17 empty] | Verifying Document - Photos | [8 empty] | Verifying Document -
[17 empty] | Frequency - All | [8 empty] | Frequency -
[17 empty] | Inspection Type (Visual, other) - Dimension Inspection Visual | [8 empty] | Inspection Type -
[17 empty] | Inspection: Key - D,V | [8 empty] | Inspection: Key -
[17 empty] | Inspection: By - SV, SE | [8 empty] | Inspection: By -
-
Inspection Point: Quality Control Activity -
Acceptance Criteria -
Verifying Document -
Frequency -
Inspection Type -
Inspection: Key -
Inspection: By -
-
Inspection Point: Quality Control Activity -
Acceptance Criteria -
Verifying Document -
Frequency -
Inspection Type -
Inspection: Key -
Inspection: By -