## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
7c1a3da3-b409-5585-a0a9-582cbf221025 | checklist | Concrete Pre-pour Inspection |  | Concrete Pre-pour Inspection
afa5d3a5-0b73-50dc-aca6-7cf16f0b26ea | section | Preliminary
a62c59e8-596d-5051-a260-fa70b945a0ee | checkpoint | Engineer notified of pour
98ffea72-4951-5484-a1cb-4a448e1233c5 | textbox | Date
7006f770-0251-5e19-ad15-3a83db9ada77 | textbox | Drawing Number and Revision
b9eafc2c-96c7-5bf6-a5bb-3f77d2a0035b | section | Formwork
b1340f06-7037-5580-9cef-d2bf8c5f7e88 | checkpoint | Installed as per formwork design
21c2f84a-9e2a-5887-81e4-03d7085f1e26 | checkpoint | Permit to load issued
2e5498ea-d2bb-5b1a-9c01-6a577398eb03 | checkpoint | Dimensions correct
448ef6dc-09c2-5b2c-8671-11eb6b6059d8 | checkpoint | Position and orientation correct
e15cc9fb-76f8-5d30-85b8-3a15efa13919 | checkpoint | Forms vertical, plumb and true
d7b52d60-39fb-5b66-88f7-32a69a8105c3 | checkpoint | Forms coated with release agent
2c9b6681-a705-5dbc-b6c5-d51dd43c97fb | checkpoint | Forms clean and clear of debris
5658db69-ee4b-573e-9a99-02666de42116 | checkpoint | Joints sealed
fb71f862-345c-5f12-85dd-337aeca9e99b | checkpoint | Pour level marks
15f721dd-2cad-5140-b52a-224004dbe0f1 | section | Reinforcement
98c4424d-05d0-57ac-a17a-d4a1af7888a3 | checkpoint | Correct grade reinforcement
a963c440-8d37-5368-b076-043b9a2372ed | checkpoint | Correct bar size
7ce71365-e057-5c13-97b4-815a1c9c89d9 | checkpoint | Correct number of bars
b2e5894b-d47e-5155-bae4-76af84c26602 | checkpoint | Correct spacing
063c4b4a-80b8-51b0-80ef-ffbfece4f7fd | checkpoint | Starters bars included
c08acb2d-4498-572a-860f-5804e9367f87 | checkpoint | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
06ae2c2a-0fff-5e07-b042-21814f8eee30 | checkpoint | Correct weld lengths (min 10 x bar diameter)
1dfe9c14-bd72-5bdb-a828-516f984ce876 | checkpoint | Correct lap length (min 50 x bar diamenter or as per drawing)
caf200a6-29f0-5a1e-82de-f81ff9e242aa | checkpoint | Correct lap position (staggered appropriately)
de950a43-eb21-5017-a840-73ae72bd0260 | checkpoint | Longitudinal bars terminate with 90 or 180 deg hook)
68165656-1dc5-5711-a328-d6471d3859e2 | checkpoint | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
260ed36a-9f96-5fad-9bcf-1c4db6998751 | checkpoint | Reinforcing adequately tied
02eb21f0-a017-5056-8fa8-ac4ddde0e1ef | checkpoint | Chairs or spacers fixed in place
bc2099f6-3c87-5e49-a354-89c7a96b78ed | section | Embedded items
8b855fa5-d884-583d-80fa-b37b1616e5ef | checkpoint | Block-outs, ducts & cast in items installed
93b8301c-9ace-5abf-a2f4-5b1e275c00d1 | checkpoint | Correct position, level & alignment
11e272fb-1d06-519a-8d3d-e7389196ff59 | checkpoint | Securely fixed in place
42fd55de-9d63-5d85-844a-49f359657c2f | section | Construction Joints
5c96949b-f291-5b6b-9ace-83913123d316 | checkpoint | Correct location
39e82156-a651-5628-ae8e-59664bcf904c | checkpoint | Adequately prepped
54a2d7fc-4be5-508e-8d6b-e0fd15cd1956 | checkpoint | Joint board installed
d2378470-cd46-547f-94e7-c7b5caf8949b | checklist | ITP - 107 - Pavement Drains | itp | ITP - 107 - Pavement Drains
8c9335a7-3af5-5e47-a887-39a89ff08c27 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
eef00716-4e5d-5b03-b172-716ad54d042a | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
765b1048-c088-5b6f-9623-8c5346ff99e7 | note | Standard / Specification - Downer
397a1e6d-4464-5f66-b1bb-bdf001298e8b | note | Verifying Document - Construction Pack
05d4a935-0ef3-5cde-80aa-4d1301943a80 | note | Frequency - Submit 10 days prior to commencement of works
eac0916a-6ddb-5a54-949e-98cefbbc2210 | note | Activity - H
806a65ec-353e-5e0d-935c-204f576001c3 | note | By - PE
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
180417cf-f085-5ace-9953-f519ccf1706c | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
96347aea-037b-5640-95a4-1d4dfc132a6e | note | Standard / Specification - Downer
16eacf5e-a788-546e-a0cd-1aedc5ee8570 | note | Verifying Document - Survey Records
be32c357-44f6-529a-8363-67b4f3529304 | note | Frequency - Prior to Works
c4af63f6-c85f-59f1-809e-59bc586c641c | note | Activity - H
f104ef54-18ca-50f8-b622-564b36e5dd3e | note | By - SV
7b8b4071-ba18-54c4-a07c-9e192aec85d8 | checkpoint | 3.01.03 - Approved Construction Drawings
c494c038-e47d-5ce7-b618-58b9f20e4c67 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
c6ecdd42-653b-5c87-9072-43a0eadf906c | note | Standard / Specification - Downer
4e3ba869-ecd5-51a9-8e80-40f8a3e0199e | note | Verifying Document - IFC Drawings
988c6302-1576-5fe0-ad37-e6e63e58da1e | note | Frequency - Prior to works start
4d176dba-b452-553e-a533-5a82796a3ab1 | note | Activity - H
526d4aa1-d98f-5698-8a92-deeccd5de232 | note | By - PE
f54e7b48-3f2b-51d6-93b0-54755388f0cc | checkpoint | 3.01.04 - Topographic surveys for measurement
f927db23-c857-5010-bccb-337cc5a5dab9 | note | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
91b1b8ba-eb23-5cb1-89e8-90e6c32ba274 | note | Standard / Specification - PS 2.2.12
795d7fbf-075a-5c81-8f14-b524bc83a870 | note | Verifying Document - As-built
8e12b724-0f78-51b2-bdef-fa392fd5d083 | note | Frequency - Prior to works and Post Works
46002215-7271-508f-b388-aa1c2f73fb15 | note | Activity - H
a41ac510-4c8f-5101-a059-58a692208e38 | note | By - PE
f26fef48-d615-5889-ba64-e206f54c0d34 | checkpoint | 3.01.05 - Permits
22e6ad25-092d-5548-a2d8-51e8a1593b0a | note | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
409b7359-80e8-5acc-9198-5d34ac52ec2d | note | Standard / Specification - ITP Register
1f3e89f2-4480-5fe8-b063-4a578a27d691 | note | Verifying Document - ITP Sign Off
ad52a87c-f310-5834-bdc5-abb31ce9ac1e | note | Frequency - Prior to commencement of construction activity
5eb73539-c018-532f-b744-52ab274ca51f | note | Activity - R
a7fc22a5-8f14-5766-918d-63b3cecf0195 | note | By - SE
72a761a8-8bee-5916-91e9-a2f4ef42bc73 | checkpoint | 3.01.06 - Stakeholder Management
6772a3a5-74ae-5849-b0e0-b36ea6baf81f | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
435660c9-5625-5888-837f-0a6f88ce611a | note | Standard / Specification - Project Stakeholder Management Plan
58ea1067-5df3-58c6-9b10-edbf2c8e408c | note | Verifying Document - ITP Sign Off
74cc34a4-f0aa-5202-9a03-dd52ea46867e | note | Frequency - Prior to Construction with continue updates throughout the works
89dcf2fb-9078-588c-aaa1-bf271fd79ee4 | note | Activity - R
96a554b1-43eb-5bc7-8a17-143409cfd62e | note | By - SE
8ec62109-1664-5fbd-8086-47c125cee66d | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
08534115-94ee-5cfc-be8c-086ea7ffdd06 | checkpoint | 4.01.01 - Subsoil Pipes
6d376193-63a5-5f57-8e40-316e71973266 | note | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 100mm diameter complying with NZTA F/5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
34ad6500-373e-5051-9826-4a1d20223e96 | note | Standard / Specification - GWS 3.2.1
bc934418-5005-5ef9-bd0e-73582085601a | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
84cc8e48-b25d-50dd-b493-0872459f881f | note | Frequency - Every Delivery to Site
4d7be173-4c31-5cd2-8ec4-6235ebf15736 | note | Activity - C
c58e9fbc-5f93-5b00-8e1c-6ccd13b803d9 | note | By - SE
71011ef5-31e0-5d97-b246-1d11311696c1 | checkpoint | 4.01.02 - Subsoil Drainage Aggregate
fcc12b20-cca2-512b-a937-1f951a99ded4 | note | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/6 including gradings (40/20 aggregate). Be open course grade clean durable aggregate, Have a crushing resistance of no less than 100kN when tested in accordance with NZS 4407:1991 Test 3.11 Meet the following gradings when tested in accordance with NZS 4407:1991, Test 3.8.1: App B - HAM2018-0136AJ Rev. 1 Geotechnical Works Specification: Table 2: Filter Material Gradings (Geotextile Wrapped Aggregate) Test Sieve Aperture (mm) Percentage Passing (%) 53 100 13.2 10 (max)
fa485186-b96a-52c9-9058-24ec2e833fe9 | note | Standard / Specification - GWS 3.2.2 & 3.4
061ef45c-ffd4-58e4-87df-e8fd7f8adeb1 | note | Verifying Document - PSD, CR
b8c5182b-9ee9-5d26-aedc-1ebac092ca1b | note | Frequency - Material Tests every 1000m³ or change of source. Visual inspection every load, verifying document photos of material onsite, if visual appearance changes, additional testing will be required.
c09d35b2-6d0a-5e65-8a73-0442d1581335 | note | Activity - C
8aeb1063-a1e3-53e1-bd84-41c3848cad13 | note | By - SE
6d7192d6-9061-5d38-a315-d4a8752b3fa5 | checkpoint | 4.01.03 - Filter Cloth
4d00d963-e5b2-5ec4-bdbe-7b83a09ad16d | note | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings. (A14 Bidim or Equivalent)
3dbf25b6-cae4-5c3a-8e05-2898bf99e521 | note | Standard / Specification - GWS 3.2.3
c126941f-b768-5b30-ae2e-6798b6457186 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
4c219803-133a-5171-bab3-8ae8749045f5 | note | Frequency - Every Delivery to Site
54eaf21a-b3ea-5116-b8f4-0d0045c266e9 | note | Activity - C
b5976aef-6260-5629-816e-6e4bacaedafe | note | By - SE
34efbf28-65bc-5d1f-b72b-f1491def807a | checkpoint | 4.01.04 - Securing Pins
d845c3e0-ef7e-5b4e-838b-d83b5a360f76 | note | Acceptance / Conformance Criteria - Pins for securing the geotextile shall be of steel, a minimum of 5mm in diameter and at least 400mm in length
8521468b-b01b-5e26-93aa-3e63694682c7 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class,.
24f277e3-b638-5d86-91c5-3dd99a8884dd | note | Frequency - Every Delivery to Site
335ffb25-ee69-51f3-a9b7-28e2ed59402a | note | Activity - C
9c92a1d5-c2c7-544b-8af9-16d4f18d2241 | note | By - SE
f4713bb7-3aea-5dca-b516-69272c0b56ba | section | SECTION 5 – CONSTRUCTION ACTIVITY
113d79bf-1485-508d-814d-8c7c8c221530 | checkpoint | 5.01.01 - Filter Cloth Wrap Inspection
6811ea07-5a89-50d9-81a0-240052de7a0d | note | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain. TNZ F/6, PWRBSS Geotechnical Specification - The geotextile shall be placed in the tench so as to conform loosely to the shape of the trench. Cloth must fully encapsulate the aggregate. Geotextile longitudinal overlap to be minimum 300 mm (as indicated on drawing 3051 and required by NZTA F/6). Additional sheets to overlap by minimum 500 mm and anchored with securing pins (F/6 requirement). Verifying document, photos of trench prior to backfill, every line.
ec53cdb7-cc25-54c6-b78e-5e162d0a5055 | note | Standard / Specification - GWS 3.2.2
4fcd2436-ca61-55b6-9fe5-fe0251ec6f08 | note | Verifying Document - Every line
5b1a35ef-fdc0-5fab-867b-ab02e3ba5f75 | note | Frequency - Photos of trench prior to backfill
e8addc07-99ec-5073-b4b5-509d0438c645 | note | Activity - HP
36b45a2b-5f18-58e7-9e19-1aeca008b0c0 | note | By - ENG
a2a25648-08b8-5ac9-b1a6-269e329744a0 | signoff | AUTHORITY HOLDPOINT
543c766a-67a1-5508-b12a-a4f69b9927f3 | checkpoint | 5.01.02 - Trench Backfill
5a6ef704-1262-5cee-8cd3-1ca88e235869 | note | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard of the material previously trenched through. Drainage aggregate to be placed in layers of 150mm or less. Only light compaction such as tamping with the back of an excavator bucket is to be applied.
3948db19-ece7-585a-af0f-11b4d7488df2 | note | Standard / Specification - GWS 3.3
d255d60e-c712-5220-9d3c-cb1bb86d98e7 | note | Verifying Document - Site Record
facea8de-cba0-5eaa-81b6-121bf1de9fe3 | note | Frequency - Each trench
cfd6590f-8894-55b7-86ae-a17a69dd2407 | note | Activity - I
7c6101e5-bd07-56fa-a1d6-fc30d486d76a | note | By - SE
f7142f9b-2009-59fd-9453-67a19dd7865a | checkpoint | 5.01.03 - Drainage Outlets and Inspection Points
e0e0dfdd-c152-5d0c-9412-91a6bd87c0fb | note | Acceptance / Conformance Criteria - At least one temporary flush point is required for each subsoil drainage system to enable flushing of the system once the earthworks are complete.
bc1e3839-cba4-575f-a42b-a8f7f6333d04 | note | Standard / Specification - GWS 3.6
af9a4333-12f2-5026-b386-959aed450a8a | note | Verifying Document - Site Records
f4c8e8e7-af68-5172-8727-d91b9dd9213b | note | Frequency - Each Subsoil Line
d5c01f6c-5dd3-57ae-a617-02ae9b57ca57 | note | Activity - I
aaed1beb-c26a-539c-a9dd-5c85e83ad979 | note | By - SE
fd83d42b-b8ea-5d41-8883-9e6215d99eea | checkpoint | 5.01.04 - Subsoil Flushing
8d739b34-85cd-547a-8247-18cc3b18c86b | note | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer.
1d5f0a20-d2df-5e6f-b48a-0e7cdb078918 | note | Standard / Specification - GWS 3.6
4beb6424-e2fd-57df-a7c9-4d3712506bf3 | note | Verifying Document - Site Records
5719ebbd-4e3f-5c51-a425-06bc997661d4 | note | Frequency - On completion of earthworks
f9a6100d-206f-59c5-b591-faca25ca1a54 | note | Activity - HP
41c18113-5b1c-5d8e-8d40-7bff82d6cc82 | note | By - ENG
efdabe6e-46f6-51c4-9707-34eb23acdd0d | signoff | AUTHORITY HOLDPOINT
65ee871c-3fae-5bef-8ed1-f015a6f0c4aa | checkpoint | 5.01.05 - Survey
73f805ec-1be1-5740-aa84-faa7472fe6ac | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
719cc0d7-da0b-50cf-b857-21dac2d03368 | note | Standard / Specification - Downer
80ec50c7-3501-5099-aad9-d3107d575a5b | note | Verifying Document - Records
38279792-2520-5b5f-ad7e-c1d3dde7b3a6 | note | Frequency - Post construction
9dcc6c76-d7ee-5853-8a71-9bc96d68aa03 | note | Activity - H
0123bb12-7443-55a7-be46-bb5296d14b9d | note | By - SV
f999ffd9-5367-57d7-994f-8ff2006b1339 | checkpoint | 5.01.06 - Excavation
4f174c16-c79f-5a5f-bc71-b199753d4ed3 | note | Acceptance / Conformance Criteria - Trenches shall be cut in such manner as will ensure that the geotextile wrapped aggregate pavement drains, and pipes if included, will be laid true to the depths, grades and lines shown on the drawings
c2c9c1ae-73f5-5d4c-8575-26ff0a4b5f5a | note | Standard / Specification - Downer
6cf18612-24aa-5169-8377-5ee893f5aafa | note | Verifying Document - Records
050f8690-1a18-59af-a187-0ae929cb0cd6 | note | Frequency - Prior to laying filter cloth
59222acb-af43-5e0d-a2a8-9d1ecc17b8de | note | Activity - I
f93a0bce-6383-52de-b82c-c023bba5a452 | note | By - SE
78b40005-4535-58a0-8f12-10ce7328ed62 | checkpoint | 5.01.07 - Bedding
2876f6cf-4450-58ef-a4e2-7e7506c0a1eb | note | Acceptance / Conformance Criteria - TNZ F/5 - Bedding thickness shall be no less than 100mm
8da47c77-5900-5d5c-939a-24a45d93b9c8 | note | Standard / Specification - Downer
e1e57d95-3cfa-5486-9252-177719884e87 | note | Verifying Document - Records
99282874-7427-5646-80c4-cf2d5c909736 | note | Frequency - Prior to laying Novacoil
1cde5baa-6f9e-594b-a1a1-92fe408db88b | note | Activity - I
dec6f213-96b0-5480-b5d3-821cf0ca163b | note | By - SE
bc02362a-9ac4-5773-899f-55a42641ec6b | checkpoint | 5.01.08 - Joining Pipes
0ef64d31-9581-5189-b3ad-fac7edb017e9 | note | Acceptance / Conformance Criteria - TNZ F/5 - Joining the pipe shall be done using a purpose made pullout resistant coupling in accordance with manufacturers recommendations
def28e6a-7bc3-51ba-a899-fd9dc500b9c1 | note | Verifying Document - Copy of delivery dockets, photos of pipes onsite with tag showing class
260824f4-3576-52b7-a7c0-82ca028678f3 | note | Frequency - Every join
d30d276f-a5c3-59dc-887d-a339a38e82d2 | note | Activity - I
532c1d45-176c-5ea0-83bb-5e82f111d571 | note | By - SE
cd33a7f8-9b6c-5422-93be-dcae98eaa460 | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
abaa7cc7-67ff-52ad-ae9f-e9176b336a01 | checkpoint | 6.01.01 - Construction Record Compilation
41282f40-d6cb-5103-bf6e-958dd729ff05 | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
dd7a487e-b81d-579c-a71f-0077755339d5 | note | Standard / Specification - Downer
1b01aacd-4fa9-5e67-bcee-f13a4f84057c | note | Verifying Document - Records
93c49c84-ab62-5d90-b6fe-8220b0513eb4 | note | Frequency - Post construction
443d80b3-29dc-5bc2-9371-f8aa81bb76cb | note | Activity - H
24d1b142-e483-53ee-b2e7-c01e05550ac7 | note | By - SE
f4876821-e136-54ca-95e8-27fd0f400f5d | checkpoint | 6.01.02 - Survey Records
3989569f-afea-526f-b341-32ff9a57d0a2 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
efdca4bd-743a-5bae-a775-15a6dc53a42e | note | Standard / Specification - Downer
13d9852a-104e-5ddd-a414-a0b3c8436476 | note | Verifying Document - Records
0fddb792-cd96-5f76-99a6-ec5d92f65f44 | note | Frequency - As-builts taken every 10m prior to backfill
bd9d5d94-7a2f-5dc0-b4ab-68c25b7e617c | note | Activity - H
03d57b79-a84e-5ad6-8f79-e3d9e35c407c | note | By - SV
a7ece1a0-6b4a-5d51-8813-156cc41a337a | checkpoint | 6.01.03 - Redline Drawings
09d83736-3d59-5664-876d-9b1e1a8010df | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.To show all subsoils, including temporary subsoils that become part of the permanent works, to show all outlet locations
183aab9b-8a98-55b8-a516-5e4f702ae200 | note | Standard / Specification - Downer
f64d0f7d-04c7-5770-8bad-bc787444a8e3 | note | Verifying Document - Redlines
fa0c06a6-38af-5efd-adbf-da3e7ed08767 | note | Frequency - Post construction
62ca144a-fde4-5465-929a-b048f4828032 | note | Activity - H
e5945e0b-7d3d-5ef9-a8bf-da45d937a369 | note | By - PE
406cc900-58d1-549c-813d-cb4c75c9a2be | checkpoint | 6.01.05 - Photos
36a80c93-c9dc-55ff-b483-5aa242fff911 | note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
01466be1-a2c6-517a-8f95-3cd5e3a2c397 | note | Standard / Specification - Downer
05d2b333-6235-5b98-a18f-eaa87e514051 | note | Verifying Document - Photo Records
4b223c81-de6d-5f09-96b9-2a7a39248c1b | note | Frequency - Post construction
66ef3d51-81b5-513d-9327-50fbd4284aae | note | Activity - H
ddc4612f-097a-5490-aa75-735a94bdffde | note | By - SE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
86b33e55-1984-4416-84d4-063fcfd184b2 | checklist | ITP - 111 - Wastewater PE Rev C | itp | ITP - 111 - Wastewater PE
3b41d634-1d3d-43ef-8adb-d3a04dbe5dd6 | section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
08e8669c-e5b0-46ab-a310-d0b3ff3aea44 | checkpoint | 1.1 - Extent of Line Setout
aeb8fe9d-d48e-5604-9ca5-d70c9b4597e4 | note | Acceptance / Conformance Criteria - Ensure line and level of wastewater has been marked out and agreed with Engineer in accordance with the drawings.
d21255b2-6816-50dc-b8f4-459b2151f44f | note | ○ Identify any clashes before construction.
3d3b87ed-e4cd-50fa-9e31-08f983c0d421 | note | Standard / Specification - Design Drawings
720275bd-215a-5100-a7a1-2754617f1004 | note | Verifying Document - ITP Sign Off
cc93520a-80a8-5d4d-9c7d-25a872dad2cd | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
ba4bbf44-cd17-5f0c-815b-8c0c65caed81 | note | Verification Activity: Activity - M
38e93665-158d-5659-b3f8-ddc3d2b316d2 | note | Verification Activity: By - PE
d25d3c93-d075-455e-9dc0-43d4af373de6 | checkpoint | 1.2 - Environmental Protection
04a63200-d53f-58f1-b0ce-2b68e546e1e8 | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans
2b2bf356-5daa-5447-b802-9aa436557030 | note | ○ Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
7eab1015-f905-59f6-959e-7b08f783c1d7 | note | Standard / Specification - Project ESCP Plans
dea900ca-7bbd-5239-8969-f85b9506a37e | note | Verifying Document - ITP Sign Off
5e08a5b5-fac3-5b35-af40-54fe54e19ac7 | note | Frequency - Prior to Construction
12705b6d-c86c-537b-9cb9-e52b92fd4ce6 | note | ○ Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
98afff49-518c-564b-9ef6-fcb3158309de | note | Verification Activity: Activity - M
f07025db-49e3-56db-9c67-abadbe7b1e2d | note | Verification Activity: By - PE
dd01c6c2-4558-4cd7-82ad-a54f9af241fc | checkpoint | 1.3 - Stakeholder
50ea45da-5b18-55e2-aa74-02b41df97537 | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works
3aeb4497-bcf3-54dd-8ebe-8b18d396bd14 | note | ○ Agree plans for maintaining access to properties during construction with landowners
53a1f713-9b56-5c03-9dbc-7acc224e0ae1 | note | Standard / Specification - Project Stakeholder Management Plan
b79b003f-2a38-558b-a246-4934244b3892 | note | Verifying Document - ITP Sign Off
2ee25f6b-3088-5d69-baf7-8d7e5e0b189b | note | Frequency - Prior to Construction with continue updates throughout the works
699a8c5e-1e14-5648-845c-2ed4649baa4e | note | Verification Activity: Activity - M
6cda8349-52f5-58d4-a2ef-4ee5d814d206 | note | Verification Activity: By - PE
652b07a0-288f-4b6c-83e7-b1142f207412 | checkpoint | 1.4 - Permits
a5052d35-33aa-56ec-bc23-42f7666866e6 | note | Acceptance / Conformance Criteria - Permit to Dig must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip.
d97c8b42-7d55-5a44-b0a9-19477bff931d | note | ○ Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections.
f9ae2df0-077c-5b2a-a588-4c0829bbb1fc | note | ○ All known services must be clearly marked on site and briefed to the workforce.
ef3c7362-e75c-5927-bbe6-23d51b0e1afc | note | Standard / Specification - Section 2.2.10 Project Specification
8c79bfc5-8c9d-5ad4-9bd1-0230ac798635 | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
14f7f7b3-b603-538c-ab5b-15e2c448400a | note | Frequency - Prior to Construction
82892767-4adb-53d3-b8f6-c5391a5c4c13 | note | ○ Reviewed and Reissued weekly or when site conditions change
456380ec-b30b-5f69-8ac2-1d6045db2482 | note | Verification Activity: Activity - H
232817e1-717a-5c92-8d76-943d6d8d1e40 | note | Verification Activity: By - PE
d2ce9723-f0d7-4d8f-b99c-3e030396441b | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
ff08673a-8620-4836-8497-ae10c996fdd6 | checkpoint | 2.1 - Pipes/Fittings/precast Units
e9c31d34-876f-5a04-82ec-40ff2e955ae1 | note | Acceptance / Conformance Criteria - Confirm pipes diameter and class as shown on the drawings.
0c79066c-65c2-5c84-bbbc-2125ef01bbf1 | note | ○ Pipe dimensions given on the drawings are nominal outside diameters.
eba0616b-c735-5a26-a45b-9747e6217689 | note | ○ Manufacturer verification/records of compliance of PE pipe (i.e. pipe resin data)
b799c7df-4ae3-5561-bcd4-a3a4ded21ac2 | note | Standard / Specification - Project Specification
312d35af-c8fb-5b14-b287-71722f13dc43 | note | Verifying Document - Visual Check, Manufacturer's Verification
740efda2-cdaf-51e6-a66a-556b1c980c9a | note | Frequency - Each Delivery to Site
c043618c-b5d3-50b1-b1b5-c6727b4704c2 | note | Verification Activity: Activity - S
6f918756-8b98-5394-907e-7794edc81cb3 | note | Verification Activity: By - PE
276f5a4f-2bc2-4846-b718-223127fa92cd | checkpoint | 2.2 - Undercut Backfill/Bedding/Side/Haunch/Overlay/Backfill Material Compliance
9c5d5479-fe16-5b02-b29a-d0a96d4df062 | note | Acceptance / Conformance Criteria - Confirm material grading and density of pit sand
5e24e1a2-32e7-5ba0-b788-e64d3e081ec2 | note | Standard / Specification - AS/NZS2566 G1 (or otherwise)
d79dd7cb-db88-5cb7-b854-6b0aa03a87c2 | note | Verifying Document - IANZ Lab Test Reports
6d3c2d6c-667b-5a52-8b99-54aa2baf77ec | note | Frequency - 1 Test per 1000m3
6946ba1a-18c4-5e0c-8c96-b7d0ce92da87 | note | Verification Activity: Activity - H
c0a2de92-0313-576b-b56a-42ede3d1095e | note | Verification Activity: By - PE
022bc2de-c3d0-4873-bd8a-f83194ec3224 | section | SECTION 3 – CONSTRUCTION ACTIVITY
2fb04865-fa75-4b15-8eef-7bd73c7a0c90 | checkpoint | 3.1.1 - Foundation Compliance
a0208e95-b9fa-5192-a5eb-d92f0ee341a5 | note | Acceptance / Conformance Criteria - Scala 3 blows/100mm
4e3e64b4-b800-566d-97b6-f2667d7f158a | note | ○ Vane Shear Strength 70kPa
da8cb4c0-8661-5db0-aad4-6c3c4592aca2 | note | Standard / Specification - Project Specification 4.3
b02584e9-24f6-5197-bec9-916fa46ac2f9 | note | Verifying Document - Scala test result
cc7e873d-7c1b-5e1e-afaa-af8bcce0e794 | note | Frequency - Every 20m along trench
23c5c8cb-325f-554a-93ed-957220ae95c8 | note | ○ 1 test every 5m² at driveways and footpaths
9b867a40-9997-5a9f-9c5c-9ed5f70ebfd6 | note | Verification Activity: Activity - H
93bbe515-3514-54ff-9c97-8358f883f017 | note | Verification Activity: By - QE
f735f248-55f1-458a-af08-8d9bbd9ce555 | checkpoint | 3.1.2 - Undercut Backfill Compliance
54465482-3160-5c72-b2f6-ff5caa5fe869 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm
22c93251-3c8e-5d2e-b714-6af3235fac97 | note | ○ Minimum Compaction 95%(Average98%) of MDD
407ad1e9-72f1-5f47-ac03-9407b446ad13 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 95% of MDD
e3c5af9c-c895-5adf-93a4-d2ea077db452 | note | ○ AS/NZs 3725:2007
8d13ebf2-c851-59c4-a080-d26a23f04334 | note | Verifying Document - IANZ Lab Test Report
47c52222-03ca-5bca-9f75-1b3fe6b0c4d4 | note | Frequency - Based on Undercut Section
507d4938-94a6-502d-afe4-0bc4c2c053a5 | note | Verification Activity: Activity - H
d361f2fd-1e2f-54d4-81bf-58dd73585322 | note | Verification Activity: By - QE
7f95d084-870c-4eed-ba49-8faabc22b233 | checkpoint | 3.1.3 - Bedding Compaction Testing
0103705a-c541-5a76-808b-1f352be3bccb | note | Acceptance / Conformance Criteria - NDM Back Scatter
3f864571-6d2e-580c-98d8-77f584344954 | note | ○ Minimum Compaction 95%(Average98%) of MDD
6bd402cb-dd52-5e38-91e3-759c5f63a656 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD
2d67a0df-5c25-5263-b410-5daed68e78d8 | note | ○ AS/NZS 2566.2/2002
cc708f24-02f4-5a47-98a4-d2152011d148 | note | Verifying Document - IANZ Lab Test Report
c82df032-4bb0-51c1-898b-356b9719048a | note | Frequency - Every 20m along trench
39cf982c-6729-577b-8b39-2395ff3818b8 | note | ○ 1 test every 5m² at driveways and footpaths
6a2671c7-77d2-51e5-b935-c36e630dacf2 | note | Verification Activity: Activity - H
e36b23fd-a61d-5a18-9fe3-158f28ca21e5 | note | Verification Activity: By - QE
393f7353-164f-4cb7-a8cd-882d4162a024 | checkpoint | 3.1.5 - Overlay Compaction Testing - Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
aab9ca39-5555-5a44-bb21-a6a60ddef38b | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm
df16f8f1-5605-58ea-b812-9316ab6efe51 | note | ○ Minimum Compaction 92% of MDD
0913efb7-a4af-5eaa-99c4-b5c1bf89976d | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD
14382105-f15f-58d7-9798-00d0df4e269a | note | ○ AS/NZS 3725:2007
3a9a59f1-d49b-5d36-9b34-ba06074f51c6 | note | Verifying Document - IANZ Lab Test Report
36a3ec45-e696-58d7-9498-e603e4ef6b97 | note | Frequency - Every 20m along trench
8f5ac71a-3883-5dae-ab7b-cd2f670a3da3 | note | ○ 1 test every 5m² at driveways and footpaths
ae60f3fb-7b7b-5434-a313-05b929eae640 | note | Verification Activity: Activity - H
a09f8926-9c98-5152-819c-c521942047c6 | note | Verification Activity: By - QE
b3f7eb01-ea80-4d95-8c01-853c65a1b69f | checkpoint | 3.1.6 - Collection of Waipa ITPs
ece1e485-b8aa-5b64-a415-e8da00091e6e | note | Acceptance / Conformance Criteria - ITP 04 Butt Welding
348a059a-f91b-58fb-9dcb-35dfefe91db8 | note | Standard / Specification - PWRBSS Quality Management Plan
94e87303-50e4-59a4-81eb-83646a768a6e | note | Verifying Document - Document Review
695c28de-20bf-5ae5-9ff1-ec56e1a0f7e1 | note | Frequency - Once
beba5da6-2bf8-516d-9e15-96c80a874365 | note | Verification Activity: Activity - HP
791fd6e9-055e-599f-a5e1-0e3eae12561d | note | Verification Activity: By - ENG
e19b7072-eec5-4898-9c84-7078bf1ebaeb | signoff | AUTHORITY HOLDPOINT
70825302-71ce-4bfc-a84c-1813935e63ae | checkpoint | 3.1.7 - Backfill Inspection
3a0d14fa-8a79-56e5-94fd-31821b94d919 | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation. No damages caused to the pipeline.
2be88f09-88fb-525a-b843-e11bf5e5b4a6 | note | Standard / Specification - Project Specification 4.3
9f880966-f001-5aee-a06e-4011edf20ac9 | note | Verifying Document - Photographs
a56255b4-0078-5471-9455-9297bdce341c | note | Frequency - Continous
9befc712-fd9f-51e9-b40c-90a2b163a885 | note | Verification Activity: Activity - S
698da5b0-b282-5ff4-b1cc-59542cba8ee3 | note | Verification Activity: By - PE
1f35e240-b1b0-44a0-b683-60b0a6ee7a17 | checkpoint | 3.1.8 - Survey
2debec50-321c-5c42-8397-95c742015497 | note | Acceptance / Conformance Criteria - All wastewater lines shall be laid per design layout. The deviation from approved design alignment permitted either in plan or elevation shall be:
fdbf7379-ffc8-5864-91d5-39aab890d7c1 | note | ○ Vertical tolerance ± 50mm on straight and 100mm in curves
ba4a551e-5a13-5038-a286-4f65a5e3226a | note | Standard / Specification - Vertical tolerance +/- 50mm
8390bc5b-2958-5dc5-9dda-53e74b1cbbd0 | note | ○ Horizontal +/- 100mm
ac90192f-0f95-5741-80fb-1178eccf1fac | note | Verifying Document - Survey Data
49c703b1-3194-5ddf-9216-075861e29824 | note | Frequency - Continous
0aa643da-9715-5163-aedd-78c3f45fb247 | note | Verification Activity: Activity - C
b94f483e-712d-5253-b85e-7712c898f0c7 | note | Verification Activity: By - SV
61b0e0a1-7ef9-4c0e-acf4-a4ae73ae6dc0 | checkpoint | 3.1.9 - Backfill Compaction Testing
48356dd8-47f6-51b1-9b5d-e8a408ea2db6 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm
1869700f-9fd5-59ae-ad97-1cac0cbea2c7 | note | ○ Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC
d6af6476-67f6-58cc-925c-6ccf76e8dd03 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD
d358a8a7-33f3-5135-94cb-31ef8ff8a63b | note | ○ AS/NZS 2566.2/2002
ff24e590-5545-5ac2-9d65-6fecfe95820f | note | Verifying Document - IANZ Lab Test Report
0872ae35-4eb9-5f3c-9a83-8b8850be856c | note | Frequency - Every 20m along trench
6dd6be41-e7eb-5b41-8644-4fbfd913d250 | note | ○ 1 test every 5m² at driveways and footpaths
76f7d514-fb39-5838-a8ff-4863f1148650 | note | Verification Activity: Activity - H
067863d9-4083-50ed-839f-d6869dc7e8bc | note | Verification Activity: By - QE
4bcb429c-a0e4-490b-b99c-b15c4c212648 | checkpoint | 3.1.10 - End Caps
f9fb7bbe-e875-5ae4-827c-2da5ff5c749f | note | Acceptance / Conformance Criteria - Red-painted sealed end per RITS D5.4.
8112e8c8-3cc4-5b33-b600-28f92c4f1b7b | note | Standard / Specification - RITS D5.4
5818a72c-8d32-56b3-972b-a2a4d04604d3 | note | Verifying Document - Photographs
9e5081af-8482-59e8-9ee7-0eb55b9d20d0 | note | Frequency - Each End Cap
81fb03c3-e1d9-5dc7-a46d-abb7aaa41ee5 | note | Verification Activity: Activity - S
3d00bb91-ef7b-58db-be8b-8310abcc8db7 | note | Verification Activity: By - PE
5df501e6-968c-4e32-b92f-a44d270299a6 | checkpoint | 3.2.1 - Manhole Foundation Compliance
33f78455-9826-5840-99a1-2f666861cffb | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm
a678d5d6-2b8a-52b1-9e96-573933e81c1a | note | ○ Cohesive Material: Vane Shear Strength 70kPa
2b713e6d-702f-514d-ad05-416c0c481ec0 | note | Standard / Specification - Project Specification 4.3
06b76edc-4705-58a2-b446-d51ef91adbb4 | note | Verifying Document - IANZ Scala test result
06c91bf0-aad0-5780-8ed4-0d0ef94f0eb9 | note | Frequency - 1 Test/Manhole
dfbffcba-aecd-5882-a046-787fc9e2c53d | note | Verification Activity: Activity - H
39101090-bb48-5e0a-9391-be3900f985a5 | note | Verification Activity: By - QE
a767cee1-7cf4-4832-b667-e5ea5d06eab1 | checkpoint | 3.2.2 - Undercut Backfill Compliance
8fb19620-71bf-5c17-888e-07e5c1faedd9 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm
9995078e-8142-5424-954b-4e9336f5c1c4 | note | ○ Minimum Compaction 95% of MDD
13ca01c4-098a-5b62-b9ca-5d03e5f22b46 | note | Standard / Specification - HS2 backfil Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD
892cf77f-f829-53bb-9bdb-b392afa84d60 | note | ○ AS/NZS 3725:2012
dbf57eda-0d50-5535-bd4d-89faa199a8de | note | Verifying Document - IANZ Lab Test Report
da3bf3c8-7cff-54a2-ae4e-a5bd80220047 | note | Frequency - 1 Test/Manhole if Undercut required
b3e18acd-2adc-56bb-be00-7694cb7e3f66 | note | Verification Activity: Activity - H
dbc5cc49-af8f-5ebc-ad7e-2358bf683944 | note | Verification Activity: By - QE
a73f421d-933f-4ea3-9c33-cfdc1b4391bf | checkpoint | 3.2.3 - Bedding Compaction Testing
b1439eaa-7bac-59a2-adaa-0c02ebc05b47 | note | Acceptance / Conformance Criteria - NDM Back Scatter
66582e6d-4f66-5ac0-b9c1-27de19544eff | note | ○ Minimum Compaction 95% of MDD
800c0b06-e185-56ab-a397-fa1561b2045d | note | Standard / Specification - HS2 backfil Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD
59864ed2-0b5a-5d97-bba9-b9232b6db99f | note | ○ AS/NZS 3725:2012
a7229e58-fb34-5e88-b311-8f8610059c45 | note | Verifying Document - IANZ Lab Test Report
27ece894-e1c3-5aca-ae27-30f0a3f3e4f3 | note | Frequency - 1 Test/Manhole
08f2a1e5-8c04-5a99-b995-97bcfcfb2bd0 | note | Verification Activity: Activity - H
149ffa98-f541-5bec-b44a-ca7400669c8d | note | Verification Activity: By - QE
8543d836-efca-47e0-92e9-c3423fda8213 | checkpoint | 3.2.4 - Backfill Inspection
3e941499-b26e-5d4e-92b9-979a6feb0167 | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the manhole
5add0c10-5e0f-507c-92fa-0d76be05f770 | note | Standard / Specification - Project Specification 4.3
f6e15a72-74e7-58a9-b5b4-9b0a4e008140 | note | Verifying Document - Photographs
6a9e809e-a582-5a60-9765-7fc462eb1711 | note | Frequency - Continous
50f7f00a-b2cc-5ee5-a549-2c2f383307bc | note | Verification Activity: Activity - S
1190d7fa-20c7-55dd-aa85-b1d0f076f630 | note | Verification Activity: By - PE
97b4c7a6-4649-43b7-a470-faa13f0ab737 | checkpoint | 3.2.5 - Backfill Testing
174079b1-ec0d-5fdb-9506-bfa703bd2275 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm
6f8896f3-7a12-5086-9ac8-ba9d630fd18b | note | ○ Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC.
cb80232f-da07-5cdf-810a-7ee2f522ebfe | note | ○ Minimum Compaction 95% (Average 98%) of MDD
90fc0a94-09b5-5722-abdd-6de523143128 | note | Standard / Specification - MDD Average of 98% with minimum of 95%, PS 4.5
40fed417-c50b-5f36-8009-458c24f15028 | note | Verifying Document - IANZ Lab Test Report
106c26e5-9056-584c-843e-ec2d6ee04361 | note | Frequency - 4 Density tests per layer at Quarter Points Around Structure
08ed4d3b-1a3a-56dd-a6af-41cab92cf519 | note | Verification Activity: Activity - H
7675d06e-7b2a-57d6-87f9-81dd3fe64e58 | note | Verification Activity: By - QE
dc41e3c3-68e2-4502-8b41-9bcf6b862e29 | checkpoint | 3.2.6 - Concrete Load Distribution Ring
0a483c15-ee22-5408-a385-87ff3890099e | note | Acceptance / Conformance Criteria - Installed per manufacturers requirements.
ea1964b2-833e-55e5-8157-24c20c4aea99 | note | Standard / Specification - BBO Request
bca504f4-81f4-513c-b80d-61ef23956028 | note | Verifying Document - Photographs
fbb79f75-cc57-520e-8643-4ad72b0bfc2e | note | Frequency - Each romold manhole
56663a83-42d4-55f6-ad52-52ec84888101 | note | Verification Activity: Activity - S
9a28d154-ae11-51f1-ab06-a0c055ea1b08 | note | Verification Activity: By - PE
5f43b102-b3e9-4e06-9de0-1213af0030d3 | checkpoint | 3.3.1 - Pressure Testing Methodology
57990fe6-2750-54b8-98bf-2300191d6a11 | note | Acceptance / Conformance Criteria - Subcontractor to submit to method statement prior to testing.
236028ba-0c7f-5a82-a130-a71bd9a500d3 | note | Standard / Specification - PS Appendix L 3.10
20b1b1fb-55e6-5741-8624-548c00eed443 | note | Verifying Document - Engineer's confirmation of witness test
1f2efc0d-d9c7-54eb-b011-afada889d681 | note | Frequency - Notification required 2 working days prior to testing
b9da16db-e9dd-5827-9880-d7f9edb6dcdb | note | Verification Activity: Activity - H
0e7d6c37-4d98-55ff-98fc-56dc7a7b2c84 | note | Verification Activity: By - ENG
1ffae514-5118-45da-9df2-9002b9c66d64 | checkpoint | 3.3.2 - Pressure Testing Qualification
28cda046-f2e5-51d4-b815-68b761562df0 | note | Acceptance / Conformance Criteria - Confirmation of qualification of personnel supervising the test.
6834f8fb-3a63-51f4-96cd-cd73066f3345 | note | Standard / Specification - PS Appendix L 3.10.3
f94a94d1-1c5b-54f6-b9e2-7f187b30b865 | note | Verifying Document - Qualification
99ab69be-12b6-50ef-8a6d-3db481ae992a | note | Frequency - Once per supervisor
a607133b-bce4-5bff-8bf7-60b3ef2e3d58 | note | Verification Activity: Activity - S
8bab25f5-e285-586a-a9f0-16742ebe1f9f | note | Verification Activity: By - PE
7215e341-906e-4cbf-98b3-0a6340a0da23 | checkpoint | 3.3.3 - PE Pipeline Pressure Test
4113a64e-1725-54dc-b0af-7f16d5a4ca25 | note | Acceptance / Conformance Criteria - Unless otherwise specified and approved with line-specific methodolfy (i.e. Pressuremain 04 and 03).
4c70af7b-8653-5220-a5ca-cc3fccd99181 | note | ○ Testing to be undertaken on completion of invasive/major works.
bc81996c-f6e2-598b-be74-966f5c64e56b | note | ○ M5 per NZS 2566.2, test pressure 1.25x lowest rated component.
545f90cf-386e-5143-a493-beb4090fcda1 | note | Standard / Specification - PS Appendix L 3.10.10 (RFI-0268)
fb0d24c0-eb62-5ff5-897f-e49a1b5817ff | note | Verifying Document - Pressure Test Report incl. data log in .csv or .xls format
e304105a-8a37-5c42-b3dd-ee8b21a91ee5 | note | Frequency - Per methodology
7ed09bc4-9a94-57ca-a19f-a9212c3d06cf | note | Verification Activity: Activity - H
7ff35e2a-1d0e-5459-ac6a-ecc762e1dd4a | note | Verification Activity: By - ENG
270cf86d-dcf6-4ae8-86bd-eb1f109b457c | checkpoint | 3.3.4 - Romold Manhole
bb7aaf0c-55fe-41fd-93c6-b260952a9382 | section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
4c47f7de-04d6-4249-b634-0430ffd7d109 | checkpoint | 4.1 - Unforeseen Items
08286f57-6faf-536f-a4dd-20ca028e85be | note | Acceptance / Conformance Criteria - Upload items which may not be captured appropriately above (i.e. EF Coupler Installation)
72b6c461-1289-50b4-94a8-44efcfff8679 | note | Standard / Specification - BBO Request
df9b358e-81d7-586a-bb3b-a30745adf20e | note | Verifying Document - Misc.
34376842-6fdc-5651-a216-4058b8568c42 | note | Frequency - Once per lot
238b3c0e-9947-592e-9cac-b92cc4da692d | note | Verification Activity: Activity - C
b9db2ac7-146e-5be9-9abb-e6eeb82f2041 | note | Verification Activity: By - PE
2fae5bcd-e8a8-4c87-88b6-a1fdfd4a8042 | checkpoint | 4.2 - Survey As-Builts
cb0fc962-5c56-5094-8b47-d5dfd6ef9260 | note | Acceptance / Conformance Criteria - Quality Check on New Works
fa425e8b-beff-5205-865f-47cf9acafb9d | note | Standard / Specification - Project Specification
310fc6d8-9613-575c-af81-9d2c69ae5e65 | note | Verifying Document - Survey Data
4eb9108f-57a9-5e2a-9923-48d5dac30ff1 | note | ○ As Built Drawings
df785beb-0283-5f4e-8e1e-f9a54591768a | note | ○ Photographs
d36ba515-3810-5090-ae95-52b301e865cb | note | ○ Red Pen As-Builts including Undercuts
26b18dcc-6f81-5cf5-ae5e-994160748440 | note | Frequency - Post Works Completion
ff61c8e4-1dad-5961-8caf-27b0a93e0ca0 | note | Verification Activity: Activity - H
a87889c5-6190-5a98-84ab-ecd4614d45e2 | note | Verification Activity: By - SV
33447f0c-a3d4-4aed-9206-29596a02942a | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
e1cd0437-ad65-5f53-8bd0-48d6d9cfd8ff | textbox | Contractor's Rep Name:
b656acf9-a794-5207-9c78-4195804703b7 | textbox | Engineer's Rep. Name:
4f06e8dd-c963-5869-af0d-cd212399f498 | date | Date:
7cc7f1d9-f91e-4b6d-bb21-3cae62da66e4 | signoff | Add Signature
076ba72b-fc42-5b3f-9a79-28a5b1e4e761 | checklist | ITP - 112 - Subsoil Drains Rev D | itp | ITP - 112 - Subsoil Drains Rev D
8c9335a7-3af5-5e47-a887-39a89ff08c27 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
6d2cb710-72cd-5df2-b3e9-73a49140a940 | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
91f28c74-e362-5849-8002-f4ae9c4468f0 | note | Standard / Specification - Downer
fd3e92cd-56d8-53bf-9ee1-0f157b79b9f5 | note | Verifying Document - Construction Pack
0ce126c2-ee88-5685-b03b-927c031c9060 | note | Frequency - Submit 10 days prior to commencement of works
b7b8c36d-a69c-55c2-b0fe-b116e8062c86 | note | Verification Activity: Activity - H
b4d48579-5db8-5887-bbd5-9af55cd14e81 | note | Verification Activity: By - PE
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
8514ab2c-cfe0-55fb-8786-674ddb1be46e | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
cc237e96-8ba8-5dfb-8137-6f250cacafb7 | note | Standard / Specification - Downer
dc52ec28-8f2e-5d5b-b028-32615db95ba8 | note | Verifying Document - Survey Records
2b88c3e5-8b7d-5041-bc40-8a64a72a2744 | note | Frequency - Prior to Works
7e8c8d26-e01c-5535-8524-f0f4fab0ae07 | note | Verification Activity: Activity - H
bdd9c68e-427f-5877-9c5f-536bad321990 | note | Verification Activity: By - SV
7b8b4071-ba18-54c4-a07c-9e192aec85d8 | checkpoint | 3.01.03 - Approved Construction Drawings
089c71b2-78a0-5832-8f98-0f4b65eda720 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
73ee12db-c958-5022-ae01-e60aa9b1e726 | note | Standard / Specification - Downer
bf3db28b-0b3d-59c4-8154-a5c95e7e27ac | note | Verifying Document - IFC Drawings
dbbc866e-098f-5006-a899-21bccd35999a | note | Frequency - Prior to works start
3b36a6be-0b05-5256-884a-d7343a017833 | note | Verification Activity: Activity - H
61ce0c6c-56ef-5f9e-901b-bc4ea60796cc | note | Verification Activity: By - PE
f54e7b48-3f2b-51d6-93b0-54755388f0cc | checkpoint | 3.01.04 - Topographic surveys for measurement
95040f2e-bcb8-522e-a629-ace59946039e | note | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
ee453a3b-3438-59ca-8f57-a55b1e8319c1 | note | Standard / Specification - PS 2.2.12
3cdbdc0f-ef12-571e-85a5-9e3cfa7b0c51 | note | Verifying Document - As-built
22735181-5cd1-5969-9fa8-c6f847bc8d3b | note | Frequency - Prior to works and Post Works
bf316beb-d352-5434-a2e2-60d4d4e09e9c | note | Verification Activity: Activity - H
690358d1-9707-5026-98c8-3ddef963b02b | note | Verification Activity: By - PE
f26fef48-d615-5889-ba64-e206f54c0d34 | checkpoint | 3.01.05 - Permits
8860f217-92be-5652-9437-05b98c40158f | note | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
9eb1e80f-921a-5448-999b-be5f51d1c52a | note | Standard / Specification - ITP Register
b587299c-4645-5da3-8880-0bc0f7d40862 | note | Verifying Document - ITP Sign Off
fa201e1f-08ca-5309-be48-8c7a6da0890c | note | Frequency - Prior to commencement of construction activity
fa017440-57f4-55f3-b3ad-4cac130943a3 | note | Verification Activity: Activity - R
eea69e6b-019e-5144-a2da-6bdd1088d3b4 | note | Verification Activity: By - SE
72a761a8-8bee-5916-91e9-a2f4ef42bc73 | checkpoint | 3.01.06 - Stakeholder Management
356df781-caef-5fbc-b34b-b0e863194f23 | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works
1967110f-ee03-505a-9b98-288ab8cb6a44 | note | ○ Agree plans for maintaining access to properties during construction with landowners
4e253cc6-5278-5d95-aa37-c3932340657a | note | Standard / Specification - Project Stakeholder Management Plan
b57b533d-7d88-5858-a56d-e7d05f12ee86 | note | Verifying Document - ITP Sign Off
757e1648-e739-590f-a6b5-59fb76adf3f0 | note | Frequency - Prior to Construction with continue updates throughout the works
b0a6dadb-0e1a-5aa1-8e35-8a846a9c6f28 | note | Verification Activity: Activity - R
a8bfe4f5-0656-5a4e-80a7-603b24b96f1a | note | Verification Activity: By - SE
8ec62109-1664-5fbd-8086-47c125cee66d | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
08534115-94ee-5cfc-be8c-086ea7ffdd06 | checkpoint | 4.01.01 - Subsoil Pipes
da810d94-d7cb-5284-a869-520fef6574be | note | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 160mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
570eddb5-7f95-5e84-b667-19b65668f688 | note | Standard / Specification - GWS 3.2.1
c1a97014-5e0c-54ea-bb13-7987af2a3d77 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
a4ed756c-0bf9-5819-9d29-492b79f5d417 | note | Frequency - Every Delievery to Site
e4f8e7f4-7a7b-532b-8cc5-29bfa4522d33 | note | Verification Activity: Activity - C
44c9bfc2-61ea-5fcb-8b39-4318245eb6d0 | note | Verification Activity: By - SE
71011ef5-31e0-5d97-b246-1d11311696c1 | checkpoint | 4.01.02 - Subsoil Drainage Aggregate
16c3e251-e06b-5881-8040-a4785d91fc7a | note | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/6 including gradings (40/20 aggregate). Be open course grade clean durable aggregate, Have a crushing resistance of no less than 100kN when tested in accordance with NZS 4407:1991 Test 3.11 Meet the following gradings when tested in accordance with NZS 4407:1991, Test 3.8.1:
9077a9e0-af21-56b5-bb8b-6640f9316153 | note | ○ App B - HAM2018-0136AJ Rev. 1 Geotechnical Works Specification:
6aa6d767-ebfb-5f1a-a293-78b8b87511f7 | note | ○ Table 2: Filter Material Gradings (Geotextile Wrapped Aggregate)
af7435e5-9b63-553a-8100-37d7591450b8 | note | ○ Test Sieve Aperture (mm) Percentage Passing (%)
0c045990-07b1-5cbb-bb4b-59c879115bc2 | note | ○ 53 100
bdaf19f5-b80e-5600-8556-9fe599a16cae | note | ○ 13.2 10 (max)
958cdcac-1d33-598c-bdee-1145e42dcdba | note | Standard / Specification - GWS 3.2.2 & 3.4
2ffb94b1-f5d7-58fe-9c7b-ff8b26e5a3c4 | note | Verifying Document - PSD, CR
27a7f7e5-ad5d-5fa8-885d-2633efadc0ad | note | Frequency - Material Tests every 1000m³ or change of source. Visual inspection every load, verifying document photos of material onsite, if visual appearance changes, additional testing will be required.
ccb00f54-e4e5-5a74-9dba-af026a8bbc2c | note | Verification Activity: Activity - C
1b2bd01b-af2e-5c13-8f6e-bf74643d9f61 | note | Verification Activity: By - SE
6d7192d6-9061-5d38-a315-d4a8752b3fa5 | checkpoint | 4.01.03 - Filter Cloth
29f7d05c-7477-58ab-92dd-52027ff1d229 | note | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings. (A14 Bidim or Equivalent)
b87a2879-3a9d-5cf5-9f28-e6a5ef163ac6 | note | Standard / Specification - GWS 3.2.3
67d13fa6-77d2-57d5-a269-72c095e8dd1f | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
6bbc0e7b-9d7f-5805-b694-7f6935c9d64d | note | Frequency - Every Delievery to Site
af3aeb56-d2da-58ae-a8e2-58806563e24d | note | Verification Activity: Activity - C
9b0b06e6-c8c1-5a40-9fba-db1da3b970ee | note | Verification Activity: By - SE
34efbf28-65bc-5d1f-b72b-f1491def807a | checkpoint | 4.01.04 - Securing Pins
9bed9f26-3e9b-5d86-abd9-5966575ce24c | note | Acceptance / Conformance Criteria - Pins for securing the geotextile shall be of steel, a minimum of 5mm in diameter and atleast 400mm in length
8c019ab4-a71e-5407-803a-b2367729bde5 | note | Standard / Specification -
ac82b453-0f01-51ce-aab4-98edd9c052e9 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class,.
f6635755-eaad-51a5-a971-c9fa250ea516 | note | Frequency - Every Delievery to Site
16c20365-cfc1-5be6-b5ee-7db34c83884b | note | Verification Activity: Activity - C
92bb85c2-4712-55d6-9e59-814032360d7e | note | Verification Activity: By - SE
f4713bb7-3aea-5dca-b516-69272c0b56ba | section | SECTION 5 – CONSTRUCTION ACTIVITY
113d79bf-1485-508d-814d-8c7c8c221530 | checkpoint | 5.01.01 - Filter Cloth Wrap Inspection
f2c7305f-d10e-5f6f-95c7-3590c0c8f7c3 | note | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain. TNZ F/6, PWRBSS Geotechnical Specification - The geotextile shall be placed in the tench so as to conform loosely to the shape of the trench. Cloth must fully encapsulate the aggregate. Geotextile longitudinal overlap to be minimum 300 mm (as indicated on drawing 3051 and required by NZTA F/6). Additional sheets to overlap by minimum 500 mm and anchored with securing pins (F/6 requirement). Verifying document, photos of trench prior to backfill, every line.
c8c23375-c309-5565-9b16-d0f323b1cc22 | note | Standard / Specification - GWS 3.2.2
a9f54cf3-45a4-5695-8eea-b6c069a55f18 | note | Verifying Document - Every line
7f69537e-373e-5123-ba29-a117205054ab | note | Frequency - Photos of trench prior to backfill
119275bc-f375-58a7-96c3-286420509ebb | note | Verification Activity: Activity - HP
b8731aaf-6c65-5b11-8439-574ad828f5d2 | note | Verification Activity: By - ENG
a2a25648-08b8-5ac9-b1a6-269e329744a0 | signoff | AUTHORITY HOLDPOINT
543c766a-67a1-5508-b12a-a4f69b9927f3 | checkpoint | 5.01.02 - Trench Backfill
041155eb-b426-59e1-9bc3-22bcd3e9bd5d | note | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard of the material previously trenched through. Drainage aggregate to be placed in layers of 150mm or less. Only light compaction such as tamping with the back of an excavator bucket is to be applied.
aee77156-3bb9-58f5-8c3a-a8a48b9ad021 | note | Standard / Specification - GWS 3.3
1202ad48-2ebe-526f-94d1-51b98d82bda2 | note | Verifying Document - Site Record
666e2a3b-fe29-56cb-a856-3a72bb07d7e1 | note | Frequency - Each trench
ec31424d-e07d-55de-9ff2-df6294bfbd7c | note | Verification Activity: Activity - I
17517802-e38b-53cd-9336-c3e2d2e5de9e | note | Verification Activity: By - SE
f7142f9b-2009-59fd-9453-67a19dd7865a | checkpoint | 5.01.03 - Drainage Outlets and Inspection Points
5b6474e9-a18a-5e30-9244-a51c96cc8e50 | note | Acceptance / Conformance Criteria - At least one temporary flush point is required for each subsoil drainage system to enable flushing of the system once the earthworks are complete.
90ee52cd-8c64-5a3d-a82f-6d0dc6276d4a | note | Standard / Specification - GWS 3.6
db88c4cc-0ee9-5b56-ba4e-6e434385382d | note | Verifying Document - Site Records
78353753-065d-50b7-9b3a-49b982808ffe | note | Frequency - Each Subsoil Line
cb1084a7-3a16-52c0-a25d-b3bf32880b2d | note | Verification Activity: Activity - I
f84a8ca7-9317-56a6-bc98-67bc52c17bb4 | note | Verification Activity: By - SE
fd83d42b-b8ea-5d41-8883-9e6215d99eea | checkpoint | 5.01.04 - Subsoil Flushing
9b567b98-281a-5352-bb76-69632d74996c | note | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer.
2160f3eb-da5a-5752-ba5f-7256119bd2b4 | note | Standard / Specification - GWS 3.6
a527da54-fb01-5e84-a5c2-01c613ab943a | note | Verifying Document - Site Records
f0d1caa8-1b26-5978-ae07-c4c74268de4a | note | Frequency - On completion of earthworks
1abae4a6-5f93-572a-b376-b1603f97ad79 | note | Verification Activity: Activity - HP
5f111d56-e431-5fdb-96f7-ac290d94bd02 | note | Verification Activity: By - ENG
efdabe6e-46f6-51c4-9707-34eb23acdd0d | signoff | AUTHORITY HOLDPOINT
65ee871c-3fae-5bef-8ed1-f015a6f0c4aa | checkpoint | 5.01.05 - Survey
445d3448-6846-52fb-8849-fd2441d881f1 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
c238e955-ca60-5db8-8693-f1fccefffe3c | note | Standard / Specification - Downer
8a8e5e7b-1f8e-5362-92e9-4561fbd69bde | note | Verifying Document - Records
c198bea4-1c96-5cf5-882f-9160c8421b12 | note | Frequency - Post construction
62170eaf-ad41-5763-aaa2-27d21853303d | note | Verification Activity: Activity - H
45f29599-e0a4-5440-9c7b-71c11a4a70e7 | note | Verification Activity: By - SV
f999ffd9-5367-57d7-994f-8ff2006b1339 | checkpoint | 5.01.06 - Excavation
09196edd-397f-50f9-ae5e-61c69e7f0fbc | note | Acceptance / Conformance Criteria - Trenches shall be cut in such manner as will ensure that the geotextile wrapped aggregate subsoil drains, and pipes if included, will be laid true to the depths, grades and lines shown on the drawings
6ca0d273-002c-5ba0-8ad1-333c6b66b8ae | note | Standard / Specification - Downer
4b1c8736-bbd3-58f0-932f-e05dd46a91c9 | note | Verifying Document - Records
8679490c-754d-5963-8f57-6c67c9b491fc | note | Frequency - Prior to laying filter cloth
3d94d594-7523-5e78-b39b-c16997211ef3 | note | Verification Activity: Activity - I
1784a8b8-56be-5a8b-a4b5-3bbf807dad17 | note | Verification Activity: By - SE
78b40005-4535-58a0-8f12-10ce7328ed62 | checkpoint | 5.01.07 - Bedding
17015693-0f2e-5640-bfc9-600a6d931188 | note | Acceptance / Conformance Criteria - TNZ F/5 - Bedding thickness shall be no less than 100mm
7c4d64dd-9bcf-5044-ac7a-6e8db34b88b8 | note | Standard / Specification - TNZ F/5
4d7ee658-537d-5020-a93d-8fdae26c5fcd | note | Verifying Document - Records
aa4e887a-3065-5968-9410-246174a62493 | note | Frequency - Prior to laying Novacoil
847176d3-115c-5665-92f1-e0751c00537c | note | Verification Activity: Activity - I
5117ddec-08b9-577c-a4fe-bb33e6123328 | note | Verification Activity: By - SE
bc02362a-9ac4-5773-899f-55a42641ec6b | checkpoint | 5.01.08 - Joining Pipes
3d53585f-ff18-58f7-9a3e-96a1c110f9fc | note | Acceptance / Conformance Criteria - TNZ F/5 - Joining the pipe shall be done using a purpose made pullout resistant coupling in accordance with manufacturers recommendations
b3a3edec-fc50-55fd-8611-c33ebbf02f81 | note | Standard / Specification - TNZ F/5
d8816b27-5e6f-5c07-8363-6868a38e5070 | note | Verifying Document - Copy of delivery dockets, photos of pipes onsite with tag showing class
5f443a7d-6e1d-5e18-b9cf-19eee81b4589 | note | Frequency - Every join
0c99cbdf-fb62-550b-b635-cd2f10346ebd | note | Verification Activity: Activity - I
6195fdff-e7c6-5f02-b8cd-dc5cca5bb6fb | note | Verification Activity: By - SE
2f363a55-4436-5df3-bb16-03fb4412a91e | checkpoint | 5.01.09 - Pipe Grade
79bed3cb-f761-5926-937a-c0f089bab383 | note | Acceptance / Conformance Criteria - Grade of subsoils must be falling in the correct direction based on the IFC Drawings and at the correct grade (greater than 1% based on TNZ F/5)
9709ef60-5f90-5e83-bcae-327ee5cbad42 | note | Standard / Specification - TNZ F/5
c046403a-2e19-5d38-9fb1-31ec5335fa24 | note | Verifying Document - AsBuilt
a7003428-7741-524c-94bc-4b7acfbeff6a | note | Frequency - Every 10m
240970bf-3541-54a0-bdf1-46ef34967832 | note | Verification Activity: Activity - H
c900571e-45bc-592d-9733-928edae0bc34 | note | Verification Activity: By - SV
d6784725-7b39-59f1-a161-bb35735b619c | checkpoint | 5.01.10 - Pipe Cover
f8323c79-4b2f-5a26-a1ea-92ecbbb426c8 | note | Acceptance / Conformance Criteria - Drainage aggregate must be placed till -0.1m from Top of SIL and verified by surveyor
5fc8ad30-3755-5b29-b2c7-a263f7277b93 | note | Standard / Specification - N/A
a67f5dd0-1db3-5005-b548-307e442ab690 | note | Verifying Document - Site Record
aca1bb03-105b-56fc-a4e1-f5644c5a8dec | note | Frequency - Every 10m
b43d1077-0a18-52cb-a528-fa62ca673b06 | note | Verification Activity: Activity - H
9dd087ae-d52d-5a40-b248-3279347d6fa2 | note | Verification Activity: By - SV
cd33a7f8-9b6c-5422-93be-dcae98eaa460 | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
abaa7cc7-67ff-52ad-ae9f-e9176b336a01 | checkpoint | 6.01.01 - Construction Record Compilation
28a769aa-0457-5acf-9c1d-116bd515da84 | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
53f7704f-2829-5f85-b2cf-5e62ca432920 | note | Standard / Specification - Downer
673656b1-000a-52bd-b675-883d1305e243 | note | Verifying Document - Records
7ef7e0a4-077e-5ad1-bbe0-e993c7ad6fce | note | Frequency - Post construction
a99883c3-9a96-5029-877e-a1fe86a64ec6 | note | Verification Activity: Activity - H
efe21c4e-3c41-506c-a0f9-adba5ccb8342 | note | Verification Activity: By - SE
f4876821-e136-54ca-95e8-27fd0f400f5d | checkpoint | 6.01.02 - Survey Records
46468559-3558-5778-b664-91a2b2a281c9 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
9764471b-4138-5b4f-9fab-5c485580c3a5 | note | Standard / Specification - Downer
d9f2516c-6067-5706-b00c-40d87acf823e | note | Verifying Document - Records
be9f4742-33f4-55e8-b397-155d38d20b25 | note | Frequency - As-builts taken every 10m prior to backfill
cb96a695-ff99-58e4-ae72-255b4a607666 | note | Verification Activity: Activity - H
b5a6f2be-4687-58bb-a88e-bce7b256ed88 | note | Verification Activity: By - SV
a7ece1a0-6b4a-5d51-8813-156cc41a337a | checkpoint | 6.01.03 - Redline Drawings
5c05f607-e492-5a6c-a941-2fbad4887232 | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.To show all subsoils, including temporary subsoils that become part of the permanent works, to show all outlet locations
f5bb4a75-89ca-554d-bb31-994884288c00 | note | Standard / Specification - Downer
7e74c2ff-0bf1-552b-91c8-e1db69862690 | note | Verifying Document - Redlines
f3b498cb-c385-513c-992a-3fe107f4e101 | note | Frequency - Post construction
97b95796-6abc-58cf-aaa9-03013a7d9fa5 | note | Verification Activity: Activity - H
886f22f1-84bd-55a2-b3a2-3fb552224e98 | note | Verification Activity: By - PE
406cc900-58d1-549c-813d-cb4c75c9a2be | checkpoint | 6.01.05 - Photos
748bdeb6-facb-54a1-b9bf-64af40990b0c | note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
5cef6e8e-5830-5084-b687-83fcb4424e3c | note | Standard / Specification - Downer
3bb98567-73f2-50c6-8ad0-8c9da2d40eeb | note | Verifying Document - Photo Records
2f16b406-d193-5c86-bd9a-9e5493c8c1e7 | note | Frequency - Post construction
ebaa79bf-e4bf-5ced-b043-5fa934182c2b | note | Verification Activity: Activity - H
264ce5d5-3d13-5e9a-b5d1-7827956470f9 | note | Verification Activity: By - SE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
1056a9ca-c791-543d-8347-28e4c4457041 | checklist | ITP - 113 - Pavement Drains Rev D | itp | ITP - 113 - Pavement Drains Rev D
8c9335a7-3af5-5e47-a887-39a89ff08c27 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
129692ca-cf9e-50b9-af21-0c2b34571c32 | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JSEA to the Engineer before works
b6344e20-bd3a-582a-bce6-3e7c10ed76da | note | Standard / Specification - Downer
69b7f7e4-cecf-5785-9742-0c0af2af33dd | note | Verifying Document - Construction Pack
cc5bf1b4-eb6d-53bd-bc4e-914a50e1fc9f | note | Frequency - Submit 10 days prior to commencement of works
a8aff456-8946-57d4-93b4-fa78942a7531 | note | Verification Activity: Activity - H
c62b2621-fb70-5afb-ae77-5632968e80e7 | note | Verification Activity: By - PE
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
35384116-3ec2-50c1-8458-9ac359c18590 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
09c0bd6f-614c-5497-9f12-20fb846f6bdb | note | Standard / Specification - Downer
33151928-f942-57c3-af0f-0a90afc76750 | note | Verifying Document - Survey Records
7946d4d2-2dbd-5ef0-a458-303264c36a35 | note | Frequency - Prior to Works
821d29ef-0dab-5a77-8289-ab5abd9b77d7 | note | Verification Activity: Activity - H
55fe4916-25de-59b5-a91f-1daf9916502c | note | Verification Activity: By - SV
7b8b4071-ba18-54c4-a07c-9e192aec85d8 | checkpoint | 3.01.03 - Approved Construction Drawings
329abf24-47ee-5be0-88ac-7bc504bec6c8 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
f6441f94-7842-5987-b483-15c7c99dc726 | note | Standard / Specification - Downer
5017ef42-81d7-5c8e-8fcb-a11cc652703a | note | Verifying Document - IFC Drawings
674221b0-b39b-5e22-a63d-8df46eaeb05d | note | Frequency - Prior to works start
bd74208d-e5cb-5a94-9468-2c1fa7c359ab | note | Verification Activity: Activity - H
983d6148-8cdd-50a9-8c05-4af3928ac7c0 | note | Verification Activity: By - PE
f54e7b48-3f2b-51d6-93b0-54755388f0cc | checkpoint | 3.01.04 - Topographic surveys for measurement
4bba2dad-9dac-5e7d-bed9-b3a23d1ff945 | note | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
b6eb4df6-4ae9-5a66-a229-caab84a97a28 | note | Standard / Specification - PS 2.2.12
5fff2221-99f3-5d5a-af52-3ec12ceb8295 | note | Verifying Document - As-built
0d85a8fc-ad0e-5f7c-9f26-88554e8553ba | note | Frequency - Prior to works and Post Works
4db64b9f-d952-5bbd-9082-e9766dbeef4c | note | Verification Activity: Activity - H
591e153a-7413-5f5e-a1b1-e5358215424d | note | Verification Activity: By - PE
f26fef48-d615-5889-ba64-e206f54c0d34 | checkpoint | 3.01.05 - Permits
1d34652c-effb-5dd3-822b-dca5687f6b26 | note | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
84a74d0a-ca71-515f-81a8-42b8107801fb | note | Standard / Specification - ITP Register
1a2fe970-d7d5-5edc-9045-dbfd5f9c250c | note | Verifying Document - ITP Sign Off
b79d8486-eb9f-57cc-98e3-6f9149480fd4 | note | Frequency - Prior to commencement of construction activity
85182a0a-c00d-5626-9d2a-8780fb0224aa | note | Verification Activity: Activity - R
fb535253-3e9c-5921-b453-981b418a8747 | note | Verification Activity: By - SE
72a761a8-8bee-5916-91e9-a2f4ef42bc73 | checkpoint | 3.01.06 - Stakeholder Management
fba96e04-b4fe-555e-b6b0-867d3f091e01 | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works
59ee5232-ca96-5533-bc46-ce09045aa410 | note | ○ Agree plans for maintaining access to properties during construction with landowners
fe76c5aa-7971-5c7b-8f86-ad8d25d353d0 | note | Standard / Specification - Project Stakeholder Management Plan
77e94b34-6eff-5197-8286-2c2716260add | note | Verifying Document - ITP Sign Off
1bbe9402-ca3a-5a68-81f1-7539d480bbca | note | Frequency - Prior to Construction with continue updates throughout the works
cced4a7e-547f-58e3-8045-09f4b6e00aa4 | note | Verification Activity: Activity - R
ef845f35-4e39-5599-95e7-7312cd4bc049 | note | Verification Activity: By - SE
8ec62109-1664-5fbd-8086-47c125cee66d | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
82f0a14a-336d-5d73-b35b-b775632e4a93 | checkpoint | 4.01.01 - Pavement Pipes
5c1b00b1-1108-5697-9ddf-94c0defd2680 | note | Acceptance / Conformance Criteria - Drainage pipes used in Pavement drainage shall be smooth bore perforated corrugated 110mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
c315dc98-de06-514a-bbe2-fb6e76959206 | note | Standard / Specification - GWS 3.2.1
6ddc05a8-243a-583b-aae3-6faaf39b590f | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
46e31382-14ea-55ce-88c5-8149071fa687 | note | Frequency - Every Delievery to Site
eba14c63-29f3-58ad-8d43-7675029a87f1 | note | Verification Activity: Activity - C
56182f11-7fcd-5808-a487-6a1afd0d3414 | note | Verification Activity: By - SE
fe620841-eb84-5798-9ad3-a857c3f54c90 | checkpoint | 4.01.02 - Pavement Drainage Aggregate
5036878c-b80c-585a-a650-22b620c53f30 | note | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/6 including gradings (40/20 aggregate). Be open course grade clean durable aggregate, Have a crushing resistance of no less than 100kN when tested in accordance with NZS 4407:1991 Test 3.11 Meet the following gradings when tested in accordance with NZS 4407:1991, Test 3.8.1:
a54c52d1-82ca-58cd-96ca-3e727119c60f | note | ○ App B - HAM2018-0136AJ Rev. 1 Geotechnical Works Specification:
c46d8dab-f59d-5d75-8375-b9d91d152f33 | note | ○ Table 2: Filter Material Gradings (Geotextile Wrapped Aggregate)
b48908bc-9c13-598a-b80f-fe840384e770 | note | ○ Test Sieve Aperture (mm) Percentage Passing (%)
62540440-4f8a-514e-ad58-f952271044b3 | note | ○ 53 100
ff4297a3-e0f0-5f6d-9d2d-6df78fec5137 | note | ○ 13.2 10 (max)
dae2326e-918a-57ea-839b-b2390c9c0d1c | note | Standard / Specification - GWS 3.2.2 & 3.4
e01bab2d-ec09-548b-9126-8de8ab29ab42 | note | Verifying Document - PSD, CR
35e3fa41-f23c-57a5-bc17-eea7660d143b | note | Frequency - Material Tests every 1000m³ or change of source. Visual inspection every load, verifying document photos of material onsite, if visual appearance changes, additional testing will be required.
e436ab8e-3431-5b24-9161-19fe6eea1e2a | note | Verification Activity: Activity - C
af2fdaee-5bc6-5ec4-8de0-a43353cc195b | note | Verification Activity: By - SE
6d7192d6-9061-5d38-a315-d4a8752b3fa5 | checkpoint | 4.01.03 - Filter Cloth
e97c31e2-2703-5531-921c-968367ba4426 | note | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings. (A14 Bidim or Equivalent)
395aaa72-f8cb-5ff7-b833-f83d51597c1a | note | Standard / Specification - GWS 3.2.3
38145b06-8215-5d7a-bae9-05b22b031c53 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
11a34487-579d-556d-af28-87ebd931137c | note | Frequency - Every Delievery to Site
b9984d57-5fc5-53e7-ba3b-88d1338b4713 | note | Verification Activity: Activity - C
98c3f6bf-f2fa-58c0-8ce4-6945531cc81b | note | Verification Activity: By - SE
34efbf28-65bc-5d1f-b72b-f1491def807a | checkpoint | 4.01.04 - Securing Pins
81765145-212d-5f11-9a15-bafd43dd3bf0 | note | Acceptance / Conformance Criteria - Pins for securing the geotextile shall be of steel, a minimum of 5mm in diameter and atleast 400mm in length
21e825c9-801a-5e5e-bf23-4dd7f89f00f3 | note | Standard / Specification -
9be1bb75-2395-5f77-936f-8fcf090b165d | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class,.
b3bb8c10-32fe-544f-bb14-522fab494c96 | note | Frequency - Every Delievery to Site
dd593997-acbf-5308-9281-0c1d7a16e204 | note | Verification Activity: Activity - C
15b0e4ac-c302-5b64-b5e7-6e9c227ba4ce | note | Verification Activity: By - SE
f4713bb7-3aea-5dca-b516-69272c0b56ba | section | SECTION 5 – CONSTRUCTION ACTIVITY
113d79bf-1485-508d-814d-8c7c8c221530 | checkpoint | 5.01.01 - Filter Cloth Wrap Inspection
2b6be960-71f1-57f0-8ea6-cdd1f2b1c8b1 | note | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain. TNZ F/6, PWRBSS Geotechnical Specification - The geotextile shall be placed in the tench so as to conform loosely to the shape of the trench. Cloth must fully encapsulate the aggregate. Geotextile longitudinal overlap to be minimum 300 mm (as indicated on drawing 3051 and required by NZTA F/6). Additional sheets to overlap by minimum 500 mm and anchored with securing pins (F/6 requirement). Verifying document, photos of trench prior to backfill, every line.
3ccf6b76-bbde-5e3b-ada6-b881ad83c9cd | note | Standard / Specification - GWS 3.2.2
1c0f6feb-de39-5114-a92f-e7f1a3b4dd6e | note | Verifying Document - Every line
b146b93c-e1e5-56f9-a2ef-ba3e5b5dce18 | note | Frequency - Photos of trench prior to backfill
84575761-6d3e-56a4-9329-95ee7877851e | note | Verification Activity: Activity - HP
bfce74a7-b98e-5bdc-9b8c-50e844e85dda | note | Verification Activity: By - ENG
a2a25648-08b8-5ac9-b1a6-269e329744a0 | signoff | AUTHORITY HOLDPOINT
543c766a-67a1-5508-b12a-a4f69b9927f3 | checkpoint | 5.01.02 - Trench Backfill
505a6f94-4bd2-511d-9d0d-4e9fc5090197 | note | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard of the material previously trenched through. Drainage aggregate to be placed in layers of 150mm or less. Only light compaction such as tamping with the back of an excavator bucket is to be applied.
d3140e35-3242-5933-b0d3-e38b8270c5db | note | Standard / Specification - GWS 3.3
1643d9aa-6eb2-5bec-a464-c029437b564b | note | Verifying Document - Site Record
bf422bec-d466-536c-b03b-f48e37c6ce0c | note | Frequency - Each trench
72d01061-88af-57bb-98c9-a754ad8fd732 | note | Verification Activity: Activity - I
7bfeb181-fb01-5a8c-9926-d1a8ffda4332 | note | Verification Activity: By - SE
f7142f9b-2009-59fd-9453-67a19dd7865a | checkpoint | 5.01.03 - Drainage Outlets and Inspection Points
5bdc6d42-db0a-5adb-8215-e7029a66611e | note | Acceptance / Conformance Criteria - At least one temporary flush point is required for each Pavement drainage system to enable flushing of the system once the earthworks are complete.
f60bd95e-fa1e-57ff-ad7d-1d00b83a57e6 | note | Standard / Specification - GWS 3.6
9c05594f-ed7d-5015-8b52-ab70ea3b8b4f | note | Verifying Document - Site Records
1a731b27-0ebd-5947-bba9-e73dccf04e65 | note | Frequency - Each Pavement Line
6dc43e98-625a-5520-8135-b8ab0d998cb8 | note | Verification Activity: Activity - I
c5c3f257-ffd9-52ab-a23e-b095eebb1d83 | note | Verification Activity: By - SE
434840e4-6129-5ff8-a5c8-120a88bb0c6e | checkpoint | 5.01.04 - Pavement Flushing
adceec4b-08d7-5638-9590-d083ff51f7a4 | note | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the Pavement drainage system. This must be witnessed by the Engineer.
6271ec30-4afb-5969-944b-54e344866ae4 | note | Standard / Specification - GWS 3.6
859164a6-ad96-5ddb-a88b-f7dc359ca8d1 | note | Verifying Document - Site Records
d94d9e49-9eca-5320-9322-f5ac86bfabb0 | note | Frequency - On completion of earthworks
3d2160ea-f1b9-5cc0-8c43-c58506bd329d | note | Verification Activity: Activity - HP
5e792c4e-c7f1-5e32-a1aa-a0dd2ddc9e8a | note | Verification Activity: By - ENG
5dd98013-4592-534f-8e98-66cb7ab35a3e | signoff | AUTHORITY HOLDPOINT
8914e134-e4d7-43d9-8785-46827c597dbf | checkpoint | 5.01.02 - Trench Backfill
654bb316-ddbe-5e42-adcf-fa72dcf5342c | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
bfa0fb89-2f4f-558d-94aa-9a0fc9c58dac | note | Standard / Specification - Downer
44090232-a2d0-5a5c-925e-210050b08237 | note | Verifying Document - Records
5903e67c-03f6-519d-810c-7603000c443c | note | Frequency - Post construction
d0c0e5fe-1a5f-55a4-a056-388fa3a0e8ed | note | Verification Activity: Activity - H
961a6fd6-7d50-5b8a-ae3f-b3d4f2411d05 | note | Verification Activity: By - SV
f999ffd9-5367-57d7-994f-8ff2006b1339 | checkpoint | 5.01.06 - Excavation
65235ddd-45ef-583c-9df0-645df14c76ae | note | Acceptance / Conformance Criteria - Trenches shall be cut in such manner as will ensure that the geotextile wrapped aggregate Pavement drains, and pipes if included, will be laid true to the depths, grades and lines shown on the drawings
f9dae494-0842-5564-ab25-737d3d617ea5 | note | Standard / Specification - Downer
d4a598a7-d37b-56f9-8ce9-67208fb05dd5 | note | Verifying Document - Records
0a7b899f-5027-5cb6-a0e9-a5ed108ab2ce | note | Frequency - Prior to laying filter cloth
438046f7-12c2-521d-aaa4-41f5f76802eb | note | Verification Activity: Activity - I
83a78f40-a888-5f4c-89a9-bd9440268d42 | note | Verification Activity: By - SE
78b40005-4535-58a0-8f12-10ce7328ed62 | checkpoint | 5.01.07 - Bedding
7defa5f5-31a9-5944-bcb3-df1f2cb77270 | note | Acceptance / Conformance Criteria - TNZ F/5 - Bedding thickness shall be no less than 100mm
de0db94e-b9cd-53b9-9a58-96aee795766f | note | Standard / Specification - TNZ F/5
16380dc3-53bd-56ae-b6f1-ca7d1dccf9e8 | note | Verifying Document - Records
67ef690e-499e-5013-b665-03d557586e57 | note | Frequency - Prior to laying Novacoil
71587158-cc12-533d-be39-764eeb56c7d0 | note | Verification Activity: Activity - I
1c0c27fb-2fa3-52d5-a59b-7678fbc81896 | note | Verification Activity: By - SE
bc02362a-9ac4-5773-899f-55a42641ec6b | checkpoint | 5.01.08 - Joining Pipes
6d762c48-d2c5-5a4f-8b0d-20269983f5db | note | Acceptance / Conformance Criteria - TNZ F/5 - Joining the pipe shall be done using a purpose made pullout resistant coupling in accordance with manufacturers recommendations
14ec8209-5172-5617-8da3-66ff73a76429 | note | Standard / Specification - TNZ F/5
b51a876e-13f1-5da3-8d29-6f2653edc9a7 | note | Verifying Document - Copy of delivery dockets, photos of pipes onsite with tag showing class
4aac0cbc-893d-5825-8ae9-efd4c84ff11e | note | Frequency - Every join
f2dba296-9eea-5252-bb45-28f8334067fb | note | Verification Activity: Activity - I
0ded4b4c-eb4e-5102-b7aa-2338e66e9e01 | note | Verification Activity: By - SE
2f363a55-4436-5df3-bb16-03fb4412a91e | checkpoint | 5.01.09 - Pipe Grade
b30ea0e5-d151-5ae2-a76c-d0f209e2b822 | note | Acceptance / Conformance Criteria - Grade of Pavements must be falling in the correct direction based on the IFC Drawings and at the correct grade (greater than 1% based on TNZ F/5)
63039763-9cac-5a8a-82fd-88c60cde71a6 | note | Standard / Specification - TNZ F/5
00b39255-fb56-5c6f-b73b-88ada0db74b9 | note | Verifying Document - AsBuilt
d4915a18-e3c3-52f5-8b03-4ac44b80bfcd | note | Frequency - Every 10m
20684865-8b5e-5fa2-bea4-d8964508f516 | note | Verification Activity: Activity - H
a8033010-40dd-5cb5-bbfc-6ac5743b153c | note | Verification Activity: By - SV
d6784725-7b39-59f1-a161-bb35735b619c | checkpoint | 5.01.10 - Pipe Cover
22d863dc-6e49-5dff-a947-5a01f9b659a1 | note | Acceptance / Conformance Criteria - Drainage aggregate must be placed till -0.1m from Top of SIL and verified by surveyor
6b94c535-a97c-5da0-b72b-0459c4888852 | note | Standard / Specification - N/A
0561413a-e201-5274-9a04-3d47ff05754b | note | Verifying Document - Site Record
4e96a172-c3c8-59a9-8933-b309679d8348 | note | Frequency - Every 10m
4362392e-14ca-58d1-a7cd-46709fe887b6 | note | Verification Activity: Activity - H
fe6beaab-16d5-5f53-8a82-fa7aca0b22b5 | note | Verification Activity: By - SV
cd33a7f8-9b6c-5422-93be-dcae98eaa460 | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
abaa7cc7-67ff-52ad-ae9f-e9176b336a01 | checkpoint | 6.01.01 - Construction Record Compilation
ec823516-bdd5-50a9-b19d-0c3a2a890c4a | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
c789a8ba-9ae4-5fcd-971c-d94eacbb7e96 | note | Standard / Specification - Downer
887591a5-e4a2-56a0-8ff0-fff1c3ecbebe | note | Verifying Document - Records
ac08efe8-cdc3-5215-9ec6-ef1a076d8edc | note | Frequency - Post construction
8e6372b4-32c9-54be-a4df-4309442031d4 | note | Verification Activity: Activity - H
9aed564b-0b6f-51c5-b80d-d7e7cee237d0 | note | Verification Activity: By - SE
f4876821-e136-54ca-95e8-27fd0f400f5d | checkpoint | 6.01.02 - Survey Records
dacff708-5a7b-5bdb-818d-06785b006c3d | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
f9496bff-7d38-5f43-9604-5d3ddc94e14e | note | Standard / Specification - Downer
6301abb6-46f8-5ab5-bfb4-f6c2ea4cd66d | note | Verifying Document - Records
b76aa70a-d9b1-5fd6-aea0-05079cba5f17 | note | Frequency - As-builts taken every 10m prior to backfill
8d10078b-0b46-5819-b7f6-692b2a161728 | note | Verification Activity: Activity - H
e83977fd-a3ae-555a-b87c-f0e49bc8f226 | note | Verification Activity: By - SV
a7ece1a0-6b4a-5d51-8813-156cc41a337a | checkpoint | 6.01.03 - Redline Drawings
676ab5f0-362b-5671-a809-c49e1d6e0f7e | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.To show all Pavements, including temporary Pavements that become part of the permanent works, to show all outlet locations
9e1f7f3a-2c37-5fdd-a24f-5b8e82b68f19 | note | Standard / Specification - Downer
1eea1431-ee7d-565e-8cd5-fe08bbaad33b | note | Verifying Document - Redlines
a62b2ffc-c6f7-53ea-b940-0159e3c38201 | note | Frequency - Post construction
710695e1-3d61-574b-be99-ad7c35a6975f | note | Verification Activity: Activity - H
9a4e76da-1a27-5e3e-a545-b057814cd788 | note | Verification Activity: By - PE
406cc900-58d1-549c-813d-cb4c75c9a2be | checkpoint | 6.01.05 - Photos
2f113112-8c0a-57e4-a8bb-b15e40b4ad6f | note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
e549179f-e214-57e2-b20e-3f497a9de829 | note | Standard / Specification - Downer
33188f4a-b1e0-530f-847a-921a7672124c | note | Verifying Document - Photo Records
58d981ea-285b-53a4-bfe5-ab9042ca61e8 | note | Frequency - Post construction
7735807e-b533-5ed5-a222-be1ab2e9c1d2 | note | Verification Activity: Activity - H
2944ca66-a734-51d6-9a0c-c47379b2b0b0 | note | Verification Activity: By - SE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
a6c8e731-b55c-5731-aa70-27d014e2f647 | checklist | ITP - 114 - Footpath Construction Rev B | itp | ITP - 114 - Footpath Construction Rev B
976a9582-8917-54ef-8971-32ce976640c8 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 - Site Requirements
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
ce5284c7-af2d-529e-9acd-6ec3ffb48e55 | note | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
351562d1-6be9-57f5-a2a1-90f7a1de99c7 | note | Standard / Specification - Downer
5a6d6486-ffec-5112-abc7-f47263382980 | note | Verifying Document - Construction Pack
db83dee9-c593-52bc-a602-a6cadf51d587 | note | Frequency - Submit 10 days prior to commencement of works
f1eb0f48-6a23-52f4-98e0-e3236e6e8124 | note | Activity - HP
9c8b9328-ba74-5759-9146-307748f2deae | note | By - ENG
ca255811-cbe5-57f5-8b49-d49ad30655f3 | signoff | AUTHORITY HOLDPOINT
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
4f71c412-f4d9-5424-be4a-38cecbf3a2ae | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
ecd7cf5c-246e-5523-9530-b5ac0afce4c3 | note | Standard / Specification - Downer
23415da0-6c29-58f4-91e9-27f1db880189 | note | Verifying Document - Survey Records
367bc75c-07f2-54c5-82ef-82ebac414fca | note | Frequency - Prior to Works
3f9d6745-524d-5c0f-9f9e-e00336e8723a | note | Activity - H
06f3dcac-1bec-5cc5-bb25-44064608dba7 | note | By - SV
a24a2c58-bf6f-5474-883c-40044bad1fc7 | checkpoint | 3.01.03 - Service Location
af821ed1-3204-55d2-ba32-4e8fd4b8731f | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
019d9f89-86ac-56b9-b69e-c6689f37786a | note | Standard / Specification - Downer
e9f13907-7099-5fc0-93b3-9e29f29ca377 | note | Verifying Document - Excavation Permit
4e839873-9cd7-5043-9740-f050b3a36d73 | note | Frequency - Prior to Excavation
f6ce9bea-ef92-543d-8768-b0cf3de2e03b | note | Activity - H
65bb7491-2f5d-5b9d-9714-5edf55aa18a3 | note | By - SE
0a214a7a-124a-5898-a837-e29e83751df0 | checkpoint | 3.01.04 - Internal Permits
d96df4ad-67ee-567c-b3e6-cbe90d1e2e84 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
c790c451-26c9-50f7-a4c9-d677f961b25b | note | Standard / Specification - Downer
57e06db8-d314-5a24-996f-9ca6d49aaeee | note | Verifying Document - Internal Permits
c8cb4af0-690d-5c60-a2ac-f11d47ce54c7 | note | Frequency - Prior to Excavation
0c71dc81-2b73-5fb6-9d2e-8ea5f544d523 | note | Activity - H
6ea247ce-2e7e-59b3-ae88-b640f7987ec7 | note | By - SE
917e2881-0901-542f-ae25-686bf9c47009 | checkpoint | 3.01.05 - External Permits
8f833f4b-5061-5ae6-a522-f5f7164954d7 | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
48e6ca0e-685c-5a45-9bec-86009bdb3e80 | note | Standard / Specification - Downer
be490c86-2175-553f-9801-0d1b5d5e5690 | note | Verifying Document - External Permits
f90cf7da-aa05-56ba-88d5-f09dd8f19558 | note | Frequency - Prior to Excavation
0aa33499-6971-597d-b391-87306aa055e1 | note | Activity - H
52769e5d-c5ad-540a-8f47-f78f8bba2793 | note | By - PE
a1302970-0389-558d-b43c-67b14bbfc27a | checkpoint | 3.01.06 - Approved Construction Drawings
2fef669d-2fa1-5fe9-9686-0b9e5a3adf42 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
98d59d68-4988-5e46-a739-d42e96b5479e | note | Standard / Specification - Downer
76a8fc04-ad6c-53b7-96fd-1db1d14ae33f | note | Verifying Document - IFC Drawings
a27455cf-46c0-5643-be87-e2c99e316aaf | note | Frequency - Prior to works start
ff94ef36-92ec-5834-82bc-4454151210f4 | note | Activity - H
7c42344c-de3d-5823-87a1-fac75afdf675 | note | By - PE
30e66181-e18e-5c62-90b6-4ffad1837210 | checkpoint | 3.01.07 - Previous Completed Work Packs
da7166a4-431d-55a0-ae99-d8950516c21a | note | Acceptance / Conformance Criteria - Review previously completed workpacks to ensure work completed meets the contract requirements
8d486b5e-27ae-5c1e-9584-8249cf992fb6 | note | Standard / Specification - Downer
d0b5cd3e-3506-522b-b6dd-ac02ad557d85 | note | Verifying Document - CONQA
24b235fb-91b1-55c5-b134-b0d11fbb7d2a | note | Frequency - Prior to works start
7c5220b5-f554-5315-8e16-be315e901353 | note | Activity - H
1b2d4d84-9278-5b0f-a62e-6c709860ee28 | note | By - PE
85f4f842-8513-5d3e-943d-b5ccaf1a84ca | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 4.01 Sub Activity
929d89be-4eb2-56fc-98ea-65e2a69ddfa5 | checkpoint | 4.01.01 - Bedding Sand
e1226926-429c-594f-962e-99cb82b9bdaa | note | Acceptance / Conformance Criteria - Record material type used and source testing of that material
1f48d203-bdad-5681-853d-4716eac5a361 | note | Standard / Specification - BBO
01ecc247-fb68-54b5-91a3-f911bd3bf5b5 | note | Verifying Document - Source Test/Site Notes
c3a5a8fe-74db-53b6-aa5e-56199009a08d | note | Frequency - 1 source test per material type
3cdc5de5-8449-591b-81d2-37302573b3e2 | note | Activity - R
52244458-0278-561b-bb96-4e1b8ad41ffc | note | By - SE
8a95e8ab-04e3-5cd2-ae71-d8d2b873ca00 | checkpoint | 4.01.01 - Undercut Backfill
1ada175c-0e6c-5bef-8cf2-e274ce0d201e | note | Acceptance / Conformance Criteria - Record material type used and source testing of that material
388d2ba7-1567-5ba8-80bd-ad1403a1fb90 | note | Standard / Specification - BBO
50497f66-815a-5188-b1fc-3a7a56cff965 | note | Verifying Document - Source Test/Site Notes
1b33edc8-73da-5d3f-b973-824077cb9694 | note | Frequency - 1 source test per material type
59430bc5-bbc0-509d-a9cf-799c20b1e24f | note | Activity - R
6d730eae-f596-57a2-95d1-b5297c57238c | note | By - SE
b956b330-0f51-5339-9048-d6958cbfd7fa | section | SECTION 5 – CONSTRUCTION ACTIVITY - 5.01 - Footpath Construction
411c2457-cdf1-53e0-ab3b-0e60912f60f5 | checkpoint | 5.01.1 - Footpath
87df6cff-9150-52f4-8f4e-b460bb53e57f | note | Acceptance / Conformance Criteria - After set-out and prior to installation of footpaths
045ed956-718d-59ca-a233-0cb4ff073a44 | note | Standard / Specification - PS - 2.2.16
73268c21-979d-5072-879a-2c1e760517d6 | note | Verifying Document - Hold Point Release
24f26b00-03b9-52b9-ac50-90aee9287b65 | note | Frequency - Min 48h Notice
73b646fc-b543-5076-a666-1efda5849508 | note | Activity - HP
66332c55-8d87-5db6-99f8-f5ae783b95ea | note | By - SE
3124fada-e76f-5dc0-a004-6003a86f88f3 | signoff | AUTHORITY HOLDPOINT
8770b06a-a35a-5cd6-9da9-ca1a7fea1afe | checkpoint | 5.01.2 - Subgrade Preparation
bb9313c5-53ef-59ac-bc5a-c524c2b15c64 | note | Acceptance / Conformance Criteria - The exposed subgrade (excavated to trial subgrade level or pavement depth) shall be tested by using a Scala Penetrometer for compliance with a CBR value >10 (4 blows per 100mm)
a0c62e94-6b18-59cd-945e-60dd7363dd8e | note | Standard / Specification - RITS - 3.4.9.4
6a55b29c-ef44-5495-92f7-38cabf543236 | note | Verifying Document - Scala Results
f4f9195d-bb3b-5220-ad16-effb38497ecd | note | Frequency - Every 15m
da7f1d8b-983c-5ba7-8ba9-658d90e76999 | note | Activity - I
da6e6413-b571-5c5a-9533-d24f66bed276 | note | By - SE
7bdc5c59-55f4-519f-bcd6-6e9d7fd6cdca | checkpoint | 5.01.3 - Subgrade Undercut and Subgrade Backfill
1b9bb59b-f2bc-5821-89f1-1829e8f9f3ca | note | Acceptance / Conformance Criteria - If subgrade does not meet the requirements of a CBR > 10 (4 blows per 100mm), and undercut and backfill of the CBR will be required. Backfill material will either be GAP or sand material and will be instructed by the engineer.
40aaf3d2-a6e2-5325-af34-6072b05658bc | note | Standard / Specification - RITS - D3.3.5
11fb04f6-fd2d-5fbe-9928-99afb580c869 | note | Verifying Document - Hold Point Release
5bc9ff8c-7d6d-5f14-b2ae-5e927b65d288 | note | Frequency - Every 15m
4bf00c67-c95a-534e-beb5-dce6b1084b20 | note | Activity - HP
922dce0a-f6d6-509d-93c9-84e6132b2a85 | note | By - ENG
14123c5e-d967-535c-8969-e41dc9c00c16 | signoff | AUTHORITY HOLDPOINT
ed8255ff-6f1c-5e6f-8826-30836c367cfb | checkpoint | 5.01.4 - Subgrade Backfill Fill Compaction Testing - Aggregate Subgrade
5e1c8060-3239-517f-b79e-d796aaa1f784 | note | Acceptance / Conformance Criteria - Aggregate Subgrade Fill shall be compacted to Clegg Impact Value (CIV) 15
5b19ab62-ede7-57e1-b588-ff92f513f966 | note | Standard / Specification - RITS - 3.4.6.5
d5196ad3-c7a3-5031-befd-092d0bad6076 | note | Verifying Document - Clegg Results
5421eec4-6911-5b15-b886-70a328b74561 | note | Frequency - Every 15m
b1c9f53a-a48b-5415-a1c1-0ffbad81cd92 | note | Activity - I
712e3587-fd40-5f4e-a449-a464158d0c59 | note | By - SE
b6900f1d-39cb-5d8d-ba5e-4adf4a22e72d | checkpoint | 5.01.5 - Bediding Sand
898b9b6e-5251-5e27-b84d-e7ef46583e4e | note | Acceptance / Conformance Criteria - Bedding Sand to be placed at a consistent thickness of 75mm free of foreign materials, bedding surface must be level and free of any peaks or troughs
0907a616-cae8-5b56-b766-b2bb240362dc | note | Standard / Specification - RITS - 3.8.3.3
73139c0a-8565-59f2-b8a2-4f396af58e13 | note | Verifying Document - Site Notes / Photos
8ec36ad8-2eee-5081-8f9a-583ec83f48b8 | note | Frequency - Every 15m
1db253e7-1fc2-5821-9b36-b520e490e789 | note | Activity - I
1f149fc6-c2fd-50a0-a6a8-3af067210be4 | note | By - SE
7675a132-d691-5bd5-88bc-11a6adfb5a60 | checkpoint | 5.01.6 - Concrete Pre-Pour
eeac9f18-9036-5812-9937-730b30252219 | note | Acceptance / Conformance Criteria - The Contractor shall give due notice to the Engineer of the time it is intended to place any concrete and no concrete shall be placed until approval has been obtained from Council.
4afd2489-822f-5cae-b486-590641667334 | note | Standard / Specification - RITS - 3.4.5.3
50189b59-5091-5422-b9bd-798a5f0a8e5f | note | Verifying Document - Hold Point Release, Pre-Pour Check
f92e6219-d0cc-5ddb-b96e-323df356d3b1 | note | Frequency - Min 48h Notice
886439f7-e505-5825-ac09-3872edf1a489 | note | Activity - HP
0287aadd-6648-5077-a2d9-59647c8f3134 | note | By - ENG
cf00d6c6-16f4-5dcb-aeaa-be1858c20bf2 | signoff | AUTHORITY HOLDPOINT
d84e1617-6447-5568-83fc-886f1615da66 | checkpoint | 5.01.7 - Ground Preparation
955dea00-b2e9-5c44-9ef2-78a9e100eedf | note | Acceptance / Conformance Criteria - Immediately before placing the concrete, the foundations shall be lightly dampened, and formwork shall be cleaned out. In all cases surplus water shall be removed before concrete is placed.Any foreign or organic material shall be cleaned out.
2be0f46a-270b-5441-9f78-b88fa06c1712 | note | Standard / Specification - RITS - 3.4.5.3
f5f979be-859b-56ed-8ad4-6046e3ee6887 | note | Verifying Document - Pre-Pour Check
072374df-ff13-5c27-9d2a-279c6526a4ed | note | Frequency - Each Pour
8d443340-6a04-5d9a-9b45-97cda6f3a4a1 | note | Activity - H
e2f2916f-bfa5-5092-8d73-252243305eaa | note | By - SE
eddc7ae7-0e47-5ac9-9187-432c79bba788 | checkpoint | 5.01.8 - Frozen Ground & Unfavourable Conditions
240798d5-5645-5742-8a9f-607fbe3971cf | note | Acceptance / Conformance Criteria - Concrete shall not be placed on frozen ground nor shall it be placed in unfavourable conditions, which may be detrimental to the quality and finish of the concrete (i.e rainfall)
43bd83ac-2572-5183-8894-44f3d96d21b4 | note | Standard / Specification - RITS - 3.4.5.3
68549b75-f80c-5fee-a15a-605038807a6d | note | Verifying Document - Pre-Pour Check
94ed8cd1-303b-5b11-bc17-589e7e799173 | note | Frequency - Each Pour
8e2024b6-338d-573d-96da-f21e306e7138 | note | Activity - I
8f41a3a1-e13f-5b3e-9557-e2dc960d3548 | note | By - SE
6741e38d-340c-568f-bffd-71e747c097eb | checkpoint | 5.01.9 - Curing Of Concrete
7b0506c4-fbea-51f1-bf28-698579515344 | note | Acceptance / Conformance Criteria - Immediately after placement, concrete shall be protected from premature drying, excessively high or low temperatures and mechanical damage and shall be maintained with minimal moisture loss for the necessary curing period and hardening of the concrete. In hot dry weather sprinklers or damp covers will need to be used.
df50fab9-c0f7-513a-bbb5-de0ced2b1bc9 | note | Standard / Specification - RITS - 3.4.5.5
e6298ec8-a5e6-5088-a5da-f5bba4a20c56 | note | Verifying Document - Post Pour Check
e17b0b60-f439-5ea9-9585-d5130438d714 | note | Frequency - Each Pour
785fced2-0338-59f7-80e0-5eb43b95a71e | note | Activity - I
a1248d1f-1114-546e-a761-9f98704a38c0 | note | By - SE
c054daeb-3170-5d6f-8793-51938562686d | checkpoint | 5.01.10 - Concrete Compressive Strength
126f30a0-7173-5dca-9c71-6aa5392eab45 | note | Acceptance / Conformance Criteria - Concrete to meet a placed 28-day compressive strength of 20-Mpa
a6647773-4132-5272-909c-c1ab1add4a52 | note | Standard / Specification - RITS - D3.3.5
8f725eda-f28c-575a-bcde-30dcbcd20f3c | note | Verifying Document - Concrete Dockets
60ef0079-98be-594d-a669-f4be24fd41dc | note | Frequency - Each pour
08ec14ed-9ebd-5d0d-9f4f-7fc9502ea89c | note | Activity - R
1e9d039b-480d-5127-a51e-fff86c8bed4c | note | By - SE
6fd90d5e-d351-53f5-9505-cc43faef187a | checkpoint | 5.01.11 - Finished Work
fe6f5a11-c908-52a1-938f-460cd9c0f8b0 | note | Acceptance / Conformance Criteria - Methods shall be used that will provide a smooth, clean and even surface on the exposed faces of all concrete work.
b7a68477-03d7-58b2-8f02-66ff8f6d634a | note | Standard / Specification - RITS - 3.4.5.7
313b25bc-ad5e-5784-baee-c15211ff8daf | note | Verifying Document - Post Pour
6c43aed2-8f84-56de-9028-ac3910f744f6 | note | Frequency - Each Pour
f75df3ca-2395-52b1-8d71-9487a9b7eedf | note | Activity - I
44cf6397-57b4-568b-b8bd-b3b9ef22d565 | note | By - SE
f902632f-e87e-5edc-9421-a3d6e3ddd48e | checkpoint | 5.01.12 - Contraction/Expansion Joints
6a775d3b-5758-5070-ace9-f3d5ec9cc1eb | note | Acceptance / Conformance Criteria - Contraction/Expansion joints shall be formed or cut along the kerb at a maximum spacing of 3.0m. The slot shall penetrate the concrete by not less than 50mm and the mortar dressed over the cut face. The contractor shall ensure that cold joints are accurately marked and set out via total station so that the subsequent saw cut is in the cold joint. Should cracking occur adjacent to the saw cut a minimum section of 1.5 metres of the footpath shall be removed and re-cast.
29c98797-12b0-51d9-8fe5-c8ab27c292d8 | note | Standard / Specification - RITS - 3.4.5.8
5f655169-cd8e-51bb-bb0a-69de9d3fe1c5 | note | Verifying Document - Post Pour
51a01500-016f-5bd2-b2c5-8c6a7a8c9b9a | note | Frequency - Each Pour
abe05d06-8549-5dc0-bab9-aa27230a6fb5 | note | Activity - I
8ecfac3a-ec12-58e4-8bd9-29473e9601a8 | note | By - SE
6e680bd4-5bbd-5674-91a0-f9e7a4ee0f52 | checkpoint | 5.01.13 - Backfilling against Concrete Work
d11f5586-c5c9-5f71-beae-1c199d6008bf | note | Acceptance / Conformance Criteria - Backfilling against the poured footpath shall take place as soon as practicable after the concrete has reached sufficient strength, with particular emphasis at curves, corners, intersections and pedestrian kerb crossings but not prior to 36 hours after pouring.
0d10d705-4ed7-5c84-a8f3-b833192f4aa1 | note | Standard / Specification - RITS - 3.4.5.9
6e141db8-3130-53a5-9895-f0cc0b7aad57 | note | Verifying Document - Site Notes
d72556a9-a38b-5ba4-b2e5-0e31285af35d | note | Frequency - Not prior to 36 hours after pouring
3cf19196-701c-5e5d-a4ee-764329620ffa | note | Activity - I
a876d563-56d1-519c-8ce8-6663eb4b3538 | note | By - SE
99850cf3-2701-5684-8054-84fdbc9ae393 | checkpoint | 5.01.14 - Finished Concrete (Surface Finish & Final Levels)
39e9b9c1-18ef-5983-a0e8-b7b4a0a8149d | note | Acceptance / Conformance Criteria - All final path and vehicle crossing surfaces shall be true to the lines and levels Specified and ‘broom’ finished.
9d8f96e1-9bd2-59b3-90bb-8afb5feab005 | note | Design considerations aside, the final surface shall not vary by more than 5mm when checked with a 3m straight edge. No finished surface shall hold water.
0e6bcd81-9749-528e-b559-18cd42691988 | note | Standard / Specification - RITS - 3.4.5.10
3e7a0871-1eb2-5dcc-8917-e55de59f1c0d | note | Verifying Document - Post Pour Check
35efb868-bd76-5de2-9bd7-d2d38d750fca | note | Frequency - Each Pour
e3174e0b-e036-5c55-ac66-9bb138488758 | note | Activity - I
9bbe291a-4b09-5e2c-9140-235b645b6509 | note | By - SE
a7db8a29-136d-5029-9d50-5fde8d3e0cda | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 6.01 - General
8d4e531c-688a-5145-b348-98da13114f31 | checkpoint | 7.01.01 - Construction Record Compilation
66a905ef-67fd-5577-9a07-1c6eb5d9f84f | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
7ef3391f-aa1d-567a-99c4-7a2f909a6923 | note | Standard / Specification - Downer
3f9c50f8-ae85-5327-baaf-0e91dfaa5081 | note | Verifying Document - Records
c8332514-2bd9-507e-a938-7e75a58cb1c2 | note | Frequency - Post construction
fadad837-b793-5499-958f-6bbb5fcd9bde | note | Activity - H
3295bdaf-8b72-5cb5-8139-990564ce17d7 | note | By - SE
19dccd2f-6441-5680-bbbb-459afb3e1dd8 | checkpoint | 7.01.02 - Survey Records
7a4f52a0-cd0b-5fa0-bf31-4f8b7d021a0a | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
f18df727-6fa5-5726-a49e-bd8f7e5e4b75 | note | Standard / Specification - Downer
d80c503c-1987-5ae1-b647-6fdb82cec402 | note | Verifying Document - Records
fe6e2180-4efc-5918-bf4c-63501e87e517 | note | Frequency - Post construction
139ecf52-71c9-5073-b035-35a7e1477ce4 | note | Activity - H
cd75a03c-9c8c-5818-a845-e1e9531da55b | note | By - SV
b068bae6-2ef0-5d88-81c8-4fb6749be6b3 | checkpoint | 7.01.03 - Redline Drawings
4c6290cf-839f-5763-9a5c-7804fdab4b5c | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red line to show any changes to footpath location or basecourse depth.
d0eece7e-d556-5eb0-958f-e221547ec3fc | note | Standard / Specification - Downer
da045d72-d79a-5ac7-afb9-a36da44bd43a | note | Verifying Document - Redlines
b76c2f29-b580-5d90-a029-494d807f2995 | note | Frequency - Post construction
6387ecfa-7d2c-5d4a-8330-3e6f14310148 | note | Activity - H
b615ee2a-9ea1-5aa9-bd0f-90ff5d3526e3 | note | By - PE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
060dc7ed-3622-529e-b412-0e77bef00530 | checklist | ITP - 114 - Footpath Construction Rev C | itp | ITP - 114 - Footpath Construction Rev C
8c9335a7-3af5-5e47-a887-39a89ff08c27 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
da4e31d1-91b7-5dfc-9883-d750aa73968b | note | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
22c2e398-038b-5ebe-9fd3-97d089f1f84e | note | Standard / Specification - Downer
51f28ae6-76b5-5476-b8a7-1e3c160ea9ff | note | Verifying Document - Construction Pack
14df887a-86c4-52a0-9263-c022d237cfe3 | note | Frequency - Submit 10 days prior to commencement of works
2c95298d-1a7a-584c-9129-0c8cc596a1e0 | note | Verification Activity: Activity - HP
0f2f83b5-5565-53f1-8eb1-64909c315acc | note | Verification Activity: By - ENG
ca255811-cbe5-57f5-8b49-d49ad30655f3 | signoff | AUTHORITY HOLDPOINT
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
7adfd0da-6cb1-514a-8414-93fb86ec0a65 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
8371c1de-3285-5475-ab9a-1feeaf3c3dbe | note | Standard / Specification - Downer
b7eb301e-1f39-5f6a-8ec4-ba779724ad10 | note | Verifying Document - Survey Records
4e4cda27-c986-5197-8d59-e672f6d2c4eb | note | Frequency - Prior to Works
572e42bb-3e75-5329-84f6-9783775f2c15 | note | Verification Activity: Activity - H
b2fb77bc-7151-5657-9f90-196e757dbb8a | note | Verification Activity: By - SV
a24a2c58-bf6f-5474-883c-40044bad1fc7 | checkpoint | 3.01.03 - Service Location
4a0a6b5c-4770-53e2-b27a-9b0bacbfb96e | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
f7a295d9-642c-5025-aff9-1e73964b4a78 | note | Standard / Specification - Downer
407fd6ef-6569-55e5-b04d-562e29d04133 | note | Verifying Document - Excavation Permit
88a68e61-5089-5738-8236-98dcf5de001b | note | Frequency - Prior to Excavation
e9c1e5af-04bd-50d3-8d54-365b51c53d26 | note | Verification Activity: Activity - H
889e2f29-22e6-55fe-b8cd-1a1cd1331ec2 | note | Verification Activity: By - SE
0a214a7a-124a-5898-a837-e29e83751df0 | checkpoint | 3.01.04 - Internal Permits
a7770878-b7b1-5e3c-80ba-e63f45ef37c9 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
77f4ae8c-c18a-543c-92d7-f14b76fdbf61 | note | Standard / Specification - Downer
3961ecde-cae0-5507-909c-616cab971954 | note | Verifying Document - Internal Permits
67543f22-4f4a-5e56-8ca5-87ac396de934 | note | Frequency - Prior to Excavation
1cfad12f-661d-5229-87a9-89b650cfd0ca | note | Verification Activity: Activity - H
592e8229-6b47-518d-8d6d-738fed132ae7 | note | Verification Activity: By - SE
917e2881-0901-542f-ae25-686bf9c47009 | checkpoint | 3.01.05 - External Permits
76e16d14-b834-51ab-b28e-585c1a480860 | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
2ab1457d-e577-5737-a9c8-d3cdf83698d2 | note | Standard / Specification - Downer
d92182ce-ac5b-580a-9ad7-74def00bfce7 | note | Verifying Document - External Permits
9e6b7642-cb72-5c3e-a7f0-07e84aa76c99 | note | Frequency - Prior to Excavation
fd47d71f-c009-5fa8-aa4e-2478702576d7 | note | Verification Activity: Activity - H
2d37fb9f-5ee1-5eea-a6b6-ecc52f598c31 | note | Verification Activity: By - PE
a1302970-0389-558d-b43c-67b14bbfc27a | checkpoint | 3.01.06 - Approved Construction Drawings
0cc6560a-b5db-5ca6-8395-cd60465052e4 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
6075603e-6ff5-5fcb-bcf9-1763b369b130 | note | Standard / Specification - Downer
c9699d70-adf3-5f19-b815-e1725a5c6077 | note | Verifying Document - IFC Drawings
c228c584-be3f-520c-9416-fadd9c318b1b | note | Frequency - Prior to works start
f529d555-ae4f-58ee-9b6f-630181516742 | note | Verification Activity: Activity - H
8f356468-5773-580d-832c-9ba5de3f9894 | note | Verification Activity: By - PE
30e66181-e18e-5c62-90b6-4ffad1837210 | checkpoint | 3.01.07 - Previous Completed Work Packs
a1fd307e-05b8-5bd4-879b-6290667bc562 | note | Acceptance / Conformance Criteria - Review previously completed workpacks to ensure work completed meets the contract requirements
473cb92d-a42e-5fa1-9d01-5cb6f9b4cf5d | note | Standard / Specification - Downer
fe316d62-99a5-556c-82fb-53fd79b60f8d | note | Verifying Document - CONQA
4333b296-f902-5a91-9ccb-11d0c7721897 | note | Frequency - Prior to works start
3ebb18de-cd32-5a6a-8755-3ad4a4fb8ab2 | note | Verification Activity: Activity - H
d585416b-64a6-5191-b9a0-fdbc224fb3c0 | note | Verification Activity: By - PE
8ec62109-1664-5fbd-8086-47c125cee66d | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
929d89be-4eb2-56fc-98ea-65e2a69ddfa5 | checkpoint | 4.01.01 - Bedding Sand
28e31cdd-c9bf-5e1c-b484-a209f941bcd3 | note | Acceptance / Conformance Criteria - Record material type used and source testing of that material
28a63c63-6b64-5f92-b0c8-c60919142920 | note | Standard / Specification - BBO
1b21c5b6-0401-55a6-9aa5-0dce895b7ca4 | note | Verifying Document - Source Test/Site Notes
5539197d-bf3c-5be0-ae91-48ea7400aa98 | note | Frequency - 1 source test per material type
1d0f6a19-310b-52a7-85ed-349ef693f717 | note | Verification Activity: Activity - R
e20fb7af-0946-58e5-8d81-fe9512a864ba | note | Verification Activity: By - SE
d5f02c1e-9666-551a-ad21-654002c998e5 | checkpoint | 4.01.02 - Undercut Backfill
7c1c82c7-fb69-5c99-9c1d-6258a5a549e4 | note | Acceptance / Conformance Criteria - Record material type used and source testing of that material
1e48974b-1904-5d12-b299-a169e4391ed0 | note | Standard / Specification - BBO
9135086a-ae39-5a1c-89ad-86a584ee315e | note | Verifying Document - Source Test/Site Notes
b6c9ed36-56c5-5172-8a70-e14af499a132 | note | Frequency - 1 source test per material type
e826c202-a533-5dac-abf1-9342b557327a | note | Verification Activity: Activity - R
5502c201-cd67-5fdb-80ab-204090226978 | note | Verification Activity: By - SE
44c195fe-264a-5d85-8ff1-8c8fa633248e | checkpoint | 4.01.03 - Uniaxial, Biaxial and Triaxial Geogrid
6c485a36-1e5b-5ff2-9e67-03168a57970c | note | Acceptance / Conformance Criteria - All uniaxial, biaxial and triaxial geogrid shall be manufactured in accordance with a management system that complies with BS EN ISO 9001 and BS 14001 and shall submit to the Engineer for approval.
e51309fb-8d25-5c69-a8af-ecf080c6c783 | note | Standard / Specification - GWS 4.2
dc54e220-2348-55d3-a447-9411a7ec607d | note | Verifying Document - Datasheet
7f729b1e-67ed-5fc8-acdb-e99025a8dfbf | note | Frequency - At least two weeks prior to works.
635de2f3-94ed-53ba-a288-1f709d14d989 | note | Verification Activity: Activity - HP
f9674768-a1f6-59c7-a1df-c55aad859451 | note | Verification Activity: By - ENG
bcae9856-1468-530a-bfc0-53336429d11e | signoff | AUTHORITY HOLDPOINT
f4713bb7-3aea-5dca-b516-69272c0b56ba | section | SECTION 5 – CONSTRUCTION ACTIVITY
411c2457-cdf1-53e0-ab3b-0e60912f60f5 | checkpoint | 5.01.1 - Footpath
908777f8-13d9-54cd-a057-cb00c27fbfe9 | note | Acceptance / Conformance Criteria - After set-out and prior to installation of footpaths
c3f7b93f-20ff-5f13-b287-1eb2d4049659 | note | Standard / Specification - PS - 2.2.16
21c7480e-6335-5273-adfc-74bb9705be94 | note | Verifying Document - Hold Point Release
0887ec57-80c8-5d4c-9820-2117ddf31976 | note | Frequency - Min 48h Notice
c8bc5408-9d80-5790-813d-4dc74448b00c | note | Verification Activity: Activity - HP
bfdd6fa3-b890-5373-b207-b1124b461033 | note | Verification Activity: By - SE
3124fada-e76f-5dc0-a004-6003a86f88f3 | signoff | AUTHORITY HOLDPOINT
8770b06a-a35a-5cd6-9da9-ca1a7fea1afe | checkpoint | 5.01.2 - Subgrade Preparation
89e10954-615f-536e-b273-95e4bb40e1e8 | note | Acceptance / Conformance Criteria - The exposed subgrade (excavated to trial subgrade level or pavement depth) shall be tested by using a Scala Penetrometer for compliance with a CBR value >10 (4 blows per 100mm). For subgrade of CBR value <10 (4 blows per 100mm), refer to 5.01.3.
28cf4ce2-cd56-531c-9e47-ff8e15d54928 | note | Standard / Specification - RITS - 3.4.9.4
507e480b-cafc-5ecd-a5aa-6bdd78c26921 | note | Verifying Document - Scala Results
b9b44e33-fd4a-5a4d-91b4-c3df9442117e | note | Frequency - Every 15m
760dcc7d-ccf8-5c6e-8ad2-5eac300c26dd | note | Verification Activity: Activity - I
3e152a2e-e61b-52aa-886e-8e2b920d32af | note | Verification Activity: By - SE
7bdc5c59-55f4-519f-bcd6-6e9d7fd6cdca | checkpoint | 5.01.3 - Subgrade Undercut and Subgrade Backfill
ddaf608f-44a3-509f-be78-c4ab1de783fe | note | Acceptance / Conformance Criteria - Subgrade CBR <10 but > 7 (3 blows per 100mm) 75mm GAP20, CBR <7 (2 blows per 100mm) 100mm undercut & 175mm GAP20, CBR < 3 100mm Undercut, grid (standard biaxial or triaxial equivalent) & 175mm GAP20.
7853bfa5-025c-55c6-8475-68e65376a1c3 | note | Standard / Specification - RITS - D3.3.5 BBO
c93e8f11-a494-5c2d-83fa-ed4c47c0e295 | note | Verifying Document - Hold Point Release
a9ba145a-104f-572b-b833-053579b5c130 | note | Frequency - Every 15m
7f703640-1047-5691-927a-c509139171d3 | note | Verification Activity: Activity - HP
c27ef9e5-5a36-5fe8-9a7c-8448e3762911 | note | Verification Activity: By - ENG
14123c5e-d967-535c-8969-e41dc9c00c16 | signoff | AUTHORITY HOLDPOINT
7b149475-9580-5d91-8533-67a79d3e2d58 | checkpoint | 5.01.4 - Undercut Geogrid Placement
94eb9090-a5b4-502e-af61-59c8afb3e86b | note | Acceptance / Conformance Criteria - Geogrid to be placed flat on subgrade. For areas that require lapping, lapping to be 500mm.
f1a2a709-2242-57eb-b842-74d62f45cf2a | note | Standard / Specification - GWS 4.1
994c46b4-6c14-5700-bcc3-85ad8cfcfbf6 | note | Verifying Document - Records
47b10ca8-9381-55ba-b356-3ad1e10d92be | note | Frequency - Each undercut
6ef10fb6-3aab-5516-93e3-b765e462fb84 | note | Verification Activity: Activity - V
2c0378ff-131f-56c5-bc1d-aa2543c28728 | note | Verification Activity: By - SE
33f7b1cf-bbcb-57de-88b6-c272b7996d44 | checkpoint | 5.01.5 - Subgrade Backfill Fill Compaction Testing - Aggregate Subgrade
30326775-e281-5ca4-b482-75b27b5cc8f8 | note | Acceptance / Conformance Criteria - Aggregate Subgrade Fill shall be compacted to Clegg Impact Value (CIV) 10 for footpaths upto 3m wide, and CIV20 for footpath greater than 3m wide.
e6622324-792e-5f27-8957-d4da4f9aac92 | note | Standard / Specification - RITS - 3.4.6.5
85fc9129-4950-52c6-bbc6-45ac0b7acc91 | note | Verifying Document - Clegg Results
1df7924b-a1bf-5ce3-a4ce-868badad09e1 | note | Frequency - Every 15m
da0c3aea-2fd1-58c2-bae0-641ac6da5657 | note | Verification Activity: Activity - I
97fab05e-d8cb-5b6f-b077-f3c5f29014e9 | note | Verification Activity: By - SE
271933a8-7928-52f2-96c6-278e54c6e8cb | checkpoint | 5.01.6 - Bedding Sand
4d42bc40-457f-54e4-b9d3-13501fb17694 | note | Acceptance / Conformance Criteria - (For CBR > 10% or 4 blows per 100mm) - Bedding Sand to be replaced at a consistent thickness of 75mm free of foreign materials, bedding surface must be level and free of any peaks or troughs
880dec4d-57e7-5e36-b3af-3e3f6278c441 | note | Standard / Specification - RITS - 3.8.3.3
b46e2e91-0db7-55f3-957f-17688ad49168 | note | Verifying Document - Site Notes / Photos
699a0042-76ca-5c90-8aa7-6ac19c487242 | note | Frequency - Every 15m
a32dd790-e1ab-585e-a45b-a8c29746f68b | note | Verification Activity: Activity - I
c655a22f-2cc5-5052-b66f-db24cff2a8c6 | note | Verification Activity: By - SE
5d691f30-9c31-5002-9611-e5072ba1906c | checkpoint | 5.01.7 - Concrete Reinforcing
09052192-4b7d-5423-aa0c-c683ec8589c6 | note | Acceptance / Conformance Criteria - In instances where rain gardens are to be installed, adjacent footpaths consist of a reinforced footing and a mesh section (Pavement Type 4). 2 x D12 Longitudinal bars with a min lap length of 384mm & R10 Stirrups @ 600 CRS. Pavement Type 4 found in DWG3152 - 150mm Concrete with 665 Mesh on 100mm GAP20. Minimum cover of 50mm.
14efbad6-affe-5f6c-b11c-97f5da93f60c | note | Standard / Specification - RITS - 3.4.5.4
3ee560cf-9f51-550c-ba3a-a2dd2eb663fc | note | Verifying Document - Site Notes / Photos
74a69f01-4738-5166-85a4-30e2337f7b90 | note | Frequency - Min 24h Notice
fc70243d-988b-5b9d-baaf-b14d71384863 | note | Verification Activity: Activity - I
60871f4e-9ad7-5b52-a9af-a96d549ecdc0 | note | Verification Activity: By - SE
d853097a-6cf3-5e82-be13-0830467ea735 | checkpoint | 5.01.8 - Concrete Pre-Pour
5a81f1a8-fd2e-5e37-a8c2-a9103ad5f466 | note | Acceptance / Conformance Criteria - The Contractor shall give due notice to the Engineer of the time it is intended to place any concrete and no concrete shall be placed until approval has been obtained from Council.
98b8f422-f39c-577a-aa54-9065195c3790 | note | Standard / Specification - RITS - 3.4.5.3
10fc23c7-1766-520d-b207-1884c1546dad | note | Verifying Document - Hold Point Release, Pre-Pour Check
11d8dcaa-2d9c-5400-8d25-49f06ea34d9b | note | Frequency - Min 48h Notice
2415e9a8-ac9e-5126-88e5-99b476a6fd64 | note | Verification Activity: Activity - HP
3a86b9e5-8421-5f37-b168-8149b16cb411 | note | Verification Activity: By - ENG
9ae2bf43-9b75-54b7-9620-e4a7bf6456ec | signoff | AUTHORITY HOLDPOINT
e718a374-5ff3-50a5-9a5b-fa04c28550ca | checkpoint | 5.01.9 - Ground Preparation
24b744e8-9641-5b2a-af8d-f37ee0badcc1 | note | Acceptance / Conformance Criteria - Immediately before placing the concrete, the foundations shall be lightly dampened, and formwork shall be cleaned out. In all cases surplus water shall be removed before concrete is placed.Any foreign or organic material hall be cleaned out.
c20186d3-ca4a-53e8-a9ea-e48f83ea6d0a | note | Standard / Specification - RITS - 3.4.5.3
50019442-d430-5090-a550-116eecd6eee8 | note | Verifying Document - Pre-Pour Check
9564bcc3-35a1-5668-9aff-b876f559b263 | note | Frequency - Each Pour
6ff546c8-7d26-5574-8e5e-b32ba34ad643 | note | Verification Activity: Activity - H
1e3a0a52-8a7e-581a-8201-12f0a6a36852 | note | Verification Activity: By - SE
f2ac9f95-675d-5825-a0ab-676ee57cadce | checkpoint | 5.01.10 - Frozen Ground & Unfavourable Conditions
8baae2ed-c68e-55e0-aecd-8aaeb381fc2a | note | Acceptance / Conformance Criteria - Concrete shall not be placed on frozen ground nor shall it be placed in unfavourable conditions, which may be detrimental to the quality and finish of the concrete (i.e rainfall)
c32ac166-e93f-5aca-81af-d3b9d7c52355 | note | Standard / Specification - RITS - 3.4.5.3
4e939bbc-43e5-5b44-9c22-82a83a43b731 | note | Verifying Document - Pre-Pour Check
89aa9783-1364-5cd6-8151-dbc82cc210ef | note | Frequency - Each Pour
ab3c9297-cb63-5e05-a586-ea9f2a82f303 | note | Verification Activity: Activity - I
436f59ea-8706-56dd-b335-434ec313839d | note | Verification Activity: By - SE
8d9cec95-8b10-594c-9b15-9ced175af34b | checkpoint | 5.01.11 - Curing Of Concrete
5694b9f5-52cf-5ca7-a599-4ef7c2e3c8b4 | note | Acceptance / Conformance Criteria - Immediately after placement, concrete shall be protected from premature drying, excessively high or low temperatures and mechanical damage and shall be maintained with minimal moisture loss for the necessary curing period and hardening of the concrete. In hot dry weather sprinklers or damp covers will need to be used.
3c3cec70-d8f6-5473-ab94-99c3096e6f41 | note | Standard / Specification - RITS - 3.4.5.5
da67b0d9-bf8e-5a4e-8dbe-3bdae2aefb46 | note | Verifying Document - Post Pour Check
a37ffe17-cc43-5a15-9b87-1bd96eb66468 | note | Frequency - Each Pour
5d565167-84aa-5918-aac0-250f7dbe8db9 | note | Verification Activity: Activity - I
3f8bfc2e-22a7-5591-bdc8-3dfb2cd621ae | note | Verification Activity: By - SE
1d9a07d4-4f31-51eb-97fb-edb3550349aa | checkpoint | 5.01.12 - Concrete Compressive Strength
13fc6a02-f751-5a8a-b0ad-ea573b03e838 | note | Acceptance / Conformance Criteria - Concrete to meet a placed 28-day compressive strength of 20-Mpa
42b8d0d1-ecf8-541d-b5b6-155c20ac194a | note | Standard / Specification - RITS - D3.3.5
e6f2d538-223e-5478-b172-e2bdc9c73bbd | note | Verifying Document - Concrete Dockets
f48bf4b1-1652-5a21-aeed-abe0e3b935aa | note | Frequency - Each pour
c6dca3c8-92a9-5068-9cc9-0532bf247072 | note | Verification Activity: Activity - R
b5bc0b4c-3c57-5520-b2b4-d3891e06e110 | note | Verification Activity: By - SE
1d41d13b-e4b8-56e2-b559-66e725a31614 | checkpoint | 5.01.13 - Finished Work
a09d24a5-7606-5230-8ea2-3745590c5d03 | note | Acceptance / Conformance Criteria - Methods shall be used that will provide a smooth, clean and even surface on the exposed faces of all concrete work.
4d408ab1-0198-52b8-b320-5acaf4871702 | note | Standard / Specification - RITS - 3.4.5.7
5a67833f-67db-5837-8fe9-9a31d40d5806 | note | Verifying Document - Post Pour
dddbd0aa-fce6-5663-9d5c-c2ce631be1d6 | note | Frequency - Each Pour
1bde09a7-e8d9-5268-accf-9503cc7e39c9 | note | Verification Activity: Activity - I
391e97e9-e992-5a05-99dc-f944a3fdf702 | note | Verification Activity: By - SE
a8d1f690-b1fe-5f9d-a08d-cdec61b079c8 | checkpoint | 5.01.14 - Contraction/Expansion Joints
3aaeef3d-83b0-57f0-9ccc-7bcf5eade92b | note | Acceptance / Conformance Criteria - Contraction/Expansion joints shall be formed or cut along the kerb at a maximum spacing of 3.0m. The slot shall penetrate the concrete by not less than 50mm and the mortar dressed over the cut face. The contractor shall ensure that cold joints are accurately marked and setout via total station so that the subsequent saw cut is in the cold joint. Should cracking occur adjacent to the saw cut a minimum section of 1.5 metres of the footpath shall be removed and re-cast. For reinforced Concrete, Cuts to be 30mm depth to avoid contact with steel reinforcing.
a8119bfe-92e8-528e-b157-d1e467b081f3 | note | Standard / Specification - RITS - 3.4.5.8
1ae26c56-d637-52a9-b983-277465c75fb1 | note | Verifying Document - Post Pour
e88895bf-ade1-5921-8816-b0fa6995dc2e | note | Frequency - Each Pour
4b3b25d2-dca0-542d-a938-b8c621c92edd | note | Verification Activity: Activity - I
63d951df-76a5-5649-a7a4-889bec116c8b | note | Verification Activity: By - SE
5ed0b099-0794-5a1e-ad40-2d8e0e66a5af | checkpoint | 5.01.15 - Backfilling against Concrete Work
32bb1c33-9eff-5723-a138-fe71e52b0d5a | note | Acceptance / Conformance Criteria - Backfilling against the poured footpath shall take place as soon as practicable after the concrete has reached sufficient strength, with particular emphasis at curves, corners, intersections and pedestrian kerb crossings but not prior to 36 hours after pouring.
a1904119-c4c9-59d6-a24d-3225e9757905 | note | Standard / Specification - RITS - 3.4.5.9
92dad5ff-c4a6-5e9a-bc45-5300b867b569 | note | Verifying Document - Site Notes
ef46bd31-a031-50e1-8fb6-c000b2e71734 | note | Frequency - Not prior to 36 hours after pouring
c6049b82-49e8-5274-8fa3-36d92c9b9b40 | note | Verification Activity: Activity - I
c36dc286-68c0-5bde-84af-70d018be772e | note | Verification Activity: By - SE
5af6bad0-72f5-5521-aba1-ee6b4f9cf85d | checkpoint | 5.01.16 - Finished Concrete (Surface Finish & Final Levels)
e9b1467d-25a3-5b45-b67d-05538f51d33b | note | Acceptance / Conformance Criteria - All final path and vehicle crossing surfaces shall be true to the lines and levels. Specified and ‘broom’ finished. Design considerations aside, the final surface shall not vary by more than 5mm when checked with a 3m straight edge. No finished surface shall hold water.
78bfc4c1-9545-5fdf-a395-8735c81cb9b8 | note | Standard / Specification - RITS - 3.4.5.10
93875082-830f-5035-b361-2f291c475bfd | note | Verifying Document - Post Pour Check
539b0dd4-d8b9-55a9-852f-bbbcc1eefc1d | note | Frequency - Each Pour
8c8c983e-3eeb-5c68-825f-98aadd284836 | note | Verification Activity: Activity - I
dd4f3d49-14ea-5e1d-a0b9-3ec2b9950058 | note | Verification Activity: By - SE
cd33a7f8-9b6c-5422-93be-dcae98eaa460 | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
8d4e531c-688a-5145-b348-98da13114f31 | checkpoint | 7.01.01 - Construction Record Compilation
6c58462b-a30c-57c5-85b3-ed6b02f4429d | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
0f4077a8-c09d-5eb1-a55b-a5ea479892ef | note | Standard / Specification - Downer
529aa3d2-e2c8-5ce5-8e1c-dd92a372e279 | note | Verifying Document - Records
fcca9f71-5bcb-5211-9bef-dc0c1e2ea35d | note | Frequency - Post construction
febf01f9-93b7-5623-a920-8aa5c90d4f4f | note | Verification Activity: Activity - H
392c4756-11b1-592f-902e-e738e419a4ab | note | Verification Activity: By - SE
19dccd2f-6441-5680-bbbb-459afb3e1dd8 | checkpoint | 7.01.02 - Survey Records
1baba57d-00b1-5734-8924-b6a1bc3c85dc | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
2553cb8b-26ec-5173-b4dd-3a00f846ca2d | note | Standard / Specification - Downer
60510461-c115-524c-88f8-23576b77f146 | note | Verifying Document - Records
d9f69550-8a85-5856-b38e-0d4ecc83ac19 | note | Frequency - Post construction
8f39c29c-f15b-55d4-a510-7de084814854 | note | Verification Activity: Activity - H
a21c9379-e2d3-50af-afcc-1e629edeba8d | note | Verification Activity: By - SV
b068bae6-2ef0-5d88-81c8-4fb6749be6b3 | checkpoint | 7.01.03 - Redline Drawings
2a5c3d60-6956-58dc-ac97-4da7689fa3f1 | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red line to show any changes to footpath location or basecourse depth.
12fe14e8-8e13-5203-b3c8-44efd6ac622e | note | Standard / Specification - Downer
04bb6fd3-e6f5-5237-9235-1e81056413d8 | note | Verifying Document - Redlines
dcceb05c-acb1-5fd5-a989-8852621b6b1d | note | Frequency - Post construction
d6e2ca6f-aec7-563c-80b5-65af2c147304 | note | Verification Activity: Activity - H
4dd40fb8-f599-5701-8cc9-9b7b4b0d7ce6 | note | Verification Activity: By - PE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
6c8c1c84-1bbc-5cc3-b58f-159d9be037a0 | checklist | ITP - 116 - Pavement SIL Rev C | itp | ITP - 116 - Pavement SIL Rev C
8c9335a7-3af5-5e47-a887-39a89ff08c27 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
c40fa04e-13bc-52d2-96ab-64f63b73c062 | note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence
6c6fb38c-6a48-589d-9f32-48e709e1cd2f | note | Standard / Specification - Downer
6639788b-38a1-5bb3-b19c-caf2d3e2300a | note | Verifying Document - Construction Pack
58a3cb4c-245f-5b89-8450-acb58a784745 | note | Frequency - Prior to Works
25464d71-aea9-51a6-a729-7bfbfbdfed60 | note | Verification Activity: Activity - H
4f0adf16-abb4-5f29-9a52-fd242a9f2a38 | note | Verification Activity: By - PE
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
64b55ec4-42f2-5ebc-9905-6c26ed810702 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
46049ddb-5425-5a76-b44e-feb4e1999006 | note | Standard / Specification - Downer
a3806e12-3999-5074-843a-c47d1b7e1cd4 | note | Verifying Document - Survey Records
b60098de-3ee2-54e3-b42d-4751a0263f1f | note | Frequency - Prior to Works
3688549a-eb1f-5beb-9832-647ec65b5a74 | note | Verification Activity: Activity - H
973b7e09-3aab-5043-8be7-072efe7e38f0 | note | Verification Activity: By - SV
a24a2c58-bf6f-5474-883c-40044bad1fc7 | checkpoint | 3.01.03 - Service Location
6e787462-9a97-553d-801b-a7dccdfafbc8 | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
ed0f280f-f8ac-5a09-9672-3cf33faa605e | note | Standard / Specification - Downer
0fc81a14-3e98-5427-88cd-2b78e1881ed4 | note | Verifying Document - Excavation Permit
c0038974-f486-5d5d-a8b1-aaa88a400346 | note | Frequency - Prior to Excavation
68f531aa-2f97-591c-9e4d-5b67241e5bf1 | note | Verification Activity: Activity - H
f8d27db9-1694-5c4d-bd5a-6ac182673484 | note | Verification Activity: By - SE
0a214a7a-124a-5898-a837-e29e83751df0 | checkpoint | 3.01.04 - Internal Permits
d986341e-82f8-58a9-8582-b70fa39800f7 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
f8306c64-b4fc-5e67-94fd-8bfdb3117a3f | note | Standard / Specification - Downer
d8105282-76f0-5cc9-bcf4-b31fc99670e2 | note | Verifying Document - Internal Permits
42494a2f-4ac2-534c-89c7-f1ed3902d88b | note | Frequency - Prior to activity being undertaken
d3331e29-8c2e-5d36-a606-e1919a129e64 | note | Verification Activity: Activity - H
d63e15fc-e8ec-5cfd-ac4c-69e191340406 | note | Verification Activity: By - SE
917e2881-0901-542f-ae25-686bf9c47009 | checkpoint | 3.01.05 - External Permits
493daff9-55ff-5ab5-b341-27e318fb18fc | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
7fc1af21-d3b9-5816-a9b0-7c975d068572 | note | Standard / Specification - Downer
08dd5f42-099a-5358-892c-f8e48ff540ce | note | Verifying Document - External Permits
3c2e104c-6d7e-5993-95cb-d49ce71ca53d | note | Frequency - Prior to commencment of activity
b6491fa9-f1bd-5a41-8d23-9c3979a6a3b6 | note | Verification Activity: Activity - H
88684cca-8136-5f3e-a94b-4bb63dc6b478 | note | Verification Activity: By - PE
a1302970-0389-558d-b43c-67b14bbfc27a | checkpoint | 3.01.06 - Approved Construction Drawings
2d8bed13-a256-5820-93c3-239f8fd05c54 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
08f89712-8651-5fe9-ab4b-d6e51a041502 | note | Standard / Specification - Downer
12ecd9d4-c68e-5a6b-8a34-d753ab18f30b | note | Verifying Document - IFC Drawings
de366472-6407-528d-9f65-88e2328d5c60 | note | Frequency - Prior to works start
4cfc74e4-63bf-520b-8f1d-d6d828782ec6 | note | Verification Activity: Activity - H
c302bdfe-c0b4-5e2b-ae14-f939b3a66f60 | note | Verification Activity: By - PE
5fe0af18-de1c-5a52-a24a-6d199c43ea87 | checkpoint | 3.01.07 - Previous Layer QA Sign Off
759644f3-c189-510e-9984-ffbbf9a4457c | note | Acceptance / Conformance Criteria - All Previous layers signed off, QA complete. Including subgrade, SW, WW, WM. Ensuring everything up to the bottom of SIL is compliant.
5d3b8915-ce59-5d36-82db-db17194583ce | note | Standard / Specification - Downer
f7ea8c9b-a684-5cfc-a407-4c595ce13634 | note | Verifying Document - QA Records
96ee17ba-5921-56cd-b22e-a1ce63b618dd | note | Frequency - Prior to works start
1970ad1c-eb9e-51bb-a5e5-10207f8738ae | note | Verification Activity: Activity - H
3f580ecb-eb69-5f18-aa68-7ee9ba5be9dc | note | Verification Activity: By - PE
d633103b-f5e3-5327-bd46-21e8742420c1 | section | SECTION 4 – ENGINEERS HOLD POINTS
7d5180df-d4eb-55e4-af4d-0e923a86f4b9 | checkpoint | 4.01.01 - SIL Inspection
ace7915d-b335-5044-bf9b-510395667093 | note | Acceptance / Conformance Criteria - Prior to placing of sub-base pavement, to include proof roll, inspection of extents of works, general shape, and tidiness, free of organic or contaminated material, review of Benkelman Beaming of the SIL and final levels.
bf3713ae-0c11-5951-882e-cd868286d53e | note | Standard / Specification - PS - 2.2.16
14c91a0d-1f8e-5153-9477-647a932eba34 | note | Verifying Document - Hold Point Release
234ef8f6-58bd-5f2d-a62f-b92075854b98 | note | Frequency - Min 48h Notice
072768c5-b408-56af-b8e2-d9fc9f83ca86 | note | Verification Activity: Activity - HP
cde2bf39-8343-5cc7-80f5-87c657e7f791 | note | Verification Activity: By - ENG
22c63970-dca6-5fd1-8231-ea707288aa18 | signoff | AUTHORITY HOLDPOINT
62f939d2-18c6-5474-abaa-4e5cecc5daba | checkpoint | 4.01.02 - Subgrade Inspection
98f56f2f-a2fc-5db0-92f7-96515cfce501 | note | Acceptance / Conformance Criteria - Proof roll, Scalar penetrometers, and shear vanes prior to SIL fill commencing
e45574da-a763-5f81-b355-413c0d29cd55 | note | Standard / Specification - PS - 2.2.16
5394684b-f36b-5ed9-b144-97b893e708da | note | Verifying Document - Hold Point Release
dfd76a41-a6a3-5e32-8fcd-8ef042ee2f19 | note | Frequency - Min 48h Notice
ace9466a-e662-518c-8004-b429923c70ae | note | Verification Activity: Activity - HP
5b4f32fd-698a-531a-b091-3c418830b074 | note | Verification Activity: By - ENG
7ad2b75a-44c0-5e3d-b3c3-e0084f7839d0 | signoff | AUTHORITY HOLDPOINT
2297f535-c21c-525d-91e6-de612eeb523b | section | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
fcd729d9-871b-5ce2-b7a9-fc012a97901d | checkpoint | 5.01.01 - Pavement Subgrade CBR
e235899c-1101-58e9-adf3-8bd9aadc8f7d | note | Acceptance / Conformance Criteria - CBR testing of the subgrade shall be carried out by the contractor prior to final trimming. The pavement design requires a soaked CBR of not less than 10 within 1.0m of the bottom of the SIL layer. Subgrade CBRs testing includes 4x DCP's at subgrade level to a depth of 1m in a 1m grid around the CBR test location and 4x NDM's DT -0.1m subgrade level with a probe depth of 300mm in a grid. CBR testing is then completed (For Subgrades in cut or fill 1 x In-situ CBR test (truck mounted CBR), Push tube CBR for subgrades in cut and remoulded CBR sample for subgrades in fill). Another 400mm material is then cut, 4 x NDMs are completed around the test location and CBR testing is completed. If the soaked CBR is less than 10 the Engineer may instruct changes to the pavement design. Invitation for engineer to witness CBR testing. To be accurate representation of site materials.
ecdab66f-f43c-594a-b89d-ddcacf94456f | note | Standard / Specification - PS 7.1
4a5a1f49-499f-55cc-b553-091f83b9217a | note | Verifying Document - IANZ Lab Reports
698cf41c-3cb1-57fe-b1e4-8bc069990d26 | note | Frequency - One test per 2,000m2, with a minimum of three tests per material type.
5552604d-44fa-536a-9995-e2684135d758 | note | Verification Activity: Activity - HP
7c10cef9-9ecd-55fc-8c30-b2bc8dbee054 | note | Verification Activity: By - ENG
93c1095a-43a9-5d7d-be8f-7a7cdce201a4 | signoff | AUTHORITY HOLDPOINT
75e3c18b-3bc3-5384-a690-0b943edb28e2 | checkpoint | 5.02.01 - SIL Conformance
01dedcf8-53dd-5801-bf4c-85d7078dabc3 | note | Acceptance / Conformance Criteria - AP200 from Taotaoroa Quarry will need Gradation (PSD envelopes, set limits for the SE and CI. (recommend SE>25 and CI<10), set crushing resistance (<10% at 130kN), WQI (AA,AB,BA,BB) and MDD/OMC test results.
0ac72aa9-a6cc-5cb5-ac17-743f2f9af6e3 | note | Standard / Specification - BBO
fbfba3c4-9265-593a-a902-33cf676e3dc3 | note | Verifying Document - Lab Reports
a3dcb2c7-c221-5093-bc8b-448af6c40ddf | note | Frequency - All testing shall be completed at the rate of 1 test per 2,500m3, and being no less than 1 test every 3,000m2 (placed).
65ac43da-eeda-5d04-b76d-4ff0736bb03b | note | Verification Activity: Activity - HP
965386b3-d89e-5be2-9b22-1a1d438b848e | note | Verification Activity: By - ENG
d189a4e6-f601-5569-9fc1-1d87e656f0fe | signoff | AUTHORITY HOLDPOINT
e318ec15-f915-557b-9af7-5c5cf6c32ccc | checkpoint | 5.02.02 - SIL Maximum Dry Density & Optimum Moisture Content
c244761f-570b-5268-aec2-b925831e8ab8 | note | Acceptance / Conformance Criteria - The SIL shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density & Optimum Moisture Content
c98f5384-794e-5d3e-bce0-e9d516934bdd | note | Standard / Specification - PS - 7.2.1
2cb005e1-9bf6-5c65-95b6-a01ab3b39b63 | note | Verifying Document - Lab Reports
d5195d6c-0837-5bc2-a127-59c598119d4c | note | Frequency - 1 test per material type and no less than 1 test every 5,000m³ (in place)
2b86371a-ca46-5d15-a45f-6bc5114324c2 | note | Verification Activity: Activity - HP
3d9bc47d-919b-5fb1-a426-02f53544201c | note | Verification Activity: By - ENG
efde04cf-22a7-574a-b477-9b8b7846f4a8 | signoff | AUTHORITY HOLDPOINT
5c6bf488-9018-5698-aa4c-b7cc685e8eb0 | checkpoint | 5.02.03 - Plateau Density Test
d74c9e5d-6e08-56db-8233-b761a40f4a24 | note | Acceptance / Conformance Criteria - Compaction shall be undertaken using the higher of the two density targets. Plateau tests to be spread out evenly to be an accurate representation on what is coming into site.
652f5d09-22e3-5ad9-b3d2-69c02a82fea0 | note | Standard / Specification - BBO
b9591980-3522-55e3-8e1c-cd0fe43598e8 | note | Verifying Document - IANZ Lab Reports
4d21c09d-1072-5f9f-97b3-8462f41b15e5 | note | Frequency - 5 tests per 10,000m2
50a9463e-98ed-51cb-88a5-43d06bb14a96 | note | Verification Activity: Activity - I
f783f559-3ec6-51b8-8833-b0b15d300d88 | note | Verification Activity: By - ENG
e258c61d-5350-5dae-b9e9-a0be257e6c38 | section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
9b03c2bc-c48f-5466-8d4c-04b6d0c3c01c | checkpoint | 6.01.01 - Subgrade Prep
958c8338-5b33-51ce-8659-d282d5eb34a5 | note | Acceptance / Conformance Criteria - The subgrade shall be prepared in accordance with the requirements of the Geotechnical Works Specification in Appendix B, including proof rolling, Scala penetrometer and NDM testing at the specified frequencies.
1c1d25c3-1c0c-5119-94ac-3bb6d4bb68dd | note | Standard / Specification - PS 7.1 GWW
335a7fc5-352c-57ba-9bb3-3c7bff749696 | note | Verifying Document - Completed Earthworks ITP
d9e82ec7-9807-5637-b51a-fbbe61b0f902 | note | Frequency - Prior to Pavement Works
36c5a72d-b0fa-5959-811d-774112aef47e | note | Verification Activity: Activity - HP
ee1691c5-9e43-520a-b738-6b90b6530c8f | note | Verification Activity: By - ENG
e2d45569-ffc7-5edf-af41-be24dc51077f | signoff | AUTHORITY HOLDPOINT
62e56d58-cfd3-5dcd-ba27-0389837faac2 | checkpoint | 6.02.01 - Layer thickness
7b7395fe-8190-5681-b681-d4eca93de0bd | note | Acceptance / Conformance Criteria - Each layer shall be checked to ensure the required layer thickness is achieved which is a minimum of 250mm of AP200.
7d347154-06df-5db4-893e-adae1e00f98a | note | Standard / Specification - BBO
4d98a622-0994-57a0-9608-0d7413eb3ca3 | note | Verifying Document - Site Notes
f40e52dd-2b7b-51fa-9e2d-e1ed4b3a1699 | note | Frequency - Check every 20m
8ff8da8a-140d-547e-9822-9d5a7f92ec4f | note | Verification Activity: Activity - I
7c4f62be-ea24-57dd-b298-073e72488a7b | note | Verification Activity: By - SV
7b99f4b7-44b4-59d3-be98-fd308bb9b852 | checkpoint | 6.02.02 - Services Protection
18a79a9e-329e-5360-807b-4a37752c162d | note | Acceptance / Conformance Criteria - In instaces where there are services, a minimum of 400mm cover of bedding sand is required prior to AP200 being placed to protect and avoid piercing.
61f852a2-b3bf-5523-a04e-d6a41712ecb1 | note | Standard / Specification - BBO
80b01301-0ed7-587f-a585-2ddfc802886e | note | Verifying Document - Site photos/ records
151db57e-af12-5370-8719-5d8c8a235f3e | note | Frequency - Every services
4b417c25-0138-5339-bdec-1e7dae8e09a7 | note | Verification Activity: Activity - I
04678288-81cf-592d-9b2b-24ee6a863cba | note | Verification Activity: By - SE
1e0af15d-264a-5748-b80e-858ba1933f81 | checkpoint | 6.02.03 - Plateau Density Test
01696134-52fd-5b4b-b347-cac5edb38264 | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. Plateau tests to be spread out evenly to be an accurate representation on what is coming into site.
68b3ecce-8f03-5060-a480-467a519f97df | note | Standard / Specification - PS - Table 7.2 - 2.2
6396dfa4-48da-5f9d-888a-66e56d9e47e3 | note | Verifying Document - Plateau Density Report
bde06433-7507-597b-8b66-2bf38cce2fc1 | note | Frequency - 5 tests per 10,000m2
593a01b6-bc47-5e64-a8dc-07f9e3bdc755 | note | Verification Activity: Activity - I
2bf421ad-0e46-5280-8082-197e172dedea | note | Verification Activity: By - PE
df95ac0d-12e7-5f2d-8e05-d1e59aa51c25 | checkpoint | 6.02.04 - AP200 SIL layer compaction
d840ee6b-3f3f-54c1-9e52-ec4c52f07504 | note | Acceptance / Conformance Criteria - Further to Figure 2 of NZTA B/2, the acceptance criteria for compaction of the AP200 SIL layer shall be a Mean Value ≥ 98, and Minimum Value ≥ 95.
6e96ba7a-b57b-570a-b3b6-d8aa5312ca0f | note | Standard / Specification - PS - 7.3.1
da698b73-9b4d-5489-bc13-6c323384730d | note | Verifying Document - IANZ NDMS
6498eb4b-b819-5cb0-a6fd-306efe87a66d | note | Frequency - 5 tests 1,000m2, 1 test halfway (250mm layer thickness) and 1 test on top of SIL (500mm layer thickness). 10 Tests total per 1,000m2.
0981876e-f991-5fdb-9d7e-8f9fd3f950ae | note | Verification Activity: Activity - I
8e766ca7-76cd-5c96-9bca-6688761eeec0 | note | Verification Activity: By - PE
b7da25a2-1706-56d9-bf0c-ab152740d6a3 | checkpoint | 6.02.05 - Proof roll
ca8b507d-b30e-5b0c-927b-5b0eceda46cd | note | Acceptance / Conformance Criteria - The SIL shall be tested via Proof roll prior to Benkelman Beam testing. Proof roll to be under supervision of engineer and verifying document to be signed off by engineer.
ef4fc51e-0eab-58e6-be7d-843037d9324f | note | Standard / Specification - PS - Table 7.2 - 2.2
961871e0-1d7f-5952-a0e0-5b1d0f54c568 | note | Verifying Document - Site Notes
08c46cf8-7010-593b-bc20-514dc63f602a | note | Frequency - 100% of layer
a1721636-5d7c-5825-a375-27f7a3a2968b | note | Verification Activity: Activity - HP
fada9282-d505-5ef1-8b80-18e8d8bb2e38 | note | Verification Activity: By - ENG
8aeb4571-3694-52c9-a22e-a9dd129ae2d7 | signoff | AUTHORITY HOLDPOINT
a0785380-fd61-5bfd-8678-a44a68ec5f7a | checkpoint | 6.02.06 - SIL Benkelman Beam test
78f988c9-a17e-56f3-8239-9d9d93f3ca19 | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be carried out on the top of the SIL layer at the rate specified in PS Clause 7.4 and reported to the Engineer. Target Benkleman Beam deflections on the top of the SIL layer are 1.6mm (90th percentile) and a maximum of 1.8mm. Performance verification of these target deflections shall be confirmed by the Engineer on review of results from within the pavement Stabilisation trial (PS Clause 7.3.3).
4202d00b-497e-5e0d-a724-4178a060f8bd | note | Standard / Specification - PS - 7.3.1, PS - 2.2.16
2bd96a39-ce74-5995-863c-36c42778e94d | note | Verifying Document - Benkelman Beam Report
96228506-0732-56f8-98c7-b52e167ea5c2 | note | Frequency - every 10m of each lane – staggered between left and right wheel path. Min 48h Notice.
4f088441-bfaf-5fdd-a434-da9fbc7df354 | note | Verification Activity: Activity - HP
624f9233-1786-564f-929d-482eaf69643e | note | Verification Activity: By - ENG
3c89b0ec-4be3-513e-abf0-367c5d158a5c | signoff | AUTHORITY HOLDPOINT
10f025ff-7251-5430-bf3b-56f5dcf76850 | checkpoint | 6.02.07 - SIL Inspection
47e80799-51b1-5c6a-bf2f-cc22a1ead256 | note | Acceptance / Conformance Criteria - Before laying of any pavement SIL and metal courses. SIL inspection to be carried out under supervision of engineer, verifying document to be signed off by engineer.
b70014cb-3981-5575-99b1-f78bd13b5599 | note | Standard / Specification - PS - 2.2.16
2524d696-5c6c-50ee-ac58-ae9b63a0062d | note | Verifying Document - Hold Point Release
53ba4b1d-5715-5388-b0a7-db5d0271dc42 | note | Frequency - Min 48h Notice
3a79f8c1-45d6-57b9-8381-0ff3a57d6316 | note | Verification Activity: Activity - HP
7a76cac5-6b1e-5ed3-ad08-272e9ae3e1de | note | Verification Activity: By - ENG
97bb6f89-11b3-5fc7-a453-48b0f0ec5d36 | signoff | AUTHORITY HOLDPOINT
9e953047-9f70-59b5-9189-aff3fc3bb70f | checkpoint | 6.02.08 - Topography
52d9391d-24c7-5f70-b1b0-5db5f76a5bbc | note | Acceptance / Conformance Criteria - Carry out level check on trimmed SIL. Survey conformance with Total Station. Tolerance = -30mm +0mm (NZTA F/2).
50fefc58-87dd-5c21-9973-e4146aff6fe1 | note | Standard / Specification - NZTA F/2
715a071e-2e75-5886-bd5f-377aaf0676cb | note | Verifying Document - Survey PDF against IFC or similar
8c663fad-9b5b-5f8e-889f-47f48a28a394 | note | Frequency - every 1m across the road (avoiding islands) at 20m intervals
1ebdd31b-775d-5cc7-ac53-4f493563334e | note | Verification Activity: Activity - R
3ea56599-c9e1-58cf-baf5-370d39ccc7af | note | Verification Activity: By - ENG
d150fc5a-aaba-5596-871b-54ab2e33d2c7 | section | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
8d4e531c-688a-5145-b348-98da13114f31 | checkpoint | 7.01.01 - Construction Record Compilation
f464ae83-eb06-538a-bb1a-4ad7d0d1a9e2 | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
69bb90df-4780-50c6-8e22-7ff538f201ea | note | Standard / Specification - Downer
91dd33e1-2376-59ff-af17-91c40bb075d2 | note | Verifying Document - Records
e6f4cdbd-f1c0-558b-b462-cfe7c77babb4 | note | Frequency - Post construction
3c061ce3-a053-513f-9871-c93507432463 | note | Verification Activity: Activity - H
84dac486-bdde-5968-bb8a-ae515d5122ea | note | Verification Activity: By - SE
19dccd2f-6441-5680-bbbb-459afb3e1dd8 | checkpoint | 7.01.02 - Survey Records
0ac1e123-4f48-505c-a410-d4a5c73c5b1f | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
fc7875d2-1020-5abe-838d-047371bcd10d | note | Standard / Specification - Downer
e79e64fc-93d8-5e8d-b06e-69f33f888e4f | note | Verifying Document - Records
d351c1a1-4a72-5d10-b94f-108b68b24ace | note | Frequency - Post construction
17ffbb98-dd3d-5541-89b2-f9730258be9c | note | Verification Activity: Activity - H
2b244de3-d7ed-58c6-9d6f-c99b39b092c9 | note | Verification Activity: By - SV
b068bae6-2ef0-5d88-81c8-4fb6749be6b3 | checkpoint | 7.01.03 - Redline Drawings
52e0efca-22b1-5f73-ba83-8c6eba817c67 | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red line to show any increase in SIL depth.
bea7c94f-2a21-5e8d-af76-2797f07c3a10 | note | Standard / Specification - Downer
a804c94e-909f-5111-9f6d-8c9f89d44605 | note | Verifying Document - Redlines
729664ad-6783-5794-8bcc-16e8f378c377 | note | Frequency - Post construction
053cc7f0-16a2-501d-9e34-5610eab1e4f1 | note | Verification Activity: Activity - H
e8c8730a-2448-5ae8-b052-b0ce0c88b6b1 | note | Verification Activity: By - PE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
4291276e-85d0-4e51-aabc-2b82b1b67809 | checklist | ITP - 118 - Hard Landscaping Rev D | itp | ITP - 118 - Hard Landscaping
d4bba13d-305c-4602-95d4-5c8e06c9fa54 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
46b49c54-9cd6-4634-b593-87a9e04b592a | checkpoint | 3.01.02 - Survey Setout
7d6fe42c-986f-5bf2-9be5-a0f0901e979f | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
4b1f60da-653e-5038-972a-e640815c71b6 | note | Standard / Specification - Downer
c2207c40-09bd-528f-a259-46a7f0fe915b | note | Verifying Document - Survey Records
510eaf36-ee2a-54f5-8ddc-32f781cb2592 | note | Frequency - Prior to Works
3ef4a88e-ef74-5d6c-bbdb-0472f1a4c111 | note | Verification Activity: Activity - H
15be2562-e869-5ecb-9cdd-4ccdb3accbf8 | note | Verification Activity: By - SV
c5c62e6b-1758-4e0f-92d7-321c6fd62bc1 | checkpoint | 3.01.03 - Service Location
2b5dc292-7306-5ffa-a88e-880460fce6b8 | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
53af5bbe-4ef5-56db-9bda-a5f397528836 | note | Standard / Specification - Downer
80ce1121-0550-5153-a31c-cda49b524c40 | note | Verifying Document - Excavation Permit
30b4c4bf-f756-575f-8fdf-a5526e427c23 | note | Frequency - Prior to Excavation
43039871-17d3-5cf8-b2ad-48610ccdfe1d | note | Verification Activity: Activity - H
1367266f-2466-5418-8b4b-37dcdb9640da | note | Verification Activity: By - SE
9fe291b7-fa41-4262-93eb-c22e4f989a6e | checkpoint | 3.01.04 - Internal Permits
770b2d02-e711-5790-8533-49c3c4935b19 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
f22c7e6a-4516-5051-a667-bf551126d480 | note | Standard / Specification - Downer
69b2e771-249c-5c4a-a345-cd7aaf6cf1e2 | note | Verifying Document - Internal Permits
db6e97a0-8e29-5f0a-9ad8-04b05c4cf2f6 | note | Frequency - Prior to Excavation
e9ec28c8-468d-5675-a435-5958b581ddf6 | note | Verification Activity: Activity - H
905bc7d6-61f4-5320-825c-d8e51eefe1d2 | note | Verification Activity: By - SE
d92a7a73-75b3-4561-9ec6-a29c992c9d5c | checkpoint | 3.01.05 - External Permits
6a0d0658-40f3-59d1-8b18-76a4f88580df | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
33c1ba76-930e-55a2-92ab-aa3a6a0c6e6a | note | Standard / Specification - Downer
26f5d7a5-4192-5feb-a8fb-15cb94d18868 | note | Verifying Document - External Permits
e8d7634a-0f2e-5d88-be85-dbb879ab7909 | note | Frequency - Prior to Excavation
d6944de0-bd46-5140-8539-1ce158b5be37 | note | Verification Activity: Activity - H
1d770408-1d31-5a9a-9259-aa6b3ea3e797 | note | Verification Activity: By - PE
129ad3a5-de63-44a9-a60b-63452fe9d455 | checkpoint | 3.01.06 - Approved Construction Drawings
6e1a4726-5159-50c2-996a-31f13ff62962 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
0ff62e0f-3a4e-57ff-8339-45518b436480 | note | Standard / Specification - Downer
fd66b635-5678-5a55-9b7f-ad4203e3f8f6 | note | Verifying Document - IFC Drawings
e164a1be-5d3d-5ae2-9e3f-a80e799b6837 | note | Frequency - Prior to works start
25f7af7b-c42a-5929-93a6-5ede3c2e76f6 | note | Verification Activity: Activity - H
be5b2e8f-5191-5a8e-8c98-c5eb6bc547ca | note | Verification Activity: By - PE
9dee24bf-9055-4385-a47c-7bcb262fb0e9 | checkpoint | 3.01.07 - Previous Lots
ea4a7db1-81f5-572f-a187-bf0fb339c1b6 | note | Acceptance / Conformance Criteria - Landscaping works to only be carried out in sections where surrounding work that will cause rework has already been completed.
e70f45c8-f203-54ee-8330-da424549ed6f | note | Standard / Specification - Downer
3b5c62cf-9cbd-5f61-8753-96abeee28eb8 | note | Verifying Document - IFC Drawings
ce3d8c35-9869-5b05-a4f9-87afbc496581 | note | Frequency - Prior to works start
c21b8c0d-ab42-5a7e-a10f-2fe1120cc731 | note | Verification Activity: Activity - H
5e968a55-abc8-5350-a4b8-2b1dba228c8e | note | Verification Activity: By - PE
ec708d9d-3c2c-4cab-866d-df31c650504f | checkpoint | 3.01.08 - Subcontractors
b26aa014-aaa7-5232-afff-17c0e3a0bd44 | note | Acceptance / Conformance Criteria - Ensure that subcontract and supplier agreements have been completed.
1ddc3838-4a8c-5437-82db-df3a722fde3f | note | ○ All subcontractors have been inducted.
1e6af1e2-75b7-5938-a0b3-a3b35e6c8f92 | note | Standard / Specification - Downer
b7d30496-b5b9-5a19-81ee-ad6b75e00fee | note | Verifying Document - IFC Drawings
1d5a7bf7-f422-5ff0-9161-b76f4fa74521 | note | Frequency - Prior to works start
ad35d24c-1e73-5020-95ee-34aef7d28385 | note | Verification Activity: Activity - H
cbf021a9-d8ac-5ae8-9e4b-960c81d4129a | note | Verification Activity: By - PE
71bab3a0-c604-4f98-b214-849a4e3d775d | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
2c9885c9-e804-44e7-bfa2-c758402ee2ac | checkpoint | 4.01.01 - Concrete
b3b6ae3a-1e3d-539e-a030-747fc44ce6e7 | note | Acceptance / Conformance Criteria - Minimum 20MPa concrete to be used for landscaped structures.
74534d7c-f3f8-5f77-bdf6-6c4f00529648 | note | Standard / Specification - Designer
3a92993d-a6b4-5697-86e1-d621d4d82527 | note | Verifying Document - Concrete Delivery Dockets
127c2525-4303-5335-ab86-e5b196148fb1 | note | Frequency - At delivery
aa8ef16d-e824-5752-963a-02a0f2b4fa1c | note | Verification Activity: Activity - H
6b3ce0af-0b14-5303-b57f-5888ce70fed8 | note | Verification Activity: By - SE
398d3f33-0e7d-46ac-bbfc-757860a3fc61 | checkpoint | 4.01.02 - Timber
ab5979d6-160d-5d69-85a0-b19a5195c746 | note | Acceptance / Conformance Criteria - Dimensions and grade as per drawings.No specific grade required unless noted otherwise.
cd01162f-2de0-5a86-9340-81ec4a56bb5d | note | Standard / Specification - Designer
15365134-a437-5e3d-bbc5-6a5337485b62 | note | Verifying Document - Site Record or Dockets
6ccc5992-1338-5435-ac06-aff1ed7d7bac | note | Frequency - At delivery
f94124e2-52c2-58a7-9ed8-25c2e8971976 | note | Verification Activity: Activity - H
2a829ec5-6230-5cab-af30-500d1c4bd5e0 | note | Verification Activity: By - SE
2f893049-548d-4cbc-88a7-5d9c60299df9 | checkpoint | 4.01.03 - Paint
eb7c21ed-8a45-5a9f-bb9e-83f9fe8eafe6 | note | Acceptance / Conformance Criteria - Dulux Weathershield x10 grade. Specific paint colours noted on drawings.
fdf69fd0-2dbe-5848-a875-d8ae47302e8d | note | Standard / Specification - Designer
9fbf21a5-433e-5df7-a10e-80be23475ccf | note | Verifying Document - Dockets
78a58975-72c2-5ac5-a2e1-73a2a5fcd97d | note | Frequency - At delivery
c728b977-4598-522a-a152-3346d8e2ecdf | note | Verification Activity: Activity - H
5a3ee192-5857-5da8-b265-448461db2333 | note | Verification Activity: By - SE
f6d3aaa5-fcc9-4470-8606-6721972db453 | checkpoint | 4.01.04 - Informal Path
2d400f0c-f47f-57bb-81c3-dbb7c38f8977 | note | Acceptance / Conformance Criteria - GAP40 to be used for the 100mm base layer of the informal path.
e4f783db-d54f-537f-8be8-e5dfcc57fb7e | note | ○ Any clay is suitable for use in informal path capping mix. 80% GAP20 and 20% clay.
f73e3694-39f0-5ef6-bbb7-b6349a68062b | note | Standard / Specification - Designer
fde627b1-7f94-55a8-a62b-296fee69ad9d | note | Verifying Document - Mix Approval Dockets
549d9888-7bef-5b28-b49b-fa42db59c826 | note | Frequency - At delivery
696e77e5-fa78-5da6-a61d-8df2c1b3e4c8 | note | Verification Activity: Activity - H
31466fb8-6b12-511c-b973-faae1375549d | note | Verification Activity: By - SE
f4828050-fea7-4d86-87df-4e5b16e0e5e4 | checkpoint | 4.01.05 - Fixings
eb6bc960-d8ad-5a01-89d4-88dbb79bf698 | note | Acceptance / Conformance Criteria - Dimensions and grade as per drawings. No specific grade required unless noted otherwise.
bd2ec363-b486-5868-ba5e-d04b73896794 | note | Standard / Specification - Designer
74148234-50f0-5b3b-9241-6a559d7ec3f9 | note | Verifying Document - Site Record
433dd558-9e70-5c1f-ab58-a1f3cf331d5a | note | Frequency - At delivery
b93e7e57-47a3-54bb-9b51-80adfbaf4beb | note | Verification Activity: Activity - H
2c4eb58a-abc4-5dd4-8c8d-fc33eae8a20a | note | Verification Activity: By - SE
53df388b-12a6-4e22-94a6-30dc4c83ca7c | checkpoint | 4.01.06 - Steel Rebar
99f6da7e-5d9a-53f9-b5d4-1774eb474695 | note | Acceptance / Conformance Criteria - Rebar for concrete play on the way items to be suitable.
6b8e3edf-454d-593f-b37c-f15d6e5f8c6e | note | Standard / Specification -
67b8eb8f-6acd-5ff6-a693-bbadd8979533 | note | Verifying Document - Mill Certificates
b4fb4a8c-5f15-5b0a-ad97-10fc2f03b1db | note | Frequency - At delivery
337f748f-4c63-58ef-80b6-bb25432622fe | note | Verification Activity: Activity - H
0c2c3ab1-e458-511b-9eb9-ed086b056e8c | note | Verification Activity: By - SE
760f8906-b972-426f-8cbd-833c94804842 | section | SECTION 5 – CONSTRUCTION ACTIVITY
54a23e0f-4b22-487e-bebe-4baead8e3878 | checkpoint | 5.01.01 - Climbing Trunk
ea982e18-8e63-5ef5-af79-5c824999c783 | note | Acceptance / Conformance Criteria - Tree trunks to be inspected and selected by suitable authority (BBO, HCC)
92bc59c8-14ca-538e-afa5-945a93653437 | note | ○ Tree trunks from felled site tree. Bark to be removed. Retain side limbs for stability.
6075d2fd-e67b-5667-977f-ba06c1fb7b8e | note | ○ Chamfer ends of branches. Minimum 100mm of mulch surrounding trunks.
6ce7f451-0ba9-5e38-92a3-a0c22a44c686 | note | Standard / Specification - Designer
4255b535-6834-5f00-9302-eb7d7d29fb64 | note | Verifying Document - Inspection Record, Photographs
46d037af-3cb1-5f99-89d2-ff0068eaad5c | note | Frequency - Per Item
b3df1c71-7a39-5fe6-b2ff-7ddfd1f609e7 | note | Verification Activity: Activity - H
478f2b3f-f549-577c-a622-250b49efb51c | note | Verification Activity: By - SE
af75309b-b489-4b51-8f02-593cbf355d40 | checkpoint | 5.01.02 - Post climb play unit
05312329-07b9-50ec-8e89-85daf785eedf | note | Acceptance / Conformance Criteria - Laser log climbing post with 100mm recessed bands and climbing foot holds.
c3df0bf4-25d8-5101-ae59-251b307da796 | note | ○ Painted in Dulux weathershield x10 in colours shown in detail.
4e3970e7-c6ab-5491-b2a0-23b2d164864c | note | ○ H5 painted post with chamfered top set into concrete footing.
e7c3b024-6386-5ae1-8b35-a46f0b2099f1 | note | ○ 150mm diametre climbing posts set into concrete footing.
e4fad8d3-2b4d-5025-8980-e8fa8c0b6bd6 | note | ○ Concrete footing 600mm deep, 350mm wide.
21e7eb9a-a511-54c2-a416-185f87c464f3 | note | ○ Posts to be spaced between 500mm to 650mm apart between centres.
f1d0c7ce-25db-5f13-8e3a-7631618f99b9 | note | ○ 125mm H5 laster log sanded smooth prior to painting. 10mm chamfer to top of posts.
318aab08-17e6-5b2f-839f-06af354e732a | note | Standard / Specification - Designer
6cadb5f4-c6bd-5299-9585-99f1648159ab | note | Verifying Document - Subbase Material Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Photographs showing Dimensions
68dcc84e-6dff-53bf-9015-f6965599838b | note | Frequency - Per Item
e11cf60a-0c7f-5678-b068-50263bc03a32 | note | Verification Activity: Activity - H
c4cf63f3-cfc3-5d8d-8aaf-945301339e10 | note | Verification Activity: By - SE
5bdd756a-9f75-471d-ad9e-e9a03be325e9 | checkpoint | 5.01.03 - Balance Stepping Log
db69d3a9-9fec-5e53-856d-18c362650d4f | note | Acceptance / Conformance Criteria - Logs buried 300mm below ground with well compacted crusher dust to stabilise.
175e6fb7-f53d-5a8e-a358-4f6f767e1860 | note | ○ Logs stripped of bark and treated 2 coats of linseed oil prior to imbedding into crusher dust.
3d6f52e9-d7bb-5b95-8ff4-9abb05d39a0e | note | ○ Leading edges to be chamfered. 100x25 H4 timber edging to contain 100mm mulch surfacing.
72e17807-b9d9-5d43-84ca-aba7d1ffb2db | note | ○ Use felled tree trunks for logs. Logs to vary in size and height.
c92bbc55-1929-555c-a4ca-9c05802b7ac7 | note | Standard / Specification - Designer
7a03eb3d-2f11-5f20-910c-0f495e824ce0 | note | Verifying Document - Subbase Material Delivery Docket, Log Dockets, Foundation Clegg Test, Concrete Delivery Docket, Photographs showing Dimensions
f1c25a92-5165-58df-a60d-78dc2a6bc824 | note | Frequency - Per Item
be068c81-82fd-5e2f-a85b-dc8815b41050 | note | Verification Activity: Activity - H
43a575ac-8e7b-5612-ad91-7e792dde8985 | note | Verification Activity: By - SE
389d595a-b877-41aa-b561-5ce2177138ee | checkpoint | 5.01.04 - Four Square Ball Play
b0c410f3-545c-56f7-bf77-f62d7b3144b9 | note | Acceptance / Conformance Criteria - 150x25mm H4 timber edge set flush with grass.
bfd63660-bae0-5cf8-868b-5182b0a2bf44 | note | ○ Coloured paint system over 100mm concrete base.
6e379775-3fed-55a6-9e5d-a27ef682bd6b | note | ○ Mask off squares prior to painting.
9fec14d1-4b3d-5ebb-9a79-16662eca5be3 | note | Standard / Specification - Designer
d8b9eda0-1fe8-57cb-86f6-54eb52f52036 | note | Verifying Document - Subbase Material Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Photographs
dade63ca-62c7-5c32-a522-18d0f3638524 | note | Frequency - Per Item
7960598d-28d3-5e52-bb87-746322477229 | note | Verification Activity: Activity - H
0cd7ffe7-504a-5fd9-83e3-31c6d7b5d599 | note | Verification Activity: By - SE
b349406a-d519-4860-b648-ea8c19600cde | checkpoint | 5.01.06 - Stepping Blocks
15ccdebf-66d9-53a0-8cf4-ec7534983264 | note | Acceptance / Conformance Criteria - Concrete has 10mm chamfer. 200x550mm concrete footing with toe 100mm either side.
1f39d74d-cdfe-52ae-a97a-b434c40a2504 | note | ○ Lengths as shown in the drawings. D12 rebar at 250mm centres with c-links.
e7887c15-13b5-520c-9bc2-c047e9d43f7e | note | ○ Backfilled with 300mm topsoil and covered with 100mm mulch.
456be826-f041-5bb2-9515-56916dfebcb3 | note | Standard / Specification - Designer
46ca22b7-20c7-5d8a-96d3-dc15672bb7d7 | note | Verifying Document - Subbase Material Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Prepour Steel Inspection Photographs
6c5b4b89-454c-5185-9b97-6d16a97f1574 | note | Frequency - Per Item
9b510815-1de4-50e9-ae70-35f0ef23e7aa | note | Verification Activity: Activity - H
524a8645-fb8f-5d6b-8825-af9c5c3645e0 | note | Verification Activity: By - SE
e3133803-ba0d-409f-a583-897f048f1017 | checkpoint | 5.01.07 - Concrete Balance Beam (straight)
5bccbc5b-8829-541f-9022-ddf93ebe1017 | note | Acceptance / Conformance Criteria - Dimensions and paint applied as per drawings. 200mm wide, 350mm deep, 6000mm length.
212eb1a3-9541-5339-9a97-e04565126233 | note | ○ Fair face finish.
ea10d29d-41fe-560f-8448-51a57d178290 | note | Standard / Specification - Designer
90733dee-1f40-59ff-9871-7e82d70dd53d | note | Verifying Document - Subbase Material Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Prepour Steel Inspection Photographs
961c3f21-130f-5568-81cb-76e187db25b5 | note | Frequency - Per Item
e669f333-1868-5689-b8df-bf2bb252f44c | note | Verification Activity: Activity - HP
68845ad1-3aad-5baf-8ccf-d10d7c4c46a7 | note | Verification Activity: By - ENG
46dfc502-a8c7-4c13-903e-e0c97ca29389 | signoff | AUTHORITY HOLDPOINT
baac0313-3525-4c86-a964-0350aede8c60 | checkpoint | 5.01.08 - Concrete Balance Beam (curved)
77271f99-ae6e-5ee6-9d4f-6cb7074abaa9 | note | Acceptance / Conformance Criteria - Curvature as per drawings. 350mm deep footing, 200mm wide, 4000mm long. Fair face finish.
bb27542f-93df-5ccc-a262-278eb878f88b | note | Standard / Specification - Designer
a9422d8c-2621-56e4-b635-708a195e5be9 | note | Verifying Document - Subbase Material Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Prepour Steel Inspection Photographs
37cb0379-8cef-5733-a259-054062d2bbcc | note | Frequency - Per Item
e948ac24-601e-55a1-9466-848876c881e7 | note | Verification Activity: Activity - HP
1828ad5c-94dc-5067-8f6e-1f174c3832cf | note | Verification Activity: By - ENG
6799ee44-165c-4316-b5fc-8ece1edd0052 | signoff | AUTHORITY HOLDPOINT
e875c230-0674-4efd-a318-4f09e48e7814 | checkpoint | 5.01.09 - Timber Balance Beam
dbccb8e8-f0e5-5eca-ab6b-5e289878491a | note | Acceptance / Conformance Criteria - Ensure correct beams are used in correct place. Beams to be embedded 500mm into concrete footing. Ensure correct nuts and bolts are installed as per drawings. 600mm deep concrete - 500mm embedment and minimum 100mm concrete beneath post. Posts to be covered with 100mm mulch.
38f26921-f22e-55f0-bee8-a2dd7e9f80ce | note | Standard / Specification - Designer
e0b0b976-ed19-55fc-901e-15b5b0b184b9 | note | Verifying Document - Concrete Delivery Docket, Prepour Inspection, Photographs
9afdbd28-b871-5d5b-8303-84cbdc840ce0 | note | Frequency - Per Item
1594db84-3b5b-52ba-a535-2ccc0e10c9b8 | note | Verification Activity: Activity - H
899ad3a5-d33a-59f9-9c64-3883a41abcb6 | note | Verification Activity: By - SE
caaaf31a-80e0-42e8-b3f0-f97f68408fee | checkpoint | 5.01.10 - Stepping Stones
07159115-6c41-5d06-b116-b3b91b1035cb | note | Acceptance / Conformance Criteria - 300mm topsoil surrounding boulder. 1/3 of boulder to be set in concrete.
3e20259c-24ba-5d46-b3cf-a535f8321bba | note | ○ Boulder to be surrounding with 100mm mulch.
7034dd98-a103-59d6-8baa-ba06ea1a9c8f | note | Standard / Specification - Designer
d756c9ee-e561-5fcf-af66-a895d61434ec | note | Verifying Document - Subbase Material Docket, Foundation Clegg Test, Concrete Delivery Docket, Prepour Inspection, Photographs with Dimensions
d0b832b7-bfba-51b7-9248-f8c15011644f | note | Frequency - Per Item
a5818617-296c-5a82-8bfb-56859e3de911 | note | Verification Activity: Activity - HP
13c23d40-720a-5b86-9521-cfa7cfad2a41 | note | Verification Activity: By - ENG
6e0b96fe-3521-4793-82c3-00e8fd7c31bc | signoff | AUTHORITY HOLDPOINT
576ce327-f985-48b5-806b-18110f12ffa6 | checkpoint | 5.01.11 - Concrete Wall
3af4a663-447d-5075-a4de-2c806897fd8d | note | Acceptance / Conformance Criteria - Concrete footing to be placed over well-compacted GAP40 subbase.
c6c7e89d-0e68-533c-b3cc-074c3f569c7c | note | ○ D12 rebar located at 250mm centres.
5653f06e-944c-5d22-a64a-95435a916423 | note | ○ Leading edges to have 100mm chamfer with fair-faced concrete finish.
7d804630-bb55-53e7-9089-00aabf47eea7 | note | ○ To be painted with specified colours as shown in drawings.
aa4ef718-2ec0-5dcf-8b04-d98b28434a9f | note | Standard / Specification - Designer
83191841-9ce2-5d9d-99e5-812845aea317 | note | Verifying Document - Subbase Material Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Prepour Steel Inspection Photographs
fb809af1-9091-582c-ab32-b674df244f16 | note | Frequency - Per Item
52a412be-5849-59a5-a12a-ef505643570d | note | Verification Activity: Activity - HP
95f7388e-8f11-5c32-a2a7-9146b3ee1986 | note | Verification Activity: By - ENG
a8aa8843-1f85-4f8d-9b04-2a2193203fa7 | signoff | AUTHORITY HOLDPOINT
a4e01278-fad1-4885-bd76-fca78da1fbc5 | checkpoint | 5.01.12 - Timber Stepping Logs
fde8fb73-66af-575a-8886-b2342ee4fad8 | note | Acceptance / Conformance Criteria - Posts to be spaced about between 200-250mm.
a4071b96-ffdc-5044-909f-f23a0778cd8c | note | ○ 600mm deep concrete; 500mm embedment and minimum 100mm concrete beneath post.
b6b59d75-95e3-5de1-9912-6fe021866712 | note | Standard / Specification - Designer
ddc98496-7bff-5c55-8380-46db432b443e | note | Verifying Document - Subbase Material Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Prepour Inspection, Photographs with Dimensions
0faa7223-974d-5efc-9f71-087011e455c4 | note | Frequency - Per Item
29c0aa38-04a8-525e-a7a0-4b0a3d089148 | note | Verification Activity: Activity - H
1c326131-e79e-52d7-8de8-f63f59b7899c | note | Verification Activity: By - SE
72adcdc0-5d65-42df-a4b8-61678017b5eb | checkpoint | 5.02.01 - HCC Signage
6746c30e-69ce-5938-bd59-bee7aaaf0fea | note | Acceptance / Conformance Criteria - Signs to be confirmed with HCC Parks and Open Space.
c11e87cf-eadf-5df6-af76-2bd1fc96a8d5 | note | ○ Signs to be concrete in 400x400x900mm concrete footing.
103065bc-c857-557c-9245-bd6dafaf64b4 | note | Standard / Specification - Designer
09833007-500b-5e8a-ae55-897157593abd | note | Verifying Document - Concrete Delivery Docket, Prepour Inspection, Photographs
46d23e0f-7174-586e-bea4-186f28f786eb | note | Frequency - Per Item
df92f7c0-369d-5aaf-a2b3-b43cf52fb1fd | note | Verification Activity: Activity - HP
bae16f69-05c2-5ef5-aea6-a05211b72fa9 | note | Verification Activity: By - ENG
b2bb351e-eee8-4f0b-8a68-e45e7b942188 | signoff | AUTHORITY HOLDPOINT
53161767-7aab-4614-86b2-0eed254fbefd | checkpoint | 5.02.02 - Drinking Fountain A280
01210044-2f04-5d5d-ab66-86fcbd1c11e3 | note | Acceptance / Conformance Criteria - 40mm diametre waster outlet pipe. Anchor bolt fixed to concrete base. 100mm thick concrete pad beneath table over 150mm thick compacted GAP40 subbase.
ee1c388b-9110-5f14-a330-c0801c2c7ae9 | note | ○ Precast pit with locable cover and isolation valve on supply line.
5322e9de-ee3b-53e4-8ed5-bbef3b116c64 | note | ○ 50mm thick drainage layer with 15-20mm aggregate.
a9a567b4-fd90-5f6b-9588-8978420c927f | note | ○ Precast drain unit with steel drainage cover with surrounding 1:40 fall into drain.
3518954f-0e99-504f-bfe3-1f2276013dda | note | Standard / Specification - Designer
851c6c97-2676-5e34-9d14-c4b0c7a10d92 | note | Verifying Document - Subbase Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Photographs
2f5e5819-f66f-561f-9eb4-10a57fd436bc | note | Frequency - Per Item
9e22ddf9-c789-5aa9-8063-a596a6621295 | note | Verification Activity: Activity - HP
69bb6c88-c8fe-50ce-b3c1-f16c692b60ef | note | Verification Activity: By - ENG
e552ebc9-965f-4a45-883c-8a88b84a988c | signoff | AUTHORITY HOLDPOINT
be98c64a-c999-4031-8659-577841ef0925 | checkpoint | 5.02.03 - Type D Cycle Stand
54550eee-91c0-5cff-b96e-145bfea7a8cb | note | Acceptance / Conformance Criteria - Mountain plates installed into 200mm thick 20MPa concrete path.
655329fd-200d-5f52-9030-a388d570506c | note | ○ Exposed aggregate concrete slab to be installed as per Engineer's requirements.
e1502a72-e959-55a4-9ec0-e5fda3370b60 | note | Standard / Specification - Designer
9459a1d3-6357-5217-8667-ab3144ead8df | note | Verifying Document - Subbase Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Photographs
3865302b-6fa1-56c0-9c64-bb3b0ca1e08c | note | Frequency - Per Item
8eb2288e-b7ea-5492-b93f-8f7c82b0b80e | note | Verification Activity: Activity - HP
ea37df39-343d-5150-ba0b-c04e2a795e50 | note | Verification Activity: By - ENG
5d14a706-b854-4da7-aa83-fb5e7a62281f | signoff | AUTHORITY HOLDPOINT
d253fbd5-fabf-4139-ae2a-efb74bfdf4be | checkpoint | 5.02.04 - Portland Picnic Set with Central Leg
902ec4fb-82f9-50bc-b602-cf16b1d2f4cc | note | Acceptance / Conformance Criteria - 400x400x1000mm concrete footing.
acf1e7e5-dbf9-5b86-b914-2be5c4a233ce | note | ○ 100mm thick concrete pad surrounding footing placed over 150mm well-compacted GAP40 subbase.
9bae641c-e9c9-52b2-9e0d-6937998d1fad | note | Standard / Specification - Designer
01e74a3d-efbe-508a-9f72-bb8383471b75 | note | Verifying Document - Subbase Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Photographs
83dec95f-8637-510b-a0bf-20c9da630d86 | note | Frequency - Per Item
cdfd0a44-1d35-592d-a1c1-a901613b1ae2 | note | Verification Activity: Activity - HP
1cab72c9-9328-5107-af2f-ba62071cff5b | note | Verification Activity: By - ENG
4c7da544-6660-40da-886c-eb86c551b738 | signoff | AUTHORITY HOLDPOINT
013207ab-8237-4cbf-a8cc-20716c0f72f8 | checkpoint | 5.02.05 - Spinnaker Bin
b06c5106-0ffb-59b0-a42c-dae768d04033 | note | Acceptance / Conformance Criteria - 100mm thick concrete pad beneath bin over 150mm well-compacted GAP40 subbase.
696d6844-5993-57d0-ace8-7dbe4496926b | note | ○ HCC to confirm finish material (s/s electro polish, bead blast or ms galv powder coat).
1482e0fa-7040-57f3-b1f9-9daa09e603dd | note | Standard / Specification - Designer
904191a1-f0b6-5daf-9f59-24edfe2429dd | note | Verifying Document - Subbase Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Photographs
0a1e38c5-bb93-5d5e-96fa-bf1344b334fe | note | Frequency - Per Item
b59e40c3-52e6-5c2c-ae5d-172fcab530a6 | note | Verification Activity: Activity - HP
0a250f89-6578-5656-a306-1280a9c557c7 | note | Verification Activity: By - ENG
ce67b030-c65c-4dc2-90d0-698757e894eb | signoff | AUTHORITY HOLDPOINT
e98ffb59-7471-42d4-85eb-08bc6f093819 | checkpoint | 5.02.06 - Surface Mounted Waihi Seat
a9695f74-4426-5f7f-88bc-eac57b8548ab | note | Acceptance / Conformance Criteria - 1800x600mm Street Furniture seat with back and arm rests. Surface bolt mount to concrete footing. 20MPa concrete pad beneath seat over 150mm well compacted GAP40 subbase.
6c94e9d1-ec19-52bb-9a91-02ae1da6e343 | note | Standard / Specification - Designer
5f596b1e-70a4-5d8e-83ad-bab8c802fba5 | note | Verifying Document - Subbase Delivery Docket, Foundation Clegg Test, Concrete Delivery Docket, Photographs
2cefb7a6-02ed-5d4a-8bbe-f027bf8b5f06 | note | Frequency - Per Item
a14c42da-03ae-5fc6-aa31-179d3daec58a | note | Verification Activity: Activity - HP
e7e3a905-c1f1-5a47-beb0-8d82410e6275 | note | Verification Activity: By - ENG
ba86200c-d60b-47ba-a03e-18f1c66f5b7b | signoff | AUTHORITY HOLDPOINT
83a5e562-f7f6-465a-9a8a-7d32bd65bf14 | checkpoint | 5.03.01 - Ecological Tree Stump
c9bc6640-ef2a-5441-9ba0-e93f63dc006f | note | Acceptance / Conformance Criteria - Tree stumps with dirt removed, laid on side and anchored to 100mm H4 Fence Post driven 500mm into ground. Wire achor to post. Ensure stump is stable position on ground to prevent rollover.
6965572c-a919-53b4-b2e5-403d98b5f4d2 | note | Standard / Specification - Designer
9b053280-8af4-5719-b6e7-ee0982fa01c4 | note | Verifying Document - Inspection, Photographs
25d00590-a807-5f27-8720-cab4a7ce3b65 | note | Frequency - Per Item
8635dc51-9881-5cea-887a-e2ea1854ebe3 | note | Verification Activity: Activity - H
ccbb19ba-4904-5d0a-bdc1-5234c1e94d98 | note | Verification Activity: By - SE
c93a107f-b7b6-412e-8367-96d8d903fe7f | checkpoint | 5.03.02 - Log Stack
b8aaefd5-1c76-5b0f-a52c-034822fd1375 | note | Acceptance / Conformance Criteria - 100mm diametre H4 fence posts driven into ground 500mm to anchor log stacks. Logs from 100 to 200mm diametre from felled trees to be laid in stack up to min. 750mm unless otherwise advised by designer.
119b60da-6d1d-53d7-85ad-f0c27d837c27 | note | Standard / Specification - Designer
47ac05ea-f605-5661-b77a-d4ac9a00ea86 | note | Verifying Document - Inspection, Photographs
e9d3d258-3c1c-561a-a6d7-450a3cb6f9ee | note | Frequency - Per Item
8d3c2694-62d4-5072-8cf5-cbfe5abd820d | note | Verification Activity: Activity - H
1e5110d6-4b70-5da9-bfbb-c38bd9283abc | note | Verification Activity: By - SE
6cb35ea6-dc82-4eee-a5a2-7a340753bbf5 | checkpoint | 5.03.03 - Bird Song Post.
c1bb9773-8807-5ae0-a5fd-716af160338c | note | Acceptance / Conformance Criteria - 150mm diametre H5 posts with turned tops set in concrete footing within wetland areas.
6fc7ca7d-2d4c-572c-bfd3-0643cc632613 | note | ○ 450mm deep concrete footing, 100mm cover between base and post. 50mm soil coverage of post.
0cec9547-513b-5994-9921-953043028a38 | note | ○ Posts to be painted using Dulux Weathershield with colours as shown in detail.
1e508c35-b52f-5c8a-805e-361637e3112f | note | Standard / Specification - Designer
cb83e35b-29e1-58f0-8423-3d112d0ca66d | note | Verifying Document - Inspection, Photographs
f6e8f412-181e-50f8-b61e-03a501ced764 | note | Frequency - Per Item
fa6ed6b6-36c5-579e-a298-b9bb685e346e | note | Verification Activity: Activity - H
9b80584b-e6a0-5300-bcd1-159ec89ecd25 | note | Verification Activity: By - SE
630ee8cc-bdec-4002-91e6-8abaef35642e | checkpoint | 5.03.04 - Lizard Refugia (Disc Pile)
176b620a-1dad-5236-8fa5-a7ff0244b750 | note | Acceptance / Conformance Criteria - Wooden disks minimum 600mm daimetre, minimum 300mm thickness.
c4bdbab2-2eeb-5616-85e4-7b381707a557 | note | ○ 100mm nails on both sides for anchorage. Space disks between 5-10mm apart.
33d4ed18-9921-5641-812a-9da5ee441f50 | note | ○ Discs buried nomimally 300mm into soil.
9a073f3d-ee66-52ec-ac78-5ad26dee799b | note | Standard / Specification - Designer
67162758-5dc7-5da2-93e0-84790acfd723 | note | Verifying Document - Inspection, Photographs
4b1ef1e7-bf13-52ad-895e-f2209076316d | note | Frequency - Per Item
3a253014-1d98-542c-a55e-c7e01b02c042 | note | Verification Activity: Activity - H
078b5a4e-eb15-59a9-98c9-895b525c1d6a | note | Verification Activity: By - SE
31f9b098-4587-41fb-9d42-fa6de657ed6b | checkpoint | 5.04.01 - Base Layer
c0333fa7-5262-5cba-9d03-e626669f4674 | note | Acceptance / Conformance Criteria - Minimum 100mm of compacted GAP40.
bad4fca9-887d-5230-8059-9c98905003cb | note | Standard / Specification - Designer
045f6712-0f6b-5ef5-b391-e6dac61ab6be | note | Verifying Document - Inspection, Photographs
40f801d3-427d-5108-ad2b-8cb4d3ac0e9d | note | Frequency - Per Item
4819e9ad-0be3-508f-b2d6-7792bee4065b | note | Verification Activity: Activity - C
06158df0-0f82-54b8-9383-a3fbb61e04fe | note | Verification Activity: By - SE
9b5075aa-54c5-493f-bec8-f5d12244f395 | checkpoint | 5.04.02 - Capping layer
892cd028-5f50-51cb-90c9-dbae974f905a | note | Acceptance / Conformance Criteria - 50mm compacted GAP20 with 20% clay content. Mixed prior to installation.
d17e6194-a9f2-5dd5-94e1-a537157fab81 | note | ○ Installed as a subtle slope for positive drainage.
35cead43-41f5-5b0c-9ff2-02f697c67278 | note | Standard / Specification - Designer
a304b291-95c6-50f7-9b52-d79d59e7ade2 | note | Verifying Document - Inspection, Material Delivery Docket, Photographs
0c78121c-4be4-5c4d-aceb-f6930b7686e3 | note | Frequency - Per Item
e886a0b3-c0b5-50ac-9fc4-0a5b1512d5ab | note | Verification Activity: Activity - C
946d5b3a-c20a-5209-982a-3230664f263e | note | Verification Activity: By - SE
742a6803-9c59-4641-9001-1512e59549a0 | checkpoint | 5.04.03 - Geotextile
150a1fa9-568a-5267-a293-0c3ea7f6ca91 | note | Acceptance / Conformance Criteria - Geotextile to be used if topsoil removal exceeds certain threshold. Designer to advise threshold.
a9768fcc-0ea8-5dbd-9861-f95c87f94b81 | note | Standard / Specification - Designer
5b6bca53-f9b6-5cc8-820a-9dc0a42161ec | note | Verifying Document - Inspection, Photographs
af0c4df0-3941-57c7-bb51-d09af63b1c59 | note | Frequency - Per Item
7d8ec100-4b56-52f0-baa4-34e46e694a28 | note | Verification Activity: Activity - C
52bb7b6e-6cce-583b-920c-d0c5a31654a0 | note | Verification Activity: By - SE
a42d4a4d-d2a9-4c60-939a-bc6277972cc6 | checkpoint | 5.04.04 - Soil Spread
680d5e7c-cb2d-5d6a-aee1-00def6bd83b6 | note | Acceptance / Conformance Criteria - Topsoil to be feathered out beside edges of path. Should be laid in a way to prevent ponding.
3c182abd-757d-5164-b51d-e794bba2888a | note | ○ Can be placed in a mound if excessive quanties are encountered.
57849268-a021-5f54-bb9e-8bcb707fcbe5 | note | Standard / Specification - Designer
755e4ff2-86f5-5bcb-9810-63ee72fcc5b7 | note | Verifying Document - Inspection, Photographs
6acb78ff-5a6e-5053-ab60-9621a6750c18 | note | Frequency - Per Item
58954def-4294-5019-aa6f-7ff1f2b2126f | note | Verification Activity: Activity - C
1dc38284-c3f9-5a7d-be68-b71ea89f88bb | note | Verification Activity: By - SE
62f71a07-f2f2-4ffa-938d-4662fb3a2b67 | checkpoint | 5.05.01 - Footpaths
de654260-f3b2-5f28-a7d0-f967dc035d23 | note | Acceptance / Conformance Criteria - As per footpath construction ITP.
c4365033-a8aa-5a1c-bb16-7d7339896dec | note | Standard / Specification -
af13f66b-23c5-56f5-8168-10d16c8af6ad | note | Verifying Document -
5a34e6d4-4f51-5892-9291-5751e19cf93b | note | Frequency -
787cf448-cb53-55c2-a7c9-b6fff5037a03 | note | Verification Activity: Activity -
cb031c5d-3406-54c3-8d6a-aada8246e53b | note | Verification Activity: By -
c44fa368-3e6e-4fc1-8bed-cbd4441eead9 | checkpoint | 5.06.01 - Piles
fc84c58c-df34-57a2-a8ba-57617a47ac14 | note | Acceptance / Conformance Criteria - Piles installed as per drawings. 500mm encasement diametre. 900mm depth if installed in sandy soil, 1300mm depth if installed in clay-type soil.
72088708-23ac-5d07-9d92-e9d5641d199c | note | Standard / Specification - Designer
19bdb543-1156-542c-9fab-5e81762b456a | note | Verifying Document - Inspection, Photographs
03118d50-fdb1-5d6e-8508-154cc6da801c | note | Frequency - Per Item
72055fe8-9a39-5051-aa59-7666efb82f5a | note | Verification Activity: Activity - C
30c0fe34-715c-567b-9c61-49788013ed15 | note | Verification Activity: By - SE
a4552f45-5816-4ad4-89ac-d3981237d944 | checkpoint | 5.06.02 - Fixings
7415a3d2-cf24-5713-90b0-b40a9d8abd32 | note | Acceptance / Conformance Criteria - Installed in correct position as per drawings.
7af122ce-5e70-54a2-b0e5-d2761b0664fc | note | Standard / Specification - Designer
4c8bfe94-a00b-50e5-9be7-824f2691edec | note | Verifying Document - Site Record
8aba6ec9-ce73-51a0-bb28-23671bfd6610 | note | Frequency - Per Item
1d56d805-eb01-5e12-87a7-ed3fd250bb47 | note | Verification Activity: Activity - C
9fd10a9a-7bb2-5e55-9172-85f983d102ad | note | Verification Activity: By - SE
c2d1234c-a6c6-4576-bdaa-267cadfc986c | checkpoint | 5.06.03 - Timber
9812352d-e94c-5892-af09-137dc2a3b739 | note | Acceptance / Conformance Criteria - 150x50mm base rail coach screwed to post.
91ce6c71-1fc3-5ef5-83f1-cd6123c2c5bd | note | ○ 200x200mm post set in concrete as per Engineer's requirements.
58db7f7d-5d78-5415-a755-836e56ee3fdb | note | ○ 50x50mm balustrade s/s screw fixed to rails.
82d4ca1b-9048-5016-b667-15bef6596712 | note | ○ 150x50mm hand rail coach screwed to post.
9f7c6d8f-26d2-57f4-b17a-d777af42c189 | note | ○ 200x50mm joists with bracket fixing using s/s screw fixings.
1022e559-e9b7-5cf7-8b03-033e6f54221e | note | ○ 140x40 decking boards atatched to joints with s/s decking screws.
b09ce976-a1b7-5c69-83c1-97c0081cf1a7 | note | ○ 250x50(x2) bearings bolted to piled post.
9ada0cce-ccde-5dd2-93a4-5a17a84590ca | note | Standard / Specification - Designer
2294fa11-0a3e-553e-8828-8fddc3f208f6 | note | Verifying Document - Inspection, Photographs
97690708-0390-5cc5-8a40-3b100cb06615 | note | Frequency - Per Item
af63b31d-fb5d-5c4f-96ff-60949a098e5b | note | Verification Activity: Activity - C
9dd2f9f5-5214-5533-9258-cb52a185d986 | note | Verification Activity: By - SE
efec5999-78f1-4f1f-8fb4-f09fcafc389e | checkpoint | 5.06.04 - Bench
32f04630-493b-5b5d-9572-3ed7f2cb4cf5 | note | Acceptance / Conformance Criteria - Solid macrocarpa bench seats fixed with angle brackets.
856df021-8537-5287-b9dd-8d710f7d9f05 | note | Standard / Specification - Designer
29912fc1-4a66-5fdc-b4cd-ef63ba6bd2e8 | note | Verifying Document - Inspection, Photographs
7c5768fd-1a98-553c-91e9-74162abd38d1 | note | Frequency - Per Item
f935d2fe-2e7e-564a-a566-72abe308fe10 | note | Verification Activity: Activity - C
bc693981-b62a-5b52-8374-df57c9128b0d | note | Verification Activity: By - SE
51c18f54-113e-4d7a-bd5c-98f9f504676d | checkpoint | 5.07.01 - Pou Tupua
130ae246-c9ec-53fa-9cf7-8807ed518088 | note | Acceptance / Conformance Criteria - Designer to advise requirements for this item.
c0aca243-cea7-5473-bb21-965d8dc28d67 | note | Standard / Specification - Designer
5d52c563-fe5d-5eee-926e-41ec8b5e7dbf | note | Verifying Document - As Required
9b9c0ae9-e69b-581f-9ff9-dd4f9d52fdb5 | note | Frequency - Each Item
41cef07e-85e8-55aa-a39a-949c5324905c | note | Verification Activity: Activity - HP
636660e2-5fa5-56bd-be92-60f813aec224 | note | Verification Activity: By - ENG
ea4ea7bf-df39-4b51-89ad-ed08f3d4977b | signoff | AUTHORITY HOLDPOINT
c7c623e5-d3d9-49c3-b931-637bf60cedc4 | checkpoint | 5.07.02 - Pou Maumahara/Whenua
523f67dc-191e-54dc-aa1b-c0f8eccdd424 | note | Acceptance / Conformance Criteria - Designer to advise requirements for this item.
3c5d842d-011f-5286-bc8e-8df8acc821a5 | note | Standard / Specification - Designer
52c423d3-47e8-5ec5-b98a-e2148b846036 | note | Verifying Document - As Required
814ecac3-10d1-5fe9-842a-b5f5e0fb3769 | note | Frequency - Each Item
e730d3f3-2f0b-5191-97c8-39251e9b028f | note | Verification Activity: Activity - HP
1ac51154-c697-5b18-933f-feb081c23bf4 | note | Verification Activity: By - ENG
0d355dfd-1d06-4580-9c72-33fb18453f77 | signoff | AUTHORITY HOLDPOINT
5f924ee4-06bb-4b0c-9723-89831f31d736 | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
a7c4d412-5fdb-43ba-a2a0-2745517e53c7 | checkpoint | 6.01.01 - Red-line Markup
f1af65ee-6b6c-5338-8aa2-16a794133e06 | note | Acceptance / Conformance Criteria - Provide red-line markups for items that have been moved, modified, etc.
74c612ba-4b92-5d53-b826-522fbd1d1261 | note | Standard / Specification - Downer
c420c050-953c-5c97-8327-60e42366246f | note | Verifying Document - Red-line Markup to be include for every item that has needed to be changed from current IFC
3d3d7d39-ea88-57e7-9ac2-bcec2bfe093d | note | Frequency - Upon Completion
7988eeb2-f3ed-584a-b5ee-c5a81f12d41a | note | Verification Activity: Activity - H
dfcb13f3-838c-5939-a37f-3448e1a1bc7a | note | Verification Activity: By - SE
0f55f6bf-fa1a-4130-8988-f1de391dbcd2 | checkpoint | 6.01.02 - Checklists
4fc3900e-e9ed-57d9-8e44-3aec9e597557 | note | Acceptance / Conformance Criteria - Provide Checklist for Each Item which shows each stage of QA and Inspections has been signed off
3225fb19-31aa-56b5-a4c3-9bc117151e96 | note | Standard / Specification - Downer
6d2a7057-c1d8-5784-a2e2-b51a7665f83c | note | Verifying Document - For Each Item
2dacdcc9-c1af-5a6c-a5c6-3ceedaeb5a14 | note | Frequency - At Completion
ee5b6652-b98f-5424-9b8a-e4b016df6e8c | note | Verification Activity: Activity - HP
30fbc91d-9a22-5347-aec0-14d597b1c11e | note | Verification Activity: By - ENG
41a37d1f-d914-48e4-823f-66fad86b6b95 | signoff | AUTHORITY HOLDPOINT
20d31625-3682-4969-a05a-de4e0a15dd97 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
f55ebbbb-9f02-5820-90c0-c513762de39f | textbox | Contractor's Rep Name:
bb88e997-3e8a-5aba-91da-e022aecf1dd5 | textbox | Engineer's Rep. Name:
4c48a344-f60f-54a0-8930-070536b516ac | date | Date:
f8e27694-c2dd-4885-8edb-f0d04623f447 | signoff | Add Signature
d9fef114-11a1-503b-9ec1-e24d0a14f5c1 | checklist | ITP - 119 - Rain Garden Rev B | itp | ITP - 119 - Rain Garden Rev B
8c9335a7-3af5-5e47-a887-39a89ff08c27 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
9def2e52-5a00-5c71-bb5d-a5731d79f771 | note | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
f8918e32-072c-5e4f-bdbe-4ee0debe3d06 | note | Standard / Specification - Downer
5451e42e-e56c-531a-a32e-217f393d85b2 | note | Verifying Document - Construction Pack
06620205-379c-56fe-a968-1c3bfd8e297f | note | Frequency - Submit 10 days prior to commencement of works
6193f489-f3fb-5464-8890-95381175b697 | note | Verification Activity: Activity - HP
5d1e4cea-dbe8-52d7-8f42-0afb29cdaaea | note | Verification Activity: By - ENG
ca255811-cbe5-57f5-8b49-d49ad30655f3 | signoff | AUTHORITY HOLDPOINT
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
8e6e2633-9699-515c-842d-4ad5617b6756 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
cdc1a5de-c649-51dc-af72-655bddf75dfb | note | Standard / Specification - Downer
32599dcb-6c95-5d61-be91-fe7c780cccf0 | note | Verifying Document - Survey Records
beca2a2d-0fe7-5424-a8a6-dea170b05ba9 | note | Frequency - Prior to Works
70978d11-faf9-5157-955a-a0eab665e53d | note | Verification Activity: Activity - H
18003291-8496-5c14-bde9-4671827d2c56 | note | Verification Activity: By - SV
a24a2c58-bf6f-5474-883c-40044bad1fc7 | checkpoint | 3.01.03 - Service Location
a145cd98-5afd-5c76-84f3-b630dcbbf24a | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
2b61464f-60ec-58a0-9716-ee55082b8e9e | note | Standard / Specification - Downer
afdc609c-3532-51db-8de0-aac2fa4fa5c5 | note | Verifying Document - Excavation Permit
69afc0c4-55c4-52e5-a629-603a532a29c9 | note | Frequency - Prior to Excavation
f5e4d1aa-ae87-5b76-9e5e-137ed9d5de0f | note | Verification Activity: Activity - H
f45161a3-251a-5e3d-b14f-eb4c283c4b70 | note | Verification Activity: By - SE
0a214a7a-124a-5898-a837-e29e83751df0 | checkpoint | 3.01.04 - Internal Permits
2ffc1661-38e8-5a7c-8801-d480405b411a | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
200ea0a8-50f6-5fcd-9745-13b0c3e5ce01 | note | Standard / Specification - Downer
025caee4-663d-51f2-90ba-87349e939820 | note | Verifying Document - Internal Permits
47643a11-8feb-5416-9bc2-be5ef37187c0 | note | Frequency - Prior to Excavation
e2cc506b-6fb3-5e3a-94b8-8b294a73074e | note | Verification Activity: Activity - H
d288e985-0f3e-5c63-8716-900de1dd6c53 | note | Verification Activity: By - SE
917e2881-0901-542f-ae25-686bf9c47009 | checkpoint | 3.01.05 - External Permits
619e42e2-93c1-59c0-9895-735c939e1265 | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
a162d817-c75f-5509-a0cc-d8ca1f32a42b | note | Standard / Specification - Downer
27c3b5a5-7f3f-5634-8c5c-c4180b4cae27 | note | Verifying Document - External Permits
e0768b2d-0d3c-5d2b-9ecf-ddec27426721 | note | Frequency - Prior to Excavation
7a307292-5710-5039-96f2-f1782db0fa01 | note | Verification Activity: Activity - H
a369be10-0c78-5535-b298-29afb02fef13 | note | Verification Activity: By - PE
a1302970-0389-558d-b43c-67b14bbfc27a | checkpoint | 3.01.06 - Approved Construction Drawings
a1181f9e-eedb-5625-9694-c5f40918b168 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
9e9fcaa7-d74f-52ed-87b2-01625a59b5be | note | Standard / Specification - Downer
6e7fc801-b160-5175-947b-6ad87f2064cb | note | Verifying Document - IFC Drawings
7feebb4e-a7a9-5202-9378-9d919a1e5fea | note | Frequency - Prior to works start
9f7c0492-f0f4-5792-a4fa-78e04f916fbd | note | Verification Activity: Activity - H
e861a933-1d19-5714-b642-a3cdb2f583e9 | note | Verification Activity: By - PE
8ec62109-1664-5fbd-8086-47c125cee66d | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
22e9bf5c-0e02-5bd7-bf15-b098e9d01391 | checkpoint | 4.01.01 - GCL Liner
0b26c487-731b-5581-98f1-6e89fd3c5f6f | note | Acceptance / Conformance Criteria - GCL to be meet or exceed the test values of Bentosure NW4000.
0d5bf86a-1738-53e8-95ea-b9314c30530b | note | Standard / Specification - Project Sechedule
d72dfea0-ab18-5c7e-9ad7-41e8baa600fb | note | Verifying Document - Technical Datasheet
9d35c253-0e9c-50a7-82fc-39331e638b26 | note | Frequency - Atleast 2 days prior to placement
30c5dac6-202c-5aad-b037-ba83f190ae1e | note | Verification Activity: Activity - HP
b71da0d6-6e42-5ac0-b642-21a082e6f083 | note | Verification Activity: By - ENG
c54f2257-bd29-5002-9946-59df2efac979 | signoff | AUTHORITY HOLDPOINT
b8eb22e2-5f82-5a3d-a701-bd5d1bc878b9 | checkpoint | 4.01.02 - Geotextile
6b191de0-f149-52fe-884e-76a9998ce5fb | note | Acceptance / Conformance Criteria - NZTA F/07 Strength Class C & Filter Class 1 geotextile is to be used to wrap 20/40 drainage aggregate. Confirm before placement
9fcef079-bab8-58fb-ad7b-48743881ea91 | note | Standard / Specification - GWS 3.2.3
2263df06-b649-5e02-80a6-f7d66da36dcb | note | Verifying Document - Technical Datasheet Delivery Dockets or photos
4f066066-135c-50df-a0e9-6b45679625fd | note | Frequency - Before placement
c1755163-cd66-5f75-a7cc-31ac3c2e097d | note | Verification Activity: Activity - C
585a4b69-728e-5cee-9769-5b85dc9dc005 | note | Verification Activity: By - SE
2bd96335-bb25-5db7-a33e-ad909dd651a8 | checkpoint | 4.01.03 - Drainage Aggregate
221b297f-110c-5871-9743-1ea092d461e1 | note | Acceptance / Conformance Criteria - Drainage aggregate should be deep washed and in accordance with TNZ F/6 including gradings (40/20 aggregate). Open course grade clean durable aggregate, Have a crushing resistance of no less than 100kN when tested in accordance with NZS 4407:1991
a6d31f75-39f4-59cb-94bf-d848199b4a10 | note | Test 3.11 Meet the following gradings when tested in accordance with NZS 4407:1991, Test 3.8.1:
aa9e6105-cb0e-5190-9303-97000a09132e | note | App B - HAM2018-0136AJ Rev. 1 Geotechnical Works Specification:
c936dee8-4a12-5e54-aabf-9d2288dc4d1e | note | Table 2: Filter Material Gradings (Geotextile Wrapped Aggregate)
01b12554-1f83-5157-80c7-42795d9468be | note | Test Sieve Aperture (mm) Percentage Passing (%)
491fd46f-234a-50a1-9d89-3523102db8f3 | note | ○ 53 100
20d7a798-62d4-56bd-9024-4acc977e81c0 | note | ○ 13.2 10 (max)
26861176-ba6c-507e-b8eb-f046ed92d7b5 | note | Standard / Specification - GWS 3.2.2 & 3.4
82aa571a-6752-5d5a-a562-d79114ac0d37 | note | Verifying Document - PSD, CR
e71e9084-b5d1-5a76-b2de-73316ce0b3ea | note | Frequency - Material Tests every 1000m³ or change of source. Visual inspection every load, verifying document photos of material onsite, if visual appearance changes, additional testing will be required.
4d8826a0-b967-5d79-81c4-5f7e7dc4fe2c | note | Verification Activity: Activity - C
3891c4cc-4d13-5d8e-b96a-7d14f6f4a329 | note | Verification Activity: By - SE
5da2ead1-452e-5eb3-be5f-a7a107a12cf2 | checkpoint | 4.01.04 - Pipes and fittings
384ab256-614e-5e0c-b042-d330884b61cc | note | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 110 mm diameter Class 200 complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
b1c32c74-89c8-5700-9514-461ee4a6b3d4 | note | Standard / Specification - GWS 3.2.1
021e83e3-92b5-54cf-be9b-225bf97036d3 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
9f479e02-87de-5a0b-b98a-058141438c1d | note | Frequency - Before placement
61f334cd-3da0-573c-99d5-b67239121813 | note | Verification Activity: Activity - C
159be186-33a6-56c8-903a-8e8c4d123e3a | note | Verification Activity: By - SE
e1aa48fa-7dfb-5f24-8ea5-3249ff35596b | checkpoint | 4.01.05 - Graded Sand
2c159e7f-e667-5167-ae10-55eccd67b11b | note | Acceptance / Conformance Criteria - (2A SAND) 10mm clean well graded sand transition layer with minimal fines, void ratio 0.3.
4e8c8953-6ba4-5a6e-9728-f9466b773cf5 | note | Standard / Specification - DWG 2195 REV1
bfa66001-aa81-56fc-8d67-72c583598df5 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of sand onsite
fe17e41b-e7b7-5fa3-9c30-f02aa4f4c570 | note | Frequency - Every Delivery to Site
20af0589-2876-558d-93c3-e3ed86adf40a | note | Verification Activity: Activity - C
20d5e767-0a1e-591a-a02d-229e6e5ebf59 | note | Verification Activity: By - SE
981be771-3111-5798-8dff-f10c46442ede | checkpoint | 4.01.06 - Filter Media
c5d062f0-ab98-5419-b038-ae7aefda4472 | note | Acceptance / Conformance Criteria - Filter/ Planting Media must follow the specification as per RITS 4.2.19. Seen below.
2d7b6ed3-c522-577d-b20c-727b72991c08 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
5d006976-72ff-5405-a583-184daabab4ce | note | Planting media is to be as per RITS 4.2.19.
8de8009b-5ef5-5cac-8abe-2a1c3ddb846d | note | Planting Media
ef0e71dd-58b5-5977-9b20-a4d728414836 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
ec5acb6c-fcef-5c7b-9fb5-000d2fce3e13 | note | Raingarden media should meet the following specifications:
349ec037-1c73-57fa-aee7-011f242e188e | note | ○ Minimum depth 500mm.
ae4b69fb-db03-5d6b-9846-d3ab2934f7b0 | note | ○ Saturated Hydraulic Conductivity: 50 to 300 mm hr^-1.
66cb35fd-e9b7-5b59-979a-aea2b3046d5b | note | ○ Plant available water: 100 mm
7f23d222-671a-5f13-8be0-f5dcaba1ddb0 | note | ○ Organic matter: 10% – 30% by volume
45e23989-4308-5ac6-ab37-3858f269d53e | note | ○ pH range: 6.5 – 7.5+
af0681bf-ced5-55cf-961a-1f52f478bbcd | note | ○ Electrical Conductivity: < 2.5 dS m^-1
a09595b1-8671-5baf-a85c-2bab48a0fcf4 | note | ○ Total Nitrogen: < 1,000 mg kg-1
452909c0-4ce3-5e73-9071-ea5c9645fe02 | note | ○ Total phosphorus: Leachate testing required if > 100mg kg^-1
c065957c-2851-569e-b8f2-4d69ad64bde5 | note | ○ Total Copper: ≤ 80 mg kg^-1
59e189fe-40f3-5950-9bc5-088da18ed886 | note | ○ Total Zinc: ≤ 200 mg kg^-1
b6d417fd-4337-5efb-8f7e-b592a9b3e2d8 | note | ○ Media sources: From a clean source (no waste products)
1c64159f-72bc-5b8b-9623-6baea1bf0878 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
3d5cbaf1-a62c-5001-893e-962490d391f5 | note | Standard / Specification - RITS 4.2.19
600675f4-47b9-51d2-9772-cd66bf2cb451 | note | Verifying Document - Verifying documents Dockets
8866c5e8-3842-5ccd-9b45-69daf7185d1c | note | Frequency - Every Delivery to Site
ea81d774-536d-5184-b97e-089b1de790b0 | note | Verification Activity: Activity - C
114ffbcf-cd8b-5dd6-b69f-ed29bdb9ceef | note | Verification Activity: By - SE
7221acfc-bdcf-5668-830f-10ba8f65a1e0 | checkpoint | 4.01.07 - Scour Protection GAP 65 Rip Rap
2e2f339d-3f91-56fd-8577-bde9f9b05083 | note | Acceptance / Conformance Criteria - Clean GAP65 to be used as Rip Rap. For soil filled scour protection a ratio of 30% topsoil, 70% GAP65.
7eb9b777-f572-5c94-85f8-4b5ac7d3c348 | note | Standard / Specification - BBO
f69eb349-24e4-5224-b102-c11f69a02e54 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of mix
6ee203d5-4402-553b-9e7e-47f4ba7cbbe3 | note | Frequency - Every Rain Garden
605bfe48-7198-58ff-9fad-ec8a176bd576 | note | Verification Activity: Activity - C
307a0731-98f3-5b73-ad12-73bb724f239e | note | Verification Activity: By - SE
c217792e-7abf-530f-a1b3-89de8474f097 | checkpoint | 4.01.08 - Coconut (Coir) Matting
b2149d44-c2c0-5ac7-9f23-e68e78f6f815 | note | Acceptance / Conformance Criteria - Biodegradable Erosion
ea308e43-ecf5-5f65-b7e5-28c8654bc6f6 | note | ○ Mat (Coir Mat). Biodegradable mulching fabric 450 gsm
5d071044-7ba5-5cda-be9e-315e9adf188c | note | Standard / Specification - DWG 2195 REV1. Schedule SP2 4.3.7
cdfa223d-c4f4-58a3-be1f-fe5d0a75a973 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of mat onsite
e9f1e6e3-856f-5b65-9c7c-93bbe37ad83a | note | Frequency - Every Delievery to Site
ff7e18fe-40d0-5df1-9789-39211dadab87 | note | Verification Activity: Activity - C
a380baee-ac44-5f56-b581-48c0f2cf96fa | note | Verification Activity: By - SE
f4713bb7-3aea-5dca-b516-69272c0b56ba | section | SECTION 5 – CONSTRUCTION ACTIVITY
19574288-2423-5ae8-9663-216f7f029c5e | checkpoint | 5.01.01 - Set-out
600f05d5-cd60-5a54-b4f3-2746d702ac26 | note | Acceptance / Conformance Criteria - Check set-out prior to excavation of Rain Garden.
4493c0d8-0bc6-5b9b-9727-0623d648a1e6 | note | Standard / Specification - PS - 2.2.12
cee83049-a5b9-512b-ae6c-d75b343325cc | note | Verifying Document - Hold Point Release
f36a231e-d26f-57b2-859d-d1e72bdf2998 | note | Frequency - Min 48h Notice
1d930587-40d8-5f7c-8e59-576f65ded1bb | note | Verification Activity: Activity - H
55190d5e-4025-5a63-b39a-ff7f394c4771 | note | Verification Activity: By - SUP
ee3347ad-b42b-52c6-a346-8179ac384378 | checkpoint | 5.01.02 - Excavation
4a27e751-010c-5453-88dc-0e8767489641 | note | Acceptance / Conformance Criteria - Excavations shall be completed in such manner that it is true to the drawings will allow novacoil to be laid true to the depths, grades and lines.
59d30fcb-b799-5c41-b903-9463f1a2acc8 | note | Standard / Specification - Downer
f4fa8486-f648-5d56-a446-e39e7c3fcd69 | note | Verifying Document - Survey Data, Photos
815aa440-231f-51d6-b6d4-041fd2de20a9 | note | Frequency - Prior to laying filter cloth
5629bd6d-6da9-5095-ade7-bac1103dce26 | note | Verification Activity: Activity - H
1080d04e-7ae6-591a-ac8a-93028cef5cd2 | note | Verification Activity: By - SV
9b37abc6-1c95-5181-8684-240049c6a4ba | checkpoint | 5.01.03 - GCL Liner Fixing to Kerb
5cd2247f-913c-5193-b633-30ebcf20b4da | note | Acceptance / Conformance Criteria - GCL Liner to be fixed to kerb as per manufacturers guidelines (Bentofix GCL 18.2, figure 14). Mechanical fasteners with stainless steel batten (connection bar) to be used to fix the liner to the kerb. Mechanical fasteners to be fixed 5 times ever meter of along the connection bar.
4c1f2594-00c0-5cb4-b283-270f41f3f716 | note | Standard / Specification - Manufacturers Guidelines 18.2
60ef2f84-00c4-54b4-a9ff-5fc8cd8012d5 | note | Verifying Document - Site Photos
fb8d44b4-9b70-5121-a5a5-fb84a118abe8 | note | Frequency - Prior to backfill
10d47998-5f5b-5baa-b21d-17ac73bdb5e2 | note | Verification Activity: Activity - I
926dcbb4-ecc0-5621-b441-bb0f962cb374 | note | Verification Activity: By - SE
27c05d4f-bd48-57e2-83a7-87435520dc3f | checkpoint | 5.01.04 - GCL Sealing (Pipes)
a1b6b76a-586d-5295-b07d-7a199bfc1d7a | note | Acceptance / Conformance Criteria - GCL Liner to be sealed around pavement drains and stormwater lines which connect into rain garden. Sealing shall be completed as per manufacturers guidelines (Bentofix GCL 18.3 & 18.4 Figuire 15). GCL shall be cut with a sharp utility knife. For horizontal pipes, vertical laps of min 1m are required. Inside the rain garden a clamp shall be used anchor the GCL lap to the pipe. Bentonite paste shall be be used in the void between the main GCL and GCL lap to ensure a water tight seal.
667d5700-5b1a-5c50-9b96-e7dc61aedb0e | note | Standard / Specification - Manufacturers Guidelines 18.3 & 18.4
909e44a4-da81-51e7-a4a4-62e5b4f0640c | note | Verifying Document - Site Photos
4bffd81b-50ac-5aac-a8a0-ec538efcc69c | note | Frequency - Prior to backfill
c7d9b028-9831-57e7-bf77-8a4e9c71b44e | note | Verification Activity: Activity - I
7c4a97d2-10a0-5a7b-bb34-1bfe52d32963 | note | Verification Activity: By - SE
179a4861-2c8c-5363-9da2-34c51344dd6a | checkpoint | 5.01.05 - GCL Repair
1b1258e3-9755-5f6e-9172-c7e48ee5dcef | note | Acceptance / Conformance Criteria - GCL to be repaired as per manufacture's guidelnes (Bentofix PVB5100c). GCL becomes damaged, torn or punctured during installation, the affected area should be repaired. For damaged areas, a separate piece of GCL shall be used and extend past the comprimised section by 500mm in every direction. Bentonite shall be used to connect the seperate GCL to the main liner.
83b9ad06-5588-58d7-9d75-46a86a271b3f | note | Standard / Specification - Manufacturers Guidelines 21
3eb9fe2a-43a3-5a97-8958-25889e12c7a6 | note | Verifying Document - Site Photos
8cb2aa44-5657-5ed3-9e0c-1a004d9d5685 | note | Frequency - Prior to backfill
1dde0c36-378e-5da4-abd1-af3d767a5e64 | note | Verification Activity: Activity - I
06d19e04-674c-52fb-b0c6-f26fea2cea48 | note | Verification Activity: By - SE
d1c33f5a-22d0-5c7b-a31d-b015e95987f0 | checkpoint | 5.01.06 - GCL Inspection
f68ab60e-2892-5e0d-b81b-ba30fd0d67fd | note | Acceptance / Conformance Criteria - GCL to be installed as per manufacturers guide and true to the drawings.The inspection should include overlaps, alignments, penetrations, connections, detections of any defects, including installation damage.
44c1fa93-473b-5b99-8da5-1d39bc90a737 | note | ○ Detected falsely installed areas shall be marked, repaired and the repairs shall be inspected and approved engineer.
6d8921ad-6f4a-533a-b456-792ec29c7d0c | note | Standard / Specification - Manufacturers Guidelines 22.2
ffe309d9-a9be-5376-bf41-bc762cea8a81 | note | Verifying Document - Site Photos
dcae8388-5132-5ced-8c26-518881685a51 | note | Frequency - Prior to backfill
1d1a34d5-8d49-57ef-b8fa-5326f02f2d1a | note | Verification Activity: Activity - HP
942e0f00-fc57-59f7-8192-02b5d3a225da | note | Verification Activity: By - ENG
195cd751-1ecb-59ce-a78b-245fae1899c3 | signoff | AUTHORITY HOLDPOINT
be7bb179-b29e-5920-961a-c9df21bd8ce5 | checkpoint | 5.01.07 - Geotextile Installation
a29735f9-34eb-5a9c-a394-c3bc94154550 | note | Acceptance / Conformance Criteria - All geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets.
d6869b93-3017-51ce-964f-159a3b47048e | note | Standard / Specification - GWS 3.2.3
6ffb215c-94e6-5854-b098-3e6eb31dfc2b | note | Verifying Document - Site Photos
4d9f8add-0e77-5722-baab-9e5e5766d4f0 | note | Frequency - Prior to aggregate placement
ffcc9995-ac25-5f61-95d2-41588d654df9 | note | Verification Activity: Activity - I
2070edc2-cb6c-5037-b67e-f39f11a7ec1d | note | Verification Activity: By - SE
a7aabac4-0ef7-589f-a41a-c0faa5e13dd4 | checkpoint | 5.01.08 - Bedding
44edf9b1-5f71-5fa1-ad4c-0a9d944929b0 | note | Acceptance / Conformance Criteria - TNZ F/5 - Bedding thickness shall be no less than 100mm
13e34238-b4ca-56ac-a4de-5bc5716b5d63 | note | Standard / Specification - TNZ F/5
da7f24f9-3732-500b-888d-2d2144d17cce | note | Verifying Document - Photos, Sruvey Data
a3a98082-d942-5028-9afe-2b1040219ee6 | note | Frequency - Prior to laying Novacoil
e065347c-a0dd-5d45-840f-f3bff790f901 | note | Verification Activity: Activity - I
a394516c-2836-5ca3-9fc0-75035d15247c | note | Verification Activity: By - SE
fe243f44-de6b-58b6-8268-97bfc0c998be | checkpoint | 5.01.09 - Joining Pipes
182f1c45-9999-59ba-b4b3-1f830467bb15 | note | Acceptance / Conformance Criteria - TNZ F/5 - Joining the pipe shall be done using a purpose made pullout resistant coupling in accordance with manufacturers recommendations
86540013-2f92-5552-826d-5b7bf226eae6 | note | Standard / Specification - TNZ F/5
96de2e5e-1bd4-5bfb-86ea-ab510f833971 | note | Verifying Document - Copy of delivery dockets, photos of joins onsite with tag showing class
21a889e4-6cf2-548b-8830-fda70e6424b2 | note | Frequency - Every join
ebab9131-d025-539d-9379-126751b0a827 | note | Verification Activity: Activity - I
6d1363a4-ba95-5a8b-b91a-72f47b42c1e6 | note | Verification Activity: By - SE
a55e4a54-a4fd-55a2-bd2a-0d8a9ba61539 | checkpoint | 5.01.10 - Pipe Grade
5ce789c6-6ee6-5be9-b07a-73a23d6afd19 | note | Acceptance / Conformance Criteria - Grade of subsoils must be falling in the correct direction based on the IFC Drawings and at the correct grade (greater than 1% based on TNZ F/5)
308913a1-b89b-5266-8230-723fd382cbc2 | note | Standard / Specification - TNZ F/5
8bee89d9-8267-5038-af59-eb0b8a14320d | note | Verifying Document - AsBuilt
b5937b6d-dee4-5863-a7e9-fe84d6368bfd | note | Frequency - Every 10m
99ae9c11-dab5-5e11-88e4-5e62e5760cb6 | note | Verification Activity: Activity - H
f3b63dcc-8c18-5779-bb93-65d3a75ca474 | note | Verification Activity: By - SV
a5e5e74c-2728-58c4-bbc1-79ee9c9f3d14 | checkpoint | 5.01.11 - Pipe Cover
45f6b39b-faef-5d70-83a8-96fbb3919e86 | note | Acceptance / Conformance Criteria - Pipe to have 100mm of drainage aggregate as top cover for pipe.
b2f4089d-485a-5329-bebb-33c600709fd7 | note | Standard / Specification - N/A
6243c14d-2fd7-58e1-af45-9ea75de8ed78 | note | Verifying Document - Site Photos
fb4ecb70-d7d8-5353-8528-e5366b4f1ef5 | note | Frequency - Every 10m
3eba3e8b-6bd9-51eb-9f13-65c91c42ced7 | note | Verification Activity: Activity - H
8e10125f-9c86-5eb8-b4c6-c8d35c42af68 | note | Verification Activity: By - SV
5070a493-26b2-5cc9-ad7b-3fe7d8a0b1d7 | checkpoint | 5.01.12 - Sand Placement
39c4cca1-9cf9-5fcb-9d92-14c46d00df2d | note | Acceptance / Conformance Criteria - Sand to be placed at a constant thickness of 100mm. Sand should be free of peaks and troughs.
12559d02-92db-5d69-922d-d36d03b735c2 | note | Standard / Specification - N/A
83f0147f-7607-5108-9dd6-e7e33a01c13a | note | Verifying Document - Site Photos
a4f2c54c-4dd2-5e5e-8c93-141232aa35a6 | note | Frequency - Every Rain Garden
79130b52-d4cf-5bd5-a1b7-64d5cbf8292a | note | Verification Activity: Activity - I
d1a9f347-148a-529d-9e40-6c028f31167b | note | Verification Activity: By - SE
e42efee3-5829-5966-a7c1-3e76e1653674 | checkpoint | 5.01.13 - Filter Media
89017aa0-48c4-538e-9a49-394f4a9415bf | note | Acceptance / Conformance Criteria - Filter media to be placed at a constant average thickness of 600mm, refer to drawing for detail. Filter media should be free of peaks and troughs.
fec33b6a-952e-59b4-bbdb-e728f3c2c2cb | note | Standard / Specification - N/A
31082cfa-3a10-5cb8-8367-0f1a29afca37 | note | Verifying Document - Site Photos
50160857-86c6-590c-b455-ea9a3457241d | note | Frequency - Every Rain Garden
4820cfd2-6c04-5db0-b627-e12d02994a3a | note | Verification Activity: Activity - I
d400e801-9172-54c9-a25d-656c4f6779bf | note | Verification Activity: By - SE
6874f319-15b9-5588-bc4d-40a4917d4f61 | checkpoint | 5.01.14 - Coconut Matting
d314f001-d64e-5690-984b-d6f0f417c538 | note | Acceptance / Conformance Criteria - Mat shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets.
21594c11-04a8-56e4-8267-7b263e7a0a70 | note | Standard / Specification - GWS 3.2.3
a093a406-d1f3-558a-89f1-58230e400337 | note | Verifying Document - Site Photos
348ffcaf-297f-5053-9328-330398f1b4c1 | note | Frequency - Every Rain Garden
f341404c-5bca-5784-9fa9-233677b37665 | note | Verification Activity: Activity - I
738700f5-6608-5a5f-9f4d-4448e1f52b53 | note | Verification Activity: By - SE
1b5340b6-cfeb-55f1-9fe3-37ffae8455b8 | checkpoint | 5.01.15 - Scour Protection GAP 65 Rip Rap
a153e58b-fe5a-52f4-a40c-413447caaee1 | note | Acceptance / Conformance Criteria - Scour protection shall be installed as per drawings around let downs, scruffy dome and the flush point end.
842ef001-1887-5763-9452-83ad19265168 | note | Standard / Specification - GWS 3.6 & BBO
16b96443-9310-5c47-9c54-c3900d0c4ea7 | note | Verifying Document - Site Photos/ Survey Data
1371382c-d043-5dc7-8622-93265a43e5c3 | note | Frequency - Every Rain Garden
fc74b2fe-916c-51da-87ba-f437eebd4b06 | note | Verification Activity: Activity - I
047d71c0-11bf-5ac7-a1f5-ab47bf21e5f8 | note | Verification Activity: By - SE
cd33a7f8-9b6c-5422-93be-dcae98eaa460 | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
abaa7cc7-67ff-52ad-ae9f-e9176b336a01 | checkpoint | 6.01.01 - Construction Record Compilation
305b604d-63af-5a53-a11c-ad86f47fc8e6 | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
34ad28d5-f430-523d-82bb-725cf094c681 | note | Standard / Specification - Downer
54b8020c-b526-5e03-9b88-ee358fc56a95 | note | Verifying Document - Records
82931b34-5b61-5522-b03f-750a4a203559 | note | Frequency - Post construction
34e75775-ad54-5544-aafd-710aee05a3b0 | note | Verification Activity: Activity - H
9fab602f-4544-58af-9146-3e170b4b9e7f | note | Verification Activity: By - SE
f4876821-e136-54ca-95e8-27fd0f400f5d | checkpoint | 6.01.02 - Survey Records
75612203-35cc-50ca-99af-d6940a3d4b1b | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
62ce2c95-23d7-5e9f-9eb5-873f8570dc4d | note | Standard / Specification - Downer
69be40fe-abd1-5235-8a5d-1deeee39adab | note | Verifying Document - Records
6f33c896-49e0-55bc-b5f5-fd20510fe684 | note | Frequency - As-builts taken every 10m prior to backfill
67c35579-6e93-5cab-9af8-6507322f38e6 | note | Verification Activity: Activity - H
42089a71-816d-5dbe-a2cd-6d348fe31e36 | note | Verification Activity: By - SV
a7ece1a0-6b4a-5d51-8813-156cc41a337a | checkpoint | 6.01.03 - Redline Drawings
d102114c-c9a7-57ea-a50b-c97676639cbb | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.To show all subsoils, including temporary subsoils that become part of the permanent works, to show all outlet locations
d1b26aec-3938-56d4-bfd2-b63867827f5f | note | Standard / Specification - Downer
c68c40c9-67a0-53b1-9e59-e46c6be6c9c7 | note | Verifying Document - Redlines
f6c46ea3-f969-56a4-b139-1b3cd17269c3 | note | Frequency - Post construction
e50a5760-26e3-5920-8abf-6644c9d59ceb | note | Verification Activity: Activity - H
afd1a16d-47c6-512f-8f51-d27376473de7 | note | Verification Activity: By - PE
406cc900-58d1-549c-813d-cb4c75c9a2be | checkpoint | 6.01.05 - Photos
ab1da870-da7a-5fb9-8982-88c1abf53033 | note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
57e29fcf-0a48-5d29-b1aa-653496a43e32 | note | Standard / Specification - Downer
6b4aef35-4b9a-5854-9860-bf464cbaba90 | note | Verifying Document - Photo Records
8dd7e61e-c163-5706-8b5a-7e8441532e31 | note | Frequency - Post construction
834d8cc4-474d-518b-ac3d-c9bbe7a931f1 | note | Verification Activity: Activity - H
c67803bd-73f2-5315-8a9f-2e8b104e1fe1 | note | Verification Activity: By - SE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
ea2ec2fe-768c-5026-973f-f53d96a04894 | checklist | ITP - 131 - SWD04 Eastern Gully Works Rev E | itp | ITP - 131 - SWD04 Eastern Gully Works Rev E
8c9335a7-3af5-5e47-a887-39a89ff08c27 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
17053592-32f5-5964-84d1-bfea17c64d15 | note | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
80553e45-1f94-584d-8d6c-8178552abd7e | note | Standard / Specification - Downer
340370a0-d3ee-51d6-8764-a6acc65e4d31 | note | Verifying Document - Construction Pack
b61c2550-a291-585d-b778-21cdd0e147e5 | note | Frequency - Submit 10 days prior to commencement of works
458dd144-001a-5c09-afc1-f89fc47a9415 | note | Verification Activity: Activity - HP
a328997a-80d0-587a-92c1-e33597cee564 | note | Verification Activity: By - ENG
ca255811-cbe5-57f5-8b49-d49ad30655f3 | signoff | AUTHORITY HOLDPOINT
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
de0209dc-910e-5370-85ed-9de131b9dc73 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
f591bd3f-9ccf-503f-9aa7-ed87a951a6c8 | note | Standard / Specification - Downer
92088bb0-3b45-5e46-a8ad-d66f647402e1 | note | Verifying Document - Survey Records
37c006b8-6c13-5399-b4a1-c7c1ac78e6c2 | note | Frequency - Prior to Works
54579433-b13b-549c-a7f8-31b3b6986df7 | note | Verification Activity: Activity - H
f54aa70b-fdf0-5135-ada5-eba098a81493 | note | Verification Activity: By - SV
a24a2c58-bf6f-5474-883c-40044bad1fc7 | checkpoint | 3.01.03 - Service Location
dbae9da8-ed02-5f01-b8cd-3888ebc18c9b | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
a287c49f-12f1-5f16-a218-f8305b0226b2 | note | Standard / Specification - Downer
fae85e2d-319b-515b-bcda-801ff483d7bf | note | Verifying Document - Excavation Permit
2bb9f676-6ec3-5eb9-9962-4c520480a7f7 | note | Frequency - Prior to Excavation
99c64542-048c-51a3-adeb-69ccf8543cd8 | note | Verification Activity: Activity - H
a46cb02c-9bd8-5c51-a29b-eef5aa72e75f | note | Verification Activity: By - SE
0a214a7a-124a-5898-a837-e29e83751df0 | checkpoint | 3.01.04 - Internal Permits
eefac666-e679-5fa9-98d4-725e56d9ca6b | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
a7336049-1dc9-5bd5-a778-15cc2961a9d6 | note | Standard / Specification - Downer
417c04fc-f5ee-5081-8a81-d15401e4000f | note | Verifying Document - Internal Permits
acfd012d-7bb5-533c-bf2a-52c5454ebd3a | note | Frequency - Prior to Excavation
f6d6554d-e80b-51e8-8f10-56e1ccd59d1b | note | Verification Activity: Activity - H
2a8b1cb6-0942-5af7-9789-c2fbd8664608 | note | Verification Activity: By - SE
917e2881-0901-542f-ae25-686bf9c47009 | checkpoint | 3.01.05 - External Permits
179271ab-fcfc-5718-a548-075031a6f706 | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
39714b05-7f05-58ba-aaf5-ab942adf357f | note | Standard / Specification - Downer
51bad531-352d-5a1d-bedf-29a6332b94e6 | note | Verifying Document - External Permits
fc84a512-59d4-5146-ae31-1510948aeffb | note | Frequency - Prior to Excavation
515f7fe9-5dde-516a-9291-c0f4cf5ae3d1 | note | Verification Activity: Activity - H
9e28b133-9ba4-54ee-b473-4ffccb0ec7b5 | note | Verification Activity: By - PE
a1302970-0389-558d-b43c-67b14bbfc27a | checkpoint | 3.01.06 - Approved Construction Drawings
7988cb2f-0e53-5528-88a2-adc46d9e766e | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
118e6f3e-0649-5c67-8339-1215aeaf582f | note | Standard / Specification - Downer
2ef056cf-ba4d-59a7-8bc9-68873aa644f3 | note | Verifying Document - IFC Drawings
2f5caa0d-2161-5849-a203-e1e49530983d | note | Frequency - Prior to works start
b8e3a7cc-b20e-5011-8bba-bdf3b1f4a3cc | note | Verification Activity: Activity - H
99f31c97-3036-550a-ae61-fc2c45fdc826 | note | Verification Activity: By - PE
8ec62109-1664-5fbd-8086-47c125cee66d | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
d7ac324e-4209-51ea-8863-c8b4feeaf81d | checkpoint | 4.01.01 - Fish Relocation
7a31ab84-0a36-595b-8812-5362424c114b | note | Acceptance / Conformance Criteria - In-Streams works to be carried out between Jan to April. Fish relocation to be carried out by Ecology NZ as per FMP requirements.
cadc9f43-d95b-501f-8d01-944c225af3e7 | note | Standard / Specification - Fish Management Plan
fc7ba2b1-121a-5451-a39a-780650172bf1 | note | Verifying Document - Ecologist Memo
86f8823c-38e6-526f-8f32-20734f0587c3 | note | Frequency - Prior to in-stream works
32191ef6-9e57-5f9f-becf-e5a2e42ea1df | note | Verification Activity: Activity - H
e466b861-03d3-5401-91ab-f72a1c752641 | note | Verification Activity: By - SE
0df419c3-61fd-5dca-b72c-f565fb673048 | checkpoint | 4.01.02 - Tree Clearance
5139519a-80ab-5512-bb6b-3c71fdbf4e37 | note | Acceptance / Conformance Criteria - EcologyNZ to inspect trees for fauna prior to removal.
f785ff5e-3874-5965-80f9-4121552723ff | note | Standard / Specification - Bat Management Plan, Lizard Management Plan
b9aa0be2-c271-522a-8631-7fa5d03ae257 | note | Verifying Document - Ecologist Memo
c790dd7a-199a-5f22-bc77-0220f05ebe93 | note | Frequency - Within 24hrs of tree felling
1c70fe35-09e1-50c1-9c4a-ce8fa7d36ab1 | note | Verification Activity: Activity - H
2be4ee2e-07f9-51f6-bc6a-842b17cae378 | note | Verification Activity: By - SE
d1f0cd98-eef9-5e84-a54a-87678f1fde0a | checkpoint | 4.01.03 - Weir Clay Fill Material Testing
2bf512e2-5b5f-5663-85b5-3c6a5f3c2722 | note | Acceptance / Conformance Criteria - Standard Compaction
978a2bcb-a9ca-5350-be0a-eca7c130f120 | note | ○ Minimum 30% fines content.
943d2135-a08c-5752-9a07-b2fc817ba251 | note | ○ Plasticity Index 16-30, Liquid Limit 30%-60%.
f0204c93-8d04-55a6-af94-83750f5ef3bd | note | Standard / Specification - GWS Table 1
5717fc90-de7e-59f0-8ec8-fd6a49ad8992 | note | Verifying Document - Test Results
d78f81a4-43ef-5ad4-ba84-0f94507b40ac | note | Frequency - 3 initial tests per source of fill
b48b4773-ed5f-5042-a486-2b62142981a7 | note | Verification Activity: Activity - HP
34d6fb86-d54a-56f8-b44d-937a37e76b77 | note | Verification Activity: By - ENG
d56fa268-a150-5390-8db7-a8857c11a32d | signoff | AUTHORITY HOLDPOINT
20aafa93-42a0-504f-b8cf-c7f603b06b7f | checkpoint | 4.01.04 - Grouted Boulders
58eccf7c-fd9f-53c6-84c1-7be60c8b55eb | note | Acceptance / Conformance Criteria - Boulders to have specific gravity >2.1, be clean and crack-free.
8b66f255-4bb6-5a92-826a-63ef763d5fa9 | note | ○ The grout shall meet NZS 3109 and be kept wet 12 hours post pour.
d21ca87a-7407-5d3e-b0f6-249ac2cce010 | note | ○ Grout should be recessed 1/3 the diameter of the boulders' side facing the channel.
e8992f9b-eadf-542d-8f50-98bcbb23b069 | note | ○ 48 hrs before grouting, placement must be inspeted by Engineer.
6c6fab36-dc7e-5e93-8d02-a5c47f8ac03a | note | ○ 20MPa concrete.
22cdb040-c28a-5ce9-a355-f4c41f8dc952 | note | Standard / Specification - Project Specification 4.7.6
4c79d79f-1cc7-5689-b0c8-f484a2f87fc5 | note | Verifying Document - Material Certs, Concrete Docket
51e959f3-0e82-516a-b662-a3f981c6b52c | note | Frequency - Before Delivery to Site
9a0d8e75-881f-5a43-9a6a-1a7cbeb9eb81 | note | Verification Activity: Activity - HP
2ec5613f-7915-5025-8739-2e15b00530b4 | note | Verification Activity: By - ENG
01c0e740-bd05-5304-82ad-1061a2a8295c | signoff | AUTHORITY HOLDPOINT
9ef63768-e292-5259-96df-3c040af12c66 | checkpoint | 4.01.05 - Riprap Material
a4b4fba3-fd23-5c20-a846-c814587f1dbe | note | Acceptance / Conformance Criteria - Density - Greater than 2.40t/m3
0b6d42f5-c833-542e-92d9-3b0c4b7caefc | note | ○ Crushing Resistance - Not less than 150kN
ffbfb70e-4b3b-5326-8f17-be7296ddcc70 | note | ○ Weathering Classification - AA, BA, AB or BB
557610b7-6a1e-53e1-b788-e7412b3f5574 | note | ○ Abrasion Resistance - Not more than 26%
8c242084-b004-5efb-bd21-cf8aff3227ef | note | ○ Calcite intrusions - Rock shall be free of calcite intrusions
99d917eb-cff1-5ada-b18f-f6cb3c681d41 | note | ○ Grading - Rock for riprap shall be the nominal D50 size shown on the drawings and shall be well graded.
8c16c804-0135-5bc1-b1b3-0cdd834027c4 | note | ○ If riprap product is unavailable, alternative material to be approved by designer.
ee9c06e1-d8f5-59de-a60a-390ceb60df45 | note | Standard / Specification - Project Specification 4.7.1
749cb8ff-6c1f-5602-b3bf-db757d14e772 | note | Verifying Document - Delivery Dockets, Lab Reports
a4e3f4a8-d5ab-5057-a9d4-52ee80ecb9ab | note | Frequency - Per Truck
60b5ae32-41fc-5ec5-b5b4-65c4ccc2439c | note | Verification Activity: Activity - HP
3f47884e-6e2f-5c00-a96c-9cc6212ddd75 | note | Verification Activity: By - ENG
9aa51ab6-babe-5c95-9260-66413553d182 | signoff | AUTHORITY HOLDPOINT
921aa0b8-1356-52d7-9766-43de742b6dd9 | checkpoint | 4.01.06 - Bulk Fill below Clay Fill
01f01445-6adf-5fc4-9408-093779ebfc3a | note | Acceptance / Conformance Criteria - Maximum 10% fines
b25282f8-bd05-549b-986a-c9c3d053bb43 | note | ○ Blue/brown run of pit material (not too weathered)
ed0a1e31-74a5-5af3-a12f-6df660a88bf1 | note | ○ Wrapped in a geotextile (strength class determined by the clast size of aggregate)
e1051fe8-a4e2-5a6f-a613-cf1ad87ea962 | note | ○ Maximum clast size 200mm. All larger blasts to be broken up.
d58762b7-a7b9-581a-9c03-5fef9e31d19d | note | Standard / Specification - Desiger
d08dbe47-03eb-55b9-b640-bc02e1016c72 | note | Verifying Document - Delivery Dockets, Proof Roll Testing
027be3b0-62f9-5fe2-89a1-77a65e312297 | note | Frequency - Per Truck
8afc855e-ebfb-5b4b-af9a-bc076ddcd0ad | note | Verification Activity: Activity - HP
4ba781a9-dc8b-5136-bd80-d9e7946f12a2 | note | Verification Activity: By - ENG
601497aa-edbe-56c9-ab27-ce7225ced642 | signoff | AUTHORITY HOLDPOINT
38ef2971-7226-5060-ad1c-eb223e83b451 | checkpoint | 4.01.07 - Grout
d317f3c7-d6ff-5297-a732-3357f201e412 | note | Acceptance / Conformance Criteria - 20MPa Grout mix design to be deemed suitable by designer.
67e76c51-bbb8-5cf8-a2dc-fdde6222f50c | note | Standard / Specification - Designer
f9f54fe0-2d28-54c0-9034-4afd79a46d00 | note | Verifying Document - Record of Approval
4abda46c-3e01-5826-9c05-5e4c9ae40faa | note | Frequency - Prior to use.
5539174c-badd-5536-a805-d425c766986b | note | Verification Activity: Activity - HP
545f8d72-9a74-5500-bb77-330462258c88 | note | Verification Activity: By - ENG
f2df7322-c33e-5e08-a13f-8e5e34f31bf0 | signoff | AUTHORITY HOLDPOINT
e92db00d-a035-518e-8867-634e90b9d4bd | checkpoint | 4.01.08 - Geotextile (Base of Undercut)
ad2e936b-0d4b-52fa-857c-c7790cbe3908 | note | Acceptance / Conformance Criteria - NZTA F/07 Strength Class C geotextile installed at the base of undercut.
b3ec8265-9e3c-58f6-b6f9-7e24607ecce6 | note | Standard / Specification - Designer
e00cb19c-2430-512f-8f35-c6139e63ec25 | note | Verifying Document - Dockets
6fa8b98b-b539-5685-b1eb-a4feee44adbc | note | Frequency - Per Delivery
03ec3c61-27e0-5be3-8454-0399610f8aac | note | Verification Activity: Activity - C
25799180-cabb-5948-a273-13f3e0a3c043 | note | Verification Activity: By - PE
30cc3fd4-8f07-5c05-8d48-fdbfa822c7a1 | checkpoint | 4.01.09 - Geotextile (Top of Rockfill)
1484735a-c95b-51a5-bf33-47377b74e5ed | note | Acceptance / Conformance Criteria - NZTA F/07 Strength Class E geotextile installed on top of finished rockfill surface. Only required if GCL is installed.
254eec6c-1835-5ac9-a1c3-4c12d9399ed3 | note | Standard / Specification - Designer
bf98bbb7-6468-5bc7-ae61-f8c422796f39 | note | Verifying Document - Dockets
7cfd4bfc-73d8-5091-be9c-9dfde21c41d6 | note | Frequency - Per Delivery
c4aa5d90-a132-574f-ad0a-4e9f87b5a37f | note | Verification Activity: Activity - HP
14e1a407-806c-599f-a125-215a0da03bc1 | note | Verification Activity: By - ENG
d4794849-f937-5817-990a-aa1b2a6e43ed | signoff | AUTHORITY HOLDPOINT
534ebabb-602d-5759-88f0-bb98c0dfbc8b | checkpoint | 4.01.10 - Geosynthetic Clay Liner
f798af58-e4d5-5ba3-87a9-883cb185261e | note | Acceptance / Conformance Criteria - Elcoseal GCL to be deemed suitable by designer. X800 grade to be used unless otherwise advised by designer.
ae08dbb7-fe74-55a6-8c9c-acc48c0c6898 | note | Standard / Specification - Designer
22194dc5-267c-5dde-b3f8-a947c37bd048 | note | Verifying Document - RFI
3590c85f-23d8-5b81-9eb7-e39bafec12fd | note | Frequency - Prior to use.
1b7d15cb-f69d-5082-8f21-da9825d313b6 | note | Verification Activity: Activity - HP
00ad5173-b4d7-56d8-b698-107ac2682867 | note | Verification Activity: By - ENG
97fb1b50-0047-520b-a73f-42fe0aec9cc9 | signoff | AUTHORITY HOLDPOINT
d7f4ecdd-f673-5f61-9b41-a26a5d1a7241 | checkpoint | 4.02.01 - Pipes, Fittings and Pre-cast Structures
5694908b-a763-5386-bbfc-e869190d9908 | note | Acceptance / Conformance Criteria - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes/manholes/catchpits are correct and in good condition and compliant.
9667d322-e54e-58d8-bf8e-890f350518b3 | note | Standard / Specification - As per design
483b1bed-131c-5a70-ba89-4a84d2c1fe85 | note | Verifying Document - Delivery Dockets
920d35f7-38d2-5003-be20-f7d4b0026d4b | note | Frequency - Per Deliver
34722adf-8440-5111-a249-25ca9d27fc05 | note | Verification Activity: Activity - S
0b042295-333b-5a2b-ab64-a1277ad5c8b9 | note | Verification Activity: By - SE
49419f8b-735f-5d69-8a4a-402bbf513847 | checkpoint | 4.02.02 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
4e2afbec-77ce-5ff4-8940-052d8ebbd4de | note | Acceptance / Conformance Criteria - Pit sand, PAP 5 or an equivalent material approved by Engineer.
284a5bae-1a8c-5c46-a7ba-c40a016e7d31 | note | Standard / Specification - Project Specification
a2a5892e-284b-5a27-a452-b0113afba679 | note | Verifying Document - IANZ Lab Test Report
c04e6e94-1d0a-5b48-a0ac-ab01db1c0d18 | note | Frequency - 1 Test per 1000m3
27d9c726-f8fa-53fb-8e80-d96a1be49381 | note | Verification Activity: Activity - H
d046acea-3a80-59ee-90f9-f397a9b31f72 | note | Verification Activity: By - SE
90098259-9776-5c08-8fb1-d3278cb9f39c | checkpoint | 4.02.03 - Quick Mix Concrete (Haunching)
fc3e01ce-01ef-5844-8f70-d7da1298aa08 | note | Acceptance / Conformance Criteria - Mixed as per manufacturer's requirements
a8af5beb-bb93-5159-aff7-59df9dedfa3b | note | Standard / Specification - Minimum 20MPa concrete mix
9b15bb09-058c-5d4f-948a-cc5eee3223b4 | note | Verifying Document - Photographs
69cd3e5e-99da-533d-9ac8-29ad708dd47a | note | Frequency - Per Application
5a475ae9-4645-5524-830f-947eab89cc93 | note | Verification Activity: Activity - C
f27f1980-86fc-519a-8185-23f3cd4efb88 | note | Verification Activity: By - PE
f4713bb7-3aea-5dca-b516-69272c0b56ba | section | SECTION 5 – CONSTRUCTION ACTIVITY
a0a3241e-d9e6-5803-bd11-02070f8fd8e3 | checkpoint | 5.01.01 - Erosion and Sediment Control
f11b4a19-70d8-5132-9b72-76475c93370e | note | Acceptance / Conformance Criteria - Super Silt Fencing and Silt Fencing in place as per ESCP Silt Buster to provide sediment control for weir.
c63ec11a-068d-5925-8eef-8b26bcdde96e | note | Standard / Specification - ESCP WRC TR0902
3bf5ab1c-d45f-5e3f-86ee-c66e26eef8e8 | note | Verifying Document - Enviro As-Built
0c76fa4f-c4f0-50a7-a993-f8b3b3c8db55 | note | Frequency - Prior
a23355b8-d70b-595e-bdd0-e9dec7d46533 | note | Verification Activity: Activity - H
6af6abb0-de5e-5576-894c-47af67b651cd | note | Verification Activity: By - SE
245b8696-adb7-5f2c-9b1d-cc1f6ce78680 | checkpoint | 5.01.02 - Upstream and Downstream Bunds
54acba75-8db2-5cce-8b2f-bc3ed58af3f7 | note | Acceptance / Conformance Criteria - Temporary dam constructed via 1m sand bags, stacked up to max 2m height. 600mm rigid pipe at stream level to connect to 600mm flexible flume.
f3f06d3c-e123-5971-b3b2-3a175f2c10bf | note | Standard / Specification - ESCP
34926255-14e2-5e92-b995-8b915ec1abe1 | note | Verifying Document - Enviro As-Built
1e7d39ef-7cb2-50d9-a407-b9b86775bfd3 | note | Frequency - Prior
073b8feb-68a1-5c9b-b303-c76ecf526001 | note | Verification Activity: Activity - H
d4b50985-804e-5aa6-b796-661d2722d29e | note | Verification Activity: By - SE
50d11960-7f79-5920-ae0a-a4fcd1ed49d3 | checkpoint | 5.01.03 - Dewatering
f058a380-8e7a-5019-8f1d-4645f78c7c34 | note | Acceptance / Conformance Criteria - Water from downstream bund to be pumped to Lamella Clarifier and discharged under into the stream further down.
29a44ca8-7729-5464-9319-e725072da56f | note | ○ Treated discharge into stream to be between pH 5.5-8.5. TSS limit 150mg/l. Turbidity limit 50NTU or 100mm clarity. Non-compliant discharge notified to WRC within 24 hours.
51660c33-51fc-58c8-b474-890b7e9833c1 | note | Standard / Specification - ESCP / DMP
6a94940e-a469-598e-84be-1e8e4fe2870e | note | Verifying Document - Enviro As-Built
b0d79beb-315c-58fd-9a82-75df05093b9f | note | Frequency - As required
0afcb97c-4cd6-5f80-8cbd-f35f32b1d983 | note | Verification Activity: Activity - M
f706d808-605c-584e-a138-e3dfc323310f | note | Verification Activity: By - SE
7a69c176-b5ec-56c9-bda7-93b4fcff70d1 | checkpoint | 5.02.01 - Preparation for Filling
b51c54e2-b0a5-57af-bcf5-a96598d301a0 | note | Acceptance / Conformance Criteria - Preparation of the firm to stiff / medium dense subgrade beneath the proposed fill areas should comprise stripping of all vegetation, topsoil, any pre-existing fill materials or weak alluvium followed by benching of the exposed subgrade where natural slopes beneath the fill exceed gradients of nominally 1:5 (vertical to horizontal). CMW to inspect subgrade prior to placement of rockfill.
2e20430c-ea4c-5b22-8709-f8fdfdfe94e1 | note | ○ Benching in accordance with CMW sketch detail.
6f350a60-686a-5957-aee5-69957402de00 | note | Standard / Specification - GWS 2.9.2
0ea6e42b-57a1-55b0-ad32-f73daac24a3d | note | Verifying Document - Subgrade Inspection
b94816b3-e34e-5b19-bd0d-4fc4741fac49 | note | Frequency - Prior to placement and compaction of fill
89ef02a6-b38f-5b6f-a3c7-53d8df05b291 | note | Verification Activity: Activity - HP
7a9d41f0-1285-5b82-96ee-d2afb82f1552 | note | Verification Activity: By - SE
53ecf4d2-b8ab-54e8-a453-d4dc2dbb49e8 | signoff | AUTHORITY HOLDPOINT
32dff269-8784-5755-a8be-2972dbfdf97c | checkpoint | 5.02.06 - Rockfill Installation
50d9325e-eb95-5fb6-99f3-9e427df1617f | note | Acceptance / Conformance Criteria - Proof rolls at 500mm lifts, to be observed by CMW.
ed71057a-9a00-589c-b7b3-66e2e01e8208 | note | ○ Rockfill to be fully wrapped in geotextile filter fabric, strength class c.
a410a494-1160-5ca5-8684-479a2147c3f4 | note | ○ Wrapping to be inspected by CMW.
1bbd5637-ad77-5c13-a5e4-9a97f9e71366 | note | ○ Upon completion of rock fill instalation, inspection by CMW.
865aff46-7bb1-538a-ac2f-59379a322c1f | note | ○ Sharp edges of rock (protrusions) to be minimised.
afab0fda-af66-561d-94c6-0f7d81172440 | note | Standard / Specification - Designer
dd8c4447-ec3d-57c6-81d2-fffa25453893 | note | Verifying Document - Proof Roll Record
d7ca839a-03f5-5550-b6fd-35d4f7b855e1 | note | Frequency - per 500mm lift
2bea75db-55e6-52c6-a011-804154480285 | note | Verification Activity: Activity - HP
4dce9bb9-f93d-5d7e-a9ba-d591af3dea14 | note | Verification Activity: By - ENG
3256f48d-b92e-5f8d-a859-ee5b07a9660e | signoff | AUTHORITY HOLDPOINT
264f6f06-a3c3-568c-b289-3016c6b3c528 | checkpoint | 5.02.07 - Geotextile (Base of Undercut)
63e95285-c783-55e6-ba38-fbbf0ca475c2 | note | Acceptance / Conformance Criteria - Class C Geotextile to cover the entire base of excavation and be fully wrapped around the rockfill material. Minimum 500mm overlap required.
c8331358-7126-5054-aca2-eb6e6a050945 | note | Standard / Specification - Designer
ae1033ab-5c52-58d4-bba0-3bc48274274c | note | Verifying Document - Photographs
cf6aced6-cc9e-581d-866c-e1461fc1ddcc | note | Frequency - every overlap
e4a05fc4-212d-53e7-92ee-0efe140b2bbf | note | Verification Activity: Activity - HP
4d48ab13-388f-503e-8e1e-8c1122cf2747 | note | Verification Activity: By - ENG
0e08c485-83c1-58fe-976b-cc8ae8acacf9 | signoff | AUTHORITY HOLDPOINT
1e8f0f08-ad2d-547c-a2fd-a4cfeb605a61 | checkpoint | 5.02.08 - Geotextile (Top of Rockfill)
7ba1d97c-9ca2-5db1-a8e7-7d3321039b44 | note | Acceptance / Conformance Criteria - Class E Geotextile to cover the entire surface of rockfill material between rockfill – GCL interface.
3142aa81-6172-5edc-ba25-6c0a5c0f7e4d | note | ○ CMW to inspect prior once installed.
d4d9617e-2c0b-59a0-8f94-d55f45d69fbe | note | Standard / Specification - Designer
5b67ce8e-2de3-5c1e-bd81-5375da872b74 | note | Verifying Document - Photographs
2d8953c8-99b5-546a-a9e4-cc7a8c7d891f | note | Frequency - upon installation
3f190c29-4f5a-5a9e-9541-1feaf505299e | note | Verification Activity: Activity - HP
e1cb2d67-f5e1-5684-8987-b56669fd7e62 | note | Verification Activity: By - ENG
fb888e07-ecaf-5f86-98bc-b09c9d72ab05 | signoff | AUTHORITY HOLDPOINT
c6a8b93a-38a8-5fcf-a689-537377ef8d73 | checkpoint | 5.02.09 - GCL
2acea702-e75f-576d-b392-eb8a75855d71 | note | Acceptance / Conformance Criteria - GCL to cover entire surface of rockfill material.
a853246d-aede-506c-a3f1-4c3f12de78f6 | note | ○ Installed as per manufacturer's requirements.
2e9e603c-abb6-5cad-a886-f8970fd6463e | note | ○ CMW to inspect once installed.
8a81350b-f176-5c49-a21e-3e289d9ca00f | note | Standard / Specification - Designer
d80b413f-dccf-5628-9854-163145872118 | note | Verifying Document - Photographs
0618005a-b774-5664-923f-e3bdeb795cae | note | Frequency - upon installation
5a258718-5ba4-5b36-8423-d15427813142 | note | Verification Activity: Activity - HP
31a0991b-bbd6-5559-ae41-4e571f69e0fa | note | Verification Activity: By - ENG
b4bbb0be-38f9-523d-af9d-a1da95286a17 | signoff | AUTHORITY HOLDPOINT
345240cc-68c6-58b3-8735-0f3890af78a4 | checkpoint | 5.02.10 - Topsoil
a6075a6f-1f76-50ee-8f44-0504ee590e83 | note | Acceptance / Conformance Criteria - Topsoil to cover entire surface of GCL. Minimum 300mm of coverage.
3382de70-34e6-5ba1-8f4e-d7bcb55a8885 | note | Standard / Specification - Designer
4a28bc8c-6123-5318-a28d-28ba4011c6ef | note | Verifying Document - Photographs
3b9b2f42-6f5d-5550-8f8c-972f548b0c97 | note | Frequency - upon installation
c239aaac-a412-5a17-99b1-392b4cb3f7a7 | note | Verification Activity: Activity - HP
720cd90e-415b-52e1-993a-42c05a901f63 | note | Verification Activity: By - ENG
ba18abf5-f14a-52f4-b376-4db208790022 | signoff | AUTHORITY HOLDPOINT
3bdb2b5f-8cd1-5973-bfde-0b61b2481405 | checkpoint | 5.03.01 - Foundation Compliance
b55ee95d-14d1-5650-9a65-a85b0438fd20 | note | Acceptance / Conformance Criteria - Clegg Testing to be carried out on pipe foundation.
60fc9774-3084-5bb2-a852-1b14c959dd04 | note | ○ Clegg Test to correlate to minimum CBR of 15.
cfab5ed2-96a6-568e-911d-193ecefcc720 | note | ○ Foundation for Manholes/structures to only be measured with Clegg CIV of where there is a rockfill foundation.
10ec5f8d-d064-5bea-a915-e8db5bb7314b | note | ○ Other MH's and impact basin structures are to meet the foundation requirement.
ce4e78a2-c8f3-5bcc-aedf-efa7cb08736e | note | ○ Granular Material: Scala 3 blows/100mm
f7a3018a-6e64-5b27-b3fd-683756608177 | note | ○ Cohesive Material: Vane Shear Strength 70kPa
1f1a0f08-4750-54a6-88a8-bbc7754b28a1 | note | Standard / Specification - Project Specification 4.3
b072b2ee-7b46-5da9-a951-0d9213bd0d91 | note | Verifying Document - Test Results
18646c9f-0410-5b79-b9c3-e0c87476e1ed | note | Frequency - 0-5m: 2 Tests
32773128-569d-5670-b036-6b68866eb2a7 | note | ○ 5m-10m: 3 Tests
c2c4bb2e-071a-57f2-8950-a6e3cefc4cd0 | note | ○ 10m-40m: 4 Tests
cadcbb97-8e16-57ac-b602-c0e31884f96e | note | ○ 40m-100m: 5 Tests
3fa32cbd-90df-5c0e-b615-b7d873f1f277 | note | ○ 100m: 1 test per 20m
ff2b2980-7d85-572b-8e8c-7fe9498da924 | note | Verification Activity: Activity - H
4a26bd66-f010-5521-bbd2-be2c3b2b41fe | note | Verification Activity: By - SE
5f91dd06-5310-5bd8-94f3-255a5f2e86cc | checkpoint | 5.03.03 - Bedding Compaction Testing
dc3a2255-a6d2-5ed7-abd1-bb346710260e | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement
a9da3725-1fac-5295-867a-87de4cfd3e80 | note | ○ H2 Bedding outside pavement
6abde6b9-1765-543c-8681-fce07700fdcf | note | ○ NDM Back Scatter
2f5ca1b4-d6b5-5aac-a3f7-14c3ba763551 | note | ○ Minimum Compaction 95%(Average98%) of MDD
dfbad3e7-4dc6-55cb-8f21-d1192edcb638 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD, AS/NZS 2566.2/2002
8e48f539-29c2-5f44-99a2-04efc63bc220 | note | Verifying Document - IANZ Lab Test Report
c47a15ec-bfa9-54e1-86d5-a46d9c885bcb | note | Frequency - 0-5m: 2 Tests
6ec5cfb0-7b3a-5a4b-b555-d5e13e2fce23 | note | ○ 5m-10m: 3 Tests
0f194002-52ac-5e1f-95af-8c3806469a31 | note | ○ 10m-40m: 4 Tests
95bc8d3c-4fcb-5e2a-9de1-a2b51ea42c26 | note | ○ 40m-100m: 5 Tests
dad51fd2-4980-5291-904d-c3da0e068299 | note | ○ 100m: 1 test per 20m
3d88fd0a-5c89-5723-9f19-33d051e2fa64 | note | Verification Activity: Activity - H
43bc6622-1ba0-54c5-a7c6-c46ff4469ea1 | note | Verification Activity: By - QE
eded27d7-0747-58dd-bb62-60a2361af5fd | checkpoint | 5.03.04 - Haunch Zone Compaction Testing - Haunch Zone shall extend from top of bedding to 0.3 times the outside dia of pipe
724d04b3-1b92-5cb2-88d8-463afe2f742b | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm, Minimum Compaction 92% of MDD
f0859c49-ea0f-50c8-996e-0f2479497200 | note | Standard / Specification - HS2 backfil Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD, AS/NZS 3725:2007
9038c9e5-610d-59b3-8312-a2923c9d8ef9 | note | Verifying Document - IANZ Lab Test Report
4d28df91-1f42-5c4f-935c-c2adfe8fd29d | note | Frequency - 0-5m: 2 Tests
d02767d9-a864-5475-9f2a-5274910df8ca | note | ○ 5m-10m: 3 Tests
0001e8db-556e-5a89-a9af-7372a994e240 | note | ○ 10m-40m: 4 Tests
320febe6-d6da-5e86-ac6c-ab3b8f0e87ef | note | ○ 40m-100m: 5 Tests
3c999428-6307-5465-bed5-2675e24727e8 | note | ○ 100m: 1 test per 20m
c37ccf38-edde-5ad8-a060-e90ea4ee96c9 | note | Verification Activity: Activity - H
135cf194-9511-53f2-b8dc-756b00716020 | note | Verification Activity: By - QE
32da2de5-898e-585c-a7e4-ff4c1ec72a80 | checkpoint | 5.03.05 - Side Zone Compaction Testing - Side Zone shall extend from top of Haunch Zone to 0.5 times the outside dia of pipe
7e66f36d-0397-5e63-ae0f-158519f7b143 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm, Minimum Compaction 92% of MDD
ce4e57ae-e943-573f-bb55-c3dd6d95889e | note | Standard / Specification - HS2 backfil Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD, AS/NZS 3725:2007
490c3461-9aeb-5f2b-aa76-162ec411e8b3 | note | Verifying Document - IANZ Lab Test Report
435ddc6f-54f4-58df-bd1b-a821a216ca8f | note | Frequency - 0-5m: 2 Tests
94551932-feb9-5f3f-bbbc-fef3af3a9dc9 | note | ○ 5m-10m: 3 Tests
8d084df6-6ff6-5ebd-8947-27cb10032328 | note | ○ 10m-40m: 4 Tests
2ddef54f-e426-584a-8ca4-d03643cbdd02 | note | ○ 40m-100m: 5 Tests
08f27d32-ed34-5691-9ce7-6bef771daecd | note | ○ 100m: 1 test per 20m
70b1094e-1ea5-541b-ac72-68409d26fb28 | note | Verification Activity: Activity - H
377815e8-475f-57e7-9101-fbafb0d1c3e0 | note | Verification Activity: By - QE
f67f1bb0-124a-5cac-896c-3ec40b4d6a11 | checkpoint | 5.03.06 - Overlay Compaction Testing - Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
29f801e7-b1e6-5e0b-aa84-d675150e2695 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm, Minimum Compaction 92% of MDD
5ca94f16-1fa0-50b1-a67a-9befb9e9b614 | note | Standard / Specification - HS2 backfil Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD, AS/NZS 3725:2007
9af48a72-2b61-544f-af7a-bf8cdb1541c7 | note | Verifying Document - IANZ Lab Test Report
cc10a700-2dcc-5b32-8147-6f2f294065ed | note | Frequency - 0-5m: 2 Tests
0c050877-5d5f-5012-a46f-d1547cd84708 | note | ○ 5m-10m: 3 Tests
c0649d09-323a-5fa4-854b-453cd9075a03 | note | ○ 10m-40m: 4 Tests
32ff98bb-4691-5d3c-ac0d-89d09c079655 | note | ○ 40m-100m: 5 Tests
86e904ea-07a6-53b1-9799-d0da4911d327 | note | ○ 100m: 1 test per 20m
ecedb7ed-d6b7-5297-9e75-2458deed2574 | note | Verification Activity: Activity - H
74e071f4-61de-50e9-b082-3724631544a0 | note | Verification Activity: By - QE
789b79cd-23bd-5d43-9cfd-b0617072c968 | checkpoint | 5.03.07 - Backfill Inspection
dcf91b58-b051-58d0-9d26-2f5053684b85 | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the pipeline.
03bf4ee6-950a-51c7-ab1a-19f369d3efaf | note | Standard / Specification - Project Specification 4.3
a88f1c7a-2f09-5411-8a2f-1af1e21e4eab | note | Verifying Document - Photographs
e6527e3e-8dd0-521d-aca1-3e32488276f5 | note | Frequency - Continous
bf88d45f-22b3-5afe-8489-92be6fea5740 | note | Verification Activity: Activity - S
449f8cad-da26-5363-8b85-5c192d2faaa2 | note | Verification Activity: By - SE
85cb5029-9359-5443-98cd-4245b546d7a6 | checkpoint | 5.03.08 - Survey
a7dc218e-8f72-5db4-b3cd-087141213222 | note | Acceptance / Conformance Criteria - Invert Levels: The permissible deviation from the designated level of the invert at each manhole or structure shall be ± 50mm, provided that the fall between successive manholes or structures shall be at least 90% of that specified.
ced861f9-5ce8-578d-a0f6-58c592bd008a | note | ○ Horizontal Alignment: The permissible deviation of the horizontal alignment between manholes or structures shall be ± 100mm.
210e443f-20bd-59ee-8b03-82f447d31bf5 | note | ○ Gradient: For straight gradients, the permissible deviation from the specified gradient shall be ± 50mm from a straight line drawn between the inverts of successive manholes, provided that no point in the pipeline is lower than any downstream point.
935c4594-bbfb-5a26-8740-d9c4274a56d3 | note | Standard / Specification - Vertical tolerance +/- 50mm, Horizontal Between Structures +/- 100mm
a210ccf6-e41c-5981-bf51-75bdfce45c89 | note | Verifying Document - Survey Data
0c242641-004d-5f84-b5b5-f7022f76127d | note | Frequency - Continous
fb6640f8-9bea-5aae-870e-ed2792c874be | note | Verification Activity: Activity - C
e2c3b92d-93ac-5342-b6fe-14415b4c32cd | note | Verification Activity: By - SV
a510b923-50d6-5044-9b85-2f72b7085b94 | checkpoint | 5.03.09 - Backfill Compaction Testing
e086987c-745d-5013-a75f-4a2757f3d279 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm, Testing to be completed on 300mm lifts of backfill - 95% of MDD at OMC (98% Average)
a2da9514-d309-5657-abc4-cd9467e73b00 | note | Standard / Specification - PS 4.3 NZS 4402 Test 4.1.2
4d870036-3fb0-5147-bec4-220f851d04be | note | Verifying Document - IANZ Lab Test Report
2d2765c9-b717-5902-a5ad-b7704afe8924 | note | Frequency - 0-5m: 2 Tests
e5ae1199-b69f-5685-8d16-01015b1b1445 | note | ○ 5m-10m: 3 Tests
9a3e4f2b-2c46-5886-8e2d-80c95bc4e4e4 | note | ○ 10m-40m: 4 Tests
c494ba11-12b8-5fe4-bd2f-b23a22f94ea8 | note | ○ 40m-100m: 5 Tests
d5add86d-8e88-58cf-959e-306c209d238b | note | ○ 100m: 1 test per 20m
94a72d94-9963-5ecb-8b15-1ea897990349 | note | Verification Activity: Activity - H
fd165329-6ad0-5b83-97a5-0648bf771ccf | note | Verification Activity: By - QE
fa33c499-47e1-583c-9603-8a520fcfb383 | checkpoint | 5.03.10 - Riprap Mix
878b4941-3a10-5414-bfb6-564c591dd6ea | note | Acceptance / Conformance Criteria - Riprap Mix Materials to be stockpiled separately and mixed in a pre-determined ratio to make a suitable riprap product
e8343953-48dc-50fe-a1bf-72e00caa754b | note | Standard / Specification - Designer
6235149d-a239-561a-b44f-d5e4ae7b4ddf | note | Verifying Document - Photographs
713842cc-94b5-5097-a161-8542d23a60e7 | note | Frequency - Prior to Use
44ec665e-a01d-5890-b5da-e03ffe673a5f | note | Verification Activity: Activity - HP
1d54fdae-9110-51e6-b7ce-8db3f99eddf6 | note | Verification Activity: By - ENG
9231d8df-716a-56ef-a9b9-12ffe2c27114 | signoff | AUTHORITY HOLDPOINT
01556592-3577-5f82-8e71-c2a719bb538d | checkpoint | 5.03.11 - Riprap Embedment (Fish Passage)
cdfc014c-a10d-548f-8d6f-c696941ac473 | note | Acceptance / Conformance Criteria - Riprap layer within 1200mm fish passage to be 400mm high. Pipe laser to be used to ensure compliance.
dcba4e6a-60c4-5713-8ad5-82ca7a07cab5 | note | Standard / Specification - Drawings
852c1f8b-9800-5f93-a3d4-383666e767dd | note | Verifying Document - Photographs
0f210afd-685f-5e6c-825d-04d32fe614d0 | note | Frequency - During Placement
7b30e782-8588-5692-97b3-b36e1c5baa5c | note | Verification Activity: Activity - H
69aec4db-4eb2-5dca-bfb1-24f55c110edd | note | Verification Activity: By - SV
0b29c5e4-6ee6-5502-a8a7-b8eaa0dfa482 | checkpoint | 5.03.12 - CCTV
bdd9892f-823c-5caa-8cdf-7c8ca33ec5e2 | note | Acceptance / Conformance Criteria - CCTV inspection of 750mm stormwater and wastewaterline. CCTV soft copy to be provided to designer.
0a974a2b-3145-535c-baaf-40d7c7c88a59 | note | Standard / Specification - Project Specification 4.4
890e9cbe-2bec-5e1b-915e-18ad6b2f3aa9 | note | Verifying Document - Soft Copy
26593b59-9967-5f89-ace2-af0abc2c2886 | note | Frequency - Post Installation
f2b9aadb-5d8b-5f68-add9-6e4dc001927e | note | Verification Activity: Activity - H
44f350ff-13b1-55d4-97fd-f09beaca045a | note | Verification Activity: By - ITP
3bc3bab2-96a4-4f2f-a916-d72307e6a577 | checkpoint | 5.03.01 - Foundation Compliance
fd34d301-26d3-500f-8f99-0c7fb6589a5f | note | Acceptance / Conformance Criteria - Clegg Testing to be carried out on stormwater manhole foundation. Clegg Test to correlate to minimum CBR of 15.
d9503fb6-220f-5276-91c5-098ab1fee445 | note | Standard / Specification - Project Specification 4.3
e8d3e17c-a71e-5a16-90c9-e4de7de8066e | note | Verifying Document - Test Results
ae626582-caa2-5365-a507-8e99f5e60248 | note | Frequency - 1 Test/Manhole
86546370-005d-505a-b6de-7a6e27a44bca | note | Verification Activity: Activity - H
f9894d30-15f7-5846-b4e4-68aa6e70a56d | note | Verification Activity: By - QE
c0036c2a-1e4f-531a-a3dc-2f6ec4abbd05 | checkpoint | 5.03.02 - Undercut Backfill Compliance
1ad0cb45-b924-5730-b7d1-4210a09ca065 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm, Minimum Compaction 95%(Average98%) of MDD
2c955765-385c-524c-9b36-c2bf200e02bd | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD, AS/NZS 2566.2/2002
6c01245b-b0d6-5ba9-b696-143972c94b08 | note | Verifying Document - IANZ Lab Test Report
7b42a5a6-6e49-5414-8d8c-bff861cab0f4 | note | Frequency - 1 Test/Manhole if Undercut required
6e1bd190-a6bb-5879-9152-ba4bdb07bb2f | note | Verification Activity: Activity - H
c9dc2025-28c8-5086-8702-13583b6304a3 | note | Verification Activity: By - QE
e90878cc-36b8-4cb8-b54f-ec77b833f300 | checkpoint | 5.03.03 - Bedding Compaction Testing
ec77daa6-f791-5169-bb68-75edec0cbfe4 | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement
5e84ee1d-c4a5-5211-9f32-7703f444b30f | note | ○ H2 Bedding outside pavement
9e7ca304-ca46-527e-8e50-0f22f431b2ae | note | ○ NDM Back Scatter
0450ab7c-3215-5452-8582-d329ea14b4b7 | note | ○ Minimum Compaction 95%(Average98%) of MDD
b8811638-806b-57a3-b416-c2a3c7bceb8e | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD, AS/NZS 2566.2/2002
4754476e-92ee-511a-9365-43c2d580e74a | note | Verifying Document - IANZ Lab Test Report
1f11f28b-b694-51a6-a649-7f240417fe99 | note | Frequency - 1 Test/Manhole
0d06c8e2-1009-502f-bacd-92d40e336d4c | note | Verification Activity: Activity - H
f47e8bfa-2b87-5112-a17b-4c8e58fde2a2 | note | Verification Activity: By - QE
86e920aa-9ac4-5f4c-a96f-7d4ef6859da9 | checkpoint | 5.03.04 - Backfill Inspection
f7e931f4-9c70-5218-8b3c-e17d39ab43ed | note | Acceptance / Conformance Criteria - Inspection of manhole prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the manhole
c4305192-6b53-55b8-9b9b-6ac7ca4a4ca8 | note | Standard / Specification - Project Specification 4.3
ef54d60b-78ff-5582-ae1a-7930d5d25c12 | note | Verifying Document - Photographs
91911a7b-45c7-5425-ba5d-e39a40f9c319 | note | Frequency - Continous
68122910-e3f9-5352-b9a6-592939924311 | note | Verification Activity: Activity - S
14e00c73-5837-5954-b5e6-3f25d08425d8 | note | Verification Activity: By - SE
6f67e221-46c1-576b-8cd6-9ae2220043b1 | checkpoint | 5.03.05 - Survey
c5cf73df-46be-5122-ae3a-3b08a98b0bc0 | note | Acceptance / Conformance Criteria - Invert Levels: The permissible deviation from the designated level of the invert at each manhole or structure shall be ± 50mm, provided that the fall between successive manholes or structures shall be at least 90% of that specified.
2ad06ee2-e1d8-5d3a-bcab-6d1eec2d78a0 | note | Horizontal Alignment: The permissible deviation of the horizontal alignment between manholes or structures shall be ± 100mm.
17e0db54-b35e-550d-b3a9-e407751a71aa | note | Gradient: For straight gradients, the permissible deviation from the specified gradient shall be ± 50mm from a straight line drawn between the inverts of successive manholes, provided that no point in the pipeline is lower than any downstream point.
f23299f5-18aa-5103-8e5d-504be8fddd73 | note | Standard / Specification - Vertical tolerance +/- 50mm, Horizontal Between Structures +/- 100mm
e247f170-c8e5-58bf-820f-c233c5c5bad2 | note | Verifying Document - Survey Data
1a873de4-86cd-5905-853f-0d36f0322696 | note | Frequency - Continous
56d9a159-e53c-5357-9aac-58c7314f6dc0 | note | Verification Activity: Activity - C
025322d8-7f53-5f13-b4ce-a3b7351c3604 | note | Verification Activity: By - SV
3b6d6adf-7ccd-5e47-bbff-fb7fe1fbbc52 | checkpoint | 5.03.06 - Backfill Compaction Testing
4c8cef46-bd8b-5c06-a6f4-615194d8c7fd | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm, Testing to be completed on 300mm lifts of backfill - 95% of MDD at OMC.
676402f0-db58-5a7a-af71-491f42dbc804 | note | Standard / Specification - Project Specification 4.3
494d7744-bba1-5594-a4b6-f8515d30506f | note | Verifying Document - IANZ Lab Test Report
8ec0ea6d-41e8-50c7-8143-da9ead265469 | note | Frequency - 4 Density test per layer at Quarter Points around the Structure
319b0245-3546-5252-86b2-86258a88746f | note | Verification Activity: Activity - H
00e9d107-9944-5c73-8268-57dc5bec2a5a | note | Verification Activity: By - QE
0ae2e1e8-d063-526a-ac83-bbeccdbdc563 | checkpoint | 5.03.07 - Haunching
fa8e61c0-7abb-56ba-8cea-5ca39f06ca69 | note | Acceptance / Conformance Criteria - All the MH's needs to be haunched as per the specifications
a6cb336e-0efe-5213-a820-c9e3d843cca2 | note | Standard / Specification - RITS
57c26e68-cc09-543d-a0f4-7cda40a44e70 | note | Verifying Document - Photographs
09e57cbd-18ee-5c11-808a-c95fac4abbcc | note | Frequency - Continous
acb1dbd0-2c47-5503-b297-f7c99400d9e3 | note | Verification Activity: Activity - S
b78a01d7-79a3-5df8-8f0d-9ce0cd6ff1d7 | note | Verification Activity: By - PE
cd33a7f8-9b6c-5422-93be-dcae98eaa460 | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
30c1fa68-4e86-52de-be2f-82bc976b49d2 | checkpoint | 6.01.01 - Redline Drawings Critical Elements
5abab56a-8459-5600-badb-3738bac3673b | note | Acceptance / Conformance Criteria - Undercut/topsoil clearance. Any placed fill. Any drainage undercuts/structures.
30c42886-a473-5b08-9056-1423791a25a6 | note | Standard / Specification - Downer
f612c9f8-6b6a-50c9-85a4-8e9e38fa9f93 | note | Verifying Document - Survey Records
e33b7842-123f-555e-9dc3-5be2d91a87ec | note | Frequency - After Completion
c9be6676-5970-54f5-a6c2-dee0feb280a3 | note | Verification Activity: Activity - H
61b1032e-6fbc-55df-844e-732cf338d6e8 | note | Verification Activity: By - SV
0a2ffea2-b95b-5c53-adb4-fe0ff23ffd3c | checkpoint | 6.01.02 - Red-line Markup
a1c16fe4-68f0-56cf-86e9-133ba4b0c69b | note | Standard / Specification - Downer
cb7eed1c-7840-597b-aed7-49daabaf0dc0 | note | Verifying Document - Red-line Markup
5433b9fd-23e6-5d94-9d72-1d0101dbe327 | note | Frequency - After Completion
bcf1c120-0ee8-5cdc-8169-70f394216c0a | note | Verification Activity: Activity - H
a26a611e-95af-5a36-b6ac-3ceeb9f24310 | note | Verification Activity: By - SE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
27a54a6d-a0b9-5ae9-aaaf-bb1f7cbb92a5 | checklist | ITP - 134 - Concrete Islands Infill Construction Rev A | itp | ITP - 134 - Concrete Islands Infill Construction Rev A
1c532be2-4976-53fe-8741-ab7deecf2547 | section | 3.01 - Site Requirements
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
ae81a148-3ca8-5190-8b63-19022415d0ab | note | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
704966a6-cfd3-5db1-b172-9c96cf937822 | note | Standard / Specification - Downer
3f5ff9a5-db98-5f56-a659-031ff6669f08 | note | Verifying Document - Construction Pack
fc46b3fe-d912-5783-9d3b-d532ad04f6fa | note | Frequency - Submit 10 days prior to commencement of works
017ea354-543c-5c12-a812-39b39ab38e70 | note | Activity - HP
f0d8d4fc-5ecc-5772-8c1a-bfa36b56cbaf | note | By - ENG
ca255811-cbe5-57f5-8b49-d49ad30655f3 | signoff | AUTHORITY HOLDPOINT
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
3f02d952-2854-554c-b911-b2da156d5454 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
491de3eb-2ce6-50ca-9f71-c9b9a1516925 | note | Standard / Specification - Downer
0f0f4735-d140-501c-9f7d-6a44f539df86 | note | Verifying Document - Survey Records
a6b57a64-b2e7-52dd-afa7-15965695ab87 | note | Frequency - Prior to Works
59e7b864-38ef-5610-ac93-7e86baef20a8 | note | Activity - H
dadab718-59f3-56c9-b6ed-415eee977643 | note | By - SV
a24a2c58-bf6f-5474-883c-40044bad1fc7 | checkpoint | 3.01.03 - Service Location
13dd371e-9143-55bf-806e-23ba29f3e6f9 | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
4c52d324-be21-5d3a-922e-6bf74ba62cbe | note | Standard / Specification - Downer
7321b4dc-29a4-56f5-b98f-53b51ad1cced | note | Verifying Document - Excavation Permit
b2860919-647f-5332-a12f-4b1b88c5b771 | note | Frequency - Prior to Excavation
578ee693-2fe3-55ec-bd47-89a43c460581 | note | Activity - H
ba0bea28-fa56-53a1-8983-b9165e9c5db1 | note | By - SE
0a214a7a-124a-5898-a837-e29e83751df0 | checkpoint | 3.01.04 - Internal Permits
bd3e016f-9150-5ecd-b4a4-bc5bbd0ead7c | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
d8125674-56e0-5b26-9d7b-46d18edd44e8 | note | Standard / Specification - Downer
ead5b870-a5da-58e0-8533-58831ce0d5ea | note | Verifying Document - Internal Permits
eb91373b-6d16-54f1-bc57-8e41c3936bee | note | Frequency - Prior to Excavation
4bb2b735-e03d-58c4-a637-80647f0bc5cc | note | Activity - H
caafedf2-480f-5a98-bf92-e0ef8597e5c8 | note | By - SE
917e2881-0901-542f-ae25-686bf9c47009 | checkpoint | 3.01.05 - External Permits
61839e6c-a50b-571c-a5ce-50ee8d310f88 | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
d4e95e7a-6666-5962-912f-0ce8c41f02f7 | note | Standard / Specification - Downer
6c653100-cca9-5b64-ae29-1abee14b3be0 | note | Verifying Document - External Permits
bd94d492-2b21-51a4-9435-eb8cc859fd88 | note | Frequency - Prior to Excavation
4dff60ee-4af4-5c3a-8bda-ac6fa1911803 | note | Activity - H
fefe45d6-d10a-5d22-b29e-2cb71d397e10 | note | By - PE
a1302970-0389-558d-b43c-67b14bbfc27a | checkpoint | 3.01.06 - Approved Construction Drawings
5c14f703-3312-5f10-b3a9-e774759bd544 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
f1626f2b-c6a5-5836-8676-06dd97aea10c | note | Standard / Specification - Downer
27634d1b-4b60-5aee-b3ba-7c8eaa0b458c | note | Verifying Document - IFC Drawings
6dbee673-fcd9-5d63-85d6-786cafa6ae9e | note | Frequency - Prior to works start
86863836-1690-5090-9199-ff4ccb507417 | note | Activity - H
10322b33-ebb9-5006-8753-d8f8cce45327 | note | By - PE
30e66181-e18e-5c62-90b6-4ffad1837210 | checkpoint | 3.01.07 - Previous Completed Work Packs
f69c15d3-5bf4-5b87-81b0-fb6984bba348 | note | Acceptance / Conformance Criteria - Review previously completed workpacks to ensure work completed meets the contract requirements
568936ee-067c-5326-a0ca-a604fdddafd2 | note | Standard / Specification - Downer
ef35e150-8df8-5ca6-be2c-a7d92a1c05e9 | note | Verifying Document - CONQA
0f58c8b6-9a3b-5926-935a-3ab50ff82aac | note | Frequency - Prior to works start
e75cbe3d-cdd9-5979-a698-9172de46832b | note | Activity - H
24c640c9-8812-5671-99e6-e566a5b2944f | note | By - PE
a9894fe9-2963-5304-81f4-e09291bd6b94 | section | 4.01 - SUB ACTIVITY
4fd6d267-7c5b-56c7-a498-2e8076151975 | checkpoint | 4.01.01 - GAP20
d55d4c8d-41d7-5a7a-8b6a-59bf08c4326b | note | Acceptance / Conformance Criteria - Record material type used and source testing of that material
f0770170-d2a6-5d3a-9ebd-e2b330011b1f | note | Standard / Specification - BBO
67484e98-2442-5581-9c6c-4db351b87a30 | note | Verifying Document - Source Test/Site Notes
a028151d-7393-5e6e-9fff-1f64c17e7d9e | note | Frequency - 1 source test per material type
d0ad34b4-4ce1-58dd-a56a-48113b787e43 | note | Activity - R
8c66e3fa-6f49-5d25-9d26-9b769965aa62 | note | By - SE
eb59e516-39e9-58e2-aeb8-24bb47f7c610 | checkpoint | 4.01.02 - Conrete Mix
f0a63cca-06f4-5b9a-9ea2-8d2cc3d53cb9 | note | Acceptance / Conformance Criteria - The strength of concrete as defined in NZS 3109 shall be 28-day cured in-place minimum strength 20MPa. With a 13mm size aggregate.
5189fe51-cace-54aa-bf9f-dc846fd2c38d | note | Standard / Specification - NZS 3019
4b7e40cb-b3a2-54be-a00f-f7653de42c14 | note | Verifying Document - Source Test/Site Notes/ Concrete Dockets
a7ed90df-8a9b-5d99-b21e-4d880eb3ad1a | note | Frequency - Each Pour
59fbcec2-56ab-5b55-8212-0c867840110e | note | Activity - R
4b751d7c-5893-5b8a-8726-1defa8c41087 | note | By - SE
9ad2b7e3-627a-5363-8e2c-34618a7d17ae | section | 5.01 - Traffic Islands Construction
41623baa-dff7-5204-804b-d95fbd906fd1 | checkpoint | 5.01.1 - Islands Set-out
0fe6d797-9e7f-5860-8de5-ccbcf7ec30d4 | note | Acceptance / Conformance Criteria - After set-out and prior to installation of footpaths
84aa6dd8-da16-5d8e-a7a9-802b3d723273 | note | Standard / Specification - PS - 2.2.16
1d16451a-6680-5408-aed2-77b493b5094b | note | Verifying Document - Hold Point Release
bae99dda-364a-540c-8e83-29f7e18ba1a6 | note | Frequency - Min 24h Notice
123e6dc3-d902-5c5e-b9a2-fa968c825d61 | note | Activity - HP
74475f97-7ab7-546a-85c1-1e3b7ce2993d | note | By - SE
9db2b286-ec3d-58c8-8ae0-96093d637b81 | signoff | AUTHORITY HOLDPOINT
daaa6a3e-47c7-58f0-9443-f018d626d762 | checkpoint | 5.01.02 - Concrete boxing and Base
06294422-f961-597d-a121-a3fe6de20d93 | note | Acceptance / Conformance Criteria - Surveyor to check boxing for concrete pour, this includes the boxing for slots. For the front side of island aprons top boxing to be 50mm above F.L.
29afec8c-83cc-547b-964c-e447606b3d43 | note | Standard / Specification - Downer
027cc3c0-6a74-5b83-8c01-8626d8544a63 | note | Verifying Document - Hold Point Release
892e665c-cd19-57f2-aa05-94795135e172 | note | Frequency - Min 24h Notice
636d010c-0a6c-5c09-87d5-88b1672a9f6b | note | Activity - HP
20e5c5b0-1380-50f3-9a1d-60ed7450c33e | note | By - SE
364352ff-bd0c-5c3e-8ffe-5e0d7c05f08e | signoff | AUTHORITY HOLDPOINT
6ffab25c-74e4-58fa-8ff1-8c139a92e835 | checkpoint | 5.01.03 - Concrete Strength & Reinforcing (Island Apron Kerb (mounatble kerb) and Infill)
a92e67be-05eb-53c0-8c50-07cd489f0d1d | note | Acceptance / Conformance Criteria - Concrete to be at minimum of 350mm on the back side of the kerb with a max of 400mm thickness for construction tolerance, with 20MPA broom finish. Island Apron/Mountable Kerb reinforcing to be D12 Bars & R5 Stirrups @ 600 centers (min 75mm cover). For the infill, two layers of 665 Mesh (75mm min cover bottom cover and 50mm top cover).
0262803d-140d-5827-b7b3-141b32dbf760 | note | Standard / Specification - Downer
263c2145-b1f7-5e21-81f2-5b94abeb72a2 | note | Verifying Document - Hold Point Release
fb7e2144-bbee-5bf1-b9d8-d53b244a77a0 | note | Frequency - Each Pour
73c9f624-45c9-5b30-b5a8-aea6e56a779a | note | Activity - HP
d03d1069-0296-54a3-b7a5-0f4723190a3e | note | By - SE
bc9ec4c0-b35b-5a7f-8500-6f8160e7252b | signoff | AUTHORITY HOLDPOINT
7301301e-e0a8-5e6e-a79d-61ddc04584eb | checkpoint | 5.01.04 - Concrete Pre-Pour
fb368de0-8112-5abc-8928-144e54eac107 | note | Acceptance / Conformance Criteria - The Contractor shall give due notice to the Engineer of the time it is intended to place any concrete and no concrete shall be placed until approval has been obtained from BBO. Pre pour check wil includes checks on cover, lap length, spacing and bar sizes are followed per drawings specifications etc.
b5f317d4-f268-5c27-b06a-ade443fe061c | note | Standard / Specification - RITS - 3.4.5.3
0a495404-fc8b-5605-b84c-0396bf83a6be | note | Verifying Document - Hold Point Release, Pre-Pour Check
b5c205da-2af3-5ccb-a1a5-ee3891749383 | note | Frequency - Min 48h Notice
4f6c5fe0-4b1e-5896-be78-30c23b44304d | note | Activity - HP
031fe49e-e9e7-5880-ad28-47805653cfba | note | By - ENG
3e6ffc13-6f9a-59bf-8666-1d2c37e68cac | signoff | AUTHORITY HOLDPOINT
90aba5c4-77c2-523d-a47c-441eace65a00 | checkpoint | 5.01.05 - Ground Preparation
815aad61-551d-5d36-b96f-bcbc447b52bc | note | Acceptance / Conformance Criteria - Immediately before placing the concrete, the foundations shall be lightly dampened, and formwork shall be cleaned out. In all cases surplus water shall be removed before concrete is placed. Any foreign or organic material hall be cleaned out.
2db51c2a-8a74-51eb-a355-531c42bc3c44 | note | Standard / Specification - RITS - 3.4.5.3
03d2d28b-9373-54b1-a7bb-0ad4a84b7a27 | note | Verifying Document - Pre-Pour Check
63bb35c0-c94c-53d7-9363-c5d1b8461d6d | note | Frequency - Each Pour
1daa4a2a-2f67-5940-af39-0fe01a6256b6 | note | Activity - H
f364f2af-39cf-5680-a74e-81f1aca7cd20 | note | By - SE
aa327647-7799-5d9b-bc66-54603dce7432 | checkpoint | 5.01.06 - Frozen Ground & Unfavourable Conditions
d3120ef9-d2ac-5f48-a0b2-d41deeecf149 | note | Acceptance / Conformance Criteria - Concrete shall not be placed on frozen ground nor shall it be placed in unfavourable conditions, which may be detrimental to the quality and finish of the concrete (i.e rainfall)
dce14285-0951-52a4-b30c-5289667c0aea | note | Standard / Specification - RITS - 3.4.5.3
d2e0877a-4c06-5a69-9c01-1bb71e139452 | note | Verifying Document - Pre-Pour Check
31bb80cf-8a0f-543c-830e-e48c59f445a8 | note | Frequency - Each Pour
09f8552f-6909-5a7c-8deb-94398cd753e1 | note | Activity - I
8be1cb01-8414-559e-841c-fe3f42093304 | note | By - SE
9225dba5-ebad-50e5-92c1-c7d4c46f8a4e | checkpoint | 5.01.07 - Curing Of Concrete
2b09eba1-044b-5415-8890-36c6730e95bb | note | Acceptance / Conformance Criteria - Immediately after placement, concrete shall be protected from premature drying, excessively high or low temperatures and mechanical damage and shall be maintained with minimal moisture loss for the necessary curing period and hardening of the concrete. In hot dry weather sprinklers or damp covers will need to be used.
0907f66c-1b92-59ef-a493-93204662cf13 | note | Standard / Specification - RITS - 3.4.5.5
fd7d7029-904f-5147-8a45-c969deae89c8 | note | Verifying Document - Post Pour Check
f010c34a-8f8f-5fc2-9d8e-70b826ff96da | note | Frequency - Each Pour
5975946b-acd9-5096-88b5-30e04829d049 | note | Activity - I
d2c9d4d6-413b-51d6-b024-d74c037cdbd3 | note | By - SE
397e2b7c-b941-5891-8ab3-34b867cf92f7 | checkpoint | 5.01.08 - Concrete Compressive Strength
424acf0c-538b-5b73-8fa4-7eee531ea118 | note | Acceptance / Conformance Criteria - Concrete to meet a placed 28-day compressive strength of 20-Mpa
4c90ca90-303e-5a90-b756-dd9bb2984cfb | note | Standard / Specification - RITS - D3.3.5
b7902e3b-811a-5489-baa4-c6d05b3acf75 | note | Verifying Document - Concrete Dockets
db8e5d0f-eac2-5359-93ee-ae4ab669a2eb | note | Frequency - Each pour
7a6247e7-d549-561c-9933-40b759f6af94 | note | Activity - R
0c88d803-a735-5738-b9fb-c1dc503ae293 | note | By - SE
b3ff8283-17ba-5a4c-9bee-1c3cddf33e87 | checkpoint | 5.01.09 - Finished Work
e940b484-42a9-5ba1-b831-536a9937e100 | note | Acceptance / Conformance Criteria - Methods shall be used that will provide a smooth, clean and even surface on the exposed faces of all concrete work.
3c0661e6-1fad-587a-a624-8486fb0ed437 | note | Standard / Specification - RITS - 3.4.5.7
b8ebe5f5-1496-5ebf-951f-f5545e00dfe6 | note | Verifying Document - Post Pour
6dc8d683-796c-5bc4-bcef-d48b7259da5d | note | Frequency - Each Pour
bb7d2291-e932-521d-8bf0-0398ad9c9a31 | note | Activity - I
fc405d27-ebb5-5e5c-995c-e4af3ffb1761 | note | By - SE
762a6d33-d78b-51db-897c-52ed575e3ed5 | checkpoint | 5.01.10 - Contraction/Expansion Joints
a6e700d4-3fa9-57f2-90c0-49db570240b8 | note | Acceptance / Conformance Criteria - Contraction/Expansion joints shall be formed or cut along the kerb at a maximum spacing of 3.0m. The slot shall penetrate the concrete by not less than 50mm and the mortar dressed over the cut face. The contractor shall ensure that cold joints are accurately marked and setout via total station so that the subsequent saw cut is in the cold joint. Should cracking occur adjacent to the saw cut a minimum section of 1.5 metres of the traffic island shall be removed and re-cast.
7c91362f-c808-5fd3-aaf1-ccfed1f9515d | note | Standard / Specification - RITS - 3.4.5.8
bedfa861-1ee1-5b12-a69d-b52117f75cc5 | note | Verifying Document - Post Pour
ceb6dd0b-f109-55c2-9bbc-a747de47ec63 | note | Frequency - Each Pour
ba31822c-b7f8-5585-81f8-f4603570dbd6 | note | Activity - I
fba2f8ae-88c4-50bc-94d1-6f6c87644711 | note | By - SE
8989e458-2a9d-5972-a99c-c0b2c7d4d5bf | checkpoint | 5.01.11 - Finished Concrete (Surface Finish & Final Levels)
b43aee56-f805-5b5e-b84f-b943cd57f73e | note | Acceptance / Conformance Criteria - All final path and vehicle crossing surfaces shall be true to the lines and levels Specified and ‘broom’ finished. Design considerations aside, the final surface shall not vary by more than 5mm when checked with a 3m straight edge. No finished surface shall hold water.
18a87a83-b3b3-5df1-9a24-dc42f368fef0 | note | Standard / Specification - RITS - 3.4.5.10
9956a369-6b69-5c03-8027-24a28f1388b4 | note | Verifying Document - Post Pour Check
0c2a5393-9b4b-547b-80c6-fc6d0bbe1377 | note | Frequency - Each Pour
a57efa40-dacd-592f-b41c-b98237c254e3 | note | Activity - I
e1989631-cf1a-59f0-bc1c-e5d009b8bf24 | note | By - SE
2afc4e4d-8153-5065-9965-5efc9d294d5b | section | 6.01 - General
abaa7cc7-67ff-52ad-ae9f-e9176b336a01 | checkpoint | 6.01.01 - Construction Record Compilation
27d0035e-08b9-5669-bb5c-17ada2d84a9c | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
7f068a28-7d10-55d8-a75f-daab061a9f8f | note | Standard / Specification - Downer
08bd4551-1fad-5172-8088-630d857169ee | note | Verifying Document - Records
5f05ade7-9020-5c1e-843d-2d5bb69b86e5 | note | Frequency - Post construction
b828fa67-8ff6-5895-8435-b1cc805eac95 | note | Activity - H
65e63267-c059-565a-b63e-ee3f4757c480 | note | By - SE
f4876821-e136-54ca-95e8-27fd0f400f5d | checkpoint | 6.01.02 - Survey Records
bc088579-acb7-5c77-bdf1-a7ee0afcc95f | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
d7aa4f66-d175-58eb-bdd4-af3b2aa666c1 | note | Standard / Specification - Downer
26bb02c4-bf47-5c9f-9d8c-283b22cbfb35 | note | Verifying Document - Records
72fa2a73-1dda-5af6-8b8b-bf899a3a4b56 | note | Frequency - Post construction
919fc70e-f6a5-5a21-96e0-3a6b18b4fd05 | note | Activity - H
dca164d4-345e-5624-83d4-7d71d92a5afb | note | By - SV
a7ece1a0-6b4a-5d51-8813-156cc41a337a | checkpoint | 6.01.03 - Redline Drawings
61a3cf43-7a3b-5adc-badb-a41fa17b6992 | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red line to show any changes to footpath location or basecourse depth.
d31590e0-dcb1-58e5-a8a2-c97df03c7226 | note | Standard / Specification - Downer
0dae8db4-789d-57f5-996a-bc5a38c77d27 | note | Verifying Document - Redlines
cbaf7b6b-47dc-5975-8c59-9844576b11fb | note | Frequency - Post construction
87fd04d6-0518-5ce5-a613-0e99d687e8fb | note | Activity - H
681da9fd-8186-5c1e-9a8c-1bbf9e7a4f49 | note | By - PE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
973813aa-1353-47f1-a473-e0d689b2c04b | checklist | ITP - 135 - Signage Rev B | itp | ITP - 135 - Signage
e502dcb4-9ed5-46e8-91f0-0dfb6d5c9b5e | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
efb997ca-5ac3-4799-a350-5b11fffef586 | checkpoint | 3.01.01 - Construction Pack
7f3c277e-1e6b-5349-ba7c-d7037a9fa9bf | note | Acceptance / Conformance Criteria - ITP to be submitted to the Engineer.
54af829e-b9b9-5cab-b329-a3a4ebc573e5 | note | Standard / Specification - Downer
d5b85287-e569-5f0d-8fbd-1bd6830fe758 | note | Verifying Document - Construction Pack
66c61582-49cc-5e75-bc93-c0bd15563363 | note | Frequency - Prior to Works
42560ae3-1ee1-5cd3-82a6-6b7d4755c6a5 | note | Verification Activity: Activity - H
e51ece46-bfed-5e2f-a12c-ad9aa6ca16fa | note | Verification Activity: By - SE
59cfed46-ab28-473f-91dc-c83d40463b0c | checkpoint | 3.01.02 - Survey Setout
712fb12f-d003-5551-bd34-f976090181ad | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
ce1894c4-59bd-5afc-b1af-206a8e3513ce | note | Standard / Specification - Downer
49f99e4b-56cd-51aa-97a2-733125c383fe | note | Verifying Document - Survey Records
2b1264d8-1a17-5f1f-a5ea-cf41c3f96452 | note | Frequency - Prior to Works
b29937d4-3523-5243-9759-bebdfe5b6577 | note | Verification Activity: Activity - H
1bb5bcb0-263e-5d1f-a6c8-58062ea7fb7e | note | Verification Activity: By - SV
8cb668ba-dd0f-4532-acab-e8718618b2ec | checkpoint | 3.01.03 - Service Location
01d9d520-4c56-5a5b-a4ac-3e542bda1d4d | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
437fcae0-b222-55f8-8fcf-551e57598b1a | note | Standard / Specification - Downer
22415648-66ff-5f09-9087-755d8d3dbd29 | note | Verifying Document - Excavation Permit
f987f1f9-9c08-5ca0-a73a-eb2cb81d9805 | note | Frequency - Prior to Excavation
ea7913b4-e4ea-5bb0-b316-2f39379b0d93 | note | Verification Activity: Activity - H
4133362f-2192-5ccf-ac29-9dd9e4c8985a | note | Verification Activity: By - SE
f76873a6-12ce-4288-a49b-2df804faaab6 | checkpoint | 3.01.04 - Internal Permits
fd8d811b-a3f2-5aa4-aedd-0db3e5df9a2a | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
9aed88e7-f8c9-571d-9b54-a9809128eb99 | note | Standard / Specification - Downer
d7fd18f2-c2ed-5153-a264-2ba6bd797c1e | note | Verifying Document - Internal Permits
b78fbf47-6379-5440-9ca0-6efa06ca44d3 | note | Frequency - Prior to Excavation
dd566c1e-a45b-5e22-9591-5b743fcc52d9 | note | Verification Activity: Activity - H
ddeaa9b9-7c4d-56a9-ac98-e808f813767e | note | Verification Activity: By - SE
ea1253c3-0871-4aa4-ad5b-30e6caf5d33c | checkpoint | 3.01.05 - External Permits
3345fede-d3cc-5a5a-9266-c418b69f307f | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
e7a68a09-4fdb-5fe8-b337-fe97963b82fa | note | Standard / Specification - Downer
a70cca35-b1d0-5bf0-90b2-1a442f9bde3f | note | Verifying Document - External Permits
8b50ef33-1449-570b-8fe3-673de30efa6e | note | Frequency - Prior to Excavation
b57846fe-2307-5bde-a4e2-79d3925bbd08 | note | Verification Activity: Activity - H
57c25990-53f0-5f8f-9748-69a65327b15f | note | Verification Activity: By - PE
2fc6ae45-d2ef-4dbf-a57b-da7a09613bce | checkpoint | 3.01.06 - Approved Construction Drawings
a42c1494-a28f-5f9e-82bd-79687e39835a | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
9af8de8c-db86-5af6-861c-6b6ed837f80c | note | Standard / Specification - Downer
24a483c9-16b1-5cd8-bbee-6f5f9c429abc | note | Verifying Document - IFC Drawings
9dcea73c-777d-57e3-919f-77ec6fd947fb | note | Frequency - Prior to works start
ccf0ef69-5102-5d7a-9b3a-bd3e11950e09 | note | Verification Activity: Activity - H
64538578-8fe0-5183-9ed5-bc93e74206a6 | note | Verification Activity: By - PE
528bcb1a-42b4-4c7f-a899-5bc5377d9f8b | checkpoint | 3.01.07 - Subcontractors
1d7e680c-e1ff-502e-8eb5-b8ec578b75b8 | note | Acceptance / Conformance Criteria - Ensure that subcontract and supplier agreements have been completed.
4c73fc20-8e94-5002-acfa-1b16eef37a8b | note | ○ All subcontractors have been inducted.
480dfc85-9074-59e7-8af3-dd272a772259 | note | Standard / Specification - Downer
b73340fb-40b5-5d8e-a680-f4a0d868a5f7 | note | Verifying Document - IFC Drawings
44a2b473-7651-5c47-baaa-48fb4101e84c | note | Frequency - Prior to works start
cff39891-ddb2-54ad-9a21-5bddecbe8de4 | note | Verification Activity: Activity - H
92bf5d1f-d4e9-58d4-bfdb-41d10916d582 | note | Verification Activity: By - PE
98e43908-a6fd-460d-a1e8-cae69ac42ba7 | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
2f984469-85af-437f-b44f-b731b0fcbb7b | checkpoint | 4.01.01 - Concrete
9552c32f-134a-56a2-8224-b6afb1e2dd72 | note | Acceptance / Conformance Criteria - 20MPa grout mix to be used for signage footings.
d0018b53-8933-502a-b392-5a1d0d2b7804 | note | Standard / Specification - Designer
bff11c72-e10e-570a-b8eb-c189bf1a3cd4 | note | Verifying Document - Dockets
24a9b98b-124d-5d63-b9cf-576ada0880a7 | note | Frequency - At delivery
0d6d3b0d-da84-5d61-a67f-d2a7e474b380 | note | Verification Activity: Activity - H
34e63289-71e8-5395-a73a-3e9d1578dc77 | note | Verification Activity: By - SE
0b05d125-015e-46ba-b61e-9cd2b81b79f5 | checkpoint | 4.01.02 - Steelworks
597b6027-d20a-5f10-a896-05f6de7cdd3c | note | Acceptance / Conformance Criteria - Any steelwork shall be in accordance with NZS 3404: 1997. Structural steel plate shall comply with AS 3678 – 250. Steel posts shall be grade ASTM 106, Grade B or AP15L, Grade B. Steel RHS posts shall comply with AS 1163: 1981 Grade 350. All steelwork shall be hot dip galvanised after manufacturer in accordance with AS 1650 unless otherwise stated.
cb096953-97ca-5ba6-a4ae-da2f8c37c732 | note | Standard / Specification - NZS 3404: 1997
596c882e-572d-518f-b624-e5defa32f1f7 | note | Verifying Document - Dockets
cfb31beb-3452-51fd-b759-2fa32ab5fdb7 | note | Frequency - Prior to Delivery
11f66ce5-c5da-5449-b486-a23de617798c | note | Verification Activity: Activity - H
f0e3fec5-3d1b-598f-b495-818bf4eb9413 | note | Verification Activity: By - SE
e9227117-b3fe-46d7-aced-a19bead5c4a7 | section | SECTION 5 – CONSTRUCTION ACTIVITY
826f3d46-1f09-4fc7-80bd-14825f2de55e | checkpoint | 5.01.01 - Signage Location
dd2c2b72-0335-5683-a5a7-baba68c94316 | note | Acceptance / Conformance Criteria - Prefered method of installation will be sockets
8fc026cd-3447-5328-abc5-a44054a0f072 | note | ○ Signage in Concrete Islands
a0ad7b58-0826-5400-99ca-f8c92e72edf9 | note | — These footings will be installed after kerbs have been poured and before the islands are poured.
f27c4f47-a055-5a48-b835-f5e8b4b93872 | note | — Socket installed into raised islands will be dug out and installed level with the kerbs.
27c99467-e397-5148-9cea-aec5595e343b | note | ○ Signage in Berms
645cd933-5053-58d4-9935-c8a24acf68a4 | note | — Excavate footings to minimum size of 300x300x600mm.
f21d4dd1-5338-5a00-90e8-8b85199d1c64 | note | — Install sockets and pour concrete to finish level.
b6498192-2929-5811-b219-bbaf39ce9083 | note | Standard / Specification - Designer
2e4dc086-248a-511d-a5c7-299b9ba9561f | note | Verifying Document - Photos
1f87211e-25c0-5f50-881b-2d862416871a | note | Frequency - Each Sign
e2f1c2b6-df9f-5066-a2b6-cdfa8517f9bf | note | Verification Activity: Activity - HP
552babfd-2b9a-59bd-a9e9-369c489967a9 | note | Verification Activity: By - SE
b9b9fd2b-859b-46e8-b4dd-81e813506cfd | signoff | AUTHORITY HOLDPOINT
40af3d67-a1d5-437d-9319-5eaf5618aa11 | checkpoint | 5.01.02 - Footings (Sockets)
f519dfae-8709-5921-bd66-d9ccfd3ae25a | note | Acceptance / Conformance Criteria - Prefered method of installation will be sockets
41cd3181-7f4e-5317-beba-c7dc94f3c253 | note | ○ Signage in Concrete Islands
baa252ad-8e79-51e5-8a69-6331aa9cdbc9 | note | — These footings will be installed after kerbs have been poured and before the islands are poured.
9957578f-4821-58f4-91f7-769f15b42658 | note | — Socket installed into raised islands will be dug out and installed level with the kerbs.
754ec5fc-0ee6-5546-bba0-d546e353d108 | note | ○ Signage in Berms
7d865071-e7cc-5ae1-8c47-aeea26602329 | note | — Excavate footings to minimum size of 300x300x600mm.
7587a88d-1c6d-50bb-a86f-589c9371770d | note | — Install sockets and pour concrete to finish level.
8619ff21-5090-5f7e-a38c-8e2f7f0d05a8 | note | Standard / Specification - Designer
be05ea09-cae3-582b-89b7-1a061f00d47c | note | Verifying Document - Photos
65a8f7cf-5fdc-536d-8030-e6ecf090be9b | note | Frequency - Each Sign
d2b8051f-372b-5eb2-a221-cd2591a54f5d | note | Verification Activity: Activity - H
8ef457e6-108b-57e9-901d-feecdb6a2c73 | note | Verification Activity: By - SE
11efe1e6-6c9c-404d-bf11-64e379e48f24 | checkpoint | 5.01.03 - Sign Installation
24906669-6c3d-5c85-82cb-1451121930c6 | note | Acceptance / Conformance Criteria - Check signs and pole sizing against drawings.
00651874-c404-56da-99c6-0053cdb01e51 | note | ○ Ensure sign is plumb, orientated correctly, correct height to underside of sign, correct offset from kerb, ID sticker is attached to back of the sign, correct bracket and channels used, all brackets secured tightly.
9618ef32-5024-5d42-b30a-e5a367cc32ce | note | Standard / Specification - Designer
41f1b903-2ad8-5ab4-90b6-13977a5248cc | note | Verifying Document - Sign Installation Record
cb759cdd-7ea3-5b4c-a0d4-c1172e4f84ce | note | Frequency - Each Sign
e85405a5-ddc5-58c1-b739-2167552d45de | note | Verification Activity: Activity - H
3a892dcb-6ef4-5ec5-a6b1-29f799241838 | note | Verification Activity: By - SE
f58d5e0e-605a-40ba-9481-46f17ab46c3a | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
e97b6b00-3a47-4e70-9672-bfd9c911d014 | checkpoint | 6.01.01 - Red-line Markup
b5edc336-6bd4-56d8-b338-028479e36815 | note | Acceptance / Conformance Criteria - Provide red-line markups for items that have been moved, modified, etc.
5a40fd44-4ae4-53ee-a5aa-fa8add49b39a | note | Standard / Specification - Downer
81587503-5346-5c92-b3a0-a47d58de9dec | note | Verifying Document - Red-line Markup
20d0cff0-5a45-546b-baf7-469d8e6b3571 | note | Frequency - Upon Completion
157f346e-fb7c-5373-88f9-760d1b0a4c63 | note | Verification Activity: Activity - H
681adbe3-4996-5d83-95c3-034b9b8fafdc | note | Verification Activity: By - SE
bced1797-4abf-4681-9959-7050db1f57b3 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
a5e8b54f-cb37-5038-9bcd-d9e8e0f08543 | textbox | Contractor's Rep Name:
c6999f2c-ba6e-510d-bf2e-216f001c9a59 | textbox | Engineer's Rep. Name:
39a7ac74-ec8b-5c1b-8b97-51949fcfe72c | date | Date:
246908ec-6358-4121-9cf5-f92b15220d46 | signoff | Add Signature
019a86ad-5f3d-445e-bb8a-42b203ffa6a0 | checklist | ITP - 138 - Texas Rail Installation ITP Rev D | itp | ITP - 138 - Texas Rail Installation ITP
6a7daf3f-8fac-4243-bafc-ac58d9ef2379 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
4d628397-08e7-4cba-89db-1df26867b4c7 | checkpoint | 3.01.01 - Construction Pack
b7fd5803-0e7b-5ea3-809e-6068e37a8133 | note | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
1628a422-5df2-5b1f-afc6-50c19328862f | note | Standard / Specification - Downer
f3323aaa-5ed4-5122-afbc-614939164ba4 | note | Verifying Document - Approved ITP on CONQA
8fa94cdc-ec77-5348-864d-0d1de93365be | note | Frequency - Submit 10 days prior to commencement of works
48423d50-80f2-5ed2-bcb7-823329418d96 | note | Verification Activity: Activity - HP
e3d351c8-0a79-5e1b-9076-e23a1c4f4e7c | note | Verification Activity: By - ENG
ba72423e-e7a7-4289-a542-36d96119ccfa | signoff | AUTHORITY HOLDPOINT
5eebef77-ca61-4722-9903-24573f59aacc | checkpoint | 3.01.02 - Survey Setout
fa20dc35-d8fa-5cf1-b6c1-99de8e75938c | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
3d2dada1-862f-5bca-9118-1713fd89d89a | note | Standard / Specification - Downer
75cfc1c9-ccc9-5856-a8f2-fd85748e9332 | note | Verifying Document - Survey Records
42086c0d-fb3c-5951-915b-a54f63be86a7 | note | Frequency - Prior to Works
43cf67f1-77db-56ff-a579-b9ccd95f4bfd | note | Verification Activity: Activity - H
005a8759-741b-5b13-b6da-64ec94621fc3 | note | Verification Activity: By - SV
1b1cceab-cb0a-48a7-9a48-8b64ec68affa | checkpoint | 3.01.03 - Service Location
049bf63f-3bb7-5347-b051-0bfe95e742f5 | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
55201160-665f-5f71-9d48-073d302f6fc1 | note | Standard / Specification - Downer
11a8dcb1-e3bf-52fa-a184-a31e41eef757 | note | Verifying Document - Excavation Permit
1eff3781-6b85-5972-801b-1b0440c87125 | note | Frequency - Prior to Excavation
3a5961d3-fe18-56a0-9933-4a8653fce95b | note | Verification Activity: Activity - H
1788ac43-67c4-5c71-842b-7c7c1e5ae7b6 | note | Verification Activity: By - SE
5be020a4-8841-4e13-a459-80939ae23c3b | checkpoint | 3.01.04 - Internal Permits
e58b65e9-9ead-5dd5-8e32-a262753d4693 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
d0f0d1ea-3034-5b25-b1bc-f4c524a5b8cb | note | Standard / Specification - Downer
711b1bca-71fa-5ce1-9d2c-c3e5a4ea1a00 | note | Verifying Document - Internal Permits
a2010aec-7833-5a2a-b659-818e9ac1148e | note | Frequency - Prior to Excavation
d2b84710-b940-536a-9a41-e2234c8aaad9 | note | Verification Activity: Activity - H
b487acb0-ac50-5d74-9c56-f12f7c57b209 | note | Verification Activity: By - SE
7013363a-7156-468e-a36c-452bc8515875 | checkpoint | 3.01.05 - External Permits
5a6996d8-1f0a-57bd-bf1b-bdfe1b8f568a | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
8fdb47fc-6ff1-50ac-8871-84ad544e6ebe | note | Standard / Specification - Downer
fbf1a85f-80d1-5482-8131-7a5827acd2aa | note | Verifying Document - External Permits
04c9ed87-fc89-500d-81d3-abcfed209eac | note | Frequency - Prior to Excavation
16d132df-6fed-552c-9c5d-7828bd2029ee | note | Verification Activity: Activity - H
db0c6efd-2c9d-5f47-8db1-0492d8f70f33 | note | Verification Activity: By - PE
bc9b02ae-dedc-411b-94fb-efc839f26b36 | checkpoint | 3.01.06 - Approved Construction Drawings
43f60326-0834-514a-bf7f-64fcc719dc49 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
07ddd56b-1281-5c16-8317-3f0894dafdb1 | note | Standard / Specification - Downer
819a997f-1d04-5694-bf48-8e6453197e2e | note | Verifying Document - IFC Drawings
91444438-1a98-52e4-8b1c-2c0325d4599b | note | Frequency - Prior to works start
22c0a234-7364-5432-a935-92e6d0f5cd00 | note | Verification Activity: Activity - H
566ce248-28b1-563f-9bf1-aa1359b0b052 | note | Verification Activity: By - PE
f8ad7438-3eb4-4097-ac58-65a27e11f1b3 | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
ebf11e53-c8d1-4fcf-987f-5c47b87e845c | checkpoint | 4.01.01 - Precast Traffic Barrier
365c685a-2c91-5b59-b80b-42661f4083ff | note | Acceptance / Conformance Criteria - All precast barrier QA to be in separate ITP for precast element. – This item to be acceptance of precast QA ITP
e00b5e40-d42b-5fdf-bc04-edfcfe9323ad | note | Standard / Specification - PS-1
f9d9ee39-e7f7-56d3-a0d9-5ec4e6c35fa2 | note | Verifying Document - BBO
83ce7085-f4a2-5582-b695-ef2b3158b17f | note | Frequency - Before Installation
5fbcb2c5-b804-5748-a3c4-1f2da80d13ed | note | Verification Activity: Activity - H
86120270-d0a5-503d-b8f8-1700b15cf86d | note | Verification Activity: By - PE
5a644377-c6d8-4309-b5a8-2e762ef6ad62 | checkpoint | 4.01.02 - Ellipse Handrail
8aa25697-261d-593f-b1b2-d5849fa0cedb | note | Acceptance / Conformance Criteria - Eclipse handrail QA to demonstrate compliance with Structural steel notes on IFC DWG 4001 (refer to fabrication ITP)
199cdf32-b451-5057-9401-ab0088fbb21e | note | Standard / Specification - Structural steel notes on IFC DWG 4001
996386c5-4473-548c-8d33-221e6ba1f40a | note | Verifying Document - Shop Drawing/Material Certificate/PDS
99fad1a2-25b5-576f-9130-717bffcf49b6 | note | Frequency - Before Installation
6a8ef3a4-894b-5094-9ff4-0c10fef79432 | note | Verification Activity: Activity - H
31ac3781-c744-5ed4-8a36-4f197d5c2f62 | note | Verification Activity: By - PE
a6dcea07-e0e0-43c0-8b73-bee465f958ec | checkpoint | 4.01.03 - Non-Conductive Barrier Coating
43f1127d-cfb0-5a56-b0da-52001cc0e548 | note | Acceptance / Conformance Criteria - Non-Conductive Barrier Coating to be Carboguard 636 XT (approved in RFI-0263), min. 150 microns to be applied to underside and side of baseplate (refer to fabrication ITP)
0f38681c-21c2-5497-b5f1-aa911b4a6be7 | note | Standard / Specification - AS/NZS 2312/HERA Report
05b9c702-c6de-59a8-ac3a-5a7e0b9dd29f | note | Verifying Document - Shop Drawing/Coating Certificate/delivery dockets
f932f333-0a08-5ec9-a874-75d2e9cf092a | note | Frequency - Before Installation
1833ce81-b797-5bdb-a96b-89cac8a7673f | note | Verification Activity: Activity - H
ecb8ec2a-1916-56eb-b6d6-f25406ee8465 | note | Verification Activity: By - PE
90482794-6db9-4ffd-832b-ab4744b9a832 | checkpoint | 4.01.04 - Fall Protection Wire Rope
2224d689-949b-5f76-87b5-fefe87d83977 | note | Acceptance / Conformance Criteria - Wire rope shall be 6mm stainless steel wire rope or otherwise approved; Material certs to demonstrate compliance of SS wire rope to be SS316 as per NZTA M23 Appendix B Rev.2
ecae7a47-d615-5fa1-a64b-b86cce152250 | note | Standard / Specification - NZTA M23 Appendix B Rev.2 & NTT003
486f2200-81df-5c86-9855-691c53eebe21 | note | Verifying Document - Material Certification
aaf94b4a-de5a-5346-b7a2-da8e86b6f09f | note | Frequency - Before Installation
d7ecfb43-dda5-56aa-9f0a-9a1e085817b8 | note | Verification Activity: Activity - H
f142ba6b-2075-5b9c-8482-bc98efdc34d6 | note | Verification Activity: By - PE
e8177b37-1f05-4ba9-82fc-4683c094ed5f | checkpoint | 4.01.05 - M16 & M24 bolts, washers and nuts
6f050f02-4022-5c40-9d72-99fa4db792b6 | note | Acceptance / Conformance Criteria - Property Class 8.8 Hold Down Bolts, HDG
28d93ecb-fa4a-5d30-b174-61a08c043270 | note | Standard / Specification - AS/NZS 3845.1: 2015, AS 3569, AS2759
25cd12c4-dde4-5b93-8aaa-6e20c5c4227b | note | Verifying Document - Material Certification
0b700310-6e6e-58a0-a324-2d06ae415f91 | note | Frequency - Before Installation
f1306fb1-0eb3-5166-a66d-f97114528c3e | note | Verification Activity: Activity - H
b2fedf10-dc2c-5217-af52-afa180fb6aec | note | Verification Activity: By - PE
e378ddeb-bb0b-406e-8d68-1611a0bf2ddd | checkpoint | 4.01.06 - Sleeve Member and Pin on bottom of Sleeve, Base Plate and Rail Vertical Posts, Rail Termination Cap
8fdf0995-6bdc-5721-a398-334596930d69 | note | Acceptance / Conformance Criteria - Material certs to demonstrate compliance with Structural steel notes on IFC DWG 4001 (refer to fabrication ITP)
a3193b62-125a-5311-9674-f7d6565cb011 | note | Standard / Specification - Structural steel notes on IFC DWG 4001
38b1c18e-9b19-5b8a-8bc1-8bf649305d2a | note | Verifying Document - Material Certification
6495f771-2a74-55a3-8c36-ec3925b785dc | note | Frequency - Before Installation
c4625768-2513-59b2-8e49-e968151a53dc | note | Verification Activity: Activity - H
1efa002d-a744-5d16-8dee-5da68d275a9a | note | Verification Activity: By - PE
19c6a19f-b1c9-4126-8691-d1e9fe8d28a2 | checkpoint | 4.01.07 - Wire Rope Termination
a785e399-257d-5c70-8e6f-ce92376efbdb | note | Acceptance / Conformance Criteria - Material cert on U bolt or similar approved for safety wire rope termination detail
b06286fe-f393-5784-b092-02725eb2d265 | note | Standard / Specification - Structural steel notes on IFC DWG 4001
8e5980d9-aa5b-5025-9794-61e51356549c | note | Verifying Document - Material Certification
c681897f-0871-56eb-a3c4-79b81d823278 | note | Frequency - Before Installation
0aa0252d-8ac0-50a9-8dad-c1850a98f0c0 | note | Verification Activity: Activity - H
5fcaf0fc-5170-5197-ba69-c13c32802b19 | note | Verification Activity: By - PE
085359e1-984f-4194-8557-596e7ff2644d | section | SECTION 5 – CONSTRUCTION ACTIVITY
f70620af-c9d9-448c-9be9-62f35766d43d | checkpoint | 5.01.01 - Temporary Works (Stitch Pour Formwork)
3e6d5d87-83aa-55fc-88f9-80e44c4e1c2c | note | Acceptance / Conformance Criteria - Temporary works to be installed as per design drawings. Permit to load to be issued by temporary works inspector prior to loading element
f63f4590-c57a-5aeb-ace8-c7e228484afd | note | Standard / Specification - Downer
dc0402dc-df5f-57f6-9268-27de831db986 | note | Verifying Document - Permit to load/Inspection
35e99095-4ed3-5714-a091-4a0a019db7c3 | note | Frequency - As defined in the temporary works design
aa1c5e75-9b3c-51cb-9f4c-bbc3f96fb3c3 | note | Verification Activity: Activity - HP
b041cad3-ac0a-53d1-b738-0f5015aca360 | note | Verification Activity: By - ENG
f61c6734-f8e2-4acd-805e-d33275dd7177 | signoff | AUTHORITY HOLDPOINT
35905bac-ef3a-479f-a2de-a874ba6625ee | checkpoint | 5.01.02 - Cast-In M24 Bolt
e94fc099-fafa-542b-9350-6c1f131ff6c5 | note | Acceptance / Conformance Criteria - Re-check all bolt assemblies are Class 8.8 high strength unless otherwise specified on the drawings
9336c217-5c40-5be5-be18-e0f1a4e76d0e | note | Standard / Specification - NZS 3404.1
832a6a24-f9f8-57bc-ba60-cfc1ef0f7331 | note | Verifying Document - IFC/Material Certification
0441c406-cb2a-544a-b9c9-7a128996c9b3 | note | Frequency - Before Installation
e280c40f-7dc3-5f2f-832e-2e8c9a11abbd | note | Verification Activity: Activity - H
74e22992-9a12-5aa2-a822-4f5c6c700641 | note | Verification Activity: By - PE
3c723ccd-32b7-4922-b315-ecf063a75994 | checkpoint | 5.01.03 - Check cast-in bolt set-out
8961357b-f115-5b87-8d30-794f59514f7a | note | Acceptance / Conformance Criteria - As-built bolt locations, and overall alignment of precast barriers, for rail baseplate hole positioning. Set-out shims/packers
20f42235-4ffc-5a84-82f0-b4d801cfa874 | note | Standard / Specification - Downer
f35e0c9c-278e-5d68-97cc-f4dd691fe619 | note | Verifying Document - Survey Data
02df38dd-a7ce-55ed-b4de-4a7aa7f5c5b4 | note | Frequency - Before Installation
e39197da-b052-5080-941c-2947c5a17492 | note | Verification Activity: Activity - HP
7e1b04d9-3868-505a-b80c-552138264f3c | note | Verification Activity: By - ENG
4cf8c4c0-7dc5-4f94-adcf-e2a00f31f51f | signoff | AUTHORITY HOLDPOINT
0c5e26f5-2928-48f5-b84c-7d390d257459 | checkpoint | 5.01.04 - Baseplate and Ellipse Handrail tolerance
0509d9ab-ab89-5741-a33a-7096e441498d | note | Acceptance / Conformance Criteria - Install vertical post with handrail and partly tension bolts onto the baseplate. Ensure tensioning tolerances for steelwork/bolts are checked.
d1dd6fa0-48b3-5fe7-a13a-171cf840ec06 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
d7262e1b-1a2b-599d-9c4f-663b9a42917f | note | TABLE G1
f575191f-1ab0-5150-898b-b3276b69a552 | note | MINIMUM BOLT TENSION
06eff592-0a73-5bdb-8355-fc988e7491c2 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
59bf81c1-01ed-5881-bdb5-a63583efb830 | note | Nominal diameter of bolt ¦¦ Minimum bolt tension kN
995ddcb4-b65d-5bc1-91df-15e1bfbbf95a | note | M16 ¦¦ 95
59d03df8-77f8-5d80-8f6e-75a3efb8e14a | note | M20 ¦¦ 145
2efc898c-7dda-5f49-b844-c80658121927 | note | M24 ¦¦ 210
593bb4df-b9f9-574c-8d1f-02fe1aa82690 | note | M30 ¦¦ 335
2fca4b8a-f7e3-52f3-b6ad-8a46f67e9e2e | note | M30 ¦¦ 335
e5dc9232-7c87-5fcf-94db-1450af9ebd88 | note | M36 ¦¦ 490
3e44c47d-719b-5814-8754-8dd9162079ab | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
b7db09ee-15ef-53d2-b0b2-517f7261dcbe | note | Standard / Specification - Downer/AS/NZS 5131: 2016
b6736399-1ed2-5e48-8a50-5c5245d4020b | note | Verifying Document - Hold Point Release
2cec41ef-85b1-5cf1-88bc-6d79080b65e4 | note | Frequency - Before Installation
4f3ea829-815d-5a3e-a630-8f3248d1ee57 | note | Verification Activity: Activity - H
92477e46-2d8a-5672-9eab-e47849d03f7d | note | Verification Activity: By - PE
e02ce643-95f0-46e9-97d3-30c498fe2ceb | checkpoint | 5.01.05 - Tension bolts
46d5beab-d2e7-58d8-bc9b-11a84d578f98 | note | Acceptance / Conformance Criteria - Check each bolt has a washer, nut and locknut and tension all bolts using part turn methodology
f192a499-49d8-5d24-b51e-5a43ffae5669 | note | Standard / Specification - AS/NZS 5131: 2016 A1 Section 8.5
02e287e4-2902-5b7b-bf3d-0356154cfb61 | note | Verifying Document - Photo/Site-Approval
026fc05e-e8cf-5d97-bbde-7ca7802a2edb | note | Frequency - Each Baseplate
72253021-43fe-54e6-a4f3-6df9fff747fc | note | Verification Activity: Activity - I
5968d53a-1c37-59bc-be4e-36c5ba454e69 | note | Verification Activity: By - SE
b1a5d654-3934-4448-a724-afb2839e1b55 | checkpoint | 5.01.06 - Grouting under baseplate
d066a74f-9aff-549c-9aa5-0086dfbbd550 | note | Acceptance / Conformance Criteria - While Hi-ab is holding the handrail components, adjust/tighten, and apply Sika212 or similar (approved by Engineer) to the underside of the baseplate (nom. 15mm)
1742f1a2-0542-5e53-a7fd-925e21daa42e | note | Standard / Specification - AS/NZS 5131: 2017
ecd015c6-c435-5883-b108-2a2b05a2e899 | note | Verifying Document - PDS
fa349f36-4c83-561c-803b-3692293a3612 | note | Frequency - Each Baseplate
18578705-f927-5e94-a90a-3f9a70889395 | note | Verification Activity: Activity - I
7bdb76b7-d3bd-5231-9025-4ed53592f847 | note | Verification Activity: By - SE
568c0fa1-01e9-48bc-a39f-57566fb03051 | checkpoint | 5.01.07 - Fall Protection Wire Rope
9c2d5f61-5725-57db-a752-335c03360a2c | note | Acceptance / Conformance Criteria - Prior to installation make sure wire ropes are free from: wear or scraping, kinking, crushing, bird caging damages. Wire Rope to be installed within the following tolerance.
fd2c95c9-8d7c-5f2c-9869-4265f75182f2 | note | AS/NZS 3845.1:2015
bb24efbe-8627-5110-b75f-e32b4df8a1ff | note | Unless specified otherwise in the system documentation of by the Road Authority, the following shall apply:
3ff88936-a1ca-572e-93f1-91f7d10a9c01 | note | (a) Fittings such as swages, rigging screws and the like, shall be placed so that the end of the fitting is a minimum distance of 50 mm away from a post. In order to comply with Item (a), the requirements to avoid clashes with fittings, it is permissible to move the location of a post.
59e0f3d5-bd0a-50b9-a8ed-8e22ee07c6be | note | (b) Variation from the true plan position of posts ±30 mm.
8a4f4e6c-5c98-5af2-8b98-920c31b3904c | note | (c) Variation in rope height ±20 mm.
b20f2c23-7c3e-5097-869d-57c40a96daba | note | (d) Variation from true plan position of barrier ±20 mm.
c00e2a3d-311b-595b-b163-482e0fd634ce | note | (e) Fottings (length, width and depth) -10, +50 mm.
a8acc2f5-2c54-5326-9d17-80b56f154908 | note | (f) Anchor blocks (length, width and depth) -20, +100 mm.
c67148a8-3303-5089-8778-6aec2a3949d6 | note | (g) Height of footing relative to finished surface levels +20, -0mm.
01287aa8-2b3e-5186-9da0-32e1d639f45f | note | (h) The system shall be tensioned to a tolerance of ±1.0 kN.
8d8d0acf-96d8-5747-a274-7f5b590a5a67 | note | (i) All anchors, footings and posts shall be capable of resisting the load nominated by the System Supplier (see Clause 2.5.4).
0990a468-59cb-5d73-84a4-9a6ca9401866 | note | (j) Upon completion of the installation, the wire rope shall be free of creases or fracture strands and the galvanizing undamaged.
75b6007c-a8b2-54a3-aad8-2cd3497d2e15 | note | Standard / Specification - AS/NZS 3845.1: 2015
98b06609-bf2f-5bf9-bcd4-3d20422f30c5 | note | Verifying Document - Inspection/Site-Approval
4e7e70d5-8b8a-534d-bdf7-e4ebfc51d774 | note | Frequency - Before Installation
55adf95d-56bf-54d3-8d70-4c758a933922 | note | Verification Activity: Activity - H
9d7136af-d253-5d35-bcbf-094d01dd7993 | note | Verification Activity: By - PE
d06a674f-49bd-4e03-9941-92c9f98a103f | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
961cf1ae-2e64-43ee-b158-1b1f928ef13b | checkpoint | 6.01.01 - Construction Record Compilation
4c6d5191-e4e9-529d-8b4f-b72de8ce630f | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
d9eb6524-4dfd-5068-9741-c8dfd1b334e2 | note | Standard / Specification - Downer
e9c8d66f-09cd-5271-aa10-e4dba552bc03 | note | Verifying Document - Records
8ac0d3c7-1bc5-5217-a4dd-1cd9f0f953c4 | note | Frequency - Post construction
2001b360-337c-5077-9968-c20439a11069 | note | Verification Activity: Activity - H
b1f1ec95-c7ae-519f-8d1a-2ada9e6300b0 | note | Verification Activity: By - SE
c753313d-b8da-4f18-bb6d-66e2bf264156 | checkpoint | 6.01.02 - Survey Records
f4993384-8dde-510c-8c0f-ce74248a53d7 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
cead58dc-c40c-5bc4-aeec-7430a7416cc0 | note | Standard / Specification - Downer
83a23a7d-52fe-5adb-a767-7ff8e4b6727c | note | Verifying Document - Records
0e63e1b6-1f1a-5cc5-bbf1-e24fdfc5bb1d | note | Frequency - Post construction
5bd87e3d-6c9c-5724-9586-8ec8f1483df6 | note | Verification Activity: Activity - H
1fd8651f-7503-581b-b2eb-803367e04e96 | note | Verification Activity: By - SV
8359db66-95ff-468e-974d-bd3bb835b04d | checkpoint | 6.01.03 - Redline Drawings
f8f4308d-c964-5d2b-91cb-8b8827cf84eb | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red line to show any changes to footpath location or basecourse depth.
65cd793c-272c-58f8-9e90-e7daf645aeed | note | Standard / Specification - Downer
1d6e05b9-b6d9-5558-9427-b9ea09c9d057 | note | Verifying Document - Redlines
610b53b5-60f4-5b03-b11c-e0a191acf456 | note | Frequency - Post construction
231241d1-7b9d-590d-bb35-08f6c2f07ef7 | note | Verification Activity: Activity - H
5d87c249-2f21-5eb0-bfb2-6ba352170ac3 | note | Verification Activity: By - PE
10955eb0-eb36-4645-97e9-0c454fc4fa2c | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
8d6bfbb2-1dd5-5444-807c-44945f5e98d5 | textbox | Contractor's Rep Name:
db4765a5-45aa-5ace-b68d-c885bd4a09a8 | textbox | Engineer's Rep. Name:
563c9322-387e-5bc9-b615-598f253536dc | date | Date:
f7d48ef6-0fb2-4b46-8eab-8f980e8ccf00 | signoff | Add Signature
c9ab3200-a496-4cc5-a35d-358a2e58f143 | checklist | ITP - 141 - Safety from Falling Barriers Rev B | itp | ITP - 141 - Safety from Falling Barriers
7323c365-e66b-4864-9055-295900cd014a | section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
a4b0437a-8a4e-42f5-899f-b60c70068fe3 | checkpoint | 1.01.01 - Survey Setout
e0644f49-7a36-591d-853b-adf88bd4728b | note | Acceptance / Conformance Criteria - The Contractor shall verify the setting out position, level and line of the bridge, prior to commencing construction. The Contractor shall advise the Engineer of any apparent anomalies identified.
66c2acca-c9c2-5d3c-837c-ba6715e28ebd | note | Standard / Specification - Downer PS - 11.2
37454b24-0c69-5f78-a4a7-ae9dc39840ef | note | Verifying Document - Survey Records
b4a5a3f5-687b-5381-bcaf-224e5edcb6d5 | note | Frequency - Prior to Works
621cacd2-00c1-5f5c-b710-08f3a994d99b | note | Verification Activity: Activity - H
75f46e63-5ac9-5716-9273-44b5713c6cce | note | Verification Activity: By - PE
fe49e325-c558-490b-9e78-3248bbc90417 | checkpoint | 1.01.02 - Approved Construction Drawings
4daad277-ce06-5c08-adfd-532f84a0f6ba | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
681c574b-6117-5023-9899-812bd53df520 | note | Standard / Specification - Downer
83aabcfb-c080-5925-805b-4eee290b132e | note | Verifying Document - IFC Drawings
2595c302-052d-5f52-a376-797e00e8b06f | note | Frequency - Prior to works start
1fac6ac4-8a8a-5712-9974-c02d585affdc | note | Verification Activity: Activity - H
af064178-3359-556d-a02e-7248c27dea21 | note | Verification Activity: By - PE
d39c8579-7941-4879-b86b-468829d526f4 | checkpoint | 1.01.03 - Approved Shop Drawings
2923fb40-910e-5dc3-9741-17e63854f42d | note | Acceptance / Conformance Criteria - Shop drawings to be approved by Engineer
a9e941c0-de10-510f-9b45-9d932bc13ecc | note | Standard / Specification - Downer
8bf774e8-022e-5a07-bab5-6b7da99fd384 | note | Verifying Document - Record of Approval, Approved Shop Drawings
a8fad99f-454b-5d0e-a98e-cc14752a5187 | note | Frequency - Prior to manufacturing
0af40399-b34c-5d35-94d1-dfa942fbf4c8 | note | Verification Activity: Activity - HP
9d3183ab-a3e6-5386-bcb9-c5f42cfed259 | note | Verification Activity: By - ENG
bb4c6333-939f-4aea-a353-3fe42cbd1892 | signoff | AUTHORITY HOLDPOINT
866a0061-2a37-481e-97c9-909fcc8b0f06 | checkpoint | 1.01.04 - Approved ITP
d167ffd0-5c55-55a9-9d32-4e1adacc0cf2 | note | Acceptance / Conformance Criteria - Include correspondence of approved ITP.
52ad47a6-5d9e-5f8c-aa03-a6b76ffcd63e | note | Standard / Specification - Downer
90bb5072-5ae2-59d1-9fbd-4a2fc08659e2 | note | Verifying Document - Record of Approval, Approved ITP
c0b2038c-8bde-5222-9522-73b359636cf8 | note | Frequency - Prior to pouring foundations
b478e980-73ef-5fcf-b370-512f2ff9639e | note | Verification Activity: Activity - H
67aa35ac-dd2e-550c-8a4e-3f5ee53aaf7d | note | Verification Activity: By - PE
8fb53833-ab01-46bb-bca7-4c9fffcc8a35 | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
5ae2a084-dda1-4b11-a0d8-47a617be0277 | checkpoint | 2.01.01 - Alsteel Defender Fence
c8bb9175-f69f-54d2-89f8-1f3b82ac7fc8 | note | Acceptance / Conformance Criteria - All panels to be part of Alsteel Defender Fence system unless instructed otherwise.
f7255e18-0276-582d-8358-09c6c849630b | note | Standard / Specification - Downer
c7faee08-2843-5af1-b608-8dcabca2d69a | note | Verifying Document - Dockets
360372bd-30f4-5ce5-ace4-a644cbcfcac5 | note | Frequency - Each Order
6d9b246e-7ce3-5ad7-a2c4-9f21f13e56e5 | note | Verification Activity: Activity - H
78da5ebe-052f-5b71-965f-a4fd3a397c53 | note | Verification Activity: By - PE
f80ee7ac-5f98-47f8-9caf-42f92c4084de | checkpoint | 2.01.02 - Hot Dip Galvanised Steel
71231f2d-422d-5408-9587-9e76a4e5ae9a | note | Acceptance / Conformance Criteria - All steelwork to be hot dip galvanised to achieve HDG600.
d91f4e98-2c7a-5926-8013-d59b021a920a | note | Standard / Specification - AS/NZS 4680
d8d65b06-0fab-547e-8a6d-3e38fd45e4ad | note | Verifying Document - Test Results
5113aed2-be6e-5e0f-a027-2e99a54e0aed | note | Frequency - Each Order
767ac7af-7aaf-5c23-a039-b1fa590a5c10 | note | Verification Activity: Activity - H
95a18a3b-7325-5d66-b699-75c1cfd392d6 | note | Verification Activity: By - PE
5ffa4a15-9e56-47e9-b31c-65bbef47f74e | checkpoint | 2.01.03 - Steel Grade
36738490-408e-5b65-aabe-c29eae24e5cd | note | Acceptance / Conformance Criteria - All steelwork to be grade 300 minimum.
d13a0c6e-1d3d-5ef6-8a2f-cf20b7388971 | note | Standard / Specification - AS/NZS 2312
d2f853be-e880-51db-9780-267e4b21eda5 | note | Verifying Document - Dockets
ec0ff503-ca2d-5bf6-bc15-56174170cb82 | note | Frequency - Each Order
dc9d97d1-6cf7-5434-9ae3-504b87ea3e9e | note | Verification Activity: Activity - H
b946008f-11ef-5c53-beb6-751986367b7c | note | Verification Activity: By - PE
fd6051cc-683f-455d-9563-c0b8e4d4980c | checkpoint | 2.01.04 - Hot Dip Galvanised Bolts
f05244b2-ba4f-5b54-8a5f-96233d914add | note | Acceptance / Conformance Criteria - M12 4.6 HDG minimum 150mm embedment.
afaaf884-e53a-55b4-b426-89f60a59f0a2 | note | Standard / Specification - Downer
bb446cac-5d18-5f05-9ef6-b034ad45c12f | note | Verifying Document - Dockets
97be38df-9809-5812-9033-1a972e2ee342 | note | Frequency - Each Order
75975de7-7cec-5d47-a0d6-a93faa79951f | note | Verification Activity: Activity - H
9fac3e67-bb57-5772-bffc-1c7514400664 | note | Verification Activity: By - PE
3d0a90fe-7f0c-4ad3-9d1e-8b959e2f5c12 | checkpoint | 2.01.05 - Repairs
e119a99d-8737-5af1-960b-83c6af43a669 | note | Acceptance / Conformance Criteria - All repairs to hot-dipped galvanised materials to be as per manufacturer's specifications or designer's instruction.
ba688de2-efbe-5d4f-b4bd-951695a2caa3 | note | Standard / Specification - Downer
9fca2dce-41da-5f49-9887-69333476b2cb | note | Verifying Document - Site Records
eda0fe70-de5f-5a1b-ad50-87ecf157af14 | note | Frequency - All Repairs
70778c3f-d678-5fab-96c3-e23ab1b11faf | note | Verification Activity: Activity - H
b66c3e24-f1ed-5743-810c-c1f31c84c96d | note | Verification Activity: By - PE
681e0eb5-ea81-4d9b-86d8-1bf9744b1a8e | section | SECTION 3 – CONSTRUCTION ACTIVITY
dc2bd5b2-cd0b-480d-9a56-d8cd87f50c4d | checkpoint | 3.01.01 - Spacings
23855f98-9f1a-596e-bad9-7aa1ad1e3818 | note | Acceptance / Conformance Criteria - Maximum centre to centre spacing of posts to be 2445mm.
e1edb15f-252e-5dc2-84ad-092efdf59286 | note | Standard / Specification - Drawings
299ff2fa-7556-54bb-9628-4b721ebee70b | note | Verifying Document - Photos
532543d1-e91c-5098-b179-1c626329b974 | note | Frequency - Each area
605475c4-b3da-5043-8f06-ca6474d88871 | note | Verification Activity: Activity - H
2814ef0d-7386-5d1f-876a-01a13a0e9f93 | note | Verification Activity: By - PE
93c87c69-4a2b-4985-9cfe-c41afc945056 | checkpoint | 3.01.02 - Height
e4a2815c-fb89-524a-9b04-4e2b17c52c07 | note | Acceptance / Conformance Criteria - Minimum 1100mm height of posts.
64d529a9-6890-5fc2-b742-3fab4418f100 | note | Standard / Specification - Drawings
2bbe42a7-efbd-5236-bf16-39a43aae812b | note | Verifying Document - Photos
6aa69f48-d22e-5f6e-80bc-979d2d42962a | note | Frequency - Each area
c10fe682-13a2-5cf3-b341-aa01efb25933 | note | Verification Activity: Activity - H
fbc0502e-033b-5c35-a330-1fb8a4268291 | note | Verification Activity: By - PE
64db0426-89a9-4cb8-bbd6-6b83a9108221 | checkpoint | 3.01.03 - Gaps
7bedf1a1-43b7-528b-b50c-a04284578a7c | note | Acceptance / Conformance Criteria - Maximum 100mm gap between ground level and first horizontal member.
70d23411-fe17-58e9-9314-3566c999ae07 | note | ○ Maximum 100mm gap between vertical members.
55c818b4-d758-59e2-9586-1bd9326ca76c | note | Standard / Specification - Drawings
c5d400d2-b0a9-5b2b-b316-a62bbffc4813 | note | Verifying Document - Photos
ffeb3f01-4738-5254-8892-ea123d12db26 | note | Frequency - Each area
0323fa7d-836c-557d-bcd4-5aebdb188147 | note | Verification Activity: Activity - H
9cad9294-3ee9-51c0-90d6-3fb9b9f24853 | note | Verification Activity: By - PE
6a0abc38-2612-4b23-b059-09c89f67c253 | checkpoint | 3.01.04 - Footings
0e6f75f7-3dee-517a-9323-16038d5f5f16 | note | Acceptance / Conformance Criteria - Standard Alsteel Base Stub footing mounted on foundation with 4/M12 4.6 HDG Bolts @ 90x110 spacing, minimum 150mm embedment.
966854cf-15ce-524d-804c-c9562931e76f | note | Standard / Specification - Drawings
7bc801b8-c509-5c91-a7e4-29f73bd9d004 | note | Verifying Document - Photos
60294762-ad9c-5057-9751-af0ab3efb4a3 | note | Frequency - Each area
60fa2e34-9d5a-50ff-891d-bda777295348 | note | Verification Activity: Activity - H
c8ad633f-71e5-5f34-bb37-a6b7d85e1cda | note | Verification Activity: By - PE
677b20fe-be13-402a-840f-6428f3f02e9c | checkpoint | 3.01.05 - Posts
0d9190b2-a0a0-5417-a682-0d6e7ea3d5b7 | note | Acceptance / Conformance Criteria - Minimum 65x65x1.6mm SHS posts.
d3fc0e27-7647-57bc-bee7-f7367737faac | note | Standard / Specification - Drawings
92a7681a-4749-575b-a9ac-eb88fd6c8e6f | note | Verifying Document - Dockets
9cef1a98-10a7-5983-bd5b-829903758412 | note | Frequency - Each area
fef20d6e-c3d2-5cfe-a4bb-7a20b7d9bd47 | note | Verification Activity: Activity - H
ac2e7d06-4afb-5d59-b62a-53d4a07c2bdb | note | Verification Activity: By - PE
c46443fc-6af3-4b55-bd3d-ab65b7e04eae | checkpoint | 3.01.06 - Returns on Corner Posts
e7212413-c3cf-5818-b3bd-70641ca2e15f | note | Acceptance / Conformance Criteria - Returns to be minimum 520mm wide with 90x90 HDG base plate bolted to foundation with 4/M12 4.6 HDG Bolts @ 50x50 spacing, minimum 150mm embedment.
eb01976e-b841-5da6-84d9-cf50683faccb | note | Standard / Specification - Drawings
54ab300f-c62c-54eb-8e07-415775d050c8 | note | Verifying Document - Photos
acab5c41-aa80-58a0-9e66-19094d282960 | note | Frequency - Each area
41fe7ec8-e992-5ccd-8929-3620c01aa371 | note | Verification Activity: Activity - H
087a4da7-84f9-5616-abd1-fab0f3478c22 | note | Verification Activity: By - PE
266e5518-4f75-4a32-946d-24896ec832c4 | checkpoint | 3.02.01 - Spacings
e9fc817c-7e5d-59f1-b66a-463718d68b37 | note | Acceptance / Conformance Criteria - Maximum centre to centre spacing of posts to be 2445mm.
f8112a3c-7c0a-5858-8db2-f631e325ae89 | note | Standard / Specification - Drawings
6b79d1f8-6ddd-5539-bd2c-d5b5b47e4cff | note | Verifying Document - Photos
6d32768a-62a5-5c20-b217-4205c5fb88ad | note | Frequency - Each area
2a6f62bc-2fd5-58f2-9a73-151b147d62c6 | note | Verification Activity: Activity - H
53791082-4293-5c69-80c7-794fe8185820 | note | Verification Activity: By - PE
87440b07-e474-4df3-92ec-5d05abeabe5b | checkpoint | 3.02.02 - Height
3d8dd3dd-c5fa-5e6b-8dff-f1b4cb643679 | note | Acceptance / Conformance Criteria - Minimum 2020mm height of posts.
7a847010-5858-5b76-a7d6-162df9cca5a4 | note | Standard / Specification - Drawings
44a015e4-4234-5501-b9cb-5b2670367b77 | note | Verifying Document - Photos
ea20c7a3-9dc2-57d9-bc49-5cf5aba5d6d9 | note | Frequency - Each area
719e2633-2466-57ff-82a0-63160251a595 | note | Verification Activity: Activity - H
0b296594-8e3b-57e0-b354-a585c166db3f | note | Verification Activity: By - PE
14ce2b35-9a0c-4235-9f6f-23fa701510e5 | checkpoint | 3.02.03 - Gaps
035b8e16-701c-5243-9f96-3bc3e9353b8e | note | Acceptance / Conformance Criteria - Maximum 100mm gap between ground level and first horizontal member.
24f98769-9526-5552-9f8f-a7a440aae378 | note | ○ Maximum 100mm gap between vertical members.
b7041e32-ae28-549d-911b-15642780581e | note | Standard / Specification - Drawings
2e631fbf-592b-5fe5-8bd4-bfaca064ff6b | note | Verifying Document - Photos
acdf3c27-b310-55f5-bc58-dd15b55e38bb | note | Frequency - Each area
a6ec7d78-7eae-5789-b2a7-3af924ec9922 | note | Verification Activity: Activity - H
a45d992b-93b2-502c-9e91-e547c252805b | note | Verification Activity: By - PE
5e641a54-2343-4a4b-bd9a-19f1006bb9e2 | checkpoint | 3.02.04 - Footings
f041cecb-5c48-529e-9ed5-b67128caf93d | note | Acceptance / Conformance Criteria - Standard Alsteel Base Stub footing mounted on foundation with 4/M12 4.6 HDG Bolts @ 90x110 spacing, minimum 150mm embedment.
0c834fb5-e3e2-56a1-bc06-4b8348dd6e55 | note | Standard / Specification - Drawings
f85d544e-8b47-5a02-86af-30db1edd6c23 | note | Verifying Document - Photos
31222501-bb17-52ae-9406-dcf2ed57e782 | note | Frequency - Each area
407936a4-2260-5784-83c8-0ada1a02ab2f | note | Verification Activity: Activity - H
ba9d89ee-c77a-5e60-93bc-ede37e873e81 | note | Verification Activity: By - PE
797ce3b9-19bc-455f-8747-d482181cc5ec | checkpoint | 3.02.05 - Long Posts
62c3f131-1d14-54f6-8ed9-15be85c28662 | note | Acceptance / Conformance Criteria - Minimum 65x65x2.5mm SHS posts.
633704de-cfc3-5bc7-90cf-316309766856 | note | Standard / Specification - Drawings
925d187d-55f1-574c-b1de-42a00f05aa87 | note | Verifying Document - Photos
d4a22534-afdc-52e5-8917-17287cca5985 | note | Frequency - Each area
a6836dcf-01b6-509a-bb92-bc316a95dad0 | note | Verification Activity: Activity - H
c24306d7-a374-51e5-867f-08245e4d7ee4 | note | Verification Activity: By - PE
1e3ac4f7-ac77-4a72-b27e-5756e3e5d1d9 | checkpoint | 3.02.06 - Returns on Corner Posts
5be7bf77-cd8a-5673-a99c-93467b22f993 | note | Acceptance / Conformance Criteria - Returns to be 520mm wide with 90x90 HDG base plate bolted to foundation with 4/M12 4.6 HDG Bolts @ 50x50 spacing, minimum 150mm embedment.
3c96dfb4-6dc2-593c-8342-d68b6f3841f5 | note | Standard / Specification - Drawings
aecf88d5-0401-5bde-8e09-e38772eee6c5 | note | Verifying Document - Photos
1e0e6945-15df-51b7-97d8-ff355fcec064 | note | Frequency - Each area
c51e91bb-9c93-5cd3-b288-e3e808829740 | note | Verification Activity: Activity - H
dfa74075-d89c-5734-a36e-2f9dc6771052 | note | Verification Activity: By - PE
b1866de0-142e-4a57-9ecd-cd39adde499d | section | SECTION 4 – POST CONSTRUCTION
9e9546f1-fe79-4756-a38d-e04fd6db7f7c | checkpoint | 4.01.01 - Survey Records
95cb5f1d-0927-5ee5-92e5-4d0577948c07 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
31a014ed-0a8c-567b-9783-9a1519187680 | note | Standard / Specification - Downer
46ce3bd9-a319-54d2-bab0-a8d8f7c79e26 | note | Verifying Document - Records
c4b60127-a3f2-58f6-8f9f-4d8a152eceed | note | Frequency - Post construction
6029f5da-92c2-5f00-babd-d1becdbbad44 | note | Verification Activity: Activity - H
d7bbee28-4219-5aec-a082-bb3569f00be5 | note | Verification Activity: By - SV
ac380bc9-696d-48e1-b0a3-9d0d009ebefe | checkpoint | 4.01.02 - Redline Drawings
c23db1e9-09cb-593f-9043-0401a1556f30 | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
67d52f33-6af6-5588-86a6-4761f22f9041 | note | Standard / Specification - Downer
817f55b6-0e96-5e8a-8c12-bb11a78a6ff7 | note | Verifying Document - Redlines
8eccc253-3b56-504d-ac5c-127e043f9e9f | note | Frequency - Post construction
21fd5892-9900-533e-a2d0-76688ceef835 | note | Verification Activity: Activity - H
67ac4929-f436-5fff-ac56-341083e36e20 | note | Verification Activity: By - SE
4f97c36d-8f13-448f-8a16-a1ee2a83bcf8 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
52c15bf3-e002-5cd4-b7dd-097eca52f33e | textbox | Contractor's Rep Name:
db3e8bc9-01e4-5a8d-ac61-a3c85ffb188d | textbox | Engineer's Rep. Name:
4527f766-0436-5ab2-999f-d61fadb0590c | date | Date:
0c669356-2b30-4cad-a22c-f9b08b558065 | signoff | Add Signature
99272ecf-aa46-5d58-b2fe-9b0a293219ad | checklist | ITP - Drilling Rev 4 | itp | ITP - Drilling Rev 4
6fa60a3d-c540-58a1-8dbb-a8b6392fb43b | section | Pre-Construction
f8c8d9c5-737e-54a2-ae72-1d5adef27bd7 | checkpoint | 1.1 - Materials
6ff88db3-b4e6-5001-ab2a-caa90a72e762 | note | Responsibility - Engineer
af392e51-02df-5c6e-985a-a073367a3648 | note | Conformance Criteria Summary - PE100 SDR13.6 450mm & 630mm; Tracer Wire – Continuity test
1ef284b2-78a8-5b38-b96b-e2a60713c49d | note | Method - Docket; Include results
d2da5b80-c5c3-5a4e-87f3-38ee740b5c2a | note | Frequency - All Pipes; Each Pipeline
bd617085-0b3b-58f1-bd71-7ec20c4096bb | note | Hold / Witness Point - HOLD
3b93a982-3700-5eb5-ac5b-f42e69346167 | signoff | AUTHORITY HOLDPOINT
0d92ae6f-42b6-567c-a317-08ce04c82548 | checkpoint | 1.2 - Settlement monitoring and ground deformation (Baseline measurements)
a2969d97-ab77-54a6-a45f-ef9d1c42f262 | note | Responsibility - Surveyor
b471031a-853a-5290-8a51-8b29bca4d22c | note | Conformance Criteria Summary - Topo survey completed before and after drill shot, (allowed 100mm in settlement)
00693403-1e55-5aa6-8188-57f80baf7851 | note | Method - Survey
3fe88b2f-a37c-5bdd-9e71-8543fd0264a5 | note | Frequency - Every 1 m
0a6421d7-0fd3-523f-bf2b-4776ec8ad648 | note | Hold / Witness Point - HOLD
e8614e26-4377-539b-b6b5-00ee06ee32f5 | signoff | AUTHORITY HOLDPOINT
122b6301-eac2-54ae-b875-9edb949187cf | checkpoint | 1.3 - Qualified staff
babc6159-e2e7-5bcf-9689-e351223cd675 | note | Responsibility - Engineer
de373cfa-b78b-5429-9ce0-e2f07b53b982 | note | Conformance Criteria Summary - Qualifications of Robbie Reeves to be submitted before start of works
f245852e-59b0-5ead-ab8b-c994bde7e9b3 | note | Method - Email
6d05fffa-08b5-5697-b3bc-604487e456da | note | Hold / Witness Point - HOLD
80116c75-b6a4-5cf2-8580-be343eb13ac5 | signoff | AUTHORITY HOLDPOINT
41d17e51-262c-50a8-9c1a-7dcb56735cc2 | checkpoint | 1.4 - Tensile Test
ec32e578-be7b-5d18-82ff-9b49a5181f0d | note | Responsibility - Engineer
becbd134-98bc-5052-8be0-abf28056f7a9 | note | Specification Reference - 4.8.7
0163d04e-ef2e-5752-ad9d-0bced3edfe4b | note | Conformance Criteria Summary - 1 – Compliant test As per ISO13953-2001
f7af9cfd-d8d9-5a68-94c9-f3833128c43d | note | Method - Email
3b7597af-4100-51ab-942d-5ab4d35de8b2 | note | Frequency - 1
8add5ffb-5acb-5001-b749-113ae2272cd5 | note | Hold / Witness Point - HOLD
6f40a9ca-b390-578a-9fd7-15698efe8ec5 | signoff | AUTHORITY HOLDPOINT
87e74af9-116f-5be1-9875-bdeda5520162 | checkpoint | 1.5 - Drilling Fluid Mix
0a0484ca-ee24-52ce-84ce-df034abc9ee6 | note | Responsibility - Supervisor/Engineer- Supplied by supplier
8f10b078-eddd-5b0d-a41d-8590896e0138 | note | Specification Reference - 4.8.5
98915550-267b-5ba2-b655-5687d88768c7 | note | Conformance Criteria Summary - Fluid design to be submitted to engineer before start of works.
4e096507-495e-53d2-b061-612983d39bfb | note | Method - Email
5a60fda4-e04d-561e-8c7d-a34b8e8a0006 | note | Hold / Witness Point - HOLD
150d8b48-b537-5a3d-835f-98e2fd90371d | signoff | AUTHORITY HOLDPOINT
6c32fdcf-d21b-5a3e-a570-fb8fb2386fcc | checkpoint | 1.6 - Alignment Pegged out
c2b01877-b42b-5181-b20d-31bcdc8d85f4 | note | Responsibility - Operator/ Engineer
5e3529a8-7d1a-585e-a6e4-4105d773d68a | note | Conformance Criteria Summary - Survey Pegs
63a424fb-4a9a-50aa-a174-b9d70c39a52b | note | Method - QC - 09
cba1f9ad-72bf-5020-8476-7f165c0d1226 | note | Frequency - Pegs 1-3m intervals
acbdaa07-a3e3-5813-a4ba-c4bb5d336ee3 | note | Hold / Witness Point - HOLD
ec158c12-9d8e-5aa9-b70f-f656c3c7e000 | signoff | AUTHORITY HOLDPOINT
ab5db85e-805b-5560-8461-17a1bcb34179 | checkpoint | 1.7 - Environmental
d2454f6d-7a7c-5840-8bc1-8b22c923819c | note | Responsibility - Downer
b65c4482-8b97-5d51-8ded-79a603ee6be5 | note | Method - ESCP
6e97df66-3293-5cce-8665-cbe6361488cb | note | Frequency - Start
fe583c3d-7683-54d0-9c44-7d5e31919aa1 | note | Hold / Witness Point - HOLD
e1d00d93-7dda-5bdd-b9d3-f8893a01db90 | signoff | AUTHORITY HOLDPOINT
9959498d-611a-514d-a8ef-56ec81052b75 | checkpoint | 1.8 - Existing services
2698c22c-dcba-5cb4-aa9c-58c67b6c0fd4 | note | Responsibility - Engineer
1a511e3b-2ebc-5191-9bd2-54e25209e686 | note | Conformance Criteria Summary - No conflicting services
83ba0dae-5972-5756-9b2f-8c429623dd83 | note | Hold / Witness Point - HOLD
64b4c4ab-fa2b-57d6-9a4c-54168788df5c | signoff | AUTHORITY HOLDPOINT
3b2ee66a-a31f-5e10-be61-db308d6d9592 | checkpoint | 1.9 - Abandon Drill Shot
773dd662-2cb4-54c2-9e4b-ced47ba34187 | note | Responsibility - Engineer
4be36ca1-38c8-513c-8427-c11a14705bee | note | Specification Reference - 4.8.7
ed2aa2b6-7a86-5815-9265-1b447904e9b8 | note | Conformance Criteria Summary - New mix to be approved by engineer
2967c620-bf85-54c4-9498-74056f73765b | note | Method - Email
ddf4fcdb-2f48-5ded-b14c-069d9e833b49 | note | Frequency - Each abandoned hole
ce423f3d-e6d9-5e76-8023-55111f1919da | note | Hold / Witness Point - HOLD
f909c832-b55f-5d4d-bdea-a3594d9cd5af | signoff | AUTHORITY HOLDPOINT
2bb190a2-0901-5028-b8c7-37464722491e | checkpoint | 1.10 - Butt Weld Data
35ee3914-4365-5e32-9f8d-485e50458b36 | note | Responsibility - Engineer
9004f3ab-0f33-5de0-ace2-c5a8984e694a | note | Specification Reference - 4.8.7
a0b1ea38-6f82-58f3-8420-9d73d7b403e7 | note | Conformance Criteria Summary - Data to be submitted
9ba4811f-06a5-5419-91f8-7d5914691e3d | note | Method - Email
b97fe185-0bf7-5962-a8c4-f5a00dab2ead | note | Frequency - Each weld
76806c75-93b1-504e-8d96-c5fc57efdb29 | note | Hold / Witness Point - HOLD
981255e1-f51d-59ac-aafd-15b1d27f014d | signoff | AUTHORITY HOLDPOINT
e0730d12-27eb-5611-98d0-bf743e68b951 | section | Construction
43f07294-7ef7-5b03-8d18-359ec3e152e5 | checkpoint | 2.1 - Drill Entry Angle
4823544f-51f1-52da-914b-6fb92537cf82 | note | Responsibility - Operator/ Engineer
718f988e-c648-5d1d-8e57-f22f010a54c7 | note | Conformance Criteria Summary - >8° and <20° to be measured with data logger
efae2b18-a95b-5858-bdea-a1850def554d | note | Method - QC - 09
ad279368-b9db-50ee-b51b-c4f637cb1d4c | note | Frequency - Every shot
b91b16ef-e77b-5304-9332-ce1c1c944699 | note | Hold / Witness Point - HOLD
5bcfd327-9928-5aeb-9d79-3eafd5751daf | signoff | AUTHORITY HOLDPOINT
65bd7b4e-b1cc-5653-a86c-ea932827680a | checkpoint | 2.2 - Check levels while drilling
84b14d25-f170-5bb8-aa0e-927b7879a1f0 | note | Responsibility - Locator
542a5280-10a0-5cf5-816e-44c3fb9b67e8 | note | Specification Reference - Table 4.10 PS
1264e0c7-cd6c-52ed-8124-2514e894eb9e | note | Conformance Criteria Summary - +/- 300mm Horizontal [NT1] 67.5mm (450Ø) Vertical 63mm (630Ø) Vertical
0377168a-64a6-56da-bb37-7d77d3d81bca | note | Method - QC – 09
3cf8bbf9-e142-5c66-873d-d87558bd5a51 | note | Frequency - At every peg
04113fbd-0bc8-5228-99b4-1a8d75ce4969 | note | Hold / Witness Point - HOLD
e453b303-23ac-56e6-9bfb-50d8f340c7c5 | signoff | AUTHORITY HOLDPOINT
23fe061e-7550-5913-9080-111f7d4c15d9 | checkpoint | 2.3 - Drilling Fluid Mix
5949a641-fa32-5496-ac99-4a782651ee19 | note | Responsibility - Supervisor/Engineer- Supplied by supplier
7befbf8e-ddea-53aa-b3af-24c5577a02e3 | note | Specification Reference - 4.8.5
3e1b27c3-e804-5432-aa1f-a8bb0096025d | note | Conformance Criteria Summary - Viscosity (Recorded) pH (Recorded) Bentonite due overs
cc888399-b00e-586d-9353-0ab56f534372 | note | Method - QC – 09
886f5155-c613-5bce-821f-67dd5ed4833a | note | Frequency - Every shot
27a1bb79-905a-510a-961f-aaab48b38214 | note | Hold / Witness Point - HOLD
bb466541-6637-5a96-b9b0-4e1a16c93e94 | signoff | AUTHORITY HOLDPOINT
7cd3dbf0-de0e-5e41-947f-c3cb0690abad | checkpoint | 2.4 - Correct Reamer used
50020b32-7d17-5b49-bc8b-e224f539da51 | note | Responsibility - Operator/ Engineer
5ba9d0a8-3507-5e0b-99dd-af5cfacc1ce3 | note | Specification Reference - 4.8.7
272d2c25-800d-512f-90b7-011635de7e9d | note | Conformance Criteria Summary - Discussed with engineer prior to starting **
8f03e162-9f63-5cae-a5ca-46a81d6551d0 | note | Method - QC – 09
98f711fd-934b-596d-a6b6-e1a8b15709ff | note | Frequency - Every Pull
e8b709ef-d4dd-5585-af59-150400a1a0ac | note | Hold / Witness Point - HOLD
447d3178-fab4-50ba-94cf-3d053a56db09 | signoff | AUTHORITY HOLDPOINT
7852af11-fbc0-5102-9aff-be5ccabd200f | checkpoint | 2.5 - Pipe Damage
1549d838-bb32-5370-b80a-1e57104b3ed9 | note | Responsibility - Engineer/Supervisor
5d2f7d8e-e56d-595d-8c64-708112618af6 | note | Conformance Criteria Summary - Check sheet completed on walk over of pipe before pull.
d5d0d196-c3be-5ba9-abda-e66b86d954d2 | note | Method - QC - 09
6bb88644-1882-5f8a-8916-8e833b4eea89 | note | Frequency - 1 per drill shot
d34305a3-ecc5-5c30-aee7-cd2c4c7a595c | note | Hold / Witness Point - HOLD
8442161f-06a6-53ca-897d-a7fc76d8fd12 | signoff | AUTHORITY HOLDPOINT
71630cd8-f0fe-557f-aed9-9e1219ceba03 | checkpoint | 2.6 - Pipe Visual Inspection
58cc539b-00c1-5801-b4e3-21b084f25a93 | note | Responsibility - Engineer
30069d36-ea86-570e-b009-c719da19be40 | note | Conformance Criteria Summary - Damage <10% of wall thickness
0ef6d46a-8b12-559b-becf-d78a0039ad64 | note | Method - QC – 09
2b8038b7-2200-5b94-8f4d-418a1cfee1cc | note | Frequency - Every Pull
3fd9a447-69e1-5f8e-9467-d2146ee776a2 | note | Hold / Witness Point - HOLD
ea7c7cda-639a-5408-ab8f-bedf04aa0879 | signoff | AUTHORITY HOLDPOINT
4394b2d4-b1b8-5b07-8094-ba4bf68269af | checkpoint | 2.7 - Tracer Wire
3a8dc71e-3af0-5f5e-95b1-cd4d249c4a4c | note | Responsibility - Operator/ Engineer
5140d2e4-c0d4-546e-a8b1-aaa2335fd065 | note | Specification Reference - 12.4
d044e739-b05e-5105-9526-b4b587ad35d2 | note | Conformance Criteria Summary - Minimum 4mm Taped every 3m
62dd4f03-3bfa-5eb1-b31c-6c0c6a0c4f37 | note | Method - QC – 09 and photos
9203daa5-2b55-577a-89a3-28eef11f360b | note | Frequency - Every Pull
b9ddc7ed-46e4-526a-9896-51ff16a48da4 | note | Hold / Witness Point - HOLD
e53ee20e-d4c0-539f-9eba-280da96e650d | signoff | AUTHORITY HOLDPOINT
61bcb9a0-ca66-5687-bd15-3b3c375852ed | section | Post Construction
a0f26c3a-acc2-5f89-b65d-87506e98b0be | checkpoint | 3.1 - Drill Report
a2a9604f-2219-50b8-b9b8-bb128f1e3309 | note | Responsibility - Engineer
c32c78fb-3af8-5cbc-b708-fb512f35fb14 | note | Specification Reference - 7
3bed618d-ad4c-5ca2-b841-5f08a831b30a | note | Conformance Criteria Summary - Drill report to be submitted
e4a7bd1e-e6a3-5203-9071-75ede7b59eef | note | Method - Email
e4173227-f70c-55d6-bf5a-f0bca33d068c | note | Frequency - Every string installed
b4104a6b-6482-575f-850c-8fec9f4e7eba | note | Hold / Witness Point - HOLD
a1b47b9e-46a3-5bf5-bef9-c786e6b2376a | signoff | AUTHORITY HOLDPOINT
32857225-8258-5244-a5f1-7af725d03a92 | checkpoint | 3.2 - Settlement monitoring and ground deformation (Baseline measurements)
aebf78a6-8ff0-5da2-956c-c9d3449f852c | note | Responsibility - Surveyor
40d44da4-4d0e-5335-a3f3-78d649716599 | note | Conformance Criteria Summary - Topo survey completed before and after drill shot, (allowed 100mm in settlement)
4cb00e68-ceb0-5b9a-b49a-34d49e376aef | note | Method - Survey
2a374420-86a1-56a6-bb21-1b4aeed6851f | note | Frequency - Every 1 m
e20c2185-8cbb-5d88-bb00-ebb9de071909 | note | Hold / Witness Point - HOLD
b1289181-eb97-5f80-aa6d-132ca05b982b | signoff | AUTHORITY HOLDPOINT
50e44c15-2986-5d55-8c38-4357344c4c8c | checkpoint | 3.3 - CCTV
bb5b9bb0-762c-57fa-8fcf-d5d675b6c16e | note | Responsibility - Engineer
a0b40396-7c83-549a-afe7-707df2bda234 | note | Specification Reference - 4.8.7
5386db2c-b469-54a9-983e-f4848df6d2ad | note | Conformance Criteria Summary - Submitted
e7b7ef73-1098-5fe1-8463-6febb3e30ac4 | note | Method - Email
79edf7b3-9e6d-5bfe-9631-288e126f9b5e | note | Frequency - Each Pipeline
975837e5-92be-56ec-959d-4d3ec59c8d2d | note | Hold / Witness Point - HOLD
63fd3703-a030-5bd7-868e-92953c336424 | signoff | AUTHORITY HOLDPOINT
ac8c92a9-23d4-5098-a3f5-4eabb3d44d5e | checkpoint | 3.4 - As-built including red pen
5900d80b-6cc5-5f2c-bc39-0b19c9848eed | note | Responsibility - Engineer
7e2e8e3c-970e-55fc-8c32-4cba5bd65c08 | note | Specification Reference - 4.8.8
6754efd4-586f-5bee-b348-55b3d59b93b8 | note | Conformance Criteria Summary - Submitted
cfc7129b-cb13-5730-b93b-c5a7c93f1179 | note | Method - Email
9eed492f-a84c-5138-81fb-d1ae13b2e733 | note | Frequency - Each Pipeline
ea5ab098-2f02-5dbb-908e-5e49ecb3b5eb | note | Hold / Witness Point - HOLD
970f9a99-bd2c-5ddc-aecb-785a47976adf | signoff | AUTHORITY HOLDPOINT
664fd8ed-c16d-5596-ab61-6758a0bd8143 | checkpoint-no-value | Additional Notes:
b79a7d5e-107e-5721-b939-0abd897d80d3 | note | Reamer size to be confirmed with ground conditions. To be closer to diameter of the pipeline then table 4.9. (for 630 Main this is to be 775mm ideally and 550mm for 450mm line)
d00911df-9745-58d3-b196-30e4d52a8634 | note | CCTV Inclinometer is as per specifications of camera (Can not achieve a consistent or accurate grade)
de6a28b5-471a-5736-af6d-bd11321ff808 | note | 1mpa is not achievable for grouting.
f83c85e0-9593-5eb9-972e-80df4c23ce93 | note | No Critical locations
3bb8eab5-b9b7-5476-b72e-87ed949477a6 | note | Material specifications and properties determined by BBO. Please let us know if you require assistance with this.
68903ba3-267c-5e10-b4c8-6af450b1e3bf | note | Methodology and JSEA to be supplied on approval of ITP requirements.
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
0a37ed4e-82bb-54ad-84a5-803b49b4efec | checklist | ITP - Earthworks | itp | ITP - Earthworks
6195b1b8-fa1e-5a7d-97fc-dbd972d19217 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements
66aab68a-f757-5648-805e-fcd3004146e4 | checkpoint | 3.04.01 - Construction Pack
bfee9e2d-a6b7-5f70-91c0-be5382ad9749 | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
73019707-9e2c-534c-a05b-3fcde5672553 | note | Standard / Specification - Downer
fc46177b-d6da-5e5f-b473-8975092b2048 | note | Verifying Document - Construction Pack
cf028689-ebb3-5192-9152-61a6781b2e1b | note | Frequency - Submit 10 days prior to commencement of works
1053d10a-8bc4-5c7e-b34e-717289b9bdf0 | note | Verification Activity - H
769b19e6-25c2-51ef-b6c5-d49c93eb7c7b | note | Verification Activity By - PE
26f60828-4451-5309-8d3b-0249cb8b6985 | checkpoint | 3.04.02 - Survey Setout
cf831fa4-9e72-5f6f-93bc-7b92ee6d3e7a | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
51686e4f-ea10-57de-b465-280fbf293317 | note | Standard / Specification - Downer
a56c6f04-de46-5fb8-aa75-7917dc94c8f6 | note | Verifying Document - Survey Records
77d6aa06-edd2-51e5-b4d1-f50385252962 | note | Frequency - Prior to Works
e9e2ae26-142d-55ca-80ae-2a4d6a362454 | note | Verification Activity - H
5ac007ba-46a3-5bdd-84ea-5f8829d48733 | note | Verification Activity By - SV
d8eb320e-d9df-5647-adeb-94fd61bee34b | checkpoint | 3.04.03 - Approved Construction Drawings
adac429a-f7e2-5e63-80d0-730d50cbd484 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
3b02b1a1-aed9-5211-a134-9a04eeffc8ce | note | Standard / Specification - Downer
3fdf891e-3ead-5017-b89f-18cf138d101c | note | Verifying Document - IFC Drawings
4173a28d-0312-5795-9c8c-5dbbcc1476d8 | note | Frequency - Prior to works start
cfa53cbe-96bf-5d97-a692-51a01ce4fd25 | note | Verification Activity - H
457bb499-0401-57d1-a2a5-f9335bba738f | note | Verification Activity By - PE
c41c9d11-3ba8-577c-b861-3303c0fbbdeb | checkpoint | 3.04.05 - Topographic surveys for measurement
b0ac2514-a724-594e-9ebc-d4a1ce86bf41 | note | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
aa70e3c8-aabb-5a4e-bbe9-5a344f485278 | note | Standard / Specification - PS 2.2.12
f4e73635-e745-53ec-9c27-42e5b3f88ffa | note | Verifying Document - As-built
c95d9ef2-4b07-5466-a47b-37893c42864a | note | Frequency - Prior to works and Post Works
e0c41ef4-e1d7-542e-b948-53432b22e03a | note | Verification Activity - H
666286b2-083d-59cc-9c48-2306a176d1d0 | note | Verification Activity By - PE
1ee852b3-c73f-5268-a975-3c912a92cb7c | checkpoint | 3.04.06 - Permits
1086a7b0-b8fe-576d-8430-21b79737c40c | note | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
5795d95a-16ee-5ff4-9521-bbea691dbe15 | note | Standard / Specification - ITP Register
abf5a4ad-1f5e-5db4-adc9-de90fce74b16 | note | Verifying Document - ITP Sign Off
d59d5929-0aa7-5d0b-89cb-e4bd1357d609 | note | Frequency - Prior to commencement of construction activity
4c981c6f-8b77-5d6e-8556-3aabf085e93c | note | Verification Activity - R
412821e0-a96c-5a47-92ad-7cf6c94f8d6b | note | Verification Activity By - SE
f3ef973a-42cb-52b5-8ea7-66cbfcf256e9 | checkpoint | 3.04.07 - Stakeholder Management
07f0300b-dee9-5f28-9128-a0d9daf1509f | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
66cd92a6-7a53-540f-9e88-afdef00c9aed | note | Standard / Specification - Project Stakeholder Management Plan
e422661f-e345-5a54-8688-d7cd237acb92 | note | Verifying Document - ITP Sign Off
4b556bcf-42b1-56a5-bfdf-aff9f8fc919d | note | Frequency - Prior to Construction with continue updates throughout the works
b486a5da-ac9f-5a37-89a1-e4205d6f2fb7 | note | Verification Activity - R
f1c12282-a223-563a-b4af-025210d3be65 | note | Verification Activity By - SE
005c296d-25f0-5738-a789-b97cd604b77f | section | 3.05 Engineer Nominated Hold Points (Engineer’s inspections)
a1b580bf-5e0e-529d-af5f-81de8644feb8 | checkpoint | 3.05.01 - Environmental Controls Inspection
220fb01b-d745-5045-be14-134205e9c4ca | note | Acceptance / Conformance Criteria - After installing measures to meet environmental requirements, before any earthworks begin.
12810a36-7076-5fa3-9309-fa15bd838414 | note | Standard / Specification - PS 2.2.16
b6e38161-1c28-58dd-8003-e06fc54c07b5 | note | Verifying Document - Site Records
2468b7fa-2b30-5143-9a17-d0cf723c63b6 | note | Frequency - Min 48h Notice
82fc3266-7242-50e7-adfc-5b87a9456b0a | note | Verification Activity - HP
6fe76645-582f-5023-93da-ab8501b34efd | note | Verification Activity By - ENG
45ce02c6-4c82-5ac3-aed2-668e7589b94b | signoff | Hold Point (Engineer)
397e246e-d5bd-577a-8f6b-81ec01a01ad6 | checkpoint | 3.05.02 - Bulk Fill Inspection
39705f9c-e934-5b3b-8800-e537f4d47d3c | note | Acceptance / Conformance Criteria - Prior to beginning bulk filling operations.
bd28e4f6-5513-5ca5-b0b9-8f398af9b0bf | note | Standard / Specification - PS 2.2.16
7f620750-7037-5f90-b423-8458b93e4bfd | note | Verifying Document - Site Records
4cc87978-3af0-54f2-a37c-2861c60b4f3f | note | Frequency - Min 48h Notice
bcaf12cf-0efa-51ad-9ded-5b8f62c0353f | note | Verification Activity - HP
4c8ec7d8-3e90-5a24-957b-45c963ead5e2 | note | Verification Activity By - ENG
d8cd9a3d-90ca-5b10-9fe2-8f39698d26cf | signoff | Hold Point (Engineer)
3db3366d-0d88-57aa-bded-c077e09e64d1 | checkpoint | 3.05.03 - Service Ducting Bedding Inspection
57a8445d-fd38-5977-b749-a3db5394a8c6 | note | Acceptance / Conformance Criteria - Prior to laying any service duct, drainage/water/sewer pipeline and associated pits, fittings and structures
0bd2a218-cf77-58c3-be8b-00842a9fa36c | note | Standard / Specification - PS 2.2.16
241bcb23-ff2f-5e2e-bd32-1b66435db087 | note | Verifying Document - Site Records/ Refer to Services ITP for testing requirements
305f24c2-0703-584a-9e40-ce3157339d1e | note | Frequency - Min 48h Notice
1bc05559-a503-5c5f-8fd1-27d0207c0609 | note | Verification Activity - W
f5ac7004-e040-5094-b259-35cbbf4b3574 | note | Verification Activity By - ENG
26f735b3-30f0-54da-b96e-22b8e5c765ea | checkpoint | 3.05.04 - Service Ducting Backfill Inspection
7e4a7988-03c3-5c7e-87af-ed5a4d520a43 | note | Acceptance / Conformance Criteria - After laying, before backfilling any service duct, drainage/water/sewer pipeline and associated pits, fittings and structures.
5397b13e-25a0-53f7-90e6-21d21174ffa1 | note | Standard / Specification - PS 2.2.16
38f7b901-ce61-5b82-ba86-2c9d95552aab | note | Verifying Document - Site Records/ Refer to Services ITP for testing requirements
e019faaf-8fe0-58e4-a4b1-8950d688b682 | note | Frequency - Min 48h Notice
d6a597bf-c1ae-5f05-a332-0e409159e8ac | note | Verification Activity - W
9abd5920-382a-5c80-a2b5-d604334cd91e | note | Verification Activity By - ENG
aacdafb1-ce5f-5662-9207-c4b7ab197387 | checkpoint | 3.05.05 - Geotextile Inspection
30235357-ba2a-5d0d-bf32-e108465a9ab7 | note | Acceptance / Conformance Criteria - Before placement of any geotextile.
af850139-ab11-59d3-8d6a-5ded512dd2e8 | note | Standard / Specification - PS 2.2.16
0ce6ff77-7be6-5200-8852-5d53e2272e01 | note | Verifying Document - Site Records
5cc966d5-e906-56ef-8ad4-2635435e73de | note | Frequency - Min 48h Notice
2e6fd158-bfe1-590a-9fbb-55341e4c9b58 | note | Verification Activity - HP
f63cd949-8628-5163-86d2-5e2ab51aae46 | note | Verification Activity By - ENG
a8c91dec-fc11-597c-8d05-68a26a62e131 | signoff | Hold Point (Engineer)
48749a16-2f17-50e3-a581-2454b8601df7 | checkpoint | 3.05.06 - Subgrade Inspection
bea3bd3e-1a67-59b3-b150-ca5c3595fab9 | note | Acceptance / Conformance Criteria - Subgrade inspection/stripped surface inspection, to include proof roll, scalar penetrometer and/or shear vanes.
70fc358c-d354-5c6c-8df9-908d48a52f10 | note | Standard / Specification - PS 2.2.16
714db9ad-f46f-52ef-a07e-a27fc0f7ea8d | note | Verifying Document - Site Records/ Test Results
089e3007-f9b2-53da-8767-6fb0c3a01dd8 | note | Frequency - After surface is stripped
40c00e8f-59e9-50f6-b11f-195e2cab0563 | note | Verification Activity - HP
fb26b3b6-d7be-55a5-b920-f8455c493cc5 | note | Verification Activity By - ENG
2c2d55b5-3df4-59c1-91e3-ee43ce6a39af | signoff | Hold Point (Engineer)
7d7e7aa1-ae37-54cb-b094-9943cfe254a2 | checkpoint | 3.05.07 - Undercut Inspection
205f430b-1d40-5338-820a-fc895c69c6b2 | note | Acceptance / Conformance Criteria - Undercut (if required) inspection, to include proof roll, scalar penetrometer and/or shear vanes.
04d27b24-5e7b-5476-a7ea-cd82483eb3f5 | note | Standard / Specification - PS 2.2.16
65d11e86-28dd-584c-80fe-f09a9af7f41b | note | Verifying Document - Site Records/ Test Results
3ff38dd2-5471-58e4-ae4a-e9a347932bd0 | note | Frequency - Prior to Subgrade Fill
cc051a3c-b0ae-58ed-85a3-2f3963327f46 | note | Verification Activity - HP
1feae0c2-2658-5f77-98b9-3f71b3aea196 | note | Verification Activity By - ENG
39632f99-b15b-5214-adee-cd16315c8d2f | signoff | Hold Point (Engineer)
c25d7356-8bb0-53c1-8727-2361fcf330cf | checkpoint | 3.05.08 - Settlement Monitoring
977450d1-fc9f-55e5-817a-1b9283275032 | note | Acceptance / Conformance Criteria - Settlement monitoring (Settlement pins & Targets) to be assessed by Geotechnical Engineer.
6d2a8eb6-7a7b-5db6-b4f9-6b3941313504 | note | Standard / Specification - Drawing 5200
70cf0c56-fdd1-5590-bef1-518c0f108a8c | note | Verifying Document - Site Records
1a1b650a-d510-553b-b01c-32e36162d83f | note | Frequency - Prior to constructing pavement and wall
f7da49b3-2c9b-5dd0-bd85-3aeaf35709bb | note | Verification Activity - HP
111c8e86-e703-5fd2-8eb8-e9bc46da9b4a | note | Verification Activity By - ENG
cd0ccdef-ce99-5ee8-9f3c-c9e95bbe82bb | signoff | Hold Point (Engineer)
de84f0d7-e75e-53ab-93ee-2a886ebb2ee7 | checkpoint | 3.05.09 - Subgrade Fill
3b6d39e4-aded-5525-9a05-2f3ba7d4111b | note | Acceptance / Conformance Criteria - Inspection of completion of sub grade fill prior to placing SIL, to include proof roll.
1e9e7ca8-b008-5387-b5a7-47972e295356 | note | Standard / Specification - PS 2.2.16
53267922-2588-5542-83ec-dcce3f7fd14f | note | Verifying Document - Site Records
9c59b01f-1e26-5caf-bc10-e68acc082366 | note | Frequency - Prior to placing SIL
c72eeff7-163c-5f7e-80c2-3f277204adcb | note | Verification Activity - HP
a33638a4-2802-5015-8b04-2758f810735c | note | Verification Activity By - ENG
7a8e1a7e-4fc8-54fa-b5d0-050a773d5a8e | signoff | Hold Point (Engineer)
de2c1e9a-cd69-5b10-8fa2-10046a6dd4a0 | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials
7ac3fd82-2973-5391-8d47-ef653930dfb0 | checkpoint | Imported Fill Approval
45fd01c7-e910-54d4-bec7-c51dc5e869fb | note | Acceptance / Conformance Criteria - Due to the fill-deficit on this project, imported fill will be required and should be discussed with and approved by the Engineer to verify its appropriateness and quality control testing requirements prior to use.
00224ad9-b44c-5c64-925b-0bdf2c3ad0b9 | note | Standard / Specification - GWS 2.4.1
034eb994-bff4-5dce-a8f5-5ca2e39e8efb | note | Verifying Document - Lab Tests
7bda6704-2e88-5a6c-903a-5abc136f5367 | note | Frequency - At least 2 days prior to placement and compaction.
be698d53-8e18-584e-b59e-5008a430fece | note | Verification Activity - HP
1b3a4554-bdab-544a-b0fe-2f429c05b292 | note | Verification Activity By - ENG
78f70bf6-2c06-5035-b60e-a22f6883679e | signoff | Hold Point (Engineer)
2e7287c7-4587-51f8-855e-cfbf51bf5280 | checkpoint | Re-Use Suitability Approval
41060b61-19fa-58c6-8795-3e53e1d8ca7d | note | Acceptance / Conformance Criteria - The Contractor shall test representative samples of the site-won material to be used as Bulk Fill and Subgrade Fill and the results are to be sent to the Engineer for approval.
71239f25-057a-5495-a65b-8059f502eb40 | note | Standard / Specification - GWS 2.4.2.1
91ac6848-60d0-5318-9a00-ed4c631f5ddb | note | Verifying Document - MDD, OMC, Shear Vane, PSD
51318647-1fc0-5090-a5bb-df5e632715e4 | note | Frequency - At least 2 days prior to placement and compaction.
4017e19b-6c59-58e0-a358-c2fb46c5bd2f | note | Verification Activity - HP
2738daad-13e6-56e2-850b-dbfe698f6491 | note | Verification Activity By - ENG
7449aaf7-2b71-58d8-9829-b0496e095d2c | signoff | Hold Point (Engineer)
4ee2b052-c438-5f8b-a38c-87ef2aad7f10 | checkpoint | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
13cb71d6-c1af-54a6-b7bd-21510996a303 | note | Standard / Specification - GWS
aa43c410-4e9d-5b14-a06b-357e23903553 | checkpoint | Eastern Gully Weir Cohesive Fill Material Testing
7e475385-e59b-545a-a386-0317f85d7e4f | note | Acceptance / Conformance Criteria - Eastern Gully Weir Fill shall be tested for Standard Compaction, Solid Density, Plasticity Index (PI), Particle Size Distribution, and Liquid Limit for
5599aacf-9b19-556b-8071-03ee88a79288 | note | Standard / Specification - GWS 2.9.4
291d7143-24d1-5bea-a541-b52e6e678f66 | note | Verifying Document - Test Results
c80900c5-6f26-514c-925c-08033d42fde0 | note | Frequency - At least 2 days prior to placement and compaction.
5e1dd57d-db29-5032-93c2-fc611966f113 | note | Verification Activity - I
2acb792c-7756-591a-9291-3d52f360c47d | note | Verification Activity By - SE
e2c74411-283e-5dcb-92e5-1ad4c8673db8 | section | Subsoil Drainage
0ad51274-e32e-5a34-bc29-557e5134bdeb | checkpoint | Subsoil Pipes
3f94bf73-bf5b-5437-9da8-17e3ae97576d | note | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 160mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
f9a94957-2d43-5bcb-b341-3538bb894ea7 | note | Standard / Specification - GWS 3.2.1
b629c8f6-6dfd-5ea2-b72e-17917646bbc1 | note | Verifying Document - Datasheet
f4e1f338-8fa7-504b-a4cb-56b41896398e | note | Frequency - Prior to installation
1a71e582-8f83-564e-92ab-12f86985a0e1 | note | Verification Activity - C
33c9ad80-23dd-5d83-a970-60e5f6105c12 | note | Verification Activity By - SE
50199267-31d3-5c23-904e-350146494d70 | checkpoint | Subsoil Drainage Aggregate
157dd5fd-3914-5a7d-b6cd-82a7e9a4aafb | note | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/6 including gradings
aa2baf26-c5d7-5049-ab44-ef2f743b3ebe | note | Standard / Specification - GWS 3.2.2 & 3.4
1248aa8d-7bc1-58cb-a514-3c47b2467f19 | note | Verifying Document - PSD, CR
7a23c5b4-57d0-5aa9-9f7e-07c02b92409f | note | Frequency - Prior to installation
5e0a201a-911e-5ee8-b97a-d9332fbdcfe8 | note | Verification Activity - C
506f0618-6e1c-5102-87bc-d361e1022c7b | note | Verification Activity By - SE
4cf2d249-01dd-583a-b300-ee9c0fdca73b | checkpoint | Filter Cloth
40786ed1-1abb-5eab-b26d-821b1c62bf75 | note | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings.
a0219122-25d9-528f-ae9a-22dbaf87c7a8 | note | Standard / Specification - GWS 3.2.3
f610f319-f379-53fa-8154-8b4d5bca6c13 | note | Verifying Document - Datasheet
2e3e366f-ba60-5836-9a55-28f1ba3a5d70 | note | Frequency - Every 1,000m3. At least two weeks prior to works.
951ef335-8d62-5c06-be73-7eec18ac3d1f | note | Verification Activity - C
fe3a95d8-88a3-576f-aa42-613286c0653d | note | Verification Activity By - SE
dd05ab25-8ed9-58ff-8c52-86614831d043 | section | Geotextile and Geogrid
c1949a02-aaa7-5fa3-8791-d10472398429 | checkpoint | Geotextile Approval
9a3d2597-ebe2-539a-aa42-61368c2611c3 | note | Acceptance / Conformance Criteria - The Contractor shall submit to the Engineer for approval the details of the filter fabric they propose to use at least two weeks prior to commencement of works, including compliance certificates.
a79a093a-64b5-5be4-812d-9f9f7aa9450c | note | Standard / Specification - GWS 4.1
561e97cf-103c-5838-ac55-be14acc86d5e | note | Verifying Document - Compliance certificates
79bd7770-6037-5577-8954-1c2bdc4582d9 | note | Frequency - At least two weeks prior to works
067be5b6-4d6d-5483-92ea-3e46a124d9a9 | note | Verification Activity - HP
967372ea-a3a3-54c8-9a64-18ddb723d059 | note | Verification Activity By - ENG
d8ea6ffc-c3de-5ea8-b878-175ea6e2f0e7 | signoff | Hold Point (Engineer)
aa4c0f31-7cfb-50e2-8525-6c6810829d61 | checkpoint | Uniaxial, Biaxial and Triaxial Geogrid
20af9f1b-6c10-5787-a2c6-f3c6221c2cc6 | note | Acceptance / Conformance Criteria - All uniaxial, biaxial and triaxial geogrid shall be manufactured in accordance with a management system that complies with BS EN ISO 9001 and BS 14001 and shall submit to the Engineer for approval.
ef41addc-1cbe-5c0d-9ca5-8d1ef6fdbe67 | note | Standard / Specification - GWS 4.2
0c7958a6-3ee8-5743-b5ce-19e007a5a8f6 | note | Verifying Document - Datasheet
913b2d66-4c18-5767-a5e9-17b67944114f | note | Frequency - At least two weeks prior to works.
aea6a083-cef0-5f4f-85d7-58111f8e5b2e | note | Verification Activity - HP
2fb75c33-4757-5988-8eb9-2f85068131e8 | note | Verification Activity By - ENG
80934c9c-deae-58f1-8340-4294589c22ea | signoff | Hold Point (Engineer)
e8dd58e3-026c-58f5-a27a-a9b089d1dc75 | section | Settlement Monitoring
84c5c33f-c8d3-5a40-9527-0b33b83cd8b1 | checkpoint | Settlement Baseplate Design
b2e13714-0793-5134-9aba-dff3f3e49e11 | note | Acceptance / Conformance Criteria - Equipment shall consist of 600mm x 600mm base plate (typically 20mm thickness),150mm PVC duct, 32mm diameter threaded bar with couplers for extensions at 1m intervals and waratahs and coloured flagging for protection following installation.
ab58a620-29e1-5cd5-9913-2c7857009c45 | note | Standard / Specification - GWS 6.2
9dc5bee6-37ba-5834-afe8-f7ef22fcf6eb | note | Verifying Document - Datasheet
177044c2-7b5a-56d8-b467-6a11c2a05f8d | note | Frequency - Prior to installation
38c7b763-7106-5ffc-9cab-8f619cc54550 | note | Verification Activity - I
9d733ae1-3eec-549d-8aba-40c2e14e2c81 | note | Verification Activity By - SE
958c01f8-566d-5276-933d-837d8aa231fc | checkpoint | Settlement Pin Design
4993c9e1-6514-5af4-8698-bf4bb1ef0f04 | note | Acceptance / Conformance Criteria - Settlement pins are to comprise 32mm diameter Reidbar rods driven a minimum depth of 0.5m into the ground surface. The top of the pin shall be domed to ensure repeatable survey measurements.
8280e55b-aaec-5527-b3ea-2bd24da7ac4e | note | Standard / Specification - GWS 6.3
6a86ff42-72c4-56ff-9fe0-eff5fd9492fd | note | Verifying Document - Datasheet
f069dae9-7360-5fcb-a785-701687cc1afc | note | Frequency - Installed within 24 hours of reaching design subgrade level
c73ca30a-597f-5a40-b41f-829e4cedbddd | note | Verification Activity - I
33be6f18-8792-5920-bf9d-de4009c5069b | note | Verification Activity By - SE
8e750017-49c9-59c2-921e-3d272003461e | checkpoint | Settlement Pin Bedding
2e1cfb65-6bc6-5474-a42d-b8ec2e0429ff | note | Acceptance / Conformance Criteria - Installation of the settlement markers shall occur at the base of the fill embankment, prior to placement of any fill. They shall be installed on a 100mm thick sand layer to form an even and smooth foundation which will be levelled using a spirit level.
2e80c0cf-b430-5cf6-8078-e90a77e6de23 | note | Standard / Specification - GWS 6.2
bb88f167-2eac-5ea1-a07a-4edb43311454 | note | Verifying Document - Site Record
433e324e-7e70-5607-946b-81fc02328d45 | note | Frequency - Prior to placement of fill
f0211247-806a-5652-b84e-408b2ce9da48 | note | Verification Activity - I
8c69d77c-c146-5a3b-9c0b-2d63827771a2 | note | Verification Activity By - SE
e7f9565e-269c-5b8f-bea7-bbe3f8910040 | section | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance
e53738b9-4ea0-5a1e-932b-1e909db7f934 | checkpoint | 5.01.01 - Clearing
78082b3a-e12b-5c21-a358-53d24b788896 | note | Acceptance / Conformance Criteria - All surface objects including fences, gates, debris, wood, dumped rubbish, concrete and other protruding obstructions shall be cleared and disposed of
9da1e544-eed3-519d-91c1-83240462c755 | note | Standard / Specification - PS 3.1
b50dac47-4fde-59b0-813f-56d6371997cc | note | Verifying Document - Site Records
a64d2405-c9fc-5811-a16d-dfcafa596de9 | note | Frequency - Prior to earthworks
1ca5d8fa-084f-53ca-b716-8880263ff1fd | note | Verification Activity - C
783b14cd-f41b-5af2-ab9a-9cdee83f416d | note | Verification Activity By - SE
c1229a05-a5ba-5ee3-9dc8-50f6b66bd874 | checkpoint | 5.01.02 - Demolition
898e6b66-9ffd-5630-8dcf-66d7cdd5cb4e | note | Acceptance / Conformance Criteria - Remove all buildings from the site including foundations, buried services and any other remnants.
1e4b5000-6877-5ca4-84b0-743bc492ac42 | note | Standard / Specification - PS 3.2
24b04cf3-b6ce-5360-8034-99e455efb90d | note | Verifying Document - Site Records
0f5cac53-5c09-5007-b349-9f02b07fb230 | note | Frequency - Prior to earthworks
676ec549-3b82-5463-b42f-70db12e7831d | note | Verification Activity - C
0937604e-d956-5db1-bf39-00d54c56fc50 | note | Verification Activity By - SE
d6abbe19-411e-547a-a0a0-c76f30ed53d4 | checkpoint | 5.01.03 - Septic tanks
f8c973f8-deef-5746-94a7-f251b5a2a71d | note | Acceptance / Conformance Criteria - Septic tanks shall be pumped out prior to removal and backfilling
b49d37c8-cb6e-501b-a4fc-a478b803a512 | note | Standard / Specification - PS 3.2
df2c9c6a-22a3-5041-8d6d-32a328bfb5ce | note | Verifying Document - Site Records
c6bf3dbd-30cf-5317-9142-90b0a2dd1c2d | note | Frequency - Prior to earthworks
f5499a7d-03ba-57c9-b1ef-2012a2864ca5 | note | Verification Activity - C
c011ed82-15bf-5f55-9f4c-d8313d37f9ce | note | Verification Activity By - SE
d94ec936-ad7a-558b-ab87-be3d2cfca838 | checkpoint | 5.01.04 - Plant Clearance
6d4d6e9c-4028-5c04-8cc4-6787c37ba964 | note | Acceptance / Conformance Criteria - Vegetation, Tree stumps, shrubs, plants, logs, including any roots greater than 25mm in diameter shall be cleared and disposed of
e513f065-fdac-5f75-a44b-2e4108a6638a | note | Standard / Specification - GWS 2.5
89f3f0b4-9bed-5b89-9ee8-bc47e57cad46 | note | Verifying Document - Site Records
dfdf7fa0-228d-51d6-a8d7-2b99f126969c | note | Frequency - Prior to earthworks
705917af-f81b-547e-848b-02cbfb8e0005 | note | Verification Activity - C
88634bea-cf7c-5452-9202-e6787e9c447d | note | Verification Activity By - SE
404c1584-e2f2-5e4b-82ac-ce76d71ee460 | section | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General
e4cd585c-3579-52e1-ab41-43c6db555cc0 | checkpoint | 6.1.1 - Groundwater Management
eb0e86e5-e733-5223-bbb9-927510d23d9b | note | Acceptance / Conformance Criteria - The Contractor shall provide all pumping plant and drainage systems required to ensure excavations are always free from water.
7e7617fa-fae5-5875-b604-3d92f1ae9a02 | note | Standard / Specification - PS 3.4
e28a6666-2864-58ac-b2be-d03fe009182d | note | Verifying Document - Correspondence
3c59ca22-9750-56f4-9528-71508147a1a2 | note | Frequency - Prior to excavation
963a9310-1758-5ef2-b107-9ca62263c7a2 | note | Verification Activity - W
6dad533d-9d56-562d-a873-7ac544b09ff9 | note | Verification Activity By - ENG
2888ef0a-7c95-5d4e-bd48-630d613dcbf2 | checkpoint | 6.1.2 - Cut to Waste Approval
4d18e52c-8158-562d-a166-7fae841d5a02 | note | Acceptance / Conformance Criteria - The Contractor shall obtain written approval from the Engineer prior to cutting any material to waste. To include evidence and extents of cut to waste. Topography survey data of all material to leave site, photographs of material and any material test reports.
e1a13489-9a5d-55a8-902e-237a7c4a31e1 | note | Standard / Specification - GWS 2.4.3
f68f05fa-aac4-5343-bc89-5a71a59747d5 | note | Verifying Document - Correspondence/Photos/Survey
db47406d-a14b-5988-af96-e4bde7d4b0ae | note | Frequency - Prior to cut to waste
1f8dfc8b-94b1-5db0-91bf-802c87634719 | note | Verification Activity - HP
d1e607a9-75e4-5ccc-9495-77974ca634ce | note | Verification Activity By - ENG
65c0bdd2-bca3-5890-b3b2-29a6b8be52f5 | signoff | Hold Point (Engineer)
5d512cb0-d81c-57fe-96ea-99a87cd34b09 | checkpoint | 6.1.3 - Foundation Suitability
8f52a174-1f14-5d9c-8f84-53832a38af69 | note | Acceptance / Conformance Criteria - The foundation on which filling is to be placed must be observed by the Engineer following clearing and prior to the placement of any filling to confirm the strength of the underlying soils is sufficient.
403a8560-3fe5-5d70-8ba0-4889dd83f554 | note | Standard / Specification - GWS 2.7
190f3aa6-7334-5f5f-a3ee-8d073c6c01ad | note | Verifying Document - Site Record
9fe9f93a-da52-5774-aa98-f6a1d17205aa | note | Frequency - Prior to the placement of any filling
49c4a9bc-2a33-58b4-aa32-18d9c49e9425 | note | Verification Activity - HP
55a75d49-9d4c-53ae-b04c-d26ae7dc6395 | note | Verification Activity By - ENG
05516c9b-7277-5725-bbb8-65d807611241 | signoff | Hold Point (Engineer)
44d96a88-c557-52f2-9d73-305345d8c03e | checkpoint | 6.1.4 - Unsuitable ground
f74e983f-b3f1-52d2-a6da-8feacdfc6948 | note | Acceptance / Conformance Criteria - Unsuitable ground shall be defined as any pre-existing uncertified filling or natural silts/clays having an undrained shear strength of less than 70kPa or natural sands having less than 3 blows per 100mm penetration when tested with a Scala penetrometer. The contractor shall obtain instruction from Engineer around extent and depth of undercut.
72b8a517-2c2f-576c-ab22-8a5927e27db0 | note | Standard / Specification - GWS 2.7
20f3605a-ef82-5349-8b91-838106d91174 | note | Verifying Document - Shear Vane / Scala penetrometer
6e495bf5-1e22-523d-9860-9240145d4445 | note | Frequency - Prior to the placement of any filling
b650b8b5-6206-5b56-9962-d2e1a99ce04e | note | Verification Activity - I
5bd7b186-b7b2-5740-b0cd-6b7cd6829b31 | note | Verification Activity By - SE
0c657410-b5a5-5209-824c-1299c15fa6c7 | checkpoint | 6.1.5 - Preparation for Filling
a6040fbd-88ee-5361-8734-01f4b7fd8f51 | note | Acceptance / Conformance Criteria - Preparation of the firm to stiff / medium dense subgrade beneath the proposed fill areas should comprise stripping of all vegetation, topsoil, any pre-existing fill materials or weak alluvium followed by benching of the exposed subgrade where natural slopes beneath the fill exceed gradients of nominally 1:5 (vertical to horizontal).
7c91a7c3-4bf8-5b9f-be81-ab10b9428ed3 | note | Standard / Specification - GWS 2.9.2
fc234cf2-875c-50a9-bd15-e27556849159 | note | Verifying Document - Site Record
22f53065-82e3-5ab6-ae5a-39840a6267b4 | note | Frequency - Prior to placement and compaction of fill
239279e4-1553-5a57-b7d5-a078fa61cec6 | note | Verification Activity - I
aa3d6ba2-bde8-57a5-aefa-e21d85e5b1ea | note | Verification Activity By - SE
5fbfc25b-ac41-5dd5-8870-2eca385a779a | checkpoint | 6.1.6 - Subgrade Conditioning and Proof Rolling
bd14a369-a5e5-53fe-af67-b8de5e4943c4 | note | Acceptance / Conformance Criteria - The subgrade shall be scarified and moisture conditioned where necessary and then proof rolled to verify the subgrade stiffness and consistency.
c9327137-4cde-584e-9d31-f301eced2c4f | note | Standard / Specification - GWS 2.9.2
5a215d15-4350-5e0a-b384-5db64abf102b | note | Verifying Document - Proof Rolling Sheet
437a76a4-fcbb-5fb8-b9c0-dba79aa678b3 | note | Frequency - Prior to the placement of any filling
5e876cd9-e4c1-583b-bce3-5c43af9e35ff | note | Verification Activity - V
51ccb122-fc8c-5e98-9471-2075d87f0242 | note | Verification Activity By - SE/QE/ENG
090dadc5-301d-552a-b293-aab6dbc64307 | checkpoint | 6.1.7 - Undercut Backill Compliance
34b385b3-2355-59e7-876f-ff44ad010bdd | note | Acceptance / Conformance Criteria - Test results for undercut backfill prior to bulk fill commencing, NDM, scala penetrometer, shear vane or cleggs, material dependant. TBC instruction from engineer. Undercut backfill QA to be filed/captured separately from bulk earthworks fill QA.
f2d5b609-ffe3-5060-90eb-b2aeb2b22cc6 | note | Standard / Specification - GWS 2.9.2
2a5ceae4-6204-56b2-af74-f7b852dc82ec | note | Verifying Document - Test Results
3d85fe98-17a1-5ba1-8548-1faff69eb73f | note | Frequency - Prior to bulk fill commencing
ec2b9ddc-86b4-5199-a84a-b585302e0d67 | note | Verification Activity - R
f06ec382-6ae1-5540-b7b0-49c345564686 | note | Verification Activity By - SE
c9bbd24f-6b19-57f9-91fc-1ac6c8d49ec3 | checkpoint | 6.1.8 - Topographic Survey
a5561c5b-ca9e-5395-be42-bdfcd8eb8c4f | note | Acceptance / Conformance Criteria - All subgrades and undercuts to be captured via topographic survey (GPS)
972f635b-ad00-5e9d-a764-3df28e80d140 | note | Standard / Specification - PS 2.2.12
67096b30-70fa-568b-8ca7-5c4476661a15 | note | Verifying Document - Survey Results
f665dbf1-e4ae-555a-a155-8f872335b31f | note | Frequency - Prior to cutting or filling.
4e3075c0-3f73-5c5e-acea-53b9ff9dc3aa | note | Verification Activity - R
0dd85854-02b3-5db4-9210-0eb8f56a5c43 | note | Verification Activity By - SE
2b19974b-beb5-5ee1-ac63-a62d27aebcc0 | section | Stockpiles
17f3c35f-f53f-5024-885d-1b98e7d342ad | checkpoint | 6.2.1 - Stockpiles
bef39443-7d85-52f7-8d0c-66f2e56b1f58 | note | Acceptance / Conformance Criteria - The location of all temporary stockpiles must be approved by the Engineer prior to placement. Where stockpiles cannot be avoided above sloping ground, they should be placed over a wide area with the height restricted under the direction of the Engineer.
25ca6fa2-218e-58ee-bfc3-2c5a7c30c9df | note | Standard / Specification - GWS 2.9.3
0234ee50-2cac-5b79-8bc4-e97d89f84622 | note | Verifying Document - Stockpile Map
db7cde91-35c2-5185-9e3b-b29a79f2176d | note | Frequency - Prior to placement.
48298222-1d4e-5d30-932c-06dd5fa4628d | note | Verification Activity - HP
1497dad8-abb9-5023-a8ca-f94c8ff694a8 | note | Verification Activity By - ENG
2bf26bc7-1a18-562a-8703-832bc250e5d6 | signoff | Hold Point (Engineer)
2192d811-69e9-5a25-bb8c-201a8e17f817 | section | Earthfill
f119c352-904c-5f3f-8f85-ce61625e357e | checkpoint | 6.3.1 - Earthfill Placement and Compaction
286ede01-a444-59af-8320-caa3012c88cc | note | Acceptance / Conformance Criteria - Earthfill must be placed, spread and compacted in controlled lifts under the direction of the Engineer. All earthfill must be placed to ensure adequate knitting of successive fill lifts by ripping any surfaces that have become dry prior to placing the following fill lift.
b3cf298a-4b4e-50e8-92bc-e06a06b5c243 | note | Standard / Specification - GWS 2.9.4
0ba917b5-eebf-5035-abc0-0e37abe8cbed | note | Verifying Document - Site Record
0e81b6c5-9757-515a-b91b-e69f20515b83 | note | Frequency - Per lift
d3f4f4d1-826c-579d-b32f-e6b543e41cf7 | note | Verification Activity - HP
4406eb78-5b4b-5bc2-ac14-4fb5ba61d892 | note | Verification Activity By - ENG
1e7f594d-dcca-55b1-b520-89726427772b | signoff | Hold Point (Engineer)
51bbabf3-a2ac-517d-96c6-d269197bde8f | section | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
3628e322-55b2-56ab-85b5-2aca3175c1e0 | checkpoint | 6.4.1 - Proof roll Testing
81e47988-85b7-532a-bae1-1a12e72c1d69 | note | Acceptance / Conformance Criteria - Each layer shall be tested via Proof roll to: 7mm maximum impression
881f0569-d51a-5ef7-8ef0-d3678621cee8 | note | Standard / Specification - GWS 2.9.4
71c058e2-0e0e-5335-9f4a-00d696132c0b | note | Verifying Document - Proof Rolling Sheet
d2cdd97d-44a2-54ec-8461-90172cb8a3be | note | Frequency - 100% of each layer
a3cf788c-318e-5cbc-adc4-8104048747c7 | note | Verification Activity - I
a6b88ab0-b9d8-5dd7-8d79-5c1cdfb29ad2 | note | Verification Activity By - SE/ENG
28d9577b-1def-5be9-a5ae-0130db5993ab | checkpoint | 6.4.2 - Compaction Testing
0361ad6d-e77a-5d58-81fe-394dbecd915c | note | Acceptance / Conformance Criteria - Bulk fill shall be tested by DT at 300mm probe depth 95% MDD. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick.
702d3671-8874-54ae-904e-c2b546422874 | note | Standard / Specification - GWS 2.9.4
84133fc7-b8f9-55b3-a993-09885b7c8b41 | note | Verifying Document - Test Results
9d017020-3c0e-553d-b800-f863103cd6c3 | note | Frequency - 1 set / 500m3 (1 set to include 1 x 0.5m deep Scala and 1 x DT within a 3m radius)
e73f6f4f-173e-5265-a670-bd32cc5dbb1d | note | Verification Activity - R
2c57898f-d1f2-505a-abc6-d6dda53bcda1 | note | Verification Activity By - SE/ENG
65b26fb1-8ee6-524e-91c3-159b39e4b199 | checkpoint | 6.4.3 - Scala Penetrometer Testing
f1331738-3f66-562e-aab4-9f1c14cd166a | note | Acceptance / Conformance Criteria - Bulk fill shall be tested by Scala Penetrometer every 500m3 to: 4 blows per 100mm. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick.
3ecfb16a-a9fc-5056-9e5c-bed455d0694e | note | Standard / Specification - GWS 2.9.4
e7df00a3-4bb3-5329-b09e-c11d8a7e7f46 | note | Verifying Document - Test Results
c5a4782b-328c-5561-92b4-2ad8f96d9ddf | note | Frequency - 1 set / 500m3 (1 set to include 1 x 0.5m deep Scala and 1 x NDM within a 3m radius)
3b2bf319-1640-5979-bca2-736dc8f5952c | note | Verification Activity - R
11826f75-4718-5556-89d7-4887d9c2d9d7 | note | Verification Activity By - SE/ENG
cc08febf-128a-537b-80e4-30bf18b2dac8 | section | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend)
1d857413-cd45-5e2e-ba04-4e49e77f5ba8 | checkpoint | 6.5.1 - Vane Shear Strength Testing
dbbc0a18-ae6a-5cf7-9ce0-18ec7a7ed771 | note | Acceptance / Conformance Criteria - Bulk fill shall be tested for Vane Shear Strength to: Minimum average 120kPa over 10 tests, minimum single value 110kPa. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm.
36bcc3d7-db98-5639-af85-741172812629 | note | Standard / Specification - GWS 2.9.4
251ea5e9-0ef2-5550-9457-1743ce45a70b | note | Verifying Document - Test Results
1d857961-37ac-5b77-a66c-91f514f529e0 | note | Frequency - 1 set / 500m3 (1 set to include 5 x shear vanes and 1 x air voids within a 3m radius)
56d13354-9e3c-5cfb-91f0-04b5ea52b5e7 | note | Verification Activity - R
2f5aef00-2b4f-5282-a689-66479c32e70b | note | Verification Activity By - SE
80b3b8a5-692f-561b-8930-bca892c54e74 | checkpoint | 6.5.2 - Air Voids Testing
9901dfd8-8abf-5c33-9555-ffa623f92f70 | note | Acceptance / Conformance Criteria - Bulk fill shall be tested for Air Voids to: Maximum average 10% over 10 tests, maximum single value 12%. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm.
f3da272a-2c60-5787-9a8d-72ddfd15ed6c | note | Standard / Specification - GWS 2.9.4
36bf09f3-2f3e-56ec-8617-e97bc6b90620 | note | Verifying Document - Test Results
0a4d47d7-3840-5c0a-a55d-504f47de1df7 | note | Frequency - 1 set / 500m3 (1 set to include 5 x shear vanes and 1 x air voids within a 3m radius)
c3c6cc28-d947-5fc1-bac2-97a43d11f29e | note | Verification Activity - R
8267f1ef-1ee0-56f7-bf44-85d36163dbe2 | note | Verification Activity By - SE
7d5b1c9a-3904-5ba1-84d5-335eb6c5663d | section | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
91de5557-94fc-563b-8e74-6032ee8dec93 | checkpoint | 6.6.1 - Proof roll Testing
b633fc11-6f49-5738-ae16-b70fd989c7e5 | note | Acceptance / Conformance Criteria - Each layer shall be tested via Proof roll to: 5mm maximum impression
bde7cd76-353a-543d-81ea-5b47ef0877e2 | note | Standard / Specification - GWS 2.9.4
2f034ce5-f965-53c1-9f07-ab3c43bb4201 | note | Verifying Document - Proof Rolling Sheet
bbc95283-876f-534a-a57e-454ecf07ca08 | note | Frequency - 100% of each layer
b884386a-1912-518f-82fa-88e7ffc3a8ab | note | Verification Activity - I
a9e47c7c-12af-5d6a-a677-b116b4721333 | note | Verification Activity By - SE
06b7dc4d-9fe4-54e2-be84-0fc93ed0deaa | checkpoint | 6.6.2 - Compaction Testing
72f4e1d4-2714-5bad-b61b-a89df2751088 | note | Acceptance / Conformance Criteria - Subgrade fill shall be tested by DT every 500m3 to: 98% MDD. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm.
90c5da6a-fd57-519a-af68-7f03ff4eeae2 | note | Standard / Specification - GWS 2.9.4
65582f1c-08a9-5ed4-9cca-7ae57b6fd2b2 | note | Verifying Document - Test Results
7d1f3f80-e554-5f08-8f36-5f61dd240c55 | note | Frequency - 1 set / 400m3 (1 set to include 1 x 0.5m deep Scala and 1 x NDM within a 3m radius)
fb7d72f3-6266-5d2f-a84a-b8ef5a9bfb43 | note | Verification Activity - I
abf82fab-4d37-580d-834e-df632b56edbd | note | Verification Activity By - SE
b5a557cc-1d11-5a26-a9f0-d4d9f12c9eb1 | checkpoint | 6.6.3 - Scala Penetrometer Testing
fa73c0bd-67ed-5c81-b9f6-bcf874f36e76 | note | Acceptance / Conformance Criteria - Subgrade fill shall be tested by Scala Penetrometer every 500m3 to: 5 blows per 100mm. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick.
b52aed14-7a5f-5c32-b592-ad178c6a4ba8 | note | Standard / Specification - GWS 2.9.4
cbf75fa7-f933-50e9-81ab-d8fe0557bba2 | note | Verifying Document - Test Results
7c9d20af-a460-54be-8d2d-db9494b4edc4 | note | Frequency - 1 set / 400m3 (1 set to include 1 x 0.5m deep Scala and 1 x NDM within a 3m radius)
d6175d17-dc53-576e-92fe-4c625f891373 | note | Verification Activity - I
b98e763c-d8e0-5357-ab9e-fbe30cc17c2e | note | Verification Activity By - SE
226b41af-6a03-486d-89fb-bcb8788d3e0a | section | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
6011d492-ae66-5da1-a554-20d696e97488 | checkpoint | 6.7.1 - Shear Vane Testing
97b9b3e5-db79-59b2-b466-0b008ccff789 | note | Acceptance / Conformance Criteria - The Cohesive Fill shall be tested by Vane shear strength to: Minimum average 140kPa over 10 tests, minimum single value 120kPa
5caf5c28-8adb-5986-ac40-117c055eb178 | note | Standard / Specification - GWS 2.9.4
08babd25-b5e1-5a0e-ab73-99303ff9fc43 | note | Verifying Document - Test Results
e2d0c240-a3cd-5182-a990-b731d77ba303 | note | Frequency - set / 500m3 and every 0.5m lift (1 set comprises 4 x shear vanes and 1 x air voids within 3m radius)
76397b3a-dd0b-59ae-b0c7-b18f4785fcd5 | note | Verification Activity - I
cb0b7c5b-f49c-59af-ab6f-04fa7cf3847b | note | Verification Activity By - SE
4a52de1c-d79a-5f08-90c6-db4398518336 | checkpoint | 6.7.2 - Air Voids Testing
4db17005-7815-5b97-af65-a2d559d0b55c | note | Acceptance / Conformance Criteria - The Cohesive Fill shall be tested for Air Voids to: Maximum average 5% over 10 tests, maximum single value 6%. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm.
9e4e2f34-58e8-5cba-8f25-809593f7e3b4 | note | Standard / Specification - GWS 2.9.4
b94e47d1-f994-5e12-9c5a-ca666b8a440e | note | Verifying Document - Test Results
33c1e730-fd7a-5790-b721-486d1a8144f6 | note | Frequency - set / 500m3 and every 0.5m lift (1 set comprises 4 x shear vanes and 1 x air voids within 3m radius)
8f1e6d8b-95ee-55cc-ab21-e7ba2bff47aa | note | Verification Activity - I
b2000c16-2302-5b4f-a14b-e4c0f973756c | note | Verification Activity By - SE
cfea36e2-72da-5eb6-8f4c-85af1908ec79 | checkpoint | 6.7.3 - Water Content Testing
5a8fb55b-62f9-5e81-87cf-23c8f3f5f47e | note | Acceptance / Conformance Criteria - The Cohesive Fill shall be tested for Water Content to: Minimum 2% dry and maximum 6% wet of optimum water content. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm.
04845150-aafd-5748-987d-ec3e37a628f5 | note | Standard / Specification - GWS 2.9.4
a24404f7-d7be-5b60-acf0-37f389166146 | note | Verifying Document - Test Results
b4089446-2691-5cae-af41-2c84000040ba | note | Frequency - set / 500m3 and every 0.5m lift (1 set comprises 4 x shear vanes and 1 x air voids within 3m radius)
607ffd22-9ae7-5e38-92d4-cdfc2d60fd38 | note | Verification Activity - I
0eb417e8-c6f3-58b8-9ce6-33a9fbcc8a53 | note | Verification Activity By - SE
f2ef1e0d-4c71-51b5-b671-5bbd19f04b08 | section | Cut Batter
344471b0-ed20-5733-9b72-3ab5307d3074 | checkpoint | 6.8.1 - Cut Batter Inspections
4d324204-dd12-5e34-b757-a5805d8ba4ae | note | Acceptance / Conformance Criteria - The Contractor will need to regularly inspect the exposed soils and check for any seepages that may occur due to the layered profile of the natural soils. All inspection records are to be submitted to the Engineer within 24 hours.
2759f9f1-0521-5f18-9d18-423ac5f16661 | note | Standard / Specification - GWS 2.9.6
ce5cab41-2c26-5482-96c2-3d22d43139ce | note | Verifying Document - Inspection Programme and Records
5c505c18-e993-51f7-949a-5b47156856cc | note | Frequency - Submitted to the Engineer within 24 hours.
a43347cf-95d7-5b0a-9e04-e6157f5a29d0 | note | Verification Activity - H
eb00df9a-b10b-5382-9e6b-464ee4e94717 | note | Verification Activity By - SE
8d672582-9e3e-536a-a565-c2a9b85d6ab5 | checkpoint | Cut Batters- temporary cut
82b32635-e0da-5dbe-96c9-9eb5a24df6f3 | note | Acceptance / Conformance Criteria - The temporary cut buffer shall be maintained for 2 weeks to see if the seepage drains out, after which it may be cut to the final profile or additional drainage measures installed subject to review by the Engineer.
73e4728b-5fd1-5e00-a3de-757a7f39c0e9 | note | Standard / Specification - GWS 2.9.6
d4b60330-816d-503d-8f99-630ff7c072c6 | note | Verifying Document - Site Record
f141fdc1-eaa1-5721-93e2-10a3bf9531bd | note | Frequency - Each Cut Batter
08a7b0a1-3bd6-52cb-a687-8fd6eec5a3ed | note | Verification Activity - I
b7d155b5-2a16-51db-b7e9-418daa45c1cb | note | Verification Activity By - SE/ENG
13a6ac74-1741-5e78-a060-6ff18a0ba665 | section | Surcharge Fill
dc74b895-83a7-5278-8bbb-885f83b87f5b | checkpoint | 6.9.1 - Surcharge Fill Installation
f8d6420c-f10e-5e92-8f1b-1938b79fc563 | note | Acceptance / Conformance Criteria - Surcharge filling shall be placed, spread and track rolled in 300mm layers. Surcharge fill will only be required if the settlement monitoring results exceed what was anticipated in the design. Under Engineer’s direction.
bea58f9c-832b-54dd-91d1-7738ce2a1847 | note | Standard / Specification - GWS 2.9.7
11e1b7c8-63f1-5b19-b041-37ef1a1a8150 | note | Verifying Document - Site Record
be46eeb9-b88f-5e12-adb3-e15853fa82ea | note | Frequency - Per 300mm layer
89c48506-43db-5c3d-aa52-bf114025d184 | note | Verification Activity - I
ac13cdb7-dc86-52f2-b78a-f98e874d68bc | note | Verification Activity By - SE
3362fc22-d85b-5472-a551-b29831ecf61f | section | Respread Topsoil
675454bd-86af-52a4-90b9-4d92fe27414d | checkpoint | 6.10.1 - Topsoil Respread on Steep Ground
612645e2-276d-5142-9b35-0c856ea5d03c | note | Acceptance / Conformance Criteria - On ground steeper than 1V:3H the surface should be roughened under the supervision of the Engineer prior to topsoil placement.
6e7f7b5a-7ed7-5cf2-9964-ab15f2fd2dfc | note | Standard / Specification - GWS 2.9.9
f6c2c4c1-e3aa-52d0-b069-b8bfb728a650 | note | Verifying Document - Site Record
28b6f014-6695-5478-a0ab-d75596c438bf | note | Frequency - Prior to topsoil placement
27f50561-beb4-53c0-85fd-f9ca434bb6ec | note | Verification Activity - HP
b0f3ff82-752c-51a9-aaa9-99a25793f796 | note | Verification Activity By - ENG
1d1cc3d7-34c3-545b-8ccd-3653008dd3e5 | signoff | Hold Point (Engineer)
a28f508d-7873-4cf5-aa58-62df4f066743 | section | Subsoil Drainage
60dea67b-10ef-56e6-a440-025a78fbac7a | checkpoint | 6.11.1 - Filter Cloth Wrap Inspection
e85fb9f6-7d2b-513a-bd83-0e4c00c9f8d7 | note | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain.
246d901e-41b6-508b-a982-d57b285d48f6 | note | Standard / Specification - GWS 3.2.2
14272c52-0910-574a-8e68-1a008caaea01 | note | Verifying Document - Site Record
4b416b83-4d74-5080-9f4a-780e2dd7ea80 | note | Frequency - prior to backfilling
b07a666c-cab0-5dc9-b74a-e8928840c5da | note | Verification Activity - HP
2a503a6b-ecda-532e-8198-34ada9d17cca | note | Verification Activity By - ENG
0d3a7fb3-9b6f-5112-873f-0d6ca9de26e1 | signoff | Hold Point (Engineer)
49d7e32c-154f-59ea-b421-fd8abab9d209 | checkpoint | 6.11.2 - Trench Backfill
9be62d94-669d-56c5-98df-f0655e525d22 | note | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard above
9943da35-02d8-5462-9871-d8df0642290e | note | Standard / Specification - GWS 3.3
14fbb3eb-8b9a-5333-af1a-fb278cb4f91d | note | Verifying Document - Site Record
71250cca-3f46-5d4d-8b23-78956c6b7201 | note | Frequency - Each trench
63f9d961-89a4-582b-8e63-ba924b5a4aa5 | note | Verification Activity - I
e9ff29db-9280-5bcb-8127-113818b5c8f5 | note | Verification Activity By - SE
b5153075-1228-599c-8105-75e3c1df8afa | checkpoint | 6.11.3 - Drainage Outlets and Inspection Points
e249ae11-1c7d-5447-bc71-995f46050380 | note | Acceptance / Conformance Criteria - At least one temporary flush point is required for each subsoil drainage system to enable flushing of the system once the earthworks are complete.
e46ceacf-cb8b-505d-8b15-1dc555be327f | note | Standard / Specification - GWS 3.6
85052b17-54d4-5a95-9cbb-ef0d6c71f674 | note | Verifying Document - Site Records
5ba4c355-4959-5072-8fd9-0aaf4250d5fb | note | Frequency - Each Subsoil Line
8a2d0f43-d8cf-5b99-be4a-77de64ccae73 | note | Verification Activity - I
ee8b451c-21ab-5f86-ba49-8c33a487de18 | note | Verification Activity By - SE
16e0a2a8-3ab2-5d22-ab09-f770bceda824 | checkpoint | 6.11.4 - Subsoil Flushing
ac40c030-449b-542a-af1b-0220426fe171 | note | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer.
b407e655-141b-5767-955c-3c2aa89b6d64 | note | Standard / Specification - GWS 3.6
e23d0fc8-d955-5bdd-9a2e-739dea834f0e | note | Verifying Document - Site Records
08a98415-27ac-5d92-accf-d6f9681783cf | note | Frequency - On completion of earthworks
8c87024e-7a19-523d-9d24-d7539bbdb6c3 | note | Verification Activity - HP
4f23f32d-52cd-557e-8dc4-002c5a2eda2c | note | Verification Activity By - ENG
4d0d1afd-4388-5c88-a38a-c74d25c23729 | signoff | Hold Point (Engineer)
b9013253-72a7-5b8d-bd30-a533437504c3 | checkpoint | 6.11.5 - Survey
157333d0-9f65-58aa-be41-2fc45a3a2cdd | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
1b3f7c5e-1e01-5a0e-a9e7-06bc3b3a5f3a | note | Standard / Specification - Downer
a335245c-0a90-5993-a7e9-27775cd90fca | note | Verifying Document - Records
ef32fdb5-96c4-5a3f-8230-c5c1f956c7f7 | note | Frequency - Post construction
343e4729-0a43-541b-963c-5e036c02f45f | note | Verification Activity - H
74b2f7ff-37a5-576d-8c7d-82789d0323f5 | note | Verification Activity By - SV
713c444f-8eee-43d1-883c-38dcfda68142 | section | Geotextile and Geogrid
1d37a543-483b-546a-8497-529e1f2639b5 | checkpoint | 6.12.1 - Geotextile Installation and Lap Length
76225046-1c0e-5471-957a-bb64165abba8 | note | Acceptance / Conformance Criteria - All geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets.
66d8fa5b-a442-549a-bea5-c3cb7452c2ad | note | Standard / Specification - GWS 4.1
de2fd70a-1a13-5c27-a39c-70f8eed0732e | note | Verifying Document - Site Records
c2acaba6-1ca8-5cac-8371-503ab5be89c7 | note | Frequency - Between each sheet
0067de7e-b9fc-5b67-8136-0342c39ff969 | note | Verification Activity - I
f5d827bb-f426-5371-a150-e95a31726758 | note | Verification Activity By - SE
a7c0d67c-1e3c-507f-bbb8-8d4fb78ed76b | checkpoint | 6.12.2 - Geotextile Inspection
5fce79e7-daa5-53c5-ad32-308b9a5bc3c4 | note | Acceptance / Conformance Criteria - Before placement of any geotextile should form an Engineers inspection hold point
b95f0b90-c3e4-514b-835d-2f189a655d86 | note | Standard / Specification - PS 2.2.16
f3c2b170-0327-54e3-b456-bc5cc93ab321 | note | Verifying Document - Site Records
b2d0e962-99a2-5b14-8134-5a715d35b1d2 | note | Frequency - Min 48h Notice
4ca5ca69-f231-5784-abee-83eeca3a889b | note | Verification Activity - HP
a8b167fb-fa63-5a5a-a9b8-2948ec01afe8 | note | Verification Activity By - ENG
e935c170-7db3-5df1-a707-7b58b919ad66 | signoff | Hold Point (Engineer)
3c2d33c0-e5f3-5aea-a629-633a37922b59 | checkpoint | 6.12.3 - Geogrid Prep Inspection
08108f8c-c97e-553e-9698-ffa2ad50e42c | note | Acceptance / Conformance Criteria - Prior to placement of the geogrid, verification of the grade, length, orientation and layout is required against the drawings.
5123368d-8f9e-559a-b60f-86578ebb8743 | note | Standard / Specification - GWS 4.2
80170ccc-66d3-58b2-b5d7-f14349acad85 | note | Verifying Document - Checksheet / Survey
0a1db885-bc81-5f42-85ea-012546cd27bf | note | Frequency - Prior to placement
d17f58fa-a7fc-5a1b-a210-e9612db174c1 | note | Verification Activity - I
b5070777-cb7a-5829-bc76-2a395a322d46 | note | Verification Activity By - SE
d675d858-cd9a-4121-93d5-bf1e0515fd8b | section | Settlement Monitoring
43fcc8d7-6125-53b6-9a5b-035d7dea05ea | checkpoint | 6.13.1 - Settlement Pin Installation
99a3f15f-8fc2-5bf6-9524-d6389239a71b | note | Acceptance / Conformance Criteria - Protective waratahs and coloured flagging shall be installed around all settlement pins for protection. Settlement pins shall be installed within 24 hours of reaching design subgrade level.
2f1d0c7e-7ded-524d-9789-d329ecdea150 | note | Standard / Specification - GWS 6.3
7a072403-7d6d-584f-b3d8-2d79756c7e87 | note | Verifying Document - Checksheet
248f1536-fe7a-5a91-887f-1bd1ed65900a | note | Frequency - within 24 hours of reaching design subgrade level.
b4f59ffe-eb6b-5ea4-80c8-cf2ba8ab3538 | note | Verification Activity - C
0cef5e12-9dee-51e8-b40d-6b3fb1589e5d | note | Verification Activity By - SE
b303cc8d-cc79-55b4-a909-2d00242f9edd | checkpoint | 6.13.2 - Settlement Survey
112e7f80-767f-5636-946f-3932d2c8e479 | note | Acceptance / Conformance Criteria - Survey measurements are to be undertaken regularly by the Contractor as specified on the drawings, to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
212ea4ee-e52a-546b-808c-745bac8d928a | note | Standard / Specification - GWS 6.3
f1489eab-003c-5a56-a03f-13ad0877b9b2 | note | Verifying Document - Both paper and electronic formats
571d823b-77b5-53aa-8f3b-cc51567a9717 | note | Frequency - within 24 hours of each reading.
d4b9d21a-a50a-5a45-8ad8-0771fa0b609e | note | Verification Activity - H
539fae9f-0f46-5cb7-ac3e-84c6f799cda3 | note | Verification Activity By - SV/SE
cb2f4838-a069-568a-bec3-af9d57ca1e5e | checkpoint | 6.13.3 - Retaining Wall Settlement Targets
b493ddef-686b-59cb-a6fa-20ce8a77e630 | note | Acceptance / Conformance Criteria - Targets shall be fixed immediately after completion of the first row of retaining wall blocks at each location and the initial baseline survey reading made prior to the subsequent row of retaining wall blocks placed.
3eeed169-5910-546d-849f-0c6770ded3bc | note | Standard / Specification - GWS 6.4
4fa0ca17-2e43-50c7-8881-fe23558af58b | note | Verifying Document - Checksheet
90ae0198-a4e3-5455-90ed-a258561cd1fc | note | Frequency - prior & after completion of first row of retaining blocks
be7c7a7f-d127-535b-ad98-78270c9a6907 | note | Verification Activity - I
a8e6571c-2ea6-520b-b643-50014469a9b8 | note | Verification Activity By - SV/SE
7d2dc634-7e36-5133-8be8-f2ca2cd3e99d | section | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities
2b19c0a6-1f40-54a8-bd0a-961674cf52c7 | checkpoint | 8.1.1 - Construction Record Compilation
9e865959-c88a-5190-9f5f-9aead8c19ce6 | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
f4dfd5a4-d771-5aff-a69f-4c87ca9911bb | note | Standard / Specification - Downer
89b72ad1-0a2c-5e13-a797-a0d4a5b77ccf | note | Verifying Document - Records
855af0eb-08d2-530f-a975-5f08114d94c3 | note | Frequency - Post construction
0c644f99-c56e-54d0-b27f-54f286afe727 | note | Verification Activity - H
271d3bf3-544b-50e2-a020-72c91450dfda | note | Verification Activity By - SE
87cddc19-8875-541a-8ee5-925099bb07f2 | checkpoint | 8.1.2 - Survey Records
e04a5f03-809c-5321-856b-6c14bbe078c7 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
ea054228-80af-5478-8e11-c723f5ec1539 | note | Standard / Specification - Downer
fcc41489-f8ba-5261-96c6-b0f25fa9d847 | note | Verifying Document - Records
0e8d161d-391b-5bc0-a9cf-621caa90b000 | note | Frequency - Post construction
606b5e65-7591-5355-8b6f-2c9e2ee4738f | note | Verification Activity - H
a10d33be-0636-5363-b915-0104e692bbbe | note | Verification Activity By - SV
274b2337-f656-5f3f-b183-089ebbccbb69 | checkpoint | 8.1.3 - Redline Drawings
c8dc263f-8b1e-52a7-beee-97d562069bee | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
e3d9d811-9f48-50aa-ad2d-fbcb143b84ad | note | Standard / Specification - Downer
c8d3d189-33f3-5e6e-a349-a2f6a1c86fce | note | Verifying Document - Redlines
bb6a84e8-3c2f-500a-8396-acf0711ef71f | note | Frequency - Post construction
fbb1edf2-dd6f-53ab-abb0-02caa90ae961 | note | Verification Activity - H
c8c2a577-65bf-5aed-9279-6ba112957dfc | note | Verification Activity By - PE
35c4da15-00e2-5c64-9258-453572b5f83e | checkpoint | 8.1.5 - Photos
94e37964-f4ea-55f7-843c-d9cff1cab647 | note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
4bbb697c-8d21-5a96-8dda-190c8bb6e3e5 | note | Standard / Specification - Downer
613458d8-44b8-5f7b-aa36-ddd3ce4f2886 | note | Verifying Document - Photo Records
706b1d90-4936-5f76-ab5e-a6ac12da6b19 | note | Frequency - Post construction
88958877-a040-53a7-a425-18f857a2b216 | note | Verification Activity - H
b80fc67a-8a18-5aef-addc-224f7da47377 | note | Verification Activity By - SE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
43896042-f281-455c-9e72-1032e80eb495 | checklist | ITP - Fencing Rev C | itp | ITP - Fencing
4162ffe1-90dd-4da6-a8f0-66cc8f503259 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
103cb27b-3a8a-491f-8a8a-9af9063a333f | checkpoint | 3.01.01 - Survey Setout
553ca973-7a1f-56d0-8424-195373e8a172 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
52935328-a210-5407-87be-3b5259633fe9 | note | Standard / Specification - Downer
0534b7b2-9a46-5bd7-89cf-279cf7296770 | note | Verifying Document - Survey Records
524d6ae0-87c2-5323-867c-db1d2777c186 | note | Frequency - Prior to Works
c26a23b6-a11b-57bd-9c38-9b5ddff53a20 | note | Verification Activity: Activity - H
bec65572-4c27-5637-b6c6-1ae9bd603377 | note | Verification Activity: By - SV
777e07c5-f31e-43db-a5e0-d220ed436a8e | checkpoint | 3.01.02 - Service Location
c7d025af-861b-5771-8924-3422e6062787 | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
c07a40d9-7664-5be6-b40f-34c91e9ecc1f | note | Standard / Specification - Downer
55a050bd-6928-5d8b-9ea7-92fe0c8cea89 | note | Verifying Document - Excavation Permit
b9d6e66f-46e1-55eb-875b-039e8e603944 | note | Frequency - Prior to Excavation
19ce816d-1283-58f8-9e4b-5dcc50b2f276 | note | Verification Activity: Activity - H
3c2f679f-4617-5714-8940-08fcd3a7ef84 | note | Verification Activity: By - SE
d37cf465-9a17-4473-a169-f390729fff31 | checkpoint | 3.01.03 - Internal Permits
5cf4c362-7c66-5891-ad50-f4d8de9eff4d | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
5d3242ae-ceda-5322-938f-23bef75d7d98 | note | Standard / Specification - Downer
4926346f-ab90-50fb-a91a-2c9ffcfd0519 | note | Verifying Document - Internal Permits
2028c628-dbcd-54d1-b4f6-f2e39ad10089 | note | Frequency - Prior to Excavation
51616f38-de7a-5fab-bc10-1535b4b68169 | note | Verification Activity: Activity - H
bec9f510-eb9b-51b7-a9fe-e2492d8ab415 | note | Verification Activity: By - SE
0742187f-0577-4b39-a2a3-88f28ce01745 | checkpoint | 3.01.04 - External Permits
93786611-ddae-5b25-81dc-e4c5912a4b50 | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
b58b1811-cdf5-55f9-9205-4e6a380b6f5d | note | Standard / Specification - Downer
67532a2a-ea6a-5e9e-888a-e662339653e3 | note | Verifying Document - External Permits
53f3fd70-c4cd-5c99-ba88-f1b4d17cea0d | note | Frequency - Prior to Excavation
719f2a5a-765f-572e-bd7c-61f65fe26a6b | note | Verification Activity: Activity - H
66cb95d9-fb21-5e19-b756-a0748827c30e | note | Verification Activity: By - PE
8f6856ca-2f55-44b2-8b61-fae8e5852b95 | checkpoint | 3.01.05 - Approved Construction Drawings
21461fce-d033-56ed-822b-6ecec3e9fed2 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
ff74fdb0-b7df-5215-b907-fd2aed1dd1ff | note | Standard / Specification - Downer
b3690d9b-d9d9-54a2-86f9-5a1c4ca43e98 | note | Verifying Document - IFC Drawings
6805a13d-aee2-50c8-bc80-50dda00dfd34 | note | Frequency - Prior to works start
37546784-2e23-5e0a-a040-3f4a7daf2001 | note | Verification Activity: Activity - H
1bca08f7-40b5-537f-bfbd-c2404c321e76 | note | Verification Activity: By - PE
be09473f-d7c6-41cb-a52e-919ee2d99e8a | checkpoint | 3.01.06 - Subcontractors
5a037352-35f4-5e61-bc8b-d7207e4be8a4 | note | Acceptance / Conformance Criteria - Ensure that subcontract and supplier agreements have been completed.
509f0768-f053-5690-8a0a-c8263161eb6f | note | ○ All subcontractors have been inducted.
cbe89e95-2fc6-5de8-abef-e38e394144f9 | note | Standard / Specification - Downer
541022ac-a579-58db-aa3b-73848b09a17d | note | Verifying Document - IFC Drawings
0792e346-9385-5240-9727-e68da5037304 | note | Frequency - Prior to works start
53c7b732-c6d3-5c42-9bc6-48edb111391b | note | Verification Activity: Activity - H
05b1d26d-4fab-5308-bc06-c19c4bf2c08a | note | Verification Activity: By - PE
ab4b709d-6c1e-4786-bcf0-e5bafdec220b | checkpoint | 3.01.07 - Pre-commencement Meeting
f6fa5b99-5a60-5da8-901c-6c057426be8f | note | Acceptance / Conformance Criteria - Unless advised otherwise, pre-commencement meeting will be conducted with designer and contractor to determine final location of fencing. Contractor to co-ordinate all fencing alignment and fencing accommodation works with Engineer, HCC Representatives, and Landowners including on- site meetings.
c8bbca06-2e66-5f4e-a16e-ee288e7b8a43 | note | Standard / Specification - Project Specification
1ac2e51e-ec9f-5a1c-8fbd-a9253a6874b0 | note | Verifying Document - InEight Correspondence
93cabeb5-8c89-5ec0-86a6-573cf1d8342c | note | Frequency - Prior to works start
a58846f6-549f-599d-83e6-973d195f56ed | note | Verification Activity: Activity - HP
386408a4-d991-5eb2-b9ee-a89b6eb33f70 | note | Verification Activity: By - ENG
59cf74c5-c090-4b38-8d83-27a09393ea3d | signoff | AUTHORITY HOLDPOINT
40370f59-f8ae-4f4f-b0c7-4776fb5b8df9 | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
5a543f3e-cefb-4140-af9c-0db3d27bcdd3 | checkpoint | 4.01.01 - Timber Posts
6911f4b0-b48c-5dd4-96d3-11e70dd1c26b | note | Acceptance / Conformance Criteria - Brand new 1.8m long H4 treated no. 1 grade full round posts.
9c84758f-d586-53c6-9045-9ec6526ea6e3 | note | ○ Or equivalent as per "2016 Conventional Farm Fencing Taratahi" guide.
33d0197c-8d61-5ba4-9bcf-bf0c5c2ce828 | note | Standard / Specification - PS 2.1.2 Fencing
680f4d89-0697-5f42-91d5-1f65f627f78f | note | Verifying Document - Dockets
ba41a470-1f22-5b1a-a66c-c4926ebee3bd | note | Frequency - At delivery
9d5c71b7-43f9-5224-a1b0-1ca5a052b5c0 | note | Verification Activity: Activity - H
a53bb226-1504-54c8-a115-b013366cffd7 | note | Verification Activity: By - SE
5648003d-ca2c-4dfd-91e0-b065ee1da9ef | checkpoint | 4.01.02 - Timber Battens
2df5588d-0428-54f9-821c-486bd02322fd | note | Acceptance / Conformance Criteria - Brand new 50x50 H3 treated battens between each post.
e4a25d04-4ffa-598e-b83e-8cb2e05b8db8 | note | Standard / Specification - PS 2.1.2 Fencing
dbba8e5f-6a33-5df6-b1d8-cc47cdf7923b | note | Verifying Document - Dockets
48558a1c-57d4-555b-bf54-38bde3172c2d | note | Frequency - At delivery
4301c027-d288-5862-b255-2a5116cac8fc | note | Verification Activity: Activity - H
feb12fe9-1dda-5c94-b7c9-8c36f704e7bf | note | Verification Activity: By - SE
5f2931bf-cde7-41c1-ad7a-fecca425393a | checkpoint | 4.01.03 - Wire
4917cd3b-ef87-5c39-b8f9-cab92adaa630 | note | Acceptance / Conformance Criteria - 2.5mm galvanised steel high-tensile 7-wire.
126ba3b9-ea55-53b9-91fb-b34eb124c65a | note | Standard / Specification - PS 2.1.2 Fencing
ecb6268f-9006-5849-9b53-aa842e07af83 | note | Verifying Document - Dockets, Mill Certs
339606d8-3952-5679-be87-0d55fba05ba8 | note | Frequency - At delivery
e575ff56-a239-559a-9688-a05697c54cd1 | note | Verification Activity: Activity - H
fadbbced-944c-50e7-bb1a-c89c3adcf1c1 | note | Verification Activity: By - SE
7badcf5e-52c0-4ee1-8f6a-7c4b330f0356 | checkpoint | 4.01.04 - Special Fences and Gates
5d830cb4-6d75-577b-9703-115b91135123 | note | Acceptance / Conformance Criteria - To be confirmed with designer.
737267d6-af34-57da-8808-c7d952f352da | note | Standard / Specification - Designer
a7c921dd-80e2-5b43-bb85-5e19c5f6904e | note | Verifying Document - InEight Correspondence
2bddcebc-b096-5e56-b11d-4f3db7f9219e | note | Frequency - Prior to installation
1fc72fc4-b336-5bf9-a545-990ac630a4ac | note | Verification Activity: Activity - HP
cf691f67-f3f3-552f-8f19-5514d8d495bf | note | Verification Activity: By - ENG
2f747120-b336-4abe-986d-b0040c5eed04 | signoff | AUTHORITY HOLDPOINT
da0d4df1-35ea-4d78-8ca0-20465edf11ad | section | SECTION 5 – CONSTRUCTION ACTIVITY
e55e27b3-311c-4289-9041-0bc4ff941899 | checkpoint | 5.01.01 - 7-Wire standard Boundary Fence Installation
84c1ba14-d9c8-5793-b2c0-15b86ab9ede3 | note | Acceptance / Conformance Criteria - The minimum standard of fence for a straight section on flat ground with favourable ground conditionsshall be a post and batten fence with 1.8m long H4 treated No.1 grade full round posts spaced at 4.0m centres, five 50×50 H3 treated battens between each post and seven 2.5mm high-tensile wires. extending and adjusting all lateral fence lines to tie in with the new permanent fencing.
0a125cec-ea12-541b-ae42-d6235adb9ac1 | note | Standard / Specification - Designer
1ae4a0fd-82dc-5dc7-89e1-34f7a1e771fa | note | Verifying Document - Installation Record, Photos
5ba97b57-63bb-5c15-b477-f31a18145e45 | note | Frequency - Each Area
a665d656-7111-538f-b3fe-4dc9c1104b5f | note | Verification Activity: Activity - H
2284a45d-f207-5bb2-b607-433113240963 | note | Verification Activity: By - SE
3b757d6f-7fd5-4feb-9b92-b6926f2a4308 | checkpoint | 5.01.02 - Posts
816454c0-96eb-550c-be62-fe801c05e8a2 | note | Acceptance / Conformance Criteria - Strainer and angle posts shall be included on the new fence lines at the laterals, and the laterals re-tensioned.
6e4c62b9-7eed-58f2-a968-2de50db4caf9 | note | ○ Line posts shall be minimum 1.8m long H4 No.1 grade full round posts. 4m spacings.
1c26d488-1d94-5ef3-b407-ba2de9be7b28 | note | Standard / Specification - Designer
3b792988-d8d7-544a-9a01-23b8ce1c3f3e | note | Verifying Document - Installation Record, Photos
8f3fe59b-99fa-5e94-a16f-99bb099b9b45 | note | Frequency - Each Area
7518186d-cd7e-5774-955c-fa046af8918d | note | Verification Activity: Activity - H
8426f467-c7ef-5f1c-b23e-67d3b8e6794c | note | Verification Activity: By - SE
6d8335e1-41ef-40c0-a643-3fbb79e00976 | checkpoint | 5.01.03 - Gates
af49f76d-d7a2-539d-9264-d201deedb930 | note | Acceptance / Conformance Criteria - 3.6m light gate or 4.2m light barred gates. Singles or double gate. As per designer's requirements.
9c258a1a-45ab-5d98-9d50-fcb99944d80e | note | Standard / Specification - Designer
6d61eb37-ff25-5aed-8d86-50cf4822b72b | note | Verifying Document - Installation Record, Photos, Miscellaneous
2e93e127-d317-5655-aa25-e09bed7eb6f6 | note | Frequency - Each Area
ddf79191-f0ec-546d-bf0a-3a5207b12092 | note | Verification Activity: Activity - HP
4dbb7678-4a16-56e5-93c1-c287e5d48c65 | note | Verification Activity: By - ENG
bae38b9c-300a-4de6-87a7-ea03e62466c3 | signoff | AUTHORITY HOLDPOINT
4c42cb86-0255-4360-b6b4-1f0b0d08b31d | checkpoint | 5.01.04 - Corner
0e24b0e4-2300-5dbe-ba4d-119d217da93b | note | Acceptance / Conformance Criteria - No.2 2.4m long strainer and at the ends of the fence line.
4b9cbe2c-902c-592e-8456-0a75122808ec | note | Standard / Specification - Designer
b68efa3f-7087-5838-b016-f848825adba6 | note | Verifying Document - Installation Record, Photos, Miscellaneous
51a6a5c9-66c1-567c-a00b-49f8c24e7d7a | note | Frequency - Each Area
462dcf65-17e3-52b0-a75f-c2c4c41a3efb | note | Verification Activity: Activity - H
1563ac38-ee25-52a6-8957-6bf505304b78 | note | Verification Activity: By - SE
717c0b53-d06a-4b01-ada0-97a6c96dcdfb | checkpoint | 5.01.05 - Height of Fence
ebc2dded-13d5-55eb-aeb9-049080ece844 | note | Acceptance / Conformance Criteria - Standard height to be 1.150m.
c57f5d70-278c-5c67-ac8e-477f662c654f | note | Standard / Specification - Designer
316589e1-c87b-5504-a2d1-e120f74a84ba | note | Verifying Document - Installation Record, Photos, Miscellaneous
798f83c4-5433-5d9c-a679-4fa7cbe8a39b | note | Frequency - Each Area
f4d81f65-372f-5bdb-ac69-f84331e6ca2b | note | Verification Activity: Activity - H
4a26ebca-65a5-5a53-af56-4e7877f37839 | note | Verification Activity: By - SE
ffff8567-911b-4308-a1f5-b46cbd9bef08 | checkpoint | 5.01.06 - Staples
ba9fe76a-daad-539a-8e76-9e9fb68e5db6 | note | Acceptance / Conformance Criteria - Installed at approximately 170-175 degrees and staggered to prevent splitting of the post/batten
083df23d-2eec-5639-88c1-a60cd0b0b45f | note | Standard / Specification - Designer
13a01276-5a19-5b15-a43d-4b7760c54a87 | note | Verifying Document - Installation Record, Photos, Miscellaneous
b8eb779d-0d37-5156-ae9f-e23582138f77 | note | Frequency - Each Area
9e265acd-d614-5b2d-8e5b-074392354b17 | note | Verification Activity: Activity - H
52d1a669-e0a2-5192-a396-43090f75543f | note | Verification Activity: By - SE
eee838fe-794a-42a5-99a1-4cd654dd4903 | checkpoint | 5.01.07 - Wire Spacing
268df3b8-efe4-5cc7-81ed-6b126cf2ee7c | note | Acceptance / Conformance Criteria - Distance from ground - general arrangement.
d08a70a8-e6c8-53ec-abcf-cb7ff909faa3 | note | ○ Wire 1 - 125mm, 2 - 250mm, 3 - 375mm, 4 - 500mm, 5- 650mm, 6- 730mm, 7 - 930mm.
f758d534-4295-58c2-8836-b5f82f6295e7 | note | Standard / Specification - Designer
ce40b7e2-4ab7-54d0-a795-fe923c15274c | note | Verifying Document - Installation Record, Photos, Miscellaneous
03961a94-8a82-5d52-afc7-f6d8fa086dc3 | note | Frequency - Each Area
0d19621b-9d44-526d-a188-1a4e2757a40b | note | Verification Activity: Activity - H
e3f884ab-652c-587f-bb14-f48e89c2fbfb | note | Verification Activity: By - SE
2e4d9726-cc40-4c13-8186-b4fa9411323e | checkpoint | 5.02.01 - Posts
5ae1b7cb-e517-5bc4-a74c-7cf9101f36b8 | note | Acceptance / Conformance Criteria - Posts Strainer/Angle Posts should be a minimum of 2.4m Long and 175-200mm Diameter or 2.4m Long x 200-225mm Diameter, Line Posts Minimum 1.8m Length x No 1 (H4 treated) Full Round 1 1 5-135mm Diameter at a maximum spacing of 4.0m or less depending on the contour of the ground.
e6f255f1-2bb9-5de4-b490-2261b5957eb6 | note | Standard / Specification - Designer
3c5a7354-bfee-5e14-8132-6f53ef42da92 | note | Verifying Document - Installation Record, Photos
10dbcd27-b191-5cff-8085-20d8ab36b2e8 | note | Frequency - Each Area
7677d773-2adf-5f72-a210-f83efbb10760 | note | Verification Activity: Activity - H
4be059a8-4523-5dcf-91d0-1db33f074d48 | note | Verification Activity: By - SE
981db228-7f08-48f7-934c-db273c2f5541 | checkpoint | 5.02.02 - Timber rails
b456074e-6ad6-5e1e-97bf-286139c64c7c | note | Acceptance / Conformance Criteria - A minimum of three timber rails shall be provided.
bd810a72-3d2c-57bd-89b8-9d4bba6f4e76 | note | ○ Timber rails shall be no less than 150mm x 50mm (unless accepted by the Owner where an alternative size matches their existing fence). Rough sawn grade is acceptable. Rails shall be fixed to each post using a minimum of three 6-inch galvanised flat head nails.
b100fafd-2aac-5143-a73d-00aa4c30f665 | note | Standard / Specification - Designer
ecd228d4-75df-54e7-8629-421e0fb8401e | note | Verifying Document - Installation Record, Photos, Miscellaneous
16e690bc-d0de-51b7-aa14-ce0b3bafc4c4 | note | Frequency - Each Area
4554e37c-00ce-54fe-a980-fefd4fea06cb | note | Verification Activity: Activity - H
961611a8-8870-5fb0-aeed-f14df43292cb | note | Verification Activity: By - SE
4e488143-2616-4a66-9734-948583b098a3 | checkpoint | 5.02.03 - Height of Fence
dfd84b44-f250-5b46-bad0-a245315c7685 | note | Acceptance / Conformance Criteria - The standard height for the fence is 1.150m
d96ee484-229c-56df-96f8-d9a5193f8caa | note | Standard / Specification - Designer
cffe2d96-4e19-59d8-ba48-b281590334c5 | note | Verifying Document - Installation Record, Photos, Miscellaneous
2a9caa7c-633f-582e-990c-3d7fc8e6c36d | note | Frequency - Each Area
fb8aa49a-dd77-5d10-80c4-f1a61dc2a58e | note | Verification Activity: Activity - H
6fee32c5-45c9-5ecf-b49b-bad0f373b2d0 | note | Verification Activity: By - SE
388a703f-5f3a-43cb-af48-292b68654b7c | checkpoint | 5.02.04 - Timber rail spacings
b4b2f3d2-89be-50ea-b595-53765d74c1f0 | note | Acceptance / Conformance Criteria - Timber rails shall be equally spaced between the top rail and the bottom rail. The top rail being positioned at the standard fence height (above), noting that tops of posts may need to be trimmed to match the top rail height. The gap beneath the bottom rail shall be no more than 150mm.
260547cd-d74e-5e2d-a47b-e4197d698dde | note | Standard / Specification - Designer
b7c28337-eae0-5253-9b08-bc93e73d13ad | note | Verifying Document - Installation Record, Photos, Miscellaneous
6f7dd4f6-37f7-5374-aa08-8ddc58b88e63 | note | Frequency - Each Area
8871d210-cc78-5b97-93f7-59a196a01ac6 | note | Verification Activity: Activity - H
de0d5334-830b-5409-ab67-cd309b95f587 | note | Verification Activity: By - SE
f326b7d1-79cc-4288-a8c9-326c21bd2d92 | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
35e7e6d7-7258-48c0-91dc-b5a6d9635fb3 | checkpoint | 6.01.01 - Red-line Markup
6947845b-3626-54a2-a9bc-b97cb1bd2ee7 | note | Acceptance / Conformance Criteria - Provide red-line markups for items that have been moved, modified, etc.
abb20743-3e85-50fe-9c6e-0b84ff120316 | note | Standard / Specification - Downer
5b727dea-a782-5094-aee2-38785a198d6c | note | Verifying Document - Red-line Markup
a9e743f7-062b-5181-bbb0-96ca7b1c1d0e | note | Frequency - Upon Completion
c073de32-e648-554a-8566-d079dc660ea4 | note | Verification Activity: Activity - H
48ec1328-3908-5479-aa3b-624347e77d48 | note | Verification Activity: By - SE
a0cf7812-0012-4fa0-917b-e58b6c99c03d | checkpoint | 6.01.02 - As-built plans
88fff21a-1d16-5ce3-8de4-2e4f3c75457d | note | Acceptance / Conformance Criteria - As-built plans to comply with RITS.
d7ebb61c-750e-52dc-89ea-b005caa4de30 | note | Standard / Specification - Downer
a629c403-f17f-56ae-b8ad-2e243a925960 | note | Verifying Document - As-built
1b11157f-8886-5eae-9d63-5f060730d7c3 | note | Frequency - Upon Completion
fba1f3a6-2e14-5a63-8c2f-fe873eca13c0 | note | Verification Activity: Activity - H
04232a67-0f0f-5951-837c-e626e556e371 | note | Verification Activity: By - SE
319c7a19-b011-4ce6-945b-1b20d90da5b8 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
86044235-92a4-5edb-a8e7-a8ff5d1bfd65 | textbox | Contractor's Rep Name:
16074939-ea53-5258-907c-dcaaf4d7ea23 | textbox | Engineer's Rep. Name:
79be2e5d-cc94-570b-a5bb-20c22374f685 | date | Date:
0acbeafb-cc8c-4251-a2ed-c1754b4ed9ca | signoff | Add Signature
5d2b1d2e-3258-562a-ad74-a098148e05f2 | checklist | ITP - Hollowcore | itp | ITP - Hollowcore
0f66e61d-af39-55d7-a549-551996ec17ca | section | 1.0 Pre Construction Tests
16741c32-4133-5e37-a426-b83d943044fe | checkpoint | 1.1 - Concrete Mix Design Approval
78f211aa-5a6d-5d2e-952f-d156b3567228 | note | Acceptance Criteria - 60 MPa at 28 days (S6014PC)
aa858af4-1c11-5fec-9807-c8bf6701d980 | note | Inspection or Test: Method - Review
d2c184e8-b5f4-5905-b93d-788ab91ca0db | note | Inspection or Test: Freq. - Once per Mix design / per supplier
17809666-3917-5c98-a776-b11dfa4ff31c | note | Inspection or Test: Responsible Person - PRECO
7fcbf47b-08ac-57d4-8bb0-1afe56b12559 | note | Verifying Document - Confirmation of Approval
3a201943-a2a7-5359-9283-ea1ac7d0928d | note | Records required for handover package: Yes/No - Y
eca077c5-ed8a-5b97-9a5e-cdf67be56ace | note | Inspection / Test Authority: Conduct - 1
cb8fb411-2aa4-5950-8709-3a3592e01c28 | note | Inspection / Test Authority: Witness - D
ab4ec765-bf98-5ad9-a7c4-5858a57c8569 | note | Inspection / Test Authority: Produce Record - 1
ffd7e38e-39d7-51a4-a0e2-e393ee9f3d6a | note | Inspection / Test Authority: Approval - D
12b13299-31df-5e0f-8a3d-1c23f32e0df1 | note | Hold Point - Y
bc850914-d12b-5672-bff8-389cfa142964 | signoff | HOLD POINT
c754f42f-db38-5d2c-9d86-50120e867cca | checkpoint | 1.2 - Reinforcement Supply
c3138b85-2b05-5574-a3a6-a2e04a6675a3 | note | Acceptance Criteria - Micro Alloying Deformed Bars Grade 500E (HD)
14abb13d-df41-55f5-9965-079418bf4584 | note | Inspection or Test: Method - Review
017175fb-024a-571d-8bc6-53d393f584c2 | note | Inspection or Test: Freq. - Per Size, Per Supplier
1c69872e-6d91-5364-849d-51759dbd028a | note | Inspection or Test: Responsible Person - PRECO
70142f81-b14b-5339-ba6e-ca12006cd9e4 | note | Verifying Document - Supplier Mill Certificates
98f163b4-fae4-5b01-a913-d13ec9072468 | note | Records required for handover package: Yes/No - Y
a86b2e81-f72c-5ede-82ea-29331059eb45 | note | Inspection / Test Authority: Conduct - 4
8cca54ad-ae01-5eaa-ba78-9a4ebd814399 | note | Inspection / Test Authority: Witness - D
3f1214ed-d4af-5cd2-b9e7-7438fb04eb89 | note | Inspection / Test Authority: Produce Record - C
73d8ecd9-f1e6-524d-89af-5c9fdf3d6927 | note | Inspection / Test Authority: Approval - D
8cc5fdc0-8b51-54b7-a5c5-f6e9b2d88efa | note | Hold Point - Y
36b26065-b8ab-516d-9d52-c286a7e630d8 | signoff | HOLD POINT
16fd4035-90c4-5fc2-9f2d-008a965903e4 | checkpoint | 1.3 - Strand Supplier Verification
4255b8e1-7562-54e5-9b12-d10442fcc85e | note | Acceptance Criteria - ACRS accredited supplier
867cf9d8-c10b-58e5-afcd-c49485bd82f8 | note | Inspection or Test: Method - Review
121bd0c4-24de-5c78-8319-dfa08a2d08c3 | note | Inspection or Test: Freq. - Per Supplier
1f928294-bd9a-58d3-9820-099b51484fcb | note | Inspection or Test: Responsible Person - PRECO
ea7943bd-f313-59cc-9d64-d02695513371 | note | Verifying Document - ACRS Accreditation
d661eee4-fff8-5c68-a2dd-5cbc821d7825 | note | Records required for handover package: Yes/No - Y
9ece86f8-116f-5b4e-ab33-20db39efcaae | note | Inspection / Test Authority: Conduct - 4
fedf724f-dd9f-50fc-9f5d-3b1ad3296fad | note | Inspection / Test Authority: Witness - D
af4df6dd-cf0c-5cc4-9bf0-f29f3fd06cf2 | note | Inspection / Test Authority: Produce Record - C
f27b0868-6259-51c2-b8d4-57ea5c1652c8 | note | Inspection / Test Authority: Approval - D
cf2a1c14-b965-53b9-ae4e-47d7133f1bbf | note | Hold Point - Y
5f9413f4-d534-5dc8-a0c7-8ddb719256b1 | signoff | HOLD POINT
91ada194-9d85-5cf8-8f94-ef40154adeeb | checkpoint | 1.4 - Strand Supply
d5831ee0-71a7-52e2-bec8-36e284be9840 | note | Controlling Documents - NZS 3109
214a8a5c-c23a-5aad-80bb-b71fba686a79 | note | Acceptance Criteria - 15.2mm diam. Prestressing superstrand
4997169f-dac4-54b3-97eb-791c68fa8684 | note | Inspection or Test: Method - Review
721a8e30-e897-53a4-9c2c-d656c7765c60 | note | Inspection or Test: Freq. - Per Size, Per Supplier
1c599276-26d7-54b6-995a-2fbf01dfb740 | note | Inspection or Test: Responsible Person - PRECO
57792685-2729-5a0e-b18f-8f70006bbe90 | note | Verifying Document - Supplier Mill Certificates
a49d69ed-5b55-567a-9f10-5ed2fbd98508 | note | Records required for handover package: Yes/No - Y
72e2b36c-de11-5d10-8e79-8724da027cc1 | note | Inspection / Test Authority: Conduct - 4
286462b3-aa49-5f42-8bb2-3945620a72f2 | note | Inspection / Test Authority: Witness - D
f7a2b0f5-5fed-5c04-a321-1e58b66cbe3f | note | Inspection / Test Authority: Produce Record - C
24164605-5635-550c-b0f1-bfc4f5cd702e | note | Inspection / Test Authority: Approval - D
3e178ecb-70b8-5db9-8bc5-e9342cbd7384 | note | Hold Point - Y
611cc3db-b365-5e76-abcf-690a96eb0ec2 | signoff | HOLD POINT
dcbea265-f2b8-5855-9d6c-c9f2aa8b6855 | checkpoint | 1.5 - Strand Certification
8dfef4d5-d92c-526e-9fa6-9601130558b1 | note | Controlling Documents - AS/NZS 4672
7e6982e4-94b6-548f-ad67-108003a3a0b5 | note | Acceptance Criteria - Conformance to AS/NZS 4672 in relation to:
4ab239d3-ccca-5821-9c30-2522ff9ea8d8 | note | ○ Chemical analysis
f801015e-c684-5f3d-81af-9a989c6bf888 | note | ○ Geometrical characteristics
6680d36a-67e8-5105-b2d1-df651faad111 | note | ○ Breaking force or tensile strength
6bd53a41-3a23-5b28-b2c4-2cfff7519141 | note | ○ Proof load or proof stress
6ba44543-2775-5a07-857c-e7c719cd7e0d | note | ○ Elongation at maximum load
8689ff12-aed6-5bac-83f6-908935756478 | note | ○ Load extension diapgram
a5bdc635-cac4-59f8-8203-4209902dc1c4 | note | ○ Ductility
2c5e90a6-933b-5cd5-b6c8-6cfbe18c960f | note | ○ Relaxation
5d19aab5-7d19-5c52-a24c-8aeec7741395 | note | Inspection or Test: Method - Review
958460c4-0198-51fc-920c-462c63ee5024 | note | Inspection or Test: Freq. - Per Size, Per Supplier
e2d1b5b3-1c0a-525d-a81b-a05b984bd7e1 | note | Inspection or Test: Responsible Person - PRECO
15936079-2d8c-520a-af28-448cfe987c26 | note | Verifying Document - Material Test Certificates
bfdf3393-8341-5999-998a-d2735a598c0f | note | Records required for handover package: Yes/No - Y
307908f2-fb06-5ef2-ba11-fc63bb9efe67 | note | Inspection / Test Authority: Conduct - 4
31b58e15-b7bc-5d95-aef4-f912fd8bc2a3 | note | Inspection / Test Authority: Witness - D
392c27e9-938c-5e17-a0b9-61668440771f | note | Inspection / Test Authority: Produce Record - C
cb9ba18e-2436-50fb-a937-167b8367d118 | note | Inspection / Test Authority: Approval - D
d1711e2b-a249-53e0-9908-a4e885436191 | note | Hold Point - Y
06e62339-34ea-506f-bea9-6091835db93c | signoff | HOLD POINT
405405d3-be37-56e4-b1a0-839cb34aea7e | checkpoint | 1.6 - Shop Drawing Approval
d81037e6-4cfd-59f6-88d8-0adca4305fac | note | Controlling Documents - IFC drawing
db0fa714-a011-5b85-b0c9-658975aa0039 | note | Acceptance Criteria - Shop drawings including strand type, arrangement and stressing notes, details of debonding lengths, concrete strengths, surface finishes, location of cast in items and set-out information
b8d6e591-4cf9-585e-a730-1862fb7924e5 | note | Inspection or Test: Method - Review
054cb47b-59e4-501a-a990-f771ee88e529 | note | Inspection or Test: Freq. - Once Prior to Casting
ce166315-bb6e-5ca4-8679-0383c87297b6 | note | Inspection or Test: Responsible Person - PRECO
a45c3f2a-0cd5-50b4-bed9-cb4c47078bdc | note | Verifying Document - Approved Shop Drawings, Issued for Construction
29014ed0-46ce-5fb5-b72f-17479d57fcf2 | note | Records required for handover package: Yes/No - Y
89e8fd82-8ecd-5ef5-a4fa-572afc64881c | note | Inspection / Test Authority: Conduct - C
0be08783-6b2c-5068-964f-61ab966f482e | note | Inspection / Test Authority: Witness - D
9bad79f3-7095-5b16-be96-c68c07c5953c | note | Inspection / Test Authority: Produce Record - C
1e55555d-5f65-5029-97ad-db570de73f9d | note | Inspection / Test Authority: Approval - D
9d941f41-78fc-5299-85e9-44f1f8a921a5 | note | Hold Point - Y
702db023-a927-57ea-9c0f-452773a19d7d | signoff | HOLD POINT
d9ee4a45-9c24-54e8-995a-f76b5f9add04 | checkpoint | 1.7 - Stressing Calculations
4142e4e5-f1ad-5627-9e33-d40bf29187f7 | note | Acceptance Criteria - Force remaining in each 15.2 mm dia. strand at midpoint of beam immediately after release of tensioning jacks
26fd898b-b0f5-5dd6-b3e1-6a81f4df8d9d | note | Inspection or Test: Method - Review
2125f996-2afa-5c9b-bc65-24a87238ecb8 | note | Inspection or Test: Freq. - 5 Days Prior to Casting
40427a1d-5c44-52d7-8417-b474dba02533 | note | Inspection or Test: Responsible Person - PRECO
0a3172c5-7508-5e53-847e-3213b5f29a5a | note | Verifying Document - Approved Stressing Calculations
8de58f1f-2e0e-5d67-a886-ef2d7360f8b6 | note | Records required for handover package: Yes/No - Y
698e7976-4c4a-562c-a5af-00ec5dca396d | note | Inspection / Test Authority: Conduct - C
c8e399ef-8561-5cb6-b5c6-5ca02bd6bce3 | note | Inspection / Test Authority: Witness - D
6b5065be-2022-5538-b577-8240c957fc7d | note | Inspection / Test Authority: Produce Record - C
943c788e-a1f4-5e22-869b-904e215411b3 | note | Inspection / Test Authority: Approval - D
e5d40d4a-6c54-5927-9d2d-14a8667156ae | note | Hold Point - Y
51ed43c9-40e5-5aca-b7be-3415e0723fc7 | signoff | HOLD POINT
ef23489f-eb00-5f3b-b643-deaae7a7e9dc | checkpoint | 1.8 - Jack Calibration
4912747c-2bce-5136-babf-2c5ef48c651d | note | Acceptance Criteria - Calibrated within tolerance
25e0f232-4bd1-517b-9285-35d662af5218 | note | Inspection or Test: Method - Certificate Inspection
c74194b3-f0c2-5267-aeca-fbb84bb25b1e | note | Inspection or Test: Freq. - Every 6 Months, Per Jack
a3976cd2-6eba-5e77-8a63-1f5b81365120 | note | Inspection or Test: Responsible Person - PRECO
d1724d1b-2de4-50e4-a7b4-db0ec34db939 | note | Verifying Document - Calibration Certificate
6687e253-a060-5987-93e6-45cc92317bfc | note | Records required for handover package: Yes/No - Y
5da45a7a-f9b6-5eee-8f02-d1e2502013f5 | note | Inspection / Test Authority: Conduct - C
5a6cfbc4-f71e-55cf-9638-1cffcab231c5 | note | Inspection / Test Authority: Produce Record - C
5b7d0374-3060-5c70-b637-56c03fb20930 | note | Inspection / Test Authority: Approval - C
ac280ed7-60d4-5318-9c00-e527014ce062 | note | Hold Point - Y
770ad0d6-9c93-5227-ba83-68cacef816d5 | signoff | HOLD POINT
17bd4489-7071-57a4-9a3a-3e10f5f3dfc1 | checkpoint | 1.9 - Form Release Agent
4a2f920f-06fa-5ca5-9440-2d784383edfc | note | Acceptance Criteria - Not detrimental to the application of any subsequent finishes
929a89b7-7a51-512f-a27b-dc18d97f6602 | note | Inspection or Test: Method - Review
3595fc7d-8930-5042-b0a6-bb4e2198d229 | note | Inspection or Test: Freq. - Once
3e905d85-7513-531e-8bf7-aaa26a8e6b8f | note | Inspection or Test: Responsible Person - PRECO
f13606ae-27d3-5641-bf45-a7c1536b7fb3 | note | Verifying Document - Material Data Sheet
9a6b2806-6e07-58fe-8a46-2fb8720007f5 | note | Records required for handover package: Yes/No - Y
bb7392da-1876-52b1-b66c-4332597659b9 | note | Inspection / Test Authority: Conduct - C
a11e2481-f601-5d2b-9949-dd42b7d87f04 | note | Inspection / Test Authority: Produce Record - C
0a89bb81-a0a4-5da9-9180-1e2537240abc | note | Inspection / Test Authority: Approval - C
8b999de5-2dd0-55a6-8c77-eda64208c51e | note | Hold Point - Y
baae1eae-8748-5092-8f37-9c430c6a38dc | signoff | HOLD POINT
254d676b-9c6a-5c89-bbdd-1e9524316f24 | section | 2.0 In Process Testing
9676fb04-593b-528b-8ca5-f04616a18093 | checkpoint | 2.1 - Reinforcement Traceability
61ccf0a1-8c43-5f03-ab35-a3c7e776a72e | note | Acceptance Criteria - Mill Certificate, Heat Number and Bend Schedule traceability
d1191534-d8b5-5a18-ab8f-9683ebb998b1 | note | Inspection or Test: Method - Review
e0f9d9c5-9dd9-5fce-ad34-5f3bc667a60d | note | Inspection or Test: Freq. - Per Unit
936505a9-7a6c-5f3f-8e24-0ad2c911c846 | note | Inspection or Test: Responsible Person - PRECO
79a6200d-a523-5ba8-bf8a-d8c222392f92 | note | Verifying Document - Pre-Pour Check Sheet
a2529bb7-64a7-5f1c-9f48-8fc49fe5e1d1 | note | Records required for handover package: Yes/No - Y
c06454a1-11cd-587b-8afc-f3091ffc8473 | note | Inspection / Test Authority: Conduct - C
100a881a-2b07-5500-8986-e757666b171a | note | Inspection / Test Authority: Witness - C
133786a1-f514-5b7a-b002-ef08f5898a12 | note | Inspection / Test Authority: Produce Record - C
b68e1c03-cf17-5cb6-9316-db5166e91af3 | note | Inspection / Test Authority: Approval - C
fb2e7852-2574-5cd3-ad63-6811ed026e03 | note | Hold Point - N
131c5882-9696-5e3c-8041-3f4b4b66a3a2 | checkpoint | 2.2 - Reinforcement Fixing
6d21fe64-6a0a-5282-99bf-2e718a847467 | note | Controlling Documents - NZS 3109
348f0eea-a018-5038-bf44-b5b8d3539582 | note | Acceptance Criteria - clear cover as per drawing to all reinforcing including stirrups and ties
47db6c98-d89e-5e0f-8df3-8cf606190dc2 | note | ○ Steel to be securely tied and fixed with no movement
91ba1cf8-25d4-59c5-97e9-7cc8f53ffe8b | note | Inspection or Test: Method - Inspect
b9149e45-01b4-5203-9eeb-3a2de6ff413b | note | Inspection or Test: Freq. - Per Unit
386d206d-d2c5-5da1-824a-1080525fc590 | note | Inspection or Test: Responsible Person - PRECO
52e37810-5c7f-5a82-96e5-05fd9b7853bc | note | Verifying Document - Pre pour checksheet, photos
eb431f8e-5183-57ee-9da9-e63271c0eb6c | note | Records required for handover package: Yes/No - Y
1ccf093b-81ca-591f-89b9-eee4a5a2084c | note | Inspection / Test Authority: Conduct - C
e0d5d116-4616-5a98-8058-45ed77b042d5 | note | Inspection / Test Authority: Witness - D
0f221cfb-6b22-56da-8523-eeabfec6955c | note | Inspection / Test Authority: Produce Record - C
a14218b6-312d-5ea1-ad99-a57fd49b362d | note | Inspection / Test Authority: Approval - D
80b3119a-03c3-5c6a-a60c-a208d6c10ad0 | note | Hold Point - N
6e14d553-73d1-562e-8c3c-c3a67188fd2d | checkpoint | 2.3 - Pre Pour Inspection
d636d527-87a5-59bd-a560-2e45f82dffdf | note | Acceptance Criteria - Completed pre-pour inspection (dimension/inserts/ reo) permission to commence concrete placement
1ce3f275-5a5a-5ad5-ad39-0e8c1c6aa2a5 | note | Inspection or Test: Method - Inspect
b22b9cc4-ebad-53ca-9105-c89f97d45417 | note | Inspection or Test: Freq. - Per Beam, Per Pour
e28ca6b4-e0e2-5f69-bb6f-0c16a10e0eba | note | Inspection or Test: Responsible Person - PRECO
3f42244e-32c9-5520-b6ac-2b7f00939e36 | note | Verifying Document - Approved Pre-Pour Checksheet
429807ba-ab0c-51d3-a509-f182bc3fada0 | note | Records required for handover package: Yes/No - Y
2ee5eb8f-a096-5e8b-b2c7-2a27643b9c07 | note | Inspection / Test Authority: Conduct - D
b2709ce4-a224-523b-919a-db37d24f51b1 | note | Inspection / Test Authority: Witness - D
4bc57f2f-9ba0-5b43-b5dc-e85d3acbc1d3 | note | Inspection / Test Authority: Produce Record - C
fc9ab214-1fa1-5317-9cf0-49661b16d828 | note | Inspection / Test Authority: Approval - C
7e57bdb0-35a3-5ab9-9eca-17fde2f2be2a | note | Hold Point - Y
9ade320c-3742-5d12-8889-a9169e1643b7 | signoff | HOLD POINT
4ae29e84-f0c1-5a7c-9625-654ddcc77c29 | checkpoint | 2.4 - Concrete Placement
39fafecd-b2e9-5b48-8c7b-daf98a4d5755 | note | Controlling Documents - NZS-3109
3a3612b0-39ea-5b3c-95d5-86105f296f6c | note | Acceptance Criteria - Slump within target 120 +/-40, all concrete to be properly vibrated
cc2863c6-eb35-512c-88ee-d78aac832397 | note | Inspection or Test: Method - Inspect
b5ae8a11-7555-51c9-a5b0-828f6b61015c | note | Inspection or Test: Freq. - Per Concrete Delivery / Per Placement
97cc9910-052d-5ee8-8fe0-979d2b08d2fe | note | Inspection or Test: Responsible Person - PRECO
d0d71ce8-ae9f-568b-b2e1-01ab7409b823 | note | Verifying Document - In-Pour Checksheet / Delivery Docket
dd891b55-3834-559f-a59c-f5a4d769d5d3 | note | Records required for handover package: Yes/No - Y
1863c022-8047-5deb-8720-aa7a43389550 | note | Inspection / Test Authority: Conduct - C
de9063fe-7287-5f4b-8ab9-6fe3e1ecc0a0 | note | Inspection / Test Authority: Witness - C
92efaba6-6645-5395-8bff-9c46a435f71b | note | Inspection / Test Authority: Produce Record - C
7acaa081-f417-528c-9e45-3c8341c68e11 | note | Inspection / Test Authority: Approval - C
2721098c-0c32-5e5f-88de-48ba461fd82b | note | Hold Point - Y
10d61ffc-fb4b-5165-8a31-89dd1fb6737a | signoff | HOLD POINT
4040dba9-523c-5c38-ada6-bdc18c543e67 | checkpoint | 2.5 - Concrete Sampling/Testing
15f240f6-87cc-500e-b08d-3abc9de99072 | note | Acceptance Criteria - Compressive test 1 x 7d and 3 x 28d results + 2 stress transfer cylinder (1 for test + 1 spare) stored at curing temperature
c17174e3-fd7c-599b-bbe5-c57e91af8e4c | note | ○ 60 MPa at 28 days
d118ff8f-c305-5261-93e2-b9629fa6eaae | note | Inspection or Test: Method - Concrete Sampling/Testing
396500ee-9dd4-50cd-a15d-cd478f6fa682 | note | Inspection or Test: Freq. - One set per precast beam with an additional set taken from any truck which has water added after leaving the plant
e4182f51-8d06-50ff-b4ff-f7c4e06fb709 | note | Inspection or Test: Responsible Person - Subcontractor
9646702c-0876-5348-9c9e-85b19ba2767f | note | Verifying Document - Concrete Sample Test Results (IANZ Accredited Laboratory for 7 & 28days test)
529fd1b4-3428-5e49-8b72-571ea73d607e | note | Records required for handover package: Yes/No - Y
2721c42e-3120-5942-9935-c29f8a846037 | note | Inspection / Test Authority: Conduct - C
c5c55d80-f4d4-5c14-9844-81e70258326f | note | Inspection / Test Authority: Witness - C
672acacb-5ee7-53fe-8c14-1bb41c1c7e33 | note | Inspection / Test Authority: Produce Record - 3
0bc79d63-84e3-532c-9e7b-cc29788e9d9f | note | Inspection / Test Authority: Approval - C
339cdc9e-5a98-5236-8e67-62fa19d28db1 | note | Hold Point - Y (Designer to be notified immediately if specimen fails)
899d3e45-155b-5a33-aa6f-0921390acf26 | signoff | HOLD POINT
df309f6a-7887-58d3-878a-bba3dd5420af | checkpoint | 2.6 - Heat Curing
0e5ebd5c-2e94-5ca3-bb7c-08e2ee65d371 | note | Controlling Documents - Approved Heat Curing Methodology
88a03694-72e0-5798-91f1-ab548320b5b1 | note | Acceptance Criteria - Concrete core temperature shall not exceed 70 degrees
d13251b0-a197-5602-8154-d1632a8eab7c | note | ○ Steady state inlet and outlet water temperatures recorded
85ada80e-9c11-56e1-95d2-2e0b7844af20 | note | Inspection or Test: Method - Temperature Monitoring
620b90c4-8f34-56d4-8094-0c3d4fc5af36 | note | Inspection or Test: Freq. - Per Beam
d36788b1-ca10-5785-a3e1-dde4fd2f2d22 | note | Inspection or Test: Responsible Person - PRECO
02bed0c0-3d6f-507d-a6c8-268d3c1283c3 | note | Verifying Document - In Pour Checksheet, Hot Water Curing Methodology
d53be086-79b2-5f5b-9004-641ef88b5803 | note | Records required for handover package: Yes/No - Y
dc210e64-5df0-55b3-883c-d9091295358f | note | Inspection / Test Authority: Conduct - C
7c9c17dd-5718-5b5b-af55-ba56a659fe14 | note | Inspection / Test Authority: Witness - C
13cf92ff-5eca-5ffc-86a3-70d3bc30ff36 | note | Inspection / Test Authority: Produce Record - C
7b832ff4-8065-5318-a882-b758b5faa0df | note | Inspection / Test Authority: Approval - C
0acf477d-6168-5666-9c59-a90a8d7aab75 | note | Hold Point - Y (Designer to be notified if anomalous temperature readings encountered)
7f081628-06d7-5ebd-94ff-244894e17897 | signoff | HOLD POINT
e36e8123-5d2f-5c62-a846-565547b4f2bf | checkpoint | 2.7 - Concrete Curing
f8bd1996-0eff-587c-82c9-cec2c936c860 | note | Controlling Documents - NZS 3109
8b4376c3-5eba-576e-a6d8-96e199a7ea80 | note | Acceptance Criteria - 7 days wet curing required following completion of accelerated curing
4ecd5945-223d-581e-84dc-40724e292517 | note | Inspection or Test: Method - Inspect
3bd1cb23-136b-580e-8d8a-2158babb60e9 | note | Inspection or Test: Freq. - Per Beam
110ce892-d8d3-5df4-9439-61440d31d9f8 | note | Inspection or Test: Responsible Person - PRECO
b7dfb368-43bb-5749-a772-93f869e24543 | note | Verifying Document - Post Pour Checksheet
cce69b92-0f21-556c-9148-62ae914dcd4a | note | Records required for handover package: Yes/No - Y
c6115285-18c6-566c-81e5-f777e6ba92ca | note | Inspection / Test Authority: Conduct - C
ac33b12b-2462-5132-9745-b874f4c18405 | note | Inspection / Test Authority: Witness - C
f2312730-daa7-5a4f-98dd-ffaaea72abe4 | note | Inspection / Test Authority: Produce Record - C
4c534583-6546-5a29-9845-4a06701677a7 | note | Inspection / Test Authority: Approval - C
9b5b94a7-929b-5d7c-9fbf-e4121869caad | note | Hold Point - Y (Designer to be notified immediately if water supply interrupted)
69f434ae-e20e-50e3-acf5-25565db9e441 | signoff | HOLD POINT
b33a8884-6633-53c1-a97e-902b5a676f90 | checkpoint | 2.8 - Type B Construction Joint
a74ae819-b8ef-5103-a472-48df91c81149 | note | Controlling Documents - NZS 3109
9dad99db-896b-5d9b-8671-6fce30d46560 | note | Acceptance Criteria - 5mm amplitude and free of latinece, cut with water blaster and with use of High Strength Spray on Retarder
48aacd0f-fa6b-51d2-8872-2b9d3e01e1fb | note | ○ Top surface of all beams and end blocks of integral beams
0b775548-e859-5652-89c9-b74b9c3e2233 | note | Inspection or Test: Method - Inspect
18393de2-a168-5ff5-9392-02646e26fe44 | note | Inspection or Test: Freq. - Per Beam
939edf25-0e76-5021-9b62-66ab7e966c1a | note | Inspection or Test: Responsible Person - PRECO
0e01020b-276a-5a0b-b2f6-4a095c5a6ebc | note | Verifying Document - Post Pour Checksheet
5deaeff2-7c53-50c7-84d4-5d4e1d103bd9 | note | Records required for handover package: Yes/No - Y
6ee08dfe-6301-5250-80f5-f3c9a38730f3 | note | Inspection / Test Authority: Conduct - C
5c2e87b9-0789-503f-9f77-ce612bd5fb38 | note | Inspection / Test Authority: Witness - C
91362d65-3729-5f6e-a392-aeee07db5b54 | note | Inspection / Test Authority: Produce Record - C
12d8baf7-0b1f-539b-9636-d888095d76a0 | note | Inspection / Test Authority: Approval - C
1432c686-83b0-5622-966b-a7651bdfff37 | note | Hold Point - N
5359042a-5aa3-58b9-b873-189580f1072f | checkpoint | 2.9 - Post Pour Inspection / Draw-in Measurement
9162f016-8ac8-5c03-bc38-5f1ff150c065 | note | Controlling Documents - IFC Drawings
88c3de0b-d061-58f5-9399-b331de92a632 | note | Acceptance Criteria - Surface Finish Requirements- (F5 for seen faces) / Dimension/inserts/cut-outs as per drawing
169eb815-1eaf-5621-bea3-46009f60330a | note | Inspection or Test: Method - Inspect
e9ad51b9-25a7-5890-b286-1e69b09effdc | note | Inspection or Test: Freq. - Per Beam
cce9461e-a042-595e-8200-93f01be1ea29 | note | Inspection or Test: Responsible Person - PRECO
326621a2-1858-5b67-8699-5f659c336dc8 | note | Verifying Document - Post Pour Checksheet
240ec643-e959-55e3-a014-efd764f512a1 | note | Records required for handover package: Yes/No - Y
c22e7cd1-4c7d-5b5b-8e97-e48c349827b8 | note | Inspection / Test Authority: Conduct - C
74c592b4-0d91-5e89-8cd9-88c8ada682eb | note | Inspection / Test Authority: Witness - C
838c00c9-44e5-5c3e-b1f7-dd9dd7686d73 | note | Inspection / Test Authority: Produce Record - C
ffa656c5-4f03-544f-bf7b-96edd380595f | note | Inspection / Test Authority: Approval - C
cf5c2e86-f608-5900-8099-9073be5f505e | note | Hold Point - Y
74e69685-83c8-55fa-85e7-952fd33a8b09 | signoff | HOLD POINT
e87484e3-671e-58fb-83a7-69415848c6c7 | section | 3.0 Stessing Related Operations
e7eb7633-94d3-5f3c-abc3-5ba7749bfd54 | checkpoint | 3.1 - Strand Positioning
6258448c-266c-50e8-b3cc-379f62795012 | note | Acceptance Criteria - +/- 3 mm in any direction
9efca5fe-1b6c-5003-abbd-77e03a1c4096 | note | Inspection or Test: Method - Inspect
95b32a57-8d78-53c4-8a3e-2bdf6503ef42 | note | Inspection or Test: Freq. - Per Beam
6ec0141b-4772-5f01-a262-7057c7578087 | note | Inspection or Test: Responsible Person - PRECO
d5ffe661-b0a9-508a-99eb-a60b5512324d | note | Verifying Document - Pre Pour Checksheet
48f5a84c-3824-5589-bace-f0f5e71023d8 | note | Records required for handover package: Yes/No - Y
515d378c-5c2f-5665-8908-3eb8f667a100 | note | Inspection / Test Authority: Conduct - C
9d3926c5-bb15-571a-84c5-9b4a3303e59b | note | Inspection / Test Authority: Witness - C
9de33223-6efa-5178-8d3f-d08f599672e3 | note | Inspection / Test Authority: Produce Record - C
39a6e795-e02d-52ea-bdd6-0ebb48890c67 | note | Inspection / Test Authority: Approval - C
78d81136-4187-5599-b59d-ced444f5274e | note | Hold Point - N
5f6f00e1-7f7e-5715-aad8-7eea83acdde9 | checkpoint | 3.2 - Stressing
3d9002a8-01c5-516f-aa32-0b7fbb69148e | note | Acceptance Criteria - Collation of stressing records incl unit ID, strand extention, jack pressures and general comments
3fcf964a-2ab3-5f98-aefc-c745ecd0ec08 | note | Inspection or Test: Method - Review
b9cb5ece-c8fa-5d67-a4fc-aec54a035324 | note | Inspection or Test: Freq. - Per Beam
32ddf547-fd9e-5fe2-9fce-5db1916fb135 | note | Inspection or Test: Responsible Person - PRECO
920bcc17-41da-5147-8c8d-46b9929ec7c9 | note | Verifying Document - Stressing Checksheet
847a6442-5d0a-579a-9d48-12af8e079d8d | note | Records required for handover package: Yes/No - Y
884a3bd6-187e-5df1-a4d6-591ca9a59f33 | note | Inspection / Test Authority: Conduct - C
69daa57c-2297-5e68-bfb1-3ea07e1dcc5f | note | Inspection / Test Authority: Witness - C
4bcbbc71-5099-5261-bbf6-597958e0ffb9 | note | Inspection / Test Authority: Produce Record - C
91eb012b-17b4-5312-9c72-30df09ecf63b | note | Inspection / Test Authority: Approval - C
a74e6dfd-0701-5fdd-89d5-3ad8a1343262 | note | Hold Point - Y (All anomalous readings not in line with Stressing calculations to be submitted)
0d2c5141-2961-571f-9f38-7f34e477a7a1 | signoff | HOLD POINT
3e05d759-6456-5149-8192-52c4f3b8f746 | checkpoint | 3.3 - Stress Transfer
49cbe5f3-da5c-55af-96a5-7d9ba9842cd8 | note | Acceptance Criteria - Concrete Cylinder Tests to be minimum 40MPa
94a4b5d2-3479-5f60-8649-f3fedcf16812 | note | ○ Cylinder to be kept in similar conditions to beam
4338d86d-a09b-5178-84cd-b178bfcf332d | note | Inspection or Test: Method - Cylinder Compressive Strength Test
a9408e8b-177c-5e74-a06b-f6120a3e38ae | note | Inspection or Test: Freq. - Once Per Beam
2f960902-c5a4-553a-af13-74ba7f058bfc | note | Inspection or Test: Responsible Person - PRECO
83b30231-3f61-5b9b-99b7-33a17af6eaf3 | note | Verifying Document - Cylinder Compressive Strength Report (In-house)
914099fa-62cd-5cb7-8d1e-ae7aceed26f3 | note | Records required for handover package: Yes/No - Y
72a7b8e9-2617-5b6f-bf5d-6fe73f980db7 | note | Inspection / Test Authority: Conduct - S
90565c20-cf1a-5784-b374-1500459228bc | note | Inspection / Test Authority: Witness - S
2d8519bc-02a3-51a4-bbd8-2ae414fa9f56 | note | Inspection / Test Authority: Produce Record - S
1a8e7152-089a-5022-be09-417f308fb7ef | note | Inspection / Test Authority: Approval - C
f660713d-289f-590f-8588-9bcd8b850288 | note | Hold Point - Y (No Stress transfer before 30MPa)
7370b437-499c-5294-9efa-2758ade68688 | signoff | HOLD POINT
d6414604-7524-5f08-8657-37dd944288f1 | section | 4.0 Final Documentation
505020bb-1b69-5b4f-a162-52036bd0140c | checkpoint | 4.2 - Producer Statement (PS3)
39010b13-1dce-56dd-9210-021be341f937 | note | Acceptance Criteria - Signed PS3
653b297f-415d-5526-b08f-50bafe58ab16 | note | Inspection or Test: Method - Report Production
b857b720-45a1-5c30-88a0-04a89f5612f3 | note | Inspection or Test: Freq. - Once
7e428ed8-e363-517f-ab8d-7ea9d283d61a | note | Inspection or Test: Responsible Person - PRECO
30d3f47b-a99b-5876-bf16-2658598ec75d | note | Verifying Document - Signed PS3
d1299c2a-f6f5-5998-a93b-64a67b2444f5 | note | Records required for handover package: Yes/No - Y
d6022bd2-cf41-569b-abb4-6a8bbe2b83fa | note | Inspection / Test Authority: Conduct - C
61dbf0dc-a414-5c3d-850d-70db3894c313 | note | Inspection / Test Authority: Witness - C
6e753d30-ec20-52bf-8bb2-dec744d82f34 | note | Inspection / Test Authority: Produce Record - C
23b51786-85de-550e-99b2-67773f6dfc58 | note | Inspection / Test Authority: Approval - D
560f212d-257b-50b8-9024-4318b05d7c13 | note | Hold Point - N
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
f8309359-1885-5ae6-9731-04b0be18ec7f | checklist | ITP - Insitu Concrete Construction - Rev D | itp | ITP - Insitu Concrete Construction - Rev D
aae66d27-7ff1-5b91-9531-00962d34af67 | section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
cefa3a25-1c25-5ccc-88ec-7d7d361477ea | checkpoint | 1.01.01 - Construction Pack
92ceac3b-e1ae-56a9-a8a4-8edc0127429f | note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence.
bb1125af-6e21-585f-b3ed-3c4c432cf7e6 | note | Standard / Specification - Downer
e10d0142-a1ef-54e1-bff5-a33bf202c455 | note | Verifying Document - Construction Pack
99333c1a-e691-5df8-a7b9-21f6e8bf3cab | note | Frequency - Prior to Works
97435b0c-f0b6-58db-abfe-8e5b0a0bd701 | note | Activity - H
0c8bdd52-22f3-5b18-9e0a-b829f82124db | note | By - PE
7d7484e5-7e1f-5fce-9b75-f8e21eb19c86 | checkpoint | 1.01.02 - Survey Setout
f12d670f-e583-5267-b1ec-73154264911d | note | Acceptance / Conformance Criteria - The Contractor shall verify the setting out position, level and line of the bridge, prior to commencing construction. The Contractor shall advise the Engineer of any apparent anomalies identified.
dcd4f506-5e3d-52ca-8c7e-7de1987a4f82 | note | Standard / Specification - Downer PS - 11.2
06f2f8c9-b3bc-59d5-98b7-c265696eca7b | note | Verifying Document - Survey Records
9164739e-ae99-5a56-8397-13f6020a5382 | note | Frequency - Prior to Works
0ca06d95-790d-5940-ade1-9894060330a4 | note | Activity - H
b4ab5ab7-90f2-57e9-8bcd-bcb06be329d3 | note | By - PE
20723b94-4586-597e-bf3d-247853796e17 | checkpoint | 1.01.03 - Internal Permits
80f4840d-3bfa-580f-b6f5-a1f184ba1e1f | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
b3230b35-0a45-5a98-852f-a3cb25db9056 | note | Standard / Specification - Downer
63a94c48-a964-5733-8371-176bd65816ad | note | Verifying Document - Internal Permits
e851d41e-f372-5742-a5d4-411984d20950 | note | Frequency - Prior to activity being undertaken
769fd35b-8009-5aee-afa0-7d2d105d46b9 | note | Activity - H
b0eb6535-8625-5eff-ad5d-61426d20040a | note | By - SE
f0168fbd-9b3e-5fe2-b811-ef9334d597a9 | checkpoint | 1.01.04 - External Permits
b0c75fe0-5871-55d2-9b1f-c93f6186803f | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
c7067bfd-b2ec-5f88-a167-31cc524f3a1b | note | Standard / Specification - Downer
f74033ef-8e27-5e1f-bc29-48e0f0434f3b | note | Verifying Document - External Permits
96f67d5c-0691-5535-b452-3853ad0ec681 | note | Frequency - Prior to commencment of activity
346e4749-5e48-5db6-8d19-cd301687a268 | note | Activity - H
2920e4a8-56ee-5016-a5c5-749cd6b21c40 | note | By - SE
c7439d99-6d49-5575-a258-28240857c7d5 | checkpoint | 1.01.05 - Approved Construction Drawings
1ed16a31-6490-5485-9039-47ce50535f64 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
06d2a285-3919-5f61-9baf-f7d2c02c4abc | note | Standard / Specification - Downer
1cf5bce5-b4ad-5672-9966-fc2c41fc43a7 | note | Verifying Document - IFC Drawings
fcbbe479-8bd4-54c4-9734-246047b2673c | note | Frequency - Prior to works start
d0abc35a-c34b-5578-85df-419f706ec434 | note | Activity - H
a2940c52-f39d-5cfd-a146-39f060e2476b | note | By - PE
7882acaa-190d-5158-9bde-d6e3cd9d08b0 | checkpoint | 1.01.06 - Construction Methodology
8eee3c74-4023-5582-9897-44ae42bfbd0a | note | Acceptance / Conformance Criteria - The Contractor must submit their proposed construction methodology and justification to the Engineer for review at least 10 Working Days prior to commencement of bridge construction.
882e5ba8-77a9-5bd5-b4c9-1ec9d8241c96 | note | • The Engineer’s review will be limited to conceptual assessment of any potential impact on critical elements of the structure.
00d9f83f-73be-5def-bdfb-e9a4fe681359 | note | Standard / Specification - PS - 11.3, SS 2146 - 3
9480445e-5e55-59a1-addf-b56328b7b136 | note | Verifying Document - Methodology
69d03473-6184-5dfa-8b5c-c020156391f3 | note | Frequency - At least 10 Working Days prior to commencement
e2b4efc1-fe2e-582a-8d9a-5d2b61a7de44 | note | Activity - HP
ce2cdaed-9009-5812-a323-cf8303dca192 | note | By - ENG
3372bd7f-c29a-5308-a7e0-eb8cadf46292 | signoff | AUTHORITY HOLDPOINT
3153bc6f-62b0-50d0-b77c-17d34c4f5be6 | checkpoint | 1.01.07 - Stakeholder
8653ddac-a145-5381-a9ff-9b969b62e48b | note | Acceptance / Conformance Criteria - Inform stakeholder of upcoming pours. Special considerations to early morning pours, potential for noise monitoring requirements being triggered.
9c757d6e-6cbe-508d-a785-77d359774049 | note | *Forward correspondence around notifications of early morning pours to the Engineer and HCC before pours are carried out.
992da153-9644-57b5-94c4-a319384e05e6 | note | Standard / Specification - CNVMO / CCCP
8b86c5e5-595d-534d-a339-b2ace543f345 | note | Verifying Document - correspondence with stake holders
0b278dae-55be-5246-a23c-f9c3f2038bc7 | note | Frequency - per pour
c4a21675-edfa-5911-8d04-1562a06eed9b | note | Activity - H
415edfef-9a9c-57ac-87fc-4f94ee49c61a | note | By - PE
eee50117-8fcb-5c7c-9af6-2daa0d33c61a | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
ae9f9b42-62dd-5a5d-95f1-ad7fb3202916 | checkpoint | 2.01.01 - Chartered Engineer
e97e36ad-9112-57c4-a773-3508113774f1 | note | Acceptance / Conformance Criteria - The Contractor shall employ or retain a Chartered Engineer registered with Engineering New Zealand and experienced in the design of temporary works and erection engineering activities to design and provide construction oversight for all temporary works as specified in these Contract Documents and/or as may be necessary to complete the Physical Works.
456287ff-ea34-5f15-a759-0f8f14c8e545 | note | Standard / Specification - PS - 11.14
5a08e547-4262-58a4-b85f-336acfd6db64 | note | Verifying Document - Chartered Engineer Details
25250fdc-ad9f-57f9-ae22-a717e235e685 | note | Frequency - Prior to Temporary Works
790b5b0c-d4a5-5491-b136-26b1fb5a6c95 | note | Activity - HP
2cc865f4-e546-55d8-9436-735522a1f6bc | note | By - PE
7b879b32-744d-5fbe-847c-5fad8f524be3 | signoff | AUTHORITY HOLDPOINT
a20f9acc-ef5f-50bf-bce9-82a050fb9bb9 | checkpoint | 2.01.02 - Drawings and calculations
2350bf3c-f010-5c51-8368-cc6c54285425 | note | Acceptance / Conformance Criteria - The drawings and calculations for the temporary works and/or erection engineering activities prepared by the Contractor shall be submitted to the Engineer for review in advance of proceeding with any temporary works covered by the drawings and calculations to facilitate construction. In no case shall construction commence until the Engineer has reviewed and accepted the drawings and calculations.
0a98b68b-9e7e-541d-b5d4-5d469fbb9757 | note | Standard / Specification - PS - 11.14
bcc21c93-ba07-54f1-bd11-8a017d8a35e6 | note | Verifying Document - Approved Drawings and calculations
5d324e5b-0b9e-54b2-8789-e57b4208b31d | note | Frequency - Prior to Temporary Works
550f05c0-88f8-5f63-9b05-10965ca9cc04 | note | Activity - HP
b2d473e4-2d4f-559d-b54e-4cde57818eaf | note | By - ENG
54d58bc9-c2ce-543b-a30e-ecdffe03a390 | signoff | AUTHORITY HOLDPOINT
34d9743d-734e-573a-bf1a-b996a4b989ce | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
becee15c-3d0d-5d28-ba67-2ef40d7243e6 | checkpoint | 2.02.01 - Concrete Mix Design
790b7eed-c78f-5e0f-993b-fba41557f02d | note | Acceptance / Conformance Criteria - Concrete mix design to be completed and reviewed by the contractor prior use on site. The following criteria are to be satisfied:
c3b8c670-f6d4-5bd1-a913-e38e3172cd9a | note | • Strength: 40Mpa
e5f4172f-cc4d-5530-a3e8-275c60a80349 | note | • Normal maximum aggregate size: 20mm
0c9161ff-5de2-59f3-ad7e-42076f547177 | note | • Basic drying shrinkage strain 720 microstain
51267fe0-ec17-5023-83fe-74189f90cc2f | note | • Concrete materials and manufacturing are to comply with NZS3109
47d723cb-a3fe-5b9c-90df-a7b21c45b678 | note | • All concrete shall contain a minimum of 25kg/m3 of micro silica for enhanced durability.
a97ce29e-cdaf-5d86-a982-ca6501886dde | note | • Only one brand of cement shall be used throughout the works without prior Engineer’s written acceptance.
6bdfbcc3-9886-5f8a-8a4f-4f9e07d9bba9 | note | • Details of the types and rates of application of the admixtures proposed are to be supplied to the Engineer for acceptance.
b86a6c62-b95c-5681-9070-5959aefb50e6 | note | • Trials undertaken in advance of production to verify outcomes are being achieved in accordance with mix design expectations. This is to include if the mixes will be pumped.
c06ac2d0-a25e-5139-a67c-ab8e42565839 | note | • The Contractor shall identify appropriate preventive measures and to justify those measures to the Engineer to minimise the risk of Alkali Silica Reaction (ASR).
519e7c0c-f65a-5a52-86dc-44224a35e7b4 | note | Standard / Specification - PS - 11.5, SS 2140 - 3, 4, 9, 6.1, 6.3, 6.5
3adcf6a0-65e6-54cf-a535-9ec38c49975e | note | Verifying Document - Concrete Mix Design
0a837975-280d-59b2-891c-336379f55662 | note | Frequency - All Mix Designs
8f8a16e3-0a0e-5547-9c1c-84bb434365e2 | note | Activity - H
084ccac4-c73a-57a5-a2d3-e24a4243fbf2 | note | By - PE
749641d0-68eb-5fb0-b253-6c9e1f08523a | checkpoint | 2.02.02 - Concrete Mix Design Checklist
84fb278d-1dd3-5e18-95b4-5d0b32e3dc71 | note | Acceptance / Conformance Criteria - Each mix design shall have a completed concrete checklist with supporting data including Trial Results, submitted at least 5 Working Days prior to production of that mix design, for the Engineer’s review and acceptance.
0a1cb2e6-40e2-5c69-b224-fd19fa9a6a23 | note | Standard / Specification - PS - 11.5, SS 2140 - 9
6fd63448-1bdd-57a1-8e00-5cdbbf67d7ae | note | Verifying Document - Concrete Checklist
ece0e023-060c-5d82-9901-18df5ea7534c | note | Frequency - 5 Working Days prior to production of that mix design
b9dd7f5d-d877-5325-91bc-30955ce392a0 | note | Activity - HP
97d25eb7-9bfb-5110-869b-6c2efb5db56b | note | By - ENG
b3d14fe6-d9f2-551a-8906-6920bf35ebc2 | signoff | AUTHORITY HOLDPOINT
2f899c33-e59b-5c7e-af0a-2d630076ef19 | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
d71aec0d-b646-5094-a1af-bd566f82ef09 | checkpoint | 2.03.01 - Reinforcement
b6afc49f-38e4-5904-ae6f-8f6491a1b94f | note | Acceptance / Conformance Criteria - 3D modelling completed, bar bending schedule checked against latest construction drawings and submitted to the Engineeer for review
a45f2372-e67f-5aab-966a-d6a5df32ceed | note | Standard / Specification - Downer
dbfc1de5-5f40-5c17-8e43-593cf9bd9c70 | note | Verifying Document - Reinforcment shop drawings
2e80847b-6e1c-5227-96f1-959c89b61a6c | note | Frequency - Each batch of reinforcement
3f3826a5-de94-5ec8-aa36-4c24e5a69c81 | note | Activity - H
b46aeed2-e77b-5800-90ec-2da66b229abb | note | By - PE
d3c8b07b-aed1-5d62-952d-f0ff7f730211 | checkpoint | 2.03.02 - Reinforcement
85787332-8b63-5e76-9aac-b236c533023d | note | Acceptance / Conformance Criteria - Mill & test certificates for each batch of reinforcement used to be provided to the Engineer. Unless specifically nominated otherwise on the Drawings, only Grade 500E reinforcement manufactured using the micro-alloyed process is acceptable.
5625c41b-0b31-55e0-9ee5-5803ddc06844 | note | Standard / Specification - SS 2142 - 3, PS - 11.6
0a98d2f9-b4f4-5648-b695-7cdff4e1be3c | note | Verifying Document - Mill Certs
fc16cd7f-c01b-5b9e-990a-a6b9d20bce96 | note | Frequency - Each Batch assigned to Each Pour
5b305dee-885d-5738-a898-35da190dff2e | note | Activity - R
6be4f6ad-b97d-55be-92b1-4398f8cd43e6 | note | By - ENG
326121f5-b8b3-5d6b-8002-2ddd985e66e1 | checkpoint | 2.03.03 - Welding reinforcing
b6b3c536-3468-51a9-b8f2-892b4ae716fd | note | Acceptance / Conformance Criteria - Prior to welding reinforcement, approval from the Engineer must be obtained. The person undertaking the weld must hold the relevant certification.
53ec7e11-e6e2-5ae2-8269-7f5dee129cca | note | Standard / Specification - SS 2142 - 9
f819f84a-616f-554d-89ff-d65ca9ba05ff | note | Verifying Document - Approval
89089fd2-0937-5402-9052-d58bcb4d9744 | note | Frequency - Prior to welding (if required)
5e77e621-5c03-5233-ba4b-fe1a71a19506 | note | Activity - HP
b23e7904-b0fb-5346-ad7c-e2ba1f29a831 | note | By - ENG
9a8e0e08-f9b2-5e30-94e6-e42b9675d5b0 | signoff | AUTHORITY HOLDPOINT
6d7e7294-3206-576a-ba5b-126896703b42 | checkpoint | 2.03.04 - Steel supply
cd52136a-c9d4-5831-aea8-12213b87de04 | note | Acceptance / Conformance Criteria - Certificate of origin for all steel reinforcing supplied
c32a9e64-feb2-5357-977c-a0ea690c6f77 | note | Standard / Specification - NA
a3faaa58-6d64-5bd0-9fd7-32d043112ae0 | note | Verifying Document - Certificate
ac279921-0b83-5fc6-b65b-6a9661f31e6a | note | Frequency - Each batch of reinforcment
6ee83ece-47f2-5f84-a638-f6574082eb9c | note | Activity - R
a739393c-522c-55bc-82a7-f7848d71108d | note | By - ENG
5e1d4271-1c6a-55dc-8665-e0ceef7f76d0 | section | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
f8c61d8a-85ba-5858-a5de-e785f4b724f0 | checkpoint | 3.01.01 - Temporary Works
7a89cb0e-af59-5896-a2b9-fb78b0fc3f45 | note | Acceptance / Conformance Criteria - Temporary works to be installed as per design drawings. Permit to load to be issued by temporary works inspector prior to loading element
7d72e1c0-8698-5fef-9d3c-00553de45152 | note | Standard / Specification - Downer
268ae1b7-092e-5e19-b760-b6280ebf8aed | note | Verifying Document - Permit to load
d58d1e61-9a2a-5061-8e60-b1f63cec00ce | note | Frequency - As defined in the temporary works design
b05aa2c5-6bf0-5f53-9fe0-72278009cc84 | note | Activity - H
12b21f7c-cbac-5728-bde7-3a3dd01e4f72 | note | By - PE
ef898241-6e95-5d7b-a013-b3fe694bf8e6 | checkpoint | 3.01.02 - Reciept of Reinforcment
29708042-3eb0-50f7-9817-eb1a9ed77b37 | note | Acceptance / Conformance Criteria - Reinforcement checked against bending schedule. Bars correct length, size, shape, grade, and free of defects.
9383dd6c-3a23-5736-9b3b-d2a687aa3ac8 | note | Standard / Specification - IFC Drawings, SS 2142
8e0a3b5d-f574-58c2-a4b4-139c394a9c31 | note | Verifying Document - Photos / delivery dockets
b219cff3-ff78-58cf-88c5-f2f1ca7b5ce7 | note | Frequency - Each pour
f5b65f4c-8970-5e55-b595-61c9db5ef0a2 | note | Activity - I
3e1874e7-c0c6-5220-814d-54eb5ab369b2 | note | By - SE
46b28df8-05ce-59e1-b2e7-735fbd020425 | checkpoint | 3.01.03 - Reinforcing Welding and NDT Inspections
621a163f-01e9-5398-bb79-7869eccdb7c0 | note | Acceptance / Conformance Criteria - All reinforcing steel welding should comply with AS/NZS 1554.3; and all welded splices shall also conform with NZS 3109 Clause 3.7.2 or 3.7.3.
eafe6a90-fa22-56e6-9054-351ea8087d7b | note | Standard / Specification - SS 2142 - 9, AS/NZS 1554:3, NZS 3109 Cl 3.7.2 or 3.7.3
f357cc29-75cb-5f9b-9d79-dba20552df1a | note | Verifying Document - TPI Report
f7185df9-611f-5c96-b8d6-22fc180b0bd5 | note | Frequency - Each weld prior to installation
4aafe222-7473-5909-a3ec-9b3cf74c4081 | note | Activity - H
49be0430-0e13-529c-8f5e-421ddf8ab1ee | note | By - TPI
fc30800a-1954-5914-a106-a44019e632c9 | checkpoint | 3.01.04 - Pre pour inspection
f862655c-6cf6-5229-95bf-2a8639fd5515 | note | Acceptance / Conformance Criteria - Pre-pour inspection checklist undertaken by the Site Engineer and captured on the ConQA web app. All aspects of the element to be checked against latest construction drawings and specification requirements.
78c31cf3-c538-5847-9598-26e5ea679dc5 | note | Standard / Specification - Downer
90c72c06-1fae-5e17-918d-d497af290eb7 | note | Verifying Document - Pre Pour
5780eb5a-ac86-56ef-b2f6-012e0edd49b3 | note | Frequency - Each Pour
003b6c68-e85d-5ddb-9a70-ece8b19ef48e | note | Activity - H
18614d22-a548-5581-8157-f27809e610ce | note | By - SE
fe4912e5-6afe-534b-996d-3559c2095fb4 | checkpoint | 3.01.05 - Engineers Inspection
6b41f6ac-e96a-538e-a166-6433c42621c2 | note | Acceptance / Conformance Criteria - The Contractor shall advise the Engineer when he intends to commence placing concrete. No concrete shall be placed until the Engineer is satisfied that the requirements of this Specification and the Drawings relating to formwork, reinforcement and construction joints have been complied with entirely.
c571cc27-1280-586f-b69c-9bd61ea0feb8 | note | • No concrete shall be placed in the absence of the Engineer without prior acceptance.
e165b02b-77f5-5280-963d-bbb06b0c5cac | note | Standard / Specification - SS 2146 - 6, PS - 2.2.16
f9967265-bb1d-5865-a008-8406f0714223 | note | Verifying Document - Hold Point Release
1d714eeb-0c46-5abb-8d10-b6ef7993b3b7 | note | Frequency - Min 48h Notice
849b583b-8f9a-556f-89f9-972ded875f32 | note | Activity - HP
69c2d6b0-7d6f-5418-9431-68fd4cfd6861 | note | By - ENG
fa2636d9-f598-56d3-96be-087715e624d9 | signoff | AUTHORITY HOLDPOINT
a2e6c8ef-339a-5b05-bc26-d8ffe4d69a51 | checkpoint | 3.01.06 - ESCP
ede482ff-3da6-56f9-80af-4253fdfed48b | note | Acceptance / Conformance Criteria - All erosion and sediment control measures are to be installed and maintained in accordance with Site Specific ESCP
eb0e2b42-e267-5574-8a3b-ac752fabcb0f | note | Standard / Specification - Site Specific ESCP
7a68ee6c-90ec-5c9c-bf70-a18db77ce92e | note | Verifying Document - Acceptance
164883cb-e145-5c11-abd4-4671c81df430 | note | Frequency - Each pour
643b731d-b5f4-5cf6-864d-ad78dae0fea6 | note | Activity - I
84d2aafe-d2bc-54ca-8537-7b0ce2e5f43e | note | By - SE
15321e5e-1bc5-5c84-b504-2bac5808d544 | checkpoint | 3.01.07 - Concrete Cover
2a8cbcdd-8da9-5397-ac26-b9973c34f436 | note | Acceptance / Conformance Criteria - Concrete Cover:
473fc378-500c-5a22-b5cc-6bd7fb2b8d81 | note | • 75mm - all concrete cast in contact with the ground
b48eb42f-85a6-5aa6-b267-165bada20d36 | note | • 50mm - where protected from soil contact during casting by formwork or by a suitable damp-proof membrane
38c7e5bf-a7df-5ca4-8c89-66e9dfa47b8b | note | • 40mm - standard unless noted otherwise on the drawings
d240c507-03e7-59c7-b7e7-7e75e70f775a | note | ○ Tolerances:
cc729938-3501-5cc3-a045-486d4be17f2f | note | i) In slabs and walls ...... +10, -0mm
486ee57a-6b95-54ab-bcb5-62f8e703fab5 | note | ii) In beams and columns ...... +10, -0mm
7523290d-4e03-57ff-a80a-fc860642d12e | note | iii) At ends of members ....... +25, -0mm
6ac3ed77-c9c6-5483-9468-c40bad194f4c | note | Standard / Specification - IFC Drawing, NZS 3109 Secion 3.9
664ad51c-1c8d-57ef-bb07-c9a3e47c5770 | note | Verifying Document - Approval
dd311c62-4017-5870-ba60-92a97c3e6c17 | note | Frequency - Before concreting
f1a3cc85-ee7b-5ead-8460-52c1917dbf51 | note | Activity - I
b833a218-7ebf-579b-8b7e-93d19a0f325b | note | By - SE
3f1c0e33-ff5c-5ed6-b469-e8e804c00f1e | section | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
2cdd80a4-05ed-58e4-8feb-895348ef5b85 | checkpoint | 3.02.01 - Unfavourable Conditions - Cold Weather
6a8560a9-58c6-565f-a814-7cf8aefdf123 | note | Acceptance / Conformance Criteria - Concrete shall not be placed in conditions where temperature is below 5°C with temperature decreasing or below 2°C with temperature increasing.
5de8dc23-9812-573d-bfcb-272bd5b75b9d | note | Standard / Specification - PS - 11.5, NZS3901 cl 7.2
1159dde7-0450-587a-a76c-4bfb012db192 | note | Verifying Document - Pre Pour
e339b2d5-99f4-51e4-b667-c48eab201223 | note | Frequency - Each Pour
5b24094a-d114-5845-9076-e59f68bd32db | note | Activity - R
9cbdec74-f0ef-5b43-b9e2-9a9dd711d1ed | note | By - SE
22145d20-ce1f-50ee-b7a8-9cb075881db0 | checkpoint | 3.02.02 - Unfavourable Conditions - Hot Weather
416f2959-f198-5ce8-b3fc-f41623f6d1c2 | note | Acceptance / Conformance Criteria - Concrete shall not be placed in excessively hot dry conditions. Concrete temperature should not be higher than 30°C
c4017fc2-5cc6-5ed2-aecc-3cd472cd11ef | note | Standard / Specification - NZS3901 Cl. 7.2.1 & Cl. 7.2.2
7cf85b13-fde5-5929-abea-2833a90b1107 | note | Verifying Document - Pre Pour
6ea5a23e-f915-56e1-af73-6e75968177d9 | note | Frequency - Each Pour
d61eb2b7-b7eb-562f-956a-849d87435111 | note | Activity - R
e53d6810-9de7-51c0-ae49-d6cd3962be32 | note | By - SE
ae059ad9-e8e7-5f60-b8f6-2222bb641fbd | checkpoint | 3.02.03 - Unfavourable Conditions - Rain
5a640c52-faa6-5202-a76e-d4bd4fc98f28 | note | Acceptance / Conformance Criteria - Concrete shall not be commenced when heavy rains is falling or threathening and if rain commences during a pour, the work shall be protected as directed to prevent damage to the concrete or to any newly finished surfaces until the concrete has set to such a stage as to withstand leaching of the cement.
e38e45b4-26f3-57ea-b1f5-e6e3dfc71346 | note | Standard / Specification - BBO SS2146
eb5c7bf0-76b5-58ed-a9c4-4eb656bdac7a | note | Verifying Document - Pre / During Pour
087aa4bd-c49c-5ac5-bf64-539c410a4ea1 | note | Frequency - Each Pour
f1d81280-3f14-5896-83a3-f4865e556fa6 | note | Activity - R
a02e601d-5d77-5dcd-9aad-b1dc81b67ac2 | note | By - SE
31ba85a5-28ac-5163-9343-8db87536557b | checkpoint | 3.02.04 - Construction Joints
fffeb533-6edb-5704-8ade-0b8ceee564ff | note | Acceptance / Conformance Criteria - Where a concrete surface is to act as a construction joint to receive infill over or adjacent, the contact surface interface shall be prepared to the Engineer’s satisfaction to be clean, free of laitance, and with a peak to trough roughness of not less than 5mm to ensure compliance with Type B construction joints as defined by NZS3109 Section 5.6.
01f58446-97c4-52e4-a945-5eb269dcf007 | note | Standard / Specification - PS - 11.5, NZS3109 Section 5.6
89bede1c-86fb-5c84-a3e2-00e8ac30792e | note | Verifying Document - Pre / Post Pour
e9cedcb0-42e5-57cf-88c1-caf41ca6b7cd | note | Frequency - Each Pour
16967cbe-34de-5cd1-89de-23142ad8c8f3 | note | Activity - I
e4973b09-f7f8-5df5-8195-db593cb80820 | note | By - SE
d1fd148f-0a46-5f76-a8dd-18da03cb8aa4 | checkpoint | 3.02.05 - Delivery dockets
d98a8ce7-0ca1-5985-bbb1-85afa1598766 | note | Acceptance / Conformance Criteria - Each batch delivered shall be accompanied by a delivery docket certifying the cement type, maximum aggregate size, specified strength, slump or spread, date, time mixing completed, and time water added at the plant.
f4ef2090-f71b-5210-8d0d-5a144583f357 | note | Standard / Specification - SS 2140 - 4
0aecafb4-78a9-502f-81e0-b64d12ece63d | note | Verifying Document - Dockets
9bbed5d5-e37b-5ab3-adbd-4f8f4c8afadd | note | Frequency - Each Delivery
7fa309d1-bf96-5090-bcbd-1cca35864793 | note | Activity - R
755d7aa7-da79-58b0-a4a3-bd7ce82047d1 | note | By - SE
24d977be-ac95-562c-9c0b-3d0341bef1b3 | checkpoint | 3.02.06 - Slump tests and spread tests
f2441e49-3296-583e-9ce8-e22680f06a24 | note | Acceptance / Conformance Criteria - Slump tests or spread tests shall be taken for each delivery of concrete and the results recorded by the Contractor
e5fa4ddd-06d0-5cb1-ad88-ce4649aa726c | note | – – – – – – – – –
03f753c3-2a28-513d-88ed-3ceadc10f5d4 | note | Table 9.1 - Tolerances for nominated slump
e08bce48-9bac-5b29-88c3-8bb04ef383cc | note | Nominated slump (mm) ¦¦ Tolerance for snatch sample (mm)
dcafbe63-35bd-5a1b-a604-704578def0f8 | note | – – – – – – – – –
59f54f36-d52d-5e7a-aa04-202f56923ac4 | note | 60 or less ¦¦ ±20
232c0dd5-c132-5513-88e8-33442e1837ab | note | 70 - 110 ¦¦ ±30
ab5f2efa-b0dc-57f5-a59d-0322ffb7152b | note | Greater than 110 ¦¦ ±40
45e41b81-25b8-5954-994a-c8bf9bfef2d9 | note | – – – – – – – – –
d52ab3fe-b28c-59d8-9327-730a4b8683c6 | note | Standard / Specification - SS 2140 - 7, NZS3109 Table 9.1
f2d69254-ddb3-55ee-8197-8b08070d0f38 | note | Verifying Document - Photos or slumps and on-site records
789c6e42-93ec-5498-8f69-fe61dfb33dd9 | note | Frequency - Each Delivery
5dddbaae-acbc-52f1-9211-5852dd09874a | note | Activity - I
0fd42dd4-87cf-5055-bc83-edc7f9e2a40c | note | By - SE
483a6e81-8e18-5117-8a69-9746dedeec1c | checkpoint | 3.02.07 - Time Limits
b3091f5d-d71f-5816-80b6-86c2a0670403 | note | Acceptance / Conformance Criteria - Concrete not placed and vibrated in forms after 90 minutes have lapsed from the stated time that water was added at the plant, or within 30 minutes after discharge from the mixer or agitator truck, may be rejected by the Engineer.
a456db93-00ad-592a-a56c-149b9c53da3a | note | • Concrete not placed in its final position in the forms before initial set has occurred shall not be used. For concrete mixes containing set accelerating admixtures the above times shall be halved.
d25a023b-75f1-5775-b1c3-3ed1b007a5a4 | note | Standard / Specification - SS 2146 - 7
5537c1d4-520f-5a57-b28e-4b1b001a3064 | note | Verifying Document - Site Notes, Batching record, Delivery dockets
ebb34dd9-ad84-55ca-b132-95e943400b01 | note | Frequency - Each Delivery
cc16ed49-1224-5b63-9312-84f903825769 | note | Activity - R
cf396d5c-8453-54d4-bc31-30640606f35a | note | By - SE
b4683937-8bcc-5cb1-9a3f-fc4a9424d54a | checkpoint | 3.02.08 - Compression Testing
12a81dfc-2735-518f-9f95-89dc89034743 | note | Acceptance / Conformance Criteria - Compression testing shall be carried out at an independent laboratory accepted by the Engineer.
c7d783a9-365c-53f6-949c-2cb040613a66 | note | • A set of specimens for compression tests shall consist of four specimens for each concrete pour, one of which is to be tested at 7 days and the remainder at 28 days. Cylinders are to be cast on-site straight from the truck, not at the batching plant.
66c7fb1f-da87-5bcf-b5c9-ad6c8729ace6 | note | • Larger pours greater than 75m^3 will require an additional set of cylunders to be taken.
f0a2235e-fd2f-53a4-84b0-dbb67da813d3 | note | Standard / Specification - SS 2140 - 4, SS 2140 - 7
661b2ca8-b561-57ab-a20f-bd7617dc146a | note | Verifying Document - Compression Tests
dd8d6713-8be2-5337-b1ff-0335454cbec7 | note | Frequency - Each pour
31fc172e-75a7-54cb-aa92-fcefd81c6e36 | note | Activity - R
5d39b2a3-1f62-5f02-a867-1b1eefb8f56a | note | By - SE
b9cf4c81-7b99-5356-9f88-4e32eb55a977 | checkpoint | 3.02.09 - Concrete finishes
770204c3-cf45-594e-a884-cba59d9b5e04 | note | Acceptance / Conformance Criteria - Concrete finish are to be as specified by NZS3114, scheduled as follows:
80c37f66-0833-5573-8d63-4410d802eae2 | note | • Barriers: F5
e67cc16d-b274-5f09-8576-d54fe382002d | note | • Precast elements - exterior faces : F5, connecting faces to other elements: Type B construction joints to NZS3109
ee5e4f73-3490-5ba5-bcdd-ac92d38b36a5 | note | • Exposed concrete : F5
0568219d-3ef7-596c-8c35-e10629522bcd | note | • Element below ground: F2/U2
1b536b9a-0e6b-521c-aa02-5d824b0c40f2 | note | • Top surface of desk: U5
e515470c-c59a-5eef-9aa5-46ebe034f185 | note | Standard / Specification - NZS3114, NZS3109
e208738b-ba48-5e9e-be4f-46bdc6d07cf9 | note | Verifying Document - Approval
0b85def7-79c7-5118-bd36-785d474d449d | note | Frequency - Post concreting
34150cc9-920a-5e73-b544-e09b5385fc23 | note | Activity - R
cf5da204-6b8c-5b5c-ada6-11f80e6204ea | note | By - ENG
9b34ced0-fdfa-5735-8e20-86feead4b0ed | checkpoint | 3.02.10 - Curing
5a0825fb-6bbe-5e63-ae9f-91c81e1c797d | note | Acceptance / Conformance Criteria - Minium of 7 days wet curing for all concrete including prestressed concrete after completion of accelerated curing
974a1cc4-2684-5006-89cc-b3ebecc7b10d | note | Standard / Specification - SS2146 -11 Construction Drawing
ab88c804-4ce9-555b-9084-be490325f69d | note | Verifying Document - Acceptance / Repair Details
f55a6a61-7f17-5324-b8ee-f16e7432c137 | note | Frequency - post concreting
52f72b64-4d1d-58a9-bb16-edad19b78ed1 | note | Activity - H
1db4265e-6898-54da-a6f7-e04a20073316 | note | By - SE
8d49e4e1-04da-5725-bfe0-ecbdf7642664 | section | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
cc9fc843-71c3-5755-969c-c793c2e92d67 | checkpoint | 3.03.01 - Falsework and Formwork Removal
dec414b1-eed3-5792-b204-68a2070abe22 | note | Acceptance / Conformance Criteria - Formwork shall not be removed until minimum periods set down in Table 5.3 of NZS3109 have elapsed.
c3a30472-0545-5670-9d32-721a967f62f5 | note | • The stripping time may be reduced if it is shown by field-cured tests that compressive strength has been attained of twice the stress to which the member will be subjected at the time of stripping or as directed by the temporary works engineer.
0da5f71b-9194-5afc-ad29-138f5866a562 | note | Standard / Specification - SS 2144 - 10, NZS3109 Table 5.3 Downer
4b26deef-4ace-5f06-8d86-e0cab898fa1e | note | Verifying Document - Approval
b43b8365-e58a-5ded-9b7a-6c6a11d3a619 | note | Frequency - Before removal of Falsework and Formwork
02d06e25-cdd1-52b5-ad9f-8966c91e5686 | note | Activity - H
ddfc129c-97cc-5641-b3d6-06df2fa75f54 | note | By - SE
8f6a83ad-939a-50dc-9b15-99bd646b437b | checkpoint | 3.03.02 - Post Pour Inspection
0b181a42-fa10-59a6-81ca-48ba475173a3 | note | Acceptance / Conformance Criteria - Post pour inspection undertaken by the site engineer and captured in the ConQA web app. Engineer notified of any defects.
2aff5a62-dc55-5de2-8f1e-68bd2ad456cd | note | Standard / Specification - Downer
762c0092-dba1-5f27-a6da-f9d21d17bd6b | note | Verifying Document - Site Photos
63b0215c-5fc3-5895-b258-2afd6a5afb14 | note | Frequency - Each pour
de152083-4e82-5c5b-89df-3aa6966c3d6d | note | Activity - H
703189ef-6266-513f-8080-f3aa10c07f00 | note | By - SE
33e38919-778f-5bb9-9438-942cff44e2cd | checkpoint | 3.03.03 - Concrete Repair
1bdddc29-7007-5de3-b762-31e575623ae6 | note | Acceptance / Conformance Criteria - Repair of any minor surface defect or structural defect of concrete shall only be carried out with the Engineer’s acceptance. All repaired concrete shall have the same strength, durability and surface finish as the parent concrete unless otherwise accepted by the Engineer.
e8ea1016-5725-5913-87fa-d8f8d68e316a | note | Standard / Specification - SS 2146 - 11, PS - 11.5
bd095117-f326-526e-98b6-ae8000ddd20b | note | Verifying Document - Acceptance / Repair Details
5ca7e0d8-1790-5caa-8305-d19193a3ca9d | note | Frequency - Prior to Each Repair
a50e1e6f-f2d3-53a4-a30c-b8d6a50966e0 | note | Activity - HP
daa68760-d745-5e56-99da-3c3019dbefcb | note | By - ENG
49cc508c-621b-5144-b075-baee96e69596 | signoff | AUTHORITY HOLDPOINT
43b7f820-48cc-5947-a616-927597f2dd0b | section | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
1c6f04d6-4ac2-5a3d-bfb6-c507c6b6c211 | checkpoint | 4.01.01 - Construction Record Compilation
fa54a5fb-70fe-5579-8986-21f71eb84ba6 | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
3b97f4fe-707d-51da-9fec-b13c052aade7 | note | Standard / Specification - Downer
a68ede23-427e-5f8f-80c1-daff6a0b4bf9 | note | Verifying Document - Records
4f3869bb-e03a-5c6a-b7f9-577b56010a16 | note | Frequency - Post construction
38826559-5404-5117-bba5-164388588f7d | note | Activity - H
6b7048a8-8b04-51a8-8c19-bed142084bf1 | note | By - SE
aa651912-aace-521c-aa99-e264193a14ef | checkpoint | 4.01.02 - Survey Records
500135bb-9cef-5337-ac14-f192690029f8 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
e7f5a82f-265f-5040-a61f-9736a97d1edc | note | Standard / Specification - Downer
97d3b3b3-b255-58a0-949a-7a6e9715afd3 | note | Verifying Document - Records
96b52f1c-77c5-5f23-b94f-c39d0692557f | note | Frequency - Post construction
b547ae6e-ba0b-58be-936a-edfd767d4e44 | note | Activity - H
8225d0b9-eeae-5070-9cd3-3ca58bdc7832 | note | By - SV
ff9523c6-e6b4-5ae2-98cb-b74ed9010a3b | checkpoint | 4.01.03 - Redline Drawings
df552f67-9595-5147-8470-d85d458a97c5 | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
0696bef3-f497-537b-b93b-6175cd96feed | note | Standard / Specification - Downer
f3c1c9cd-0020-566d-b289-9fc5aadf7a3c | note | Verifying Document - Redlines
77cedc8e-6b60-5514-bca8-5d9867a97457 | note | Frequency - Post construction
229b9136-df9d-5d15-b775-d41a69cd622b | note | Activity - H
29bd9bb4-29d0-5090-8cbd-e8704572436d | note | By - SE
ac1ea9c0-9abb-5c2e-a566-b437f58dd944 | checkpoint | 4.01.05 - Delivery dockets
e62d23f9-8df3-5761-87aa-0d54b31ef97f | note | Acceptance / Conformance Criteria - At the completion of the Contract a schedule of delivery docket numbers for all concrete supplied shall be forwarded to the Engineer.
a97e0c17-6693-5ee3-9288-105e7865c27a | note | Standard / Specification - SS 2140 - 4
3448efdd-5a80-5913-a8c3-1a2e38df75c6 | note | Verifying Document - Dockets
eb9fa779-7e94-529d-a4f8-b10575b7a698 | note | Frequency - Post construction
474db2fa-1510-5eb4-ac17-126827ef5127 | note | Activity - H
5e99b310-752b-5256-bdff-e3220ed45d9d | note | By - SE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
c2c794f0-0e10-5ccc-ba18-47b2cfc82ddc | checklist | ITP - Mangakootukutuku ST Rev 3 | itp | ITP - Mangakootukutuku ST Rev 3
6c8b6b73-6473-5f13-adda-ca5e8c131c88 | section | A. Pre-Construction
d0b118bf-4866-5dfd-a7a4-3cb57a95fc8e | checkpoint | 1 - Shop Drawing Approval
7f551341-4092-5f41-b608-365d16f7af0a | note | ACTION (Hold, Monitor, Witness) - Hold
21a25c85-7669-5e43-b881-cb382d0cdcf1 | note | Detail - Shop drawings to be submitted for approval.
bffa2df9-33f7-511b-b3fc-ab1be1a76bea | note | Reference - Structural drawings
665c516d-76b1-5aa6-9126-10f6537864fd | note | Frequency - Prior to casting
f573a840-2c00-5fb2-b5ab-a06cf4dd26d7 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
94e10edb-c26e-5561-a211-7af1d2f73c9a | note | Conformance Criteria - Approved IFC Shop Drawings
a578b38c-a938-5cc7-a081-f444b003b6cc | note | Records - Client approval
0eb78f61-f25f-583d-9e72-ec868b88f33f | note | Responsibility - Project Manager
46a3e53b-75cc-5a54-afb9-d71434340129 | signoff | HOLD POINT
f19fea31-2d56-544c-8b5c-1d88d82f2dca | checkpoint | 2 - Concrete Mix Design Approval
b4a7e83d-f7e2-5386-a8d0-bdce94a58340 | note | ACTION (Hold, Monitor, Witness) - Hold
a361c484-876b-5df1-ab52-16c3d4d3a3d1 | note | Detail - Concrete mix design to be submitted for approval prior to concrete being supplied to site.
1742277d-7193-50aa-8080-d6b50de0bcde | note | Frequency - Prior to casting
9dc02ba3-edcd-52e5-ae2e-27beb06afe27 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
8aed14d2-9e72-5d42-9292-552147cc8c76 | note | Conformance Criteria - Minimum compressive strength at 28 days 60MPa. The mix design to comply with aspects of the contract specification.
3eb4a396-88d9-5085-a6a0-3eff50c8f8db | note | Records - Client approval
8c70c253-b98f-5db0-aa4d-6fe8b1c7b33c | note | Responsibility - Project Manager
42a2780b-6b9b-5f60-ba21-16129f643dea | signoff | HOLD POINT
f429301c-ca52-577c-ac36-680c886f0f24 | checkpoint | 3 - Lift Design
72a3e126-69fe-5331-8d3c-3cb9bed90c53 | note | ACTION (Hold, Monitor, Witness) - Hold
8e3c3373-6ac1-5937-81fe-bad027c8e376 | note | Detail - Lift design provided for units demoulding, storage and transportation.
247154f6-4b94-573f-b348-c9c4696d731f | note | Frequency - Prior to casting
e2060d2f-34fe-57ac-b22f-dc007a76e3d5 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
a79b995c-26bc-5e0f-9381-9f98a434f799 | note | Conformance Criteria - Specific Lift design (Lifting eyes and position) produced and followed
3483a0fd-cc1f-59a7-b920-e5e057f9c41b | note | Records - Lift design Shop Drawings
b905620a-4d8d-5d4e-a3a7-53824569a358 | note | Responsibility - Project Manager
d8703e80-0411-5b56-918e-675a5eb7b7e9 | signoff | HOLD POINT
0a8c134b-db66-5671-ab98-07875080f8ec | checkpoint | 4 - Steel Reinforcement compliance
8a87d0fa-e2d7-5382-abbb-7559965df98c | note | ACTION (Hold, Monitor, Witness) - Hold
dc2aa740-0704-5c57-9315-5bd3434e5084 | note | Detail - Mill certificates for steel reinforcing to be provided
84b89b85-f301-5869-80df-0741626d9978 | note | Reference - AS/NZS 4671
0be59b34-46b4-59f8-be20-5324c088df7b | note | Frequency - Prior to casting
e18e88e4-798f-5709-9d17-caeba780f4f5 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
435840fc-5c7e-5ed7-8196-c57795815028 | note | Conformance Criteria - Steel to be manufactured with ACRS certificate details and verification
9aef982d-f1ee-5d4b-8c43-aa4585465456 | note | ○ Mill certificates to match ACRS certificates.
4a9eef66-564d-52e1-bdb1-749ac415648e | note | Records - Mill Certificates Detail sheets Test Certificates
224e08df-d43c-5baa-850c-365e78cbec56 | note | Responsibility - Production / Quality Coordinator
6416c12c-d6f1-5877-99c9-3798aa512c21 | signoff | HOLD POINT
feaffeb9-02cf-5eff-a2da-f2aba24f5112 | checkpoint | 5 - Steel pre-stressing material (Strands) compliance
31c2bab4-6967-5982-8252-679329640788 | note | ACTION (Hold, Monitor, Witness) - Hold
e6226ee2-84ea-510d-a413-1f05e36cbfda | note | Detail - Mill certificates for prestressing strand coils to be provided
32cd856e-af64-555b-bbcb-beafca175edb | note | Reference - AS/NZS 4672
0d6a44bf-7515-528e-b9ff-e27410caf60a | note | Frequency - Prior to casting
24a4e194-84f5-5cc7-bc56-9844e407437b | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
ad0406fe-662b-544c-87dc-3fa17e11c21e | note | Conformance Criteria - Prestressing strands (coils) to be supplied by ACRS accredited Manufacturer.
e681fcf6-ed21-5216-bdd0-c80ff47f280a | note | ○ Mill certificates checked against size, type and strand - mill certificate to match ACRS certificate
661a7406-1789-5ca9-8dd1-9ff81b2232f8 | note | Records - Mill Certificates ACRS Certificate
f3e0a21c-8f19-552d-acf6-27af1d03f4df | note | Responsibility - Production / Quality Coordinator
613c6cdd-2b14-54c6-91fb-ff2b855bb469 | signoff | HOLD POINT
b7d4cbf2-f5ad-5ae7-ab1c-e12d844f077f | checkpoint | 6 - Design Stressing calculation
02e5ba00-1841-508e-88e9-39d62acb03da | note | ACTION (Hold, Monitor, Witness) - Hold
b61dc034-995f-5a8f-b50b-d857eafda1d1 | note | Detail - Design stressing calculation and calibration certificates to be submitted to the Design Engineer
c04a58dc-439f-5d7d-8fa1-63ff20c0c2d8 | note | Reference - Structural drawings
22e98be8-f1e3-57fc-a027-d820b4865448 | note | Frequency - Prior to casting
84a194d4-cd04-59ef-bc72-be360077947b | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
23dbf582-8563-551b-b047-6676ee83726d | note | Conformance Criteria - Expected extensions and gauge readings to be calculated for each cast.
0460bfcb-18af-53d5-84e9-334ab18aa823 | note | Records - Design Stressing Calculation Calibration Certificates Client Approval
b7f2b866-abde-5ca0-9e68-6218a4aed178 | note | Responsibility - Project Manager
d11d0c5b-a9a2-5352-8a9a-8040f61d2da4 | signoff | HOLD POINT
cc6ef693-d53c-5381-8589-6b47637220de | section | B. During Casting
ae49fb65-5ec8-5106-a68e-1fa4bdb19de1 | checkpoint | 7 - Steel Reinforcement cage assembly
bbb86996-1306-53de-92bd-7b21db04436e | note | ACTION (Hold, Monitor, Witness) - Monitor
d6e9e554-3562-5659-b411-0a6dbf8fd943 | note | Detail - Steel reinforcing cage to be assembled and inspected.
d724b6cc-c017-5e9a-9bea-8e52bbcf82ee | note | Reference - Approved shop drawings
d7ab26fa-5758-5365-8712-d8e50b24bf35 | note | Frequency - Prior to each cast
3f6e926d-9ab1-5a6e-bdcc-89f9f4436e82 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
15bc6d2f-fa18-5f0b-ad6a-c27f4c806501 | note | Conformance Criteria - Cage assembly to comply with correct size, class, length, shape and location/spacing as specified in shop Dwgs.
a5492493-815d-5d4a-900f-e4bce94a1b05 | note | ○ Free from visual damage.
022fa99d-8580-5db1-94d3-9fbbb8691e3b | note | Records - Pre-Pour Inspection sheet REO detail sheets
9cfbf8d0-b2c5-52d9-bb65-65a95a91455f | note | Responsibility - Production / Quality Coordinator
20fdc9c5-8386-5839-a7a9-a01dc047c7df | checkpoint | 8 - Mould Preparation
43fe340e-b9b0-538d-8621-ba7f3318bfb9 | note | ACTION (Hold, Monitor, Witness) - Witness
fe206031-d2ba-5e19-857b-d0740b5960e0 | note | Detail - Before casting ensure mould has been prepared to comply with tolerances.
0c681922-0513-523e-bd51-52e5225d4a57 | note | Reference - NZS3109 Table 5.1
91ae295d-84a2-5001-8bba-931750dbddd5 | note | Frequency - Prior to each cast
4663dd7a-dc7f-5241-a762-c541366ac4a8 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Measure
c26ea311-eda5-540f-89f0-1c218f3670a9 | note | Conformance Criteria - Tolerance on placement of moulds shall be a per NZS 3109
00d231e6-2d84-5b52-b840-9513bd292965 | note | Records - Pre-Pour Inspection sheet
76e7dcf0-de89-5a71-b6bf-23284989ec0c | note | Responsibility - Production / Quality Coordinator
3e4b9585-9ca9-5197-acc4-c8df288417f1 | checkpoint | 9 - Pre-Stressing
9c5e267f-852c-5784-bb06-b77b0f341dd4 | note | ACTION (Hold, Monitor, Witness) - Monitor
156da291-3e2f-538c-a6f1-8f01b26d7867 | note | Detail - Review actual strand extension/pressure compliance with approved design calculation. Draw-in measurements to be taken and recorded
89d5f0b4-87a3-513c-a8bb-fde46de78203 | note | ○ Check that debonding has been included as required. Debonding shell be by plastic sleeves around the strand.
53513eea-415b-5397-bace-18380b39200a | note | Reference - Approved shop drawings Design Stressing calculation
f6443357-0e8a-5be2-920f-9388d9a4ce65 | note | Frequency - Prior to each cast
dc95e6dd-a9f5-513b-ac08-2eb177d117ce | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection/Measure
ee1c4d01-6f3b-50de-a259-994acbbcca4a | note | Conformance Criteria - Stressing data/records reported on stressing calculation sheet.
d94f394f-2237-54c6-ba30-aaa4093be6d7 | note | Records - Stressing Calculation sheet Pre-Pour Inspection sheet
6c33327f-4ece-5777-8fbe-9a8e26d44332 | note | Responsibility - Stressing Controller
fa37f0bd-e6ea-55a3-96b8-11656964e3e5 | checkpoint | 10 - Steel Reinforcement Placement
71101c6f-a534-50b3-9511-2c6063359adb | note | ACTION (Hold, Monitor, Witness) - Witness
f1dd1e46-5c1b-5492-8045-ebc58b503aa4 | note | Detail - Reinforcing steel shall be handled, placed as per NZS 3109.
340e129f-d759-5aab-bbf0-6227e531e49b | note | Reference - Approved shop drawings NZS 3109
b691864c-eca4-5a3e-8d5e-a3aa6ddb08bd | note | Frequency - Prior to each cast
6c971a7b-073f-51bc-b5a5-0e8064f8f469 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
697d608b-a8b9-5e91-9866-7308204ce618 | note | Conformance Criteria - Steel reinforcing cage placed as per approved shop drawings.
c043c1fb-3973-50ca-80a1-8f4434cc8a56 | note | ○ Spacers shall be installed evenly to ensure correct cover as per shop drawings achieved.
4d4e6ca6-fc8c-567f-8dad-6d34b9197e87 | note | Records - Pre-Pour Inspection sheet
7f2a04b5-c7b0-53ef-b90e-14b915df5dc7 | note | Responsibility - Production / Quality Coordinator
778a00b0-3496-571a-93d9-dc583bfe2a5b | checkpoint | 11 - Cast-in Items
fe536922-ec0a-562b-8b32-da5cfe699326 | note | ACTION (Hold, Monitor, Witness) - Witness
7e6518c4-5902-5d48-880a-df652300e336 | note | Detail - All cast in items positioned as per shop drawings Lifters positioned as per lift design
fd745cbd-6b98-54d4-962f-e79c3285daac | note | Reference - NZS3109 Table 5.1 Approved shop drawings Approved Lift Design
f6f59f88-e7d5-54ce-9107-a68ee4b8806c | note | Frequency - Prior to each cast
662e8aa6-b9aa-58e6-9bb8-f5657702a15d | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
aca746dd-5131-5204-9a2b-f1cc75f1b6e6 | note | Conformance Criteria - Correct type and number of cast in items used Correct Lifters used, positioned in accordance with approved lift design
2ef43b5d-e49e-58dd-bb51-00dc5a337802 | note | Records - Pre-Pour Inspection sheet
eab0fc36-07a8-5e5a-b470-6c5fe90648d8 | note | Responsibility - Production / Quality Coordinator
7fbac7e8-a6c6-5c26-b4fc-6094fd0eaff5 | checkpoint | 12 - Pre Pour Inspections
9610250c-a6e8-5748-a901-50d9ec1f58d5 | note | ACTION (Hold, Monitor, Witness) - Hold
e169089e-503c-584e-a545-6ea525b5872e | note | Detail - Pre Pour Inspection shall be carried out before casting.
a73a93b7-54bf-577d-b463-728716aa1f09 | note | ○ The Engineer's Rep shall be advised at least 48 hours before the proposed pour.
5b7e1687-4e07-5373-ae80-e6e4c22163a3 | note | Reference - Approved shop drawings
ea266cef-f33e-5e17-8cb4-cddabe92dbd0 | note | Frequency - Prior to each cast
1a8e14fa-821b-5cbe-aba4-f90cedbbed80 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Measure, Document review
019ed32d-6966-5225-8f76-2a67e4bf6b5d | note | Conformance Criteria - Confirmation that the unit has been cast in accordance with approved shop drawings and NZ standards for tolerances.
a01183aa-1c69-5ad0-8267-d0479f1bcdb3 | note | Records - Pre Pour inspection sheet Marked up shop drawing, Stressing records
b5baa92c-78a5-5ac1-8c60-3f962fd9fa84 | note | Responsibility - Foreman & Production / Quality Coordinator
dfd8ab0f-53a2-55d2-81f5-18bdd3ddf2b5 | signoff | HOLD POINT
7d3a59d2-dc2a-573f-8a58-aa95cae36daa | checkpoint | 13 - Concrete Mix Conformance
311117ac-3155-5539-a777-674b996bf619 | note | ACTION (Hold, Monitor, Witness) - Hold
6db8b1b3-2817-561e-bf0c-593f1b25912e | note | Detail - All concrete dockets reviewed at time of delivery.
a165b695-2965-535c-bc57-2d3d04cb5ace | note | Reference - Approved mix design
9370f9fa-3cf8-5619-a925-3d62e5b8fe41 | note | Frequency - Prior to placement of concrete
6148a39e-7d5d-5efa-9bcb-455615636d8b | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
0c458253-3efd-59d6-8e91-7791f4319959 | note | Conformance Criteria - All concrete delivered to site shall be produced in accordance with the approved mix design
b811b79f-2d25-572e-975a-a02276a48af2 | note | Records - Concrete Delivery Dockets
4c842c98-2566-5e00-ad8c-cc5d77f34cd3 | note | Responsibility - Supervisor & Production / Quality Coordinator
ad1e779b-95bc-5a97-a643-d8f4dbc0ac59 | signoff | HOLD POINT
ec1444bf-f270-525a-bc56-e9c0aea58c32 | checkpoint | 14 - Concrete Mix Workability
7a334b4b-7737-5c51-866a-9c853b5cf709 | note | ACTION (Hold, Monitor, Witness) - Hold
fd3bc877-8753-5f64-9e66-453baed60ccd | note | Detail - Fresh concrete to be visually assessed for its workability compliance.
e46c0b51-3685-5315-8d13-c30cdecb41a5 | note | Reference - Approved mix design
0142e3c7-3508-5acc-9f85-df8e25e44292 | note | Frequency - Prior to placement of concrete
768a44ca-4a4a-5073-8b4f-c7328566a890 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
92f4fa5e-031d-5a99-ac4d-b449dec86fb0 | note | Conformance Criteria - Workability as per mix design.
90070146-4e54-5605-a12f-dcd06ee86053 | note | ○ Concrete slump test to be performed by concrete supplier before delivery
b6789452-9098-557d-b59a-48a6433402e6 | note | Records - Concrete Delivery Dockets
8595d649-ab63-5660-a481-42756681bb5b | note | Responsibility - Supervisor & Production / Quality Coordinator
3eb04312-7b4b-52b5-8734-9e952c1f6412 | signoff | HOLD POINT
0b42768e-638b-5ce9-a65f-50b098b8e7fc | checkpoint | 15 - Concrete Finish
ffda2a76-6528-5d93-a851-c9706278b15e | note | ACTION (Hold, Monitor, Witness) - Witness
48b8c739-dca4-5c03-b99a-a6d0e0aa3f04 | note | Detail - Concrete to be placed to achieve the specified formed and unformed finishes
42cd536b-8b98-5dbb-a933-2ab4e9951e9e | note | Reference - Approved shop drawings NZS3114
319497f6-1355-533d-b8d1-69845caef18f | note | Frequency - During and after placement of concrete
561d4630-0862-5e59-ad24-4fe0a5e8d775 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
47874d4f-1668-58a0-a01a-346d8df68456 | note | Conformance Criteria - ST Beam to be Type F4 finish
3ad84433-4b23-5d29-ba07-1b5d516cb884 | note | ○ All construction joints - Type B / UNO
d8c14651-d0e7-5a17-b51c-a4ff74c0bb2c | note | ○ Top surface Type B / CJ and U2 where specified
333da850-fdda-5870-9d8c-89652d76e88e | note | Records - Pre-Pour Inspection sheet
f7cb8e4d-b176-500d-9ca2-f77e871b02c6 | note | Responsibility - Foreman & Production / Quality Coordinator
c58e9127-52d5-57bf-9ba3-f187fd87775b | section | C. Post-Construction
6f20b392-5a93-5ee9-bfc6-936f7c903340 | checkpoint | 16 - Curing and Release Strength
83fe2645-c52a-5ed2-b008-4d454814155d | note | ACTION (Hold, Monitor, Witness) - Hold
67eb983b-0580-5566-84c6-27120456b012 | note | Detail - Heat accelerrated curing as per approved methodology.
71c95f64-4e80-52b8-9214-c5d34640cd49 | note | ○ 7 Day post mould water curing as per approved methodology
2e1e5b66-8947-5034-8df6-9cace7b9ee3e | note | Reference - NZS 3109, NZS 3112
1b3bb031-68ca-5dce-9cee-1faf40c0532e | note | Frequency - Prior to every unit transfer
29171571-516c-5465-aa92-036c69d303c3 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Testing (Schmidt hammer or Compressive strength test)
75ce6f2f-056e-5814-9266-d4528833d946 | note | Conformance Criteria - Minimum compressive strength at transfer of prestressed units to be 40MPa prior to stripping and demoulding.
a6a1b21e-1b8d-5ec7-8363-c7038caef5c4 | note | Records - Post-Pour Inspection sheet
35e0f182-6c39-5260-b30a-0f1e47a13019 | note | Responsibility - Production Manager
3ec34be8-0667-52d2-85e4-f9836add7efd | signoff | HOLD POINT
1f9a1267-9b7b-5001-a031-4440573331f2 | checkpoint | 17 - Transfer
dca831aa-0a41-55d3-bdb9-23f9f12f80a4 | note | ACTION (Hold, Monitor, Witness) - Monitor
86efa140-caa3-5d23-a936-c12143ffdc1e | note | Detail - Visual inspection to ensure strands are tight and no slippage of strand into concrete. Locallised spalling around full bonded strand at transer as result of excessive slippage will be identified as non conformance and the unit will be rejected and remade.
2c15f307-7610-5f79-928a-5f76b2be7231 | note | Reference - Approved shop drawings
2f770336-c37d-5921-88d2-d5adbe33ac34 | note | Frequency - Prior to transfer
7c20d68e-d849-53fe-a90a-9e62feba776e | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
e2c67bcd-cc11-595d-81dc-e2a00aff1b10 | note | Conformance Criteria - Stressing data/records reported on stressing calculation sheet.
e4cb9fd6-82be-54a2-8137-19bf8139eb78 | note | Responsibility - Production / Quality Coordinator
6b5d4cec-0d9b-5448-9da1-c734f865a051 | checkpoint | 18 - Draw-in
7a0c13e9-093c-5682-8d1b-e60370172781 | note | ACTION (Hold, Monitor, Witness) - Monitor
1e2fe925-028d-5379-890f-a0bd96d228bb | note | Detail - Strand draw-in to be measured on each cast. If ave draw-in for group exceeds 2mm, or 4mm for single strand, then results to be submitted to Eng
bff52761-f10d-5b32-9a96-c2e6f259adf6 | note | Reference - NZS3109 C8.72.3
66b150d8-cf4d-5c53-a9a8-19989e9dc75e | note | Frequency - Every unit - at transfer
941faba9-d19c-563d-a257-c361b146104c | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Measure
868bbe88-0540-544f-bde0-c635769310b0 | note | Conformance Criteria - Draw-in to be measured on each beam at transfer
efc87e3d-5551-5bc7-8473-64158b9bb748 | note | Records - Post-Pour Inspection sheet
3f5e4a31-7372-5378-8977-0209a93256c0 | note | Responsibility - Production / Quality Coordinator
ebb71627-7643-5d5f-961f-0e920d05b5ac | checkpoint | 19 - Lifting
c49d51f6-a795-5014-b414-bd86d118b587 | note | ACTION (Hold, Monitor, Witness) - Monitor
13ede2b5-5b4c-5a09-8046-aef69baa9e0e | note | Detail - Units are to be demoulded following lift design
60dab494-c2a1-50de-bfa2-3dc3b9ff4694 | note | Reference - Approved lift design
46f2cc6e-738f-5188-9f4b-ba8db6bbfd7e | note | Frequency - Every unit
7bfb66b1-e02d-576a-a838-e48e020d9746 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
ea91a55e-6c8b-59bb-9f0b-92c4eebc6c0e | note | Conformance Criteria - Approved lift design to be followed.
00d14c8c-7757-5442-8152-ec5f786dcde2 | note | Responsibility - Production / Quality Coordinator
157b3f4a-e957-520e-8ccb-c7e705cfdef7 | checkpoint | 20 - Marking
6ff1f621-a675-540a-aae3-a86d79a29035 | note | ACTION (Hold, Monitor, Witness) - Hold
c7fd609e-b2ac-5f38-885c-beb54ed5a4a5 | note | Detail - Units are to be clearly marked each end with unique number, cast date and installation direction (Super T).
161bd468-0322-5036-93be-26ac20754dc0 | note | Reference - Approved shop drawings
27d71e1f-5d89-55d0-8cc6-b04510b589b7 | note | Frequency - Every unit - after demoulding, prior storing
4abfe7b5-7b7c-5e98-b96d-29b109203c9e | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
abc4c0ea-d7ac-580a-9dbf-539e63312f44 | note | Conformance Criteria - Ensure every unit is clearly marked
80cebd3c-1d86-5073-baf7-4db5179ad035 | note | Responsibility - Production / Quality Coordinator
790c9791-a515-52ba-ae0f-aa22af613964 | signoff | HOLD POINT
a7534f13-6f0d-5649-9f91-d056faf87402 | checkpoint | 21 - Concrete Supply Testing
a50a5106-58ac-5154-b636-4e9d9baf5168 | note | ACTION (Hold, Monitor, Witness) - Hold
524723cd-0b10-5b32-a705-0aaf1f106914 | note | Detail - Concrete compressive strength test to be carried out by supplier. 1 Set per beam with additional set for any truck with water added after leaving the batch plant
3fe6190e-caa7-5090-99f8-40eaaf9458cb | note | Reference - NZS 3112, Part 2
331227d1-8d3c-5dc4-b1b8-7ec0f3ee2639 | note | Frequency - 1 test sample for every beam [1 cylinder - at 7 days age, 3 cylinders - at 28 days age, 3 cylinders - transfer strength]
ef3e12d0-76f2-5b65-9cfb-0b4f1a44dc33 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Testing
025465c7-5017-563b-a711-8ca08e0408b2 | note | Conformance Criteria - Compressive Strength result to be a minimum orf 60MPa at 28 days
0f0c4a8d-861c-5471-969e-3658197a17f5 | note | Records - Concrete suppliers Test Reports
ee7efde4-c434-5036-a461-9dcb8ab13561 | note | Responsibility - Concrete Supplier + Production / Quality Coordinator
3b0b38d5-d5de-5b88-8a39-edee17a6c732 | signoff | HOLD POINT
4288a69d-fabb-520a-a506-67c8b8d010d8 | checkpoint | 22 - Post Pour Inspection
721abcd0-5901-5c3e-b54f-0ea4ebb89e4e | note | ACTION (Hold, Monitor, Witness) - Hold
f8c468dd-cbfc-59fa-840e-626b72f8d26d | note | Detail - All units shall be inspected for its compliance prior to delivery
139fc4d8-86d9-5641-a088-8d6a6481b470 | note | Reference - Approved shop drawings
f176d10f-98c5-5a13-b724-be54170c4ad9 | note | Frequency - Every unit - prior delivery
8d5e7b13-a589-5f24-9b46-c5b8cbcd54fe | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
a403cc31-9e23-5f4a-9c73-ac4489955d3b | note | Conformance Criteria - Confirmation that the unit has been cast in accordance with approved shop drawings and NZ standards
8b0f1bbd-a572-581f-953d-7b495ef12b98 | note | Records - Post-Pour Inspection sheet (red pen mark-up - as-built)
f321ff1b-89d3-5b73-b0d5-a61c496aa4bd | note | Responsibility - Production / Quality Coordinator
5076d25e-bc7e-5a9e-ba97-3ef4d68a99c1 | signoff | HOLD POINT
ec61566e-039d-5374-9586-f0a4d7509568 | checkpoint | 23 - QA Package / Redline Drawings
2f204df4-bf44-5875-8ed5-2fc070b896f3 | note | ACTION (Hold, Monitor, Witness) - Hold
e5e86938-3e39-559e-b0f1-f12261960b37 | note | Detail - Compliance documentation is to be collated as per project requirements
9b670fca-7b98-5440-a777-b5d556f58b3f | note | Frequency - At Delivery and installation
b6d92ed9-8b0d-58f3-b32e-7c0f31b46779 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
308eecf0-d585-5ce6-9006-1532ba7cb0b0 | note | Conformance Criteria - Compliance documentation is to be submitted to the Engineer.
9c00f19f-17d7-56d7-a209-5abed1961002 | note | Records - Post Pour inspection sheet Marked up shop drawings - as built
3a897618-00a4-59f5-88ac-593de51db2e6 | note | Responsibility - Production / Quality Coordinator
6faff287-504f-5594-90a8-afa8ce6fff97 | signoff | HOLD POINT
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
fa40a8b6-3937-45a1-afb1-e2391b5343ca | checklist | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A | itp | ITP - Pavement & Surfacing - AC20 - Asphalt
cc7c9d80-ff45-4bf8-9c17-d940de7f64b3 | section | SECTION 01 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
93af617d-8481-4055-96e0-9f733cfd53d0 | checkpoint | 01.01.01 - Coarse Aggregate - Property Tests and Sampling
e993d093-3a65-5857-b277-e47883dadac2 | note | Acceptance / Conformance Criteria - The Coarse Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Weathering Quality Index, Crushing Resistance, Broken Faces, and Particle Size Distribution
5e669058-17b6-5c70-9acd-2b95ebe52e54 | note | Standard / Specification - NZTA M10:2020 - 2
7a45ee10-da75-591d-9491-d8f4f80db2f0 | note | Verifying Document - IANZ Lab Reports
5401e64f-2994-5b8e-94a2-04dedad75640 | note | Frequency - 1 Test per source of the coarse aggregate. Additional samples if source is changed
9af4f78e-ee38-5049-ad2d-aa20952ba4b1 | note | Verification Activity: Activity - H
6b9cbaa5-5657-58fc-8e86-e719f820affb | note | Verification Activity: By - PE
85aab887-1ca1-41d9-bd36-10c96aa7f4f9 | checkpoint | 01.01.02 - Fine Aggregate - Property Tests and Sampling
840bbac2-daa7-58d1-8c7a-5888c5329697 | note | Acceptance / Conformance Criteria - The Fine Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Sand Equivalent, and Particle Size Distribution
ee4c82e0-caf5-5e24-ada4-8ee11ae91559 | note | Standard / Specification - NZTA M10:2020 - 2
cf9167ae-42fd-5513-b854-b4346fe9e11b | note | Verifying Document - IANZ Lab Reports
6c3de341-d3a5-5bec-a217-19de0fab8e25 | note | Frequency - 1 test on the parent source
38dc9170-2c39-533e-b2a8-969e48b95292 | note | Verification Activity: Activity - H
dfcfbe78-653a-51f9-a359-f91e22937a5d | note | Verification Activity: By - PE
5d412691-91c6-4d06-9adc-375d66591c11 | checkpoint | 01.01.03 - Coarse Aggregate
0bb3e29d-105a-5c08-bb5c-1ab37f3ba1cd | note | Acceptance / Conformance Criteria - Coarse aggregate is comprised of particles that are retained on the 4.75 mm sieve. Coarse aggregate shall comply with Table 2.1 except that the Engineer can approve the use of non-complying materials from sources of proven performance.
2dd97932-2e6c-547f-9f28-234446c72760 | note | Standard / Specification - NZTA M10:2020 - 2
856e003c-add2-51df-9bba-11e5e72776ed | note | Verifying Document - IANZ Lab Reports
db408a2f-49da-5acf-983d-a8e06b207c34 | note | Frequency - Prior to use as per BPG05 - 15
97fcbde9-2896-5379-87dc-3a28659fcf78 | note | Verification Activity: Activity - H
54d07525-8e56-56c0-bfb1-f47a79caa6e1 | note | Verification Activity: By - PE
f84fd228-4f29-4062-a6f9-9eccd5f61616 | checkpoint | 01.01.04 - Fine Aggregate
7b426166-8593-5136-80b9-dbe241bd9086 | note | Acceptance / Conformance Criteria - Fine aggregate shall consist of crushed rock particles finer than the 4.75 mm sieve and manufactured from a source complying with the requirements of Table 2.2.
22da16f5-2a64-5efb-8770-32c98cd1dff6 | note | Standard / Specification - NZTA M10:2020 - 2
e1ebe6ff-840b-5fd5-8145-d9a894b02465 | note | Verifying Document - IANZ Lab Reports
a121e4b9-0b0b-56e5-b941-cf5ed462e276 | note | Frequency - Prior to use as per BPG05 - 15
41a00c85-1cba-51d1-b379-6791e6d90f3e | note | Verification Activity: Activity - H
9aec213a-5ab1-5cca-91f2-0a1555f140ee | note | Verification Activity: By - PE
3903f36e-6cd4-4da7-b049-af24b1667c62 | checkpoint | 01.01.05 - Mineral Filler
ba22a895-f5af-51d0-97f2-50905affbd02 | note | Acceptance / Conformance Criteria - Filler shall be consistent in mineral composition. It shall be dry, and free from lumps, clay, organic matter or other material deleterious to asphalt.
e1c94724-a79d-5929-a267-963e054b5912 | note | Standard / Specification - NZTA M10:2020 - 2
b63f1c02-e051-51c2-826c-ac817e52af00 | note | Verifying Document - IANZ Lab Reports
1b69e03b-477e-5ec8-9d05-734a845b028d | note | Frequency - Prior to use
972b3c60-b173-55b0-9990-71a01c84a0b3 | note | Verification Activity: Activity - H
326ce5fb-8642-502e-ab1b-55ce60924df5 | note | Verification Activity: By - PE
d40d5892-b148-4288-ad36-0363cd8e8c5f | checkpoint | 01.01.06 - Bitumen
ec6040eb-b1b4-54ed-94b9-60f98d90aeec | note | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01-A specification.
504ebcf9-95d3-52e3-973a-a119a265008f | note | Standard / Specification - NZTA M10:2020 - 2, NZTA M01-A
7aba7d80-2074-5e89-84d1-254a390c3ed5 | note | Verifying Document - IANZ Lab Reports
b10ef54e-6591-502d-bd37-097c6314edf1 | note | Frequency - 1 test per 25,000 litres or part of
719748d3-bd3f-50b9-bc4b-c9506a106f58 | note | Verification Activity: Activity - H
381d4eec-bd7d-55bd-a539-85fe7c8fa941 | note | Verification Activity: By - PE
e66e6e6b-9272-4dd8-93df-a876e1bde420 | checkpoint | 01.01.07 - Aggregate Wet Strength
320c5e97-ccf1-59d6-9a4f-f66b698616a3 | note | Acceptance / Conformance Criteria - When tested in accordance with AS 2758 Part 5 the aggregate wet strength shall be not less than 100kN. The wet/dry strength variation shall not exceed 30%.
77053458-ccbb-5f59-847b-507078ab5978 | note | Standard / Specification - NZTA M10:2020 - 2
91c99a54-f4a3-544a-ba75-acefe1cd02fb | note | Verifying Document - IANZ Lab Reports
21413b94-b1d7-5cdd-8684-5fa0b674de18 | note | Frequency - Prior to use
96bbb6fa-3a88-54b6-afb9-3b22e1ddbe92 | note | Verification Activity: Activity - H
6f86db17-7a3a-50f6-a8ce-0c7831493123 | note | Verification Activity: By - PE
71ae40a9-8d5b-4104-b452-fee959fdbf19 | checkpoint | 01.01.08 - Wheel tracking Testing
93c75eae-d6d4-5ca0-b18f-06c8d6cf94d7 | note | Acceptance / Conformance Criteria - The acceptance criteria for wheel tracking shall be a tracking depth of no more than 3.0mm after 10,000 passes, in respect to AC20 (Type # 2 pavements). All other asphalt layers, including SMA10 and AC10, shall apply the 6mm maximum tracking depth as per NZTA M/10.
5e84958e-71d3-5b55-ad46-8ac2ddf2e460 | note | Standard / Specification - NZTA M10:2020 - 3
520f8ddc-9f6c-5e01-be54-6416fda917c2 | note | Verifying Document - IANZ Lab Reports
efbd239e-835c-59cc-838c-58ff660e7f6b | note | Frequency - Prior to use
d9e2eaa3-1372-548b-af40-3e9f9399c535 | note | Verification Activity: Activity - H
d03beec7-13cb-548e-ba12-b9373fd7b80b | note | Verification Activity: By - PE
bf5a7da0-fe54-4095-a350-0a15a956d0c6 | checkpoint | 01.02.01 - Mix Design / Job Mix Formula
ada8a329-7c4d-592e-89fc-0d99fdaf308c | note | Acceptance / Conformance Criteria - The Contractor shall supply details of the mix designs together with the Job Mix Formula (JMF) and the Marshall or gyratory compaction properties as required to the Engineer for approval. No works shall commence until the JMF of each mixture to be used has been accepted by the Engineer.
83f6b0f0-ef96-56a7-bbc1-ab8a5276a36b | note | Standard / Specification - NZTA M10:2020 - 3
fdd3a197-7373-50ae-898b-42f8af203cbb | note | Verifying Document - Approved Mix Design
cf92acc6-b458-5c33-a0ab-72b093139eb5 | note | Frequency - 3 tests per mix
7030ceba-dbaa-5b2d-a190-8931a895639c | note | Verification Activity: Activity - HP
92acf587-479f-59a1-bdaa-b4111dca4ec2 | note | Verification Activity: By - ENG
1d9667bc-f2af-4de2-bb59-317ecb6aaaa4 | signoff | AUTHORITY HOLDPOINT
1e77a789-af13-43e6-8f78-7b187f881cfb | section | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
e485635d-cefc-4c28-902f-cc2b7a4b6c21 | checkpoint | 02.01.01 - Paving Plan
2ba7807f-bec9-5977-a100-3807baad2fb0 | note | Acceptance / Conformance Criteria - The Contractor shall prepare and submit a paving plan to the Engineer for approval not less than 7 days prior to construction of the asphalt pavement.
b988dc06-1ead-5291-bc80-4a21eadb58fc | note | Standard / Specification - NZTA M10:2020 - 8, 9
ac8181f9-79e8-5d33-b2f4-88fbac66df0c | note | Verifying Document - Construction Work Pack
21ef14a1-36f8-5deb-b008-8cb63f950c38 | note | Frequency - 7 days prior to construction of the asphalt pavement.
66066785-0af4-50ea-ba35-1ad5ac72204c | note | Verification Activity: Activity - HP
753ff630-facd-50f5-b718-f77dd401389f | note | Verification Activity: By - ENG
b1b2fe42-c0a2-4dc6-8a26-66e8838c0d1d | signoff | AUTHORITY HOLDPOINT
efd16165-e8eb-464b-b41b-87fff546411d | checkpoint | 02.01.02 - Sealing Inspection
207c2fb9-54a3-5d0c-9739-5748fedaf981 | note | Acceptance / Conformance Criteria - Before sealing and resealing.
11789a8a-d5a3-5d41-a098-473bd9403de8 | note | Standard / Specification - NZTA M10:2020 - 9
289e3aa0-d249-57ea-adf5-57769ac2d3bb | note | Verifying Document - Hold Point Release
3680234a-ae13-5a30-be71-ba4fbdebdb7e | note | Frequency - Min 48h Notice
a56d8390-07cd-5c30-8afa-103049485857 | note | Verification Activity: Activity - HP
42575366-1588-558b-98cc-2b52583e0246 | note | Verification Activity: By - ENG
8e5f2cae-1950-474e-8cf7-121796d92e60 | signoff | AUTHORITY HOLDPOINT
7435d3e1-5fd4-4c66-b713-c98b267edc58 | checkpoint | 02.01.03 - Weather during Paving
de0c76c4-5b64-578e-a925-0c2e8adec4c7 | note | Acceptance / Conformance Criteria - Asphaltic concrete shall not be placed when it is raining or on a wet surface. Dense-graded asphalt shall not be placed on a surface with a temperature of less than 5°C.
ca4bcdd7-aae0-51b2-a350-ff033d6a630d | note | Standard / Specification - NZTA M10:2020 - 6
4ef66e67-040b-59e2-b9f6-360f0a122bfb | note | Verifying Document - Weather / Site Notes
5b3c0403-d0a3-5572-8062-88ea13d458be | note | Frequency - Each day prior to placement
2b4ffd06-ce63-5c4d-809a-309f539dc8dc | note | Verification Activity: Activity - H
5874f7ea-5ef0-55a0-a272-bda51f0c267b | note | Verification Activity: By - PE
3b8ed5ad-f7d8-4194-9710-1d0e7944ddde | checkpoint | 02.01.04 - Asphaltic Prep
26906b2d-2493-5158-8085-788910055e41 | note | Acceptance / Conformance Criteria - Prior to paving asphaltic concrete, the area to be paved shall be dry and free from loose material or dirt. If swept, all sweepings shall be collected and removed from site. Barriers, kerbs and other adjacent surfaces shall be adequately protected against over-sprayed bitumen or vehicle damage
af872119-c6ab-5310-a7ed-80e5a8316a28 | note | Standard / Specification - NZTA M10:2020 - 9
981e5ecb-5fc6-5fe3-a1bd-d9ba02acecb8 | note | Verifying Document - Site Notes
7c5cb7bd-4ba3-5445-a7a0-26386d9fc80e | note | Frequency - Prior to paving asphaltic concrete
a5ddfb81-da5f-5a23-bab1-9d4981caf963 | note | Verification Activity: Activity - H
a313a494-99f9-514f-b082-f71bd7f3415d | note | Verification Activity: By - PE
c390c4b5-4590-417f-9d74-d667ec650f77 | checkpoint | 02.01.05 - Tack Coating
2a00dcdc-8a43-5caa-8523-a90a1f2a34fa | note | Acceptance / Conformance Criteria - Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. The use of a hand lance shall be minimised to ensure an even application of the tack coat.
13f03a37-dcf8-548f-925e-14630ec46472 | note | Standard / Specification - NZTA M10:2020 - 9
5f26643a-1d38-5a92-b708-b8126ea90a92 | note | Verifying Document - Site Notes
6f8559fa-df22-5859-a352-94a47ab57bc7 | note | Frequency - Prior to Paving
51619a77-5aa5-5f26-8dd5-2259ffd97219 | note | Verification Activity: Activity - I
c3399253-9931-5c21-819e-6aa9b41569d8 | note | Verification Activity: By - PE
110d57cb-04ca-4adb-a247-ab318ff56ae1 | checkpoint | 02.01.06 - Asphalt Production Conformance
93186d2f-6c7a-5522-bc41-f719a0f0d210 | note | Acceptance / Conformance Criteria - Conforming Grading and Binder content by mass
336c6f52-ef0a-5997-8e05-3d6f2d7f7df9 | note | Standard / Specification - TNZ M10 Table 3.1, TNZ M10 Table 5.1, PS - Table No. 7.2 - 3.5
b2bf3998-6acf-5566-a266-955d73355111 | note | Verifying Document - Test Results
ad61e3b9-e0aa-58c4-b9c9-7f5b9b085c72 | note | Frequency - 1 per 200T, Min 3 tests per mix
32d16a04-320b-5138-acfb-03e68d69ffdb | note | Verification Activity: Activity - I
fe31651a-73f2-5776-ba1a-8a9e03a3d598 | note | Verification Activity: By - PE
b747fb4a-27c9-4dc9-a3e5-253e05ae277c | checkpoint | 02.01.07 - Asphalt Production Conformance -Volumetrics
f1a4fa5c-c319-58f7-a22e-c026641358b6 | note | Acceptance / Conformance Criteria - Conforming Volumetric testing. Refer clause 5.2 and table 5.2 for frequency and tolerances
941a62cd-c5eb-5157-a82b-2407aa0db782 | note | Standard / Specification - NZTA M10:2020 -Table 3.1, 5.1 and 5.2
a86ae1e5-16ad-5a14-a7be-7bdf78fd2f01 | note | Verifying Document - Test Results
a60a097d-936f-5c20-9347-40131532c68b | note | Frequency - 1 per 600T
8e35617c-c949-57db-9023-468327018f6e | note | Verification Activity: Activity - I
aedb4bf2-7f27-5fe9-8fa3-0b7710f7183f | note | Verification Activity: By - PE
eca13dc3-3a49-4996-864b-ec46af9cad90 | checkpoint | 02.01.08 - Mat Density
7dee2f32-63b8-56ef-8825-bf3f7cdbc094 | note | Acceptance / Conformance Criteria - For mixes with a nominal maximum aggregate size 14mm or less cores shall be 100 mm nominal diameter or greater. For mixes coarser than 14mm cores shall be nominally 150mm diameter. For layer thicknesses 40mm or less the core diameter shall be nominally 100mm.
715c0572-a524-56cf-804e-0d1dd0b3a463 | note | Standard / Specification - NZTA M10 9
376506f3-35e7-544c-92d3-aa7a380376e9 | note | Verifying Document - Cores
2ce07192-3d32-5425-a9e0-e7c382cd3361 | note | Frequency - min 8 per lot (day) (1 for every 300 m²)
59bc688c-524d-55ed-a37a-57ea234e69c9 | note | Verification Activity: Activity - R
e5d658bc-170b-58e5-81ff-0ef714e3d7b5 | note | Verification Activity: By - PE
b0ffc1a9-c92e-45b8-a064-2b6a04d80fb9 | checkpoint | 02.01.09 - Joint Density
0d0c6b6e-4b41-53ab-a026-f2bfcfe7a139 | note | Acceptance / Conformance Criteria - For mixes with a nominal maximum aggregate size 14mm or less cores shall be 100 mm nominal diameter or greater. For mixes coarser than 14mm cores shall be nominally 150mm diameter. For layer thicknesses 40mm or less the core diameter shall be nominally 100mm.
07d93b3b-c657-5c53-95d6-c5b159a4b1af | note | Standard / Specification - NZTA M10 9
5503b929-2bb3-51dd-96eb-9b2469533864 | note | Verifying Document - Cores
5e1691f2-2008-5679-abd2-811f194db265 | note | Frequency - min 3 per lot (day) (1 per 100 m of joint)
1daf8087-455a-5195-8a2a-f6cba74a82e5 | note | Verification Activity: Activity - R
75c09beb-794e-52a1-84e6-13410a4be2d3 | note | Verification Activity: By - PE
76703371-f3da-463b-9fb8-6e7101c50404 | checkpoint | 02.01.10 - Density Testing
d44c83a2-4689-527f-8607-4110ca3b3af7 | note | Acceptance / Conformance Criteria - The upper and lower characteristic values of in-situ air voids for that lot shall comply within the maximum and minimum characteristic limits specified in Table 9.2
02279646-c51c-5bf3-866c-37b4b86b5a81 | note | Standard / Specification - TNZ M10 - 9
c525e228-58a4-5a8b-95e1-9b2732b737a3 | note | Verifying Document - Lab Report
0a585547-f5dc-5c55-a254-d6cd3bf1c489 | note | Frequency - 24 hours of them being cut from the pavement
2bc9aeb5-f71b-5eef-ba88-e49d3665653c | note | Verification Activity: Activity - I
8a6b6d12-d495-5980-b91a-49d4825d1b0d | note | Verification Activity: By - PE
c6083640-1311-4065-bd41-8dafdf4d4e54 | checkpoint | 02.01.11 - Core Thickness
11e0be0d-cef9-50a6-9e9f-5350ff8459aa | note | Acceptance / Conformance Criteria - The nominal thicnkess for the set or lot of cores shall be equal to or greater than the specified nominal thickness.
f0a36426-12b2-56ad-adc5-466d1a06f4da | note | Standard / Specification - NZTA M10:2020 - 9
ad963cca-e6c0-5f61-a0a0-e2fc019d60a1 | note | Verifying Document - Lab Report
6e21e802-6310-5e71-b88a-40981087b211 | note | Frequency - Mat - min 8 per lot (day) (1 for every 300 m²) Joints - min 3 per lot (1 for every 100m)
46503f52-3e0e-589e-a0cb-2af79f57ab57 | note | Verification Activity: Activity - R
63420864-44e7-5c43-829c-da43ef77e338 | note | Verification Activity: By - SE
067d2d35-0157-4d08-82f1-c83524778612 | checkpoint | 02.01.12 - Mat Density
e84438da-ceee-5631-96f4-ca5989289a1b | note | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be cut from the pavement at a rate of one core for every 300m² with a minimum of eight cores representing each lot
3d861bcc-780c-5b81-a79a-fbadc58e5c87 | note | Standard / Specification - ASTM D5361, NZTA M10:2020 - 9
25de561f-f302-5da5-8d09-754b5c2b4af8 | note | Verifying Document - Cores
97892a20-535a-525c-b832-57bedc8a2ced | note | Frequency - min 8 per lot (day) (1 for every 300 m²)
8f1af231-34ba-51d9-8a44-4cf53e1ef69f | note | Verification Activity: Activity - R
439c14ec-acec-5e28-97a0-6e16bfa99961 | note | Verification Activity: By - PE
9f9a9739-fb3e-4f1d-ae64-a2a9054348e3 | checkpoint | 02.01.13 - Joint Density
a9501458-e62e-5c65-ad1b-beea30dbbf67 | note | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be taken from randomly located distances along joints at the rate of one per 100m of joint with a minimum of three representing each lot
5b090b24-a68c-5879-85dc-b378e2cbc1e2 | note | Standard / Specification - NZTA M10:2020 - 9
c28431ef-bf25-55ff-b378-3dd9b21da34e | note | Verifying Document - Cores
41b35ec6-8e52-5612-b88a-82f580faada6 | note | Frequency - min 3 per lot (day) (1 per 100 m of joint)
56bfe421-ebfb-5d6a-9640-915f44c40a5c | note | Verification Activity: Activity - R
02420d46-6d00-523d-bd58-b992a43b88ba | note | Verification Activity: By - PE
53a2a340-1a8a-4048-8279-f7e09084f053 | checkpoint | 02.01.14 - Density Testing
c65c3c54-ee1f-5b9d-9990-2d09ff5d9fcb | note | Acceptance / Conformance Criteria - The upper and lower characteristic values of in-situ air voids for that lot shall comply within the maximum and minimum characteristic limits specified in Table 9.2
21f88937-fb76-5de1-af8c-a7fa83c13a36 | note | Standard / Specification - NZTA M10:2020 - 9
afe32d43-9757-5275-b759-5af0a45a1904 | note | Verifying Document - Lab Report
abf43ae9-c388-5d61-961e-56f58a208805 | note | Frequency - within 24 hours of them being cut from the pavement
7cb86469-fd4f-5645-9d92-a6965934af9b | note | Verification Activity: Activity - I
5c93dcea-c73e-5e6f-9d34-213e152bf5b7 | note | Verification Activity: By - PE
0d694d28-b2f8-4a6b-aae4-b7cd3b5390c0 | checkpoint | 02.01.15 - NDM Density
03e55206-2475-5173-b383-30347d959a36 | note | Acceptance / Conformance Criteria - NDMs are to be completed at the time of placing to ensure compliance when cores are taken
e887941f-545c-5e4d-94d9-c8621a55cc6d | note | Standard / Specification - NZTA M10:2020 - 9
2653b7b7-45f6-502c-99a1-727c55574f11 | note | Verifying Document - IANZ Lab Report
7c92240a-f242-553f-8270-5c3cddc28d0e | note | Frequency - min 8 per lot (day)
b634e8d3-cdb1-5aa5-b231-b9ffc845b6b9 | note | Verification Activity: Activity - I
a9540eaa-5fbc-5e43-a64f-a65d31f7b6ab | note | Verification Activity: By - PE
e1fcb6c5-69df-4b15-b863-39f931c24ad3 | checkpoint | 02.01.13 - Transverse truth of the surface
90a72441-ea46-5719-96b2-8fc43249f10b | note | Acceptance / Conformance Criteria - The transverse truth of the surface shall be checked with a 3 m straight edge over the straight cross-fall portion of the cross-section for irregularities, which vary more than 5 mm under this straight edge (excludes the start and end of the job where the new seal matches the existing road).
d2a95c0b-e7fe-5daa-b9e8-07a827067935 | note | Standard / Specification - NZTA M27:2020 - 9
03e72814-340d-5f62-895a-2599c1bf63a4 | note | Verifying Document - Site Notes
01866712-8fd9-5a26-8aa0-db66bf14fcb6 | note | Frequency - Post Seal
7a5abee0-1511-51fe-8d46-26b59749d0a2 | note | Verification Activity: Activity - I
390b852b-1f41-5f59-9cf6-ffa8f530c1e0 | note | Verification Activity: By - SE
d7aaf001-be74-4a26-8b7b-369bbcb45485 | checkpoint | 02.01.14 - Finished Pavement Level
0910646c-3efb-5cb2-96c6-eecf0b2cb5b0 | note | Acceptance / Conformance Criteria - The level at the top of each layer of asphalt shall not differ from the specified level by more than 10 mm, except that where asphalt is placed against kerb and channel where it shall be flush with, or not more than 5 mm above, the lip of the channel. 2mm at Construction Joints (Bridge).
cef5c784-8b40-57d8-ba9b-327bdaa2f9fa | note | Standard / Specification - TNZ M10 - 10
fd731c91-634a-5257-9a36-d9fc566dd43c | note | Verifying Document - Survey
999f076b-e577-50d0-863b-9bfdc8e62160 | note | Frequency - Continuous throughout construction
165493d1-c80d-56e0-8745-8ec754ce862d | note | Verification Activity: Activity - I
9149e37d-2dba-5ef4-a506-f6f8440b742c | note | Verification Activity: By - SE
ab2edf96-b6da-45ec-9fab-8f1d231799c8 | checkpoint | 02.01.15 - Finished Pavement Alignment
698c768c-85fd-5bd1-b059-4029e0287032 | note | Acceptance / Conformance Criteria - The horizontal location of any point on the pavement shall not vary by more than ±50 mm from the design except where alignment with an existing pavement structure is necessary, when the new work shall be joined to the existing work or structure in a smooth manner.
4b869f4a-2bdd-569b-919e-090a13f9b123 | note | Standard / Specification - TNZ M10 - 10
f7dd5f28-16d5-562f-b3b6-f98b0dd4d0dd | note | Verifying Document - Survey
ae9be23a-e51c-5d5d-8cc1-061cc51f47ab | note | Frequency - Continuous throughout construction
a3a46bf0-caf3-5160-af03-85218129ad62 | note | Verification Activity: Activity - I
43ee7a67-1fa6-5775-9f16-a82c6a0ba81a | note | Verification Activity: By - SE
bf6d1f5a-475a-4896-938c-57e749d9f568 | checkpoint | 02.01.16 - Finished Pavement Thickness
5d1a1b8e-3308-5612-8209-6bd1c6ff6362 | note | Acceptance / Conformance Criteria - The pavement specified layer thickness shall not be less than the average measured thickness of each lot.
6bd99527-59bf-5142-b593-62ece99482e1 | note | Standard / Specification - TNZ M10 - 10
14432ccc-2fa5-5310-a3c9-77368b48b159 | note | Verifying Document - Survey
69a9c7df-e7c5-5ab5-97e3-c020cabe423b | note | Frequency - Continuous throughout construction
3b80136d-54a1-5a83-8bc7-582492aa2ab5 | note | Verification Activity: Activity - I
08ac311d-8e62-598d-80eb-35c4a4faa9e4 | note | Verification Activity: By - SE
2ceaa4cd-8d76-43e2-aaad-10f58191a41b | checkpoint | 02.01.17 - Transverse joints
0124e2fc-0d97-51d6-b757-8a1c1a126451 | note | Acceptance / Conformance Criteria - Transverse joints shall be milled back to provide a square edge and bitumen shall be hand sprayed on the vertical face. Successive transverse joints shall be staggered by a minimum of 2.0m.
511629a9-f696-5cf6-bf66-12966bc679f4 | note | Standard / Specification - TNZ M10 - 9
0c162884-e085-521a-b021-dfda939fbb72 | note | Verifying Document - Site Records
cd3145e7-5f4c-588f-a6bb-751be39fb665 | note | Frequency - Continuous throughout construction
7f92b5b3-8f8b-551d-a1ee-567953b4b03a | note | Verification Activity: Activity - I
f912f27c-50da-5209-9d4b-2700438c84c3 | note | Verification Activity: By - PE
af130c55-6aab-4181-a3ed-777856db8026 | checkpoint | 02.01.18 - Longitudinal joints
5b306e29-2484-56e8-9847-0b31475dc303 | note | Acceptance / Conformance Criteria - Longitudinal joints between successive layers of asphalt shall be offset by at least 150mm.
94cd192f-3bc9-51ec-a10e-3273c8519ea4 | note | Standard / Specification - TNZ M10 - 9
0099a3d4-4e05-5e92-a6aa-74205986db11 | note | Verifying Document - Site Records
4b15496f-1c6f-51d6-b584-f2246cc01bfa | note | Frequency - Continuous throughout construction
45f83ae3-5791-5222-be16-07bc52bec018 | note | Verification Activity: Activity - I
dc3c0a9d-27c0-5740-baa5-32903e43d831 | note | Verification Activity: By - PE
89591b2a-f56b-4b73-85c6-3f80a6afcad0 | checkpoint | 02.01.19 - Asphalt delivery temperature
8e19927e-f9b7-5753-ae19-21e0fc504389 | note | Acceptance / Conformance Criteria - Asphalt paving should be carried out at temperatures between 121–149°C to ensure optimal workability and compaction. If the temperature falls below 120°C, the asphalt mixture becomes too stiff, leading to inadequate compaction and a compromised pavement structure. Proper temperature control during transportation and placement is essential to achieve a durable and long-lasting surface.
31ffaac2-fa73-5845-adc0-fd04c13bbff8 | note | Standard / Specification - TNZ M10 - 8
faba9055-08e9-5fce-a3d4-af09d45725d2 | note | Verifying Document - Site Records
72983c4f-122c-5f21-9a9c-5d358c62bf48 | note | Frequency - Continuous throughout construction
04ce8654-8722-5e5f-a039-e98a9aebff2e | note | Verification Activity: Activity - I
1ab9a585-9fb6-5b71-9512-a1bca3d9ffdf | note | Verification Activity: By - QA
b642a560-6dc0-43bc-8f88-69eb6bd3d90a | checkpoint | 02.01.20 - Depth Checks - Loose during paving asphalt material
0f882033-37bc-554d-9b1a-fe081da2f00e | note | Acceptance / Conformance Criteria - Best Practice technique. Allowance for depth is dependent on asphalt type and compacted effort required to mmet Specification. Normal practice is to add 20% of the nominal depth and use a dip stick to visually check behind the paver.
0f8b70c9-e4f3-578d-ba2f-35760d1e5f36 | note | Standard / Specification - Industry Best Practice
884a7151-c93e-5942-a937-3aa0bf5deed7 | note | Verifying Document - Site Records
3b5bc4e6-c365-5e2f-9dd7-1ab18261942e | note | Frequency - Continuous throughout construction
9df5a92d-17f1-5702-b5ea-930b94672a08 | note | Verification Activity: Activity - I
dd9ee907-e4b2-5bf3-b704-46f3c6a43302 | note | Verification Activity: By - SE
e63e2155-b71b-44c4-9500-478d66a2695f | checkpoint | 02.01.21 - Plateau Testing
2e58b9e6-c55b-5b49-bcbb-33bd0ceb3932 | note | Acceptance / Conformance Criteria - One test at the start of the project. Typically a target density of 93-97% of the maximum theoretical density.
226a022b-e15d-5441-8531-367062587f57 | note | Standard / Specification - Industry Best Practice
58c5aa41-841a-5a77-bef6-c2cfb8eb76f8 | note | Verifying Document - Lab Report
720cf828-117d-5464-a5a7-5f8c44996291 | note | Frequency - 1 Test at the commencement of the project.
e4d4841c-2dba-5b79-bc0d-582087e4f90b | note | Verification Activity: Activity - M
7622867b-d99b-558e-87a2-294f34b69716 | note | Verification Activity: By - Spec
2e2379c9-4161-42ae-bcfc-6c0af4e4ee2b | checkpoint | 02.01.22 - Backfilling Core Holes
7c58bea3-e5b7-5028-87f4-c0d61e55c6cc | note | Acceptance / Conformance Criteria - Core holes filled with material similar in composition to the surrounding asphalt layer. Well compacted and finished flush with the surrounding pavement.
4daf1d87-c731-5740-b795-6518b691dbb0 | note | Standard / Specification - NZTA M10:2020
3e036823-fc54-556b-bf23-223ae45c2f9a | note | Verifying Document - Site Records
9b175587-b08f-5521-8a43-79f328b4ea5f | note | Frequency - As soon as possible after core extraction
b6e4bb07-6ad9-52f9-83b9-44383f60e938 | note | Verification Activity: Activity - O
679b3e46-3ee4-5cfc-add4-da7b3ee83d8c | note | Verification Activity: By - SE
86bcfc35-c512-491f-ac73-61c1586ab3f7 | checkpoint | 28.09.01 - NAASRA
e8f0f41a-3a8e-5725-bcb4-183b00a4796a | note | Acceptance / Conformance Criteria - On completion of surfacing and placement of pavement markings and raised pavement markers Contractor shall carry out surface roughness measurements in accordance with the Transport Agency’s Technical Memorandum TM7003 (TM7003).
ff7e1236-da80-59eb-be21-6d1109a7f073 | note | Standard / Specification - PS 21.4.1
1b3255b7-39bb-58c6-9352-8c4621c54ba4 | note | Verifying Document - Test Results
a2b54524-9e3e-5827-a9f9-0c587bf6de51 | note | Frequency - Each lane. 1 test on surfacing post construction and again at end of defects notification period
bb2c0a71-faf1-5c1a-8d06-1e03341b9ec7 | note | Verification Activity: Activity - I
699913e5-c917-5a15-a631-4923d5134112 | note | Verification Activity: By - PE
d24b0ddf-f351-490f-b6c9-e82ca89dac95 | section | SECTION 39 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
8dfae0b5-0c42-4f18-9980-c33327f9c589 | checkpoint | 39.02.02 - Survey Records
3b619a41-0fcd-52b6-a17e-23329e21857b | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
8e12755b-ea85-55b9-9eff-0c2edd4aa4e3 | note | Standard / Specification - Downer
7b82806a-4f8f-5d64-bff9-d1a03fe3abc8 | note | Verifying Document - Records
e853badc-68ee-5a3a-9962-3abf4f10d926 | note | Frequency - Post construction
0406a169-a095-5774-858d-2f3d10d621ce | note | Verification Activity: Activity - H
33f66e66-666c-5c3c-b9ff-a2ce639bf42e | note | Verification Activity: By - SV
b337798c-8444-4603-a0ed-321907226477 | checkpoint | 39.02.03 - Redline Drawings
6c95e966-051f-54ca-ac23-11fd2e7d78ad | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
b99cc507-d122-5bc1-bcc4-ec9706b5042c | note | Standard / Specification - Downer
90e7435d-ee02-5e9b-b288-5ae98a9980ea | note | Verifying Document - Redlines
1a0f0702-33eb-594a-a3c0-ec312ac353dc | note | Frequency - Post construction
9124e3bb-91b0-58a1-9276-3aa27b78b70b | note | Verification Activity: Activity - H
0586f7a0-1fd0-5445-b16f-732f835d3963 | note | Verification Activity: By - PE
b64ee940-4979-4488-b7b2-c357adda795b | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
5a4ee0d1-5628-5733-90ef-0014140079a5 | textbox | Contractor's Rep Name:
375f558e-d812-5044-86fd-0aeef508552b | textbox | Engineer's Rep. Name:
3b62d4c5-011c-5342-a29c-757f50433c19 | date | Date:
e16fa880-5e03-43a8-9c0b-eb976b0144f6 | signoff | Add Signature
90c96669-2bc6-5c9c-a873-69bd07e35501 | checklist | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | itp | ITP - Pavement & Surfacing - AP40 Material - Rev 1
624c9523-567e-5961-bcbb-c2696781b917 | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
b0529998-93c5-5453-a2e5-2c44366e9f2c | checkpoint | 2.01.01 - Basecourse CBR
49feefc3-588f-5a18-a041-0e972e47510d | note | Acceptance / Conformance Criteria - (a) compacted in accordance with NZS 4402 : 1986, Test 4.1.3 New Zealand Vibrating Hammer Compaction Test at Optimum Water Content and;
60fe236d-5085-5b0d-bf42-d0daecc97a4f | note | (b) tested in accordance with NZS 4407 : 1991, Test 3.15 The California Bearing Ratio Test (without a surcharge for at least 4 days). The soaked CBR of the basecourse aggregate shall not be less than 80%.
f2d19251-5dc6-5502-b284-ae9daf0e77c5 | note | Standard / Specification - TNZ M/4: 2006
c0fb680d-688a-5a53-8ee8-018c1be109c8 | note | Verifying Document - IANZ Lab Reports
092ee455-c68a-52da-b948-069dbee4c3e5 | note | Frequency - 10,000m3
a20f305f-4ca6-5475-b922-31e79decface | note | Activity - HP
0eea9014-d4d1-5b97-9f91-3ae4d1913b50 | note | By - ENG
29ed9ccb-712c-50ab-9d42-c0fd44745cb4 | signoff | AUTHORITY HOLDPOINT
b837b78b-b0a4-557a-8a87-e178b07b8903 | checkpoint | 2.01.02 - Running Course Material Approval
c35c4f61-7668-59a9-8a32-5fa88411ca5e | note | Acceptance / Conformance Criteria - The running course shall have a crushing resistance of not less than 130 kN when tested in accordance with NZS 4407: 1991, Crushing Resistance Test, Test 3.10. It shall be free from all non-mineral matter.
00ee2165-c923-52c1-a7c1-c8be26b744a0 | note | • The grading of the running course shall conform with Figure 3 of TNZ B/2:2005, 10.2, when tested in the same manner as required for the parent basecourse. (IF USED)
4b73ec4b-e5d5-5465-8748-2724aaf33df6 | note | Standard / Specification - TNZ B/02: 2005 - 10.2
09652dfd-98c4-557f-b304-99834837ee0d | note | Verifying Document - IANZ Lab Reports
d8499938-8384-5e3a-974e-f813ce8ea501 | note | Frequency - 1 test every stockpile
30b3ebf3-2c6a-582c-b8dd-ec8a5461615e | note | Activity - HP
090b0c2a-58bd-525e-b9df-1cc56bfd03c0 | note | By - ENG
694bbc49-b523-5ff7-a549-6e3e5d78408f | signoff | AUTHORITY HOLDPOINT
548ad985-2ecf-52ce-8844-2be0a9fd6e9f | checkpoint | 2.01.03 - Basecourse MDD and OMC
4b76bb15-0733-5f17-be70-a7872640bbc9 | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). Test on heavy compaction, vibrating hammer.
231b71bc-a331-597e-9693-4b71838c0655 | note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
c13ccd03-f4be-578f-9839-018fceb45966 | note | Verifying Document - IANZ Lab Reports
89535989-ce9f-5033-b5a5-0d2d0f850ac6 | note | Frequency - 1 test per material type
095585ed-5db8-560b-b506-42b6f64bb47f | note | Activity - H
4922a46a-ce96-5b3b-9f26-174f9c43f553 | note | By - PE
75ece572-d277-549f-97f5-9d2eea646d14 | checkpoint | 2.01.04 - Crushing Resistance
edb7e3ac-db99-5ab7-b928-75906bda42c0 | note | Acceptance / Conformance Criteria - The crushing resistance shall not be less than 130kN when the aggregate is tested
d7d65de4-a18b-5fc7-b83b-85abf5a7b5ef | note | Standard / Specification - NZS 4407: 1991 Test 3.10.
8556196e-9046-5bbd-ba48-6a9f2df45fa2 | note | Verifying Document - IANZ Lab Reports
e81886fc-44c2-5966-80d6-283cbbfba1a7 | note | Frequency - 2 tests per source 4 weeks before use in the works
367b8f1b-d809-5e45-93cc-53fba2acb9df | note | Activity - HP
49c94da8-65cf-53c3-9870-956af1c22f4d | note | By - ENG
a003c3fc-8627-5101-be25-bc6c38bfe92a | signoff | AUTHORITY HOLDPOINT
4b4fe5d4-91f3-5027-a33b-636e1248f7a0 | checkpoint | 2.01.05 - Weathering Resistance
86ae2acf-2389-5ba7-aa9f-1b3ec70d4642 | note | Acceptance / Conformance Criteria - The aggregate shall have a quality index of AA, AB, AC, BA, or CA when tested
98ca51b1-9259-5e18-8408-177657df2e00 | note | Standard / Specification - NZS 4407: 1991 Test 3.11
bea56576-48b0-5a51-a4b7-025c2d69fdc6 | note | Verifying Document - IANZ Lab Reports
3388c215-27fb-5b48-9360-a185b1a46bc0 | note | Frequency - 2 tests per source 4 weeks before use in the works
cb6be75d-bc7e-5543-8ee6-c9509f04b222 | note | Activity - HP
13ddf1ad-108a-5528-8c58-ba360195dc4c | note | By - ENG
0755029e-495b-5e5b-9bc5-ce9ec5b00d8a | signoff | AUTHORITY HOLDPOINT
1be2a772-ef73-5a20-9f7b-ff55584b77db | checkpoint | 2.01.06 - Particle Size Distribution
ea27af91-c4e8-5aca-8207-6ea4a0cd81b8 | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 2 and 3 from TNZ M/4:2006.
02b46647-7530-5d7b-a380-a55e3640f4e5 | note | Standard / Specification - TNZ M/4: 2006
da23db52-ff3f-5278-8584-c1c8331d43c4 | note | Verifying Document - IANZ Lab Reports
8d967d1b-3eed-5ec9-9777-0b99a39c3ed2 | note | Frequency - 0 to 400m³ - 2 tests
5e5fcd4f-ace5-569d-ad71-4f9f9bed611b | note | • 400 to 1,500m³ - 3 tests
2fffda83-5727-5289-aee5-19ffe6c6683e | note | • 1,500 to 4,000m³ - 4 tests
ee93229f-5f11-51a0-b51d-0029d2a1adb2 | note | • >4,000m³ - 1 test for each additional 1,000m³
0dc8fd25-ab31-5aad-82f4-810b3de3a30b | note | Activity - HP
00fd27c9-c403-5163-b669-8aa7eb6c25ee | note | By - ENG
78a21ef1-b7d3-5597-95ee-fba52abdc91d | signoff | AUTHORITY HOLDPOINT
2c48e4c6-f0da-570a-b0f9-774b3da00b3c | checkpoint | 2.01.07 - Sand Equivalent
5572a225-1b12-5ec7-8e4d-976f85ad6de0 | note | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 40 when the aggregate is tested according to NZS 4407 : 1991, Test 3.6 Sand Equivalent Test.
da6de437-7513-56ce-9a69-3041123d9c89 | note | • If Sand Equivalence is < 40, then Clay Index shall not be > 3 and Plasticity Index shall not be > 5 (both being tested in accordance with the methods described above).
684c06d1-5e7b-59d1-b2e8-e5820065c7b1 | note | • The Sand Equivalent shall be determined using the Wet Method in NZS 4407: 1991 Test 3.6
7257ff58-571b-5bcc-94a7-16d39d767a16 | note | Standard / Specification - TNZ M/4: 2006, 4.2.1.1
25672133-332c-5316-8c22-fb96afcda8d7 | note | Verifying Document - IANZ Lab Reports
9404f767-20ec-57bc-8b9a-b05ff4161aa4 | note | Frequency - 0 to 400m³ - 2 tests
42fdb336-16c8-5801-9a29-38141af43cbc | note | • 400 to 1,500m³ - 3 tests
093f1489-71be-5cc8-a336-d0fa8111d0a5 | note | • 1,500 to 4,000m³ - 4 tests
b0fae1ce-8a94-5e2a-847a-c05f4aa5aa46 | note | • >4,000m³ - 1 test for each additional 1,000m³
a4ffeded-c0bb-5d1c-9d42-03a9244068ac | note | Activity - HP
092f8827-5d9c-5bfd-beec-decc3e8ca447 | note | By - ENG
b7f2b347-0e8d-5e6f-b844-c75eb8ea8162 | signoff | AUTHORITY HOLDPOINT
454d072b-71d1-59c6-b531-512bf3793c41 | checkpoint | 2.01.08 - Liquid Limit
94ea2bb8-2f99-505a-8180-8022555be423 | note | Acceptance / Conformance Criteria - The Liquid Limit shall be ≤ 25 when tested in accordance with NZS 4402 Test 2.2.
f8df0db3-87ee-5e8b-a51f-1abbf517ed5e | note | Standard / Specification - PS - 7.2.3
4743447b-1543-5fd0-8df4-19273089b6b8 | note | Verifying Document - IANZ Lab Reports
dcd6b8fd-0e3f-5326-b0d1-a2ae57b687cd | note | Frequency - 0 to 400m³ - 2 tests
ed1b49ae-d253-5dd0-a7ca-b88b10599425 | note | • 400 to 1,500m³ - 3 tests
cbe58cad-de5b-5630-877d-52cabfb0ead7 | note | • 1,500 to 4,000m³ - 4 tests
42bf96a7-239a-5fd4-9ffb-4211ff77611c | note | • >4,000m³ - 1 test for each additional 1,000m³
db9425ad-9a83-5aa4-be0f-e8e02b812dd6 | note | Activity - HP
caba5892-dec1-557e-830c-eabd731d1d79 | note | By - ENG
e812b52f-9fe9-518a-8788-a0160c62bc55 | signoff | AUTHORITY HOLDPOINT
16ce7ace-e77c-5302-99e6-731cd605e2a3 | checkpoint | 2.01.09 - Plasticity Index
ca0b0430-ecf9-520f-8416-fab47706e4ad | note | Acceptance / Conformance Criteria - The Plasticity Index shall be ≤ 8 when tested in accordance with NZS 4407 Test 3.4
b4d6bad6-93f6-5675-bffd-4ee930dad6c3 | note | Standard / Specification - PS - 7.2.3
07d5b80a-e1fd-5cd5-bd63-cde18bc7873a | note | Verifying Document - IANZ Lab Reports
26da61b9-4fbb-5351-92e6-cd4ebda2f352 | note | Frequency - 0 to 400m³ - 2 tests
e7ccd9e2-d84e-563c-b72a-5efa3b79d686 | note | • 400 to 1,500m³ - 3 tests
c9ef1931-3a0c-56a4-93c1-4f20cf8ba5be | note | • 1,500 to 4,000m³ - 4 tests
e70c514d-ec28-5306-9b1e-309be1e35650 | note | • >4,000m³ - 1 test for each additional 1,000m³
d9d286ee-3b26-56ce-9fd5-2744c4cc31f4 | note | Activity - HP
929aa643-972c-556c-b644-30bbf8e8fd00 | note | By - ENG
8068389f-81b5-5e5c-add9-417418b5ff36 | signoff | AUTHORITY HOLDPOINT
52a5e716-c19f-5ad8-8370-8bbc35daeeb5 | checkpoint | 2.01.10 - Clay Index
c5cb8138-5b5b-5f01-b352-637dda2343de | note | Acceptance / Conformance Criteria - The Clay Index shall be ≤ 5 when tested in accordance with NZS 4407 Test 3.5.
2ad9ee32-a09a-5f57-ac4f-c468049aee8c | note | Standard / Specification - PS - 7.2.3
b9754f71-3ee9-598c-80f5-6eed4874cf24 | note | Verifying Document - IANZ Lab Reports
d00de851-7991-56ce-854f-29f6020cdd60 | note | Frequency - 0 to 400m³ - 2 tests
1b71fb50-1e21-51f7-954d-368e6721ef85 | note | • 400 to 1,500m³ - 3 tests
3553b48c-be94-5eaf-933d-43138b9114d5 | note | • 1,500 to 4,000m³ - 4 tests
771b5fa2-88f6-5018-a3bb-7822e8da2eb4 | note | • >4,000m³ - 1 test for each additional 1,000m³
18ff526f-0935-5e42-b47e-0ba352cb4ff9 | note | Activity - HP
e7708385-c49e-50f2-af6f-296359364d18 | note | By - ENG
37c9d3b1-676e-5e35-87a1-efb852bd8594 | signoff | AUTHORITY HOLDPOINT
3243bdbe-628e-5c36-8ebd-fd3becd9b18b | checkpoint | 2.01.11 - Accelerated Weathering Testing
cdacb3fe-de6e-5c12-ad45-1dbd1af37f24 | note | Acceptance / Conformance Criteria - If the difference between the tested sample and the control is >30% in the accelerated weathering test, the Contractor shall undertake additional x-ray diffraction analysis
a9d66b2d-7268-5744-8c47-38883fc76356 | note | • The levels of smectite clay minerals are not classified as “abundant”
ccc5af32-24c9-55f6-90e9-53323ade5810 | note | Standard / Specification - In accordance with NZTA Standard Specification T20 Draft Specification
74f995cb-5cbf-5689-a8aa-04f4a1dd8737 | note | Verifying Document - IANZ Lab Reports
3b2ff59f-6c50-57e2-b1f9-7295eab28dc6 | note | Frequency - 2 tests per source 4 weeks before use in the works.
e7c1bd06-7278-50d5-86d3-bb687be7ac91 | note | Activity - HP
117a5286-a1a7-5aad-b5f6-b5ad8f6bb408 | note | By - ENG
6ab4e183-98ed-530e-bb16-371ac278c73f | signoff | AUTHORITY HOLDPOINT
d0430dca-b283-5720-b469-62a57fdf94d1 | checkpoint | 2.01.12 - Repeat Load Triaxial Test
08b10ea8-0e4d-5cc2-accc-084aca7b4501 | note | Acceptance / Conformance Criteria - In accordance with NZTA T15
a116e146-494a-5233-bce3-d2b9ff94d20d | note | Standard / Specification - NZTA T15
f29381aa-0a34-5bd4-90eb-659c4c25497b | note | Verifying Document - IANZ Lab Reports
706b2437-18b6-5b03-b048-d2d22378dcf6 | note | Frequency - 2 tests per source 4 weeks before use in the works.
1bafa94a-9672-572d-a26e-d49166cc001b | note | Activity - HP
a08e87bb-c079-574c-bde9-416f9a9578f9 | note | By - ENG
740b30b9-cfca-5337-a89e-aca4c87f0759 | signoff | AUTHORITY HOLDPOINT
fced821f-9140-5acb-adeb-311c37d3b39f | checkpoint | 2.01.13 - Broken Face Content
1dee13a2-b73f-5338-b58c-2f21196685fe | note | Acceptance / Conformance Criteria - The aggregate broken face content in each of the three aggregate fractions between the 37.5mm and 4.75mm sieves shall not be less than 70% by weight and shall have two or more broken faces, when tested according to NZS 4407: 1991, Test 3.14 Broken Face Test.
f57c44fc-b5a6-5d80-8fd0-bdfa97109bc1 | note | Standard / Specification - TNZ M/4: 2006, 4.2.2
72ce007a-6242-5bbd-a8d8-35849dcb2816 | note | Verifying Document - IANZ Lab Reports
184d8c50-9feb-5fae-9a01-4b7ec19c54f9 | note | Frequency - 1 Test per Source
285defd3-5103-5420-85c5-e8b8af0b82c9 | note | Activity - HP
d7fa7ff3-d18c-519a-b767-83a3181df103 | note | By - ENG
a3df93d1-6c56-587a-86a1-2946c4363d06 | signoff | AUTHORITY HOLDPOINT
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
722223d6-2f82-54c7-aeb7-4311df0ed5eb | checklist | ITP - Pavement & Surfacing - AP65 Material - Rev E | itp | ITP - Pavement & Surfacing - AP65 Material - Rev E
d9ad54c1-a038-5152-8598-fb6c422dc437 | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 General Materials
60a57887-488e-553a-9235-dee549dad0fa | checkpoint | 5.01.01 - Sampling and testing
f587ec91-c904-5aa5-810e-812a47bf658c | note | Acceptance / Conformance Criteria - For all aggregates, test information confirming compliance shall be supplied to the Engineer not less than five working days prior to delivery of the material to site.
cbd8acf3-e0f5-55db-8156-67ac9226e388 | note | Standard / Specification - PS - 7.2.4
93885b9b-13f0-53a3-be48-b4c45fe9878c | note | Verifying Document - IANZ Lab Reports
98899682-c28d-54da-9530-1cac6628eb21 | note | Frequency - five working days prior to delivery of the material to site.
4bc3cedf-4f02-54f0-99c0-606777acf2c0 | note | Activity - HP
1684e61d-f968-5bc6-93c8-d16116aaff01 | note | By - ENG
def14926-a024-5a92-85d5-c6280e455630 | signoff | AUTHORITY HOLDPOINT
44bbb52e-eb08-5fb4-9a98-c4769a88e409 | checkpoint | 5.01.02 - Sampling and testing
e3222ecf-c962-562e-b51d-a385ea926d99 | note | Acceptance / Conformance Criteria - Water to be used in stabilisation - The Contractor shall be responsible for ensuring that the water for stabilisation, construction and curing of stabilised layers is free from impurities that may deleteriously affect the setting, hardening, strength or durability of the bound aggregate layer.
9f24b800-ed24-5e34-9fd0-3a76c6d2158e | note | • Water from sources other than public supply may have its suitability established to the satisfaction of the Engineer by repeating the final approved laboratory based mix design tests with the water now being considered for use.
75e0f194-01e2-5647-b89b-d15318f6a4c3 | note | • The results of these subsequent mix verification tests shall be greater than 90% of the final results from the previously verified mix design. In addition, work shall be stopped if any discolouration or residue is observed when adding or sprinkling water into or onto the material.”
e658a265-fcf3-51b9-b816-6da8f17ff91f | note | • Verifying documents to be dockets from fill up station, or proof of using public water supply. Or Lab reports for alternative supply.
a3c76a02-e132-5f46-bd9e-b4e2c019c057 | note | Standard / Specification - NZTA B/6 item 5
de7c7586-7099-5189-b616-4a6a29441748 | note | Verifying Document - Lab reports
92d38b6d-5ffe-54da-ae7b-214d1c0bfec0 | note | Frequency - Prior to Works start, per source
cf34b954-d990-5942-823e-8d5103020e49 | note | Activity - HP
9af1c353-0319-5f13-b777-4c09759ce4e8 | note | By - ENG
9e0439f0-b29c-5ad6-b128-ee827b0bc0be | signoff | AUTHORITY HOLDPOINT
899bfcc4-56fb-51f7-a6a0-b3bf3866f97d | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate
dcf4666f-ed3b-5158-a808-679d32a007f3 | checkpoint | 5.02.01 - Sub-base MDD and OMC
0a20a9e1-9754-5595-b8be-f26bb33aab64 | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
dfed941e-c73f-5d66-b1a7-3eeeb24eb7fc | note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
803756db-7d93-5b60-b603-1af60b69ee66 | note | Verifying Document - IANZ Lab Reports
74aba5d3-54cb-500c-83d1-edce95b9c997 | note | Frequency - 1 test per material type
b8db62ec-cc1f-509b-9903-eb4e81b83a44 | note | Activity - H
5789a56b-3eb4-5866-9ae7-24d49846f94d | note | By - PE
08dc85f6-1e83-5eb9-95c8-9381d1b2b315 | checkpoint | 5.02.02 - Cement for sub-base stabilisation
90aad58e-40f2-5ded-aea7-47f72532c0c1 | note | Acceptance / Conformance Criteria - Cement for stabilisation shall meet the requirements of NZTA B6.
dbdace18-4d98-5009-8ab6-b14277b731a8 | note | Standard / Specification - PS - 7.3.2, PS - 7.2.6
e5b34312-89b5-5827-ba09-6bb0fcb8e0c7 | note | Verifying Document - Datasheets
4c4b00a1-be0f-5d87-9a3b-54576dcb3ae2 | note | Frequency - Prior to Use
47801d41-6821-5e8a-82e3-0184841d09f2 | note | Activity - H
04c79bb8-fe77-5de7-8f36-985b35480d08 | note | By - PE
78ae2b7a-c28e-5b57-a046-1fdb2eff521d | checkpoint | 5.02.05 - Crushing Resistance
41f160dc-388f-56b3-b37a-ddf10704fe4b | note | Acceptance / Conformance Criteria - The crushing resistance shall not be less than 130kN when the aggregate is tested
e2d9fc40-231b-5baf-9d2f-0fbd19fd2833 | note | Standard / Specification - NZS 4407: 1991 Test 3.10.
4822f417-d7af-50af-a334-6483bdcbd0bf | note | Verifying Document - IANZ Lab Reports
99c76d46-18fd-534a-9fd2-473398ee471a | note | Frequency - 2 tests per source 4 weeks before use in the works
7c1c7573-6dae-5717-b1b5-fc54365f8ce0 | note | Activity - HP
6977e619-cd8f-5904-a66f-a9a7645f4498 | note | By - ENG
fefe6c68-50e3-5203-b081-fc14cfcc29be | signoff | AUTHORITY HOLDPOINT
9022871e-5b68-5285-8105-45564ce8225d | checkpoint | 5.02.06 - Weathering Resistance
943638a1-740f-55b4-be99-af0fcc241c16 | note | Acceptance / Conformance Criteria - The aggregate shall have a quality index of AA, AB, AC, BA, or CA when tested
9db6d585-f4c9-5f36-859c-3dfb88fe2450 | note | Standard / Specification - NZS 4407: 1991 Test 3.11
094254b1-853c-5c3f-8b07-5966870ba227 | note | Verifying Document - IANZ Lab Reports
ae7cd138-fb2d-5f88-b416-1f78bfa9b31a | note | Frequency - 2 tests per source 4 weeks before use in the works
162e4230-64db-5c47-86cb-a0dfc237c92a | note | Activity - HP
17931dc9-651a-5859-8652-0f215ae0b1cd | note | By - ENG
8d6baafb-7a8d-5d80-9269-13464595db51 | signoff | AUTHORITY HOLDPOINT
85ee47d1-ad42-5e77-9b51-b0b7d10ea380 | checkpoint | 5.02.07 - Particle size distribution
e5535789-0a6e-5fe0-af5c-1f047760a453 | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1.
96e0ef6b-e2b6-5d89-be5a-93e58e38be79 | note | Standard / Specification - NZS 4407: 1991 Test 3.8.1 Standard Method by Wet Sieving
4873cafd-8d6f-5d61-bc11-6c4e07fee6f7 | note | Verifying Document - IANZ Lab Reports
b74d783c-e32c-5f19-bd48-ba28e3d805ba | note | Frequency - 0 to 400m³ - 2 tests
d39f35a7-71b1-5d66-88ed-38a7e132652f | note | • 400 to 1,500m³ - 3 tests
68fcfe30-4312-5c70-916f-ddafa39da156 | note | • 1,500 to 4,000m³ - 4 tests
009abe47-8c79-5476-bf59-fb711379c37a | note | • >4,000m³ - 1 test for each additional 1,000m³
25bb434e-40d3-55e4-bf28-275ab9962c20 | note | Activity - HP
fb6fab50-41b0-571a-bd3c-9f033205e847 | note | By - ENG
129b8835-7d77-5545-af8f-f202ea555b78 | signoff | AUTHORITY HOLDPOINT
c0dcf9e2-6abe-544f-b671-04d7121ee831 | checkpoint | 5.02.08 - Sand Equivalent
408360b1-394d-50d2-8cbe-d6a8bf76af41 | note | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 25 when the aggregate is tested
ac6fcc4f-6636-515e-b5a3-d5ab9dfa131e | note | Standard / Specification - NZS 4407: 1991 Test 3.6 (Wet Method)
db322c43-e10c-59b5-86a8-357f5e898528 | note | Verifying Document - IANZ Lab Reports
4635a1fe-6265-53b9-bb2f-ebbd287eca12 | note | Frequency - 0 to 400m³ - 2 tests
d32b7222-3ce6-5d44-8117-8d53245f7295 | note | • 400 to 1,500m³ - 3 tests
6012f74f-1ac3-5d23-8a19-9e26cf3fb202 | note | • 1,500 to 4,000m³ - 4 tests
4d7c60bb-3bbe-5e64-b3bb-3f11f650b42b | note | • >4,000m³ - 1 test for each additional 1,000m³
97d1c748-b110-5bbd-b3a5-66b8a5b9eec5 | note | Activity - HP
56d76160-229c-5574-97bb-af898fe419e4 | note | By - ENG
1cfc74a4-63e3-58ba-a4fb-88a40554c1c8 | signoff | AUTHORITY HOLDPOINT
ae882592-6535-5217-89b2-b66f7d161cf7 | checkpoint | 5.02.09 - Liquid Limit
b1f61dae-82c3-5e9e-89b9-12aec0d5b5a5 | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Liquid Limit shall be ≤ 25 when tested - The LL may also be inferred (where appropriate) from the Cone Penetrometer Limit (CPL).
d30e3560-afd1-52a2-8f65-b6d210a42614 | note | Standard / Specification - NZS 4402 Test 2.2, NZS4407:2015 Test 3.2.
a713b910-3257-556a-9998-d526eb484870 | note | Verifying Document - IANZ Lab Reports
a5c57916-56d9-5d29-af16-60561b046e11 | note | Frequency - 0 to 400m³ - 2 tests
21aff8b0-4190-58e3-b6a3-adfeb9ecaf07 | note | • 400 to 1,500m³ - 3 tests
53416fef-9ded-5deb-968d-ff0c84a6ae6e | note | • 1,500 to 4,000m³ - 4 tests
9f8f13c3-7929-5ce0-9ab2-e9daeb8a08a1 | note | • >4,000m³ - 1 test for each additional 1,000m³
39b78350-5aca-5bbb-adb5-d1db03058103 | note | Activity - HP
d696f796-fd2c-54a7-ab30-edadea7c98b0 | note | By - ENG
523797f1-355d-5b2b-98ca-c9f9f751c1cd | signoff | AUTHORITY HOLDPOINT
a21cc376-5cf7-5d74-91c9-7c1733c3fd7d | checkpoint | 5.02.10 - Plasticity Index
adcce8e1-086e-5f16-8b3e-0792d22031b6 | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Plasticity Index shall be ≤ 8 when tested
3ae28c04-98fc-56f1-97c4-9da685d1244b | note | Standard / Specification - NZS 4407 Test 3.4
62fef554-b15d-5bb2-8b95-655f9be8465b | note | Verifying Document - IANZ Lab Reports
115e070d-ecf9-51ea-9828-df026b036f6c | note | Frequency - 0 to 400m³ - 2 tests
ce1f32af-869e-5563-82da-4c6ea9d83866 | note | • 400 to 1,500m³ - 3 tests
2f47e4d6-a598-554b-9088-068be9d6f2a9 | note | • 1,500 to 4,000m³ - 4 tests
34a3e50c-cae8-5b0c-b74a-03f4ee673d85 | note | • >4,000m³ - 1 test for each additional 1,000m³
a1211ea0-d576-5ad0-99b7-8cc957e13c21 | note | Activity - HP
e436f6c2-4547-52cb-908c-cc19fa506125 | note | By - ENG
5196aee7-d9f1-55aa-b012-a6ce06f7ee5c | signoff | AUTHORITY HOLDPOINT
cb3bf6ca-20c8-5a7c-847e-d41f73e602ed | checkpoint | 5.02.11 - Clay Index
b2bbfdd1-90e7-590d-a1f7-de299ec76b03 | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Clay Index shall be ≤ 5 when tested
093a4d30-4c15-5956-84e0-5830b526ba2d | note | Standard / Specification - NZS 4407 Test 3.5
dd67cab4-a009-5bce-9ac1-39c19dcb481b | note | Verifying Document - IANZ Lab Reports
05b26edc-dd98-518e-b6f6-98acf445836f | note | Frequency - 0 to 400m³ - 2 tests
d716371f-afa1-5e38-97ee-1ceafba9e5e0 | note | • 400 to 1,500m³ - 3 tests
cfde53d7-841e-512c-aeba-e555c5bbfc6e | note | • 1,500 to 4,000m³ - 4 tests
9487e901-321c-5011-a414-7a0ca08a6e9b | note | • >4,000m³ - 1 test for each additional 1,000m³
ff882013-d580-5e74-b60d-a144e998ad53 | note | Activity - HP
b2ba9321-be58-5b53-8cd5-881dd664d718 | note | By - ENG
94cd9054-2ac2-5d95-86eb-2a71edade0c7 | signoff | AUTHORITY HOLDPOINT
00a049c7-fa08-5eaa-a1c1-4286cf25b2b3 | checkpoint | 5.02.12 - Proportion of Broken Rock
aa0b256e-7b28-5996-9be2-1f852a1da5a6 | note | Acceptance / Conformance Criteria - In each of the aggregate fractions between the 63.0mm and 4.75mm sieves not less than 50% by weight shall have two or more broken faces
482ec926-0b1f-5da2-9eeb-10a9f0030d74 | note | Standard / Specification - PS - 7.2.2
e333c2ba-7723-57a3-87b9-4d16523a0be3 | note | Verifying Document - IANZ Lab Reports
15deb5f3-d612-5476-bd5b-d4b23829a0bb | note | Frequency - 1 Test per source of the coarse aggregate. Additional samples if source is changed
4155f610-28fa-546a-9fe8-f175b8d82a56 | note | Activity - HP
7617584e-1f14-5d96-9a6e-06795b8d0012 | note | By - ENG
4fac71dd-be3d-5be6-a8e7-ade3236dd1f1 | signoff | AUTHORITY HOLDPOINT
b87390da-e8b4-5066-b43c-5d098cda23ee | checkpoint | 5.02.13 - Organic Matter
ce67a179-8cd6-5d21-9f2d-650078b91c33 | note | Acceptance / Conformance Criteria - It shall be free of organic matter
91d09f65-eb33-5b6e-a4fd-f93d0a7534e8 | note | Standard / Specification - PS - 7.2.2
e70cdb01-3c8b-572a-a18f-a87e1e5cb32c | note | Verifying Document - Photos
0809aba2-401a-5ffb-b7f0-475f02e5e2e3 | note | Frequency - Continuous
1934c074-cd46-5c96-bfb5-f5c8b3778de3 | note | Activity - I
51d07c23-348a-50b1-aa98-8690dd477705 | note | By - SE/PE
cafccf67-d4a4-52ce-86ca-59031142aa61 | checkpoint | 5.02.14 - Accelerated Weathering Testing
0192bd9c-f10b-5fc5-a61c-ba4f96f4b151 | note | Acceptance / Conformance Criteria - If the difference between the tested sample and the control is >30% in the accelerated weathering test, the Contractor shall undertake additional x-ray diffraction analysis
b273779b-40d9-52f7-8241-3fbe6fe3df57 | note | • The levels of smectite clay minerals are not classified as “abundant”
4c242fa6-3cd2-5be1-9cb0-13424bbc41c6 | note | Standard / Specification - In accordance with NZTA Standard Specification T20 Draft Specification
41b3ea5e-a1c6-5310-8a98-443fa930bc3d | note | Verifying Document - Lab Reports
bc7814fd-f2a7-5b94-85cf-ec53b9af7904 | note | Frequency - 2 tests per source 4 weeks before use in the works.
4b884df7-5ea8-59e9-9629-47b4389dc632 | note | Activity - HP
18d8d1e0-413c-5580-aef7-de3b62856bd4 | note | By - ENG
4fc46efe-5434-5360-aeea-81ccc050ba8c | signoff | AUTHORITY HOLDPOINT
52a5baa6-7252-5829-85ae-9f01011c7607 | checkpoint | 5.02.15 - Repeat Load Triaxial Test
d09076b1-b61f-5eb2-974a-f781cc4d3ee7 | note | Acceptance / Conformance Criteria - In accordance with NZTA T15
013ba046-1451-5298-8bfb-78a4bb304c9f | note | Standard / Specification - NZTA T15
8935eef6-8e74-5a06-bfea-84643c31fb0f | note | Verifying Document - IANZ Lab Reports
dd0ece6a-d4e7-5fe5-8423-8f7e23a191eb | note | Frequency - 2 tests per source 4 weeks before use in the works.
8ec6d9e7-5281-5db7-b6ab-613f13e2453e | note | Activity - HP
0763efe7-8190-5247-9b7e-fcbced428056 | note | By - ENG
44646cc1-0805-5206-8ff2-ad2805cd38d2 | signoff | AUTHORITY HOLDPOINT
0b3c41da-9864-553d-886c-e0e0f1bdd386 | checkpoint | 5.02.16 - Unconfined Compressive Strength (UCS)
b95df1b9-16bd-5fb4-8380-6ce5ceb43701 | note | Acceptance / Conformance Criteria - Unconfined Compressive Strength (UCS) testing of source aggregate for modified layers to test sensitivity to additives.
8cbd082d-b3b6-56f1-845f-7ae5f4d52587 | note | Standard / Specification - PS - Table No. 7.2
9a5e5f78-ea85-5d1a-a3e8-bd1050b974a8 | note | Verifying Document - IANZ Lab Reports
16412a24-8bb2-55e5-8dd0-893f133e87c8 | note | Frequency - 1 set of tests per stockpile at source. Set of tests to include proposed mix plus tests with 0.5% more and 0.5% less additive than proposed.
fbc17876-2779-535f-902b-4ff53d219016 | note | Activity - HP
76b1b5d9-289e-520d-8bd0-dfa2ec9522d1 | note | By - ENG
03cf8542-b3b1-5080-a4b3-84858ca10066 | signoff | AUTHORITY HOLDPOINT
74060e22-bf57-5ae1-9306-20409b4430fa | checkpoint | 5.02.17 - Indirect Tensile Strength (ITS)
e47a2fa0-3663-5f12-aad1-d62f108d6350 | note | Acceptance / Conformance Criteria - In accordance with draft NZTA T/19 at the rate specified in Table A7.4 using 4.0%, 4.5% and 5.0% cement (with 7 days curing) and results forwarded to the Engineer not less than 7 Working Days prior to construction for confirmation or adjustment of the additive contents.
e5bb67bd-1a40-5895-a4f1-d9bb7d80efb6 | note | Standard / Specification - NZTA T/19 - Table A7.4
e7824d9c-8295-5b65-8434-4efbe8a73f4f | note | Verifying Document - IANZ Lab Reports
e16db668-c136-5947-82cf-f976b5d3771b | note | Frequency - 1 set of tests per stockpile at source. Set of tests to include proposed mix plus tests with 0.5% more and 0.5% less additive than proposed.
f1e2d0a3-a3cb-558d-bf43-fbe94d13b4dc | note | Activity - HP
397eeebd-78df-50e8-9e26-e4bf565540a5 | note | By - ENG
69dfb56e-21ee-5ddd-a6dc-cf1b2b495b33 | signoff | AUTHORITY HOLDPOINT
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
800d5d05-b43e-5ae9-83b7-c92acf52c46d | checklist | ITP - Pavement & Surfacing - Basecourse - Rev 1 | itp | ITP - Pavement & Surfacing - Basecourse - Rev 1
9dbf9507-d5c1-5f76-b0e9-632a875b7d7c | section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
cefa3a25-1c25-5ccc-88ec-7d7d361477ea | checkpoint | 1.01.01 - Construction Pack
86b41d6e-7a57-54f0-acd4-9e40ed52643f | note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled, uploaded and transmitted on InEight before works commence
48b32bc9-0a62-50c7-92a9-de4758e2d5b9 | note | Standard / Specification - Downer
c2407745-6aec-5335-a45f-487d44e0628d | note | Verifying Document - Construction Pack
635d558b-83ae-53b6-8c28-324ff841586c | note | Frequency - Prior to Works start
179c0622-56ca-569d-ba6e-cef8dd739f70 | note | Activity - H
07f5d58b-597f-5e2a-9f4c-03dbb5fe0c94 | note | By - PE
7d7484e5-7e1f-5fce-9b75-f8e21eb19c86 | checkpoint | 1.01.02 - Survey Setout
ec56372d-7f16-5af7-9f23-164babafc370 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
28cbcb6f-c9fb-5f99-97ef-82f133603fab | note | Standard / Specification - Downer
571e6655-cf54-56a2-9cc4-32c6cf1b01a8 | note | Verifying Document - Survey Records
f8e4441a-1fc7-5887-bc24-e5e60ee6611a | note | Frequency - Prior to Works start
b24be07a-99c7-505d-bcb1-651936634b9e | note | Activity - H
eb0f9fe1-4d71-5775-8d5e-50050bef0de8 | note | By - SV
79e2e2cc-742b-5773-8fd6-174684bde5a5 | checkpoint | 1.01.03 - Service Location
cd865226-1847-5604-87bf-c74fdf0f19a3 | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
806a9f08-5828-5c64-bc3e-a0cb61d5562b | note | Standard / Specification - Downer
5ddce83b-fb05-5414-958c-e8cb3781aa33 | note | Verifying Document - Excavation Permit
867bcb55-3fec-55a1-b73e-5f950b8c745d | note | Frequency - Prior to Excavation
f7a63b5b-8d8b-5f81-ba95-3bfcd9af5f72 | note | Activity - H
b2a6ad39-f65a-58c5-b7c7-7bde258f6dd4 | note | By - SE
ad83f4fc-998f-5888-aac1-cc53c7027f3f | checkpoint | 1.01.04 - Internal Permits
8ef54786-5417-587e-b131-af96f335f981 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. if applicable.
d05b2ec1-4b76-5f23-95bc-f96aab74703d | note | Standard / Specification - Downer
3480ef1e-9618-5dc4-a9a1-7d1d972a0262 | note | Verifying Document - Internal Permits
5674f571-bbd2-58e6-ae20-7a40c27a268a | note | Frequency - Prior to activity being undertaken
21fbf00a-0cdf-5c56-b06f-31055c0966db | note | Activity - H
c5e199e6-c2fe-53c2-9477-f27de993e720 | note | By - SE
e11cb217-f08d-5dc6-99ac-594e90eeba14 | checkpoint | 1.01.05 - External Permits
61f5d04c-2805-5c3f-abc9-de003443ecb3 | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc, if applicable.
fe163655-f22f-5068-bc08-29a102908d62 | note | Standard / Specification - Downer
9f87a84d-c1e7-5534-9993-4b54a1767bfd | note | Verifying Document - External Permits
843356da-df80-5dec-8e71-df4baaa2d60a | note | Frequency - Prior to commencment of activity
33c77b62-d5e6-5d1d-bf39-72822d0fa627 | note | Activity - H
093b1822-81bb-5110-af70-8af678b7a11e | note | By - PE
43363844-3b56-5615-9c65-3fbf47407c1a | checkpoint | 1.01.06 - Approved Construction Drawings
faadc6af-5fc5-5d53-850f-a7ec9dc5cd62 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
4bb0d13c-160f-5d2a-8221-f236cbe9a59b | note | Standard / Specification - Downer
ce420d1e-c0ed-5cdd-aa45-43bd7850568d | note | Verifying Document - IFC Drawings
5e753f69-7365-5fc6-9c5a-7b100bcdf085 | note | Frequency - Prior to works start
4b246132-854c-59e0-b14e-8bf9a1b68ab3 | note | Activity - H
b25acc76-bd2a-5e63-a65f-bfc35c711d0e | note | By - PE
65941cbf-2f0f-533b-8392-c7461b71c15e | checkpoint | 1.01.07 - Subbase Approval
0c114bd5-9799-56e0-b63a-0ad5d4fb9e0b | note | Acceptance / Conformance Criteria - All subbase QA to be sent to Engineer for review 48 hours prior to placing basecourse. Final inspection of subbase required, looking for any cracks in stabilised pavement and pavement is clean, free of and contamination
22226472-fa19-56c0-a111-b205214c4dad | note | Standard / Specification - PS - Page 42
854702a8-e776-568c-a112-a6486a17a17f | note | Verifying Document - ConQA
a90e1905-ceb6-558f-80c3-6a4abce9955a | note | Frequency - Before proceeding to the next layer
29b3dba1-842b-5a4e-8b73-4613dc36d483 | note | Activity - HP
a16e36c3-e5cd-5bfe-99b1-d56bc2c4dbae | note | By - ENG
4de458ee-d43a-5185-b6f3-d9955ae6749c | signoff | AUTHORITY HOLDPOINT
2099df3b-c276-5838-a49f-4a50752ce07c | section | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
352fed59-897f-5876-9fd2-24566b9b76ad | checkpoint | 3.01.01 - Average Uncompacted Layer Thickness
dbbd429c-71bb-5812-85da-dcc9a18eedc9 | note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
a371278e-8f76-5b57-b0e1-d6b44c03d6d2 | note | Standard / Specification - TNZ B/02: 2005 - 7.3
b40b0852-21dd-5607-a013-f8e6812c5725 | note | Verifying Document - Survey / Level Checks
8ead24d5-9c8f-5d9f-b807-27ff02162e82 | note | Frequency - 1 test per 20m
030068ab-38a5-5036-82f6-7ac7a7c1bd1e | note | Activity - I
659025bf-5cfa-55f8-856f-5b915f8d83d3 | note | By - SV / PE
6bff0f11-9f30-55fa-ad6d-a9738b399ec2 | checkpoint | 3.01.02 - Basecourse MDD and OMC
9fb00a71-854c-50c7-beeb-d555fad763b0 | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). Test to be at heavy compaction vibrating hammer, Test on Mat Samples on site.
d7dcc15a-3087-5bd3-8abd-001433a8da70 | note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
9938c1d4-af1e-54ec-ab05-56cbfcbe7dab | note | Verifying Document - IANZ Lab Reports
97c4a02d-759c-5772-a5d0-568ae3601e2a | note | Frequency - No less than 1 test every 5,000m³ (in place)
667eba4a-5457-54fb-b177-accc707507cc | note | Activity - R
02b79946-e421-55fa-8f12-ece77e587346 | note | By - PE
2720a964-8fc8-5970-9840-dd73e5fd0868 | checkpoint | 3.01.03 - Plateau Density Test
92929d68-63f0-57fb-ac65-531cb6e97659 | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC.
7ae1ef54-9208-5e9a-9fa2-285c104c3707 | note | • Every plateau to be completed at start of works and witnessed by a member of BBO.
80a36b75-0644-57d6-b71a-01cbf8adf488 | note | Standard / Specification - PS - Table 7.2 - 2.3
1c6e177a-3638-54ba-b5da-acd2905a56f3 | note | Verifying Document - Plateau Density Report
23d37c95-78a9-507c-934c-2f3070031b71 | note | Frequency - 5 tests per 10,000m2
45af7d7f-9458-53aa-8eec-57f4e7c57ee8 | note | Activity - I
d61ec9d0-c82c-5d5b-b51c-8d408366ffc7 | note | By - PE
4e14b0f0-c185-58d4-9839-d9056137f0a5 | checkpoint | 3.01.04 - Plasticity Index
e71f59ac-edd0-5e70-beca-82c70dca5b37 | note | Acceptance / Conformance Criteria - The Plasticity Index shall be ≤ 8 when tested in accordance with NZS 4407 Test 3.4
b86b747b-e06f-56e2-b657-241efaf003a0 | note | Standard / Specification - PS - 7.2.3
c489a8b1-a8ea-5f82-80ba-4ff4eded1c9a | note | Verifying Document - IANZ Lab Reports
d0adc64e-bcd5-5457-86b4-ec52e3ab0aa1 | note | Frequency - 2 tests per 1000m3 (in place)
90bd30ec-e53e-5268-94dc-d9959a20dc19 | note | Activity - R
a78cabee-87cf-590d-9de2-bf174b81ae9d | note | By - PE
8a2c0976-e84e-5cf4-b6b0-3ac926fe3e13 | checkpoint | 3.01.05 - Clay Index
3a8afc40-bfb2-549a-9089-5e6cbffcfc0d | note | Acceptance / Conformance Criteria - The Clay Index shall be ≤ 5 when tested in accordance with NZS 4407 Test 3.5.
18e72bbf-5f3e-5c0a-b3e4-b741b323ed91 | note | Standard / Specification - PS - 7.2.3
2cfd3280-099b-589e-b0ad-7f3ef4136fe4 | note | Verifying Document - IANZ Lab Reports
f2948c97-c966-5ad9-a79d-7bcb312db057 | note | Frequency - 2 tests per 1000m3 (in place)
3d3935ec-fb55-5601-bae8-b23d5ec8039c | note | Activity - R
512ba664-826d-5b63-aede-02a1b8d62ee4 | note | By - PE
b88285ba-0f34-5cb7-a186-5c9887a7c5ef | checkpoint | 3.01.06 - Sand Equivalent
e166ae74-624b-5e5b-8d9a-3a8218aff852 | note | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 40 when the aggregate is tested according to NZS 4407 : 1991, Test 3.6 Sand Equivalent Test.
de055241-e1a2-5d0b-af5e-54efa88d6216 | note | • If Sand Equivalence is < 40, then Clay Index shall not be > 3 and Plasticity Index shall not be > 5 (both being tested in accordance with the methods described above).
3bcda7c7-cfe0-5d4e-9e67-ea1bf377c756 | note | • The Sand Equivalent shall be determined using the Wet Method in NZS 4407: 1991 Test 3.6
c0544496-3ce2-5232-addd-e6938e540abe | note | Standard / Specification - TNZ M/4: 2006, 4.2.1.1
95f11bf1-a8e0-5084-9d61-adb3d2756506 | note | Verifying Document - IANZ Lab Reports
a9ad710d-e165-5ea8-9e4a-195b132d5d53 | note | Frequency - 2 tests per 1000m3 (in place)
dc69b47a-7de9-58a0-8dc6-5dfc49859c1a | note | Activity - R
9a56c638-031b-545e-9eb5-c0d4183f3245 | note | By - PE
449c088a-3ebf-54be-9533-ad0513888c3d | checkpoint | 3.01.07 - Particle size distribution
dc243aeb-782c-5f73-b035-5d90192571f4 | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 2 and 3 from TNZ M/4:2006.
b0c97723-290e-5e45-b606-54c180dd52e6 | note | Standard / Specification - TNZ M/4: 2006
c9462b1e-4a16-5f8f-a838-4b695ad099c3 | note | Verifying Document - IANZ Lab Reports
de976264-2028-5f1e-8b40-58405ee4b2d9 | note | Frequency - 2 tests per 1000m3 (in place)
b5a313f0-8f07-5136-8235-a6fc300ace71 | note | Activity - R
b094c546-d0d7-50d0-91ac-5751b343c6f2 | note | By - PE
e50d581c-ff5c-5a8b-9090-af0dbfd70512 | checkpoint | 3.01.08 - Basecourse Pavement Layer Compaction
8450682a-d54d-54ca-a371-5bb0648b9165 | note | Acceptance / Conformance Criteria - Mean Value ≥ 98 Minimum Value ≥ 95, Backscatter.
8e0dcf5b-a8df-5f00-b697-e5b4bce57cf6 | note | Standard / Specification - TNZ B/02: 2005 - 7.6
b8033767-e17d-51ab-bb92-a013d34318a7 | note | Verifying Document - NDM Report
bab4c537-af20-54f8-af38-8deb39ed41a2 | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
278f4a50-e7d8-5134-80fb-5ad235f4576a | note | Activity - I
3423ebfa-0c74-5182-b8a1-5bd4e9ada4e3 | note | By - PE
076acd1a-d68c-56e6-8e09-9d28fe8e6eea | checkpoint | 3.01.09 - Surface Shape
aa160684-d90c-5c2f-8670-9c7345013797 | note | Acceptance / Conformance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual..
6fd83484-45a3-58f8-9dfb-7c1c0a96d94b | note | Standard / Specification - TNZ B/02: 2005 - 7.7
96340ffb-3e65-5eac-96b6-68c84daeac5e | note | Verifying Document - Survey / Straight edge Report
baf33aa0-13cb-5856-9ee2-6358746e87ea | note | Frequency - Prior to sealing
c7ebfe0c-56a3-53c5-927d-4715673a2ac2 | note | Activity - I
2e63751b-2609-5a3d-a6ec-0035cf8985f6 | note | By - SV / PE
68647e04-f177-5bf8-ae53-a691675b2ae3 | checkpoint | 3.01.10 - Holding Water
9d5e3f97-39f7-5393-8985-e46df7d9353c | note | Acceptance / Conformance Criteria - No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1%
9e6d2939-557c-5f76-9ccd-0aaf26976c71 | note | Standard / Specification - TNZ B/02: 2005 - 7.7
e2d3939b-60a7-5161-99e9-c40aa73acc53 | note | Verifying Document - Visual Inspection / Site Note
a9885a41-188f-5625-9424-581588ef206f | note | Frequency - Prior to sealing
c2a0b25b-48f3-5d30-9933-3bc05f48181c | note | Activity - I
a5393c6e-4bf8-5dc9-b8a0-9fe9bf6779f0 | note | By - SV / PE
114181ad-1d3e-5704-8bad-57e55e62cc3f | checkpoint | 3.01.11 - Maximum Width Variation
c54a8880-c803-53c9-905e-907270e1e49d | note | Acceptance / Conformance Criteria - Unconstrained : –20 mm +100 mm
4f2614cf-5d0f-5220-b839-2250b118dac0 | note | • Constrained : Zero
0a07615c-bdc7-587d-93e7-0fa6ef846f00 | note | Standard / Specification - TNZ B/02: 2005 - 5.1
509cb0c4-b4c6-5133-83a7-abddb21b59b5 | note | Verifying Document - Survey / Level Checks
8546fa8e-8880-5859-9034-8b5f93cc0f54 | note | Frequency - Before Next layer or Surfacing
88f457ae-d9e2-5dda-96de-604c02b89acd | note | Activity - I
1b214982-fb22-5d0e-ad43-16521eead8bc | note | By - SV / PE
0ac7854a-15e5-5cba-9b22-49dac0fe46f5 | checkpoint | 3.01.12 - Maximum Vertical Basecourse With Concrete Channel Variation
b4a7ebbb-018c-5af9-9c36-b41eb6e36384 | note | Acceptance / Conformance Criteria - At or close to the lip of channel: –5 mm +5 mm
a908229c-118d-555b-8caa-30536f9ea3d8 | note | • At other locations on pavement: –5 mm +15 mm
2a799e2e-2862-583b-9ee6-f85293c43566 | note | Standard / Specification - TNZ B/02: 2005 - 5.1
f7bac258-a191-5284-b56a-383259c8f3bc | note | Verifying Document - Survey / Level Checks
b45a69e9-5f6f-5327-84db-99e2e8e8e8ac | note | Frequency - Before Surfacing
d88b2f97-bb88-5415-8669-2314cddde2d5 | note | Activity - I
732ddd51-a403-5cbd-8243-c72ee577856a | note | By - SV / PE
60f50fac-f8d5-5660-82a2-c867c3e1eeb4 | checkpoint | 3.01.13 - Maximum Crossfall Variation
5c67f160-a2f0-52f8-bd42-ca23ee461ed7 | note | Acceptance / Conformance Criteria - The crossfall between any two points more than 2m apart, transverse to the centreline, shall not depart from the crossfall shown in the documents by more than 0.5%
ea889ddb-0e1d-5c83-bc77-c98178a4b221 | note | Standard / Specification - TNZ B/02: 2005 - 5.1
9c527da4-f334-5def-9908-16581146a1d7 | note | Verifying Document - Survey / Level Checks
12ebf109-2be6-5908-ab45-7c266f20332a | note | Frequency - Before Surfacing
11e72989-7bc6-5b31-9135-f0d7b62160fe | note | Activity - I
888d745c-7ad7-5f0a-9f6e-38e8a8b6c5ca | note | By - SV / PE
5d9724b3-36dc-5598-895e-a900378b0ac2 | checkpoint | 3.01.14 - Benkelman Beam
4b5b3f0a-183d-5bad-a8f7-b0818fd4feff | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer. Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY
8126b007-cc77-532a-bd21-14c073978c8d | note | Standard / Specification - PS - 7.3.2
44fa1f00-8205-5566-8533-f958b07c388e | note | Verifying Document - Benkelman Beam Report
09ab0245-b2b2-5a04-ace4-d10a308c257c | note | Frequency - every 10m of each lane – staggered between left and right wheel path.
be216873-42cc-5f8a-9ca4-94e7e2d5e346 | note | Activity - R
678cb500-e4e0-5f55-a9d7-eae559b8cca6 | note | By - PE
d9a818f0-8e9a-541c-9894-3a3f6a089dea | checkpoint | 3.01.15 - NAASRA roughness
cbc72159-c7a3-5248-b9fa-4b94345cd365 | note | Acceptance / Conformance Criteria - The longitudinal smoothness of the final surfacing layer shall comply with the maximum NAASRA roughness value detailed in the specific contract requirements. (Recommended but not required)
e65d3e44-613d-58e9-815d-8d6ee333a610 | note | Standard / Specification - TNZ B/02: 2005 - 7.7
f1bbe188-bfad-554e-9963-e3f3b39545ba | note | Verifying Document - Test Report
802ff844-fdea-55c2-93c0-8ab81c71a1f2 | note | Frequency - Prior to sealing
b5a75739-990b-5360-a212-bfef6bf93040 | note | Activity - R
f6c7ac08-c956-5cb3-9ea3-82b27ff339de | note | By - PE
2422f5b8-6c41-5a92-8059-73c45dd7ed52 | checkpoint | 3.01.16 - Running Course
6ddc7923-4ea0-538c-ae2e-d8a58e7ee576 | note | Acceptance / Conformance Criteria - If running course is used it shall be spread uniformly over the pavement surface and maintained until removed. During working hours traffic shall be channelised by suitably defined traffic lanes with frequent transverse shifts of the defined lanes to obtain an even spread of traffic over the entire surface.
97ad3067-b7f0-5183-9345-e0fee5d98b01 | note | Standard / Specification - TNZ B/02: 2005 - 10.1
02bd5c5e-5d29-59e1-8ff6-cae122d46f05 | note | Verifying Document - Site Notes
f865adc9-6ac9-5412-824c-c1bc4657fe59 | note | Frequency - Prior to sealing
4f958e86-7437-5460-81fa-2c20b405c6af | note | Activity - S
307c7f07-0e69-5b30-9a9c-742cac6987f0 | note | By - SUP
8e7858c9-873d-51d1-a21b-ad5d40fe337a | checkpoint | 3.01.17 - Surface Finish post sweeping
79301678-cdc5-526b-92a5-ec40a58b15ca | note | Acceptance / Conformance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
f1193419-55d8-5a46-bbc4-268999939f01 | note | Standard / Specification - TNZ B/02: 2005 - 7.8
2c5eaac8-6be2-5db5-9e07-971bcecf801f | note | Verifying Document - Photos
f4da713c-d90c-560a-bec2-643d270444e3 | note | Frequency - Prior to sealing
06cb4779-3c73-5927-bd81-50253589081b | note | Activity - R
650e5f29-2aab-5136-a6e5-352e41824e4c | note | By - PE
935cb117-67ba-5982-9257-c1cb9a890a02 | checkpoint | 3.01.18 - Tie in into Existing Pavement
e47c839e-10ab-52bc-9da5-4b3f5302db06 | note | Acceptance / Conformance Criteria - Where tapering of basecourse including finishing layer aggregate is necessary to provide a smooth transition from the new surface to an existing surface, placement of the basecourse or finishing layer shall be stopped at the minimum uncompacted thickness specified in clause 7.3(a).
f49955e8-2930-5eaa-8fff-4aa29fef0f12 | note | • The Contractor shall then saw cut the existing seal at the tie-in (end of taper), remove existing pavement material and replace it with approved basecourse to an average uncompacted thickness of greater than 2.5 times the maximum particle size of the basecourse used.
79ff790a-0eb1-5f0b-bdb3-8bd78d10ad67 | note | Standard / Specification - TNZ B/02: 2005, 7.4
29ad3d21-5e2a-5945-88fa-8b02f6537760 | note | Verifying Document - photos, and survey data of undercut
bd7ebd18-69e0-5efd-ba7c-bb5f6c987414 | note | Frequency - Every tying into existing pavements
91296060-7787-5b8d-8503-893e4f648768 | note | Activity - I
623ed7a7-5277-5241-9051-22912d88a908 | note | By - SV / PE
84c3283d-24bd-504e-b593-7adb2a662256 | section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
3b5a624e-1a11-5114-9440-fe27a39734f1 | checkpoint | 4.01.01 - Survey Records
61996f2a-360d-58ca-b002-d0ec112979d3 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and record.
ef33a047-ce94-5d83-9ec1-97210b4bb05d | note | Standard / Specification - PS - Page 42
9f15b713-aa3c-537d-a7c5-4acc6e9e898e | note | Verifying Document - Records
ee3094fe-e7d2-51aa-bc36-b1fa4b41ea8e | note | Frequency - Post construction
ce7486bf-d5e6-58ba-9bf6-7f600631abc4 | note | Activity - H
beea42b2-951f-576f-9550-2639c1a409ef | note | By - SV
e8ea0340-b993-5d44-af71-763ab2d18509 | checkpoint | 4.01.02 - Redline Drawings
6b4ad168-19a5-5e59-baa8-dd5981f8c644 | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
e38cab94-b76a-53bd-a428-60832ee679fb | note | Standard / Specification - Downer
95e8391a-7508-5b76-8a26-3cf9c3b3a58b | note | Verifying Document - Redlines
1808be42-969c-5144-9ffb-757393ac708f | note | Frequency - Post construction
5e63c918-6e2f-5606-9087-3b173c5b56a6 | note | Activity - H
a8b3b982-00ae-54bb-bc28-91cd1ff00f38 | note | By - PE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
589c503d-a1e4-5603-9c3f-8b673493a762 | checklist | ITP - Pavement & Surfacing - Kerb - Rev C | itp | ITP - Pavement & Surfacing - Kerb - Rev C
cdc14ca8-f130-5a81-8492-a1c271a003a1 | section | SECTION 1– PRELIMINARY - KERBING
8453d9d0-a56c-5a53-a197-8b2f7f5761bd | checkpoint | 1.01 - Survey Set out
7d955466-29de-5316-9cfa-6c42ea873290 | note | Acceptance / Conformance Criteria - As per design, the surveyor to install lift pegs
97b6a2ab-3b99-59f3-9237-51a91370b802 | note | Standard / Specification - PS - 2.2.12
26c38dfb-9763-53d5-b10c-409bef813166 | note | Verifying Document - As per design
4d3edfad-dd12-5daf-a5a1-d1bc12648f78 | note | Frequency - As required for Kerb construction
3826f264-8d56-5387-b812-a1268fcd05e7 | note | Activity - A
16ed9906-4cce-57a0-82c8-faa1220be6e5 | note | By - SV
ec6b68b6-398a-5362-9431-48ddad7f9a83 | checkpoint | 1.02 - Kerb construction Set out
7348ea96-65f5-52e4-927c-1588f047e9f4 | note | Acceptance / Conformance Criteria - Ensure that steel pins and string line are in accordance with design levels and entranceways and kerb transitions have been marked. Tolerance +/- 5mm (basecourse level tolerance at channel edge)
9adb5bc4-eace-5244-a0fe-0a5e2bc7736a | note | Standard / Specification - RITS - Page 201
e2521931-9bbb-5066-8e60-a7482a2fc932 | note | Verifying Document - Visual inspection and measurement
a516095d-e0e6-5907-8bd3-1ba4d085c40c | note | Frequency - Prior to slip forming
dc8af7b1-bae9-5b97-903e-dc56e1da1340 | note | Activity - I
b1aa47bb-a769-516e-8eaf-3faecb7c4708 | note | By - SE
0b888b88-3be9-589e-9033-069487cddb43 | checkpoint | 1.03 - Approved kerb and Channel profiles
8c78ac23-1bb6-51fc-afb5-2f1a9c74b6b5 | note | Acceptance / Conformance Criteria - As per drawing no. 146000-002A-1901
18fcfc32-240f-5474-adc9-80409f710992 | note | Standard / Specification - As per drawing
464ca852-6c7f-522f-8227-540c92e95b91 | note | Verifying Document - As per drawing
0949db91-0086-5b5d-ab2d-a8f6802232df | note | Frequency - Prior to construction
3515316a-d3d8-5a40-882d-b135bce1d1ee | note | Activity - I
b69c62b9-f656-5e4a-a6c7-a27855f15ba1 | note | By - SE
033b3647-f5f1-5bf7-baf7-399d874f5df5 | section | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING
27c72069-19ec-52ce-adee-b19aed2e4830 | checkpoint | 2.01 - Approve mix design from Certified batch Plant
e9ef93c1-b0c1-5fd7-9d24-64764cef673b | note | Acceptance / Conformance Criteria - Material meets project requirements - 20Mpa Kerbing Mix
5a0ef905-ea0d-5046-bcce-41ec7bcddaff | note | Standard / Specification - Refer to RITS - 3.4.5.2 / 3.4.5.6
ef13bb40-cf14-58bf-bbb8-a682222869bf | note | Verifying Document - INSERT APPROVED MIX CODE
55cbc80b-03cd-5e9c-8a5d-801836757880 | note | Frequency - Prior to construction commencing
83948472-7d3f-5c90-8b83-f23ecd63605d | note | Activity - C
2465b951-f961-5f00-a62a-e1a9ced4f074 | note | By - SE
719e57fd-6345-5aac-a1f3-c909a0dc1dcc | section | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING
774acca9-538d-5356-ab81-dbc0ca40defb | checkpoint | 3.01 - Survey Set out Confirmation
97b3a708-4ec3-5ea4-964c-3f03734ab723 | note | Acceptance / Conformance Criteria - Ensure kerb preparation is to design level.
923bc9bc-8d0e-535f-8ab2-f2d5c9e2bec6 | note | Standard / Specification - As per design
16f6083f-6ca4-5c31-988f-54abfaca1e06 | note | Verifying Document - Survey Records
792c7781-ea5f-555d-aebe-33c0d2cdf6e8 | note | Frequency - Every steel pin
1009bd04-9c5d-5563-9afe-afb34af2ca8d | note | Activity - I
8b77a263-a130-583b-a57d-6898303d9bff | note | By - SE
308f08a1-4d4a-51d9-a1e5-2b2612caf3b4 | checkpoint | 3.02 - Clegg Hammer Test
3e6f909a-0839-5771-b87d-7ce49744648f | note | Acceptance / Conformance Criteria - Only if kerb and channel is constructed separate to the road, the base that the kerb and channel is founded on - Clegg Hammer must be tested every 15m at 25 CIV (where applicable)
fb0bfa8f-da6d-54cb-a3cb-70013c6fdcbc | note | Standard / Specification - Refer to RITS - 3.8.2.10
2ef0d09c-ce74-5972-bd92-777b04b6e82b | note | Verifying Document - Test Records
4ec4f351-5c24-5ba7-8c69-1ece04a4c8bf | note | Frequency - Every 15m prior to slip forming
be6223ce-c3d6-59d0-a02d-464d8ffbb2dc | note | Activity - C
d025571d-7664-5551-b043-b5225791faf4 | note | By - SE
9e60e85d-45af-5685-b945-345381fb2de6 | checkpoint | 3.03 - Pre-pour inspection
45af77d9-6b82-5f2f-a0de-f716e11e7cb1 | note | Acceptance / Conformance Criteria - As per RITS specification 3.4.5.3, BBO Engineer approval to proceed. / reo-inspection with 24 hours’ notice prior to pouring
f03b22cb-36fc-5e0d-9952-4a8e452058fb | note | Standard / Specification - Refer to RITS - 3.4.5.3 PS - 2.2.16
be021b70-d6ba-5cf3-93ba-158dc14da3ca | note | Verifying Document - Visual inspection / Photos
bf852721-07f3-534b-8942-39cc933eba36 | note | Frequency - Prior slip forming
21a22d89-90da-54d7-b43c-0dadef67a690 | note | Activity - HP
8001cba0-7ef9-5746-9d63-52760940e199 | note | By - ENG
aa095e2d-cd18-55cd-b312-cc90f265b12f | signoff | AUTHORITY HOLDPOINT
dea8f8d1-2346-595d-9723-c588db945421 | checkpoint | 3.04 - Concrete Cylinders/Slump
ddb9f5a2-1b90-5712-9e78-932c193136ba | note | Acceptance / Conformance Criteria - Minimum 20MPa strength, 1@7-days and 3@28-days
f8ebdf82-eed3-5dde-a8dd-6f55c7ce0d94 | note | Standard / Specification - RITS requirement (Drawing D3.3.3, Note 1)
5da12b5e-1aed-553b-903a-b2fb4fe361ea | note | Verifying Document - IANZ Test Records
d7d20e1a-f544-582c-9f56-08e2a8eae494 | note | Frequency - Each pour day
1ed0ab54-0805-545d-9def-36e384b5e2ba | note | Activity - I
d6de34f8-b1bd-533c-8817-8055611e107c | note | By - SE
dba6abea-e77c-54a1-b48e-7480193017da | checkpoint | 3.05 - Curing Of Concrete
2d7e457a-1623-518d-9b8b-a99d89e0a4d1 | note | Acceptance / Conformance Criteria - Curing period shall not be less than 36 hours
b3ff426b-615e-5670-8c03-c611187b5513 | note | Standard / Specification - Refer to RITS - 3.4.5.5 / 3.4.5.9
90535db4-5f9b-5af8-b3fd-b755221f2044 | note | Verifying Document - Visual inspection
75f8cc93-2962-5300-b563-0f9e23f9fee8 | note | Frequency - Throughout the activity
69ea095c-57d5-5861-a60c-8c201100e1e2 | note | Activity - I
398ec7d8-bfa2-56ec-a231-3e0b6ae49899 | note | By - SE
1f0c2293-e94e-57ec-bf45-41f99084e0f0 | checkpoint | 3.06 - Post-pour level check
cb1f1576-ba0f-5896-bed6-e6e7e8b0115b | note | Acceptance / Conformance Criteria - As per drawings
39811371-720c-5a52-8bfc-b16b362c0efe | note | Standard / Specification - PS - 2.2.12
28bc6470-95ac-59d5-833f-033cb02967a4 | note | Verifying Document - Total station topo and check prior to carrying on with further pavement layers
1f2a57e0-d01e-5bb3-abd5-3245436761c5 | note | Frequency - Every survey peg
ee1fe224-ff61-51df-b342-f316a7f93d55 | note | Activity - I
1c5b9fe2-4120-5d6e-a238-36aefb19ccde | note | By - SV/SE
692fdb81-91c4-5d69-bf2d-1ac0c49c007a | checkpoint | 3.07 - Contraction/Expansion Joints
ac9db46b-4000-5c9a-80ee-f2ac39bb4a78 | note | Acceptance / Conformance Criteria - Contraction/Expansion joints shall be formed or cut along the kerb at a maximum spacing of 3.0m.
5a4c419d-4412-5b68-90ec-12aacb6786c7 | note | Standard / Specification - Refer to RITS - 3.4.5.8
bec91869-f51b-524a-9605-bd5f610022dc | note | Verifying Document - Visual inspection
0492c58f-995b-5fc7-b03b-1a99b0dc1fdb | note | Frequency - Every 3m.
ca5bb3a1-1e2a-5278-beca-5bb81b49f4f2 | note | Activity - I
be0b39af-554b-5a1f-b5d2-8b6597f4d8b8 | note | By - SE
d439609d-e2d9-59c7-9a4b-c7012e656f55 | checkpoint | 3.08 - Concrete Mix Dockets
c9399c42-c5a4-5deb-81c7-357117b23aff | note | Acceptance / Conformance Criteria - Matches approved mix code
13d4a077-ec71-502a-a1b6-21162c175b8a | note | Standard / Specification - As per approved mix
5bf57c96-5735-5dde-b4a4-c6d7f111b5d4 | note | Verifying Document - Dockets
b6326348-0f0d-5545-9428-805af4e2b492 | note | Frequency - Every truck load
1c065f24-baba-5f32-8ac5-e99b9f1fc80b | note | Activity - R
273e9cba-6eca-542d-bd1d-cba2738f7296 | note | By - SE
135542d8-784f-5c4d-8a96-ae6d725ae438 | section | SECTION 4 – POST CONSTRUCTION – KERBING
dc3fbf65-7210-5b9c-8d1e-64e4bd132529 | checkpoint | 4.01 - Post pour inspection
0f047b9f-8ee3-5bed-bca6-d64c1e72f853 | note | Acceptance / Conformance Criteria - Acceptance and sign off by the client Engineer.
83e48047-0b11-5148-b984-ddbddbd42a89 | note | Standard / Specification - Surface finish and levels acceptable
65bb29c0-80b3-5be3-af8d-d2bac7629509 | note | Verifying Document - Review of total station topo
7f87d946-d5b3-5d3f-ae15-7bbc4d7301c6 | note | Frequency - When work is complete
bdae422c-284e-5c67-b1f0-ebc7fa266e5d | note | Activity - I
169369f3-d955-5506-be6d-13c132ead951 | note | By - ENG
804eb43b-8914-57f5-88ed-27ac22d9ca25 | checkpoint | 4.02 - Redline Drawings
8b1b8286-6eed-5797-a9a9-39828abdaf1b | note | Acceptance / Conformance Criteria - Electronic points file to be provided
0d50a8b1-6c63-596e-9ab1-a03435d3780f | note | Standard / Specification - PS - 2.2.17
e5705a29-9315-5b47-bd59-c92ee73bb244 | note | Verifying Document - Total station asbuilts
96c33f0b-bf83-5f1c-b914-125971f39f41 | note | Frequency - When work is complete
b93fa637-87ea-53b9-8322-c0f6c07828c0 | note | Activity - A
bf15c63c-7bb5-5654-9fd9-d3b4d797c932 | note | By - SV
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
aedc4cf4-0c15-5a97-993b-f5542e50de7f | checklist | ITP - Pavement & Surfacing - Sealing - Rev 1 | itp | ITP - Pavement & Surfacing - Sealing - Rev 1
8b5943c0-4539-550c-8dad-5350406ef755 | section | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
adfc0f61-f139-5650-a9a6-bf02e023e388 | checkpoint | 16.08.01 - Sealing Chip - Source Property Tests and Sampling
f72cc165-27da-5cd3-a2a3-8738244d63b5 | note | Acceptance / Conformance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV
423c1f2c-1b85-59ee-8837-db3ca86913c7 | note | Standard / Specification - TNZ M/6: 2019 - 4, PS - 7.2.8
1e6e13d0-5040-53d8-a28e-9351742ac8da | note | Verifying Document - IANZ Lab Reports
b5fef9e4-b133-5ca3-aebb-24d6529f7588 | note | Frequency - 10,000m3
0702d244-1f93-5b2d-8150-2e02e09d0069 | note | Activity - HP
656e0c67-8bf9-5da6-a7f0-979ef2070a8f | note | By - ENG
91706b27-4b16-5cc3-af8c-8bc6d225db80 | signoff | AUTHORITY HOLDPOINT
aa95eb07-07b0-5907-8ee6-62cec7a8e155 | checkpoint | 16.08.02 - Sealing Chip - Production Property Test Sampling
59d0648b-965c-593d-8c54-ee1f33d05fdf | note | Acceptance / Conformance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6
0778486d-802b-5642-b787-54b28b889813 | note | Standard / Specification - TNZ M/6: 2019 - 5, PS - 7.2.8
71a87208-8ff3-548d-b433-5608c6ddf464 | note | Verifying Document - IANZ Lab Reports
7224cf73-2afe-5bed-822b-111c2b0a2550 | note | Frequency - 500m3
66a555cc-52d6-5318-9e0e-990e309fedc7 | note | Activity - HP
c9c0dd8c-5162-5885-93bc-dfc24d77576e | note | By - ENG
b8564601-7c3b-5437-9cd0-864739bac510 | signoff | AUTHORITY HOLDPOINT
63bb7db5-2824-50b2-a76c-2d37e5833c76 | checkpoint | 16.08.03 - Bitumen
a4923ef6-0f75-58cb-87e4-5fab4ca68408 | note | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01-A specification.
9407e156-6df1-5d9d-b127-2eea90e91ff0 | note | Standard / Specification - NZTA M10:2020 - 2.3.1, NZTA M01-A, PS - 7.2.8
54c4067b-6883-5adb-9b44-8a1a385fb181 | note | Verifying Document - IANZ Lab Reports
94a8dcbe-885f-567a-8ca3-44642a550665 | note | Frequency - Prior to use
2b3e5074-080a-5dd8-8c22-8959c9398141 | note | Activity - H
6de56487-3a96-5453-bffc-225d597963ff | note | By - PE
0cfb900b-774e-522d-8382-11f45ee6c95c | checkpoint | 16.08.04 - Sprayer E-2 certification
c1ed1d90-0a52-5602-b37e-1d951a9dedb8 | note | Acceptance / Conformance Criteria - E-2 certification and is up to date
750c4b85-0fdc-555e-9f7c-71e36e534785 | note | Standard / Specification - BCA E/2 Specification
8deada11-0ecf-5e45-8b19-e048947f9d87 | note | Verifying Document - Certificate
66742a5f-1fe3-5787-b935-c3b3e56445d7 | note | Frequency - Prior to use
d2acc12a-3ccd-5ded-91be-d3335f36ff2a | note | Activity - C
e315cf47-680d-58f6-a2a8-6ccd76b1ee3d | note | By - PE
b88cbcdc-0ec4-5cd6-adad-045aa1042702 | checkpoint | 16.08.05 - Sealing Design
9c9a2b3a-3972-5a7d-8895-4e4ec59e36cd | note | Acceptance / Conformance Criteria - Chip seal type, chip source, bitumen and/or emulsion grade, % kerosene, AGO and diluents, polymer (if applicable), sand report reports, hot application rate(s) including spray rates
85646657-8972-5bc1-a519-126ae5edaaba | note | Standard / Specification - PS 7.3.4.
17074ecd-fecd-57f9-92a3-b9081866afc3 | note | Verifying Document - Design Document
08a63143-714b-548f-927f-4814682e7088 | note | Frequency - Prior to use
c651762d-d5d2-5bda-8cb5-b9edd01dc852 | note | Activity - HP
66421952-0624-562d-af31-bae357bd0170 | note | By - ENG
ffa400a2-8ccb-5b46-8866-fcdb01e56bc0 | signoff | AUTHORITY HOLDPOINT
17d9b8eb-c728-5b6c-89b8-b5fe39466667 | checkpoint | 16.08.06 - Bitumen approval
ef41b259-4f32-5713-aaf4-8c949aa03238 | note | Acceptance / Conformance Criteria - Applications for approval shall contain the information required by NZTA Q05 clause 4 and the testing information required by Table 5.1
b9cb265a-75c9-5f3e-a319-bc00a27e782d | note | Standard / Specification - table 5.1 of NZTA M1:2022
8a9787cf-c73f-5593-b9e7-8034e115c3c4 | note | Verifying Document - Report
3494da08-2937-55d7-be14-8cb442e30733 | note | Frequency - Prior to use
1ace09e4-9546-575a-86ac-9231abcff70f | note | Activity - C
8adbad93-1366-5fbf-9710-0a3b9e97c223 | note | By - PE
f7b3c20d-9dec-50ad-9de5-6ba1c8224201 | checkpoint | 16.08.07 - Bitumen Quality
61d2add7-8f3f-529f-a4c6-2c9bdeeab619 | note | Acceptance / Conformance Criteria - All bitumens used for road pavements construction, supplied or blended by New Zealand-based bitumen blending facilities shall meet all the requirements of Table 6.1 or M01-A specification for the grade supplied.
3f47ea2d-af01-517a-b556-fa1a953cb7f2 | note | Standard / Specification - table 6.1 of NZTA M1:2022
3fa8115b-491d-5715-9759-01bb6995f189 | note | Verifying Document - Report
ae50f405-62a6-56c2-9693-183b399ada46 | note | Frequency - at least one test per grade supplied following delivery of a shipment into a bulk blending facility.
09b80dd6-dd9f-5329-a000-96a30cec77c1 | note | Activity - C
02ad4278-edce-5860-939c-4aa811a1de72 | note | By - PE
ae7c919c-800b-54bb-8ce4-d650657fb70e | section | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
2871bb8b-9370-54cd-81be-076ea005324e | checkpoint | 28.07.01 - Sealing Procedure
dba6e33f-1c8b-5569-9fda-1cd45f031f5a | note | Acceptance / Conformance Criteria - Sealing shall be carried out in accordance with TNZ or NZTA Specifications M/1, M/6, M/13, P/3, and Q/1.
a4a4f0c9-6e21-5f44-b95d-433b8ef1d6b7 | note | Standard / Specification - M/1, M/6, M/13, P/3, and Q/1.
5fc5d2df-ff01-5bd2-9ffb-10b00f3635f5 | note | Verifying Document - Methodology / Construction Pack
ed9de7e0-e62a-5439-b8a5-e510536d69f3 | note | Frequency - Prior to sealing
9f8e4f9f-c752-51d7-8bdb-f6a4a9129f2d | note | Activity - H
272e3268-25e7-5506-8897-5d0b5eb0b69e | note | By - PE
987da8d6-869a-52f8-82a6-64d9d019be20 | checkpoint | 28.07.02 - Sealing Inspection
e13f8aab-ed03-55f5-8e78-f98b839e92bf | note | Acceptance / Conformance Criteria - Before sealing and resealing. A pre-seal walkover with the Engineer to ensure that the surface is swept clean of loose aggregate, dust, dirt and other deleterious matter and the sweepings shall be removed to the satisfaction of the Engineer.
281850fc-cf15-536b-9f5f-324fb470bcf2 | note | Standard / Specification - PS - 2.2.16
0f39351b-d7e3-58fa-b711-5f9a347a6ac9 | note | Verifying Document - Hold Point Release
112d7768-c8f8-57bb-ad76-f1cf1b734677 | note | Frequency - Min 48h Notice
f44c5759-933f-5e05-a26f-09374ba9092f | note | Activity - HP
157cd6f5-9fae-5594-9f70-b18acffa1e96 | note | By - ENG
e8de70ad-25a8-50ee-a86e-ee732888188d | signoff | AUTHORITY HOLDPOINT
97f74a51-90b2-591d-9d46-97b788789ecc | checkpoint | 28.07.03 - Presealing Requirements
6bfc3f46-9301-5932-903b-18a175248417 | note | Acceptance / Conformance Criteria - Further to Clause 12 of NZTA B2, the degree of saturation of the basecourse prior to sealing shall be less than 60%.
e43ae18f-91be-5454-a63a-b509872abb85 | note | Standard / Specification - PS - 7.3.4
481fc55c-a247-558a-abe5-eef34f4994ac | note | Verifying Document - NDM Report
7e15df9c-a8d2-5ecc-adfc-72c8a3ed2d1b | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
2a6f4a94-045d-5ea9-8ab1-787a40b218e3 | note | Activity - HP
cc0fc382-4bdc-54b7-acb7-8d673f72ea57 | note | By - ENG
147512ba-bbe7-59c7-b55f-f9d4c0992a25 | signoff | AUTHORITY HOLDPOINT
600fb3f6-6266-58ed-9a50-762110113d0f | checkpoint | 28.07.04 - Adhesion Agents
714e7f71-3f88-5c80-b683-ebba7a9bc233 | note | Acceptance / Conformance Criteria - An adhesion agent approved and blended in accordance with the requirements of TNZ M/13 Specification for Adhesion Agents shall be incorporated in the sealing binder.
9fcef9d2-abf5-544d-966d-7797e5229986 | note | Standard / Specification - TNZ M13
5a1c992a-9d0e-54bb-b63c-2f47a5134230 | note | Verifying Document - Site Notes
9a6c9667-0e13-5c8f-bf79-8ba0f02bbb4f | note | Frequency - Prior to sealing
957e939a-0437-509b-9cd1-d721bd205a3a | note | Activity - R
9c44be23-e462-51a2-a526-12d7653abe12 | note | By - SE
7be6ce73-a318-5599-8798-e17614ccf289 | checkpoint | 28.07.05 - Post Seal Inspections
4de718da-c59f-5c40-8b3e-057ea10e2816 | note | Acceptance / Conformance Criteria - The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed.
0f87b092-2b0d-5b7e-a8a5-64a8d21119e3 | note | Standard / Specification - TNZ P3
0dce8072-911c-516a-9a63-42116abbb3b3 | note | Verifying Document - Engineers Acceptance
b8cb5257-62e6-54ed-bd7e-097972155e2d | note | Frequency - Prior to TM removal and after final sweeping
c39f97eb-0abf-51ec-84e4-bd67e0b31185 | note | Activity - HP
30538ae5-fdf0-507d-84f3-4cb464919235 | note | By - ENG
15d3cd20-59ee-55bf-8a8f-397ca3be1d64 | signoff | AUTHORITY HOLDPOINT
04954196-eee5-5f02-b55f-cc4acc6713ca | checkpoint | 28.07.06 - Bedding in Chip
73313444-c073-515b-88db-5885511e9ac4 | note | Acceptance / Conformance Criteria - If no traffic on site to bed in Chipseal, 3 days of constant rolling with PTR's and laden HCV's will be applied to bed in the Chipseal.
f4f59b8c-77bb-5856-a645-e4801f47a3e2 | note | Standard / Specification - PS - 7.3.4
11d7b076-b24b-566a-9534-0d19043973b9 | note | Verifying Document - Site Notes
f72333df-bde2-5b2d-aeeb-28a6b881847b | note | Frequency - Post Sealing
81931cdd-bf2c-5546-b7ee-38044ba55f72 | note | Activity - R
4ddec918-3ba6-5820-8ba0-fddba1a45d6f | note | By - SE
82dadf7e-bf2d-5092-b40b-132dd3b2a700 | checkpoint | 28.07.07 - Surplus Chip Removal
ef706484-67aa-5993-8ad5-a5d28c1bc76c | note | Acceptance / Conformance Criteria - If no traffic on site, removal of surplus chip will occur 2-3 days after rolling has been completed. If traffic on site, sweeping and removal of chip will be within 48hrs.
2d0127d6-6d7d-5ab8-b035-c9fb11052ce8 | note | Standard / Specification - TNZ P3
0019d5cd-a080-599a-bf39-6dbee283253c | note | Verifying Document - Site notes
2e4999ee-a3e4-5d3a-80ba-71327225d785 | note | Frequency - 24 hours of completion of any section of seal.
7c70c37b-7cdb-5548-8118-d8554ac64740 | note | Activity - R
777fa846-33d2-508b-b217-ca42693a2721 | note | By - SE
387048ba-8198-5c54-a002-cb9830e7474f | checkpoint | 28.07.08 - Chipseal Repairs
01937e39-1bfb-59ba-95cf-cfd96da7518d | note | Acceptance / Conformance Criteria - The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used
42158fc7-a86e-52a8-9201-74679aeb85d9 | note | Standard / Specification - TNZ P3
0bf8e279-9ac8-50a4-a204-62abf8cf26b6 | note | Verifying Document - Approved repair Methodology
ee3b471d-6939-5602-9644-fd38c86c7090 | note | Frequency - Prior to repairs
c0d25fdd-a140-5c55-b79c-71845879df7e | note | Activity - HP
0eda0423-5ccc-58ca-9b86-55421513367d | note | By - ENG
6eec2a1c-2298-5d1c-bfaa-7f4d2470f385 | signoff | AUTHORITY HOLDPOINT
5a5a3ab7-b98b-515e-8829-c6b77dcde4a6 | checkpoint | 28.07.09 - Weather
2b32c452-707f-5c90-8adf-e5750f1e15d6 | note | Acceptance / Conformance Criteria - Ensure that weather is suitable prior to spraying & pavement temperature checked. Pavement surface temperature ≥ 10C.
8859ee9a-271b-54c7-9124-9a3ab5113dfa | note | Standard / Specification - Requested by BBO
c9d1dee2-1f09-54e4-9743-1ace0a24604f | note | Verifying Document - Site Notes
6195f572-a5aa-5e68-b3d2-b075afb7b1af | note | Frequency - Prior to sealing
c0d4ec4c-7ad4-5001-8a51-1a76af47a494 | note | Activity - C
ff877007-8fb3-5893-a34e-f93cbf8806f1 | note | By - PE
c52674b3-5735-530c-a4c6-a6fbb45598fc | checkpoint | 28.07.10 - Protect Road Furniture
33905c35-66dc-5422-bca0-d10eba9003dd | note | Acceptance / Conformance Criteria - Paper cover any concrete that could get sprayed by bitumen such as kerbs and barriers
813f33b5-0cc5-54d5-bae0-6d8c6db63a43 | note | Standard / Specification - NZTA (2005) Chip sealing in New Zealand – 11.2.5.
1ae76e23-a4e2-5798-9c4e-a7d3daab8da7 | note | Verifying Document - Site Notes
02b452e3-3c94-547a-925b-3721bb9b11d9 | note | Frequency - Prior to sealing
ae6f69cf-c324-5cca-980e-1cc39acec6a2 | note | Activity - C
38846de8-a4de-51fc-8ce9-b2da71097d02 | note | By - PE
efc43278-19a3-56ee-b7ee-7febad520026 | checkpoint | 28.07.11 - Joins, Overlaps & Hand Spraying
5b9230a4-10bd-582c-bdd1-7427ce9045f6 | note | Acceptance / Conformance Criteria - Set up Spray Plan ensuring joins, overlaps and hand spraying is kept to a minimum; joins are not in wheel paths and overlaps are appropriate for curves, channels, straights
ef6da712-6974-5b5f-9560-3774b85e7112 | note | Standard / Specification - NZTA (2005) Chip sealing in New Zealand – Section 11
ac3922fc-604e-5bf5-a54c-858085c3c2f0 | note | Verifying Document - Site Notes
380f76ed-c2ca-5f93-8d62-d09c60583e4a | note | Frequency - Prior to sealing
3cd1d841-702e-556f-8455-3c4a6a081375 | note | Activity - C
a6f72d9f-ead0-5257-bb80-bd4acd5db742 | note | By - PE
e4115331-b361-565b-8e30-16b24b56d977 | checkpoint | 28.07.12 - Binder Temperature
0369770c-20bf-5e77-9cbc-4c9b666ce9af | note | Acceptance / Conformance Criteria - Temp. appropriate to base binder and additives +/- 10 degrees. Daily records
dd4e915f-62e4-5296-9b92-4a7572e088ae | note | Standard / Specification - NZTA (2005) Chip sealing in New Zealand – Section 11
f9948422-218b-57c0-a169-db3d459da9f7 | note | Verifying Document - Site Notes
e2481c47-962d-5dd4-a274-5239383c5218 | note | Frequency - Prior to sealing
e514c9ce-b115-5273-afd5-6ccc70480e1b | note | Activity - C
9d75c0b4-1a1b-5a7c-ae77-8edd53c6ae5e | note | By - PE
9dd523a7-748d-5edb-8e82-5cb13e3876a4 | checkpoint | 28.07.13 - Binder Application Rates
16b8e348-6a57-51aa-9757-4e828599a2c8 | note | Acceptance / Conformance Criteria - Confirm spray rate is correct by comparing actual spray rate to that calculated. Note error in measurement increases as area reduces. Within 0.1l/m² from target on spray run.
8fe8f093-73ea-5fc8-bb93-56349251e1e6 | note | Standard / Specification - Requested by BBO
68c9a18f-0b99-505a-a999-e43d898af2e0 | note | Verifying Document - Site Notes
a2d0ac60-2a79-540d-b9d4-cf395a3e735b | note | Frequency - Daily
89d74fa4-a686-5c5f-b459-13ce3afb2eae | note | Activity - C
f18395c8-2757-5cd9-ad6b-67b6412136dc | note | By - PE
4c005acc-c507-5b7f-88f6-0f990950d26f | checkpoint | 28.07.14 - Chip Application Rate
cebefc05-edac-519a-a52d-ba7f6e15b3c1 | note | Acceptance / Conformance Criteria - Monitor chip spread rate and compared to target, record volume of chip used
134a9b0d-32ef-515d-b97f-4f8762d20b07 | note | Standard / Specification - NZTA (2005) Chip sealing in New Zealand – Section 11.3.7
60861daf-849e-59b6-8747-c19ed36c06b1 | note | Verifying Document - Site Notes
0784a178-482e-5ee7-ba3c-8a3d13346758 | note | Frequency - Daily
1d6ed067-6108-5e8e-87de-b6d4278e8d60 | note | Activity - C
39a55291-edb7-56fb-8bea-114c65df0b67 | note | By - PE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
2e394091-a373-434d-8881-949a1e03a723 | checklist | ITP - Pavement & Surfacing - SMA10 - Asphalt - Rev A | itp | ITP - Pavement & Surfacing - SMA10 - Asphalt
3554e27f-fe8e-470f-83de-cd347d583535 | section | SECTION 01 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
3a1ec2ba-d4a7-4fa7-8015-0adcffd843d9 | checkpoint | 01.01.01 - Coarse Aggregate - Property Tests and Sampling
a90fca7c-b8c9-540f-9142-ebbe374529f9 | note | Acceptance / Conformance Criteria - The Coarse Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Weathering Quality Index, Crushing Resistance, Broken Faces, and Particle Size Distribution
37ebd8dc-79b6-5e87-98ea-d7905439903a | note | Standard / Specification - NZTA M10:2020 - 2
67f02bc9-db8a-5839-a909-bd531993614d | note | Verifying Document - IANZ Lab Reports
6dc6df90-9a51-5b1e-af68-15412d039af8 | note | Frequency - 1 Test per source of the coarse aggregate. Additional samples if source is changed
bfa43ac2-73a8-551f-84d7-8f40dc48efc3 | note | Verification Activity: Activity - H
02bc178d-0dd2-5046-9a0d-e7dffa9b271a | note | Verification Activity: By - PE
7082d9b1-46d1-46bb-b367-56ee6a69db5c | checkpoint | 01.01.02 - Fine Aggregate - Property Tests and Sampling
1d1bab25-84c4-58bb-bdf4-a15ba12d40a2 | note | Acceptance / Conformance Criteria - The Fine Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Sand Equivalent, and Particle Size Distribution
a49853dd-44cd-5e22-ae75-5c6cfe817e3e | note | Standard / Specification - NZTA M10:2020 - 2
152cdeee-2089-5d65-855e-16f5e7df6cb5 | note | Verifying Document - IANZ Lab Reports
d4768ba1-b223-5bdd-8820-046d42171bad | note | Frequency - 1 test on the parent source
88d94a8a-0a45-568b-8ad9-cf40372b92ce | note | Verification Activity: Activity - H
7b8d407c-1550-51b7-8fa6-eced37b07027 | note | Verification Activity: By - PE
1d0f1f2e-b1b4-4b75-aa0e-71463e028663 | checkpoint | 01.01.03 - Coarse Aggregate
e4149b6d-67ff-5e83-92c5-f73d15435fcd | note | Acceptance / Conformance Criteria - Coarse aggregate is comprised of particles that are retained on the 4.75 mm sieve. Coarse aggregate shall comply with Table 2.1 except that the Engineer can approve the use of non-complying materials from sources of proven performance.
5232af78-f0f5-5fec-b729-44b02c730562 | note | Standard / Specification - NZTA M10:2020 - 2
39f11da3-07c2-52c7-aa51-06861ad6ba9d | note | Verifying Document - IANZ Lab Reports
978233b7-208e-5312-b57c-65cfe790c30f | note | Frequency - Prior to use as per BPG05 - 15
16b25418-e137-5776-b710-7945dbe71e9a | note | Verification Activity: Activity - H
e27aced3-6753-5212-a011-2a0b6a40d41c | note | Verification Activity: By - PE
d325cef3-849e-434e-9992-1e5b9ffa8bf7 | checkpoint | 01.01.04 - Fine Aggregate
1154a83b-e5be-57ae-9b98-abb92eef1627 | note | Acceptance / Conformance Criteria - Fine aggregate shall consist of crushed rock particles finer than the 4.75 mm sieve and manufactured from a source complying with the requirements of Table 2.2.
95c907fd-a6ab-50fd-8328-32c6a1dfc707 | note | Standard / Specification - NZTA M10:2020 - 2
4da642a8-dca2-5eb8-b85e-d6f05f9cc3fd | note | Verifying Document - IANZ Lab Reports
ec9e49d9-bad3-5918-959e-e79386342c02 | note | Frequency - Prior to use as per BPG05 - 15
0c138036-9991-5e46-9411-efaae600f57f | note | Verification Activity: Activity - H
afe29805-1927-5f48-9304-5402d378ffb9 | note | Verification Activity: By - PE
4b24108b-ebc2-4040-a0bf-5d65f3e0a06b | checkpoint | 01.01.05 - Mineral Filler
ad9c30ad-3165-537c-85b7-15ed918222db | note | Acceptance / Conformance Criteria - Filler shall be consistent in mineral composition. It shall be dry, and free from lumps, clay, organic matter or other material deleterious to asphalt.
12afbc5d-9de2-5869-9c29-660521976919 | note | Standard / Specification - NZTA M10:2020 - 2
30918093-3f89-5261-a7e5-dc60fd467a93 | note | Verifying Document - IANZ Lab Reports
58c40df5-4f9a-5a0b-a78e-ab9dab7d0aa3 | note | Frequency - Prior to use
9bd0f546-3c8a-5c69-ad69-e6ef36855c35 | note | Verification Activity: Activity - H
b42f86f6-da75-517f-8fd2-659ba99250f1 | note | Verification Activity: By - PE
fd6b3e07-0394-4520-b5b4-24e44318e67b | checkpoint | 01.01.06 - Bitumen
54e2d8f0-636f-5a5e-b4c1-6a20eadadac6 | note | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01-A specification.
25fe2c10-1a92-5eed-9319-1e8231298ea5 | note | Standard / Specification - NZTA M01-A, PS - 7.2.7
b8c5bb27-4cc8-5a65-84cc-8db01dac1b6c | note | Verifying Document - IANZ Lab Reports
93764f83-971f-560a-9ffe-e27a59c01c7e | note | Frequency - 1 test per 25,000 litres or part of
4f8e6dff-227d-5dfd-b5bf-51dc3c6b005c | note | Verification Activity: Activity - H
73e29faf-d4f4-56bf-b4ff-4c7cb58ebd4c | note | Verification Activity: By - PE
6ae1b940-a02e-4fd2-a5ff-247a9259072e | checkpoint | 01.01.07 - Aggregate Wet Strength
b87087df-8ac0-5482-bec4-f131a0485e5d | note | Acceptance / Conformance Criteria - When tested in accordance with AS 2758 Part 5 the aggregate wet strength shall be not less than 100kN. The wet/dry strength variation shall not exceed 30%.
00399b4a-55af-589d-a136-15edf7567cc6 | note | Standard / Specification - NZTA M10:2020 - 2
97633d4f-31ab-5c21-9eb5-1b05c3800653 | note | Verifying Document - IANZ Lab Reports
7de5ad15-b88f-5432-add4-84fb211a32b5 | note | Frequency - Prior to use
2c0cd825-6f18-5d37-9d88-089ffa854079 | note | Verification Activity: Activity - H
8379776a-969e-58d6-87a6-5ef4155a863f | note | Verification Activity: By - PE
42418b3a-9b9a-44af-b97e-66c2b8ae5e95 | checkpoint | 01.01.08 - Wheel tracking Testing
e43ccbba-1cb7-5235-988c-310c9fc03c7d | note | Acceptance / Conformance Criteria - The acceptance criteria for wheel tracking shall be a tracking depth of no more than 3.0mm after 10,000 passes, in respect to AC20 (Type # 2 pavements). All other asphalt layers, including SMA10 and AC10, shall apply the 6mm maximum tracking depth as per NZTA M/10.
07fa3d8e-8e24-5bf1-98e5-cdc861f1d324 | note | Standard / Specification - NZTA M10:2020 - 3
7b9484e8-16a0-5d6f-aace-a541554f6a46 | note | Verifying Document - IANZ Lab Reports
825a0ead-3ac1-575e-8860-d868e2db4b18 | note | Frequency - Prior to use
3748660b-8533-5a15-b596-0ca0f1d290fb | note | Verification Activity: Activity - H
cfc4dc42-a871-5e8f-9ed5-e1d45b575844 | note | Verification Activity: By - PE
ef4d60cb-5cff-42e0-bd1c-46f967a2f868 | checkpoint | 01.01.09 - SMA PSV Requirements - Pavement Type 2
d4e0dba9-0ebe-5a3f-b98f-d7da73595d57 | note | Acceptance / Conformance Criteria - A minimum of 85% by mass of the coarse aggregate fraction (fraction retained on the 4.75 mm sieve) of the SMA surfacing shall meet the minimum PSV requirements of 63 for Pavement Type 2
d22141db-3523-504f-9b34-6ae51c2c7337 | note | Standard / Specification - NZTA M10:2020 - 3
cf8d994d-b2b9-5bc0-b0e5-2d97d4e35ede | note | Verifying Document - IANZ Lab Reports
e81e0620-7d4a-5435-8188-8c9a2d89f5df | note | Frequency - Prior to use
69eb6f86-8ff5-55d9-a3a9-2145a49e38b7 | note | Verification Activity: Activity - H
59e7a626-9ff6-5241-81ef-0ed46c2acdf2 | note | Verification Activity: By - PE
2e2a2808-c611-4792-8767-3a743f4f14e8 | checkpoint | 01.01.10 - SMA PSV Requirements - Pavement Type 1
fea4f385-5eb4-5660-a7b7-3266a0ddf5b6 | note | Acceptance / Conformance Criteria - A minimum of 85% by mass of the coarse aggregate fraction (fraction retained on the 4.75 mm sieve) of the SMA surfacing shall meet the minimum PSV requirements of 46 for Pavement Type 1
b5d094a6-b100-5d47-b425-5ecb257fdc38 | note | Standard / Specification - NZTA M10:2020 - 3
0b47fe92-7a25-51ea-9348-09a816c37831 | note | Verifying Document - IANZ Lab Reports
6df5449e-ac3f-5916-8806-0d91e4e8659f | note | Frequency - Prior to use
e191962c-beb2-5963-8e07-4c79b1e6dc70 | note | Verification Activity: Activity - H
54838607-08b7-5b51-9c36-c264abf75fd7 | note | Verification Activity: By - PE
1e36de77-8cc7-434f-a37e-b299f31fbc55 | checkpoint | 01.01.11 - SMA PSV Requirements - Pavement Type 2
d8b3ef75-3e34-530b-986f-713c455034bd | note | Acceptance / Conformance Criteria - The minimum PSV for SMA surfacing on Pavement Type 2 (intersections and approaches) shall be 63.
8d653102-bd97-5f46-a69c-505ebd903025 | note | Standard / Specification - NZTA M10:2020 - 3
4527d090-6e5b-55e1-9bd3-ab24fa428eda | note | Verifying Document - IANZ Lab Reports
5957b1d9-7a31-54de-b98a-47f4e6715284 | note | Frequency - Prior to use
3c3e9173-2ed7-5b66-9af1-b70854295588 | note | Verification Activity: Activity - H
2ac4ae38-055d-56cc-ac22-b0113640466a | note | Verification Activity: By - PE
7468bf26-a073-467d-bbbf-95e8337ce54c | checkpoint | 01.02.01 - Mix Design / Job Mix Formula
3470b481-b000-56f7-a883-82626f30ab13 | note | Acceptance / Conformance Criteria - The Contractor shall supply details of the mix designs together with the Job Mix Formula (JMF) and the Marshall or gyratory compaction properties as required to the Engineer for approval. No works shall commence until the JMF of each mixture to be used has been accepted by the Engineer.
c576d04e-24b5-58b2-8298-0665253026e3 | note | Standard / Specification - NZTA M10:2020 - 3
b50d0e30-3c77-506a-a0e2-7ce30afc32bd | note | Verifying Document - Approved Mix Design
86c6e54f-eca8-54c5-a998-1f6c816b456e | note | Frequency - 3 tests per mix
53a5abfd-00b3-5d6c-8582-f3f59f678a2d | note | Verification Activity: Activity - HP
f0129530-a9e2-53eb-89fe-06dc804a31a4 | note | Verification Activity: By - ENG
4f1c7a86-e792-41d0-b974-0447fcb5dbb4 | signoff | AUTHORITY HOLDPOINT
5dff12c0-d963-4ead-bf13-f2aab36e1c33 | section | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
ef9ae914-a6ed-4c52-8da4-416720a3a0b1 | checkpoint | 02.01.01 - Paving Plan
ecd375a9-b078-574e-be46-4351b712694d | note | Acceptance / Conformance Criteria - The Contractor shall prepare and submit a paving plan to the Engineer for approval not less than 7 days prior to construction of the asphalt pavement.
130575f1-0710-53d0-9161-d3a8b52d9d28 | note | Standard / Specification - NZTA M10:2020 - 8, 9
80959263-7242-5f33-87ef-702bb39150be | note | Verifying Document - Construction Work Pack
dd3f86ec-2e9a-5c72-8c46-b73e212cb41d | note | Frequency - 7 days prior to construction of the asphalt pavement.
9924835a-140e-5170-adbf-f61f685ff241 | note | Verification Activity: Activity - HP
06246360-fd1e-5efa-ab00-cb4eef752129 | note | Verification Activity: By - ENG
382fa79e-c0d9-4f0e-aa24-6852f00e69e0 | signoff | AUTHORITY HOLDPOINT
568a3667-3baf-4968-a4b7-61c0c94a7365 | checkpoint | 02.01.02 - Sealing Inspection
db2a8fe4-8ce9-5ca0-9da4-12c23046cb62 | note | Acceptance / Conformance Criteria - Before sealing and resealing.
15951771-612d-567d-aea8-b04e56da0f42 | note | Standard / Specification - NZTA M10:2020 - 8, 9
1a769ae1-bff8-558b-aab8-6738cf3eeee0 | note | Verifying Document - Hold Point Release
8c17af7a-a939-51f8-b07b-96390289c810 | note | Frequency - Min 48h Notice
4decd51c-b7f9-58cc-b2b2-52f33894dfce | note | Verification Activity: Activity - HP
ec0304c9-8f45-5040-a696-0639cbc9460a | note | Verification Activity: By - ENG
ee86f5cd-b9bd-4f91-9de6-a2602b96dcc8 | signoff | AUTHORITY HOLDPOINT
52fcb7c8-d995-49b2-a357-52ec86cd1eee | checkpoint | 02.01.03 - Weather during Paving
38288192-f7c9-56d0-8385-77fa4aec6bb9 | note | Acceptance / Conformance Criteria - Asphaltic concrete shall not be placed when it is raining or on a wet surface. Dense-graded asphalt shall not be placed on a surface with a temperature of less than 10°C.
0c6ad51a-dd24-5002-ad47-082fd8df5653 | note | Standard / Specification - NZTA M10:2020 - 8, 9
1cf65ce9-813a-582d-85ba-d25cf5873c0c | note | Verifying Document - Weather / Site Notes
4de221fa-6852-54e7-b2b2-d06b94bf2cb6 | note | Frequency - Each day prior to placement
8f2f2259-a672-582e-a3d4-3cb61672c998 | note | Verification Activity: Activity - H
5cc3afb4-a68d-5535-a8dc-efdd0136fd9b | note | Verification Activity: By - PE
28971b91-f02a-4167-8fef-20a36d1a80d7 | checkpoint | 02.01.04 - Asphaltic Prep
9a5bee31-3752-5246-ab14-ad99c0f36290 | note | Acceptance / Conformance Criteria - Prior to paving asphaltic concrete, the area to be paved shall be dry and free from loose material or dirt. If swept, all sweepings shall be collected and removed from site. Barriers, kerbs and other adjacent surfaces shall be adequately protected against over-sprayed bitumen or vehicle damage
54ce811c-22ad-53d6-b9eb-ab4bde1b1487 | note | Standard / Specification - NZTA M10:2020 - 8, 9
ab228965-83a2-5d23-88da-9511e9e9d6a3 | note | Verifying Document - Site Notes
e7891149-7211-51db-8ec2-da63d79fef22 | note | Frequency - Prior to paving asphaltic concrete
9d080623-53a0-5128-bd2b-a10ada460cbb | note | Verification Activity: Activity - H
a45b11e1-6742-58e4-afa3-614d95589a1d | note | Verification Activity: By - PE
5732c6bf-cba3-441f-87d2-4ab1c54525ad | checkpoint | 02.01.05 - Asphalt Production Conformance
5e8d2cee-c6d6-5b7e-80f4-4ab2fd61020a | note | Acceptance / Conformance Criteria - Conforming Grading and Binder content by mass
76661cd6-f505-5956-aa57-a1b1c63aa66d | note | Standard / Specification - NZTA M10:2020 - 8, 9
db494b14-7c6d-5201-b253-4cfd152e8299 | note | Verifying Document - Test Results
c40226a1-66f0-5c70-903d-f4ceaa367a73 | note | Frequency - 1 per 200T, Min 3 tests per mix
ad6eb1f5-7e6e-5833-b945-cf0358843f50 | note | Verification Activity: Activity - I
54453965-f4c3-53ed-a00f-a4fd53ec0382 | note | Verification Activity: By - PE
ecb71c98-8b62-4059-abb7-902ebfe8b575 | checkpoint | 02.01.06 - Asphalt Production Conformance -Volumetrics
ebe03d2f-0f4c-5fb0-ac16-0b784e8205e1 | note | Acceptance / Conformance Criteria - Conforming Volumetric testing. Refer clause 5.2 and table 5.2 for frequency and tolerances
c743ae49-c6a3-5337-b685-3ba7f0630991 | note | Standard / Specification - NZTA M10:2020 - Table 3.1, 5.1 & 5.2
f6c8292d-7636-5d30-8a06-14dbb33263a8 | note | Verifying Document - Test Results
d347355e-9b65-5100-a860-7b7bfc7754d8 | note | Frequency - 1 per 600T
2ae10a8a-8958-5925-8848-dad1c9babbd3 | note | Verification Activity: Activity - I
f3934beb-9918-57e8-bb5c-59eb359b47c1 | note | Verification Activity: By - PE
163d569f-60a5-4a0c-8e2f-3baa1c037e3b | checkpoint | 02.01.07 - Mat Density
0853c466-b968-5cb5-ab41-75262d615820 | note | Acceptance / Conformance Criteria - For mixes with a nominal maximum aggregate size 14mm or less cores shall be 100 mm nominal diameter or greater. For mixes coarser than 14mm cores shall be nominally 150mm diameter. For layer thicknesses 40mm or less the core diameter shall be nominally 100mm.
8db410d2-f871-5f4f-9702-fff93b48de6e | note | Standard / Specification - ASTM D5361, NZTA M10:2020 - 9
687d2570-19bf-5e57-a1d2-e6ec263755b8 | note | Verifying Document - Cores
4ae73240-fca8-54a9-bda1-ff3fccc9216a | note | Frequency - min 8 per lot (day) (1 for every 300 m²)
9355ffbf-6d2d-5110-beb9-75ca7fdd3101 | note | Verification Activity: Activity - R
66f3e011-a273-50ba-9de7-14dce3287905 | note | Verification Activity: By - PE
c0a639de-23a7-4da2-99f7-1fa8c6b92935 | checkpoint | 02.01.08 - Joint Density
2c48d56c-8ff9-5980-b757-fdf4f3b34902 | note | Acceptance / Conformance Criteria - For mixes with a nominal maximum aggregate size 14mm or less cores shall be 100 mm nominal diameter or greater. For mixes coarser than 14mm cores shall be nominally 150mm diameter. For layer thicknesses 40mm or less the core diameter shall be nominally 100mm.
a6ffcbf2-df6f-5b42-8199-5f9937068c44 | note | Standard / Specification - NZTA M10:2020 - 9
fb5446c7-2769-589c-8f77-a54f0b63d283 | note | Verifying Document - Cores
cbbc434b-51a8-5925-9077-90eb28ac4077 | note | Frequency - min 3 per lot (day) (1 per 100 m of joint)
e7bffd2b-14e1-5529-8c6b-d9d6493d4d27 | note | Verification Activity: Activity - R
61014609-0b48-5c79-bf94-dffbff1ceb63 | note | Verification Activity: By - PE
f2a5d7b2-cd79-4c24-b23a-d42137bd9078 | checkpoint | 02.01.09 - Core Thickness
a2175765-ec3b-5f32-b8cd-dd5d65801b29 | note | Acceptance / Conformance Criteria - The nominal thicnkess for the set or lot of cores shall be equal to or greater than the specified nominal thickness.
86e7cf1a-afe7-5c10-8b11-76de16df2709 | note | Standard / Specification - NZTA M10:2020 - 9
04e5d238-197c-52f5-a273-37ff05e42d25 | note | Verifying Document - Lab Report
5f10ea85-c678-521a-a76c-3279b9b92c70 | note | Frequency - Mat - min 8 per lot (day) (1 for every 300 m²) Joints - min 3 per lot (1 for every 100m)
b2fa108b-1f57-527d-bb0e-d89364d62ec0 | note | Verification Activity: Activity - R
59f5d0d7-9d32-5390-9d16-427b6314334e | note | Verification Activity: By - SE
27610580-8542-4ab8-ad21-bda61e6c57be | checkpoint | 02.01.10 - Mat Density
b3bb8821-8e7c-5b74-a427-0b986aea1461 | note | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be cut from the pavement at a rate of one core for every 300 m² with a minimum of eight cores representing each lot
2988f854-cf29-5cb7-9041-c8decfb8de44 | note | Standard / Specification - NZTA M10:2020 - 9
740fdd4b-73fc-5d89-8ad5-a9683623e985 | note | Verifying Document - Cores
5d0e53b7-5aea-5375-b928-7a364fc22f44 | note | Frequency - min 8 per lot (day) (1 for every 300 m²)
e5fc2d16-886f-5d6d-977c-cdc8308b5d24 | note | Verification Activity: Activity - R
7aa0fedc-1788-5584-9801-b01af727fcac | note | Verification Activity: By - PE
a8454d41-7ddb-46d7-b867-0355860c4c25 | checkpoint | 02.01.11 - Joint Density
7180f026-a3c0-505c-a524-c3b67f768b64 | note | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be taken from randomly located distances along joints at the rate of one per 100 m of joint with a minimum of three representing each lot
af713bcd-2f85-5fbe-8979-8a2416c53300 | note | Standard / Specification - NZTA M10:2020 - 9
c0d375a1-cd3a-50c4-bfbc-b6e04b856aa5 | note | Verifying Document - Cores
1f827771-c844-5d88-bd14-131408901f94 | note | Frequency - min 3 per lot (day) (1 per 100 m of joint)
bc62c015-97df-503c-935b-ff4e5198ab40 | note | Verification Activity: Activity - R
50b12689-9a4a-5589-8413-dc114845ddd3 | note | Verification Activity: By - PE
0c6acf46-f4ba-4a8a-9721-a80345b26745 | checkpoint | 02.01.12 - Density Testing
ebdcc0d9-3390-5077-98c9-8180099e85e3 | note | Acceptance / Conformance Criteria - The upper and lower characteristic values of in-situ air voids for that lot shall comply within the maximum and minimum characteristic limits specified in Table 9.2
07edde9d-6ae5-5522-87fd-7c778c20d109 | note | Standard / Specification - NZTA M10:2020 - 9
1bd6d707-4807-53ba-a406-301411c926a8 | note | Verifying Document - Lab Report
f892d9b7-64f8-5806-b963-dee3e974e58a | note | Frequency - within 24 hours of them being cut from the pavement
1a00c115-24c9-5ef5-9645-5e6d313b7309 | note | Verification Activity: Activity - I
4aba39fd-40c2-54c0-968f-c47c3ef4d545 | note | Verification Activity: By - PE
9b03bbfa-2a2e-48ab-a4ea-54399978da0b | checkpoint | 02.01.13 - NDM Density
52eeac0a-7f69-5588-812b-343b20f41a9d | note | Acceptance / Conformance Criteria - NDMs are to be completed at the time of pacing to ensure compile when cores are taken
f3899422-bf2d-5a67-814b-58fb73ab71f8 | note | Standard / Specification - NZTA M10:2020 - 9
53468432-6c37-5759-9d00-01bd3795b315 | note | Verifying Document - IANZ Lab Report
ba14c261-d03b-57b0-99ed-0d56d680dfaf | note | Frequency - min 8 per lot (day)
bdc44445-7022-591f-a93f-da123f6cf57f | note | Verification Activity: Activity - I
8fc56545-2fca-5564-b537-c54b21d03a22 | note | Verification Activity: By - PE
a3c1f789-70ad-473d-9bc7-2d62c2e6c2ef | checkpoint | 02.01.14 - Transverse truth of the surface
0d549071-56d3-56da-ac25-d15d46d6ace3 | note | Acceptance / Conformance Criteria - The transverse truth of the surface shall be checked with a 3 m straight edge over the straight cross-fall portion of the cross-section for irregularities, which vary more than 5 mm under this straight edge.
77efb18d-8d5c-54d5-a4c0-fb24915f370d | note | Standard / Specification - NZTA M10:2020 - 9
6bd26b54-fa97-5238-b55d-018cfbe16791 | note | Verifying Document - Site Notes
5e69c3b7-674e-5647-a370-298ac82395e6 | note | Frequency - Post Seal
0b13631c-d30b-50a9-a8b0-5125fa9d6b3a | note | Verification Activity: Activity - I
ea9c0aec-d93d-59f7-bced-db5fb9deeca5 | note | Verification Activity: By - SE
6256763d-7dc5-4251-b2ea-485f424b6851 | checkpoint | 02.01.15 - Finished Pavement Level
b66fc6ce-64cc-59fb-ab8a-25a4d2950bd7 | note | Acceptance / Conformance Criteria - The level at the top of each layer of asphalt shall not differ from the specified level by more than 10 mm, except that where asphalt is placed against kerb and channel where it shall be flush with, or not more than 5 mm above, the lip of the channel. 2mm at Construction Joints (Bridge).
cdd4267a-fd3e-5deb-b263-46563c70fb5f | note | Standard / Specification - NZTA M10:2020 - 9
02cc5b0a-a8b0-5894-92fc-c531b8cc29d1 | note | Verifying Document - Survey
bc18fc38-9975-5c81-84f9-091bf2c55120 | note | Frequency - Continuous throughout construction
854c26f3-7be1-5185-a281-4311ab6a742a | note | Verification Activity: Activity - I
48dd19e3-6f85-5406-8744-380adc515665 | note | Verification Activity: By - SE
69a5b458-804c-4040-8e07-3c56de07a246 | checkpoint | 02.01.16 - Finished Pavement Alignment
1489a187-dae3-55a5-b99c-eaf25674ff53 | note | Acceptance / Conformance Criteria - The horizontal location of any point on the pavement shall not vary by more than ±50 mm from the design except where alignment with an existing pavement structure is necessary, when the new work shall be joined to the existing work or structure in a smooth manner.
63169882-c2c9-5328-b066-318bc356fad2 | note | Standard / Specification - NZTA M10:2020 - 9
5a69f426-4dd0-50f9-9c2e-5ff404620b4d | note | Verifying Document - Survey
ed50a7c6-ba59-53d8-b0c7-b04169c53973 | note | Frequency - Continuous throughout construction
13a937c4-06bc-5f69-9024-888bc857eb26 | note | Verification Activity: Activity - I
54fb955b-8e4f-56bd-b89d-2923e2946676 | note | Verification Activity: By - SE
8b5f6bfc-281f-4eeb-a5fa-4d8250c78a4b | checkpoint | 02.01.17 - Transverse joints
ec75a8c0-171f-54f9-801f-ef87887ebf06 | note | Acceptance / Conformance Criteria - Transverse joints shall be milled back to provide a square edge and bitumen shall be hand sprayed on the vertical face. Successive transverse joints shall be staggered by a minimum of 2.0m.
d1a1fb46-ff3c-55cb-89fa-82c62c6fd09a | note | Standard / Specification - NZTA M10:2020 - 9
fc798210-8e93-55e3-bb0d-b139817db4dc | note | Verifying Document - Site Records
2f164565-e735-5e9f-a4b7-d8fd71f71d49 | note | Frequency - Continuous throughout construction
353c4062-91bd-5851-9d3c-70e015cda24b | note | Verification Activity: Activity - I
d3995f1c-de94-5002-801a-f0aad7a16fbf | note | Verification Activity: By - PE
d6c015e1-d44b-472a-bf62-867b97ec4858 | checkpoint | 02.01.18 - Longitudinal joints
3cd9717c-eb5b-510d-97e2-b03a00c612de | note | Acceptance / Conformance Criteria - Longitudinal joints between successive layers of asphalt shall be offset by at least 150mm.
fd70f4b6-88ae-589e-ad34-aba39dc9d464 | note | Standard / Specification - NZTA M10:2020 - 9
dd99ed25-69f1-5850-8879-7e1cde8222e2 | note | Verifying Document - Site Records
42b73312-cb53-5e32-bf28-23c1dd4cad4d | note | Frequency - Continuous throughout construction
ec5b2d56-4567-5174-ad43-d1b4a72dd171 | note | Verification Activity: Activity - I
81cb0f43-89a3-5e63-906f-27fefe6f1a9c | note | Verification Activity: By - PE
bc1ce7d1-6768-4dde-8377-bc65a0940bb0 | checkpoint | 02.01.19 - Asphalt delivery temperature
5f64e58e-96a4-5f71-aba9-04d88e078b73 | note | Acceptance / Conformance Criteria - Asphalt paving should be carried out at temperatures between 121–149°C to ensure optimal workability and compaction. If the temperature falls below 120°C, the asphalt mixture becomes too stiff, leading to inadequate compaction and a compromised pavement structure. Proper temperature control during transportation and placement is essential to achieve a durable and long-lasting surface.
846848b5-b271-5d73-ab75-b68051bdb40a | note | Standard / Specification - TNZ M10 - 8
1f5bdde9-6224-5054-8980-83706d3ee08b | note | Verifying Document - Site Records
df92607a-e50d-53f2-8acf-0992e410a9c4 | note | Frequency - Continuous throughout construction
da7fde41-76c0-5536-8091-a025c9ed1ec3 | note | Verification Activity: Activity - I
e57cb8aa-30d2-57cf-850d-f26adfb38056 | note | Verification Activity: By - QA
af8b66d8-79db-48cf-a702-42d7d890c0ac | checkpoint | 02.01.20 - Depth Checks - Loose during paving asphalt material
387d590e-74be-5711-93e6-21416788fb33 | note | Acceptance / Conformance Criteria - Best Practice technique. Allowance for depth is dependent on asphalt type and compacted effort required to meet Specification. Normal practice is to add 20% of the nominal depth and use a dip stick to visually check behind the paver.
6a897b9a-3264-5b30-910e-f45d8d123bfd | note | Standard / Specification - Industry Best Practice
16bc3052-00c8-53ed-9b44-01ba8f0fb3d8 | note | Verifying Document - Site Records
581496cf-f01c-5e2f-b053-1fe3ca46bb42 | note | Frequency - Continuous throughout construction
ca5c24ac-6108-55f5-9cb0-2273b13a6381 | note | Verification Activity: Activity - I
0a536b40-744f-56f8-bf87-de25c1abbbd5 | note | Verification Activity: By - SE
8f3fe467-78a0-402b-bd2f-e2b2a706eded | checkpoint | 02.01.21 - Plateau Testing
ee91fceb-a509-5040-8b3f-c5b7040488c5 | note | Acceptance / Conformance Criteria - One test at the start of the project. Typically a target density of 93-97% of the maximum theoretical density.
6f9828b6-0e23-5e46-936e-69ced67bf7e8 | note | Standard / Specification - Industry Best Practice
e644e6d5-8b21-598f-b8f1-627543d80772 | note | Verifying Document - Lab Report
c45a1e45-f182-5937-8387-5df55efe93f8 | note | Frequency - 1 test at the commencement of the project.
b6bcc037-d749-5f60-b98c-19eebfe909bc | note | Verification Activity: Activity - M
954b9267-427f-5175-99ef-938a52bd5107 | note | Verification Activity: By - Spec
2f97151d-e773-45c2-a465-a8cde6c80547 | checkpoint | 02.01.22 - Backfilling Core Holes
e5e1b955-a828-5ca7-856f-75f408f3aef9 | note | Acceptance / Conformance Criteria - Core holes filled with material similar in composition to the surrounding asphalt layer. Well compacted and finished flush with the surrounding pavement.
f5883722-d5d6-50ba-8456-4d13724e6e8d | note | Standard / Specification - NZTA M10:2020
4e76ce7f-7c22-52a3-a33a-fea89008a5d0 | note | Verifying Document - Site Records
1e836897-cc4b-5e8d-b06c-b4f1b9d675e5 | note | Frequency - As soon as possible after core extraction
062e60ce-705a-54d9-823d-0e60a70fd8d9 | note | Verification Activity: Activity - O
0508ddef-414d-5bea-a0b3-a28653ce8a62 | note | Verification Activity: By - SE
42b6ae34-97f5-45fb-bad5-0e253829e18e | checkpoint | 28.09.01 - NAASRA
35c8b56b-86ca-5ffd-a838-5b815d5fd84d | note | Acceptance / Conformance Criteria - On completion of surfacing and placement of pavement markings and raised pavement markers Contractor shall carry out surface roughness measurements in accordance with the Transport Agency’s Technical Memorandum TM7003 (TM7003). The criteria for acceptance shall be in accordance with Section 2 of the Transport Agency’s TM7003 and in addition no 20m reading in any lane shall exceed 100 NAASRA counts/km.
c5d33995-dfab-5102-9845-4cfbf75db068 | note | Standard / Specification - PS 21.4.1
e878322d-0e01-55f3-b516-686c19ccafcd | note | Verifying Document - Test Results
acd5cace-ae43-5429-ad50-a52641c286f4 | note | Frequency - Each lane. 1 test on surfacing post construction and again at end of defects notification period
628bc94f-f94b-586f-96bf-eef20062a787 | note | Verification Activity: Activity - I
43131c44-2918-5cd2-ba44-fb4b0c0af7f0 | note | Verification Activity: By - PE
765cb99e-6af9-48e9-a650-779e0e92ae58 | checkpoint | 28.09.03 - Texture
f611973f-7ad1-51af-853f-37c5481fe055 | note | Acceptance / Conformance Criteria - Texture shall be measured in accordance with the TNZ T/3 Specification or with the Mini Texture Meter. The measured texture shall be converted to MPD using the following equations.
6f7a7722-3415-5de8-8653-9b75a08988c2 | note | Standard / Specification - PS 21.5.1
b0874ffb-a5a2-5be6-a5f5-d8ceabd62f98 | note | Verifying Document - Test Results
5c715b05-bab8-5e19-bdb0-f46ab60c1cec | note | Frequency - Upon completion of the asphalt surfacing and at the end of the Defects Notification Period.
faac885d-4616-5af7-9c84-50f31f3ed20e | note | Verification Activity: Activity - I
a07e7121-809a-5c88-9e1a-3ae6b2b19348 | note | Verification Activity: By - PE
49aac8a9-9779-4abe-954d-ecea3247a7c8 | section | SECTION 39 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
bacbd34b-7beb-4195-9d25-3384c1676333 | checkpoint | 39.02.02 - Survey Records
5c054d61-9770-5925-8395-ff563fa12504 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
a39fc029-12e3-5b43-9eed-065a1d5167f2 | note | Standard / Specification - Downer
a989c075-dd5c-5a8f-a409-a6517484cf2c | note | Verifying Document - Records
1aad767e-11ea-57a2-a20f-4c3d2515fa86 | note | Frequency - Post construction
e2ec4308-b91e-5844-9b80-1820e034df5e | note | Verification Activity: Activity - H
8c68d817-3f39-5ec8-83ba-8c3c58d528dd | note | Verification Activity: By - SV
3a74cab6-4c9a-4168-b161-0557c03c634c | checkpoint | 39.02.03 - Redline Drawings
a5141be3-5b40-56d2-92e6-3c0bcf512626 | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
cb39515d-170c-5c62-a69e-42c8c787d042 | note | Standard / Specification - Downer
d13d2307-d890-570d-b66e-b34c39f91f0e | note | Verifying Document - Redlines
2b33a455-5318-5db2-818d-60e2233736d7 | note | Frequency - Post construction
6a7679e2-8bd7-50f4-b990-a4b3aa3214a5 | note | Verification Activity: Activity - H
c98b38ec-1d0a-5533-a7f8-de968801810e | note | Verification Activity: By - PE
a87042f8-add6-4398-9e50-e7f92ac3b8b4 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
67ece742-eb7f-5453-8c51-5c6851078550 | textbox | Contractor's Rep Name:
987cd25e-e5a2-58c3-836e-c691e8504eda | textbox | Engineer's Rep. Name:
5e6e6eac-852a-55dd-a74f-be00f4ff6443 | date | Date:
50fd948b-9f9c-4810-934c-f44185e71180 | signoff | Add Signature
2787356f-966f-5d25-93cf-7ee6ab7b94b7 | checklist | ITP - Pavement & Surfacing - Subbase - Rev E | itp | ITP - Pavement & Surfacing - Subbase - Rev E
3969119e-9d77-5427-b958-ecc82f083c46 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
ec4e551b-3f47-528c-ae6c-fdfb3458be34 | note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence
eb1c5ab0-d958-5aff-9e01-8f56d5db5c3c | note | Standard / Specification - Downer
95e813a5-8719-5ac9-9ed3-db95c88daa4f | note | Verifying Document - Construction Pack
805d2c95-dc1c-508e-8b9e-fbca9c1eeaf6 | note | Frequency - Prior to Works start
fc39fb4d-ffff-5e1f-8d56-399758b18a65 | note | Activity - H
802be262-7e7e-53e8-b8bf-6038d6e34751 | note | By - PE
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
27f3be6b-b818-5263-817f-5ba924480d35 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
1f441f83-2c34-577a-90e0-73818924a2cf | note | Standard / Specification - Downer
a4fa1ba9-6110-5364-ab83-c9684041414a | note | Verifying Document - Survey Records
7fe5d102-a89b-537b-849f-5cc7bf99618c | note | Frequency - Prior to Works start
d378e4fb-1992-5af0-8e29-ab8e511f0e7e | note | Activity - H
ed48a75e-9faa-5783-b481-e3f0f2090547 | note | By - SV
a24a2c58-bf6f-5474-883c-40044bad1fc7 | checkpoint | 3.01.03 - Service Location
07cf3e6e-2226-5ee4-b1f5-8fff7d3c89fe | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
e5694d8a-f45f-52e8-b573-2ce535af9e31 | note | Standard / Specification - Downer
b2970209-fe08-5050-ba93-b0537bd69e94 | note | Verifying Document - Excavation Permit
e872e4d7-566c-548c-8e05-f649772197fa | note | Frequency - Prior to Excavation
0ef56c5b-7c85-56e8-9a7e-aab9f6807218 | note | Activity - H
53f0bb53-59d4-5d30-9a93-b3b481462cec | note | By - SE
0a214a7a-124a-5898-a837-e29e83751df0 | checkpoint | 3.01.04 - Internal Permits
8f9ece01-d727-5876-8560-edbd9d82bcf8 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. if applicable.
a7ee36d2-9b73-5f58-b71b-db5ca41fe4a2 | note | Standard / Specification - Downer
85ad478e-6552-52d0-b8b4-54e1f7ffbc8d | note | Verifying Document - Internal Permits
93d4943e-f796-520a-9124-ecb481319afe | note | Frequency - Prior to activity being undertaken
ea702c86-97c6-5605-ba1e-bfeeb7f387ec | note | Activity - H
a2718418-fc15-5b59-89c6-07251b3f0c0b | note | By - SE
917e2881-0901-542f-ae25-686bf9c47009 | checkpoint | 3.01.05 - External Permits
f23abc2d-c8ee-50ea-854a-9f64a7d9d86a | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc, if applicable.
6b62d5fe-af97-5ca3-b301-bd92f2791dc8 | note | Standard / Specification - Downer
a02559dc-175e-589a-9b8a-8eab68d69cad | note | Verifying Document - External Permits
b2f5d673-8cc4-5dbc-8d75-deccfbe742fe | note | Frequency - Prior to commencment of activity
d3a90524-e3a6-5f9e-b9d3-b83ba77aa7bf | note | Activity - H
13bc7be9-6edd-55c9-a267-e302e9aee166 | note | By - PE
a1302970-0389-558d-b43c-67b14bbfc27a | checkpoint | 3.01.06 - Approved Construction Drawings
f56d4abb-1946-538b-aad6-86aea7955913 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
09117102-46e6-57a9-9743-cdcaf0e4e481 | note | Standard / Specification - Downer
46964b83-84c6-5336-b6bd-922be5cef306 | note | Verifying Document - IFC Drawings
39dfba69-75f7-5742-968e-a4c90dbb0b22 | note | Frequency - Prior to works start
68e4c5de-58e0-5dec-91c6-170e024e015a | note | Activity - H
3d527e69-1c47-5f3d-8273-fc7878a3c156 | note | By - PE
4dd36031-ce9c-52f9-bfbc-d1541a841138 | checkpoint | 3.01.07 - Stabilising Methodology
f31947ca-c372-52b1-9187-bb4248d3254b | note | Acceptance / Conformance Criteria - Written approval of the Engineer with the approval of the methodology
a161a67c-8a7a-5dd1-9557-f02e91f6b027 | note | Standard / Specification - PS - 7.3.3
07fd60c0-fd43-5cf7-befe-31b3417972ce | note | Verifying Document - Correspondence
5f17963d-05de-50a8-9578-9003dcf71a00 | note | Frequency - Prior to stabilisation start
4c607593-a8eb-5c32-8ec8-95b0db6dee42 | note | Activity - HP
b8772278-c47a-56b1-a98c-0284beffbb55 | note | By - ENG
bcc75d59-fda9-5665-870d-6406349e1ed2 | signoff | AUTHORITY HOLDPOINT
9ffb2cc0-a1b6-5e07-aa7c-34ea633a63b0 | checkpoint | 3.01.08 - Acceptance of the SIL layer
f6339289-345f-5f4c-9a10-88376f46e5fd | note | Acceptance / Conformance Criteria - Written approval of the Engineer - All compliant test results for subgrade, SIL, all road crossings, storm water, wastewater, watermain, subsoil/pavement drains and any other activity that has been completed in the pavement area.
02730cba-a67f-5416-abdc-90b5998957c6 | note | Standard / Specification - PS - 4.8.3, Table 4.3
847b87f3-2330-5a62-abcc-ad8b65920f34 | note | Verifying Document - Hold point relesed / Testing reports
683e6528-9871-5c86-b102-a59b4f362661 | note | Frequency - All sections before proceeding to the next layer
c2f09181-52a5-56b6-a1b5-1c437cb54f45 | note | Activity - HP
ad1d82fa-b960-58f5-b406-029832fbcf42 | note | By - ENG
d3949fe3-b334-5e1c-a2b3-f23ab054269d | signoff | AUTHORITY HOLDPOINT
bc43c978-69d8-5f48-8b7f-ecbcce31a7dc | section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65
ca87e1fb-7246-51ad-9189-73e2340ccb26 | checkpoint | 6.02.01 - Sub-base MDD and OMC
f168b349-b948-59e0-834f-0b2ba45e5df5 | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
94791044-7035-5d70-836b-5bd471f60add | note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
72003631-2a30-59ed-9ccd-8bb41b9e6939 | note | Verifying Document - IANZ Lab Reports
a294e292-acfa-5d4d-8bb2-ac429ec82d86 | note | Frequency - No less than 1 test every 5,000m³ (in place)
f3890077-fa2d-5c9d-ac37-159c3531b5d4 | note | Activity - R
a55f805a-3e05-57ce-9887-0771a0f2e46b | note | By - PE
70fabdf0-7745-50be-96bf-2ded7dc55eed | checkpoint | 6.02.02 - Plasticity Index
1a02b294-b8c7-54a8-88ad-4b2eadf677b4 | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Liquid Limit shall be ≤ 25 when tested
de15fba3-2af3-5447-92e4-0ff93b28081b | note | Standard / Specification - Table 7.2
c8b38c01-7756-58f6-b0f0-b99d29d920dc | note | Verifying Document - IANZ Lab Reports
bfa862fa-eabc-5114-9532-f6da19c44f1a | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
bb7cea44-7b13-513c-8a99-abf001a2a74e | note | Activity - R
eadf6b0e-0f1f-54ef-b126-27840805effb | note | By - PE
22886128-c2cb-5f11-b511-007c412fa0ae | checkpoint | 6.02.03 - Clay Index
d48bd89a-2cde-500f-a65a-9c0ead3920c3 | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Plasticity Index shall be ≤ 8 when tested
24123e95-13ac-553f-becd-8e344e653d5b | note | Standard / Specification - Table 7.2
5041442d-2667-52e6-a388-347fcd1cc8bc | note | Verifying Document - IANZ Lab Reports
864c5f20-dd61-50e0-9e7c-7c6a82ee48d0 | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
2c66b3e5-64c2-50ca-add7-1f48a636da59 | note | Activity - R
84b352e3-3712-5479-adda-d025a9ad206a | note | By - PE
39fe01b4-f08b-5b33-9943-aadecfa5826a | checkpoint | 6.02.04 - Sand Equivalent
ee50526c-e9ec-5c79-91e8-670f2c1bb39e | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Clay Index shall be ≤ 5 when tested
c3d6c15e-6c07-5af7-84c6-1527766f8f9a | note | Standard / Specification - Table 7.2
8181ba8f-30d8-5506-b06d-a29546a00eb8 | note | Verifying Document - IANZ Lab Reports
7f791590-653e-5bbc-b299-61b3e8ad6c10 | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
d7befb75-e056-5ad0-9068-054f15d42590 | note | Activity - R
068d12a9-5531-5e68-ad78-ad8c0ed428d7 | note | By - PE
4aff0413-9e3c-530c-b97a-0793ec692f9c | checkpoint | 6.02.05 - Particle size distribution
1a8c69dd-c0e2-5b47-94bb-913d372659c7 | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1
ceeab263-cfbd-5a84-ae44-c53ca329d997 | note | Standard / Specification - Table 7.1
7ea3aa39-7de2-5b9f-a333-ab9d10071ce9 | note | Verifying Document - IANZ Lab Reports
836f527e-24cd-55ae-8a9c-b4fcff7cf69f | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
4df9e8bd-bbda-58ac-aec9-614f3c35ec32 | note | Activity - R
519ac218-21ef-581c-bc55-b73daef7619a | note | By - PE
e8905abc-1647-5fbc-9fa2-b0958848732e | checkpoint | 6.02.06 - Average Uncompacted Layer Thickness
6b32e036-d252-594f-8ce0-3eb80aff0240 | note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
648b2fed-46ce-540e-9f51-a18bfb12ba86 | note | Standard / Specification - TNZ B/02: 2005 - 7.3
a42810de-1507-53dc-be0f-446a8c7d0ee8 | note | Verifying Document - Survey / Level Checks
a0f4bd8f-6e11-51e8-bc6d-c882447e2666 | note | Frequency - 1 test per 20m
67978ffa-b835-59d4-9b56-3c8a6dad8a32 | note | Activity - I
72a4512d-e758-58f5-9856-07e0d6ca6500 | note | By - SV / PE
50dc97be-5c04-59c3-8703-cd318c3ee35e | checkpoint | 6.02.07 - Plateau Density Test
bc29dd99-a71a-51dc-8d02-33bf0f61312d | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
a31f8a84-a71e-59ae-80d8-12cc4a5710e9 | note | • Testing shall be at OWC.
a79e6939-4ab3-5aa1-a23e-dc5097a70f43 | note | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
4db60e69-808f-52cd-b326-970523d0b24a | note | Standard / Specification - PS - Table 7.2 - 2.3
d156f274-aee5-52c1-bb6b-8c7211c6a105 | note | Verifying Document - Plateau Density Report
22cb08a8-dbdb-5f03-aa42-cd222fd52a80 | note | Frequency - 5 tests per 10,000m2
0da96e90-93be-5ae0-8294-d4d6764a24d9 | note | Activity - I
bd2aacaa-57e0-578e-ab16-49fcbb5e5588 | note | By - PE
3ee4467b-b164-5546-a4a6-7cc3c4ecf208 | checkpoint | 6.02.08 - Sub-basecourse Pavement Layer Compaction
a565c723-69ac-5886-b35c-2693ff3155e2 | note | Acceptance / Conformance Criteria - Mean Value ≥ 95 Minimum Value ≥ 92
3051c527-6171-5f07-a895-8e8d848accaf | note | Standard / Specification - TNZ B/02: 2005
fbf04794-d375-5824-a102-a8516cf4f602 | note | Verifying Document - NDM Report
001719f7-47b0-537b-8df8-97351cfd4bb3 | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
4b955460-5c4e-5883-ab40-c8250043fc8c | note | Activity - I
6329ddc7-ac2c-5ed4-9026-9cdc6dfcb567 | note | By - PE
b152466a-921e-56d5-9032-1b468cc0597c | checkpoint | 6.02.09 - Surface shape control
f6d19746-988e-53c0-bd07-7cf2bbecfe30 | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
4a673db2-094e-5953-9808-6c7c3a311467 | note | • Vertical: - 25mm +5mm
3bda55bc-9b4e-5f0b-8a0e-8913bca49280 | note | • Cross fall: 0.5% on 2m straight edge
f0699e7d-4488-5930-bc24-e6bde8144145 | note | Standard / Specification - TNZ B/2
1b64c389-5f95-5892-ab77-39b0c10f8109 | note | Verifying Document - Total station Topo showing levels compared to design
2c19adde-02f1-5f99-b87f-abae30ebd503 | note | Frequency - Continuous
d69e2e2d-e889-5d9e-9ec6-25206323c908 | note | Activity - I
e95c8e22-5607-581f-acaf-8299ff2bd117 | note | By - SV / PE
7c9c928b-9d6d-55e2-9057-4eae9a377090 | section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial
6c098115-ed50-5770-83bf-79ab8107d3a0 | checkpoint | 6.03.01 - Stabilization Production Plan
c9ddb8f7-8811-5c24-a98e-4a7b7bde9d00 | note | Acceptance / Conformance Criteria - Production plan sent to engineer for review 48 hours prior to stabilising commencing. This is to include all information set out in NZTA B/6 7.2.3.
da0f5c1e-3efd-569f-b2ef-0d62230cc56f | note | Standard / Specification - NZTA B/6 7.2.3
503a87ad-53dc-5338-b7d6-41d39018bdad | note | Verifying Document - Correspondence
4b686472-ead5-5dca-9e19-e1a7af89afd6 | note | Frequency - 48H hours prior sabilising commencing
cb4be3d2-1fc8-5f91-99ab-ff9da052c5f2 | note | Activity - HP
abad576a-df96-543f-9ab1-765a1ff468b2 | note | By - ENG
efaac3d4-313c-53da-9b8a-af70649a58b8 | signoff | AUTHORITY HOLDPOINT
33bc697f-3ee0-5632-94ad-1cc6ea4d8aff | checkpoint | 6.03.02 - Longitudinal Joints
f2cfb2e7-40b5-5204-868e-224c0ffe7c5f | note | Acceptance / Conformance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by a minimum of 200 mm or half the layer thickness, whichever is the greater.
7b7caba1-a9c4-5c5d-a3af-5fea17a64691 | note | Standard / Specification - NZTA B/6 7.5.2
1ac5d31f-9758-50ae-9f72-48d864679110 | note | Verifying Document - Stabilisation Prodution Plan
9af7f4d5-44b2-586a-b84d-14083db10bdc | note | Frequency - 48H hours prior sabilising commencing
703a7061-48ec-50a2-bf67-28fd4c8b61f9 | note | Activity - H
3ecbad6b-6769-52d3-8371-9bae9e3e68bc | note | By - PE
f2fd84d9-a211-565e-a0e0-957d8630417c | checkpoint | 6.03.03 - Stabilisation trial
aaf3fcc6-69cf-5107-bdd2-324afb462409 | note | Acceptance / Conformance Criteria - A trial shall be conducted on a minimum stabilised area of 2,000m2 to verify the performance of the stabilising operation and finished product prior to full scale production.
32d89166-cc92-5257-8a02-b42deb788bcf | note | Standard / Specification - PS - 7.3.3
fc6cde74-b4bb-53b0-8942-0552487547d2 | note | Verifying Document - Triall Report
835b815b-b849-51c9-8abc-91b75b5897e4 | note | Frequency - prior to full scale production
10b65111-54b2-5545-b5b5-be46c4838f88 | note | Activity - HP
c72f6072-5eca-5743-b96b-117fc11d2cf9 | note | By - ENG
836a28a7-55e3-5ddb-91a4-e7dccd925e7a | signoff | AUTHORITY HOLDPOINT
c77ae1a3-eb3d-5fdd-85c2-176a01d6eedf | checkpoint | 6.03.04 - Stabilising Equipment
b85e3249-9895-5172-a001-1466f4265669 | note | Acceptance / Conformance Criteria - The Contractor shall use stabilising plant purpose built and appropriately adjusted for the in-situ stabilisation of roading aggregates, as opposed to plant designed for soil stabilisation or re-cycling.
1ee3589b-5081-5efc-bdad-6aba26d6e9a5 | note | • The stabiliser drum shall have a straight tooth pattern and the drum speed must be adjustable in real time during stabilisation.
a3776b5d-7d91-53eb-bb08-1af17fb325a2 | note | Standard / Specification - PS - 7.3.2
3b65390a-1386-58dd-8d6a-5e763cde91a7 | note | Verifying Document - Plant Approval
88a73c18-536b-5f46-bb46-d7b80e90b423 | note | Frequency - Prior to works
83e5610e-6576-5395-a4fa-7274e96a60c7 | note | Activity - H
64cc6353-220e-5907-bfcd-449c0bc979dc | note | By - PE
65357786-cd6f-5367-a375-639ab3f50f85 | checkpoint | 6.03.05 - Stabilising Supervisor
4892293b-c97e-5f7b-8af6-863f1c449d64 | note | Acceptance / Conformance Criteria - During stabilisation the Contractor shall employ a suitably experienced person to continuously walk behind the stabiliser to assess the uniformity of the mixture and water distribution and to check the stabilisation depth every 100m.
b82eadfd-0943-56e1-8a03-094e7c34f50c | note | Standard / Specification - PS - 7.3.2
3551a47b-12a0-5a1a-8ea5-7b63cff98b4c | note | Verifying Document - Supervisor Approval
8251bbf9-5e57-58ad-aee4-43bbe9f37c78 | note | Frequency - Prior to works
a4146f77-cb32-5f0c-9c04-6338cd5be9c9 | note | Activity - H
21f6550a-d45f-508e-b98b-d3e37a65df52 | note | By - PE
b2e16153-370f-553c-9fbe-4d6c94095131 | checkpoint | 6.03.06 - Before Stabilisation Surface shape control, layer thickness
04e2ce5c-fc23-51ac-b996-8b395cb81ee1 | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
c79417a1-d3da-5554-8196-a20418d2f028 | note | • Vertical: - 25mm +5mm
be91c280-43e7-5a2f-b532-dea6df56a8d0 | note | • Cross fall: 0.5% on 2m straight edge
7ce457fc-836f-5cc6-a269-ba8371d1833a | note | Standard / Specification - TNZ B/2
84a096bf-3ee3-5f72-a1d9-f550bc29364f | note | Verifying Document - Total station Topo showing levels compared to design
038c979c-acff-5c79-bdf8-95a17d456d70 | note | Frequency - 1 test per 20m
25a6b6d3-0568-511b-98c0-be8b869b3e71 | note | Activity - I
80588976-67d6-54ca-9d40-618b6fdcc383 | note | By - SV / PE
61811b90-1233-52f7-81cc-b19f731dbfcd | checkpoint | 6.03.07 - Average Uncompacted Layer Thickness
57abe783-f1ed-53d3-84cc-34e27300e213 | note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
f3e06d3b-2107-5ca4-ab1d-8e980c44d108 | note | Standard / Specification - TNZ B/02: 2005 - 7.3
b91bd336-8e5c-532c-ad9d-fea08ac6590e | note | Verifying Document - Survey / Level Checks
46a082e0-947d-55f6-9700-208f12e701e9 | note | Frequency - 1 test per 20m
b0e66bd0-e4af-5d26-8d47-bf34fe7b8ca6 | note | Activity - I
7b9507c3-415a-57b6-ad99-2fa7d63f6ca9 | note | By - SV / PE
0f3c4886-911f-570e-9380-945bb931b659 | checkpoint | 6.03.08 - Pre Stabilisation Compaction
2de608fd-6034-5977-8b48-ace7c120a2de | note | Acceptance / Conformance Criteria - The full thickness of the layer to be modified shall be compacted between Value ≥ 95% and Minimum Value ≥ 90% Prior to stabilisation, this will be reviewed following the stabilising trial and adjusted to suit and the updated target shall be added after the stabilising trail. DN1205-DOW-RFI-0043.01
c076cd42-6e8e-5b46-a0df-e078704d7870 | note | Standard / Specification - PS - 7.3.2
f288a3ff-d1e2-5f20-920c-7fa4a3abc914 | note | Verifying Document - IANZ NDMS
f0c423cb-1eba-5011-80ac-05005e695439 | note | Frequency - Min 5 Tests per lot 1000m2 max lot size (Prior to stabilisation)
35184592-ddea-5789-9628-76295e981225 | note | Activity - I
5948452b-0aae-5278-993c-de000a64b387 | note | By - PE
03cc060f-e525-5da1-b4a4-927a2c816637 | checkpoint | 6.03.09 - Pre Stabilisation Crossfall
7dcc80a1-3999-5c00-bfc3-bf293b8a8647 | note | Acceptance / Conformance Criteria - Before stabilisation the Contractor shall check the crossfall by string line to confirm compliance with the design.
cf25e97d-2159-5462-a6ce-4196b9d4293a | note | Standard / Specification - PS - 7.3.2
3b2b548d-399e-519d-9d69-9a2927c0b6b1 | note | Verifying Document - Total station Topo showing levels compared to design
5303e7de-4445-5c0f-9266-790d456b0644 | note | Frequency - 1 test per 20m Prior to stabilisation
de272e7d-a2c4-580c-9190-796fa51c3638 | note | Activity - I
ca2a2111-0158-5182-be1b-445174fedcb3 | note | By - SV / PE
dd46457d-0574-5b56-b7ac-f21afadaed60 | checkpoint | 6.03.10 - Stabilising Visual appearance
8f8865c0-7ffc-5b16-807d-503d621cbc5a | note | Acceptance / Conformance Criteria - The stabiliser shall produce a uniform particle size distribution behind the stabiliser, both laterally, vertically and longitudinally and produce minimal break down of the coarse aggregate particles during mixing.
cf749d9a-5bf1-50bf-a203-7e3c464d3673 | note | Standard / Specification - PS - 7.3.2
aa34d7ad-4e05-5677-b27c-5f6f1411f00b | note | Verifying Document - Site Notes
69f6c763-0a03-51d9-bfa5-534ccacaf6ef | note | Frequency - every 100m
d91ec8a3-6ce2-52e2-80f0-1b03438f13ee | note | Activity - I
87e701c1-161f-5285-9b2e-cd20ebb3e36d | note | By - PE
6eed5d81-e5b0-55cf-bece-401f93ecd9b8 | checkpoint | 6.03.11 - Cement Mat Test / Spread Rate
da3f72b4-b1e3-5657-808e-2bc54fe47d04 | note | Acceptance / Conformance Criteria - The stabilising agent shall be uniformly spread at the specified application rate across the pavement to Within ±0.5 kg/m2 of the specified rate
24f9b6df-5b16-5895-9f6b-b49960501d8d | note | Standard / Specification - Table 7.2
94fee484-a5b3-5490-bb40-6bf4b0938f69 | note | Verifying Document - Stab. Sheet
99cdf68f-0152-5f34-b1a5-3760076113bb | note | Frequency - One per each run of cement spreading, until the Contractor can demonstrate consistency in cement spreading and/or demonstrate accuracy of on-board computer equipment calibrated/compared against weighing cement mats.
7ddb2bae-c964-5cf3-8183-009d7060c3bb | note | • Upon successful demonstration of this, the 1 per 500m2 minimum can applya
1cfad76f-afa0-56a5-94e6-cd4c58e6b657 | note | Activity - I
e92ba43f-b2f2-5c8a-9649-ee66f9671721 | note | By - PE
58788175-0c81-55f7-8c9c-122dc5a74310 | checkpoint | 6.03.12 - Cement Average usage test
201f6146-1817-5edb-a22c-c29f7f45f2a0 | note | Acceptance / Conformance Criteria - Compare tonnes used (from delivery docket) with measured area Within ±2.5 % of the specified rate
f17dd1db-7f20-5312-b139-97755128b80c | note | Standard / Specification - TNZ B6
749b65f8-ccd4-520b-90d3-1e9fdbd250c1 | note | Verifying Document - Stab. Sheet / Delivery Doc.
6586c6f9-d9c7-524c-beaf-40df78cc4131 | note | Frequency - Upon emptying the spreader and bulk tanker
914cde35-1363-5dfb-920a-556fed6e74b9 | note | Activity - R
658e3f08-7984-52e5-8b16-f6fa47795fdf | note | By - SE
8dd5c234-a389-5dfe-8991-b7486bab77cb | checkpoint | 6.03.13 - Control of cut depth
46b9f88e-99c9-5a60-a968-15cc96292ceb | note | Acceptance / Conformance Criteria - Maximum variation from the specified depth of cut is –5 mm and +15 mm. Without picking up sand from SIL
8f09f694-78a6-5532-93a0-59f7ad96ba2a | note | Standard / Specification - TNZ B6
4afa3e59-c79c-5e6c-b5c5-86d8c9c5c9b0 | note | Verifying Document - Stab. Sheet
2be0fa1c-b437-5b11-a13e-69e22b6f8b08 | note | Frequency - First check of cut depth should be immediately behind the stabiliser at the start of each run, then again every 200m, or as requested by the Engineer
ce80a921-3335-5a15-a8f6-c9b7326838fd | note | Activity - R
5f9d6dc1-3b64-5181-89c5-19a73f488add | note | By - SE
19eac722-f22d-5929-8126-b167f6613939 | checkpoint | 6.03.14 - Plateau Density Test
decd180e-26e7-56c8-a3c1-c00f8720c9e0 | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
c865ae35-c13e-5881-99c9-18bc78a225a6 | note | • Testing shall be at OWC.
f64e7a3a-7098-52be-8784-a85fae85996e | note | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
177e1bb7-f470-50c1-bb79-20e420d6426e | note | Standard / Specification - PS - Table 7.2 - 2.4
f69b2107-9d61-5d1d-afc0-990e1ee682b7 | note | Verifying Document - Plateau Density Report
572e474c-67c5-55ad-aa87-750d7a624c7e | note | Frequency - 5 tests per 10,000m2
1e50156b-7f28-5a92-98ef-c62f718b4864 | note | Activity - I
f832f683-84fa-54d1-b808-402011fa634a | note | By - PE
2ee5ae31-1ce2-5318-b785-95fce0922ca9 | checkpoint | 6.03.15 - Particle size distribution behind stabilizer (Wet Sieve)
9a4fb5ed-bd27-535b-a022-bebf285b6004 | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1. A Wet sieve analysis will be completed within 4 hours after stabilizing
00eb80fa-3200-5417-b532-c46d18a37a6a | note | Standard / Specification - NZS 4407: 1991 Test 3.8.1 Standard Method by Wet Sieving
c1e6242b-b982-5e22-a725-33ef54319773 | note | Verifying Document - IANZ Lab Reports
d2116d61-7adf-57d3-8106-1c51336749a8 | note | Frequency - 3 samples bag per stabilise day post hoe
a2dcec01-55c7-552c-b0b0-ddc1a435ae63 | note | Activity - I
ca9469bb-b5fa-592e-b002-a0f30567b1c6 | note | By - PE
3744d9ba-d8e1-5383-9d2c-5335ed0cf31b | checkpoint | 6.03.16 - Mixed material testing (ITS)
e2b5c14a-af27-5eb6-b955-0adb175e234a | note | Acceptance / Conformance Criteria - During mixing, the contractor shall take a pair of representative samples behind the mixing plant per lot or at a minimum of 2 pairs of representative samples per day.
d688278a-6706-534e-8852-c900e1806fab | note | • These samples shall be placed in a sealed plastic bag and cured for 1 hour before compacting into a mould and testing the indirect tensile strength (ITS) of the mixed material according to NZTA T/19
47d240fd-1755-530d-8cb6-4e1fc7b7bf94 | note | Standard / Specification - TNZ B6 7.5
773ab540-931e-5436-96b7-b637f29e940a | note | Verifying Document - Test Results
b5a4545b-eeba-56b5-ac7c-309e3f13ba69 | note | Frequency - 2 tests per stabilise day
9405b5d3-7923-5d1c-ab1e-7daadd0fb3c8 | note | Activity - R
a81873b5-9bab-5d3c-bab6-8f7d512b6321 | note | By - PE
9b3b1023-6a86-5a49-9ba8-c3eceb03ddce | checkpoint | 6.03.17 - NDM Water correction
c25bbffd-26b9-5cd1-9007-ea0430d5425a | note | Acceptance / Conformance Criteria - Daily Laboratory water content tests shall be carried out on samples taken and used to correct the NDM measured dry density.
7094f35a-7333-5c0e-a9fd-b35dd164b270 | note | • Will get the Moisture correction factor from the Plateau report itself. That is the difference between the Moisture reading on the NDM vs the actual moisture when dried in the oven.
a4a8ac4a-1615-59b8-a711-d27a3ceeb43a | note | Standard / Specification - NZS 4407
d9b5523a-05b2-58fd-9e57-a9303f0304c4 | note | Verifying Document - Corrected NDM Results
9249129b-f15a-54ce-b381-d81ad35dac4b | note | Frequency - Per Stabilise day
245a86d9-a73e-59fa-aa80-37e87cd97e1e | note | Activity - R
8af1dd0a-24d3-5a19-a2b8-7017f0a60f45 | note | By - PE
189483f5-5c2e-5d24-8c0e-4762ac1f0541 | checkpoint | 6.03.18 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
5d68a0f4-4196-5761-9790-d8be3e07e987 | note | Acceptance / Conformance Criteria - The sub-base compaction requirements in Table 2 of B/6 shall be replaced with a Mean Value ≥ 98% and Minimum Value ≥ 95%. - Direct Transmission
71e6b7a8-57ce-5ca8-a855-be653ee16563 | note | Standard / Specification - PS - 7.3.2
c38c893e-c4af-5435-8b10-5cea4af66292 | note | Verifying Document - IANZ Lab Reports
09c7affc-1350-5f10-b8e6-a01c82222f60 | note | Frequency - Min 5 Tests per lot 1000m2, minimum 7 days after stab.
f13edf28-3a07-5e5e-8f90-380006fa79fa | note | Activity - I
766ab5be-df67-5b77-9a8a-613a23d83192 | note | By - PE
4eafc89d-3d95-5e4e-b4f9-e4c39a2227af | checkpoint | 6.03.19 - Post Stabilisation Surface shape control, layer thickness
8b976792-3213-50e1-9b79-b17bfa92e2cd | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
bb1aaf06-ac2a-5c01-b59c-99c125149d3d | note | • Vertical: - 5mm +10mm
826abe9c-7624-52b5-81ae-9dba7f27ccbe | note | • Cross fall: 0.5% on 2m straight edge
c94a6cad-a425-5c8c-b31f-1d39bfc23390 | note | Standard / Specification - TNZ B/2
504e543b-ebf4-5caa-97da-11e2e571a421 | note | Verifying Document - Total station Topo showing levels compared to design
844977c8-ff1d-5b87-8ce8-15c352b20022 | note | Frequency - 1 test per 20m
d1b3ec14-8717-5fd1-aff6-6d207298a937 | note | Activity - I
7badf766-988c-53cd-9bbf-3c397b0a935d | note | By - SV / PE
72280022-fd87-5882-b3d4-4682359acdc4 | checkpoint | 6.03.20 - Protection, Curing and Maintenance before Overlaying
3d71e903-b505-5839-85cf-cc631955ea52 | note | Acceptance / Conformance Criteria - The Contractor shall protect, maintain and cure the completed cement bound sub-base until the next layer is applied. Besides construction traffic required for the above curing no other construction traffic shall be permitted onto the layer within 7 days of stabilisation
2ccf6b0a-db10-5b23-b23c-8b040512c59a | note | Standard / Specification - TNZ B6 - 7.8
a1ab7aa0-62a0-586d-85bb-84e441f89c33 | note | Verifying Document - Site Notes
13fbbedb-5f36-5063-a677-5482008a00f9 | note | Frequency - For 7 days after stabilisation / Photos
aafc97a3-8cfb-53f8-b823-b6d7c5d4fecc | note | Activity - R
54e81eef-18ff-5283-8882-1692dfd66af4 | note | By - PE
80726abb-7f00-5a67-ad5c-4f9961a101e8 | checkpoint | 6.03.21 - Benkelman Beam
86073cf5-cb7d-5788-8fad-6c6c432370b0 | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer.
f46ea1ac-e9f1-5874-9372-f9aea3a5d9c8 | note | • Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY
3efa5857-763b-54d3-8278-799e35daacd2 | note | Standard / Specification - PS - 7.3.2
9e77db51-97a0-5170-bcaa-6857975a2049 | note | Verifying Document - Benkelman Beam Report
265fb537-4cec-53b7-86ff-39b6861b114d | note | Frequency - Every 10m of each lane – staggered between left and right wheel path.
96390e81-b614-50bb-93c7-f3d2b0c95b35 | note | Activity - R
eb2d27cd-0b0d-5dd3-b96e-e4eb2ff8392a | note | By - SE
00ccd532-6cdc-5994-8bfb-114564ace123 | checkpoint | 6.03.22 - MDD / OMC / SD
4f4ed41d-cb8c-59e9-8606-f95b6bac1490 | note | Acceptance / Conformance Criteria - Post hoe, stabilised MDD, OMC, and SD. 1 test per 2000m² or a days work whichever gives the greater number of testing.
8ed938ff-2157-5aa2-ba7c-f6efdb4d2cfc | note | Standard / Specification - NZS 4402:1986, Test 4.1.3
ec991d8f-7516-5322-a5ea-fb77853e2a97 | note | Verifying Document - Lab Report
f69218dc-8c78-51c4-8c14-62b6a43378b7 | note | Frequency - 1 test per 2000m² or a days work whichever gives the greater number of testing.
8330547e-cf6f-5e95-ae6d-e1e3125e40a5 | note | Activity - I
8e65f206-c8d3-53c9-9d6e-4c3adf41f08d | note | By - PE
ba7d06af-c7af-5c9d-8ab4-2e3c21a61daf | checkpoint | 6.03.23 - Sub-base stabilisation trial
33db0125-cfac-51c2-bb13-8f2039ec729c | note | Acceptance / Conformance Criteria - After the sub-base stabilisation trial, prior to proceeding with further stabilisation.
97852424-7570-5606-b7c8-390f1c5314de | note | Standard / Specification - PS - 2.2.16
1b5a9b91-a178-56d2-a4d1-b6f3efed76b6 | note | Verifying Document - Hold Point Release
09d9073d-8a0f-5d5e-afa6-7c41e1c3daed | note | Frequency - Min 48h Notice
f548d775-5ebc-56b3-bf85-04c9216f346a | note | Activity - HP
bf8a7659-4300-5770-8079-4c595911ef49 | note | By - ENG
944ea1fd-b7c9-5949-95b5-51c9f13d6c6b | signoff | AUTHORITY HOLDPOINT
3ed998ef-a740-59b5-a205-c17d1ea4ae1e | section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base
bfa46ea3-f62a-522a-aeaa-762b5defdaf1 | checkpoint | 6.04.01 - Stabilization Production Plan
4bc5963e-cd2c-51c9-aca5-69592b28e7b2 | note | Acceptance / Conformance Criteria - Production plan sent to engineer for review 48 hours prior to stabilising commencing. This is to include all information set out in NZTA B/6 7.2.3.
71cb6c20-295f-57d5-a171-0161932e085a | note | Standard / Specification - NZTA B/6 7.2.3
a63946e0-13fc-5f8f-af3f-dd8702db5ce8 | note | Verifying Document - Correspondence
21058093-260c-502c-9a10-4289560be62c | note | Frequency - 48H hours prior sabilising commencing
e8b8790c-3ca2-5fdb-89d4-45c8244f3825 | note | Activity - HP
3f7f445d-4e23-5bda-9bff-1d2d926e9369 | note | By - ENG
e4ed9518-8669-550c-8d69-a36a5a98261d | signoff | AUTHORITY HOLDPOINT
718a330a-7558-52f6-be9b-f238816a905a | checkpoint | 6.04.02 - Longitudinal Joints
22db6f42-ec9d-5643-90f1-7b79fa348ab3 | note | Acceptance / Conformance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by a minimum of 200 mm or half the layer thickness, whichever is the greater.
719e890d-d568-55b5-84e6-bed77f0f46a3 | note | Standard / Specification - NZTA B/6 7.5.2
78c93c41-abe6-58db-a342-afd7b48c2a61 | note | Verifying Document - Stabilisation Prodution Plan
6c9b5431-1a5a-52bb-9e62-0e81f150c6d6 | note | Frequency - 48H hours prior sabilising commencing
f59876a0-5a1f-53f6-b4bf-cb2e0bcdacd0 | note | Activity - H
1ced5c1f-5106-5c18-8962-145b62d99b22 | note | By - PE
3057a053-0fa8-5141-99e1-8805c8143030 | checkpoint | 6.04.03 - Stabilising Equipment
b8341bd7-673c-5dc2-808a-b5591245a41d | note | Acceptance / Conformance Criteria - The Contractor shall use stabilising plant purpose built and appropriately adjusted for the in-situ stabilisation of roading aggregates, as opposed to plant designed for soil stabilisation or re-cycling.
13969d9f-b85a-5f7a-9aa8-66e1e0edae96 | note | • The stabiliser drum shall have a straight tooth pattern and the drum speed must be adjustable in real time during stabilisation.
2deb8519-49c2-5487-9cf7-444377be1b25 | note | Standard / Specification - PS - 7.3.2
20980237-258c-5659-ade7-2366ac0b8b3f | note | Verifying Document - Plant Approval
5cdb0063-1c4f-5b26-af41-f8037bdb887a | note | Frequency - Prior to works
fd180c27-27ce-546e-80c4-4d43ec441f4b | note | Activity - H
3524338e-2ce4-5f52-b118-b96a05ccca61 | note | By - PE
d10c1293-8308-5402-8f5a-943d59292a90 | checkpoint | 6.04.04 - Stabilising Supervisor
840c29c2-0a8c-5ea5-ba9e-1cbbf8bf56ed | note | Acceptance / Conformance Criteria - During stabilisation the Contractor shall employ a suitably experienced person to continuously walk behind the stabiliser to assess the uniformity of the mixture and water distribution and to check the stabilisation depth every 100m.
459a0a17-3115-50b1-8574-e577b9fa3289 | note | Standard / Specification - PS - 7.3.2
4931d8f6-9541-5ae3-bcab-bf8298c7c272 | note | Verifying Document - Supervisor Approval
527ee89c-1792-57ee-a5a9-287bcfcbc472 | note | Frequency - Prior to works
5f19806f-af48-5c20-b1eb-99d26cdcd076 | note | Activity - H
ed8cc6f7-ff4c-5eed-9210-4c62bf32bba9 | note | By - PE
1c51f95a-b88f-562b-b314-9008bea93499 | checkpoint | 6.04.05 - Before Stabilisation Surface shape control, layer thickness
9d8c8e5e-11ce-58a7-860d-c33d6c7859b2 | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
616c8ede-e9b2-5437-b1f6-ce66bcd2f0e7 | note | • Vertical: - 25mm +5mm
bdb504a7-1ca9-50f7-b822-c9b3a4acf4c6 | note | • Cross fall: 0.5% on 2m straight edge
f92c3ee3-0fce-5b0f-8b35-7932831125a2 | note | Standard / Specification - TNZ B/2
71e702c3-1afe-5980-aab7-e902f1ec27f2 | note | Verifying Document - String sheet
69ce19e3-2200-5312-b708-210d89c586eb | note | Frequency - 1 test per 20m
5f7c86d0-2816-5f16-b69f-5c2bed0014c7 | note | Activity - I
16cf3505-f954-591c-92f1-db3b12cd003e | note | By - SV / PE
0d6f6583-baee-5c8d-8dea-ee479453f289 | checkpoint | 6.04.06 - Average Uncompacted Layer Thickness
9570be19-0fe8-57ce-bcb1-ef4816b0e78c | note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
3aa0923e-f1c9-58dc-a8ae-da58cae7c067 | note | Standard / Specification - TNZ B/02: 2005 - 7.3
876ae953-7cdc-56d4-b12f-0969f34eb79e | note | Verifying Document - Survey / Level Checks
7eb6d98c-375e-576e-ac51-7e0c32aeb52e | note | Frequency - 1 test per 20m
1364f684-6351-556e-8189-03544cf0bdf0 | note | Activity - I
15f9afb4-4f6e-561c-9b64-85ec16932a31 | note | By - SV / PE
917f88ba-1bf1-5687-b499-860c1cb7ca16 | checkpoint | 6.04.07 - Pre Stabilisation Compaction
395eae28-4c8d-59bc-bd7b-7283b16b67bb | note | Acceptance / Conformance Criteria - The full thickness of the layer to be modified shall be compacted between Value ≥ 95% and Minimum Value ≥ 90% Prior to stabilisation, this will be reviewed following the stabilising trial and adjusted to suit and the updated target shall be added after the stabilising trail. DN1205-DOW-RFI-0043.01
614970bc-9f95-51d2-85d7-240c03166f66 | note | Standard / Specification - TNZ B/02: 2005
03cd9565-736a-5c41-b2bb-2c62bef5a03a | note | Verifying Document - IANZ NDMS
7d062746-9063-552a-8600-70c701e6de9c | note | Frequency - Min 5 Tests per lot 1000m2 max lot size (Prior to stabilisation)
819a1ad6-5e53-520b-ad5f-c702560be83c | note | Activity - I
ec31e201-c41b-5fc2-9b67-fefc9467feff | note | By - PE
609cd901-d33f-51ea-8bf0-2ac755e5ea9a | checkpoint | 6.04.08 - Pre Stabilisation Crossfall
9e8fe53f-a4f1-5780-8ccb-6c86d9016322 | note | Acceptance / Conformance Criteria - Before stabilisation the Contractor shall check the crossfall by string line to confirm compliance with the design.
71360f74-312e-57d7-bb04-30fff5aea2e0 | note | Standard / Specification - PS - 7.3.2
de23d183-7039-5637-980c-457a089db70b | note | Verifying Document - Total station Topo showing levels compared to design
60c78e68-7cc6-5c38-8fa6-1f1e015f1735 | note | Frequency - 1 test per 20m Prior to stabilisation
fc9d3184-55ac-5435-a416-d61089d7c36f | note | Activity - I
a514a1b0-5d8e-57ef-b0a0-53b72199740d | note | By - SV / PE
c5459efa-5597-5eb0-a767-a817864c6611 | checkpoint | 6.04.09 - Stabilising Visual appearance
5271a85c-4033-5182-87d5-e949d8805412 | note | Acceptance / Conformance Criteria - The stabiliser shall produce a uniform particle size distribution behind the stabiliser, both laterally, vertically and longitudinally and produce minimal break down of the coarse aggregate particles during mixing.
7099c8a2-8d24-5440-a12e-deca0db77cbc | note | Standard / Specification - PS - 7.3.2
ea995418-cd6c-5018-87a7-dbda26d9543b | note | Verifying Document - Site Notes
51ab3f3a-0703-53a4-909f-ab0246c7ba52 | note | Frequency - every 100m
bbb26c31-a3d5-5e57-9c1f-0918ac1187c8 | note | Activity - I
26a05264-4d7b-5c54-8b74-ae3956ac22bd | note | By - PE
7fa669a4-d877-59f3-a991-2960916f29d5 | checkpoint | 6.04.10 - Cement Mat Test
46c51070-6f39-5c90-b926-7f40ec685408 | note | Acceptance / Conformance Criteria - The stabilising agent shall be uniformly spread at the specified application rate across the pavement to Within ±0.5 kg/m2 of the specified rate
f4280e81-30e6-5494-bf91-f3f1fd2bf034 | note | Standard / Specification - TNZ B6
e50e070d-6787-5c4a-9684-171f12480f21 | note | Verifying Document - Site Notes
797abd0c-2fe3-51b1-a8c0-306322b0abdb | note | Frequency - One per each run of cement spreading, until the Contractor can demonstrate consistency in cement spreading and/or demonstrate accuracy of on-board computer equipment calibrated/compared against weighing cement mats.
6377a24c-c013-5ceb-a8f8-7b0711433e34 | note | • Upon successful demonstration of this, the 1 per 500m2 minimum can apply
991cd70b-faf9-5183-8e93-ca3425890e1e | note | Activity - R
e201a738-c914-5bbe-ada2-7f7d94fe58ed | note | By - SE
0fabe193-9a41-532d-98d6-aa037b156014 | checkpoint | 6.04.11 - Cement Average usage test
68b97820-43ef-5f18-975e-3fc3c9960e38 | note | Acceptance / Conformance Criteria - Compare tonnes used (from delivery docket) with measured area Within ±2.5 % of the specified rate
aca9e915-5aec-53eb-bc48-4f755a7c2c21 | note | Standard / Specification - TNZ B6
e3228326-a428-5903-8a5f-45c605273519 | note | Verifying Document - Site Notes
d679f51e-32a8-5a92-bb32-fecca5ba6b2c | note | Frequency - Upon emptying the spreader and bulk tanker
d541f030-6686-527f-a67e-eb3922abd445 | note | Activity - R
75111d96-39ac-520b-bbad-af92c278c2f1 | note | By - SE
74caf95c-5000-5bc8-b4b2-04774c703212 | checkpoint | 6.04.12 - Maintain OMC during stabilising
67a7bf6e-5925-5f91-8b98-58f13ec66fc4 | note | Acceptance / Conformance Criteria - The water content during compaction shall be in the range of 90% to 100% of the material’s optimum water content by NDM
221c45c9-9783-5127-ae8a-4d9fdc76cb94 | note | Standard / Specification - TNZ B6
df070077-c6a5-5b64-b8fe-57ffd4c9d52e | note | Verifying Document - Site Notes
1d3ac4db-33db-5204-be5b-4cce824f0fa7 | note | Frequency - Continuous
afc29ce6-1580-50c0-875a-7d3aab9a5e13 | note | Activity - R
9db2b5c8-defd-582c-a4ca-837200747cbb | note | By - SE
7b488497-b6e3-515a-a2cd-a6fa3fd2f415 | checkpoint | 6.04.13 - Control of cut depth
0ddfa63a-fd18-5bae-a74a-6c98f04519f3 | note | Acceptance / Conformance Criteria - Maximum variation from the specified depth of cut is –5 mm and +15 mm.
25ee1494-9d5b-5d4d-b5a3-a40e2a8cd101 | note | Standard / Specification - TNZ B6
ca9c51c8-b702-5df5-bf81-99449144462d | note | Verifying Document - Site Notes
37d1ce92-57b8-5546-b45e-95aa72e6d33d | note | Frequency - First check of cut depth should be immediately behind the stabiliser at the start of each run, then again every 200m, or as requested by the Engineer
9b9978ae-2445-5c30-b771-a7c7e932bc80 | note | Activity - R
479a411d-566d-5a03-84db-2ef8e0048266 | note | By - SE
a7d56f3a-97b2-545b-8bfb-724ae17d31c5 | checkpoint | 6.04.14 - Mixed material testing (ITS)
182a9fe4-2949-5d3e-b7d3-fa5b4add3c9e | note | Acceptance / Conformance Criteria - During mixing, the contractor shall take a pair of representative samples behind the mixing plant per lot or at a minimum of 2 pairs of representative samples per day.
a16b5584-eb92-5996-a447-640616a6119e | note | • These samples shall be placed in a sealed plastic bag and cured for 1 hour before compacting into a mould and testing the indirect tensile strength (ITS) of the mixed material according to NZTA T/19
794886b0-a9e7-5160-9efb-77c08cfa7659 | note | Standard / Specification - TNZ B6 7.5
d8b792e0-ef84-513a-be03-c931ca889de2 | note | Verifying Document - Test Results
aa8aa106-429b-510b-8ded-44d4974a6b19 | note | Frequency - 2 pairs of representative samples per day
2cce68a2-8e49-577d-8452-1338d837f301 | note | Activity - R
d9dd5959-3630-54c0-be19-04a149b58bc7 | note | By - PE
3cedef64-08d4-5b77-aec2-06e0043b20c5 | checkpoint | 6.04.15 - Particle size distribution behind stabilizer (Wet Sieve)
1595fc51-d5fc-5df3-a8b1-0773e76f8c91 | note | Acceptance / Conformance Criteria - A Wet sieve analysis will be completed within 4 hours after stabilizing, and consist of a minimum of 3 sample bags per lot.
e177ed60-e00e-51b1-895a-acc923dfc0f0 | note | Standard / Specification - TNZ B6 7.5
b07b0c57-20d3-5c59-9388-46d75e9923ed | note | Verifying Document - Test Results
0c70ede9-d3ba-5994-b6d1-9957929423c4 | note | Frequency - 3 sample bags per lot.
574bf161-e84e-5d84-ae04-3162922faf6f | note | Activity - R
f1ad340c-ef06-5def-a22c-94cd6377d488 | note | By - PE
d62ad979-e997-5694-a31c-92d3522dc172 | checkpoint | 6.04.16 - Plateau Density Test
68a2ad58-5808-5d0c-819d-28b10696645c | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
6d0085de-57cf-557c-91b6-4672f368d027 | note | • Testing shall be at OWC.
d22a0b2c-00d9-5356-b5e9-2c972d6ecf9f | note | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
7bea7d1c-f70f-56a2-8442-27215f842acc | note | Standard / Specification - PS - Table 7.2 - 2.3
068b6962-d280-59ef-82e1-3d35849927d3 | note | Verifying Document - Plateau Density Report
6adfe101-3863-5448-b479-fed6fb6eecfd | note | Frequency - 5 tests per 10,000m2
6077f9fc-e466-501e-83cb-2e4a91af231b | note | Activity - I
87cbce07-02e0-52d7-a53f-d13045dca5c8 | note | By - PE
5fce28a7-9260-5974-9b51-6a9f0890352a | checkpoint | 6.04.17 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
b1a1c4c4-a226-5240-9436-4b643503254b | note | Acceptance / Conformance Criteria - The sub-base compaction requirements in Table 2 of B/6 shall be replaced with a Mean Value ≥ 98% and Minimum Value ≥ 95%. - Direct transmission
227b8354-585b-5405-b88c-7c7fcdcfeec4 | note | Standard / Specification - PS - 7.3.2
f36eb166-000e-58bf-be19-f92bb30d703b | note | Verifying Document - IANZ NDMS
cd6f29e3-2a32-5b63-ab04-d66b4b185db8 | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
d9507bce-a48c-50aa-ab82-c8811ad35072 | note | Activity - I
58b68c5a-e4b7-5f89-a3b2-685edfa044cd | note | By - PE
4aa55dcd-a656-5a26-8180-ba5534462e9c | checkpoint | 6.04.18 - NDM Water correction
f071d565-d785-572a-922d-f08a064dbc0b | note | Acceptance / Conformance Criteria - Daily Laboratory water content tests shall be carried out on samples taken and used to correct the NDM measured dry density
2e044633-d7c7-5d9e-b5dd-dafff9d7c0bd | note | Standard / Specification - NZS 4407
836d50b3-7c26-50b4-baaf-bbe5282e1ec4 | note | Verifying Document - Corrected NDM Results
c8f85b5b-bbd3-5b8c-ab68-033d78da6733 | note | Frequency - Per Stabilise day
7e936f2b-4eb0-5b41-ab57-92180a1d77ef | note | Activity - R
83e332d0-a668-5154-84ac-e7fbc301bf14 | note | By - PE
ba631b52-5dc2-5c4a-87ff-800c5e357854 | checkpoint | 6.04.19 - Post Stabilisation Surface shape control, layer thickness
9526862f-91c5-5dac-95ad-70cd020f619e | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
6522fc0e-4196-5f03-afbd-9b75927f8d6d | note | • Vertical: - 5mm +10mm
f4863cc8-486b-5be9-a731-8bfa42984a1e | note | • Cross fall: 0.5% on 2m straight edge
6954ac89-9caf-5018-b91d-b28e25c03733 | note | Standard / Specification - TNZ B6 8.2
3daf20d1-728d-5007-97c3-0bb9105461f6 | note | Verifying Document - Total station Topo showing levels compared to design
d07c63a7-48c1-5be3-b5cc-1adac4534f34 | note | Frequency - Continuous
98fcf74d-8e60-596d-8907-88b9d7ef90f9 | note | Activity - R
bc888039-e7fd-5dc3-aee8-ae317a7d7b11 | note | By - SV / PE
eeb24f51-2626-5cc0-a95a-e896cb9f7dc9 | checkpoint | 6.04.20 - Protection, Curing and Maintenance before Overlaying
e92392ec-97c2-50e1-821a-33d79ed2472f | note | Acceptance / Conformance Criteria - The Contractor shall protect, maintain and cure the completed cement bound sub-base until the next layer is applied.
c8bc45de-bc79-5b30-864f-5bf260d7c2d1 | note | • Besides construction traffic required for the above curing no other construction traffic shall be permitted onto the layer within 7 days of stabilisation
e0059b71-6b51-5fd4-8250-d3218d19768e | note | Standard / Specification - TNZ B6 - 7.8
c2673520-0068-526c-b733-bd1c5e249159 | note | Verifying Document - Site Notes with photos
c4df2b91-2813-55d7-a6f8-582b3ae81f62 | note | Frequency - For 7 days after stabilisation
5b871b77-b3c3-5fbe-b180-46fc780076ee | note | Activity - R
565020ac-19d7-5868-a1ba-35b0f8e9edd9 | note | By - PE
8895530f-a026-5a64-aa6e-d3d4b0b121b6 | checkpoint | 6.04.21 - Benkelman Beam
70de7fe9-6b26-586f-899f-398eec09a3f7 | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer.
e954676f-2098-54d1-ab59-fe6251457716 | note | • Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY
68252c7e-3e47-53cf-bf1d-ef2c070c1ef6 | note | Standard / Specification - PS - 7.3.2
81139e68-a273-5646-81ae-6695ea090e1f | note | Verifying Document - Benkelman Beam Report
053563ae-5872-575a-8948-c0b3e4514eb3 | note | Frequency - Every 10m of each lane – staggered between left and right wheel path.
bdccd325-dd78-5064-9cc2-edf57d634663 | note | Activity - HP
93770925-a868-5d26-a5e0-1f1fd3e3eb92 | note | By - ENG
69352328-8f56-52c5-bce0-ccf55cf27bbb | signoff | AUTHORITY HOLDPOINT
42dd6dc9-09fe-578b-bfbb-13b10408700c | checkpoint | 6.04.22 - MDD / OMC / SD
2630dcc7-1a5c-52aa-a82f-67d5bf7350e1 | note | Acceptance / Conformance Criteria - Post hoe, stabilised MDD, OMC, and SD. 1 test per 2000m² or a days work whichever gives the greater number of testing.
173d78d7-805d-513b-b61d-766211856e8c | note | Standard / Specification - NZS 4402:1986, Test 4.1.3
290efdc4-fa23-54c6-85e0-bab5dc5134d8 | note | Verifying Document - Lab Report
44cbef68-a14f-5753-a329-5e07e7fc9006 | note | Frequency - 1 test per 2000m² or a days work whichever gives the greater number of testing.
b0f23bc1-17a6-5c33-b386-f2fee8d0dfe5 | note | Activity - I
fbe34ad3-62fb-5820-bbff-e6bdea491916 | note | By - PE
b4bfcba9-7ebb-50d5-ac19-ccbd0eaf5f97 | section | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
2c7daec9-a3b9-5141-9709-d474c280ddfa | checkpoint | 7.02.01 - Redline Drawings
e9831178-47b0-59a6-9d3e-db8fe82d67ba | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen mark up showing lot numbers and areas stabilised in different days including clear delineation of all joins.
42ae6479-0812-5f6c-9c07-a74a778776a8 | note | Standard / Specification - Downer
46a567d6-e788-5ef8-9b53-7728cb226c3d | note | Verifying Document - Redlines
52a691ee-b7b7-55cf-b940-d4a415e252dd | note | Frequency - Post construction
e23418a8-3819-5731-b4b1-40b53b1be0dc | note | Activity - H
c5e2fca2-dd50-5ce1-b220-2d2b1f521bff | note | By - PE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
a2ce095e-44dc-530e-98c0-2acd2202933e | checklist | ITP - Pavement Drains - Rev B | itp | ITP - Pavement Drains - Rev B
8c9335a7-3af5-5e47-a887-39a89ff08c27 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
f9f905ec-dac3-502f-bb0c-10f8858f0b9e | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
64202acb-dcc4-53ad-a7c8-b0edb777bdc3 | note | Standard / Specification - Downer
0e4649de-7aaa-5b42-b147-fc3af9edce0b | note | Verifying Document - Construction Pack
99e69b24-2ef8-559a-8b36-853cb81f4080 | note | Frequency - Submit 10 days prior to commencement of works
62f27ab6-cd9a-5e30-8824-fd5102c3dc6e | note | Activity - H
1c5f89a8-cb44-594e-9268-a2c140fb894e | note | By - PE
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
e8398258-2279-5bf9-a5b7-9ff664595e60 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
5816aeb8-9264-5828-b482-fe53c2cb6552 | note | Standard / Specification - Downer
f37c6830-756c-5cff-8a65-d31b68f3c4ba | note | Verifying Document - Survey Records
b09e40a4-5de5-5202-a114-0d8c5269a277 | note | Frequency - Prior to Works
ebc91c34-ab8c-5188-813c-aeae8fa3bcdf | note | Activity - H
ab80a7c3-9993-5b5b-bd1d-36bb7b2216d3 | note | By - SV
7b8b4071-ba18-54c4-a07c-9e192aec85d8 | checkpoint | 3.01.03 - Approved Construction Drawings
5dd3cf45-0f1e-5179-a129-76755e28ce4e | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
4986bf31-15c7-5782-b32b-ffc4e530cbcb | note | Standard / Specification - Downer
7091b149-f5f8-57d4-ba8e-474e7db85504 | note | Verifying Document - IFC Drawings
1fa87834-82d3-5a29-8c87-4ce1da32837b | note | Frequency - Prior to works start
d7a880fb-ee40-5de3-bed9-57e309c271d8 | note | Activity - H
ea67c3b9-7d45-549a-8fbf-e9469ca18927 | note | By - PE
f54e7b48-3f2b-51d6-93b0-54755388f0cc | checkpoint | 3.01.04 - Topographic surveys for measurement
3270d049-2f44-501a-8d00-f1ee3abb8282 | note | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
beb20a08-9dac-5a7a-8b7f-c9aa5fccf934 | note | Standard / Specification - PS 2.2.12
1c1d5108-bae1-5026-b409-4c885281efc6 | note | Verifying Document - As-built
65a51382-d93a-598e-8f98-972b6ebdbf49 | note | Frequency - Prior to works and Post Works
4749ceef-fab7-5f70-9251-d1ada48d7c50 | note | Activity - H
02840a85-27c0-527f-9ef6-145c8754fa88 | note | By - PE
f26fef48-d615-5889-ba64-e206f54c0d34 | checkpoint | 3.01.05 - Permits
50807822-529d-505b-a163-5260822af788 | note | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
90b6e93b-e6e1-58c0-9936-c6693972fc15 | note | Standard / Specification - ITP Register
536c9218-f180-54c7-bfd0-48076237f10a | note | Verifying Document - ITP Sign Off
04cc1cf9-2d9d-5bfe-98df-804c10b36d4a | note | Frequency - Prior to commencement of construction activity
06a73eb2-aa91-559e-8f70-68e42bc28d2a | note | Activity - R
c4bc4db5-753d-5597-954b-c24cf6203150 | note | By - SE
72a761a8-8bee-5916-91e9-a2f4ef42bc73 | checkpoint | 3.01.06 - Stakeholder Management
86a06a11-d37c-5901-a3c7-4170d371020f | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works, Agree plans for maintaining access to properties during construction with landowners
7f6c4578-84b1-5cc5-bf3d-44319a87a4ad | note | Standard / Specification - Project Stakeholder Management Plan
1e9ebef0-55a8-5fdf-b99e-a12ee2df4cee | note | Verifying Document - ITP Sign Off
5566c7d3-d686-5ed2-b4bc-0bc271c44753 | note | Frequency - Prior to Construction with continue updates throughout the works
68b35d31-4a79-5437-badd-6b93a5b58f90 | note | Activity - R
bc6f5e99-7b6b-57a8-8e41-e1d5262397a6 | note | By - SE
8ec62109-1664-5fbd-8086-47c125cee66d | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
82f0a14a-336d-5d73-b35b-b775632e4a93 | checkpoint | 4.01.01 - Pavement Pipes
96b1a7f1-85cc-5d66-b770-6f76866fd3c9 | note | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 100mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
0f69f95d-6aec-5570-9b13-d8eacf3060b2 | note | Standard / Specification - GWS 3.2.1
4434c9c7-43b7-5f1b-8b22-c4453c52bad5 | note | Verifying Document - Datasheet
754a3cf0-725b-5cd1-a08a-e2d078c31fe7 | note | Frequency - Prior to installation
2d7c460e-131e-5907-8d9f-1c8f104f048d | note | Activity - C
cac7a427-106b-5f9c-b5c7-e4a37b7aeb41 | note | By - SE
41e99487-aabf-58c0-8d33-87a5cdea2e96 | checkpoint | 4.01.02 - Pavement Drainage Aggregate (20/40)
3b6dca9c-61bd-5bc5-b686-03fbe0eeedfd | note | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/5 including gradings
2fae3c1e-3bfd-5ef7-9d9d-4dae40916943 | note | Standard / Specification - GWS 3.2.2 & 3.4
2b8f8a7c-4e73-59e1-83ff-4ef962505cf0 | note | Verifying Document - PSD, CR
af4c9b13-db0d-5519-aae1-62da809db0cc | note | Frequency - Prior to installation
eed3aa0b-0614-5487-9549-b87c73f1a53e | note | Activity - C
537db11d-3155-5bfb-ae34-d8a3c5ee89cb | note | By - SE
6d7192d6-9061-5d38-a315-d4a8752b3fa5 | checkpoint | 4.01.03 - Filter Cloth
d29b7dfc-b211-5b9c-9984-0ba0bf576307 | note | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings. (A14 Bidim or Equivalent)
28bad559-4928-5e5f-9f41-7122fcb75523 | note | Standard / Specification - GWS 3.2.3
43db19b4-f454-5c15-beae-a67d9cbde2bc | note | Verifying Document - Datasheet
e55becd8-4595-555d-beec-d2ea73ad571b | note | Frequency - Every 1,000m3. At least two weeks prior to works.
56a52d32-7c27-5128-b939-c78098c959da | note | Activity - C
6976b6dc-e081-5550-a1e7-0468e98a8f95 | note | By - SE
f4713bb7-3aea-5dca-b516-69272c0b56ba | section | SECTION 5 – CONSTRUCTION ACTIVITY
113d79bf-1485-508d-814d-8c7c8c221530 | checkpoint | 5.01.01 - Filter Cloth Wrap Inspection
9e165128-781e-549d-89fe-6ba0bca83d9d | note | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain.
75acbafd-f4b7-564a-8f2e-7e3b8e6175ac | note | Standard / Specification - GWS 3.2.2
2601e94e-bfc9-5ba4-9935-34bc6e32d41a | note | Verifying Document - Site Record
f1472b9f-081e-501c-97bc-997a7550c79a | note | Frequency - Prior to backfilling
574ae29e-835a-5d55-851e-15072719c473 | note | Activity - HP
2a1aa356-e8e2-5dc1-8a69-e3bee66a163c | note | By - ENG
a2a25648-08b8-5ac9-b1a6-269e329744a0 | signoff | AUTHORITY HOLDPOINT
543c766a-67a1-5508-b12a-a4f69b9927f3 | checkpoint | 5.01.02 - Trench Backfill
c32fb6b0-6d31-50b5-a9f9-b15ce15cb266 | note | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard of the material previously trenched through
a350e562-5565-563b-be45-c7de757f35e3 | note | Standard / Specification - GWS 3.3
eb589190-0764-5bd8-b196-ab9f89aeadd3 | note | Verifying Document - Site Record
ec64a5de-6292-5125-afc8-6e484dc921d5 | note | Frequency - Each trench
96223a88-c42f-59bc-8a2f-75d750191bf5 | note | Activity - I
0fe3e741-b0c9-5b4a-950e-675b8e7a8cb4 | note | By - SE
f7142f9b-2009-59fd-9453-67a19dd7865a | checkpoint | 5.01.03 - Drainage Outlets and Inspection Points
3c810906-ab97-5027-8b14-018bdbf84883 | note | Acceptance / Conformance Criteria - At least one temporary flush point is required for each pavement drainage system to enable flushing of the system once the earthworks are complete.
8625e483-70ac-58fa-a63c-5b505f19c155 | note | Standard / Specification - GWS 3.6
acf2d88b-83dc-5f64-9576-d0852ac6e813 | note | Verifying Document - Site Records
cdb25d2a-550a-504f-b06c-c084ae70a89e | note | Frequency - Each Subsoil Line
c9725a45-5a3f-5375-8852-34fce7841b01 | note | Activity - I
3fa79c56-5063-5667-b1ed-187effecba41 | note | By - SE
fd83d42b-b8ea-5d41-8883-9e6215d99eea | checkpoint | 5.01.04 - Subsoil Flushing
146b43a4-7c16-57cc-a6cf-da5fc2dc11fa | note | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer.
3dc5f9d6-6b7e-598a-bcf1-9ef49a626c66 | note | Standard / Specification - GWS 3.6
40597163-48fe-5bb4-abed-f49a4ab3f727 | note | Verifying Document - Site Records
81138943-d4c0-5721-8706-938fd6ea6c1e | note | Frequency - On completion of earthworks
77f50290-a8cc-5b36-8fbd-7ebde75092c5 | note | Activity - HP
80964aa3-b2e1-5303-8e6f-9b2b7f6e2b61 | note | By - ENG
efdabe6e-46f6-51c4-9707-34eb23acdd0d | signoff | AUTHORITY HOLDPOINT
65ee871c-3fae-5bef-8ed1-f015a6f0c4aa | checkpoint | 5.01.05 - Survey
83dfab8a-5f1d-5b7b-a954-59c2747642a3 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
6c26521b-8245-5d7e-b411-4c900816384e | note | Standard / Specification - Downer
2c583d67-eb6e-53d2-b2ab-3baa3432b8a6 | note | Verifying Document - Records
f17845ff-202a-5027-9bf4-c357176b925e | note | Frequency - Post construction
35f5336e-12df-51d7-be76-3fbfd57b0294 | note | Activity - H
00a72da5-033b-540e-8cfe-fd04d992fbb1 | note | By - SV
cd33a7f8-9b6c-5422-93be-dcae98eaa460 | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
abaa7cc7-67ff-52ad-ae9f-e9176b336a01 | checkpoint | 6.01.01 - Construction Record Compilation
94904fe6-c43b-559a-aef9-d0a9d69d2747 | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
76fe4fd9-d793-5a9b-9bb6-1ba89c817758 | note | Standard / Specification - Downer
41b86b8f-efcf-5168-92e9-5c3a7cbe723e | note | Verifying Document - Records
bf359400-b405-5c46-8907-c725b0286925 | note | Frequency - Post construction
c38a501d-bb9a-5874-b05e-cc342037f315 | note | Activity - H
4abd56a4-d3e0-50b3-b3f4-45abf498776e | note | By - SE
f4876821-e136-54ca-95e8-27fd0f400f5d | checkpoint | 6.01.02 - Survey Records
342e2dfe-333c-563c-ac47-bf2ad8809947 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
3ecd713b-e021-58a2-b407-73e34039e4c7 | note | Standard / Specification - Downer
f2c7697f-6ab7-5136-85d0-2c87cabad9fe | note | Verifying Document - Records
b8b21edf-472a-5f12-821e-5aa99e216de4 | note | Frequency - Post construction
c05c2993-8167-58db-91d5-a3321df9a3e2 | note | Activity - H
a58f2874-0112-5df0-af4c-ec4b73c7c8fa | note | By - SV
a7ece1a0-6b4a-5d51-8813-156cc41a337a | checkpoint | 6.01.03 - Redline Drawings
85b5a3e2-2bbe-5298-b838-18c0854aaacc | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
48e37755-862a-50fb-9b1a-5b2267c78356 | note | Standard / Specification - Downer
76233806-0448-5389-9e1d-3a92930e7685 | note | Verifying Document - Redlines
2d0fd7b7-749a-58dc-8dc7-75b5936b0277 | note | Frequency - Post construction
f3817025-ebd0-5ca4-a077-81025f6261cd | note | Activity - H
39ae6ec5-d5c7-5a26-9e5e-2bdfc068a03b | note | By - PE
406cc900-58d1-549c-813d-cb4c75c9a2be | checkpoint | 6.01.05 - Photos
03b319ab-784d-5a7a-a8b1-8411dd191456 | note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
da852884-2aaf-536d-9dcf-952353840ca1 | note | Standard / Specification - Downer
b08880c2-7512-5591-b327-dc150a36a882 | note | Verifying Document - Photo Records
0b59f7aa-0b29-5389-a957-c398d4254551 | note | Frequency - Post construction
2f5bb31c-dc18-5378-b91d-1fb9c4ec1d18 | note | Activity - H
f0e156ea-88a2-5ba3-9cbf-1dd50dce592f | note | By - SE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
8d9a0322-0afe-50c4-9984-8d9eb2d78320 | checklist | ITP - Pavement SIL | itp | ITP - Pavement SIL
3969119e-9d77-5427-b958-ecc82f083c46 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
4b26e7cb-ace0-58bb-a616-39483fc6b83d | note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence
39bdd60b-5a55-5725-9d44-67dc819f7e82 | note | Standard / Specification - Downer
f37b21b6-fe75-518e-99e7-441bb2e54568 | note | Verifying Document - Construction Pack
e20b4b8a-d1f3-5800-add6-1b620896d23b | note | Frequency - Prior to Works
2c256560-e7aa-55c9-98a1-86938a36f071 | note | Verification Activity - H
5aa00b7c-8cab-5b58-9c8a-a8ebcd4457f9 | note | Verification Activity By - PE
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
e3e94e95-7461-5602-8ae5-1f475a9a9372 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
a9ccfcea-23ab-5f83-98aa-01aa55f14f09 | note | Standard / Specification - Downer
bd924ba3-e98a-5a37-88f8-deb39c1915c3 | note | Verifying Document - Survey Records
21d5543a-b500-5bb2-b23b-7150daaf8fee | note | Frequency - Prior to Works
8155419d-e2cb-5987-8b90-4a5df3da5317 | note | Verification Activity - H
651d4ceb-5a87-5cee-aa2f-1d5af93f48ca | note | Verification Activity By - SV
a24a2c58-bf6f-5474-883c-40044bad1fc7 | checkpoint | 3.01.03 - Service Location
beea7a1c-046b-5fb7-91cd-46b86eb7ecfd | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
8c0340ae-3f3f-57df-8af6-8836db439d12 | note | Standard / Specification - Downer
eaababd1-32a0-5323-ad8b-8e999dafd51d | note | Verifying Document - Excavation Permit
558c19e0-5e33-5b6a-a931-c34e81e92a2c | note | Frequency - Prior to Excavation
85387089-5afd-5a2b-974f-78eb26637df0 | note | Verification Activity - H
33484b60-704b-5d44-8ca8-0d2f7803fb57 | note | Verification Activity By - SE
0a214a7a-124a-5898-a837-e29e83751df0 | checkpoint | 3.01.04 - Internal Permits
24c5b6b2-98a4-589a-a0ad-fa73c558e90d | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
f1ead7c5-425d-5829-b8d1-0edd0ebada26 | note | Standard / Specification - Downer
7bc080ae-d60d-55ed-9e48-c9efb7f6d7ce | note | Verifying Document - Internal Permits
f051067e-abc8-58c0-96b0-6932e794b31d | note | Frequency - Prior to activity being undertaken
518ffaca-a960-5750-b6b8-c85a4e56025c | note | Verification Activity - H
cfe1cce4-c9a2-53b0-9062-99d2666b7ccb | note | Verification Activity By - SE
917e2881-0901-542f-ae25-686bf9c47009 | checkpoint | 3.01.05 - External Permits
b2e25bb1-ceae-59ce-be7a-ac0fa86efbac | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
26281c77-fff7-5dd4-88f3-7e33e61e9cbf | note | Standard / Specification - Downer
fb232d0f-a63d-56c9-8cef-c489fe97494c | note | Verifying Document - External Permits
9e657bb1-bd49-5ffa-98e1-3b2ad9d187b6 | note | Frequency - Prior to commencment of activity
8037d5ba-0dd4-5d90-9102-4cba9dadd771 | note | Verification Activity - H
62198747-f56f-5a64-8a05-cde299bdfa49 | note | Verification Activity By - PE
a1302970-0389-558d-b43c-67b14bbfc27a | checkpoint | 3.01.06 - Approved Construction Drawings
bb46b8a2-0124-5764-b4dd-7bdf0e69e95c | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
f9faecd7-6ccf-5952-87fc-e7dc6b36747a | note | Standard / Specification - Downer
030bf603-8060-5f9d-9f7a-d5e4d6516677 | note | Verifying Document - IFC Drawings
73c5b094-94c7-5167-9ef9-037fd27c4209 | note | Frequency - Prior to works start
cefe589e-775b-5225-b22e-07aa1e40a577 | note | Verification Activity - H
434a1998-8714-52c5-bd16-87cddbd9fb72 | note | Verification Activity By - PE
5fe0af18-de1c-5a52-a24a-6d199c43ea87 | checkpoint | 3.01.07 - Previous Layer QA Sign Off
6983331f-cd49-553d-9d1b-2fb72a289629 | note | Acceptance / Conformance Criteria - All Previous layers signed off, QA complete. Including subgrade, SW, WW, WM. Ensuring everything up to the bottom of SIL is compliant.
915f2668-b583-53ab-a791-7764dde86a86 | note | Standard / Specification - Downer
77414674-0ef9-565c-bd1e-9e79630527df | note | Verifying Document - QA Records
f3a3f4b4-c411-555b-86c7-ecf46bcdf601 | note | Frequency - Prior to works start
c6466e5e-b003-544d-bb6f-6a7c079699e2 | note | Verification Activity - H
e1d16e4b-df18-54d6-933a-5129d5ba5833 | note | Verification Activity By - PE
f235ea97-6575-526f-981f-e1d053fa1d5c | section | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections)
7d5180df-d4eb-55e4-af4d-0e923a86f4b9 | checkpoint | 4.01.01 - SIL Inspection
589c641a-aa63-5852-9ee0-74bb69e89f17 | note | Acceptance / Conformance Criteria - Prior to placing of sub-base pavement, to include proof roll, inspection of extents of works, general shape, and tidiness, free of organic or contaminated material, review of Benkelman Beaming of the SIL and final levels.
63d5d160-5d5e-5d1c-8f98-de84fd1bffb8 | note | Standard / Specification - PS - 2.2.16
c3cb4613-e4f5-5cfc-b1af-22f8b68c2820 | note | Verifying Document - Hold Point Release
c154df35-5954-5684-b09e-81eb77940267 | note | Frequency - Min 48h Notice
af005a20-54f3-5277-886e-7af9e988939a | note | Verification Activity - HP
18fb0707-f3d9-5d50-af1f-10287369254f | note | Verification Activity By - ENG
22c63970-dca6-5fd1-8231-ea707288aa18 | signoff | AUTHORITY HOLDPOINT
62f939d2-18c6-5474-abaa-4e5cecc5daba | checkpoint | 4.01.02 - Subgrade Inspection
ccdd5453-ce4a-5556-99a1-e628c9df66ef | note | Acceptance / Conformance Criteria - Proof roll, Scalar penetrometers, and shear vanes prior to SIL fill commencing
4bc1e182-7aa8-55c3-b605-7ac285d42607 | note | Standard / Specification - PS - 2.2.16
d3d56a58-b3ff-5de8-80eb-b959f7028b02 | note | Verifying Document - Hold Point Release
daf11b30-c8b1-541a-9e0a-1f48878bd249 | note | Frequency - Min 48h Notice
3f765b21-ec87-5fc9-b2c0-516f6ba42d38 | note | Verification Activity - HP
54909fee-8367-537a-913e-c78a0b548259 | note | Verification Activity By - ENG
7ad2b75a-44c0-5e3d-b3c3-e0084f7839d0 | signoff | AUTHORITY HOLDPOINT
b3826b6c-de4b-591c-a488-5e8079ba2150 | section | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 Subgrade Materials
fcd729d9-871b-5ce2-b7a9-fc012a97901d | checkpoint | 5.01.01 - Pavement Subgrade CBR
b3e03a0d-8900-51ac-be82-923b82921d09 | note | Acceptance / Conformance Criteria - The pavement design requires a soaked CBR of not less than 10 within 1.0m of the bottom of the SIL layer and 4x DCP's to a depth of 1m below subgrade level in a 1m grid around the in-situ CBR test location and 4x NDM's DT with a probe depth of 300mm in a grid around the in-situ CBR location. CBR testing of the subgrade shall be carried out by the Contractor prior to final trimming. If the soaked CBR is less than 10 the Engineer may instruct changes to the pavement design. (Push tube for Cut and Filed sample for Fill). Invitation for engineer to witness CBR testing. To be accurate representation of site
8bc2d425-ceb7-5734-bb77-d28559cf4dd1 | note | Standard / Specification - PS 7.1
7a8b0934-9135-54fb-b2a4-e6b80a154256 | note | Verifying Document - IANZ Lab Reports
1086e7dd-eabe-514b-87d6-33b88e67f9b1 | note | Frequency - One test per 2,000m2, with a minimum of three tests per material type.
d8f0f437-a191-57db-ab63-ab5fa84405d2 | note | Verification Activity - HP
07eb9ac4-2f53-5c6b-9ec0-d3b5327d7a95 | note | Verification Activity By - ENG
93c1095a-43a9-5d7d-be8f-7a7cdce201a4 | signoff | AUTHORITY HOLDPOINT
fac294aa-8548-5fc8-bb58-2088ac62dc7f | section | 5.02 - SIL (Clean Pit Sand)
75e3c18b-3bc3-5384-a690-0b943edb28e2 | checkpoint | 5.02.01 - SIL Conformance
7b7cbf9c-e8ee-5e03-b9c4-19e9defd7ac5 | note | Acceptance / Conformance Criteria - The SIL shall be pit sand meeting the following requirements: · 4-day soaked CBR (NZS 4402:1986 Test 6.1.1): Shall be ≥ 30. · Organic Matter: It shall be free of organic matter. · PSD (NZS 4407:2015 Test 3.8.1): Shall be <7% passing the 75μm sieve.
ab9dc707-18c8-576e-aaac-433561430047 | note | Standard / Specification - PS - 7.2.1
68faef9d-392a-59d7-bcaf-6fa1bc1f1e4f | note | Verifying Document - Lab Reports
c4fedb90-397f-5d70-8393-ddd5f80bc3ef | note | Frequency - CBR and PSD testing shall be completed at the rate of 1 test per 2,500m3, and being no less than 1 test every 3,000m2 (placed).
2aa170d9-fa30-5034-aee7-9c13a2cf0362 | note | Verification Activity - HP
ff1df35a-76b1-5238-93f8-cfc823b7b0f1 | note | Verification Activity By - ENG
d189a4e6-f601-5569-9fc1-1d87e656f0fe | signoff | AUTHORITY HOLDPOINT
e318ec15-f915-557b-9af7-5c5cf6c32ccc | checkpoint | 5.02.02 - SIL Maximum Dry Density & Optimum Moisture Content
a27e8fb3-c719-5968-a595-666a016a330e | note | Acceptance / Conformance Criteria - The SIL shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density & Optimum Moisture Content
9401944b-e210-541c-9a33-a939c9d05c3e | note | Standard / Specification - PS - 7.2.1
008a0244-1f95-5a7a-9e8d-80305a50d1ed | note | Verifying Document - Lab Reports
05358614-5f37-5794-981b-b6ef430b82c7 | note | Frequency - 1 test per material type and no less than 1 test every 5,000m³ (in place)
0e569234-ac64-532c-a6a1-d7a30e8d6b76 | note | Verification Activity - HP
73f1f2dc-3ee4-55d4-a027-2e6d2c716e44 | note | Verification Activity By - ENG
efde04cf-22a7-574a-b477-9b8b7846f4a8 | signoff | AUTHORITY HOLDPOINT
5c6bf488-9018-5698-aa4c-b7cc685e8eb0 | checkpoint | 5.02.03 - Plateau Density Test
4d47d092-b781-5579-afbe-d0a041d3ac9d | note | Acceptance / Conformance Criteria - Compaction shall be undertaken using the higher of the two density targets. Plateau tests to be spread out evenly to be an accurate representation on what is coming into site.
3646b1f1-33f8-54ed-978d-3519e10c9441 | note | Verifying Document - IANZ Lab Reports
292f8656-46b5-5e25-9d81-b6c1be49f298 | note | Frequency - 5 tests per 10,000m2
cf700307-c8b6-5b85-8348-1951da8bab5f | note | Verification Activity - C
c2e994f8-60dc-5a5e-808d-82e1602f55ad | note | Verification Activity By - ENG
1cba0748-82d5-5f8d-9319-32091b6769d0 | checkpoint | 5.02.04 - NDM
a65fdecb-7522-5aef-8f72-c9c72775f831 | note | Acceptance / Conformance Criteria - Mean Value ≥ 98, and Minimum Value ≥ 95. All NDM testing shall be undertaken via Direct Transmission method at 300mm probe depth.
737f32a6-ca14-58fd-aea3-8aff714c61e6 | note | Standard / Specification - PS - 7.3.1
e55891f8-d0de-516a-b9c8-54ad6ca789e9 | note | Verifying Document - IANZ Lab Reports
df80991c-456f-5a22-94b9-66aea17bf2ea | note | Frequency - 5 tests per layer per 1,000m2
ddeea918-5e1e-53c5-bdb0-567b4a7edd31 | note | Verification Activity - C
fa4e54ea-eb3c-5011-b31b-85f88f881e0f | note | Verification Activity By - ENG
5c910787-b40b-5937-881a-26cc5ec60151 | checkpoint | 5.02.05 - Benkelman Beam
f1e57e77-c46f-5c32-a4b7-5c36a4a04f61 | note | Acceptance / Conformance Criteria - Target Benkleman Beam deflections on the top of the SIL layer are 1.6mm (90th percentile) and a maximum of 1.8mm
4f236964-6a78-58bb-a2ad-29ca204c836c | note | Standard / Specification - PS - 7.3.1
9af0f383-b583-5491-8e2a-112b9bbfe9b3 | note | Verifying Document - IANZ Lab Reports
f7a61f4b-00fa-5389-858d-3782c067994b | note | Frequency - every 10m of each lane – staggered between left and right wheel path.
70f2fcc9-b04d-51bc-a428-0e43ad15a03b | note | Verification Activity - C
e7ad119b-d74a-5d5c-b2d6-3a42d6de70a8 | note | Verification Activity By - ENG
937d3289-52f9-5ac5-8c90-59cd2914799d | checkpoint | 5.02.06 - Organic Material
b3e67920-8037-5400-8c1c-642e5ee8991f | note | Acceptance / Conformance Criteria - Ongoing visual and physical inspection for any roots/organic material, photos of clean sand, and any organic material removed.
a0c385bf-bf9c-5c1c-ac4e-583139a2d735 | note | Standard / Specification - PS - 7.3.2
936b6251-f4a7-5a3b-bf3c-24cba6f93080 | note | Verifying Document - Site Records, photos of clean sand, and any organic material removed
db82440f-7ec5-5382-8705-2ae2bae059b1 | note | Verification Activity - I
b5079f59-52f0-5920-ac35-007512183c86 | note | Verification Activity By - ENG
c269ea2a-2959-5cb8-b76b-38dd023d527b | section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.01 Construction
9b03c2bc-c48f-5466-8d4c-04b6d0c3c01c | checkpoint | 6.01.01 - Subgrade Prep
3314eb0a-8401-58d3-a782-af26e847ee14 | note | Acceptance / Conformance Criteria - The subgrade shall be prepared in accordance with the requirements of the Geotechnical Works Specification in Appendix B, including proof rolling, Scala penetrometer and NDM testing at the specified frequencies.
4832cdc2-16f0-54fb-b9f5-b13fd4db465b | note | Standard / Specification - PS 7.1 GWW
4d5bf8ee-a1ae-53dc-83a1-b890969d9705 | note | Verifying Document - Completed Earthworks ITP
81025f5f-e79f-5ae5-98f3-223c68ae7b80 | note | Frequency - Prior to Pavement Works
08eae87e-fbb1-52e4-abc1-c936b9f15f93 | note | Verification Activity - HP
531c5d6a-0940-5478-b658-d32ba101608b | note | Verification Activity By - ENG
e2d45569-ffc7-5edf-af41-be24dc51077f | signoff | AUTHORITY HOLDPOINT
565e4230-204c-5dff-9c26-c4b4d7ec8e26 | section | 6.02 SIL (Clean Pit Sand)
db9fd37d-3155-5bfc-a59e-7698b9c5a10b | checkpoint | 6.02.01 - SIL Scala Testing
dcff1fcc-0468-5c64-97ec-07f5bb15626e | note | Acceptance / Conformance Criteria - In addition, the SIL (tested in accordance with PS Clause 7.4 below) shall achieve a Scala penetrometer blow count no less than 10 blows/100mm. Depth to be 1.5m from top of SIL.
4163e9ea-e5a1-5798-9f16-4efc158777b9 | note | Standard / Specification - PS - 7.3.1
e34d2610-b9ae-5077-ba99-de1bc7d627bb | note | Verifying Document - Scala Results
9faf4a1c-754c-5fea-ade0-407e75652614 | note | Frequency - 1 test per 200m2
894e4cdf-7c9d-5780-a212-8b8d34c34071 | note | Verification Activity - I
7f61f95f-4eb2-5bcd-b43f-2b57f7050d3c | note | Verification Activity By - PE
e46181c1-7bbf-535b-8314-791da9fafd9c | checkpoint | 6.02.02 - Layer thickness
3f529307-5392-5a66-acbb-081265d82c69 | note | Acceptance / Conformance Criteria - Each layer shall be checked to ensure the required layer thickness is achieved of Maximum
0fa5048b-d270-5ea1-9593-a35fc1bbadaa | note | Standard / Specification - PS - Table 7.2 - 2.2 NZTA B/2
f5c571b2-b56a-5c59-8c5f-481204083b8b | note | Verifying Document - As-built data
5c79b190-c473-5a2d-9a81-4b6cf4384c9d | note | Frequency - 1 test per 20m
940c333f-fade-574e-82a7-6ece487ed079 | note | Verification Activity - I
da0419c8-3af1-55d4-a644-463ad1be3e53 | note | Verification Activity By - SE
1e0af15d-264a-5748-b80e-858ba1933f81 | checkpoint | 6.02.03 - Plateau Density Test
20cea371-9a84-570b-8d74-aa280094c8ab | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. Plateau tests to be spread out evenly to be an accurate representation on what is coming into site.
0aa05dd5-ffc9-504e-9a7c-60990433443a | note | Standard / Specification - PS - Table 7.2 - 2.2
51fc55fa-f4bd-5d31-af32-b4186c256bfb | note | Verifying Document - Plateau Density Report
0118de71-b76e-5cdf-8df4-d9032daf63dd | note | Frequency - 5 tests per 10,000m2
24168a1d-4d75-5639-b2fc-a4cbf8e189ca | note | Verification Activity - I
d016790e-e344-529a-93dd-38a52669b805 | note | Verification Activity By - PE
d963eff8-38eb-5e0f-8cb5-5ca02792d6bd | checkpoint | 6.02.04 - Sand SIL layer compaction
dfb1d2fa-07ef-574d-824b-bdc7ebddb7a7 | note | Acceptance / Conformance Criteria - Further to Figure 2 of NZTA B/2, the acceptance criteria for compaction of the sand SIL layer shall be a Mean Value ≥ 98, and Minimum Value ≥ 95.
80e7f2c7-ef44-58a0-a547-4edbf52dec16 | note | Standard / Specification - PS - 7.3.1
72f78430-a5d7-5df8-88f4-eb2aab833a7f | note | Verifying Document - IANZ NDMS
09a46328-eb63-5bf7-b4b2-789d16cf2ce4 | note | Frequency - 5 tests per layer per 1,000m2 (Min per lot)
aac1ee29-8af1-503f-a4ab-7102ea90cd06 | note | Verification Activity - I
b6d28b73-0c57-5903-886a-50e7c7b030f5 | note | Verification Activity By - PE
b7da25a2-1706-56d9-bf0c-ab152740d6a3 | checkpoint | 6.02.05 - Proof roll
07b326c3-ea68-549d-9128-c3000d49c9de | note | Acceptance / Conformance Criteria - The SIL shall be tested via Proof roll prior to Benkelman Beam testing. Proof roll to be under supervision of engineer and verifying document to be signed off by engineer.
f5e9d4dc-40e8-58cf-a4aa-b27c60255de8 | note | Standard / Specification - PS - Table 7.2 - 2.2
564d8205-b741-54d5-b073-d48e5d67d9c6 | note | Verifying Document - Site Notes
75ed5345-a8b0-52aa-bbc1-534c1cbcdb82 | note | Frequency - 1 test per 20m
e7f0260f-c6f5-50d7-84e5-50a351b4280e | note | Verification Activity - HP
61899164-dfe5-5bc3-b907-b5b068e82afd | note | Verification Activity By - ENG
8aeb4571-3694-52c9-a22e-a9dd129ae2d7 | signoff | AUTHORITY HOLDPOINT
a0785380-fd61-5bfd-8678-a44a68ec5f7a | checkpoint | 6.02.06 - SIL Benkelman Beam test
1474a3bc-5812-5d34-93c3-2a76dbcbc6d8 | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be carried out on the top of the SIL layer at the rate specified in PS Clause 7.4 and reported to the Engineer. Target Benkleman Beam deflections on the top of the SIL layer are 1.6mm (90th percentile) and a maximum of 1.8mm. Performance verification of these target deflections shall be confirmed by the Engineer on review of results from within the pavement Stabilisation trial (PS Clause 7.3.3).
04c2be5d-e694-5630-ae8f-3cd00f7c3b8f | note | Standard / Specification - PS - 7.3.1 PS - 2.2.16
b519543d-4049-5ba0-bd30-397138d05564 | note | Verifying Document - Benkelman Beam Report
2acdff5b-4e24-5f1d-87a6-475ceff0ac5b | note | Frequency - every 10m of each lane – staggered between left and right wheel path. Min 48h Notice
e4b7f0ea-806f-538d-9a07-d162c6b4f901 | note | Verification Activity - HP
62e03724-57d9-548c-9937-de3062eaf727 | note | Verification Activity By - ENG
3c89b0ec-4be3-513e-abf0-367c5d158a5c | signoff | AUTHORITY HOLDPOINT
10f025ff-7251-5430-bf3b-56f5dcf76850 | checkpoint | 6.02.07 - SIL Inspection
add1780d-3465-530b-bd7c-6b3040e3182b | note | Acceptance / Conformance Criteria - Before laying of any pavement SIL and metal courses. SIL inspection to be carried out under supervision of engineer, verifying document to be signed off by engineer.
aaa691c7-ddbd-559c-b7d2-ece1f6df8a75 | note | Standard / Specification - PS - 2.2.16
62109f41-cacd-5114-9387-f25dd7090a0b | note | Verifying Document - Hold Point Release
53749f59-1a97-5155-aa0f-01f9dede2b1c | note | Frequency - Min 48h Notice
8cf9b4d1-106e-5b75-8410-1d614ffa90d2 | note | Verification Activity - HP
c500ca95-c927-5ef8-8063-ff8836fab8fe | note | Verification Activity By - ENG
97bb6f89-11b3-5fc7-a453-48b0f0ec5d36 | signoff | AUTHORITY HOLDPOINT
9e953047-9f70-59b5-9189-aff3fc3bb70f | checkpoint | 6.02.08 - Topography
bb8d94d0-cad7-5b1c-8c9b-72bfccbba337 | note | Acceptance / Conformance Criteria - Carry out level check on trimmed SIL. Survey conformance with Total Station. Tolerance = -30mm +0mm (NZTA F/2).
dfea0969-3fe2-5fb8-b6e2-71a12b4b8f40 | note | Verifying Document - Survey PDF against IFC or similar
c4f76caa-a1e7-5193-a040-20aa641b2936 | note | Frequency - every 1m across the road (avoiding islands) at 20m intervals
9af73578-466b-5e6f-8458-cf20471145cb | note | Verification Activity - I
0f251313-de06-520b-8bad-69923864004d | note | Verification Activity By - ENG
b4bfcba9-7ebb-50d5-ac19-ccbd0eaf5f97 | section | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
8d4e531c-688a-5145-b348-98da13114f31 | checkpoint | 7.01.01 - Construction Record Compilation
e33b7f2d-364e-554c-bbc9-71565eeabdcd | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
02cb16d6-62a9-5c07-b1fd-9212d27af6d9 | note | Standard / Specification - Downer
d5242ce2-72cf-5b1b-93ee-f2289178affc | note | Verifying Document - Records
89f45c46-bd82-5272-9f96-7c18301858fe | note | Frequency - Post construction
e3b23594-8fa7-5800-9495-7772a6d9da38 | note | Verification Activity - H
1f3b92d1-88f6-5192-86a8-d876bfc05b8f | note | Verification Activity By - SE
19dccd2f-6441-5680-bbbb-459afb3e1dd8 | checkpoint | 7.01.02 - Survey Records
09ede6c8-4248-52cc-ab76-a1b266afc9e7 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
64e2281b-04ef-5dd0-a95a-ed86a87e480f | note | Standard / Specification - Downer
c7cbca71-5e4d-5ee2-9c7e-338c155a00cc | note | Verifying Document - Records
6bfdd8a6-0e45-5a32-b543-6abfceba1022 | note | Frequency - Post construction
b936ae2a-5b7f-575c-b00c-96f40edeb440 | note | Verification Activity - H
239d20eb-1cda-5151-8ee0-a1a37fa759ad | note | Verification Activity By - SV
b068bae6-2ef0-5d88-81c8-4fb6749be6b3 | checkpoint | 7.01.03 - Redline Drawings
4d55e902-6fc9-5949-bd90-3718360ae31b | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red line to show any increase in SIL depth.
92347465-5877-5da6-87bb-b262af7857d7 | note | Standard / Specification - Downer
9dcd9ed1-320f-5caa-9c10-bea4580085c4 | note | Verifying Document - Redlines
3bb64a96-941d-58a0-8054-c7df7e8a417b | note | Frequency - Post construction
34016d76-9cb7-5f99-ac70-5ccdd07ac80a | note | Verification Activity - H
dc0a719b-c026-5d33-b5c3-421f855beb57 | note | Verification Activity By - PE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
f3842a7b-be6f-5da3-a5bd-a81c87a9c4d4 | checklist | ITP - Piling | itp | ITP - Piling
e631fd1c-c7ec-5455-943c-2624fae3e7e6 | section | 1.0 Pre-Construction
6f43080d-629b-5e1b-8c1f-67f555a9f9e1 | checkpoint | 1.1 - Accepted Method Statement
62f24d58-7b8d-5c3c-877a-87b9c30bd50d | note | Standard / Spec Reference - Project specification
a0b5d7c8-4a0d-5607-8b54-315563f25d70 | note | Acceptance Criteria - Engineer’s acceptance
28af8229-fd5f-5619-8cd4-8a74166f2400 | note | Frequency - Once prior to commencement of piling
cdf61e20-5f96-5025-bb8b-a720e08c10d0 | note | Responsibility - CLL
42dbd898-35a4-5d93-9470-cbe81a90cfc2 | note | Hold Point H/W/S - DO: H
a1ec3af8-c244-5f77-86b8-956c98095f24 | note | Hold Point H/W/S - BBO: H
70b032bf-215e-54b0-aa18-0d92e380695b | note | Hold Point H/W/S - CLL: H
3c8ff899-625e-54c0-8499-92db7435fcbc | note | Verifying Record - Email Confirmation
4a44b871-e815-52b1-ad16-4142fb42906c | note | Comment - To be submitted at least 10 days in advance.
a2a0b4f0-e0f3-59a1-bad1-49d7ee3d895a | signoff | HOLD POINT (DO/BBO/CLL)
f4810438-62df-5388-8725-f411da743d4e | checkpoint | 1.2 - Accepted Inspection and Test Plan
2ce3b27d-4838-5fdf-8ea1-5777c3137557 | note | Acceptance Criteria - Issue
06dee5e8-d630-5c38-8931-a607754c1810 | note | Frequency - Once prior to commencement of piling
dc72a423-376b-5cae-937b-223b0a105f3c | note | Responsibility - CLL
0c173d62-8c26-58af-a7a3-39f4347d19c7 | note | Hold Point H/W/S - DO: H
3df5f23f-af35-55a9-9587-e32a590ad958 | note | Hold Point H/W/S - BBO: H
5f9fee3e-3c65-5efa-9192-259130cafef3 | note | Verifying Record - Email Confirmation
6d80a3a1-dc7c-5efb-8e5d-c48eccde4217 | signoff | HOLD POINT (DO/BBO)
3cc18b14-a7bc-537e-89b0-e7dddf8e0405 | checkpoint | 1.3 - Accepted Safety Plan - SSSP
ff600164-3277-50b6-94a3-86ea098289f5 | note | Acceptance Criteria - Issue
06052266-f1f1-54b6-a031-cb2d8e0c405d | note | Frequency - Once prior to commencement of piling
bf30a35e-ff8b-5b6f-9447-5647b88ecdf7 | note | Responsibility - CLL
97ebb5fd-1f19-5b3e-8f91-58c1104c5a15 | note | Hold Point H/W/S - DO: H
eca49034-bb54-5944-af21-bcd279d2168a | note | Verifying Record - Email Confirmation
f22188a5-0382-5eaf-80dc-15667845b3b1 | signoff | HOLD POINT (DO)
4168a7aa-2162-590e-89df-55c2652f1eea | checkpoint | 1.4 - Accepted support fluid details
9d9e6f8d-9bfd-52de-bbdc-1f7f1dc34fce | note | Acceptance Criteria - Issue
841f33af-4eb0-587a-88aa-b73cd866eb6d | note | Frequency - Once prior to commencement of piling
d5496b4c-34d2-531a-beb3-ae08c31d0301 | note | Responsibility - CLL
f3f25f47-92c5-56a5-b797-8c25e7eca7f7 | note | Hold Point H/W/S - DO: H
1aee7c34-a76d-50c3-8ffa-ed0ce8228d6c | note | Hold Point H/W/S - BBO: H
44f5d988-5199-51e2-bc00-c0aa67df1d6b | note | Verifying Record - Email Confirmation
8923a83b-3f93-5cbe-9157-af59ace73531 | signoff | HOLD POINT (DO/BBO)
ab8845fe-974c-5c2d-b7ba-bd306b249cc1 | checkpoint | 1.5 - Permits issued
33d41727-c9f2-5083-9bd9-49bba94dbb0e | note | Acceptance Criteria - Issue
4c345aab-e5df-5b13-a11f-0b728c28b7e9 | note | Frequency - Once at commencement of piling
fb36ee4d-02af-585e-889c-13435199ceda | note | Responsibility - DO
439a55e4-8990-5dd9-9727-13cdb6f987e9 | note | Hold Point H/W/S - DO: H
57a2c843-280f-5427-9e97-d1a4df1a33ad | note | Hold Point H/W/S - CLL: H
296af5e8-e172-5439-9015-be08147b2c9c | note | Verifying Record - Site Hardcopy
8f136149-2587-506a-bba1-6e1440bb081d | signoff | HOLD POINT (DO/CLL)
1fe8a6a6-7cd8-5282-b2be-5498e29c032a | checkpoint | 1.6 - Concrete Design Mix Verification
9fe70b6a-6f02-56e1-bb40-4a94473b735a | note | Acceptance Criteria - Issue
9cc52df2-2af2-5401-94e7-bf56e94fb584 | note | Frequency - Once prior to commencement of piling
942686fb-326b-5357-831a-0ea14c4b61de | note | Responsibility - DO/BBO
7ad59786-5dd0-52fd-81bf-5124f748ce8f | note | Hold Point H/W/S - DO: H
7a6a55e0-45ce-557d-9deb-ec74e6509fef | note | Hold Point H/W/S - BBO: H
6882a143-762d-5a98-8b9f-902ff910d6af | note | Verifying Record - Email Confirmation
b1b80037-1c57-587f-b42e-6fb24abbe9b2 | signoff | HOLD POINT (DO/BBO)
3345c9ea-7673-503d-8d45-f0719eecd85d | checkpoint | 1.7 - Reinforcement Steel – mill cert
f6de07d6-4d18-5c75-81da-f08f6fb541bd | note | Acceptance Criteria - Project specification
141b17c5-9fc2-586b-9410-b96125cc12a9 | note | Frequency - Post Construction for every pile
b80a6d66-54c7-55bd-95eb-f59fff342051 | note | Responsibility - CLL
cad41ae2-3493-53ae-b614-f1959efe03f1 | note | Hold Point H/W/S - DO: H
d26751fd-462b-5396-a946-21163b38326a | note | Hold Point H/W/S - BBO: H
02860350-2e3b-59fb-83e4-62c11e383e7e | note | Verifying Record - Issued by supplier - email confirmation
76f84977-d7a8-5150-8552-80556ac814f1 | signoff | HOLD POINT (DO/BBO)
1b04b2f5-a1f9-522d-b749-815e5b9edc57 | section | 2.0 Pile Boring
3b4421f0-8da0-5669-a934-aed355ded325 | checkpoint | 2.1 - Client Notification
127d74af-39ee-57b4-a28a-8cf89457a511 | note | Acceptance Criteria - Issue
49626cce-3ba4-5b4b-8e30-da4c6b2583bc | note | Frequency - Once at commencement of piling
17ffa176-be6e-5b07-ba5c-b7dd57754998 | note | Responsibility - DO
130ab38d-2a4f-5193-a58a-f7e4a2988b03 | note | Hold Point H/W/S - DO: H
f3b265fb-d836-5d1f-8d1c-866a9f0de264 | note | Hold Point H/W/S - BBO: H
21e632d0-2534-530c-871b-2a9bdf651709 | note | Hold Point H/W/S - CLL: H
77455024-dec7-509f-b8d8-de5cf34c0984 | note | Verifying Record - Email Confirmation
fdb7c117-096d-5971-a534-fcbd3b2e8936 | note | Comment - 48 hours’ notice of pile drilling commencement.
c5c2169c-5bbc-5c8b-acff-03bb7d0a17e1 | signoff | HOLD POINT (DO/BBO/CLL)
d71966cd-c8cb-57dd-bbdc-0ab16870f1b7 | checkpoint | 2.2 - Check drill tool diameter
d89977b4-e455-589d-bda2-95d41c40471b | note | Standard / Spec Reference - As per HCC 1298/2022
02263750-9fb4-5713-9e34-ab9cc0be1904 | note | Acceptance Criteria - Visual Inspection
84df2b0a-dbe3-594f-aad1-ec57437387ad | note | Frequency - Prior to commencement of piling
6df99fc9-0967-5811-acba-87a73fc2c335 | note | Responsibility - CLL
2933e753-6f07-5d06-8e7a-e42ae959ac36 | note | Hold Point H/W/S - DO: W/S
393df755-3739-5884-9e6c-94e1f8fadaea | note | Hold Point H/W/S - CLL: W/S
0d6ee654-a922-56c2-8592-9d75ffecf944 | note | Verifying Record - As per pile QAC
6d6df6d9-b3b8-519c-b879-061a4b65ada3 | note | Comment - Minimum agreed diameter is 870 mm for 900 DIA piles, due to ID of permanent casing supplied by DO, and 1200 mm for 1200 DIA piles.
87eb682d-76bd-5714-83ed-ade24669de4e | checkpoint | 2.3 - Check depth gauge/instrumentation of piling rig
d6a54a60-5171-50d0-a2fb-bbf927dcb062 | note | Standard / Spec Reference - Operators Manual
065bc6b8-60ce-578b-af89-e217a11acdcb | note | Acceptance Criteria - Visual Inspection
a2d08314-7d81-5714-80c3-c8f1bc580566 | note | Frequency - Daily
db42a45b-c24c-5d96-bbde-0abc33e268e1 | note | Responsibility - Rig Operator
99da9c5d-0d27-543e-a1bf-2f05b9b06576 | note | Hold Point H/W/S - DO: W/S
740ec1ab-51f6-5ac2-900f-93198bfac9d9 | note | Hold Point H/W/S - CLL: H
a31142ee-a7b2-52b4-972f-ffc06e078136 | note | Comment - Operator daily checks
033d1e71-1a92-5ccf-b696-c15bf3e46633 | signoff | HOLD POINT (CLL)
0ed639e4-eced-56cf-be4e-1ccfb7dcf320 | checkpoint | 2.4 - Ground penetration and extraction with due diligence
f8c37aee-8bcf-566e-a8f8-a9904e57e933 | note | Standard / Spec Reference - Operators Manual
8d566718-caad-5858-81ad-cc6ea83eaf2d | note | Acceptance Criteria - Visual Monitoring
0a48287b-b7a0-5a5f-9fa3-bc09c323b0aa | note | Frequency - Every Pile
356f007f-dde7-5250-8a44-73fe0a500963 | note | Responsibility - Rig Operator
ee6e25eb-084a-523b-9584-20acecc2b8e1 | note | Hold Point H/W/S - DO: W/S
b3f2d9ff-8a74-5efe-9170-f5230537c108 | note | Hold Point H/W/S - BBO: S
8886fd93-785d-5ce6-9209-95c655a90763 | note | Hold Point H/W/S - CLL: S
ea32cdba-2701-54b6-9e29-f89140d2a1e9 | note | Comment - Operator to penetrate/extract with due diligence, no adverse effect on bore integrity.
ba64cb2c-ed2d-5c10-98dd-3ebdaf61f7c6 | checkpoint | 2.5 - Check pile position/pile numbers
cc8a5683-4085-548b-a06d-f7650d7005d9 | note | Standard / Spec Reference - Drawings
92a5ffa7-ae71-57cc-85b8-cffec705debf | note | Acceptance Criteria - Visual Inspection
2cef91b0-b80f-5093-8153-34079e147fb8 | note | Frequency - Every Pile
476f8d0a-1369-57ff-88e7-0f0ac2ec346e | note | Responsibility - CLL
ed3b6a51-fe04-5388-8892-b10ac93febc3 | note | Hold Point H/W/S - DO: W/S
c59e9228-3d42-55b0-a461-1f58e181c916 | note | Hold Point H/W/S - CLL: W/S
4944f1a3-446c-519f-bcd5-33fafc434a70 | checkpoint | 2.6 - Pile Setout/Offsets
5265d5f9-82d3-5dd6-9a58-f8eff57c8283 | note | Standard / Spec Reference - Drawings
f24a2128-74bc-5847-8af6-c497eeafbfa7 | note | Acceptance Criteria - Hz +/- 10mm
7c7906c8-387d-5188-9b49-236c00fa0047 | note | Frequency - Every Pile
8e098ff8-97b2-5f13-ab15-adcf0b176acb | note | Responsibility - DO
84f8b9a2-ac2c-5ebd-a7ca-4c37f2f7bdb6 | note | Hold Point H/W/S - DO: W
00f62530-9241-5485-bf60-6e174363a69d | note | Hold Point H/W/S - CLL: W
d425f2f4-e41d-532b-b7f6-71474f6300f4 | note | Verifying Record - Survey record
d29e8f1c-a503-5d7b-a47b-10953ba557eb | note | Comment - Due to tight plan tolerances set-out is critical
dd2ba2e9-7691-5018-a2f9-d42a13ad30c1 | checkpoint | 2.7 - Casing Inspection
b1d70420-7211-5b5d-a523-795c11cee7fa | note | Standard / Spec Reference - As per HCC 1298/2022 – note minimum agreed diameters at ITP item 2.2
2a09fa2c-6c38-537f-88a4-0b7f4d770363 | note | Acceptance Criteria - Visual Inspection
1e31b424-6d87-54fe-95c5-21c32676d495 | note | Frequency - Length/diameter/Wall thickness at start of piling, RL every pile
19666f1f-b9e2-5641-93d7-5a1a94cf3d38 | note | Responsibility - CLL
d7248886-5235-5b47-938a-355fca0b2588 | note | Hold Point H/W/S - DO: H
27468874-90c7-5246-bae6-faccfa31dcab | note | Hold Point H/W/S - CLL: H
a34bd4c1-a19f-5bb3-9e49-e017835f383b | note | Verifying Record - QAC - Pile Card
3ac82270-8df9-5a7a-af3e-2ded1a6f9e18 | note | Comment - RL check pre-concrete & pre- drill
d2b56091-a501-532b-a85f-bc1ae59b9bec | signoff | HOLD POINT (DO/CLL)
e7f79d2b-ba69-50e2-b1de-bb90f8c43187 | checkpoint | 2.8 - Measure and check position and verticality
23eddc2e-82ab-516b-92d0-61bbdcfeecfd | note | Standard / Spec Reference - As per ASGPILES - Rev G
38af7733-fcbe-538e-ae27-d87df6ad910a | note | Acceptance Criteria - Visual Inspection Permitted deviation from vertical shall be not more than 1:75 or 0.8 degree.
f96ea33d-aa2a-5392-8fcc-36c22987bf7f | note | Frequency - Every Pile
f89ccee3-f773-50f8-80e1-ba63b89582f5 | note | Responsibility - CLL
1bcaf796-ce95-5492-b124-fd429a98dfdf | note | Hold Point H/W/S - DO: W
f2a11210-b84a-5872-8699-0eae8aeedcd2 | note | Hold Point H/W/S - CLL: H
145715cb-ad7b-58c5-8371-d3a2c6719f7d | note | Verifying Record - QAC - Pile Card
69c0eac7-e7d5-504b-aba6-266beb30f2f6 | note | Comment - Spirit level has a +-0.5 degree accuracy. Verticality of pile to be checked via use of electronic level on the side of the casings & against Kelly bar.
0f8b87af-1047-55e7-ad3c-846f0598b540 | signoff | HOLD POINT (CLL)
71c7c42c-6155-5afd-9bb2-efa351147076 | checkpoint | 2.9 - Bentonite checks
062d9b9d-4b1d-56b5-9efd-059c3b888bec | note | Standard / Spec Reference - Fluid Specification
5fe673aa-6ab8-5bb8-af0d-76175afc840c | note | Acceptance Criteria - Visual Inspection/Testing
86b6f252-d5b4-5f79-80ac-39e90ae7c1b9 | note | Frequency - Per batch, each pile prior to concreting
dc20cc6e-41b5-5948-a9f3-0d2a2b13cefa | note | Responsibility - CLL
4d57e3db-de1d-56e9-9095-d4f971652c07 | note | Hold Point H/W/S - DO: W
fccbd892-06f0-5f86-97c1-e84026cf31b1 | note | Hold Point H/W/S - CLL: H
80030517-2764-5cfb-98fe-42a66de35365 | note | Verifying Record - QAC - Pile Card
fba28799-ccbc-57df-8746-229dcebbe296 | signoff | HOLD POINT (CLL)
b45c7ad1-0ee0-5790-a39a-8764545e3d10 | checkpoint | 2.10 - Bentonite level
7110409d-ae16-5282-86de-3aa5ca979499 | note | Standard / Spec Reference - As per construction specification - Methodology
aada31d1-5145-5d1d-96f4-e39f66fd25b4 | note | Acceptance Criteria - Visual Inspection Bentonite head to be maintained at 0.5m above groundwater level or adjusted as required.
6a7aaae7-3195-5b64-9426-50157cf84b48 | note | Frequency - Each pile
6b92b846-b8e7-5b82-8593-683a180e5ef0 | note | Responsibility - CLL
ea1f1680-0813-5a0b-8b60-50e9e28c2657 | note | Hold Point H/W/S - DO: W
28a4502f-6369-56c9-bf97-85320653eacf | note | Hold Point H/W/S - CLL: H
99e7656a-56b5-587f-8b3f-d755d44ad5cf | note | Verifying Record - QAC - Pile Card
e22b5738-9a18-534e-931c-ee4065ed4aaa | note | Comment - Any significant fluid loss/stability will be addressed with Project Engineer.
c410c9e4-c988-52bc-894b-68478bbbacde | signoff | HOLD POINT (CLL)
3c73a5eb-731d-5cfe-9e84-556300112151 | checkpoint | 2.11 - Soil logging and bagging
05a5cf28-2374-5f59-9c31-3616a8a99710 | note | Standard / Spec Reference - As per HCC 1298/2022 11.7
fbd76925-eca8-59d2-a939-d88d07abe294 | note | Acceptance Criteria - Visual Inspection Engineer Inspection
0a151c42-9cdf-530d-bee4-76c07ab75bf1 | note | Frequency - Every Pile
7356630e-687f-5d18-a2bb-5d85ce4ea06c | note | Responsibility - DO/CLL
1702070a-6cc6-5e5c-b0ef-d303f17de8fc | note | Hold Point H/W/S - DO: S
643415d9-95d7-5382-a7c1-9e4fab189209 | note | Hold Point H/W/S - BBO: S
2d8e6ed3-f642-558f-8257-536dd4a3f482 | note | Hold Point H/W/S - CLL: S
eb6034dd-7c82-5fbc-9d02-e8f393445fc1 | note | Verifying Record - QAC - Pile Card Labelled, bagged core samples
f1fdf6c2-d77c-55c9-a0ef-1e61e7398409 | note | Comment - Boreholes are to be continuously logged on QAC - Pile Card. Material from the base will be bagged, labelled and securely stored on site for Engineer’s inspection.
e7b4547d-122f-538b-80fc-c8ba34fb4010 | checkpoint | 2.12 - Confirmation design minimum toe depth achieved
f50e9dec-3595-5314-ae00-dd46e1835e51 | note | Standard / Spec Reference - Construction Specification/ Drawings
adb9a044-27ee-5b93-afda-4c2160bd656a | note | Acceptance Criteria - By means of weighted tape Designer Hold Point: Maximum depth exceedance
b0040e5d-93ff-57bb-9c57-0322b1aa89c1 | note | Frequency - Every Pile
c3fdff0a-1bf1-5832-a0cc-5d34b56ba509 | note | Responsibility - BBO & DO Rep/CLL
545a7558-dd79-53b1-b2af-9bac40f9f4db | note | Hold Point H/W/S - DO: H
6544d048-4b5e-57ee-9cd1-d0d118c09b42 | note | Hold Point H/W/S - BBO: H
90620fbf-5ac0-5b79-a5c2-f951fd7f12ba | note | Hold Point H/W/S - CLL: H
2a3ddc38-bb98-51d1-98e0-68311e26d69f | note | Verifying Record - QAC - Pile Card
35ac5247-116a-50fd-a332-d2212b87d98a | note | Comment - Visual inspection not possible due to drilling under fluid. Engineer to agree correct drill depth. Designer to be notified if drilling reaches >300mm below design RL for pile toe. Maximum depth exceedance to be 40m from piling platform.
c5835909-1009-5ddf-a0e1-5fe7560b622b | signoff | HOLD POINT (DO/BBO/CLL)
1466b6ea-8333-5218-bacb-d052d88fcf46 | checkpoint | 2.13 - Base cleanliness
e1f9cbcd-2a01-5ebe-bb7c-269e23ae51e1 | note | Standard / Spec Reference - Construction Specification
82257d50-4b95-5b95-9d48-328d7f1c16da | note | Acceptance Criteria - By means of weighted tape
ee5d6323-0a66-52d8-9bc0-e825aa8ff225 | note | Frequency - Every Pile
30bdf695-1094-5aee-9fb2-eca1e3b47259 | note | Responsibility - BBO & DO Rep/CLL
98e336f8-cdf7-55c4-b3bb-cde97b83c563 | note | Hold Point H/W/S - DO: H
c3bd29d6-5ba4-537b-bdb1-ad8279ec335b | note | Hold Point H/W/S - BBO: H
8fbb5c9f-d190-5f21-bd03-c9ce09194916 | note | Hold Point H/W/S - CLL: H
6457918b-7bef-52a5-b94f-5d9dd88a9dc1 | note | Verifying Record - QAC - Pile Card
09fa7eea-a4cd-5d30-b66d-1618849fd90d | note | Comment - Visual inspection not possible due to drilling under fluid.
b804ed3e-bce8-5f15-9c80-14c4ce8663a8 | signoff | HOLD POINT (DO/BBO/CLL)
c2746085-9a50-522a-b189-9a0ffe6773c6 | checkpoint | 2.14 - Pile Boring Monitoring
da5690c2-364c-54ba-b5bb-c44b04b0d497 | note | Standard / Spec Reference - Construction specification
a6065435-836f-5a15-8633-d9964351b9cc | note | Acceptance Criteria - Visual Monitoring
f6f28ca6-10a8-549b-888c-201999d02812 | note | Frequency - Every Pile
3a3807e6-8ce3-5acf-97a5-9c3a73876454 | note | Responsibility - Rig Operator
9b483e89-f254-5424-99b4-94ba331da17f | note | Hold Point H/W/S - DO: S
e4e7c507-d7e4-5582-849a-f80b0dcf2c7a | note | Hold Point H/W/S - BBO: S
6a180e2b-611a-5e21-be53-009e8f2c2989 | note | Hold Point H/W/S - CLL: S
6eb9b0f5-7f5c-56ba-b44b-618e668925ae | note | Verifying Record - QAC - Pile Card
66c0ec2a-e112-57cd-bd96-8583d38bf0c4 | note | Comment - Depth check, possible collapse, changing ground conditions, any unexpected occurrences
7c935674-82a6-53c3-b3e8-df3abc90f83c | section | 3.0 Pre-Pour Inspection
d953a050-a6b7-52ae-9001-6d8f111ca051 | checkpoint | 3.1 - QA check on previous pile
d9ffa3b0-f2fc-5ffb-856b-d9d0845faecb | note | Standard / Spec Reference - Engineer Specification
9a7315d4-da70-50ea-8600-34cee05752e2 | note | Acceptance Criteria - Client notification/Engineer’s Approval
dcefb148-106b-5e4f-8706-4172893e6f2c | note | Frequency - Every Pile Ongoing Engineer’s approval
e8801f3e-fb09-57f6-9efc-2d002ec58f1d | note | Responsibility - DO Rep/CLL
da467a95-7061-5faf-9080-31eea866c4a1 | note | Hold Point H/W/S - DO: H
ffd50456-cf6e-5bb2-beed-fbf83ed7e06a | note | Hold Point H/W/S - BBO: S
66620fd5-c1e0-54d9-9de7-342197c68564 | note | Hold Point H/W/S - CLL: H
9063f978-984c-53db-958a-bd6fe16cbb1c | note | Verifying Record - QAC - Pile Card
91ce59a3-8964-5126-94c0-09cb8f71bdf3 | note | Comment - Engineer’s approval to proceed with subsequent piles
bffddf96-fcf5-5cc1-b267-facf012d0f6e | signoff | HOLD POINT (DO/CLL)
434d2641-9e45-551c-a35a-2d7e12dde700 | checkpoint | 3.2 - Reinforcement Cage inspection/ check spacers, pile bore tolerances
32332388-f3b4-55a2-9d5c-c08b1c59ed2c | note | Standard / Spec Reference - BBO SS 2110 Rev 9
48b7e1b9-800d-56cf-83a8-c0e4f9770b27 | note | Acceptance Criteria - Alignment lesser of +- 4% DIA or +-75mm
d5540b5f-3471-5520-9228-6539eb73f067 | note | • Height +- 50mm
e72c4a70-0261-5b44-9219-ded85717bbf0 | note | • Reinforcement Type- As per drawings
553844e0-efd1-5c21-8bfe-bf0e46735eb0 | note | • Concrete cover: 75mm, 50mm minimum
ec2f10f5-139d-59cd-ad7c-18817e2a9d83 | note | • Bottom of pile position lesser of +-1% pile length, +-12.5% of shaft diameter, or +-400mm
0377f0a6-1588-5155-80df-064446b2858d | note | Frequency - Every Pile
b2c5375a-93e3-5631-bb55-b566d619b2bf | note | Responsibility - DO Rep/CLL
edc040f2-1b2a-5360-b2fe-f9d6b91be355 | note | Hold Point H/W/S - DO: H
c2ad4d47-631d-5ab3-8369-f005614c714b | note | Hold Point H/W/S - BBO: S
08169f5b-32ca-5a6d-9a2f-c323e831759d | note | Hold Point H/W/S - CLL: H
b7c36495-da2e-5fca-ba1f-b0783430ad08 | note | Verifying Record - QAC - Pile Card
818a252f-b1d9-5349-a139-880703f85f88 | note | Comment - Pre-installation check required of all pile sections
f2892bd9-85b7-5ec9-bb7a-a768688b39dd | signoff | HOLD POINT (DO/BBO/CLL)
b65f5ce9-fc79-52d9-84a7-91d525dbe893 | checkpoint | 3.3 - Stabilising Fluid Verification
5db9a565-4b7d-520a-ab7a-5002ffb8ec92 | note | Standard / Spec Reference - Construction Specification
61003af8-6099-572f-878d-f618d906d86a | note | Acceptance Criteria - <4% sand content acceptable
96895dee-5600-5b2f-899a-5649edfadb0d | note | Frequency - Every Pile
1b730cb4-d0e4-5279-aabd-d0ae4e97bf0c | note | Responsibility - DO Rep/CLL
5d5d8ccd-c809-5a56-b041-88f09e37347a | note | Hold Point H/W/S - DO: H
abe3398c-d030-5b8b-89e8-32292c3e894f | note | Hold Point H/W/S - BBO: S
17422081-e128-5f7e-af79-f85ad3432e47 | note | Hold Point H/W/S - CLL: H
e042cbd3-73aa-5b5d-a1bf-188e90bb416b | note | Verifying Record - QAC - Pile Card
03377fca-a7c5-560b-9e9d-b131a800afa7 | signoff | HOLD POINT (DO/CLL)
e552fec4-73ee-5d9d-8552-4914d74ed513 | checkpoint | 3.4 - Pile cage installation
c14f16e2-c6e0-5fe2-9a6a-c08be4f34bed | note | Standard / Spec Reference - BBO SS 2110 Rev 9
a366130f-a6ec-5928-b165-74f227cf6450 | note | Acceptance Criteria - Engineer Inspection
2f85f743-0569-5391-804e-03a846d65820 | note | Frequency - Every Pile
2ffb28ec-ad8b-5994-8c3c-8cd898a3b850 | note | Responsibility - BBO/CLL
d2f62d4b-a998-5546-84f9-cfe0f3c21dc2 | note | Hold Point H/W/S - DO: H
c4c98d6c-9521-536c-9071-c2245c4f36df | note | Hold Point H/W/S - BBO: H
b7c7ccec-7d4f-5066-a1aa-488ab9fa68e4 | note | Hold Point H/W/S - CLL: H
d282ff52-af4e-5eb2-a129-3fb0d079f068 | note | Verifying Record - QAC - Pile Card
5d35f620-2870-5913-9055-a5c03c33d726 | note | Comment - Pile cage to be installed immediately after Engineer inspection and acceptance
a878fc0a-6ed0-5f22-9c93-439cb5fcd982 | signoff | HOLD POINT (DO/BBO/CLL)
8ca18c17-4604-5af4-989a-cfc9ac9338cd | section | 4.0 Concrete Placement
23df560f-8d0b-581e-9bb5-fdeae8a124e3 | checkpoint | 4.1 - Verify Concrete Mix – batch times, mix
987a0787-d2b3-5b07-9263-e7e9494c1061 | note | Standard / Spec Reference - BBO SS 2140 Rev 5
103db8b0-60cb-5751-9268-1b15d271c6b0 | note | Acceptance Criteria - 401T4504R
2be52e69-9efb-5473-8caf-f9bc414ab1d7 | note | Frequency - Each delivery
33819dc0-5bb9-5115-88db-863b5140a336 | note | Responsibility - DO Rep/CLL
d23d2690-5722-5931-b595-fee021a5f480 | note | Hold Point H/W/S - DO: W/S
43bd3a62-328b-5f77-a0cb-b0132d6b601a | note | Hold Point H/W/S - BBO: S
a4459d03-2dc6-5823-a5ba-cd9e516f3176 | note | Hold Point H/W/S - CLL: W/S
f8d935ff-2af5-5d7e-b866-f9d9e2dbeae4 | note | Verifying Record - Concrete Docket
78485264-f0e4-54b8-ac4b-477c6df97791 | checkpoint | 4.2 - Slump/ Spread test
fa08a831-c5de-53eb-9558-6f592339dead | note | Standard / Spec Reference - BBO SS 2140 Rev 5
45987288-bffe-5d95-8ebe-2a340eccaec8 | note | Acceptance Criteria - Slump 100-130mm +- 25mm
dbe3811c-1311-5d5f-a209-c1cd9ff2821f | note | • Spread 500mm +-100mm
2415bb64-12b8-5cfb-ab35-82ebf82ed75f | note | Frequency - Each delivery
80f8af05-ec45-587d-a244-c2ed7ba804fd | note | Responsibility - DO Rep/CLL
d5b5124b-2f99-50ca-9008-15ff5672228e | note | Hold Point H/W/S - DO: H
689c9610-76fd-5b70-9a87-5b00a6e3df64 | note | Hold Point H/W/S - BBO: S
61c250cd-15f7-5e49-91ae-e4c2264ed653 | note | Hold Point H/W/S - CLL: H
85ef6231-6847-5b11-ab6e-38c97f93da77 | note | Verifying Record - QAC - Pile Card
a961e012-3d81-537c-b38d-db8d73cea422 | signoff | HOLD POINT (DO/CLL)
9fba1f14-cfc3-5695-b685-e4690fd1364f | checkpoint | 4.3 - Concrete level
cf5c32d9-8b2e-5212-87e3-a22f3b3a6b60 | note | Standard / Spec Reference - BBO SS 2140 Rev 5
616a5865-4d49-5b8f-90bf-938f9945c06f | note | Acceptance Criteria - Design +50mm
d1462899-cdaa-5978-924c-52b8512a87a9 | note | Frequency - Every Pile
bdc77f32-0256-5520-a294-f327d7b77df6 | note | Responsibility - DO Rep/CLL
a3393c8c-6837-5251-ada2-d9b693e96a0c | note | Hold Point H/W/S - DO: H
8920593f-b999-56b4-bb76-4988cac6b525 | note | Hold Point H/W/S - BBO: S
74fd1a5b-2a16-5da8-9dca-a87ff8167a7d | note | Hold Point H/W/S - CLL: H
02286bfc-65f6-52c1-8372-112c2bf4c366 | note | Verifying Record - QAC - Pile Card
301ce10c-e0f8-5c36-a47c-33191b4de49a | signoff | HOLD POINT (DO/CLL)
7f1856f7-f74e-5f60-ae0d-98bde995d6c8 | checkpoint | 4.4 - Concrete placement
4b2d27f3-d304-5954-97ca-42e3ad806688 | note | Standard / Spec Reference - HCC 1298/2022
50ec78e8-7a60-590b-880a-90d07cb85e3d | note | Acceptance Criteria - ITP Item 3.3
b99e46f2-3d8f-5c8f-97ba-a1b6aaada3e5 | note | Frequency - Every Pile
aadd7598-b457-5050-bb50-1e4909442eac | note | Responsibility - BBO/CLL
5ec50698-bb96-5c58-90fc-e33bbec12743 | note | Hold Point H/W/S - DO: W/S
b2c8600c-42f1-543e-b39d-2871d135a7cc | note | Hold Point H/W/S - BBO: S
2b2362b2-b4ac-5f42-858d-9d482142d396 | note | Hold Point H/W/S - CLL: W/S
f7a9c4b9-b545-533f-8e2a-85395f12c4e5 | note | Verifying Record - QAC - Pile Card
8296c2e6-2872-5b02-b7e0-6bdbca76b520 | note | Comment - Pile to be concreted within the same day as Engineer’s acceptance of reinforcing cage installation, ITP Item 3.3.
e61c6faa-a7aa-59fc-9f15-51df6c3c54fd | checkpoint | 4.5 - Concrete pouring – Check volume
f3e683a1-f21f-5432-b184-5ac50c69bd57 | note | Standard / Spec Reference - Construction Specification
cce7751b-fd79-593a-a271-f53492199ba3 | note | Acceptance Criteria - As per QAC - Pile card
983417f3-6810-5eef-a4b7-f594983ade3a | note | Frequency - Each delivery
26737af6-8647-5ac3-8e1c-e95412dc9700 | note | Responsibility - DO Rep/CLL
384298bd-f756-5bfc-83da-38bfaaeb5852 | note | Hold Point H/W/S - DO: W
28138a08-16cb-5f31-a057-4da8dd96c255 | note | Hold Point H/W/S - BBO: S
145cef34-c356-59b3-a213-248300218be7 | note | Hold Point H/W/S - CLL: W
78cb32b7-ba2d-59e8-bffb-afc56409d1a0 | note | Verifying Record - Concrete docket, QAC - Pile Card
4bd8d361-e465-5bed-8717-bfa87d4bcb5c | note | Comment - Concrete volumes and Tremie records to be maintained as per QAC - Pile Card
34841c95-3f50-59ad-abca-ea5991b7b24e | checkpoint | 4.6 - Pile concrete overpour
6b7c9fec-bb14-52a8-966e-2c2739099dfd | note | Standard / Spec Reference - HCC 1298/2022
fba889d8-b628-516c-9809-6f56ff55c148 | note | Acceptance Criteria - Visual check - Sign off by Engineer
6c87a0ad-b23b-52d9-a9f0-3b007a8513f0 | note | Frequency - Every Pile
13a64774-e81c-53d5-b24a-bac36a2941d4 | note | Responsibility - BBL/CLL
ba236230-a27e-53a6-9dcb-4239f6ee7a1e | note | Hold Point H/W/S - DO: W
5a84510a-0eda-5b08-9220-d0e33b82945d | note | Hold Point H/W/S - BBO: W
6f3a1949-8b26-5c23-9f67-fb6e263dc4c4 | note | Hold Point H/W/S - CLL: W
5fbfce19-4d3e-5a01-abaa-3efa57f45c03 | note | Verifying Record - QAC - Pile Card
8536857f-2eab-5bad-9af8-1141c44eae76 | note | Comment - Pile to be overpoured and slurry at the top of the head removed until only sound concrete is present.
3b387d27-4e8f-5bf5-a611-a36cd9ac758c | checkpoint | 4.7 - Formation of construction joint
f581d9e2-cf40-5b7c-9b91-1cee11e67b4f | note | Frequency - Every Pile
79fb3271-da92-539e-9432-4c34ce89a05a | note | Responsibility - DO Rep/CLL
6b7303eb-5980-5128-8213-65756c332029 | note | Comment - Formation of construction joint by others.
36319a26-0d74-5320-b2d4-025a269fd3db | checkpoint | 4.8 - Concrete curing (tops of piles)
3ab9db28-18b1-58b9-8375-29b082114500 | note | Standard / Spec Reference - BBO SS 2146 Rev 4
adeffec9-e085-532b-b412-08212435cc08 | note | Acceptance Criteria - 7-day wet curing required
47ea7a56-bad4-5e05-83d5-65cfcfc01141 | note | Frequency - Every Pile
348082e8-a6fd-58d0-b953-7227dbd8ff1a | note | Comment - Concrete curing by others. Curing requirements will depend on the thickness of concrete which to be removed after concreting and weather conditions.
b2dfdc1a-0799-5ded-abb7-0d34bdf4b9d6 | checkpoint | 4.9 - Compressive Strength Sampling
522b68f4-7f1a-5bd3-adbe-25fbf41c7d31 | note | Standard / Spec Reference - NZS 3112
c3c8a389-8e3f-5e23-ac9e-53b49815cf55 | note | Acceptance Criteria - 28 day - 40MPa
c5b425b0-91f0-5222-af98-f0b2dc7b10bd | note | Frequency - Batch plant sampling and testing per piles – 4no cylinders – 1no @7 days, 3no @ 28 days
3c52277d-9bc0-545f-b820-abddd70359a4 | note | Responsibility - Concrete Supplier – samples cast at plant
67d5fa2a-2c19-5428-913e-81ca3f22e876 | note | Hold Point H/W/S - Sub: H
62e37f45-5d3b-56a4-be03-47ee6d03fb66 | note | Hold Point H/W/S - DO: S
92a92103-e907-5e5b-af77-1c42ce1d2964 | note | Hold Point H/W/S - BBO: S
bff9179e-3d25-5c50-b266-6d4335e05e1f | note | Hold Point H/W/S - CLL: S
b9194c85-45aa-537b-90aa-386b69c592a8 | note | Verifying Record - Lab. Test Record
6e5ebf70-a293-5979-8666-1c5743f59f04 | note | Comment - On site independent testing to be done by others. Samples to be taken at batch plant.
518e1be3-0530-582f-87a7-25c343e683e5 | signoff | HOLD POINT (Sub)
b5dfdef5-a300-5b32-99ff-12f5244d5c2f | checkpoint | 4.10 - Post pour/ Post casing removal - Reinforcement and concrete RL, orientation check.
5da39c36-338e-5d61-a610-cad927166bfc | note | Standard / Spec Reference - As per Auckland Structural Group Piling Specification
988a0b99-7530-5211-a1ea-809b054a8511 | note | Acceptance Criteria - Alignment lesser of +- 4% DIA or +-75mm Height +- 50mm Concrete cover: 75mm, 50mm minimum
445109f9-c35c-5735-afb4-9bf9e584066d | note | Frequency - Every Pile
dfbcc84e-ca31-5d63-a996-cedd4ed942ac | note | Responsibility - DO Rep/CLL
f805c3db-43a5-528a-848f-dcfcdb3914b8 | note | Hold Point H/W/S - DO: W
63899f76-220b-5c2a-ae75-8e9eb90a4f96 | note | Hold Point H/W/S - BBO: S
0c25cf28-8d08-5695-a159-a4380545d5b7 | note | Hold Point H/W/S - CLL: W
f3708420-2a35-54c9-aa00-3b636a2bb2fc | note | Verifying Record - QAC - Pile Card
79d0df54-b810-5bfd-ae22-b36a0dc1cbeb | note | Comment - As builts by others.
dd75deed-8bee-573b-8fa3-73588bc89154 | section | 5.0 Close out
d5fa4318-166b-51a6-96cd-c786a5350aad | checkpoint | 5.1 - Pile Cut off level verification
60e6bef7-48b9-5403-bec6-e68922ffa1d3 | note | Standard / Spec Reference - Construction Specification
d1dff8dd-ad15-57db-94c3-8538a13d2789 | note | Acceptance Criteria - +/- 10mm
ac152506-9a0d-558b-8ab6-d519b419ff0e | note | Frequency - Every Pile
1dc3fc39-ff34-5147-aef0-8828f79642ab | note | Responsibility - DO Rep
fa793d5d-0fbc-523e-b022-a779407e78a5 | note | Hold Point H/W/S - DO: S
4c0297bb-3fc0-50a4-9bf7-e53e27873c43 | note | Hold Point H/W/S - BBO: S
08375f72-a0fc-53ff-b22c-04f7c7b8cc76 | note | Verifying Record - Survey Record
034f27c1-41c4-5d8e-80f3-fcfbc00596a4 | checkpoint | 5.2 - Pile & Reinforcement Cleaning
f10bacc4-6c83-59dc-ae57-0e47e11d700a | note | Standard / Spec Reference - Construction Specification
bbc7e2a8-6728-5dc4-ae5d-9f4d738d5319 | note | Acceptance Criteria - Visual
54efc8f7-eac3-5e18-861f-28439453975b | note | Frequency - Every Pile
55699227-4f9c-56b9-996a-f2468339df0c | note | Responsibility - DO Rep
25389885-052a-54dd-83c3-ef60830d729f | note | Hold Point H/W/S - DO: S
98f9e32b-e020-5b9d-ac8b-befaf733daae | note | Hold Point H/W/S - BBO: S
67785e7e-86e3-5d48-97e6-e288a24d6435 | note | Verifying Record - QAC - Pile Card
15547e0d-3fc9-57a5-8b6e-4156c19e1f82 | checkpoint | 5.3 - Reinforcement to specification
e2231008-11df-5670-ab3f-458806c1c46d | note | Standard / Spec Reference - Construction Specification
cd4704b4-6f33-50e1-92b0-7e2d5e19ca43 | note | Acceptance Criteria - Visual
4a0b20bc-43a1-50e6-ad70-4be701ee1b8a | note | Frequency - Every Pile
eaaaf82c-5480-50e5-9298-582fac5dcd44 | note | Responsibility - DO Rep
e2c90418-6ab8-594b-a1d3-8c51b06d6859 | note | Hold Point H/W/S - DO: S
75e11b29-a15b-5b1f-a177-b23bfa350852 | note | Hold Point H/W/S - BBO: S
cc52a099-c4a8-5d40-9fab-5352cf304efc | note | Verifying Record - QAC - Pile Card
5a047b61-e09b-5a34-ba03-2f64cba1794a | checkpoint | 5.4 - Pile records
c027e63f-fd56-5676-a6d3-e5084e17b286 | note | Standard / Spec Reference - Construction Specification
efd3822b-78c4-56fb-a0a2-4afec4dd0e0d | note | Acceptance Criteria - Collation and Submission of records
4abf990d-cf56-502c-94fa-403039ac85d0 | note | Frequency - Within 24hrs of completion, Every Pile
cf5d8ca2-1b61-55d9-9a96-c2d50d40a909 | note | Responsibility - CLL
75c2c23e-5b26-5df6-8591-b673e576d090 | note | Hold Point H/W/S - DO: H
243147c3-4704-5bb6-a66c-ab5c836f8356 | note | Hold Point H/W/S - BBO: S
3a6b8d88-311d-5206-92a9-770062142582 | note | Verifying Record - Email Confirmation
03da7126-7c0f-552c-9b83-1da110831867 | signoff | HOLD POINT (DO)
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
5b0315b8-b590-58e2-a613-c7b2192c13bd | checklist | ITP - Precast Barrier | itp | ITP - Precast Barrier
0f66e61d-af39-55d7-a549-551996ec17ca | section | 1.0 Pre Construction Tests
79a6efe8-8a71-5f56-aa54-a208ce355858 | checkpoint | 1.1 - Concrete Mix Desisgn Approval
d8c1387e-f340-5cb6-a9cf-119cf09ff8a4 | note | Acceptance Criteria - 50 MPa at 28 days (S5019MS8)
82822e8f-c181-529b-8ae6-9b7c3e8ee282 | note | Inspection or Test: Method - Review
17e1e32a-d78f-5fb1-9f9d-d80575a7af30 | note | Inspection or Test: Freq. - Once per Mix design / per supplier
922f1a8b-5a26-5977-8b57-0cac27c84dba | note | Inspection or Test: Responsible Person - PRECO
6e97688f-cb5f-547d-9922-2f73763498cf | note | Verifying Document - Confirmation of Approval
590495b6-fb84-5ea7-b9b2-a2e350925859 | note | Records required for handover package: Yes/No - Y
b24f9295-91b2-525a-bc27-a17dc6de323f | note | Inspection / Test Authority: Conduct - 1
a4a94b2c-233f-5b8c-8b94-42a42d0f34c7 | note | Inspection / Test Authority: Witness - D
21479b33-a765-589f-997e-a1e9506e3e0b | note | Inspection / Test Authority: Produce Record - 1
ead0723a-e8ec-56ee-8426-2f4945e60bf1 | note | Inspection / Test Authority: Approval - C
e84d0568-c9d5-5add-9e54-6d49955cd793 | note | Hold Point - Y
6e9623ef-496c-5185-9970-cb96499f598c | signoff | HOLD POINT
bcf9db4c-7bb0-5ae9-b472-b2d4f03da2d2 | checkpoint | 1.2 - Reinforcement Supply – Certificate of Origin
6a3b2ea9-9c3a-5aad-9002-842ec48435f1 | note | Controlling Documents - Approved Drawings
e11db8b4-4148-5e5f-8a96-d6daf72989f5 | note | Acceptance Criteria - Provide certificate of origin for all steel reinforcing supplied.
92472c27-961a-5122-be14-5ff33260c473 | note | Inspection or Test: Method - Review
41843fb2-e96d-58a0-8f59-7428c40b6ed5 | note | Inspection or Test: Freq. - Per Size, Per Supplier
1d32e0c0-28aa-5c23-807e-31c15534bbc1 | note | Inspection or Test: Responsible Person - PRECO
851cb19b-14e9-583e-9fb7-444b361cb39b | note | Verifying Document - Supplier Mill Certificates
8bcd55e9-b715-562c-aeb7-35db9a2d1780 | note | Records required for handover package: Yes/No - Y
d0897f08-0a46-5ab2-a2aa-26b4cc70e071 | note | Inspection / Test Authority: Conduct - 4
5f717aef-d570-55f5-a7e9-588facad603c | note | Inspection / Test Authority: Witness - D
978c43fd-466c-5213-8c70-200dd0e727c5 | note | Inspection / Test Authority: Produce Record - 4
8b09c1ac-afd5-5f14-9319-cb632d46e505 | note | Inspection / Test Authority: Approval - C
2b805cb5-8bd6-5a2a-a47f-e4826f8c3386 | note | Hold Point - Y
54b462f5-5d63-5e5b-a048-1001479a4687 | signoff | HOLD POINT
97627c82-e1de-5e36-b91c-9665868e0cf9 | checkpoint | 1.3 - Shop Drawing Approval
01f24f63-a8a8-5533-9795-d54100f46f05 | note | Controlling Documents - IFC Drawings
82a163aa-5ebb-5a1f-be85-a4d3dd3f1988 | note | Acceptance Criteria - Shop drawings including, concrete strengths, surface finishes, location of cast in items and set-out information
05e7ca4a-ae0a-5f34-a26e-5b9670930949 | note | Inspection or Test: Method - Review
695835da-bf07-5525-8b1c-47c5b4e314cc | note | Inspection or Test: Freq. - Once Prior to Casting
997d69a6-5c30-5ad6-87d5-923d6035c8e8 | note | Inspection or Test: Responsible Person - PRECO
62d2c64d-62fe-5e04-a810-579213f4ac7e | note | Verifying Document - Approved Shop Drawings, Issued for Construction
839e54a5-4a5c-5f3d-a108-fcd224e34d4a | note | Records required for handover package: Yes/No - Y
f4fd2d1a-3534-58ab-9235-c15f5cbada6d | note | Inspection / Test Authority: Conduct - C
ab881588-246c-5c6b-a63f-3332cb50be3d | note | Inspection / Test Authority: Witness - C
b0e4bc24-e62f-5ec1-a1bd-2e8c11a5e6f0 | note | Inspection / Test Authority: Produce Record - C
190341d8-174d-5b38-a15b-1870094d5a12 | note | Inspection / Test Authority: Approval - D
20a5d1e7-b4cb-515f-b447-f892596aea77 | note | Hold Point - Y
aec1ebb0-f517-59df-98b4-921e7311cafd | signoff | HOLD POINT
7f45d116-630d-5799-8d7b-003f855faf5a | checkpoint | 1.4 - Form Release Agent
3ae381ed-20c5-51b1-97f3-1f566263548a | note | Acceptance Criteria - Not detrimental to the application of any subsequent finishes
20128331-ac7c-5ce1-999f-2a235b14700b | note | Inspection or Test: Method - Review
7d670198-1d1a-524a-b380-7af2ceb3ef58 | note | Inspection or Test: Freq. - Once
22eb0f03-2aee-54a6-9e46-92b83d40a4ae | note | Inspection or Test: Responsible Person - PRECO
e5a880a0-5942-5372-9568-9fcbf5f0458f | note | Verifying Document - Material Data Sheet
aa2035b9-00ae-5b2f-a8a3-77293821f2c6 | note | Records required for handover package: Yes/No - Y
6a8e216c-3a6d-5a39-a1d4-e0d1cc53f8aa | note | Inspection / Test Authority: Conduct - C
437aac02-281f-549e-8aa4-dba7011957da | note | Inspection / Test Authority: Produce Record - S
8dafda5f-5c6d-5397-97d9-fd57a8fadd13 | note | Inspection / Test Authority: Approval - C
0d828057-93e9-5e69-8d1e-079094db6520 | note | Hold Point - N
e012e307-41a0-53fd-a516-ffcebbf7db1a | checkpoint | 1.5 - Cast-in Items
191fdecd-efd8-52c3-bf6f-fb59fbd5baa1 | note | Acceptance Criteria - Provide certificate of origin for cast-in-items
fc62b7b0-cad3-531f-b28a-dca8e9324524 | note | Inspection or Test: Method - Review
7b724a24-18dd-518e-9580-d4c69eed6379 | note | Inspection or Test: Freq. - Per batch delivered
c706b1fd-9a71-5789-84a6-97e8f67a1258 | note | Inspection or Test: Responsible Person - PRECO
76a37be5-fbc7-531b-b323-6e2757c8b25d | note | Verifying Document - Suppliers Mill Certificate
5b9e05d2-a92b-51ac-910c-0a990b6a07db | note | Records required for handover package: Yes/No - Y
c5d321b4-8305-5159-a1cb-2b116d474a21 | note | Inspection / Test Authority: Conduct - 4
3dc93ab7-004e-56a4-8fad-e30442f4cf2a | note | Inspection / Test Authority: Witness - C
474dd962-a1cb-5aa2-a069-a4dec55c6dd8 | note | Inspection / Test Authority: Produce Record - 4
2cb46a60-93aa-5849-8620-5df7c6b2f17a | note | Inspection / Test Authority: Approval - C
4078a876-a52a-5bcd-8995-a003a05e0174 | note | Hold Point - N
254d676b-9c6a-5c89-bbdd-1e9524316f24 | section | 2.0 In Process Testing
46612ebc-5681-527c-9122-bbad93780ad4 | checkpoint | 2.1 - Inspection of The Reinforcing
8dda2c2a-6ce2-5130-a053-532dfee26c60 | note | Acceptance Criteria - 40 mm min. clear cover to all reinforcing including stirrups and ties
9482d366-67a4-5ebe-be2b-03e80b5a4174 | note | ○ Steel to be securely tied and fixed with no movement
22ac8de6-6e72-584e-ac23-0d37e0e42adc | note | Inspection or Test: Method - Inspect
59b84c6c-85b2-5826-b7bf-4afa30c31b4b | note | Inspection or Test: Freq. - Per Unit
4eab1891-96b6-59c3-957f-05e9e7f8c667 | note | Inspection or Test: Responsible Person - PRECO
980bd4e2-fede-5d11-b49a-00ca53cdf45d | note | Verifying Document - Pre pour checksheet, photos
52dd7dcb-9fb5-5455-9c91-18ea7e926987 | note | Records required for handover package: Yes/No - Y
646d609a-8a56-5657-ae06-8224973902ea | note | Inspection / Test Authority: Conduct - C
c3248dcf-db60-5ea8-987f-6b8cb50642c5 | note | Inspection / Test Authority: Witness - D
78951cc8-b562-545c-8fd6-473256170749 | note | Inspection / Test Authority: Produce Record - C
a075679e-8bd9-57ae-82a3-8853d4e7fc6f | note | Inspection / Test Authority: Approval - C
1c40571c-d8e9-536e-814a-f22448a2afff | note | Hold Point - N
53993a1c-9c13-57a3-bda1-b81de933cc36 | checkpoint | 2.2 - Checking Formwork
d59f7513-cf1d-528f-87ee-7f54243a1361 | note | Acceptance Criteria - Dimension including edge details and rebates as per drawing
1175cfb5-e783-560d-a6a9-d91dda4acea1 | note | Inspection or Test: Method - Inspect
f29a3f3b-d608-50aa-9650-55fc0a38d3ce | note | Inspection or Test: Freq. - Per Unit
aacc72e0-9968-58ff-92b3-8e6e4f2f5b89 | note | Inspection or Test: Responsible Person - PRECO
af983bfb-d586-5e80-9fc4-583a4cbf32a0 | note | Verifying Document - Pre pour checksheet, photos
5cac43b4-6466-5164-a815-c76dc171549c | note | Records required for handover package: Yes/No - Y
58763972-25fd-5ac6-a1d8-ef95cfabe5a5 | note | Inspection / Test Authority: Conduct - C
ecd6bf87-85e5-553c-95f0-c5d61bc48ecb | note | Inspection / Test Authority: Witness - C
f98de228-e39b-5174-9a7f-8bb2d6f92974 | note | Inspection / Test Authority: Produce Record - C
e64ec3aa-a4bc-52e1-9339-c7a2ad308c5e | note | Inspection / Test Authority: Approval - C
802ea10b-5e2f-5af8-854d-5ff010bdc2d6 | note | Hold Point - Y
5bfdaa9b-a51f-5d8b-9954-dc67379f0406 | signoff | HOLD POINT
00b46d42-78fb-5405-9d94-c4453711b55a | checkpoint | 2.3 - Pre Pour Inspection Prior to concrete placement
9ab5217c-e2cd-5fdb-9388-5f25adfb5d63 | note | Acceptance Criteria - Completed pre-pour inspection, permission to commence concrete placement
444c6e66-1951-5b7b-8799-659954e74703 | note | Inspection or Test: Method - Inspect
10fa7972-4848-5030-92c5-a39c41f0179e | note | Inspection or Test: Freq. - Per Unit
b39d3345-104b-5d2a-901d-766e47400126 | note | Inspection or Test: Responsible Person - PRECO
273b5932-9a67-5edc-af41-00ff28326c5f | note | Verifying Document - Pre-Pour Check Sheet/ photos
87e0b84d-92d4-51f0-b63e-fb69c1e86fac | note | Records required for handover package: Yes/No - Y
6365b53b-d5f9-5e8f-b8fe-0aa99e7506be | note | Inspection / Test Authority: Conduct - C
ea11e90c-e0bb-5340-9710-b5df8f2cfde8 | note | Inspection / Test Authority: Witness - D
208f718f-0a75-5f36-aa38-1a35ca59f7a9 | note | Inspection / Test Authority: Produce Record - C
e3b7a418-9b94-5f4d-a64d-cde7d8ac481e | note | Inspection / Test Authority: Approval - C
1317ad0a-ce1c-56b9-9d31-51ef2fd53508 | note | Hold Point - Y
aa1db9aa-a218-5ccb-8204-e2d046734448 | signoff | HOLD POINT
29677ff6-eca0-5c79-b5ce-e206db46a187 | section | 3.0 Concrete Testing and Inspection
f15c6158-7e0c-52b2-b575-3406d0541d67 | checkpoint | 3.1 - Concrete Delivery
296c0544-627f-5cb8-8ccf-fa3c00e0c563 | note | Acceptance Criteria - Approved Mix Design (S5019MS8)
e09836e7-e944-5b41-a628-e3f722fd1112 | note | Inspection or Test: Method - Inspect
73172d08-d70c-5c91-8a6d-abc43520e3bb | note | Inspection or Test: Freq. - Per Concrete Delivery
6491128f-374a-59e8-8c93-46f50daa8abf | note | Inspection or Test: Responsible Person - PRECO
76468661-1f35-509e-987c-bb8ddef86349 | note | Verifying Document - Delivery Dockets
6a509483-7609-5bea-b5d3-42e77bb27926 | note | Records required for handover package: Yes/No - Y
7e5c1ae7-4654-51e1-a97e-8b3a557b59d6 | note | Inspection / Test Authority: Conduct - C
1d1cadf0-d5ad-5ab5-92e1-51052729e03e | note | Inspection / Test Authority: Witness - C
5fa8589e-5b9c-571f-bac9-db74040c9459 | note | Inspection / Test Authority: Produce Record - C
de346339-d61a-55a7-ba96-207fe74e50e4 | note | Inspection / Test Authority: Approval - C
70768a97-bb2e-5c6c-bb41-b6dffa215225 | note | Hold Point - Y
0ca929b5-3ca2-5e0e-bbb5-e156abc63081 | signoff | HOLD POINT
d4fd98b4-853b-5e7a-a0e9-29ca24fad4e1 | checkpoint | 3.2 - Concrete Placement
b7612537-785b-5c47-897f-0dffa8459c5c | note | Controlling Documents - NZ 3109
03d33a90-5556-5f22-8d9c-46cd3ffee61d | note | Acceptance Criteria - Vibration of concrete to ensure suitable compaction
f92b1f4a-62e7-54be-b0f6-06940e48a240 | note | ○ Slump within target 100+/-40
58a16842-dc9d-5669-81a9-f9cce43d1705 | note | Inspection or Test: Method - inspect
a09d97af-f824-5dce-98df-b0de190ff109 | note | Inspection or Test: Freq. - Per unit
077c5cd0-3f48-5446-9775-52c6ce128d2e | note | Inspection or Test: Responsible Person - PRECO
27d1c5c3-6b9a-5d30-acf9-519451febdf5 | note | Verifying Document - Witness inspection
3a7fe327-77c7-53f8-8685-610a5c572c56 | note | Records required for handover package: Yes/No - N
762ee824-9acb-51e9-80eb-fc021982475c | note | Inspection / Test Authority: Conduct - C
4bb788dd-8ff2-5043-99e2-67aa9adccb74 | note | Inspection / Test Authority: Witness - C
1b6a9469-9659-527b-9fcb-b8b9b191f43f | note | Hold Point - N
2389af1c-b946-57a8-b0f6-8145f9c97871 | section | 4.0 Post Concrete Testing and Inspection
18547f45-4bc4-5223-a262-cd3962e10164 | checkpoint | 4.1 - Concrete smpling / testing
ac8036a4-52c9-55c5-9048-7e4424a39e53 | note | Acceptance Criteria - 1 x 7d and 3 x 28d - 50 MPa at 28 days
cb06f198-2fc0-5a49-96ff-af413b4280e6 | note | Inspection or Test: Method - Concrete Sampling
1d3ac0ba-70e5-5047-94ee-68ff84fbdb5c | note | Inspection or Test: Freq. - Per 75 m3 (not part thereof)
73dc4b4d-6d20-50e7-a00c-53beb9e7e682 | note | Inspection or Test: Responsible Person - Subcontractor
867bc4d8-1c15-5688-8f7c-d12e26deeafe | note | Verifying Document - Concrete Sample Test Results (IANZ Accredited Laboratory)
6a8dd5b4-8114-53f0-a625-9f2a10d108ec | note | Records required for handover package: Yes/No - Y
fb47404f-d673-51d1-9dde-96e1c28ec324 | note | Inspection / Test Authority: Conduct - C
2a5b41ca-7ced-5247-a3b5-592077b03b9d | note | Inspection / Test Authority: Witness - C
555306d6-43ec-5ead-96da-7a4dadecdaed | note | Inspection / Test Authority: Produce Record - 3
a04b5bc2-3ceb-5151-9f28-03ee5bed39a1 | note | Inspection / Test Authority: Approval - C
8580c40a-f952-5a4e-b4de-ed19a5b5b4e0 | note | Hold Point - Y (Designer to be notified immediately if specimen fails)
e6860c27-b58f-566e-8bb5-65263e7f000d | signoff | HOLD POINT
93bd6e30-b508-51fb-94fd-a732a754c7b7 | checkpoint | 4.2 - Surface Finish Requirements
970ed5bd-ceb8-5bb4-9cd6-a51374433d88 | note | Controlling Documents - IFC Drawings
3a816951-23ae-5c00-be0d-9bf406e64319 | note | Acceptance Criteria - F5 / Type B construction joint to NZ 3109
2cfd5b87-68dd-5eb0-86dc-9d4f396b91b9 | note | Inspection or Test: Method - Inspect
bbcab98e-e450-5f80-96b7-dd2bc0853272 | note | Inspection or Test: Freq. - Per Unit
730970bd-c98c-5426-8a15-749f3ebf02e8 | note | Inspection or Test: Responsible Person - PRECO
d9dc372c-d89b-5b40-9169-08a8380efbea | note | Verifying Document - Post Pour Checksheet
f1075e86-4059-5992-ace8-f806ec58a37e | note | Records required for handover package: Yes/No - Y
b2e4f0f2-e6fe-537d-a7be-93bd9deb8d21 | note | Inspection / Test Authority: Conduct - C
f3c88a89-d0e9-59f4-8308-4a403d177b96 | note | Inspection / Test Authority: Witness - C
4bb6e2f2-8054-5fa2-a8f2-5fe75440994c | note | Inspection / Test Authority: Produce Record - C
7d325357-f7e2-5bf4-8242-6b2eb96e5fce | note | Inspection / Test Authority: Approval - D
cb6579f7-877d-5b49-b14f-556ce8468624 | note | Hold Point - Y (Designer to be notified if finish requirement not meant)
1fd06edf-566b-55a8-b25f-f4b758c38c4e | signoff | HOLD POINT
164e4aba-4070-5a43-b4a9-40b890057f0d | checkpoint | 4.3 - Concrete Curing
6d81ae7e-5250-5248-9ee3-94b487944a98 | note | Acceptance Criteria - Curing with curing compound (e-cure)
8e9da9c3-29f5-5d7b-96e9-5695fa15434d | note | Inspection or Test: Method - Inspect
2026a907-8246-52c2-afbc-9c7e1cb8da2f | note | Inspection or Test: Freq. - Per Unit
72b915a8-7450-50ee-9e42-0fbe53eaf8b6 | note | Inspection or Test: Responsible Person - PRECO
3c0231eb-070d-54e7-9229-07e3271c5cb3 | note | Verifying Document - Post Pour Checksheet
115a294b-f979-5d22-9393-cfeb8bbedc79 | note | Records required for handover package: Yes/No - Y
a3a2c096-c118-5c4e-9165-c4ad75f5c906 | note | Inspection / Test Authority: Conduct - C
4e8933ed-b582-5d65-8d62-5dbe6846e0a7 | note | Inspection / Test Authority: Witness - C
82c6c6c3-8dd7-5b6c-a6ec-04d5507d41de | note | Inspection / Test Authority: Produce Record - C
775663b2-4b2f-52e6-9523-c4da7e95f922 | note | Inspection / Test Authority: Approval - C
45785fe4-d994-5bd7-9d20-b13f8492185d | note | Hold Point - Y
fa6f85fb-503b-5a8a-9f1a-319abd064687 | signoff | HOLD POINT
cc80522c-cd8a-5e79-93b7-cfceaabcd10f | section | 5.0 Final Documentation
3ada7b4d-b206-5bb4-9b41-40bf4f3caf32 | checkpoint | 5.1 - Producer Statement (PS3)
1a1341a6-c738-5453-a224-d291e69b0bec | note | Acceptance Criteria - Signed PS3
0cb2d76c-afdd-5abf-863e-08404ef07f13 | note | Inspection or Test: Method - Report Production
1d9396f6-ea72-58e8-8c21-22cf717d212a | note | Inspection or Test: Responsible Person - PRECO
38b5f39c-b2bd-5bd8-a5a8-7e63a9478b96 | note | Verifying Document - Signed PS3
c684c088-1b8e-5e64-9f95-d76853df1aae | note | Records required for handover package: Yes/No - Y
0d43f981-bf55-57a3-ac91-131e1ebce22c | note | Inspection / Test Authority: Conduct - C
b1fb543e-72a2-57cf-a247-ac4f7222d82d | note | Inspection / Test Authority: Produce Record - C
063d5691-9cda-5cb6-901b-6e036a4af6e0 | note | Inspection / Test Authority: Approval - D
c599dcef-8922-57d8-8daa-4b939c9f4ea3 | note | Hold Point - N
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
9bb0f25e-0af0-54e9-b147-45751c4f6d69 | checklist | ITP - Retaining Walls - Rev C | itp | ITP - Retaining Walls
8c9335a7-3af5-5e47-a887-39a89ff08c27 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
dfb723bb-584a-5713-be6d-07b0f19feadc | note | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
e2830cdf-362b-5f0e-8d22-f68f1a98219d | note | Standard / Specification - Downer
14282032-c33f-55dc-9ae6-ba093f01c0fa | note | Verifying Document - Construction Pack
9e7ee91d-d82a-5694-af12-0f67083b3c87 | note | Frequency - Submit 10 days prior to commencement of works
2a4ab9d4-071d-53fa-ac91-77f26febe2a2 | note | Activity - HP
d5d6a8c7-50e2-54b9-96ba-d6ed63ed046c | note | By - ENG
ca255811-cbe5-57f5-8b49-d49ad30655f3 | signoff | AUTHORITY HOLDPOINT
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
dc572b14-0ed6-54c7-bc8f-85ed00c03dfe | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
3e946a9d-b5c8-50e7-96e0-0400e8f6e89c | note | Standard / Specification - Downer
34bb53e5-aed2-52e3-a5c2-9f81d0a823ca | note | Verifying Document - Survey Records
61d76f5d-0ad9-583f-ac76-86ad184fa739 | note | Frequency - Prior to Works
376f33df-3b2b-5b0c-ab68-eb1a544a497d | note | Activity - H
c900da17-59f9-5691-b9d1-3bcd5996d491 | note | By - SV
a24a2c58-bf6f-5474-883c-40044bad1fc7 | checkpoint | 3.01.03 - Service Location
b9f21eeb-7675-5741-9a79-4af249ac51cd | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
434102cd-5777-54cc-b4b5-32744d498024 | note | Standard / Specification - Downer
07a728fa-eece-56e9-af95-f512783809d3 | note | Verifying Document - Excavation Permit
077eeafa-3bad-5034-9687-5e46d0d70d1b | note | Frequency - Prior to Excavation
f621f899-2387-5113-900d-6bf9fc014ca0 | note | Activity - H
765fd8e2-b34a-5911-8b80-bd9e215f5033 | note | By - SE
0a214a7a-124a-5898-a837-e29e83751df0 | checkpoint | 3.01.04 - Internal Permits
b356337b-ff8b-5218-b916-0250a1283683 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
a1b106e9-f9c2-5c82-9b78-bc7a5e36b3d8 | note | Standard / Specification - Downer
62309b3c-27a8-5c74-8629-890633f13944 | note | Verifying Document - Internal Permits
83e97ed8-8c87-565f-9e65-f307d506c6a2 | note | Frequency - Prior to Excavation
d9a60eb7-5a01-5a8f-8f3f-6ce4ccaaa502 | note | Activity - H
3d563ef1-3b79-577d-b94f-308e34e1ca4e | note | By - SE
917e2881-0901-542f-ae25-686bf9c47009 | checkpoint | 3.01.05 - External Permits
b3b0e978-a810-584e-aa53-c42ce3c97641 | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
da4f0b71-5efa-5c01-ad1a-988c4ed5ce74 | note | Standard / Specification - Downer
9637f9ab-b7c6-54c8-8436-24c62804f0c4 | note | Verifying Document - External Permits
86a70157-a919-5dd5-aa32-c8681501a34c | note | Frequency - Prior to Excavation
bdcdc434-1b5d-5073-8411-b8512f1171ba | note | Activity - H
9a96dd8f-f51a-5d85-90aa-2277fca1a9b8 | note | By - PE
a1302970-0389-558d-b43c-67b14bbfc27a | checkpoint | 3.01.06 - Approved Construction Drawings
9ff0acba-9273-52f4-a0a4-2ab6d34c8a37 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
35f67329-e2c7-5487-a6d4-58b982b7c249 | note | Standard / Specification - Downer
3dfe5430-9c4a-5998-aade-3c0355af63af | note | Verifying Document - IFC Drawings
2b7e4a6a-c00a-5a00-ac72-61e46e5f805a | note | Frequency - Prior to works start
64beb55c-164d-586e-993a-71bf994ecd03 | note | Activity - H
16b491c1-6520-5184-a1cd-e89a84b6dddc | note | By - PE
34b3d838-f63d-5499-aad4-14b7c1eb24ae | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS
1437ac3f-e25b-5932-8866-3f1e2bab518b | checkpoint | 4.01.01 - Stone Strong Block Molds
24a4862f-20e9-5858-9e47-682e8ebdcd0f | note | Acceptance / Conformance Criteria - Stonestrong blocks to be supplied by an approved supplier. The Contractor shall liaise with the Principal-appointed Cultural Artist to coordinate carving of the supplied blanks and the production of moulds & blocks
b7e1ac9b-4fd0-5aed-91f1-207545543544 | note | Standard / Specification - PS - 12
4fbb56e2-610f-5ab3-b571-8d5a95c19942 | note | Verifying Document - Conforming Molds Post Carving
4ea6de2e-aec5-50b2-a438-bd4bd870e686 | note | Frequency - Before Installation
d4a2256c-c353-57e5-9fce-3979c4f41a52 | note | Activity - H
1c7d0313-833b-5b02-8452-76e926b94d30 | note | By - PE
a3cd3258-fb54-5b31-83f8-74d9198b64d1 | checkpoint | 4.01.02 - MSE retaining wall backfill Material
cc3d6c38-7cdf-5ccc-b3de-82e5fa7d81b3 | note | Acceptance / Conformance Criteria - Backfill is to comprise a well graded, granular material such as GAP65 or site won Hinuera Sand, which must be free of any deleterious material. Sand backfill shall have a fines content (less than 0.075mm diameter) of no more than 10%. Labratory MDD (x2 per material type) at standard compaction
22721888-49d4-5ebd-a823-b786fde9c2dd | note | Standard / Specification - GWS - 5.3.3
f760ee7e-3e30-5748-ac8d-dd6f4cff2189 | note | Verifying Document - Lab Results
ac1f5c71-71b7-5418-a6b3-d83649055b3c | note | Frequency - Prior to works
951e9d5f-bd61-5982-b242-bf9f0c0caffb | note | Activity - H
8ebf4f1b-07e1-53f7-b331-bcd4af254b27 | note | By - PE
05bce6c9-76c8-5aeb-94f0-6addb618072e | checkpoint | 4.01.03 - Geogrid
a5ac5972-5125-5559-af6d-1c6c4e7dedcc | note | Acceptance / Conformance Criteria - Geogrid to be Miragrid GX200/30 or similar approved
9f8013ff-90e1-57c2-9d72-3a9dffbf0e78 | note | Standard / Specification - GWS - 5.3.1
0a7a8e2c-6643-54d0-a7a9-d2756a3ae4b4 | note | Verifying Document - Datasheet
8616060a-d369-50b8-aaba-ef3009718c94 | note | Frequency - Before Installation
a58b35f4-bec7-526e-a186-cb8cfac7ff0c | note | Activity - H
96867ef7-72bf-5c39-9276-a8fa57a392dc | note | By - PE
6e039cf8-38d9-583d-81da-a16916cec0db | checkpoint | 4.01.04 - Para web
1caebfdf-02c1-5487-a1c2-99494d3a7d32 | note | Acceptance / Conformance Criteria - Paraweb to be the correct grade: Paraweb 2D-50
fc6b5ecc-9ae5-5429-b362-4e4e740b858a | note | Standard / Specification - GWS - 5.3.2
c6a61179-13b0-5cce-86df-0b2aee73ba18 | note | Verifying Document - Datasheet
d6d44771-ac67-536d-add9-852624175da7 | note | Frequency - Before Installation
9d9aac6a-b187-50c7-bcbc-e7f671b406f3 | note | Activity - H
55508e0c-9e1b-52b3-a5d1-64da039c0ec6 | note | By - PE
e132fae1-e9b4-511f-a4c3-4d0a9e983806 | checkpoint | 4.01.05 - Drainage Pipes
7a5b659a-8903-53d2-923a-b6d92a4b1645 | note | Acceptance / Conformance Criteria - Shall be 110mm diameter NZTA F/2 compliant smooth bore perforated corrugated pipe with filter sock
7794d7ea-668a-5c32-bb0f-3680b36f6de3 | note | Standard / Specification - GWS - 5.3.4
ea8e0216-d0f1-54d5-92d8-9b9fa06b7076 | note | Verifying Document - Datasheet
d56eee96-b50c-5a01-acdc-8056d052ceaa | note | Frequency - Before Installation
395116fd-81ab-5fbc-8151-6255ffeb4a71 | note | Activity - H
8fb5b411-f437-5583-8180-b42cdf2a2a99 | note | By - PE
e7adda1d-89e3-5dee-b757-9e3f5f015cac | checkpoint | 4.01.06 - Geocomposite drainage board
cd6be02c-c749-5f25-acc3-4ffb2cefa944 | note | Acceptance / Conformance Criteria - Shall be Cirtex Armour flow, or similar accepted by the Engineer
ebf65b67-521d-5975-ac96-0b04a5a626cd | note | Standard / Specification - PS - 12
1de52d81-e41e-553d-9c21-f0f6340ab64c | note | Verifying Document - Datasheet
0987a3f2-09ee-5a15-a403-5dac4b2b4eb3 | note | Frequency - Before Installation
f2e98e9e-bba5-51b9-b10c-728c27a797b5 | note | Activity - H
29b83dfe-e46e-5abc-a914-d0df434d4e6f | note | By - PE
7d04c6ae-3cb1-5c0a-9796-1cc24d0858ea | section | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS
838e6cd4-76c0-5235-b72d-9a0f1a44ed66 | checkpoint | 5.01.01 - Excavation to subgrade
a44eca19-0903-53b8-b909-f430fbf6b9bf | note | Acceptance / Conformance Criteria - The foundation materials are to comprise natural Hinuera sand material, stiff Hinuera Silt or imported clean sand and must achieve a minimum of 4 blows per 100mm when tested with a Scala penetrometer. Any exposed silts must have vane shear strengths greater than 70kPa.
5722bcfc-454b-577a-9ad1-d3e3205134b4 | note | Standard / Specification - GWS - 5.2
915e6908-c8fe-5ac1-9db4-a947962d0041 | note | Verifying Document - Scala Results
a490c5fe-167a-5b44-ab44-b30841d751aa | note | Frequency - Every 10m
6289dc62-ab20-571f-9d3e-14f5140d96a5 | note | Activity - H
b7a8ce23-7996-5bcd-af78-3797ae943025 | note | By - SE
c4674b26-69c0-5262-a38b-746e46d5825b | checkpoint | 5.01.02 - Foundation Approval
88bbf40b-3a7e-5106-a1eb-b04cac8b3276 | note | Acceptance / Conformance Criteria - Results of the foundation material testing shall be supplied to the Engineer for approval and the prepared ground shall be inspected by the Engineer. Construction may not proceed until receiving Engineer’s approval.
87cf84f3-b265-54c8-91f4-8fe99cf580ac | note | Standard / Specification - GWS - 5.2
1686d54b-8287-51df-86cf-43bc7127c4b6 | note | Verifying Document - Approval
92f82e7a-8f29-5590-9360-08dca36f2305 | note | Frequency - Prior to proceeding. Min 48h notice to Engineer
75d2a1b0-4525-5583-9519-6b0bab956b25 | note | Activity - HP
13ca0be8-8086-5cfa-835c-649526f18337 | note | By - ENG
2ddb755a-f329-5467-ab5f-6a7fca5b3f95 | signoff | AUTHORITY HOLDPOINT
19ca66fa-e5a2-5cfc-b467-61317531b98d | checkpoint | 5.01.03 - Undercut subgrade
3a1426c3-4a4b-50d6-8c92-de9a0f129814 | note | Acceptance / Conformance Criteria - Any unsuitable materials, such as uncontrolled fill, contaminated materials or any weak or organic materials, shall be undercut and replaced with compacted granular fill (WHAP65 or equivalent) or Hinuera Sand. Surveyor to capture extent of undercut (if any) to include in asbuilt.
a162c6e4-10cd-5f4e-aee1-19aebcb4c8b1 | note | Standard / Specification - GWS - 5.2
f1f6c15f-6596-5cfe-9cd1-5734db4e100b | note | Verifying Document - Survey Record/ Photo record
37cd6678-71f7-5b8a-aaae-7266b0c53b90 | note | Frequency - If required
09fca302-cdb5-5d57-a109-7acf55153583 | note | Activity - I
839acd88-9afc-5d25-87e1-5dc15047bc55 | note | By - SE
11e626b6-30f1-58a8-84fd-9bad3add61ff | checkpoint | 5.01.04 - Undercut backfill compaction
686827fe-56ed-5bab-9d64-495ebf6340bf | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
e5515d9a-8cc8-5f73-9ca8-e055c4cc041f | note | Standard / Specification - GWS - Table 3
08c502fa-14b9-5b61-b1a0-0533d2b91f20 | note | Verifying Document - NDM Results
49be031b-95ea-5b55-97e3-3536950c4134 | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
14a27680-1a25-52b8-bd00-1fab40f44075 | note | Activity - H
c95dd2e2-6397-5c53-ba34-465a08f15a20 | note | By - SE
429c469f-d0be-5299-88a0-616d51d283a0 | checkpoint | 5.01.05 - Geogrid Installation
7c06f150-6a83-5a7f-bf9e-26add933060a | note | Acceptance / Conformance Criteria - Geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets. Engineer to inspect 1 layer prior to backfill.
8150c2df-f463-5e1e-9900-9baeb8241b95 | note | Standard / Specification - GWS - 4.1
502aec9f-4e98-5c7b-ade9-d8d49f08c81f | note | Verifying Document - Photo record
956b32f9-ff13-55e8-a916-4c3f79f7faac | note | Frequency - Each layer - 1 layer per abutment to be inspected
1f4aba03-43ec-52d8-9410-bef8fd128ad6 | note | Activity - HP
2ce0bc49-bf59-54a7-a221-56df0205defd | note | By - ENG
80a3b809-4a16-5781-8b97-a04ae2c7abfa | signoff | AUTHORITY HOLDPOINT
bd17909b-24fc-567d-8e74-41ab189fc4b3 | checkpoint | 5.01.06 - Backfill Installation
c7c2d1b0-c2f8-5768-8d67-067103ab63da | note | Acceptance / Conformance Criteria - All backfill is to be installed in 250mm lifts and compacted to the following standards.
523bffe5-aaee-5a9b-8e89-14e05f013cba | note | Standard / Specification - GWS - 5.3.3
11658044-8281-56e6-9f67-20faad0299fb | note | Verifying Document - Photo record
ac859c0c-278d-5b8e-a292-46ad56fb0962 | note | Frequency - Each layer
ef9db130-4c9f-5391-867a-972b372090fa | note | Activity - I
a3687b6e-7c6b-53f0-b274-e31e41cd696f | note | By - SUP
a62858e4-ea20-5ed9-923e-9ca82c01b7a0 | checkpoint | 5.01.07 - Backfill Compaction (NDM) (Gap 65)
f8d240d7-018f-5b3f-8c5e-fe7537ae63e0 | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
ad7fa407-e378-5634-ab93-1828e1f82e34 | note | Standard / Specification - GWS - Table 3
84067f73-90f3-5c9f-bcc9-3412062ae46f | note | Verifying Document - NDM Results
215fd151-1567-5313-ab16-40cc8c973c76 | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
b1904192-86c4-5dc0-983d-0c4625692197 | note | Activity - H
1759d2ab-8aaf-5e44-8271-0bca9708cfa4 | note | By - SE
8ecddfdf-b738-562d-924c-6d9e94ab9029 | checkpoint | 5.01.08 - Clegg/Proofroll (Gap 65)
98614c55-f750-506f-9503-10c3e30e1881 | note | Acceptance / Conformance Criteria - Proofroll of each layer. 4 Cleggs to be undertaken per NDM test. Engineer to proofroll/inspect final layer of load transfer platform.
2f9fe1ac-2fbc-57be-ac76-85de65fe652e | note | Standard / Specification - GWS - Table 3
4e604154-4a81-55e9-b377-2b88c923b018 | note | Verifying Document - Clegg Result sheet
bd438c47-31e5-566a-944c-a5b5c76088c7 | note | Frequency - Each layer - final layer to be inspected
774d86f1-ba7c-50b6-94d6-30bf5a948c3f | note | Activity - HP
7364a921-2ff7-5c35-9159-3054bb9afa4c | note | By - ENG
bb7a1071-2609-5dff-a667-8d15d7b69bbd | signoff | AUTHORITY HOLDPOINT
79e53a18-7c06-522e-b64b-df9faebbb82e | checkpoint | 5.01.09 - Scala Penetrometer (Hinuera Sand)
0de6b358-0f29-58af-ad62-e6befe37e01e | note | Acceptance / Conformance Criteria - Minimum average value over 5 tests of 5 blows per 100mm, minimum single value of 4 blows per 100mm
723574f2-3e35-56ba-972d-31c4f942de55 | note | Standard / Specification - GWS - Table 3
950d9fe5-4c1e-50e8-b794-ead1b2cf7d81 | note | Verifying Document - Scala Results
1f645c31-308b-548f-8dde-196580b6b892 | note | Frequency - 1 per 500m3, 1 test per 0.5m lift per 20m run of wall
6720fe90-9a00-56ad-8968-01ae35b290ac | note | Activity - H
714be469-f8be-5424-9050-e3ecf0a94400 | note | By - SE
1fa40bf2-514b-5091-af6a-f9081489cccb | checkpoint | 5.02.01 - Level founding platform
9c8eb987-df2c-50a7-95ae-edac73b9c3d4 | note | Acceptance / Conformance Criteria - The Contractor shall construct a 200 mm thick levelling pad on top of the load transfer platform to create a level founding platform to accept the MSE retaining wall.
ca1e2ed9-2c2b-5b18-a741-e994b2b723df | note | Standard / Specification - PS - 12
43ce2579-fec0-5318-87c6-4a8e9b3a20bb | note | Verifying Document - Site Photo / Checksheet
1b680dd9-e479-578f-bbde-69c1729e3ee9 | note | Frequency - Prior to Stone Strong block installation
a9c7ed43-8613-5ebc-857e-690eca1a5585 | note | Activity - I
b5fbdddf-aa08-5620-83bd-7340b7acd380 | note | By - SUP
70fcc93e-5f6b-523c-8390-a613fc5c0dd4 | checkpoint | 5.02.02 - Installation of blocks
90ef02e4-593b-5fb9-a2a3-b68fe5c81ecb | note | Acceptance / Conformance Criteria - Blocks to be installed to the height and location as detailed on the construction drawings. The table below details acceptable tollerances.
32d1b68c-0bfe-5bb2-abd7-26cb71e423d5 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
b12d3329-7987-5247-b922-ec1c92c9ed00 | note | Table 4: MSE Tolerances
dfcb71bb-f02b-56d1-bd66-3ef672ac4eab | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
8d01ee4b-e521-522d-8a7a-9bd9cf9cf39e | note | Element ¦¦ Vertical Position ¦¦ Horizontal Position ¦¦ Vertical Alignment ¦¦ Horizontal Alignment
c9b8de3b-7e7d-54be-a648-be447dff7dc0 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
18339fca-9026-508b-96e4-2fb4655e0c6a | note | Soil Surface ¦¦ ± 100mm ¦¦ N/A ¦¦ N/A ¦¦ N/A
7e0bf557-a381-509d-8795-4822c3e0c715 | note | Facings and wall structures ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
a3fbd331-d3ef-513a-8a89-9470f7fdb303 | note | Footings or supports ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
3c7b2ddd-a24b-5b7f-9049-436a8e69bce4 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
07037d56-3fae-5229-bb84-bcd2d797e781 | note | Standard / Specification - GWS - 5.4
48c1e9a8-8b89-527a-91c8-f72b261b72e0 | note | Verifying Document - Site Photo / Checksheet
54fda68a-448a-5dcd-8ed6-0a86c20b0e5a | note | Frequency - Each layer
913f0a58-b1ca-5bfb-8468-b952a9389447 | note | Activity - I
2396be86-4697-57ce-b7b9-b3a1d1c2257a | note | By - SUP
0738a9e4-1da3-543c-acc0-e874f185dfd9 | checkpoint | 5.02.03 - Paraweb Installation
0bef5334-c77a-5d85-8b74-f29c3c8ca7fc | note | Acceptance / Conformance Criteria - The correct number of parawebs are to be installed as shown on the construction drawings.
622c6a80-827b-564b-a1b0-826cc8553560 | note | ○ Para web is to be placed flat or with a 1% fall toward the rear of the wall. The Para web must be free of wrinkles and lightly tensioned prior to and during placement of backfill. Shallow trench to be dug toward the end of the paraweb, pin to be used to pull paraweb taught prior to backfilling.
50d68f77-c004-52f2-a57e-49698bdf2f38 | note | ○ The Para web must be continuous over the design embedment length and no joins are permitted unless adequately lapped and spliced according to the Manufacturer’s instructions.
8668a89a-332f-5adb-87ff-04813367b41f | note | ○ 150mm of fill cover is required before construction equipment can travel over the area
302495c3-5f3f-555b-bf19-8ba352b3798f | note | Standard / Specification - GWS - 5.3.2
e0f8ebd4-b7ce-5d74-8e8e-61d1497a1d0e | note | Verifying Document - Site Photo / Checksheet
19a36404-73ee-57c2-ad94-ea23f2a50577 | note | Frequency - Each layer
4ed90da9-8014-54fc-aff4-4d93fce754c9 | note | Activity - I
62c634e1-5096-505b-a986-ddb7ae13ae72 | note | By - SUP
2dcf3162-5511-56d9-bc4e-c15f2eadb5ea | checkpoint | 5.02.04 - Geocomposite drainage board
c4be583a-f1eb-5cd7-8b53-c99e616f142c | note | Acceptance / Conformance Criteria - Geocomposite drainage board shall be installed continuously along the back face of the block facing of all MSE retaining walls using an approved adhesive recommended by the manufacturer. Check for correct layout, orientation, and any damage prior to backfilling
78a5af09-b43a-593b-9bb0-cca35aca7587 | note | Standard / Specification - PS - 12
118e3434-7671-5ed3-835d-7fc4d8175aa3 | note | Verifying Document - Site Photo / Checksheet
660025ef-3ab6-58f4-8765-86925343e3ef | note | Frequency - During Installation
f0897641-79a2-502d-bcea-6e4441ba74e5 | note | Activity - I
d79c9d3d-ecfc-5167-a08b-44cff7e6fe7e | note | By - SUP
2eb38c46-8cb7-54e6-b99a-4b79e2de53ac | checkpoint | 5.02.05 - Drainage Outlet Installation
a3d090c3-4428-5e0a-b209-adf7336af691 | note | Acceptance / Conformance Criteria - Drainage pipe wraped in filter sock to be installed along the base of the wall. Drainage outlets shall be connected to the reticulated stormwater system or other approved outlet structure at the discretion of the design engineer
6cfacb22-26fd-5135-a015-17dab1cd0170 | note | Standard / Specification - GWS - 5.3.4
2f5a5615-723b-5d5e-8c70-f4b89d64455c | note | Verifying Document - Site Photo / Checksheet
f38b6aaa-750a-5eb3-81e7-0481324cad07 | note | Frequency - During Installation
63a09817-83ab-53aa-95b2-fbb6cbd5e6e6 | note | Activity - I
64e8f6bc-35c8-50a6-aeff-2ac4d35244b0 | note | By - SUP
1034be8f-e2b5-5d56-ad2f-7ae17d328c57 | checkpoint | 5.02.06 - Backfill Installation
68b82bbb-bd2b-500a-9ace-74ec7c5ebb50 | note | Acceptance / Conformance Criteria - All backfill is to be installed in 250mm lifts adnd compacted to the following standards.
31c539fd-4460-53ad-bfdf-2e97fcb8b655 | note | Standard / Specification - GWS - 5.3.3
633cfa75-f662-58c2-a120-4024e3c6b0a4 | note | Verifying Document - Site Photo / Checksheet
6d4d0c18-479a-58d2-a5ec-cf710b5f1faa | note | Frequency - Each layer
5972cd9e-2fb0-509b-bef1-f765dd7cccb7 | note | Activity - I
b83ffa94-0016-517c-bb97-f82c899c2703 | note | By - SUP
35abd0c3-22bf-5ac6-b46a-a8a9993e38f8 | checkpoint | 5.02.07 - Nuclear Densometer (NDM) (Gap 65)
f13ff92b-3515-51d0-a988-a8689f2dd02b | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
4a4d2b6a-8a2e-5174-a75c-a0f7cf753f69 | note | Standard / Specification - GWS - Table 3
6554928e-3918-5c68-b1ac-81e6cb332423 | note | Verifying Document - NDM Results
98493087-ecca-5702-9b92-25f0664f918b | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
554f611d-c99e-592d-bee2-843015f016da | note | Activity - H
ccf5b3da-cdf5-5795-9145-2a6b32d69f7e | note | By - SE
bbcbe397-d3aa-5f25-b343-5d2e0f43e6f8 | checkpoint | 5.02.08 - Clegg/Proofroll (Gap 65)
003d8931-bc62-5135-b7be-32aa75313eac | note | Acceptance / Conformance Criteria - Proofroll of each layer. 4 Cleggs to be undertaken per NDM test.
3874ad51-8f8b-575e-9170-0695e7fdc9bc | note | Standard / Specification - GWS - Table 3
4d765a6d-f986-55ae-a453-6684618ffc0e | note | Verifying Document - Clegg Result sheet
12a070cf-7dac-57ab-a68e-41e36105e8a1 | note | Frequency - Each layer
0313e548-65cb-50f0-85a4-231e5e4b576b | note | Activity - H
dcd71dcd-85cb-5dee-945b-745855383c9a | note | By - SE
e466154a-3525-5208-8981-a1953fc53c31 | checkpoint | 5.02.09 - Scala Penetrometer (Hinuera Sand)
4efbde40-a847-5874-adf2-744ee100a9d9 | note | Acceptance / Conformance Criteria - Minimum average value over 5 tests of 5 blows per 100mm, minimum single value of 4 blows per 100mm
78e0595b-f746-5ce0-b84e-30718f228843 | note | Standard / Specification - GWS - Table 3
afe343f9-b761-5bae-855e-8f1669892985 | note | Verifying Document - Scala Results
3242c858-14d8-526d-8fce-da11c78994d1 | note | Frequency - 1 per 500m3, 1 test per 0.5m lift per 20m run of wall
3b61ccc5-55eb-529c-ab6e-c36b4195619a | note | Activity - H
f0eff603-e0e2-56fe-a76e-7f727936301e | note | By - SE
ebac0833-9543-57fd-b1da-1aaccbed6ef2 | checkpoint | 5.03.01 - Settlement Pins
6be00cc8-35f7-58b4-9aac-3e2f7da37af6 | note | Acceptance / Conformance Criteria - Settlement pins shall be installed within 24 hours of reaching design subgrade level. Survey measurements are to be undertaken to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
a15120ed-c718-5d31-baef-0c8bf1202b40 | note | Standard / Specification - GWS - 6.3
c328b2c9-2589-5ea8-a5a5-29f4fbb679b6 | note | Verifying Document - Survey Results (in paper as well as electronic format)
c44e4189-f4cd-5c8a-94c5-7045748d766f | note | Frequency - Weekly for the first month, then monthly
976b9f25-82ac-5367-a238-3dc87271bf9f | note | Activity - R
f42af643-c395-58bc-a22e-585a9ebaf8f8 | note | By - SV, ENG
4135a9de-8aa7-57ed-8b36-d80ac6243fe6 | checkpoint | 5.03.02 - Settlement Targets
08507682-93c4-5452-97e2-8150c20bfab6 | note | Acceptance / Conformance Criteria - Targets shall be fixed immediately after completion of the first row of retaining wall blocks at each location and the initial baseline survey reading made prior to the subsequent row of retaining wall blocks placed.
480b8b47-6145-593e-9237-ad72d6db0cee | note | ○ Survey measurements are to be undertaken to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
28d6069c-16cb-52bf-8b0f-2855091f5e5d | note | Standard / Specification - GWS - 6.4
4d86ed34-2564-57a8-98f7-1460af0da7f9 | note | Verifying Document - Survey Results (in paper as well as electronic format)
ee49474b-e7c1-5904-abb4-5613386fddb2 | note | Frequency - Weekly for the first month, then monthly
67d177c4-6ae0-544d-8cca-4963c96f1e14 | note | Activity - R
cd844407-15dc-5abf-ab6a-581e0b72a97e | note | By - SV, ENG
ae4acacc-e86b-5197-a5e0-e058937ce41d | checkpoint | 5.03.03 - Engineers Approval
129d7748-60d8-5b2a-9b1a-b1ea68c4b7f9 | note | Acceptance / Conformance Criteria - Geotechnical engineer assesment required before commencement of Pavement construction
9c535da8-1110-57cf-bd8b-4b3a4cb67048 | note | Standard / Specification - BBO
c03b5ad1-5238-50bf-94b3-a6d95d7561a5 | note | Verifying Document - Written approval
43a8c2cd-762b-5905-a363-f38629034b45 | note | Frequency - Prior to pavement construction
e735b9e1-02c3-5526-9bcd-5fbbcfc69b4f | note | Activity - HP
655aedea-3982-579f-8070-73df15d33ff2 | note | By - ENG
d0174289-54fd-51ad-9124-6c7c9fcb16c6 | signoff | AUTHORITY HOLDPOINT
cd33a7f8-9b6c-5422-93be-dcae98eaa460 | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
c67c36c3-6604-547c-97e6-f35b09622953 | checkpoint | 6.01.02 - Draft Redline Drawings
fa2526ab-b8b9-509f-b4ec-43a5d96dfe8c | note | Acceptance / Conformance Criteria - Draft as-builts completed on the completion of MSE wall including red pen mark up to IFC drawing changes.
1b08806c-38dd-54fa-9d51-79482791edaf | note | ○ The draft as-builts shall be provided on a continual basis throughout the project for verification by the Engineer, and as a minimum shall be provided in electronic form prior to application for Practical Completion.
71c7e106-4037-5b64-8bc7-4d64f708bf04 | note | Standard / Specification - PS 2.2.17
a9791038-927a-56e8-92bc-092094da73cb | note | Verifying Document - Draft As-Builts Drawings
8b640c55-480e-521c-b672-75b78b29968d | note | Frequency - Prior to PC
66bc92ec-3655-5cdd-82f9-c85ade2d83b3 | note | Activity - H
0f0c9cf5-c28d-5026-9f36-cb989728faad | note | By - SV / PE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
7e370288-25ad-5264-bf45-2471320d8a2d | checklist | ITP - Retaining Walls - Rev F | itp | ITP - Retaining Walls - Rev F
8c9335a7-3af5-5e47-a887-39a89ff08c27 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
8a0d1e79-aa30-51a2-ba44-7e773615758e | note | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
12169806-1115-5ff0-ba3e-50d4314ff524 | note | Standard / Specification - Downer
af51c198-73b7-5f4f-be92-be712d6ddde9 | note | Verifying Document - Construction Pack
48603452-d2df-56b3-9899-8d1d2c56c91f | note | Frequency - Submit 10 days prior to commencement of works
5f4f30a6-272d-5089-ab98-f393eefa5a13 | note | Activity - HP
338fe5c7-f79d-5c0c-82b7-78c44e04ec25 | note | By - ENG
ca255811-cbe5-57f5-8b49-d49ad30655f3 | signoff | AUTHORITY HOLDPOINT
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
dddde4ec-2ce4-5cca-b048-84ba820ffcc4 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
639f83cc-1519-586e-9361-968b514b9a9f | note | Standard / Specification - Downer
0c896799-a5c4-516e-b4c3-42555bb915b1 | note | Verifying Document - Survey Records
20c85229-60c2-503f-9538-b2beb431a551 | note | Frequency - Prior to Works
86423e76-30d9-525d-8808-f96fbd6ed7fc | note | Activity - H
ce2fcaac-b474-5060-99e2-e7888842fb8a | note | By - SV
a24a2c58-bf6f-5474-883c-40044bad1fc7 | checkpoint | 3.01.03 - Service Location
f5628cab-5077-5102-9f11-504f9c8b3bff | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
27fe4e06-bf24-51ae-ae35-8c94c3add973 | note | Standard / Specification - Downer
f3850256-943c-5b46-b361-b26f02b009ed | note | Verifying Document - Excavation Permit
32418d8f-d2d7-54c7-b906-b4de1c2fcd78 | note | Frequency - Prior to Excavation
102a84f6-f432-51ed-a382-1be410f6a54a | note | Activity - H
4bb0a952-5ee1-5e53-9b56-e6e11ef925d0 | note | By - SE
0a214a7a-124a-5898-a837-e29e83751df0 | checkpoint | 3.01.04 - Internal Permits
e0db3084-6898-5399-a920-c969ddebc22d | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
08d928a0-089f-5a43-87c8-7d5b384d90ee | note | Standard / Specification - Downer
9fecac0d-4892-5ecb-94e5-ab2719336490 | note | Verifying Document - Internal Permits
b865ee54-2bb4-50c9-b34c-86b0bf4e81f7 | note | Frequency - Prior to Excavation
068c0dd7-62c5-5950-98c8-e67082eb895b | note | Activity - H
6ab2c64e-5cde-5a51-ac12-f1744f451166 | note | By - SE
917e2881-0901-542f-ae25-686bf9c47009 | checkpoint | 3.01.05 - External Permits
a3982939-a09b-5f65-930a-83594b1a59aa | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
b2d0d73e-f7e2-5875-b911-e85ff1d240c9 | note | Standard / Specification - Downer
011655fb-a45e-501f-86b9-6cc831676b0d | note | Verifying Document - External Permits
16b6c62e-5868-5a39-b7c0-20e9059ab261 | note | Frequency - Prior to Excavation
9e8a8bbc-0fe7-57ea-97a1-ecb01eafcbff | note | Activity - H
546353b2-ed6c-54d3-bf31-dade141b15f2 | note | By - PE
a1302970-0389-558d-b43c-67b14bbfc27a | checkpoint | 3.01.06 - Approved Construction Drawings
60849391-f32f-54e4-8e16-62402da84e44 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
045af579-5f15-52c8-9546-02f8db13abb9 | note | Standard / Specification - Downer
904b65ac-f718-589a-95c3-4f074bd25870 | note | Verifying Document - IFC Drawings
6084e46b-70e4-51cb-b498-19cfd82da7e1 | note | Frequency - Prior to works start
68fc39e6-7547-5e92-8708-44c16e49cfdd | note | Activity - H
205ac354-d64b-5142-beea-3b7eaa98ecd2 | note | By - PE
34b3d838-f63d-5499-aad4-14b7c1eb24ae | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS
1437ac3f-e25b-5932-8866-3f1e2bab518b | checkpoint | 4.01.01 - Stone Strong Block Molds
2bd89bae-07b6-5306-a504-fa7d87898321 | note | Acceptance / Conformance Criteria - Stonestrong blocks to be supplied by an approved supplier. The Contractor shall liaise with the Principal-appointed Cultural Artist to coordinate carving of the supplied blanks and the production of moulds & blocks
5be549d7-8210-58bc-a46b-b4bdbbefdcaf | note | Standard / Specification - PS - 12
2e6b8cf7-45ab-51bb-a94d-de3b08c4ed0a | note | Verifying Document - Conforming Molds Post Carving
8cdfbb95-eb11-56c4-83d8-dc0efbed5003 | note | Frequency - Before Installation
7dbec491-e5e0-5c7d-b569-801b75228eed | note | Activity - H
1d495b03-9a7d-5d9a-bf8d-8c1d1b108639 | note | By - PE
076f2f53-aa02-563d-89c7-7a03bd974c84 | checkpoint | 4.01.02 - MSE retaining wall backfill and drainage Material
5f015f0a-32ca-5098-8f7e-01b6ab150fe8 | note | Acceptance / Conformance Criteria - Backfill is to comprise a well graded, granular material such as GAP65 or site won Hinuera Sand, which must be free of any deleterious material. Sand backfill shall have a fines content (less than 0.075mm diameter) of no more than 10%.
bf2155e0-85ae-5718-a69c-542b4ce59d21 | note | ○ Drainage metal to be 20/40 drainage aggregate or similar approved by engineer.
75fab186-5801-5e68-9100-4a34687cbb97 | note | ○ Labratory MDD (x2 per material type) at standard compaction
8f7afa0b-5b75-5f6b-92de-0cd7f64fce3a | note | Standard / Specification - GWS - 5.3.3
83502b73-a1c5-5a72-a2a1-987eb3f77198 | note | Verifying Document - Lab Results
e8b815d5-61b7-5376-917d-312c8aa6e454 | note | Frequency - Prior to works
b04a20ad-42ff-541f-bf2c-d10818b0936e | note | Activity - H
015ea7d7-f005-5d0b-bdf4-46bd41480460 | note | By - PE
05bce6c9-76c8-5aeb-94f0-6addb618072e | checkpoint | 4.01.03 - Geogrid
c06baadf-ef00-5ca8-bca2-64a9f1f46702 | note | Acceptance / Conformance Criteria - Geogrid to be Miragrid GX200/30 or similar approved
4478a1a1-70ad-5088-b9c4-8a7ddf82c58f | note | Standard / Specification - GWS - 5.3.1
144d0adb-5334-5c39-a0c9-92958b3efaae | note | Verifying Document - Datasheet
1ea05c3d-ee6a-524c-8230-329e985e9c82 | note | Frequency - Before Installation
072791d9-790d-52c3-aad4-c4a3e5c2c5fa | note | Activity - H
6b54ee3c-ecfb-57bf-9a29-f9dcb8d80120 | note | By - PE
6e039cf8-38d9-583d-81da-a16916cec0db | checkpoint | 4.01.04 - Para web
5934a350-5f2e-5022-8dfd-c10537e5288a | note | Acceptance / Conformance Criteria - Paraweb to be the correct grade: Paraweb 2D-50
f82987c4-1411-5e76-83d5-61542e7b1c87 | note | Standard / Specification - GWS - 5.3.2
209066d1-282d-5039-90e0-c0d53068ff9c | note | Verifying Document - Datasheet
0a1827ff-240b-53b7-a030-375286a892cf | note | Frequency - Before Installation
c2e8d5fd-723a-5ef3-b4a6-d9041b635f41 | note | Activity - H
5420955b-884e-51fd-b9d9-29af2ff49edc | note | By - PE
e132fae1-e9b4-511f-a4c3-4d0a9e983806 | checkpoint | 4.01.05 - Drainage Pipes
bbf9a41e-2354-54ca-9352-18bebc8e6b8e | note | Acceptance / Conformance Criteria - Shall be 160mm diameter NZTA F/2 compliant smooth bore perforated corrugated pipe with filter sock
93e7a20f-f527-5dfd-acd2-d1e2db74cc60 | note | Standard / Specification - GWS - 5.3.4
44558f33-7964-532d-8691-62d48d83acaf | note | Verifying Document - Datasheet
5da2d153-ac8e-55a4-a9e8-94503c1b61f0 | note | Frequency - Before Installation
929dcb63-f7b4-5c8a-bfdd-3ca7a972b9ed | note | Activity - H
dd3d1dc4-897b-5ec6-ba98-9ab5fc052a03 | note | By - PE
e7adda1d-89e3-5dee-b757-9e3f5f015cac | checkpoint | 4.01.06 - Geocomposite drainage board
646bb77c-96b0-50dd-a508-936005ea6d9a | note | Acceptance / Conformance Criteria - Shall be Bidim A39 geotextile or similar equivalent
dcdea1a2-f37e-566e-9c49-5d39f3a8b913 | note | Standard / Specification - SS - 12
5a3869e5-a16f-533b-812f-86cb749ae79f | note | Verifying Document - Datasheet
e84e1b4b-607c-540b-b627-aa5ee4b4bee6 | note | Frequency - Before Installation
115e5717-fcfc-5841-8335-d0172b615d64 | note | Activity - H
5c2be74e-8680-5260-a593-221b1b1dc1fa | note | By - PE
7d04c6ae-3cb1-5c0a-9796-1cc24d0858ea | section | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS
838e6cd4-76c0-5235-b72d-9a0f1a44ed66 | checkpoint | 5.01.01 - Excavation to subgrade
98c4fafd-ab95-510b-9274-83170e7fb1ee | note | Acceptance / Conformance Criteria - The foundation materials are to comprise natural Hinuera sand material, stiff Hinuera Silt or imported clean sand and must achieve a minimum of 4 blows per 100mm when tested with a Scala penetrometer. Any exposed silts must have vane shear strengths greater than 70kPa.
56174934-ed1b-5740-8f1b-6dcfb3a2cf63 | note | Standard / Specification - GWS - 5.2
e135ce3d-fd9f-5a99-b2f9-9d52d6c35183 | note | Verifying Document - Scala Results
fa1199dc-6eab-5131-af89-dbbde3ab9d25 | note | Frequency - Every 10m
93a2abe7-a982-5303-a0e4-50f54484400e | note | Activity - H
4a8c3298-ba99-5b17-ac28-48838788e2e1 | note | By - SE
c4674b26-69c0-5262-a38b-746e46d5825b | checkpoint | 5.01.02 - Foundation Approval
b103f257-35bb-5294-a2a6-4f86aee86d31 | note | Acceptance / Conformance Criteria - Results of the foundation material testing shall be supplied to the Engineer for approval and the prepared ground shall be inspected by the Engineer. Construction may not proceed until receiving Engineer’s approval.
8c864b0f-f0a3-595f-8266-70e555cee82f | note | Standard / Specification - GWS - 5.2
01bbc8ec-34b7-5895-9e25-71a8c9322222 | note | Verifying Document - Approval
41e279c5-4f96-5aa2-a9d6-b9714b99a680 | note | Frequency - Prior to proceeding. Min 48h notice to Engineer
7cfa6829-b695-5c46-9e68-e9c742de5bcf | note | Activity - HP
2feb039d-a053-5cbe-86e2-9b523e9ec7cf | note | By - ENG
2ddb755a-f329-5467-ab5f-6a7fca5b3f95 | signoff | AUTHORITY HOLDPOINT
19ca66fa-e5a2-5cfc-b467-61317531b98d | checkpoint | 5.01.03 - Undercut subgrade
80ceed1b-5540-5ba5-8e69-aabd21c7c4d1 | note | Acceptance / Conformance Criteria - Any unsuitable materials, such as uncontrolled fill, contaminated materials or any weak or organic materials, shall be undercut and replaced with compacted granular fill (WHAP65 or equivalent) or Hinuera Sand. Surveyor to capture extent of undercut (if any) to include in asbuilt.
fe9af0e2-afc8-58e2-86ac-8a827f1e04f2 | note | Standard / Specification - GWS - 5.2
16b49003-06c2-577d-a206-032e2453f7c1 | note | Verifying Document - Survey Record/ Photo record
9a7c2aa7-d9db-58b4-aadc-5c7ff886dffa | note | Frequency - If required
28e9d57c-b860-5593-a71d-e9e4ede87632 | note | Activity - I
54ca8536-8ed8-56b3-97c9-264f25e0f011 | note | By - SE
11e626b6-30f1-58a8-84fd-9bad3add61ff | checkpoint | 5.01.04 - Undercut backfill compaction
24a7cc88-aa3d-55c8-bc85-b0d51bf4e1a5 | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
eeeb1e4d-ef2e-57a5-92df-6e015891d7e6 | note | Standard / Specification - GWS - Table 3
89e8e2fb-8c6e-5f0e-824b-142686613834 | note | Verifying Document - NDM Results
7f2d9b74-c157-5148-821d-bf10570eaa83 | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
01e4886b-f8ea-5200-85aa-46b2e0927993 | note | Activity - H
12ce8d52-3adb-53a3-b4eb-1c300b027d18 | note | By - SE
429c469f-d0be-5299-88a0-616d51d283a0 | checkpoint | 5.01.05 - Geogrid Installation
4416f2f8-5c15-57a0-8811-a39439e0f963 | note | Acceptance / Conformance Criteria - Geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets. Engineer to inspect 1 layer prior to backfill.
abe05164-12c7-5ef3-80ef-9c9cad1fa87f | note | Standard / Specification - GWS - 4.1
63ee82fa-9a46-521b-b7a9-09a559835c33 | note | Verifying Document - Photo record
3510d9fe-2161-50d8-b854-c10320454d31 | note | Frequency - Each layer - 1 layer per abutment to be inspected
325c9edb-3634-5b38-a1ec-8a9ec1144d30 | note | Activity - HP
c5b7876f-6bc0-53f2-b207-4773516e899e | note | By - ENG
80a3b809-4a16-5781-8b97-a04ae2c7abfa | signoff | AUTHORITY HOLDPOINT
bd17909b-24fc-567d-8e74-41ab189fc4b3 | checkpoint | 5.01.06 - Backfill Installation
899e5bd8-adca-5159-96db-eb250698bf99 | note | Acceptance / Conformance Criteria - All backfill is to be installed in 250mm lifts and compacted to the following standards.
85edcc97-c060-51e9-bf7d-481a4344728c | note | Standard / Specification - GWS - 5.3.3
40d64713-6f83-55a1-b70f-66fa466ddd1c | note | Verifying Document - Photo record
cd63bee6-886d-509d-8958-fa0e37587f60 | note | Frequency - Each layer
2fa77c66-32c4-5683-86b7-11496ca08d24 | note | Activity - I
15afce54-64d6-571f-a5dd-803ba962ca64 | note | By - SUP
a62858e4-ea20-5ed9-923e-9ca82c01b7a0 | checkpoint | 5.01.07 - Backfill Compaction (NDM) (Gap 65)
87407d10-62b7-5ff5-ba90-5593726c5faa | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
30f2408f-adbe-53df-aa2c-74ef756e47a1 | note | Standard / Specification - GWS - Table 3
0b85a524-7f9b-5708-bc76-3abb9d4be284 | note | Verifying Document - NDM Results
eb4bbfde-b9a0-59ca-b3f1-42814e28d5a6 | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
e4bbee84-89d6-50b3-ac3d-d4e33075692f | note | Activity - H
5d10d11b-0675-5e18-8326-8a2ebbdb6366 | note | By - SE
8ecddfdf-b738-562d-924c-6d9e94ab9029 | checkpoint | 5.01.08 - Clegg/Proofroll (Gap 65)
6af11bef-2749-5a8a-8a5a-fff40f1bb2ab | note | Acceptance / Conformance Criteria - Proofroll of each layer. 4 Cleggs to be undertaken per NDM test. Engineer to proofroll/inspect final layer of load transfer platform.
2f991953-3d11-5eb4-ba38-2cfe91f0bee8 | note | Standard / Specification - GWS - Table 3
6d8ab319-c5ea-5f8b-bc11-b91a60e1c8ff | note | Verifying Document - Clegg Result sheet
e1ef96ea-02ac-5c4c-9717-9314287dfdc8 | note | Frequency - Each layer - final layer to be inspected
7cbbabb3-ac98-52a5-abc3-2deb617bbf37 | note | Activity - HP
cf5ab66c-e5fe-583b-8691-03257766dc41 | note | By - ENG
bb7a1071-2609-5dff-a667-8d15d7b69bbd | signoff | AUTHORITY HOLDPOINT
79e53a18-7c06-522e-b64b-df9faebbb82e | checkpoint | 5.01.09 - Scala Penetrometer (Hinuera Sand)
cde21a07-5d67-5ca1-9a7f-b339b50bc5e9 | note | Acceptance / Conformance Criteria - Minimum average value over 5 tests of 5 blows per 100mm, minimum single value of 4 blows per 100mm
972a1ee8-7b07-5741-89ee-e1b26a5ed84e | note | Standard / Specification - GWS - Table 3
41a92435-c912-5c80-9abf-7fe925708fdd | note | Verifying Document - Scala Results
cf752176-b0a8-5b9a-b7b8-75529c330a51 | note | Frequency - 1 per 500m3, 1 test per 0.5m lift per 20m run of wall
bd1f19b6-b73f-56e2-be79-b5258d2a4ce7 | note | Activity - H
1b40fc59-8332-5ce0-908e-9cbe7280ce66 | note | By - SE
1fa40bf2-514b-5091-af6a-f9081489cccb | checkpoint | 5.02.01 - Level founding platform
cd3652ed-252c-58b6-bcc5-2a17f3e24677 | note | Acceptance / Conformance Criteria - The Contractor shall construct a 200 mm thick levelling pad on top of the load transfer platform to create a level founding platform to accept the MSE retaining wall.
361f02ab-fbd9-50de-99da-cf6960afddf7 | note | Standard / Specification - PS - 12
06408132-2b51-593f-9345-3f6af46d9fea | note | Verifying Document - Site Photo / Checksheet
a4b51cc9-1120-52fa-bc34-10b3e5a57a98 | note | Frequency - Prior to Stone Strong block installation
5745bbcd-406f-5d59-b220-74e9d988a65e | note | Activity - I
8f522c83-6a6b-521c-9eae-0f46bf135fae | note | By - SUP
70fcc93e-5f6b-523c-8390-a613fc5c0dd4 | checkpoint | 5.02.02 - Installation of blocks
82f65001-8ff9-5f81-b3aa-8868c968a8eb | note | Acceptance / Conformance Criteria - Blocks to be installed to the height and location as detailed on the construction drawings. The table below details acceptable tollerances.
6f3ab58a-1676-5555-804e-c46e1b83cc25 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
aaadf9ec-7382-571e-9fda-0ba6552d382f | note | Table 4: MSE Tolerances
43c7f889-085c-5eec-840e-f3ba927d88d9 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
1bc65494-f9e6-5e2e-94ec-9988e9527c8b | note | Element ¦¦ Vertical Position ¦¦ Horizontal Position ¦¦ Vertical Alignment ¦¦ Horizontal Alignment
a0f0bf7c-c8cf-5f63-9415-9e0dde785dfb | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
5078d3e4-8089-5243-ac7f-1f93b304c28c | note | Soil Surface ¦¦ ± 100mm ¦¦ N/A ¦¦ N/A ¦¦ N/A
b657d697-7696-53ab-b5bd-0d38b6d42719 | note | Facings and wall structures ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
bb919e11-3810-5383-8a20-35ee44bd53f8 | note | Footings or supports ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
63c06ce9-9952-5a63-a6e3-96a18dcdfb35 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
96022c5e-a42b-5b78-b512-7f105236804a | note | Standard / Specification - GWS - 5.4
78c121e1-c205-57fa-aee8-157df0802bd3 | note | Verifying Document - Site Photo / Checksheet
5e801a16-ca92-5ad3-a6e3-7164a3742bfa | note | Frequency - Each layer
148c9f71-1619-543a-8ac0-328293eeafa0 | note | Activity - I
fb3bb93e-e224-5154-ab88-dd27f30a4a78 | note | By - SUP
0738a9e4-1da3-543c-acc0-e874f185dfd9 | checkpoint | 5.02.03 - Paraweb Installation
b2308c38-b919-5d53-ac15-1229842d1da0 | note | Acceptance / Conformance Criteria - The correct number of parawebs are to be installed as shown on the construction drawings.
19388c80-71ce-5f88-b8e0-e795761d0f72 | note | ○ Para web is to be placed flat or with a 1% fall toward the rear of the wall. The Para web must be free of wrinkles and lightly tensioned prior to and during placement of backfill. Shallow trench to be dug toward the end of the paraweb, pin to be used to pull paraweb taught prior to backfilling.
f89b9399-2faa-5b45-bff7-5e47f63da2f9 | note | ○ The Para web must be continuous over the design embedment length and no joins are permitted unless adequately lapped and spliced according to the Manufacturer’s instructions.
5700ca77-1484-5112-9811-8f89dd8ddf31 | note | ○ 150mm of fill cover is required before construction equipment can travel over the area
45bca719-125c-5539-a255-2122fa63fb47 | note | Standard / Specification - GWS - 5.3.2
edb3ac52-82b7-529f-be91-f62e742f6e5f | note | Verifying Document - Site Photo / Checksheet
81123ea4-c795-5c40-b10f-fbf99c68426b | note | Frequency - Each layer
5fe8ff9b-e494-5042-812f-c84ae57f4f72 | note | Activity - I
10f788f3-9055-53de-8e2d-1687d0b95e68 | note | By - SUP
d7e05ad4-017a-5c53-8850-a7a729d14f34 | checkpoint | 5.02.04 - Geotextile
f1a8bb54-9914-5908-800a-019f85bc7027 | note | Acceptance / Conformance Criteria - Geotextile to be placed against rear excavated face with a minimum overlap of 400mm between adjacent geotextile strips. Further Geotextile required to separate drainage aggeragate and MSE wall backfill, if sand is used. Short widths of geotextile to be placed across the internal open join area on the rear face of each Stonestrong block join to contain internal block void hardfill. Geotextile to be used to block paraweb voids within Stonestrong blocks that are not in use.
94cc05b3-7ed4-549e-b03a-e2ee7b360416 | note | Standard / Specification - SS - 5
647f2bf3-b023-5467-aedc-97bbb0515d40 | note | Verifying Document - Site Photo
7279ff2c-aff4-5b1d-a3f4-f63375d504cb | note | Frequency - Each Layer
a7b243d3-c6cb-535d-90b5-65a181495255 | note | Activity - I
bd118e8a-bc42-5377-b62a-9b6acb61244a | note | By - SUP
2eb38c46-8cb7-54e6-b99a-4b79e2de53ac | checkpoint | 5.02.05 - Drainage Outlet Installation
9ee8df9f-b706-55ee-8519-02e9f3ab549c | note | Acceptance / Conformance Criteria - Two x 160mm Drainage pipe wraped in filter sock to be installed along the external perimeter of the Load Transfer Platform.
a8364235-fc92-5b0f-b783-499970ee5864 | note | ○ Drainage aggregate to be placed along external perimeter of Load Transfer Platform for each MSE wall layer backfill, forming a Chimney Drain. Chimney Drain to be a minimum width of 300mm and extend to the base of the Load Transfer Platform.
bfdccc2a-f87a-559a-a09d-f22ca6b2550d | note | ○ Internal block void hardfill to be 20/40 drainage aggregate or similar approved by engineer.
f50624df-79b1-5d2c-a119-85e58c1d959e | note | ○ Additional Drainage pipe wrapped in 0.75m3/m run of drainage metal only required beneath wall embedment at toe of the outside of the wall if the slope doesn’t grade away from the toe of the wall.
a9df338d-dd93-5a01-b470-27f025b047c8 | note | ○ Drainage outlets shall be connected to the reticulated stormwater system or other approved outlet structure at the discretion of the design engineer
ba32300a-18c6-51ad-9b3e-f5c37464fe0b | note | Standard / Specification - SS - 5
53567f00-05db-5a58-917d-b1a978e56890 | note | Verifying Document - Site Photo / Checksheet
6be29782-2749-5e9e-acd2-446695c190cf | note | Frequency - During Installation
342b7fa8-1803-5fd1-9c9b-a45f3d56f346 | note | Activity - I
fd19484e-4527-5d4c-ba92-996f5eaf5baa | note | By - SUP
1034be8f-e2b5-5d56-ad2f-7ae17d328c57 | checkpoint | 5.02.06 - Backfill Installation
af9d4419-c84d-5922-b84f-e4b5f9fba21f | note | Acceptance / Conformance Criteria - All backfill is to be installed in 250mm lifts adnd compacted to the following standards.
2ff5acbc-2441-5914-b466-eceb1bb021f9 | note | Standard / Specification - GWS - 5.3.3
4a7c55ba-2c0a-5085-b17c-dd45445553f8 | note | Verifying Document - Site Photo / Checksheet
30810479-7899-5c37-82a0-b47fdd9f12c6 | note | Frequency - Each layer
123779de-51e8-57df-9006-afe3c5d732e0 | note | Activity - I
8dfe733a-517e-59b2-8b5f-794fa672edb5 | note | By - SUP
35abd0c3-22bf-5ac6-b46a-a8a9993e38f8 | checkpoint | 5.02.07 - Nuclear Densometer (NDM) (Gap 65)
b847ce07-00bc-5608-ad0f-d3a81d9f94ed | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
4328a99a-5536-59cb-b110-ccb710847e94 | note | Standard / Specification - GWS - Table 3
c7971168-a004-5036-9f2b-1ed3ea128222 | note | Verifying Document - NDM Results
e5023db2-34bb-57e5-afed-29b12bed2459 | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
8cdff723-0bb1-5eda-b0dd-3311715e1015 | note | Activity - H
db8b0f3f-ff9c-577e-b319-25d981210cd2 | note | By - SE
bbcbe397-d3aa-5f25-b343-5d2e0f43e6f8 | checkpoint | 5.02.08 - Clegg/Proofroll (Gap 65)
34f46bc0-660e-59a9-87b3-f7d46d61f7b1 | note | Acceptance / Conformance Criteria - Proofroll of each layer. 4 Cleggs to be undertaken per NDM test.
55b742a7-f1db-531f-a649-27c88e7838c1 | note | Standard / Specification - GWS - Table 3
d5b9941f-faf4-5d61-a2c3-0e5aaee11ab4 | note | Verifying Document - Clegg Result sheet
e3522a14-a2a0-5082-bd51-44a43486a497 | note | Frequency - Each layer
240afa7e-52fe-51d3-92d6-41ad2714d903 | note | Activity - H
7ac8ff9e-7fbb-570a-97d4-35d1bbc41844 | note | By - SE
e466154a-3525-5208-8981-a1953fc53c31 | checkpoint | 5.02.09 - Scala Penetrometer (Hinuera Sand)
62504378-93e1-5436-8f83-4677141f4acc | note | Acceptance / Conformance Criteria - Minimum average value over 5 tests of 5 blows per 100mm, minimum single value of 4 blows per 100mm
e2de32a1-2c6d-518a-abca-f3d6ceabb328 | note | Standard / Specification - GWS - Table 3
4977a5a6-2522-5a87-8b18-23854d812a24 | note | Verifying Document - Scala Results
be1fc94d-8950-5572-91b8-2af6e059fc7f | note | Frequency - 1 per 500m3, 1 test per 0.5m lift per 20m run of wall
12ad0ee7-bc51-5cd4-9a23-aa3216f918ed | note | Activity - H
6478289f-1f2c-5ec0-83ab-fedda90f9e95 | note | By - SE
60d12d54-946a-5d14-a179-44f6b0bbe1c4 | checkpoint | 5.03.01 - Tensar Triaxial 170
b7b6b90d-c046-44f6-84e9-98097ed32631 | note | Acceptance / Conformance Criteria - Geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 300mm is required between sheets. Engineer to inspect layer prior to backfill.
24628f91-905b-4919-9547-c3db25e1e6db | note | Standard / Specification - GWS - 4.2
54840355-d1ea-4777-9d5b-6ad907f4fc01 | note | Verifying Document - Photo record
e4c27b20-14a0-466b-932c-f2bfe6c5a0b5 | note | Frequency - Each layer - 1 layer per abutment to be inspected
92855898-8fd4-41e9-9ffc-b8cdb7a3f09f | note | Activity - HP
136c3b84-b512-41df-87e1-dba880b264ca | note | By - ENG
514384b9-8a6a-50c3-9354-b04bfb25986b | signoff | AUTHORITY HOLDPOINT
4d8b933a-5957-55bb-8b21-ef93921ef05e | checkpoint | 5.03.02 - Tensar Uniaxial RE580
0ea32e00-9760-40e8-9fe5-b080daf044a9 | note | Acceptance / Conformance Criteria - Geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. No overlapping requirements when connected with Bodkin joints. Engineer to inspect each layer prior to backfill. Grids must be taut prior to backffilling
8fb0fc4e-66e4-4c9c-b0e4-e4b8640e477c | note | Standard / Specification - GWS - 4.2
f13ceb32-2533-41ac-bfeb-dca8e273f776 | note | Verifying Document - Photo record
022bcb15-4959-4678-b859-596c2cd1f642 | note | Frequency - Each layer - 1 layer per abutment to be inspected
b48fd9c3-bfcf-450e-b240-2de1ae9976fc | note | Activity - HP
f15f51f3-5909-43a2-9ce0-74db5d1700c4 | note | By - ENG
1749caf0-95ae-558d-9e40-0cb21ba1a8ff | signoff | AUTHORITY HOLDPOINT
68eb27de-28a0-5c6b-b80b-1a0b3a7dabaf | checkpoint | 5.04.01 - Settlement Pins
7df0273f-2726-573c-8319-234334b15439 | note | Acceptance / Conformance Criteria - Settlement pins shall be installed within 24 hours of reaching design subgrade level. Survey measurements are to be undertaken to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
a8caf30b-b9d1-5a46-aeb5-4dbe3f8a424c | note | Standard / Specification - GWS - 6.3
235db810-ad9d-56f9-9b7a-832a7715a7a1 | note | Verifying Document - Survey Results (in paper as well as electronic format)
9cf7e1c7-e135-5b40-918e-94fc4847f36e | note | Frequency - Weekly for the first month, then monthly
5494d2e5-3ff5-587e-afa6-7da2c5782e66 | note | Activity - R
9ea475f8-54c7-5150-b398-7d78ec86a5f7 | note | By - SV, ENG
65bdb657-7dd2-575b-8068-4d8a3bbf8080 | checkpoint | 5.04.02 - Settlement Targets
bdf89470-9cbc-5946-80fc-b3956bda633d | note | Acceptance / Conformance Criteria - Targets shall be fixed immediately after completion of the first row of retaining wall blocks at each location and the initial baseline survey reading made prior to the subsequent row of retaining wall blocks placed.
cc54a364-6dce-5b48-9181-dadf83f2781b | note | ○ Survey measurements are to be undertaken to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
2bf0e43a-b99a-57be-895d-15eca0dfe222 | note | Standard / Specification - GWS - 6.4
7dc30c5f-7c95-56a7-be44-1e1575e44215 | note | Verifying Document - Survey Results (in paper as well as electronic format)
c191b3a4-241a-5dce-9f28-f631fd35ecfb | note | Frequency - Weekly for the first month, then monthly
455b2891-a1a2-519d-a193-7630a3c712b2 | note | Activity - R
da1b9953-f7b3-5ba8-a6b6-1889d694713e | note | By - SV, ENG
19e8c979-4bbd-5b44-b6f1-f5f0c60cc435 | checkpoint | 5.04.03 - Engineers Approval
68ab0ad8-4387-5097-a8b1-ebe274ec1bb0 | note | Acceptance / Conformance Criteria - Geotechnical engineer assesment required before commencement of Pavement construction
daf4f6df-f633-5b49-aa86-a6ffbbe52acc | note | Standard / Specification - BBO
c0a8b60a-f1db-58b1-a845-681f2ca879f8 | note | Verifying Document - Written approval
dc733efa-8e48-5814-ac8a-c3c3cf3be8eb | note | Frequency - Prior to pavement construction
f98910be-3ed3-55ca-b6df-4fc2d1b26c55 | note | Activity - HP
c8e8760d-cc9c-5702-afd5-a55af9baf9d9 | note | By - ENG
2ef33948-5bbc-5304-bec0-43db699435f7 | signoff | AUTHORITY HOLDPOINT
cd33a7f8-9b6c-5422-93be-dcae98eaa460 | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
c67c36c3-6604-547c-97e6-f35b09622953 | checkpoint | 6.01.02 - Draft Redline Drawings
4420550a-537f-5032-818b-40f1768a8347 | note | Acceptance / Conformance Criteria - Draft as-builts completed on the completion of MSE wall including red pen mark up to IFC drawing changes.
66d1e4c9-6287-50dd-9a72-f96d4f113dcc | note | ○ The draft as-builts shall be provided on a continual basis throughout the project for verification by the Engineer, and as a minimum shall be provided in electronic form prior to application for Practical Completion.
5477e57b-d05e-5d5f-8996-79cc3de0e690 | note | Standard / Specification - PS 2.2.17
894a9d79-71c5-5fe8-b709-aff0019a8dca | note | Verifying Document - Draft As-Builts Drawings
f119bd10-b211-59ef-9d97-9a27ed553bb0 | note | Frequency - Prior to PC
c19c636b-ce51-5f62-ab48-0d6a79b16cfc | note | Activity - H
eab67930-078b-512e-bef4-5b6f5727abd7 | note | By - SV / PE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
b8fe775b-5eb1-5f42-9cdd-df60ad6c4085 | checklist | ITP - Soft Landscaping - Rev E | itp | ITP - Soft Landscaping - Rev E
8c9335a7-3af5-5e47-a887-39a89ff08c27 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
c51e2085-f336-5d09-acc4-f7b5518ef907 | note | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
5b4598d9-8543-5b2a-a51c-0a6069c2aeb5 | note | Standard / Specification - Downer
18a207d9-066d-50cd-8872-fb95ba7d9522 | note | Verifying Document - Construction Pack
541d1743-7db1-51ff-8d0a-83f5ee69445f | note | Frequency - Submit 10 days prior to commencement of works
37d77a77-80ad-507e-b62d-4174780b85c5 | note | Verification Activity: Activity - HP
a5898aaa-5a2e-59e7-bbda-e12d85ac3c7e | note | Verification Activity: By - ENG
ca255811-cbe5-57f5-8b49-d49ad30655f3 | signoff | AUTHORITY HOLDPOINT
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
dbe31f68-d57b-5430-a67c-1b7e2dd2fd1c | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
74c07e46-8fa6-5d5b-a1eb-041f88d7fff4 | note | Standard / Specification - Downer
6cfc2f9c-17df-5b07-a447-f43b7d70a2f6 | note | Verifying Document - Survey Records
e6bc9c6d-b3b1-53a3-9b84-dc2aebcc42e0 | note | Frequency - Prior to Works
f4c91611-4de5-58e8-aeb0-6e62eafe386a | note | Verification Activity: Activity - H
63d06381-ae37-533b-b360-726519542bee | note | Verification Activity: By - SV
a24a2c58-bf6f-5474-883c-40044bad1fc7 | checkpoint | 3.01.03 - Service Location
d827da96-4bd8-53bc-8b83-85dec9a8bccc | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
9cbbeb8c-fc58-5c56-b134-beb80c08359a | note | Standard / Specification - Downer
db1aa2cd-9d7d-5cb0-83e0-875746fc68a9 | note | Verifying Document - Excavation Permit
481d9b29-5545-50f4-a9e3-267b770459e1 | note | Frequency - Prior to Excavation
b980cf04-cad6-5353-9529-6da0e32a7308 | note | Verification Activity: Activity - H
00cc6941-f030-5b6b-9aa7-4ff477d092a6 | note | Verification Activity: By - SE
0a214a7a-124a-5898-a837-e29e83751df0 | checkpoint | 3.01.04 - Internal Permits
0321cc1b-cf5e-5cae-a8f8-3d97bacb2069 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
739a1e80-1191-5299-ad07-2c770ca4350e | note | Standard / Specification - Downer
15af99d7-e9e4-5b32-b0c0-31f34f05c91d | note | Verifying Document - Internal Permits
db10d0b2-b716-5d0b-9cf9-50e4b571eaf0 | note | Frequency - Prior to Excavation
537404a9-d85f-50a5-b138-f78a393e92f4 | note | Verification Activity: Activity - H
d8af6e77-e7a2-5004-9a88-dc9f923c3a7a | note | Verification Activity: By - SE
917e2881-0901-542f-ae25-686bf9c47009 | checkpoint | 3.01.05 - External Permits
fed65574-1061-5c22-997d-f67486696d2d | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
7551b8f8-ba78-5e07-b8e2-c38babeb9af5 | note | Standard / Specification - Downer
402a434d-5be9-59aa-add1-a2ffdc377e5b | note | Verifying Document - External Permits
62b6b3ee-b6b2-5035-93f1-1966fc9e97a5 | note | Frequency - Prior to Excavation
62f647f0-a0fb-54a6-8cf9-9de627c56cfc | note | Verification Activity: Activity - H
11469b81-4b1c-5145-a06b-d9a65326a8cf | note | Verification Activity: By - PE
a1302970-0389-558d-b43c-67b14bbfc27a | checkpoint | 3.01.06 - Approved Construction Drawings
f27f73a6-4d63-5b42-a22e-f4a3dc2d0993 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
45d6b73a-f8bb-52e4-8788-1b90f959b9a8 | note | Standard / Specification - Downer
bef69abd-26db-55c1-b986-96878fb270ff | note | Verifying Document - IFC Drawings
db4ce00a-57fa-5e27-b9b4-71183bafbe0c | note | Frequency - Prior to works start
34f84c64-cc74-5c37-9573-906e6c841910 | note | Verification Activity: Activity - H
5b78a1c3-ad6d-56af-8c59-1d5bf2730968 | note | Verification Activity: By - PE
febb1ef1-a8bd-5296-8445-7d95da832c71 | checkpoint | 3.01.07 - Previous Lots
95957275-ac71-5454-b8f3-dbe62b4e2cf6 | note | Acceptance / Conformance Criteria - Landscaping works to only be carried out in sections where surrounding work that will cause rework has already been completed.
49f09c73-a5db-551d-a808-49344c2bebfe | note | Standard / Specification - Downer
cdc894dc-6d29-59d6-b471-3f69773ca5b6 | note | Verifying Document - IFC Drawings
27dd5eaf-1816-5970-b177-5828f9adae78 | note | Frequency - Prior to works start
03b0349b-0484-5dce-bd33-158c9bf171bb | note | Verification Activity: Activity - H
4d114508-9824-5a9f-bf8e-ef6921488825 | note | Verification Activity: By - PE
8b92164f-c577-5ff1-862d-50241d4dadab | checkpoint | 3.01.08 - Subcontractors
22fa2562-9ecf-5b9f-bb70-0e7030ba3b54 | note | Acceptance / Conformance Criteria - Ensure that subcontract and supplier agreements have been completed.
e2166493-7bbf-5822-8f19-cd37c344c308 | note | ○ All subcontractors have been inducted.
acffce59-4ee7-5686-97d5-2edfee61a312 | note | Standard / Specification - Downer
ab4c9c44-2236-5859-b2a9-0369aa4ed5d9 | note | Verifying Document - IFC Drawings
83c3eaf6-72c9-5150-9bcf-d93aeeb93b58 | note | Frequency - Prior to works start
f57a296a-2f80-50fd-9bea-2c45f28b4387 | note | Verification Activity: Activity - H
0933a67d-44ac-5b36-b17e-7f98b1da80c0 | note | Verification Activity: By - PE
ecbb056f-9300-589e-a7c1-a434d9d624e7 | checkpoint | 3.01.09 - Site Preparation
c14b25a1-1100-5c73-a3c6-17185b1c15e3 | note | Acceptance / Conformance Criteria - Ensure the area has been sprayed with herbicide. The area has died off and is free of noxious weeds, plant pests, annual and perennial weeds and grasses. Ensure at least two weeks has passed prior to planting.
9459dec2-c677-5784-9eca-701f799c1b5c | note | Standard / Specification - NZTA P39 Section D: Plant Pest and Animal Pest Control
c70e64ea-68e6-553c-89b0-c82a90f2af31 | note | Verifying Document -
dcefcc71-1e63-5977-b22c-7bc93e9e277d | note | Frequency - Prior to works start
a33396de-2d9f-557d-958d-648c02384b86 | note | Verification Activity: Activity - H
c24b5732-1855-5168-b8bf-49781adcf1e0 | note | Verification Activity: By - PE
8ec62109-1664-5fbd-8086-47c125cee66d | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
e84a7142-c5fa-5583-b0d6-707bcd6bd90c | checkpoint | 4.01.01 - Mulch
e1c7ea96-beb2-5e0c-8fb3-b84bc91d7226 | note | Acceptance / Conformance Criteria - 100% pallet mulch.
a4aca0fb-2686-53a9-bf82-5b9a34767d26 | note | ○ Material will be stored in stockpiles nearby to work areas where possible.
8967a093-aaa4-563b-9eaa-c1ef2e8bcf8a | note | Standard / Specification - NZTA P39 Section G: 3.9.1
5ea54813-bf27-5edb-9dde-d47363b3c103 | note | Verifying Document - Dockets, Record of Approval
6100b406-e384-56d5-92ee-db2b31539dfc | note | Frequency - Prior to use.
41f029b3-fef3-5ab9-b4b3-3caf91d15322 | note | Verification Activity: Activity - H
6d4356ee-0b87-59ab-b517-0857e5fad46e | note | Verification Activity: By - SE
d9b389a6-97ae-550b-92c7-fb351e196c0f | checkpoint | 4.01.02 - Weed Matting
83662dfa-f2a3-5d8f-8626-23f90d9498ac | note | Acceptance / Conformance Criteria - Weed matting supplied is what is specified for the contract.
f9db0fe7-be92-52a2-a836-b5546c0bf5de | note | ○ Biodegradable mulching fabric minimum 450 gsm.
44b64f58-5e14-58df-87f0-269acbaaafa2 | note | Standard / Specification - RITS Section 7.3.11, NZTA P39 Section G: 3.9.6.1
9f5bc38e-a493-5a47-aef4-18a96f7937ab | note | Verifying Document - Dockets
8bd00f54-03d4-52f4-9384-84b090838e5c | note | Frequency - Prior to use.
94c3dac2-6ceb-5ffe-a0c8-fa847328885c | note | Verification Activity: Activity - H
a4402619-feb5-5546-90f6-7721bd2681db | note | Verification Activity: By - SE
9d9a43f0-d187-5157-9ff7-de0ffc452af3 | checkpoint | 4.01.03 - Grassing
ff6276a2-0d35-50db-b046-91501417c2f4 | note | Acceptance / Conformance Criteria - Specfied grass to be used unless alternative has been approved.
8d03b8e7-1ca1-51e3-81b6-1cfbb8b3ff90 | note | ○ Perennial rye-clover seed mix has been approved for use and will be used for all permanent grass application.
216e1368-6833-57c8-92da-ba18a8370942 | note | Standard / Specification - NZTA P39 Section C: Site Preparation
697ecf4e-545f-55b4-b381-1f055603d562 | note | Verifying Document - Dockets, Checksheet
7665932b-a4ba-51a6-b8bb-50450b7e0a32 | note | Frequency - Prior to use.
846469e1-8751-564f-89a2-dc0d00c958e6 | note | Verification Activity: Activity - H
46d1d21f-6329-58ed-96d5-a7034af4be09 | note | Verification Activity: By - SE
67f21a49-22e9-5eda-9881-745a96c4b5ab | checkpoint | 4.01.04 - Plants
f4b19b21-75f8-5c6e-a67c-739fa8b2fff3 | note | Acceptance / Conformance Criteria - All plants and alternatives have been approved for use.
98f0b7f9-8bb1-5f86-a996-1009762106d6 | note | ○ Plants to be as per the plant lists shown in landscaping drawings and schedules.
66a30246-2690-551a-a3b9-1a8d08e8f3ea | note | Standard / Specification - NZTA P39 Section C: Site Preparation
62560723-85d8-5a46-9e85-e4e85bac6e1b | note | Verifying Document - Dockets, Checksheet
5b1f0216-678e-5307-8dfb-b155c03e3332 | note | Frequency - Prior to use.
f747db15-51f6-5410-ade7-edd6167478b8 | note | Verification Activity: Activity - H
833fb40b-5a6f-5bc6-8be5-bdbd5842fb02 | note | Verification Activity: By - SE
ba6c1aaa-c83b-58b0-86ed-71f4cb0741da | checkpoint | 4.01.05 - Topsoil
63c6d1fb-cce2-5af5-889b-3588cce5de37 | note | Acceptance / Conformance Criteria - Topsoil used is good quality material, clean and free of debris.
8074f852-a088-5c50-b410-75933aec0266 | note | Topsoil should not contain rubbish, contaminated material or pest plants.
d15aa0ea-9d58-539c-b54f-8180460306d8 | note | Material will be stored in stockpiles nearby to work areas where possible.
37ed8921-0a20-5021-89e2-2b00c31dd5e6 | note | Topsoil will be managed to prevent saturation and over-compaction.
58c47f29-8313-5cc1-86dc-029b7cb7772b | note | Avoid handling topsoil immediately following any heavy rainfall events.
f8c1a9f2-d8f1-53d7-bc41-a8aec64c7043 | note | Standard / Specification - NZTA P39 Section C and F
bff45c6a-7f09-52e2-b031-8b89b30d2851 | note | Verifying Document - Photographs, Inspection
9de50a14-f8f2-5ae9-ba4f-9a098c7dcef3 | note | Frequency - Prior to use.
9a98f5fa-5c29-5bb1-a5be-a4a5ac827226 | note | Verification Activity: Activity - HP
85748278-b0d5-5f5d-bf4a-9562f8b3e0cc | note | Verification Activity: By - ENG
78c1dfc1-5913-5748-8c32-e6918d56f91a | signoff | AUTHORITY HOLDPOINT
f9f05bc2-2a1d-57b6-9cd0-3563b61d34fd | checkpoint | 4.01.06 - Root Barrier
d616d13a-dee1-5483-b221-e5b6846db3fa | note | Acceptance / Conformance Criteria - Root barrier to be 1.0mm thick, 600mm high, recycled HDPE non-ribbed material.
c9364361-e84a-5c48-a540-50be9939ee10 | note | Standard / Specification - RITS Section D7.4
aadc70b9-a8e8-5dd5-a83b-26fbf8598b3e | note | Verifying Document - Dockets, Checksheet
9bc88b34-d318-51d9-9f01-d8a80a19981d | note | Frequency - Prior to use.
06145c29-1b45-5030-945f-e65919d491f3 | note | Verification Activity: Activity - H
8964cb97-4b2a-596c-868a-8c68dc55a0f1 | note | Verification Activity: By - SE
f4713bb7-3aea-5dca-b516-69272c0b56ba | section | SECTION 5 – CONSTRUCTION ACTIVITY
28b4fdbf-8cde-5b8b-9f63-eb6fae6491a0 | checkpoint | 5.01.01 - Topsoil
9171b746-42f7-5867-9756-b82b4b0b6f52 | note | Acceptance / Conformance Criteria - Minimum topsoil thickness as follows:
f5a8fa82-837f-5853-9b69-b635b7f042ca | note | – Grassing 100mm
56292213-6b6d-52d6-8dfa-5e61d569fb3b | note | – Mulching 300mm
f92fe421-5937-5f51-a54b-5ac32d6bdc76 | note | – Swales 150mm (TYP)
eaab4b49-4211-5f6f-8910-dc76de63e557 | note | – Swales 300mm (swales requiring 300mm to be advised by Landscape Architect)
96edb7b9-dc06-564d-86ee-9ca76792d331 | note | Standard / Specification - Drawings
c0a25b6d-1128-598b-887b-c5be17ffea98 | note | Verifying Document - Inspections + Checklist + Photographs
88616a3a-5bee-5bfb-8710-8c2f9640d3c9 | note | Frequency - Each Area
4a7dcc26-9600-5b79-92ad-d0ee851b38e7 | note | Verification Activity: Activity - HP
38dfe7cf-8671-5258-b11f-a7944e149634 | note | Verification Activity: By - ENG
492b4570-e8e0-5a10-8ec6-7542c3c8a46f | signoff | AUTHORITY HOLDPOINT
0bb5b1c3-be9e-596a-92b9-1fedf16c5744 | checkpoint | 5.01.02 - Planting (Dry)
13573266-01ff-5a58-ae69-97ae831d179b | note | Acceptance / Conformance Criteria - Correct amount, size and type of plants have been delivered to relevant zone on site.
3bff1209-57cd-5832-b22c-7fb85e2e021d | note | ○ Supply of plants - confirm order, inspect plants for health -
a9f56323-5cd2-512c-afba-e910cb5b94dc | note | ○ Set up a test planting area for Landscape Architect inspection. This is to benchmark and agree typical set out (once for each planting mix/type).
2f857bcd-c439-5064-bfa2-cccc3736fd10 | note | ○ Ensure plant spacing and plant numbers are correct.
cd7186cd-9d6e-5000-8785-e0a4afb568e0 | note | ○ Confirm application of slow release fertiliser tablets as per requirements - 3 per plant. (Photos)
f0373550-6b34-5ee3-8194-d20a1b013b31 | note | ○ Ensure plants are correctly planted, upright and firmly heeled in.
e20722ab-992e-5766-8602-dc3db9b51466 | note | ○ Small trees and large shrubs should be size 1.3L
fb65ec49-e59c-5104-a091-4774cb64b178 | note | ○ Delivery dockets to be provided for fertiliser tablets.
bf8e8d37-4040-557f-8242-b30752d3d8a1 | note | ○ Plants to be carried out during planting season unless approved by designer.
2dca46f8-85fd-50d5-8d6b-7bc8ea07b13e | note | Standard / Specification - Designer
7c187481-a755-548f-a471-f742f1ad31c1 | note | Verifying Document - Dockets + Inspections + Checklist + Photographs + Record of Approval
f1ac9870-4967-5999-9367-fa5d81fb22a1 | note | Frequency - Each Area
c538eddd-d1d5-5581-81d5-06d512c09501 | note | Verification Activity: Activity - H
64a3020e-1550-59e9-b327-288b26d0abec | note | Verification Activity: By - SE
ad27038a-e553-5612-bc5a-1d6970df5eb2 | checkpoint | 5.01.03 - Wetland Planting
738d63d3-2166-50a4-8689-8baae0d01d25 | note | Acceptance / Conformance Criteria - Wetland Planting to be done outside of summer months (Dec-Feb).
91cfe9f0-d028-5c56-ab55-0d4f9f797d4b | note | Standard / Specification - Designer
aed425bf-f6ae-5143-9959-990a70740c2d | note | Verifying Document - Checklist + Site Records
afe3ca8c-003d-5705-903b-05ade877a11c | note | Frequency - Each Area
e28e2c67-d1f9-5f60-a952-b35e210d3aeb | note | Verification Activity: Activity - H
13a17881-a598-5e3f-a52c-eb19185f53a9 | note | Verification Activity: By - SE
c02d0097-610f-5200-b1ec-ca941c6b6a73 | checkpoint | 5.01.04 - Grassing
be6c2126-e744-58e2-b193-7c1cc4250c4f | note | Acceptance / Conformance Criteria - Grass seed has been applied and has full coverage in all required areas.
9a618807-5db5-5634-a3ec-253aa5041ea2 | note | Standard / Specification - Designer
dead71e1-0058-5bce-8a24-151a4d88a750 | note | Verifying Document - Checklist + Site Records
67145d06-4e82-582e-ac63-b871f646e630 | note | Frequency - Each Area
c2718c32-02d7-5ca3-9bb6-2d72cdf5e190 | note | Verification Activity: Activity - H
212a0127-b4c6-513a-8c80-2c268acef590 | note | Verification Activity: By - SE
c10a8b1c-9e6f-5a57-b3e7-a3fc01885bca | checkpoint | 5.01.05 - Specimen Trees
42dc9f2b-a439-530c-ab74-39fbd922bb26 | note | Acceptance / Conformance Criteria - Site meeting held with Landscape Architect to agree specimen tree locations prior to excavation of tree pits.
804e77fa-cc70-5a74-ab01-8aad2b90620e | note | ○ Supply of trees - confirm order, inspect trees for health - landscape architect to check samples for compliance.
0b97e6f1-fcca-5e24-b361-377df7c32c34 | note | ○ Ensure tree pits have been dug out to the required dimensions (varies depending on location/slope). Check no standing water in tree pits .(Photos)
367f3bd7-7bad-5331-bdcf-9499427c7b9d | note | ○ Confirm application of three slow release fertiliser tablets per tree. Larger trees (160L) will be planted with a minimum of 8 tablets. Trees have been staked correctly.(Photos)
a442f3c4-711c-54a4-91d9-e2b69da32ecc | note | Standard / Specification - Drawings
f579d12c-3806-5a99-8d77-3614655932d3 | note | Verifying Document - Dockets + Inspections + Checklist + Photographs
80ad0064-5835-5b06-a712-077aec204991 | note | Frequency - Each Area
8ed5e62a-dbd9-5ded-8d3b-15253807ace9 | note | Verification Activity: Activity - H
57e4af49-3567-5528-a564-f2cfa68b6cde | note | Verification Activity: By - SE
eebf7a4b-aec8-529e-9977-dd0427ad8364 | checkpoint | 5.01.06 - Mulching
2605e288-b36b-534d-828c-9f07c0449848 | note | Acceptance / Conformance Criteria - Areas that are mulched and been laid 100mm thick and depths have been checked. HP (Inspection at Completion)
bcc65685-dc80-5bc8-becf-870fc238c4c1 | note | Standard / Specification - Drawings
a4e98406-475e-5a09-851b-f0b72425153e | note | Verifying Document - Checklist + Site Records
b4303e21-5b36-5951-8657-46a27c074b05 | note | Frequency - Each Area
645d42e8-9a11-57cd-96c0-7182e96edb90 | note | Verification Activity: Activity - HP
24467f21-c218-5976-8da5-ff3f5caee286 | note | Verification Activity: By - ENG
cc07c8d9-7b1b-56b0-a63a-4bdf5dfe1ffc | signoff | AUTHORITY HOLDPOINT
411805b7-d4a5-5f82-9856-5cbc59b5ddd2 | checkpoint | 5.01.07 - Herbicide
c76da0bd-03bc-554f-b3f6-8c19fc723d8a | note | Acceptance / Conformance Criteria - Avoid spraying any herbicide next to streams.
472740d5-06ac-564b-98e7-03aae4ae9bea | note | ○ Where required, only non-toxic herbicide may be applied near waterways and wetlands.
c355edd0-19b4-5490-8a0f-227d8016080f | note | Standard / Specification - GEP
caa2ab6b-c93c-5fbb-9e13-3c7afdb61216 | note | Verifying Document - Checklist
052cb266-d7ad-5c69-96a2-02ef2bf8a3d1 | note | Frequency - Each Area
ddba96a5-5ba8-5f56-afca-12ccd189d1d9 | note | Verification Activity: Activity - H
2ba201e4-ef1e-5a4e-9a1f-78fac967d898 | note | Verification Activity: By - SE
b423157a-4217-5a45-80d3-8dd697915fe2 | checkpoint | 5.01.08 - Tree Pits
e8feab18-9b31-5276-af11-7a897e4cf02b | note | Acceptance / Conformance Criteria - Tree pits to be installed as per drawings. Individual pits should be 800mm wide and 850mm deep unless agreed otherwise. 150mm soil layer beneath tree pit should be scarified/loosened. Tree pits to be backfilled with topsoil and slow release fertiliser mixed with compost. Trees to be kept upright with 50mm stakes with horizontal straps no more than a third the height of the tree. Trees to be covered with 100mm mulch and pulled back from the tree trunk.
170a26cd-4830-578c-8394-4c62fd166a55 | note | Standard / Specification - Drawings
caa0fdd3-d8ca-5e5d-bdeb-45388d2a4348 | note | Verifying Document - Checklist + Site Records + Photos
966ad349-9c96-5020-86bf-e0b60053d99f | note | Frequency - Each Area
4438448b-db20-586b-b4d4-7158769220cd | note | Verification Activity: Activity - H
d914f23a-7c4e-5243-b663-8e0fb52b004c | note | Verification Activity: By - SE
631deb3c-177c-5d12-adef-5bed9255c5a0 | checkpoint | 5.01.09 - Root Barrier
def0ebd3-cd42-5618-a7fb-9171703914bb | note | Acceptance / Conformance Criteria - Root barrier to be installed where tree pits are close to kerbs and footpaths.
afe30ec5-6d3e-5a04-acdc-ba11b0fee15a | note | ○ Root barrier to installed 2m wide and to be 600mm deep where required for tree pits. (Photos)
3da8eed3-af79-568b-946f-867d5d57cf20 | note | Standard / Specification - Drawings
3ce0aea9-754c-53df-a678-a933cb580513 | note | Verifying Document - Checklist + Site Records + Photos
395380b9-9417-5cf4-9859-6de63e18f955 | note | Frequency - Each Area
43d62f5a-cd65-545d-be48-8970ea4a05cc | note | Verification Activity: Activity - H
4fccbe46-a86c-5371-b97d-af9d698deb72 | note | Verification Activity: By - SE
cd33a7f8-9b6c-5422-93be-dcae98eaa460 | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
0cac8075-a3fa-5c67-b8a3-64b6a9a02349 | checkpoint | 6.01.01 - Maintenance of Plants and Grassed Areas
c4d3e3f8-6097-566e-8767-99925bface21 | note | Acceptance / Conformance Criteria - The Contractor shall remedy all defects relating to the landscape treatment works, each year during the defects and maintenance period, at the first available opportunity. All planting defects shall be addressed duuring the correct planting season.
75d86a0e-a783-5635-b02d-17c27b808e46 | note | Standard / Specification - Landscaping Specification
02ec7518-9dcd-5c0d-8dc2-6202ca100ebc | note | Verifying Document - Site Records
9f341dfb-2660-5149-86e2-e3ee108fe03f | note | Frequency - Each Area
2e21c004-29cf-50cd-948d-9932fc37f19e | note | Verification Activity: Activity - H
05bac49b-88f4-5fa5-bf56-140213437b84 | note | Verification Activity: By - SE
0010ee0a-b371-5dab-b2e5-f13fb762ca3f | checkpoint | 6.01.02 - Redline Markup
38d95eef-2428-5668-8526-844f212d3d20 | note | Acceptance / Conformance Criteria - Redline markup of any design changes.
1079bb67-d6a9-573f-95cd-25135de87bf6 | note | Standard / Specification -
0cd5e592-db99-5450-afe9-35d487eed518 | note | Verifying Document - Redline Markup
95cbb7f4-34d6-51b8-bcf5-07edf9bc1abf | note | Frequency - Upon Completion
e2825751-4075-5af2-8a74-94003b2edcc5 | note | Verification Activity: Activity - H
e0ac8223-222d-5647-be4d-914d50678326 | note | Verification Activity: By - SE
6774916f-4052-5277-afc2-16ddba850b5f | checkpoint | 6.01.03 - As Builts
f50e72ac-e6c2-547b-a135-fde880f49435 | note | Acceptance / Conformance Criteria - Final tree locations to be provided.
98495aae-41fc-5dc1-97f1-568dc1916ae3 | note | Standard / Specification -
cf86ca19-c6e8-5ad0-bc35-93a321985b4a | note | Verifying Document - As Built File
42b3c30b-7857-5402-9e41-09e2ede31416 | note | Frequency - Upon Completion
07de8232-3494-5730-93dc-f494ba185855 | note | Verification Activity: Activity - H
919d0b0e-8f94-5b20-90d0-1737a4d77c23 | note | Verification Activity: By - SE
7765cd5b-2e9a-57eb-9811-d1ea9a19558b | checkpoint | 6.01.03 - QA Pack Compiled
654350ad-219a-538a-9758-e579b4c89091 | note | Acceptance / Conformance Criteria - Submitted for approval.
92908d77-5c82-58d0-a9da-430ac5dec8f9 | note | Standard / Specification -
d9b266aa-a52b-544c-a677-2510c0e6fd75 | note | Verifying Document -
9b5b1e18-5999-5330-923d-0f7723a17050 | note | Frequency - Upon Completion
c2559640-c815-5f37-a7f4-e8a2bfc3ba21 | note | Verification Activity: Activity - HP
4c62059d-d17a-5f1f-81f3-674dfaa23db3 | note | Verification Activity: By - ENG
4a64cff7-3fa7-5124-9f8b-273c7ff877d5 | signoff | AUTHORITY HOLDPOINT
a20ed714-af06-5eca-ac5e-6fc8f4e5ca6f | checkpoint | 6.01.04 - Final Acceptance
14097e6f-ec2b-54bb-aac9-381c5609e2e3 | note | Acceptance / Conformance Criteria - Planting shall achieve an 80% canopy coverage of the ground by contract completion,
5e94bd76-f651-562c-aff6-bffbdd0cad83 | note | Standard / Specification - NZTA P39 Section A
46aad054-dfd8-5c39-b7ac-5876aa108cc0 | note | Verifying Document -
5fb6b364-06f7-5a22-805e-15747d31e52d | note | Frequency - Upon Completion
e63d1c40-cf02-5712-aa36-d29b3bec66d8 | note | Verification Activity: Activity - HP
7ad83ecb-fe07-502e-86af-c639c30b16db | note | Verification Activity: By - ENG
5b224134-595b-5521-9455-6267e1f4ae49 | signoff | AUTHORITY HOLDPOINT
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
a0875115-15b1-5ace-b806-f4d0ef82c71a | checklist | ITP - Stainless Steel Pipe Site Welding | itp | ITP - Stainless Steel Pipe Site Welding
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
d23d82c5-8f42-50c7-ba8f-162334c64ec9 | checkpoint | Inspect all pipe & fittings are correct to job requirements and no signs of damage
8cfe2aaf-721a-5de5-9d1a-7d5b55c6e849 | note | Quality: Hold Point - W
e0977afa-d426-5857-842c-23fd26825696 | note | Quality: Sign - LS
cef4f7e8-5081-521d-a422-a39a187081b8 | note | Quality: Witness - AG
a1f232cf-6903-422b-bffa-374411907eae | checkpoint | Inspect all pipe & fittings are correct to job requirements and no signs of damage
72a70939-b2c8-590e-90e6-d08793e3aeef | note | Quality: Sign - AK
aadb0693-2cc2-5620-bcae-9782278a34ce | checkpoint | Familiarise yourself with the job
1a4133f3-4614-55df-9511-34b140e3f468 | note | Quality: Sign - AK
b20a0af7-73e9-556a-947d-4febc223c156 | checkpoint | Setup worksite, welding equipment & rollers
b4843adb-3502-560e-91d4-3dfc76e06e39 | note | Quality: Sign - AK
db1eb665-1185-5020-8156-938e4e296812 | checkpoint | Load length into rollers
129a13a7-b545-5beb-a3d2-0d8925781ce1 | note | Quality: Sign - AK
ac284ff4-ba0d-57fd-84b8-4c67bf94f5a2 | checkpoint | Bevel pipe ends
473dbab3-66ee-5c3d-a29c-eaee14e9c98a | note | Quality: Sign - AK
eb4c3f44-45fb-5baf-8863-b657653af373 | checkpoint | Tack weld 6m lengths into instructed lengths
b45fc73e-8716-53ab-92b5-e7a8a1a0b5df | note | Quality: Sign - AK
e902e8af-3dd1-557e-a6c1-e7f9c93d3961 | note | Quality: ID - AK1
f6c4ac93-8c52-5b74-bf2a-509593377415 | checkpoint | Check for straightness alignment
78322bd6-9015-5260-bb56-66680edddc32 | note | Quality: Hold Point - C
8914a38e-7940-5245-9eca-ade47d2a3cef | note | Quality: Sign - AK
94417a05-32cc-5f95-ba16-ae92d19d480c | note | Quality: Witness - AG
b6dc238d-4f49-593e-8bb1-363dd19f1c8e | checkpoint | Setup purge baloons & purge with nitrogen
30e8af7c-20ab-56a4-ac60-9026171eb594 | note | Quality: Hold Point - C
94450fec-d239-5009-8039-6d06ba261720 | note | Quality: Sign - AK
c8798ef9-cc48-58fa-9f9f-19832a405769 | note | Quality: Witness - AG
da78b9c3-df9d-5c79-b8a5-5c3e549de77e | checkpoint | Peform butt welds
6d740a76-6493-502c-8e18-89499b172d16 | note | Quality: Sign - AK
bfb56a40-f0b0-5414-bd9f-6f648d08d6aa | note | Quality: ID - AK1
d0293b09-81ec-5139-89ce-1472088e276a | checkpoint | Tack flanges on spool lengths & check for square
cd5e67a7-8a32-5bf1-af3a-cf55de6a0735 | note | Quality: Hold Point - C
87c1b39f-af85-58f3-95ba-7c5000f5c432 | note | Quality: Sign - AK
b6efe9d1-d180-572e-a3f8-02b35bb3be75 | note | Quality: ID - AK1
375df33c-659c-5bbd-889d-35b60819e097 | note | Quality: Witness - AG
e500a9ca-8d75-5125-aaa7-4af5c648b4fa | checkpoint | Weld flanges on ends
955dca95-c19e-53d2-89b5-f92d19e3c3c0 | note | Quality: Sign - AK
ff1e457f-c928-5fef-8ad6-44e417044c94 | note | Quality: ID - AK1
c3e43bd3-aed5-5eac-87f4-bddef998735b | checkpoint | Passivate all welds
e5848a77-4422-5ff7-b891-234cca2dbe7e | note | Quality: Sign - AK
44e33adf-c562-5da7-bc81-19c849279ec7 | checkpoint | Remove from rollers and move to lay down area
f6879104-c440-5809-af28-607ea958a40e | note | Quality: Sign - AK
f0ffd1e2-3dab-50f3-be12-aeb1ec69baa9 | checkpoint | Final inspection
34ec5d81-65ec-5b91-ae74-6f51f5e930c6 | note | Quality: Hold Point - H
f9e5c8b0-7a12-5793-b652-770c6f2697ae | note | Quality: Sign - AG
a17d4418-f643-5665-b00b-1016f21de2ba | note | Quality: Witness - LS
8a8c980b-e46c-5f30-bf74-bcf638dccb81 | signoff | HOLD POINT
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
a1a64109-8025-590c-be92-a68c4ae1503c | checklist | ITP - Stormwater | itp | ITP - Stormwater
250f8899-b0a3-538c-87fa-1443b890324b | section | 1. Pre-construction (P&G / EStablishment
40e50969-1ceb-5dd9-9b3c-01f7c53f618e | checkpoint | 1.1 - Extent of Line Setout
447440a5-2c0a-5624-85c7-5c5695b6237d | note | Acceptance / Conformance Criteria - Ensure line and level of Stormwater has been marked out and agreed with Engineer in accordance with Stormwater drawings Identify any clashes before construction.
c2a79509-fed9-5e36-b6c2-55161fc3b698 | note | Standard / Specification - Design Drawings
ca3ef045-41f3-51eb-926d-2360a7098b93 | note | Verifying Document - ITP Sign Off
98ad0bfb-34bb-5a09-9755-5781e4c3ebe3 | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
9f6fba78-f4fa-5da9-aba5-069ad45174ef | note | Activity - M
8de4d596-b054-5659-bc84-16e38ba8fb5f | note | By - PE
29b93ae9-4f0f-5379-a3b9-3f819c7cf4c4 | checkpoint | 1.2 - Environmental Protection
6612df47-d954-53c4-b894-edb8ce9af6f9 | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
062afe7b-306f-5969-b9db-f7d2dc2afc15 | note | Standard / Specification - Project ESCP Plans
7a2cc52d-ca2a-57de-905e-1840593283b1 | note | Verifying Document - ITP Sign Off
b38eb8cb-5d9d-5cd6-aae7-aace11a0a128 | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
de4a0ce0-290c-5f62-9d8d-6caf8dc1f487 | note | Activity - M
052d5bf8-5a20-5976-ac01-5a2ef8b5e4f3 | note | By - PE
c1757774-9612-5bda-8f1b-91d1e7f574f0 | checkpoint | 1.3 - Stakeholder
964041ce-8f47-5f43-9ecb-4bc963a55457 | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
8b5fbeb7-f07a-5d9a-8009-c74944313641 | note | Standard / Specification - Project Stakeholder Management Plan
eb2ede20-7062-5ae6-ae42-6281a683f1fd | note | Verifying Document - ITP Sign Off
d15bcff4-95f0-5150-accf-6527317b301c | note | Frequency - Prior to Construction with continue updates throughout the works
5ec3de2c-4b7c-5ade-a197-bd5ea77fcabe | note | Activity - M
4c067108-806e-5e92-9370-1ad1b8a35d89 | note | By - PE
2d17bcb2-0fc6-51c9-86f5-20bc7fe95d1e | checkpoint | 1.4 - Permits
4c825895-8c78-55b8-b08e-a8351d233bd8 | note | Acceptance / Conformance Criteria - Permit to Dig must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip. Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. All known services must be clearly marked on site and briefed to the workforce .
1d27dde7-938b-501b-832f-694ad3898bab | note | Standard / Specification - Section 2.2.10 Project Specification
ebcd1d8c-89e5-5cf8-892d-b66059936aa9 | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
e8bbb9a1-2854-5867-a418-82b8a8d75d70 | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
50b252e4-9a1b-55a1-8fcd-272b57170589 | note | Activity - H
05b3ff20-3c01-57de-94a8-610a07e19afa | note | By - PE
b0124294-c375-5468-89f3-32274ca5d856 | signoff | AUTHORITY HOLDPOINT
2b839b91-0e59-52bf-bfbc-2a6a8cc5432d | section | 2. Material, Personnel & third party approval
405352c0-5f6d-5187-918d-a540cbfd3a1d | checkpoint | 2.1 - Pipes, Fittings and Pre-cast Structures
8cc73743-a549-5b8a-9972-bd0ed83002b2 | note | Acceptance / Conformance Criteria - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes/manholes/catchpits are correct and in good condition and compliant.
99c3e5ae-e54f-5495-9913-be9258ec6a39 | note | Verifying Document - Delivery Dockets
c00daa9a-8446-5e5a-80c6-f2424b52f9d1 | note | Frequency - Each Delivery to site
a6e87c58-81fd-59d2-a37c-c5b5ea4ddfbd | note | Activity - S
34dca5cd-53ed-5e78-9eca-2b4049551dea | note | By - PE
8907bdeb-f5d3-517d-9285-d6893b320753 | checkpoint | 2.2 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
2f2b959f-0b91-593e-af76-befcf5d8037b | note | Acceptance / Conformance Criteria - Confirm material grading and density
df46ccd2-8662-5f7d-b6ba-bec7f384f640 | note | Verifying Document - IANZ Lab Test Report
9c4db143-fb28-5f31-bc3c-43f6c7034508 | note | Frequency - 1 Test per 1000m3
245aee90-a07b-5d58-8087-a5a14ee20ed3 | note | Activity - H
f3b05688-3c15-54c6-8fba-318cf71f63e7 | note | By - PE
c30b6c14-92f7-5ed2-a6a8-3f7e8a154f8f | signoff | AUTHORITY HOLDPOINT
22aee86e-39c3-5dae-b364-06afb43756dc | checkpoint | 2.3 - Undercut Backfill Material
fe88c77f-3e70-515d-bb22-3fd140cb3a92 | note | Acceptance / Conformance Criteria - Engineer to Specify Material to meet specifications dependant on material selected
07567e87-88a2-541c-b30e-632f15b06a13 | note | Verifying Document - IANZ Lab Test Report
54e4e4a8-5298-504a-a852-f33bcd7d4d87 | note | Frequency - 1 Test per 1000m3
8c66e4e0-bc8f-506b-a85f-f5d65b949fb1 | note | Activity - HP
3d96e459-1e65-5754-b945-41afc0373867 | note | By - ENG
76eff2ac-dcf6-53be-bbec-f153144f0126 | signoff | AUTHORITY HOLDPOINT
1f8d7f1f-2254-58d1-b0a1-af1db979e4f5 | checkpoint | 2.4 - Geotextile/Geogrid
d07e6c50-2ff7-59c3-8fea-34e730e14a76 | note | Acceptance / Conformance Criteria - NZTA F/07 Strength Class C & Filter Class 1 geotextile is to be used in the undercut. Geotextile or Geogrid that is used in the undercut is to be documented / marked up on drawing
6dbbe61e-6416-5303-b213-94a8c466f688 | note | Standard / Specification - Project Specification
e0bf4fe2-31b6-5f29-9c4a-9c35585633c8 | note | Verifying Document - Certification
9db1ab35-a02a-50b0-a859-3077e8340c2f | note | Frequency - Material Used
14c378a1-3d7d-5e88-b0b4-dc90aa22f05a | note | Activity - C
3fd12297-a538-5970-b61b-2ca319e65cd8 | note | By - PE
9df583ab-155b-5efc-bfef-074fd09cf696 | section | 3.1 SW Pipeline Construction
6060b861-66f7-50a6-931b-1a3e09522cab | checkpoint | 3.1.1 - Foundation Compliance
7a04d12b-d747-5ffd-b944-2bd05ad77fc9 | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
4f0e99a5-bfaf-5f02-a719-5a24a42d5913 | note | Standard / Specification - Project Specification 4.3
a9f17d3b-c88e-50fe-8d6f-ab8064428d69 | note | Verifying Document - IANZ Scala test result
f3841af3-80ba-5c41-8777-03f1b887719b | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
3575732c-7133-5f5c-849a-1c506255b232 | note | Activity - H
ff25d653-974a-54e0-a0d3-32abec523435 | note | By - QE
261a9718-d291-5946-8039-995e6b970cd3 | signoff | AUTHORITY HOLDPOINT
27e1b1c2-fd5c-53c7-8ab8-4e7ee944dd8d | checkpoint | 3.1.2 - Undercut Backfill Compliance
e1ff91fe-c3fb-58ee-9e70-19bef3c46199 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average98%) of MDD
a64090ac-0958-5091-b76f-c28c35eb76a9 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
93d8490e-c5e1-5da8-888e-c2e3ae4d55d2 | note | Verifying Document - IANZ Lab Test Report
8b1bde27-f241-50c2-a50d-193151536635 | note | Frequency - Based on Undercut Section
021146ef-473d-5414-88e2-ce3b10842f12 | note | Activity - H
905f63e2-3f0e-5d40-8280-5163a1b608af | note | By - QE
3b42b8af-9265-5fcf-bc40-7a447dcc1e0a | signoff | AUTHORITY HOLDPOINT
e98da528-b79e-502b-b67d-feb4cee476d0 | checkpoint | 3.1.3 - Bedding Compaction Testing
e3797ba1-d525-5fd9-a978-8a5831163f09 | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average98%) of MDD
a2064d5a-38c8-55fd-a7dc-82c5a0133fc2 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
1d9d16c0-cfa7-5e49-8d48-39ef0a0d8c21 | note | Verifying Document - IANZ Lab Test Report
499bcee3-0521-5833-b992-397bfa037601 | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
730ed117-3d39-5268-949a-02db9efa951e | note | Activity - H
82f85a51-88c4-5669-8e7c-07d8953148f8 | note | By - QE
f6f7cc71-a5d8-563e-9557-337605059128 | signoff | AUTHORITY HOLDPOINT
98147742-c8f1-5506-a60d-ea4b86794e0e | checkpoint | 3.1.4 - Haunch Zone Compaction Testing Haunch Zone shall extend from top of bedding to 0.3 times the outside dia of pipe
943c75a0-548a-5877-b083-6d8b113d77be | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD
98d9189b-0f93-5541-86a3-f57e2e828180 | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
b6029590-f98f-5925-9315-855030e5fe08 | note | Verifying Document - IANZ Lab Test Report
db6a89fc-c15b-5eaf-9b4e-48577b15dbce | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
aa4f8012-e8f7-54c9-a4ac-7df2a309121b | note | Activity - H
c1462d73-a82d-5e15-9b73-6b6f3fd47075 | note | By - QE
c86c5a9e-3030-5e16-8e37-17489dd9db4f | signoff | AUTHORITY HOLDPOINT
31a94ebb-2103-56ee-a677-646d0ec2ea45 | checkpoint | 3.1.5 - Side Zone Compaction Testing Side Zone shall extend from top of Haunch Zone to 0.5 times the outside dia of pipe
c71bafd6-9b9a-586e-a9c4-1a21adf96b38 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD
24f21671-d0d3-5a9e-bc01-b6a76b22570d | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
13b55999-794e-5122-af3b-a8aa97997815 | note | Verifying Document - IANZ Lab Test Report
32feea1a-ae98-558d-9737-dbd1f32fab48 | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
4a48af67-2ab9-5de9-9c40-82b43aee0a97 | note | Activity - H
fd47be6f-6c6a-5ff9-94b2-800c521a7759 | note | By - QE
a7cf3fdc-ffec-569d-97cd-8b9702c88056 | signoff | AUTHORITY HOLDPOINT
adad8470-6db5-5f41-8ecb-c7e2c95cd14f | checkpoint | 3.1.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
05192b11-1a31-586d-905f-5659d3cebd1e | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD
50b2983f-227f-536d-b0eb-3584ee19e873 | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
8a3c30b9-73dc-5a8a-838b-86b5b0bd2ed5 | note | Verifying Document - IANZ Lab Test Report
3d025453-8849-5aed-8278-b85d2c7e3df9 | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
bea3a1ac-8116-579e-9399-b859af1663b6 | note | Activity - H
b5599516-b1eb-5110-99be-fa5c76828b21 | note | By - QE
f0e2effc-94d3-5057-b41d-c7f3b97e2844 | signoff | AUTHORITY HOLDPOINT
12d805c7-e9b5-5c8e-87a9-36632fb2d485 | checkpoint | 3.1.7 - Backfill Inspection
1adaab6a-26da-5cfd-b3e6-23db6fc87b44 | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the pipeline.
3084c2a0-39cc-51ad-a0a2-094544a82dc1 | note | Standard / Specification - Project Specification 4.3
57109279-457b-5e21-a601-66ebf67dfde3 | note | Verifying Document - Photographs
191df840-3870-5720-a4de-26fffe4f3f34 | note | Frequency - Continuous
8feee862-4ff9-5b2c-96aa-b341303a3086 | note | Activity - S
398a1038-926f-5031-b65a-f2b2a115b4ea | note | By - PE
a6195f87-84e2-5fbd-a630-649970446481 | checkpoint | 3.1.8 - Survey
74d6bc52-ea28-5f9e-a46e-d8a11a8a62aa | note | Acceptance / Conformance Criteria - Invert Levels The permissible deviation from the designated level of the invert at each manhole or structure shall be ± 50mm, provided that the fall between successive manholes or structures shall be at least 90% of that specified. Horizontal Alignment The permissible deviation of the horizontal alignment between manholes or structures shall be ± 100mm. Gradient For straight gradients, the permissible deviation from the specified gradient shall be ± 50mm from a straight line drawn between the inverts of successive manholes, provided that no point in the pipeline is lower than any downstream point.
377dd711-8851-5fde-899f-26d3b19d6e49 | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
779ac31a-8be8-5b43-a12a-7ce6784654ce | note | Verifying Document - Survey Data
0758b277-e14d-5292-8882-bfddd9492976 | note | Frequency - Continuous
666f3657-a9b9-5643-8c00-9d8c5e540590 | note | Activity - C
7c5f006f-2bf8-54b5-bf65-9f6706fc2204 | note | By - SV
91e3a928-56b8-54e5-a782-8bb9063a0c3b | checkpoint | 3.1.9 - Backfill Compaction Testing
dd1b4c81-03ce-519d-86b6-a52d4bb8409b | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC.
5a0adf60-74ff-5fe6-b4d0-bd4064d2a01e | note | Standard / Specification - Project Specification 4.3
57b31059-a1ef-5138-ac81-a2c861002c3d | note | Verifying Document - IANZ Lab Test Report
2ca7f613-162c-5ee2-83fc-db1a58a8a44f | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
3ca2a53a-d16f-538d-8f33-c2e7d8481abf | note | Activity - H
ba3f57e7-fa79-5100-999c-4e83448459c4 | note | By - QE
b320de80-8843-5e19-8d19-01ff011794aa | signoff | AUTHORITY HOLDPOINT
fdd741d2-6577-58d6-8c1e-2d0c043b5480 | section | 3.2 SW Manhole Construction
8a67bad2-49a0-5b3e-9e07-3e95e06d76d3 | checkpoint | 3.2.1 - Foundation Compliance
dcec4b76-a35a-5a06-9a8d-29d8238c9847 | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
00c8b96c-19a5-5475-912e-4316d41e6e37 | note | Standard / Specification - Project Specification 4.3
7d677d75-abd9-53e8-b241-5dcf600e67ef | note | Verifying Document - IANZ Scala test result
5d063390-2611-5165-8299-86528408eea5 | note | Frequency - 1 Test/Manhole
dbd0670e-e320-5db0-84a5-dd06c660d2bf | note | Activity - H
bd3b026b-9a06-55d4-bdb5-132aa5be49ca | note | By - QE
1d9c8c56-63b0-51a5-9a79-b07c71904f6b | signoff | AUTHORITY HOLDPOINT
bba225a9-0f80-59b4-9bef-ab1078d3c8c6 | checkpoint | 3.2.2 - Undercut Backfill Compliance
39adc7b4-7c09-5d68-b4de-2afda2fef248 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average98%) of MDD
2e017776-83f1-57c1-b446-0ea74d0331e5 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
97f1d62b-680b-5711-ba4b-7f5b0f2b1450 | note | Verifying Document - IANZ Lab Test Report
b82b0243-c431-5bf6-bef2-54f9e9604ed4 | note | Frequency - 1 Test/Manhole if Undercut required
db6d6ab5-d974-5cc2-b57c-e9036d4fe47f | note | Activity - H
51b8047d-5ab9-52d7-b996-5a03129f824d | note | By - QE
af94d21a-5271-5425-9f08-ed410f981ce9 | signoff | AUTHORITY HOLDPOINT
add54623-858b-5fb5-ae1b-e4f44b3957d6 | checkpoint | 3.2.3 - Bedding Compaction Testing
2ae700cd-cdff-561f-9c54-c990abd4899e | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average98%) of MDD
8eb8191a-61be-5741-99e3-a38fa32a2bd4 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
15e97f48-55d1-5511-b25c-c3910dd31d24 | note | Verifying Document - IANZ Lab Test Report
6596043b-5c4a-581d-b4bd-86665c83b1dd | note | Frequency - 1 Test/Manhole
003075f7-e290-5eb6-a26a-9457ff57961c | note | Activity - H
75d1fa86-4533-5a8f-b029-aec3817e6ed7 | note | By - QE
9a0b64af-4c06-5035-a1a7-ffdc00e72ca6 | signoff | AUTHORITY HOLDPOINT
23f98f0a-b4da-5918-8708-f0ec9ba2ce0a | checkpoint | 3.2.4 - Backfill Inspection
80e98b3b-70ee-589d-99a7-8585136c48f5 | note | Acceptance / Conformance Criteria - Inspection of manhole prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the manhole
c72fb28c-e022-5303-a650-9e008cf50310 | note | Standard / Specification - Project Specification 4.3
87c71e3f-7a35-5568-bb19-d8524210f6d0 | note | Verifying Document - Photographs
6e2b4e89-bad4-5a42-96c2-1a70cf38076d | note | Frequency - Continuous
c5f29725-7a10-5c82-a80d-e13fc08c62b8 | note | Activity - S
5ea80f2a-4b35-53da-a64f-0b12bc74d1c2 | note | By - PE
971e11e1-7485-5df2-ad2e-34c9f843d784 | checkpoint | 3.2.5 - Survey
6b93d645-4ecf-56be-a7fa-df9892ec778e | note | Acceptance / Conformance Criteria - Invert Levels The permissible deviation from the designated level of the invert at each manhole or structure shall be ± 50mm, provided that the fall between successive manholes or structures shall be at least 90% of that specified. Horizontal Alignment The permissible deviation of the horizontal alignment between manholes or structures shall be ± 100mm. Gradient For straight gradients, the permissible deviation from the specified gradient shall be ± 50mm from a straight line drawn between the inverts of successive manholes, provided that no point in the pipeline is lower than any downstream point.
1ac3f541-1f81-5dc6-8556-14d6f56de1d6 | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
2ef1a085-438f-59d5-b3fd-50ead3ef546b | note | Verifying Document - Survey Data
235d4e1e-4ebb-569d-b7c5-6ef33aa85739 | note | Frequency - Continuous
5483ddd0-7ac7-592a-bc95-d7f40b712b95 | note | Activity - C
caf7d5bb-97cc-5104-9b91-f1fdf092b1af | note | By - SV
51a08071-576d-586e-a242-7407b41b31bd | checkpoint | 3.2.6 - Backfill Compaction Testing
318dea9e-f21a-516d-998f-cefd11329da4 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC.
3fcf6580-7b80-5d37-8434-4a4bf5773b2f | note | Standard / Specification - Project Specification 4.3
41973aa3-f55c-5b99-af6c-3e7072fe92c3 | note | Verifying Document - IANZ Lab Test Report
085388e7-2c92-5ba2-a83e-694ebd60d6ab | note | Frequency - 4 Density test per layer at Quarter Points around the Structure
c006baea-7876-523a-b03d-5b741204d653 | note | Activity - H
6e4a94cc-536c-56b9-9988-83741cadbbc5 | note | By - QE
4b1913c1-d7cf-5611-8bb8-1cfb1a20ddf0 | signoff | AUTHORITY HOLDPOINT
63c09d65-2137-531e-91b3-c1d0a8339711 | checkpoint | 3.2.7 - Haunching
5659e5ec-fb84-5ec0-9f8c-a5b25af378c7 | note | Acceptance / Conformance Criteria - All the MH's needs to be haunched as per the specifications
40a23dd4-539d-586c-b1b7-6b350a9581dc | note | Standard / Specification - RITS
d9a6375d-0eef-528f-9a15-48556a44142e | note | Verifying Document - Photographs
2799a095-3978-5051-aa95-4d0db01a222c | note | Frequency - Continuous
6f9a12d4-fd19-5973-8db6-606ab7a73450 | note | Activity - S
08a70049-a942-524f-91d4-b28a82d75d02 | note | By - PE
daa43319-258f-5c35-a641-e55348d73e9f | section | 3.3 SW Catchpit Construction
300b8fa1-28bb-53b2-8f55-761644c8d091 | checkpoint | 3.3.1 - Foundation Compliance
b5bcd2e4-2d17-56bd-a5db-81d297579443 | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
6bbdf8da-2c8e-5d2b-b460-d0096881e4c4 | note | Standard / Specification - Project Specification 4.3
18d529ea-89eb-59fb-97f7-391b734c33f8 | note | Verifying Document - IANZ Scala test result
87595e9e-bb05-5747-87d5-a4ed3ece4f65 | note | Frequency - 1 Test/Catchpit
e726b3b3-be6d-5a7c-a618-aa07aebbec81 | note | Activity - H
bd723658-bc76-5c1f-bc44-f3eca7d562d1 | note | By - QE
5d6e6d8d-55e5-5479-9783-aa0b5e657ed4 | signoff | AUTHORITY HOLDPOINT
528b8a8c-c255-597a-a5aa-ccae7f5d2756 | checkpoint | 3.3.2 - Undercut Backfill Compliance
80cc47a7-b6e1-5136-81bd-f07069b91b8e | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average98%) of MDD
c4c34550-803d-55f4-838d-e8392fdf9fd2 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
b7643824-0758-5387-ac1b-54ba81825658 | note | Verifying Document - IANZ Lab Test Report
f9947440-9d2b-53b7-832d-0d9d1f819fbb | note | Frequency - 1 Test/Catchpit if Undercut required
11bfade2-10e4-5df8-a782-7f7e1df7d556 | note | Activity - H
ad79f347-8d68-53d4-8203-fd74f1958ad5 | note | By - QE
8bbc0a68-437f-5361-a976-eb875cb85fc0 | signoff | AUTHORITY HOLDPOINT
99104720-245c-5b25-8b1b-18aeffe4b9f6 | checkpoint | 3.3.3 - Bedding Compaction Testing
648a2b95-dd00-54ea-ac31-e22564f82a91 | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average98%) of MDD
5646338b-6181-5b18-b998-28102fa4c4b3 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
60218604-2f09-54fd-9073-ae1aaed2a405 | note | Verifying Document - IANZ Lab Test Report
e7c00a95-6aa8-5929-87fa-96e4a3c4dde4 | note | Frequency - 1 Test/Catchpit
f0a01638-4414-5fa4-a096-f22a36e03247 | note | Activity - H
d558e9a6-05a1-54d6-9592-b7fe56f33911 | note | By - QE
3c79a68b-3003-5e37-bd3f-e2d6d8c7e743 | signoff | AUTHORITY HOLDPOINT
8c75aa70-f4b1-5a44-b5ae-7c14fc238095 | checkpoint | 3.3.4 - Backfill Inspection
c467db57-ff4b-5807-8eee-15fae2cf0df7 | note | Acceptance / Conformance Criteria - Inspection of catchpit prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the catchpit
ffb11fbc-3b83-5abd-913a-240698c4df57 | note | Standard / Specification - Project Specification 4.3
32b11a35-8a77-5aaa-bdb1-d7cf228e6aaf | note | Verifying Document - Photographs
b6eafff6-bdea-547a-8a04-1cb3793877d3 | note | Frequency - Continuous
a1f137a5-0c59-59e3-b70b-62dc170cc355 | note | Activity - S
c9cef0a2-1b0e-535b-8f99-d8e4d17c3ecd | note | By - PE
d2e13628-b927-50fd-ad8e-db3f761f1f7d | checkpoint | 3.3.5 - Survey
7197b535-45c2-5809-829e-ebe391e834c7 | note | Acceptance / Conformance Criteria - Invert Levels The permissible deviation from the designated level of the invert at each manhole or structure shall be ± 50mm, provided that the fall between successive manholes or structures shall be at least 90% of that specified. Horizontal Alignment The permissible deviation of the horizontal alignment between manholes or structures shall be ± 100mm. Gradient For straight gradients, the permissible deviation from the specified gradient shall be ± 50mm from a straight line drawn between the inverts of successive manholes, provided that no point in the pipeline is lower than any downstream point.
a1ee0ca8-a47b-5917-bd54-f5214297b86b | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
76fa5315-b0f5-58e3-acfe-56024a1d6ac4 | note | Verifying Document - Survey Data
e150227c-5e94-5830-b10d-ea0b898175bf | note | Frequency - Continuous
5d550601-8749-5225-a5ab-5b74c1aa57c8 | note | Activity - C
16a0960f-ef12-5ca6-ba4b-afc4551b968b | note | By - SV
652c96e1-768e-5161-abb8-33857043d37c | checkpoint | 3.3.6 - Backfill Compaction Testing
eb686d29-26c4-5f20-adc9-e52220561e9e | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC.
3e46d6be-d908-593c-b47a-2cdd80cb0094 | note | Standard / Specification - Project Specification 4.3
b1763e05-12f1-56b7-8fe0-96265442db5b | note | Verifying Document - IANZ Lab Test Report
5bcd4b69-2adf-5059-bc82-158e8c321dbf | note | Frequency - 4 Density test per layer at Quarter Points around the Structure
a5f5cba0-c703-577a-af89-de2bad6a32ee | note | Activity - H
ebbf3c75-97de-50a0-b256-7d083ae04ea3 | note | By - QE
2071ec85-9200-561c-aa34-f24a7392bb50 | signoff | AUTHORITY HOLDPOINT
91838760-1f3d-5d5a-aef7-b8985744096a | section | 3.4 Riprap & Boulders Installation
bd188581-f077-5ef2-a86e-5982480525c1 | checkpoint | 3.4.1 - Rip-Rap Material
b321cd8c-5e46-5864-aba5-f794ff7ad43c | note | Acceptance / Conformance Criteria - The material shall comprise imported screened quarry blasting's and/or crushed basalt, greywacke or other angular hard rock which shall conform to Density, Crushing Resistance , Weathering Classification, Abrasion Resistance, Calcite intrusions, Grading, Shape. No rock riprap or boulders shall be placed until the Contractor has provided test results to prove compliance with the requirements and obtained approval of the Engineer.
b68f6a88-b769-531b-b43d-ea229b1af715 | note | Standard / Specification - Project Specification 4.7.1
710b49eb-0085-53e1-9708-0c05bc07c290 | note | Verifying Document - IANZ Lab Report
509fd158-cd61-5f76-9574-a828fce7ffd9 | note | Frequency - Prior to placement
c4be62b1-dd9b-5431-9751-6efbea20f7f2 | note | Activity - HP
08dd237a-e262-5a54-9704-4d1aafdb9aa1 | note | By - ENG
eaabc864-faa9-5a81-ae67-142bdcfbceef | signoff | AUTHORITY HOLDPOINT
57540095-a1da-5db5-8879-72ce52ebc6a7 | checkpoint | 3.4.2 - Soil Rip-Rap Material
ae586004-69f3-51f9-a2ab-3fb9c500fb06 | note | Acceptance / Conformance Criteria - Where soil riprap is specified on the Drawings, approved riprap rock shall be pre-mixed with topsoil from on site at a ratio of 70% riprap to 30% soil by volume.
4585a3e6-61dc-5271-b76a-4db994ee98c2 | note | Standard / Specification - Project Specification 4.7.4
5afcc23e-4686-5030-adc5-8cf217b29856 | note | Verifying Document - Dockets/Site Notes
1b6e59a7-08e6-5461-b23a-b005331f1c91 | note | Frequency - Each Batch
4f1355f3-bfa8-5d3e-95e0-b69bb3f6889a | note | Activity - R
e0e2ab75-0816-5f19-955a-022b76b98747 | note | By - PE
6f4b44e8-e52b-59c3-bfd7-07b4903aaffa | checkpoint | 3.4.3 - Void Filling Rip-Rap Material
0fb9879d-1dc8-5b88-8be9-e9d76f5bee87 | note | Acceptance / Conformance Criteria - Where void-filled riprap is specified on the Drawings, the riprap rock shall be premixed with well graded granular material with a maximum particle size of 40mm (GAP 40) at a ratio of 70% riprap to 30% GAP 40 by volume.
4cd86cc3-8c69-5de8-943f-2ea0f7b3290f | note | Standard / Specification - Project Specification 4.7.5
72cb2c30-925b-5688-bcae-53c504748bb8 | note | Verifying Document - Dockets/Site Notes
2c5fc2af-b150-58a3-871e-7fda26bfac99 | note | Frequency - Each Batch
55719c40-e0df-5036-a089-ee1c0d9c9da6 | note | Activity - R
0dc87d3c-994a-52bd-bcde-99f769a51b07 | note | By - PE
c23265cb-94ad-5549-95f2-08d7740bde24 | checkpoint | 3.4.4 - Grouted Boulder
5d119a4a-7190-56ea-a138-60a8225dc9f2 | note | Acceptance / Conformance Criteria - Boulders must be approved by the Engineer, prior to placement Grout used for grouted boulder structures shall meet the requirements of NZS 3109
e49b26c5-3d8c-535e-a12c-c23ce98772d4 | note | Standard / Specification - Project Specification 4.7.6
79b8a383-a5a9-5a06-969f-f6aba483cb0e | note | Verifying Document - Site Records Data Sheet
b03711ab-ad6c-5f3b-b345-55a98e6258f5 | note | Frequency - Prior to placement
1b8ab041-d166-5770-a6f6-2e79d7c9116c | note | Activity - HP
5191a328-e62a-5de8-9966-507dbde63370 | note | By - ENG
a1c8800a-1602-5c05-88e7-0f27fd5de5b5 | signoff | AUTHORITY HOLDPOINT
d7e3d429-5c2c-560c-a07e-a3b9ac4a87c4 | checkpoint | 3.4.5 - Achieving Required Depths
953e1403-bb20-5da8-8128-631b97ed3482 | note | Acceptance / Conformance Criteria - As per IFC Drawings
830943ec-076f-5cb7-bc84-87871c978dea | note | Standard / Specification - Project Specification
4c48f30e-2955-567f-a1dd-288e00897eac | note | Verifying Document - Photos showing thickness/depth Each Section Labelled
969c046d-ac38-5cd9-9eb3-4264be2d77bf | note | Frequency - After Placement
b22883ca-794f-5d96-a004-b5aa14482988 | note | Activity - H
dc639aaa-e29a-5d1e-a35b-050828c37bdb | note | By - PE
67469e4c-4702-511c-993c-4fd2ca883b4a | signoff | AUTHORITY HOLDPOINT
10fb46ce-e0b0-5ea6-9067-24f1b6b0b998 | section | 3.5 CCTV & Reinstatement
69f084dc-a280-5bae-885a-038ae9240059 | checkpoint | 3.5.1 - CCTV Inspection
f0fab8de-949c-5ebc-a248-d79779f581c8 | note | Acceptance / Conformance Criteria - Quality Check on New Works
18687b5c-cc85-5a1b-b730-2eb46416a2ca | note | Standard / Specification - Project Specification 4.4 NZ Pipe Inspection Manual
63f2aecc-85a2-59a9-9b6d-adc6a21fed50 | note | Verifying Document - CCTV Report
69d35b40-75fe-5dd2-b466-ea0d100bbaa8 | note | Frequency - 1 per line
66432b17-ac2c-5cfd-967e-78fc98c03e74 | note | Activity - S
488fadbe-90bf-5b0d-8b6b-8eb71925a20a | note | By - PE
f7a982c0-3823-54cd-9694-7913082459bc | checkpoint | 3.5.2 - Reinstatement
a312f052-372d-50f9-9883-57a8dbe105e1 | note | Acceptance / Conformance Criteria - Quality Check on New Works/All the MH Lids and Cespit Levels should align with the pavement specification in terms of level & alignment
7be67543-bfaa-5a20-997e-ed431314971f | note | Standard / Specification - Reinstate and Tie into existing surrounds
d1cee765-ff68-569f-93cc-97c4f195f95c | note | Verifying Document - Photographs & Level Checks
4d5922ad-a59f-5136-9229-4b0ba6edc19b | note | Frequency - Continuous
a287eccd-79c8-502e-9bf6-c7365abc4ed2 | note | Activity - S
63711978-92e4-5993-a92f-a80b22d2f3bd | note | By - PE
85475bb6-9a9c-571e-bdc0-15f2014da4d2 | section | 4. Post-construction (Final Inspection & Handover)
7ae1b87b-673c-5c28-a4bd-4b55b08e4e89 | checkpoint | 4.1 - Survey Redline Drawings
53857957-862a-5c02-affb-420f8bbcb2d4 | note | Acceptance / Conformance Criteria - Quality Check on New Works based on the tolerances in RITS
0a6e7516-d189-58bf-b63f-ed3019cfa3f0 | note | Standard / Specification - Project Specification
97975fe6-bf31-533e-aa46-c1eb07ef0da3 | note | Verifying Document - Survey Data As Built Drawings Photographs Red-Pen As Built
64440248-836a-5ff7-84fb-19292f75fdaf | note | Frequency - Post works completion
eca96e49-ee5e-5cc0-966e-5e8083612ee8 | note | Activity - H
f0c23b4c-fd20-5916-b85f-437a97b969e5 | note | By - SV
b4c049a0-485a-5f2e-99f2-48ccf99481f6 | signoff | AUTHORITY HOLDPOINT
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
f88220e1-35f0-5d10-a2fc-48f29fe0b58b | checklist | ITP - Streetlighting - Rev C | itp | ITP - Streetlighting - Rev C
5628a8d4-88a1-5785-a410-312c9b25dfa1 | section | 1.1 - General
44167cb4-9cba-5322-8cf8-54cda693e177 | checkpoint | 1.1.1 - Drawings
a3de2d74-21d0-5582-92b4-1ae7bc58ac16 | note | Acceptance / Conformance Criteria - Prior to starting works, ensure that the construction drawings are both IFC and the Current Version.
8f9725e5-dffa-5475-b513-f3c7a432abda | note | Standard / Specification - Downer
48977b38-2a3c-5563-b98c-9206b4725e94 | note | Verifying Document - IFC Drawings
06dc42aa-f4c7-5de2-ba65-f7ab71ce7356 | note | Frequency - Prior to work planning and start
3c8f00a4-011a-5c2f-9675-062f8e61effa | note | Activity - M
3168ccd6-ebc3-5d7f-a7d5-863e0c0bf506 | note | By - PE
bd8dbf15-4c94-513c-89b3-b7a8ad8aee55 | checkpoint | 1.1.2 - Power Connection Application
ccd54300-d4d7-5058-b31c-7d6d34ba8fcd | note | Acceptance / Conformance Criteria - Submit new streetlighting connection request via WEL Connect portal.
4c5eae55-5181-56bd-99f7-93457375ae5f | note | Standard / Specification - WEL Requirements
cf6da2e8-7fbf-50a0-a5db-29a5aa8f0244 | note | Verifying Document - Application Form
1db5b030-fd3c-57bf-aa68-601f31651c04 | note | Frequency - Once
6a2ebb1a-804e-5c37-9f5f-2bb31b01449d | note | Activity - H
7dcb24ca-8578-5a58-94a7-c7aebeaba83e | note | By - PE
c2a12f9a-bf3c-5765-b5f4-aa2e3913e9bc | checkpoint | 1.1.3 - Construction Pack (1)
8a6216df-bc96-5a7b-a5d6-508324b8e2b0 | note | Acceptance / Conformance Criteria - ITP to be submitted to the Engineer and approved prior to works beginning
99a26ea9-263d-5b32-813b-3bdaa137025d | note | Standard / Specification - Downer
adfe312a-266c-5b24-ba0a-62cd06db1fd8 | note | Verifying Document - In-Eight Document Approval/Acknowledgement
acd68749-24f5-5aea-9762-8580ee45d332 | note | Frequency - Submit 10 days prior to commencement of works
bb80e0e9-e097-569c-a112-fb905f182e87 | note | Activity - H
58718269-f871-5198-84d0-0c12964f5d6a | note | By - PE
d406a60c-ceaf-50be-b99a-1589f1f90d4a | checkpoint | 1.1.3 - Construction Pack (2)
d68c3e67-fc7e-5393-abff-6c3a11024596 | note | Acceptance / Conformance Criteria - Methodology and associated documents to be prepared, reviewed and approved internally prior to work commencement.
5c2199e1-2a20-5368-85e1-19c004989898 | note | Standard / Specification - Downer
83e6e0d1-2866-53b3-a1d3-98be7f650486 | note | Verifying Document - Construction Pack Sign Off
832a34b8-c26b-57c3-8cb6-abbdfd99d78b | note | Frequency - Prior to Construction & after any major incident
b90921d0-c20e-5c18-aeed-42bb1346090b | note | Activity - M
47b29234-b37b-539a-b7ac-022807ed6a3f | note | By - PE
dc3cffd8-503b-5d65-af51-96286f96d0b6 | checkpoint | 1.1.4 - Survey Set-out
076e2c3d-7984-5a7c-9409-aef47385f457 | note | Acceptance / Conformance Criteria - Ensure streetlight locations are set out per IFC drawings/data.
948f3092-04ec-5e4a-89ff-64e7987cfdc2 | note | Standard / Specification - Design Drawings
ea90aa83-5866-51e7-a527-82b168584f4b | note | Verifying Document - ITP Sign Off
b465bc9b-e0be-5348-b733-88cceb9f6b03 | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
f84c7a7c-a29e-5e94-9896-143af8ffb392 | note | Activity - M
eb825140-f341-575f-853a-599d96e1d56d | note | By - PE
c38fc1a4-700d-537c-87e7-8cbac3d52996 | checkpoint | 1.1.5 - Environmental Protection
82db6031-9ffa-50e7-93b9-b0240c35b755 | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
62fec460-e442-58e6-a255-638e495550d2 | note | Standard / Specification - Project ESCP Plans
eec13850-623f-5b2f-a4c3-5f53916dbd39 | note | Verifying Document - ITP Sign Off
b22e0258-66e6-5635-8a28-52bfa8c69cf5 | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
231e5c4a-1751-5a4b-8293-ec3381d1809c | note | Activity - M
ade57c56-b692-5aa7-95ca-e191cdaa2f71 | note | By - PE
b9c7d6e1-8d3e-588b-a8d5-2d79f6ca8788 | checkpoint | 1.1.6 - Stakeholder
d0ff9ed4-8621-510b-92f2-c0d228d4a2b4 | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works. Agree plans for maintaining access to properties during construction with landowners.
fe50bc8b-5efa-5ea9-828b-35c73834152c | note | Standard / Specification - Project Stakeholder Management Plan
1a1b544b-cd6a-5b70-a36e-072d0c6fd792 | note | Verifying Document - ITP Sign Off
dee95153-7e76-5f5a-ac7a-c74e016e71b6 | note | Frequency - Prior to Construction with continue updates throughout the works
0a41c492-74cc-5b7e-ae98-bdfe791ac4c4 | note | Activity - M
fa4ce277-bace-5414-9b1e-2e809d05421f | note | By - PE
50d318b7-94f9-5c07-86c4-dc1703189d8f | checkpoint | 1.1.6 - Permits
0da166e2-d8ce-54bd-a796-84c21a2ec108 | note | Acceptance / Conformance Criteria - Ground Disturbance Permit must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip.
c4fa453b-967a-59a2-9b46-8f3c119a56ef | note | ? Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. Doner Permit encompasses external provider permit requirements.
f221c398-07cf-5fe9-8262-e64bd9dbb056 | note | ? All known services must be clearly marked on site and briefed to the workforce .
35ccb006-0e03-5ff7-9338-01382db03d15 | note | Standard / Specification - Section 2.2.10 Project Specification
f0d8c0b3-c31a-5c8d-918e-02309cc3acb8 | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
5d46cde5-8510-552f-824f-5978bc315f07 | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
78ad1714-004e-53d8-ad4e-d23d0ea1d896 | note | Activity - H
b01936ac-c17e-5be5-aff7-167214ad7479 | note | By - PE
4247510b-2756-559a-b5d6-1e8797938e03 | section | 2.1 - General
b000bbeb-8d76-552d-952e-2b3c29a6f0bd | checkpoint | 2.1.1 - Walk-over
2d143d4c-8c17-5af2-a95a-3b2808340849 | note | Acceptance / Conformance Criteria - BBO representative to walk over and confirm/approve locations for install. Including reviewing accessibility of doors.
67ae121c-bcd5-5155-bf07-1aa9e02704c7 | note | Standard / Specification - Design Drawings / RITS 3.6.3
77440c7f-dd26-5957-a2a7-140dc7778cc8 | note | Verifying Document - Written correspondence
99c519b7-ab20-5881-8d41-faee9e08d22c | note | Frequency - Prior to construction
3306da5c-16d6-5fe1-810b-3ba7c39bf4c5 | note | Activity - HP
b94539ae-bd38-52ef-87b1-b7df994d4c54 | note | By - PE / BBO
e0f66e31-9449-5c36-8d41-3cc0058cff45 | signoff | AUTHORITY HOLDPOINT
ea4c8202-6851-5106-bf05-c605970f3d1d | checkpoint | 2.1.2 - Light Poles Materials/Delivery
2df090cd-abe8-5432-86cd-70cd721474f2 | note | Acceptance / Conformance Criteria - Evidence of manufacturer and product name.
a42a8f65-8703-5eab-b13c-913fd6d7ac4c | note | Standard / Specification - BBO Request
e8ab109f-73f6-5d53-877b-dc2187455ada | note | Verifying Document - Delivery Dockets
9927671c-c4d0-56d4-b6e9-7ed16b3f8f9c | note | Frequency - Once per pole group installation
2b52bb6d-2046-5761-8aba-b5cffdfd2f56 | note | Activity - M
90bce1d5-b3fe-58e5-8754-8b9bee86752d | note | By - IBEX
8cbfd47a-19e4-5e58-9213-c56a4eb312bd | section | 3.1 - Civil (Pole) Installations
8fcbec6a-3e96-55e7-9ea5-ab141665349e | checkpoint | 3.1.1 - Ducting Backfill Material
8222565c-699f-5a03-9f0a-4e96d0da6f75 | note | Acceptance / Conformance Criteria - COVERED UNDER UTILITY TRENCH ITP.
72a9835d-dcaa-57dc-b623-07a7798b36c3 | note | ? Where there is any exposed part of the cable (i.e. between termination of the duct and entry into streetlight pole underground hatch), surround with min. 100mm thickness sand material.
90df0d16-05a1-5b62-9f6d-69ce9e4aab72 | note | Standard / Specification - WEL Requirement
3325b3eb-a509-5bad-addc-6d9349885307 | note | Verifying Document - Photographs
ed60b599-34f8-501e-8dfd-e934ea3c2cd1 | note | Frequency - Verification on random selection of poles
899316fc-6aba-5ba1-add1-e507dad579c4 | note | Activity - M
1fa822c1-9461-5929-afc8-52b6980b2bb9 | note | By - IBEX / PE
1dde91b2-95bc-5d05-9620-2745f9382893 | checkpoint | 3.1.2 - Access Hatch/Door Accessibility
ee96db52-4f63-5782-8241-a5f44a5029a9 | note | Acceptance / Conformance Criteria - Visual check to ensure accessibility of doors.
1008970d-3942-50fe-a9c1-17c117b79c13 | note | Standard / Specification - RITS 3.6.3
cd84f61d-ee2b-5661-90c9-435ff63f05da | note | Verifying Document - Nil - Visual Check
84446c3e-6c42-59f2-8de0-292bd9e4ba71 | note | Frequency - Each pole
006b666d-12db-5bba-b683-47532f57fae9 | note | Activity - M
6e2178ef-8c03-5b83-96c6-076e813002ff | note | By - IBEX / PE
1ecdb50c-ad04-55f6-8779-07048dda3412 | checkpoint | 3.1.3 - Pole Installation Positions
86ac0252-2e53-537f-915d-dc7a37d49d13 | note | Acceptance / Conformance Criteria - Poles within following tolerances:
e3084716-5af0-5451-8b30-b3b98c5729ae | note | ? +/- 0.5m parallel to the carriageway
1fb4a3b2-13a7-511d-8231-ee27be182692 | note | ? +/- 0.2m perpendicular to the carriageway
1955698b-f110-5875-ac0a-bb6d94af9676 | note | ? +/- 0.2m vertically
df0db22f-1601-5121-a804-6d9ab2e09d5e | note | Standard / Specification - Design Drawings
8ba4e170-2fef-5cde-ba48-4c970f277719 | note | Verifying Document - As-builts
3a035543-9c9e-5149-ba5d-d3cdb785caa6 | note | Frequency - Each pole
0fa1f756-81b0-5590-b768-76d84fd7f25a | note | Activity - H
fc89723f-6e6c-5b63-9b4c-b6cb8b60b179 | note | By - PE
fb42c1d2-bc07-5391-b3de-530de2519477 | section | 3.2 - Cabling, Electrical Testing and Commissioning
b53734fb-17c0-5b4a-af29-2d7906ae504b | checkpoint | 3.2.1 - Earth Wiring
04e0591b-bffb-5dd0-8d3c-405231de065a | note | Acceptance / Conformance Criteria - Photos of streetlight earth once completed.
11ba273d-db14-5bba-899f-d13ee78f2190 | note | Standard / Specification - BBO Request
52da4e9c-f6fe-5966-8b40-b123e87bda76 | note | Verifying Document - Photograph
80e8fb9f-55b8-53d3-8904-d0a53bba398b | note | Frequency - Each earth
fe02b727-f9db-5bf5-864e-7f3c6a20d15e | note | Activity - M
0f99849b-2d19-545b-a63f-a65f354fc19b | note | By - IBEX / PE
1b60eff4-4e67-5de7-ad23-b48e4cd4583b | checkpoint | 3.2.2 - Electrical Certification
60ed628e-c347-5e43-a2cf-313e39e188cf | note | Acceptance / Conformance Criteria - Completed and signed certificate of electrical compliance (COC) and record of inspection (ROI).
8cd95bbb-2165-561a-95f2-cdfa4e1c6a7e | note | Confirm that poles are:
2940a440-c09b-5946-9270-6a42b9d8b611 | note | ? Earthed to AS/NZS 3000:2018
916b87fa-0ffe-53c6-bafd-6c7ba048d95e | note | ? Wired to AS/NZS 3000 and AS/NZS 3008:1.2
a56cd35c-ebfd-5101-bb1d-2850a326c5ef | note | ? Conforming to the NZ Electrical (Safety) Regulations
20dc2bd8-e318-5d56-b92a-2e3cf9194ab3 | note | Standard / Specification - Design Drawings
3fba7efc-79c2-5e27-b97b-046dfb789646 | note | Verifying Document - Certificate
86bb62e9-5297-59f4-937d-aaf7b81a59cf | note | Frequency - Each pole
f55925cf-b786-5b43-a307-65616f5f8eb1 | note | Activity - H
c7c12ee1-0517-519c-8622-e88996d84bd9 | note | By - IBEX
10f73d4d-2f99-5826-9ff7-95a501918f48 | checkpoint | 3.2.3 - Network Company Acceptance
5d99ecc1-c413-5887-a3a6-3919ec19957d | note | Acceptance / Conformance Criteria - Written acceptance of all underground cabling and circuitry, including acceptance of assumed responsibility for future maintenance and renewal.
1f0a9489-1b13-5cd4-88ae-2fa58ca1546a | note | Standard / Specification - RITS 3.6.8
5d1abee3-2209-5100-8bdc-68a137f45aa6 | note | Verifying Document - Written Correspondance/Acceptance
3b03f4d6-bc3b-5261-bc7b-7838647e1721 | note | Frequency - Once prior to comissioning
9a8c39f0-3f9e-55fe-9953-c44bd15ca842 | note | Activity - H
e7c1bdf1-00be-5b9a-af09-67b81949a1ff | note | By - WEL
af1d387a-e24f-53f3-98c0-b94e4af93490 | section | 4.1 - General
b03e43a0-bbdf-5edb-8b45-6757c3f8d578 | checkpoint | 4.1.1 - Survey Redline Drawings
3d242e5a-b3c9-55f0-9521-a042a3d4928d | note | Acceptance / Conformance Criteria - Asbuilts reviewed and submitted showing final location of all poles
d991739a-0e59-5272-9a31-ded1a4dfe9a9 | note | Standard / Specification - Project Specification
9f595855-e3bd-59de-ad0b-c42a74766405 | note | Verifying Document - Survey Data As Built Drawings, Photographs, Red Pen As- Builts including Undercuts
c34cd3ea-534b-5a69-9490-940ab4263809 | note | Frequency - Post Works Completion
c2416c06-035d-5532-b108-88fa948554bd | note | Activity - H
73a5bd3b-dd02-59cf-85fb-aa4a3e2ae993 | note | By - PE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
d293f4cf-ebaf-502a-a227-628f998876f5 | checklist | ITP - Subsoil Drainage - Rev B | itp | ITP - Subsoil Drainage - Rev B
8c9335a7-3af5-5e47-a887-39a89ff08c27 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
e3e4320b-0ae2-5934-8f86-f48691f90a6d | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
a5cff262-b410-5ef3-a4ed-c68ff3ccedfc | note | Standard / Specification - Downer
ed9bd141-5b48-5aad-97ce-36073ad871fe | note | Verifying Document - Construction Pack
f85a1e6e-b3ee-5bb9-8cc8-e9cfe23826e0 | note | Frequency - Submit 10 days prior to commencement of works
d94ea74e-8904-5764-8156-a617a6ac5fc7 | note | Activity - H
bc1e6f46-f6c8-598f-ba1d-340b08b6912e | note | By - PE
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
66f5e34e-d324-54c8-8b73-6557f7a98a92 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
fcead67b-af71-5ce8-8593-1f4cf7fe5175 | note | Standard / Specification - Downer
6b14f005-ad29-5551-90c6-e9748d55704d | note | Verifying Document - Survey Records
2922226c-8e5b-5dd5-b869-a226857e8214 | note | Frequency - Prior to Works
fb6b461f-dfa6-5b91-9443-7737b0ef96a5 | note | Activity - H
f1cd4e61-b516-5014-a260-98792eea5814 | note | By - SV
7b8b4071-ba18-54c4-a07c-9e192aec85d8 | checkpoint | 3.01.03 - Approved Construction Drawings
fde2da03-ff8d-5b00-a0b9-84eaa06a0153 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
0752b5eb-71af-54dc-bb93-4cf9c204bd79 | note | Standard / Specification - Downer
dffe62dd-1ef0-51e7-aac4-0fabcb726105 | note | Verifying Document - IFC Drawings
9c70aef2-39e1-51c0-814f-d725d260b35d | note | Frequency - Prior to works start
9d1a3400-5b43-5b12-9930-7ff952aa762c | note | Activity - H
6da2d4f1-345b-5e86-bc5b-84d2012936f5 | note | By - PE
f54e7b48-3f2b-51d6-93b0-54755388f0cc | checkpoint | 3.01.04 - Topographic surveys for measurement
247ba338-8e35-5709-9cab-dadbbba10a43 | note | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
4dbb98dd-29b1-52dd-9a5c-8a652de07099 | note | Standard / Specification - PS 2.2.12
3ae9b607-c597-5bfb-9af8-f8c5783c9711 | note | Verifying Document - As-built
c2a3b149-b534-56d2-a2aa-fcccf7b87d6f | note | Frequency - Prior to works and Post Works
55219e30-e8ae-52f1-bb10-3d6fc1d24903 | note | Activity - H
849ec13f-9f1a-5628-8a2a-f193408133a4 | note | By - PE
f26fef48-d615-5889-ba64-e206f54c0d34 | checkpoint | 3.01.05 - Permits
6ce3adac-36c3-5bce-b254-8cfcea71578f | note | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
e69af894-0cdf-50fd-b743-4abf087bfb2d | note | Standard / Specification - ITP Register
9294d374-5eea-5067-9d6c-a8f6fa839752 | note | Verifying Document - ITP Sign Off
89e12c86-d074-50e1-8928-59e72a1a5c3f | note | Frequency - Prior to commencement of construction activity
32991eac-0b64-550a-ab84-ebf1587c4b7b | note | Activity - R
c206fb6c-57e6-55e5-8e8f-d54261253461 | note | By - SE
72a761a8-8bee-5916-91e9-a2f4ef42bc73 | checkpoint | 3.01.06 - Stakeholder Management
20f0f9cb-1274-5fb3-8d3f-e17434c67467 | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works, Agree plans for maintaining access to properties during construction with landowners
4cf723b9-eb44-5949-8b79-80925a2b783d | note | Standard / Specification - Project Stakeholder Management Plan
9f36a72e-254c-5020-a432-7a482ca704be | note | Verifying Document - ITP Sign Off
0198f785-e291-5042-ba9d-db23179da972 | note | Frequency - Prior to Construction with continue updates throughout the works
968643e6-cfa8-5234-be55-6b7dda886fda | note | Activity - R
01ed8ab7-4614-553d-a7cb-9e105236fd40 | note | By - SE
8ec62109-1664-5fbd-8086-47c125cee66d | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
08534115-94ee-5cfc-be8c-086ea7ffdd06 | checkpoint | 4.01.01 - Subsoil Pipes
37447c21-d9bd-500c-aa31-0993a799cb1c | note | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 160mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
2dad1c15-6feb-55ce-abf9-6797ac003351 | note | Standard / Specification - GWS 3.2.1
dceab4c2-2c90-57bf-8251-d7850b54fd8e | note | Verifying Document - Datasheet
0f33bfda-b27d-591d-ae27-6d5df859df2c | note | Frequency - Prior to installation
5d5cc8ae-9729-5ed8-b644-c4f5f81cb84c | note | Activity - C
95ca03e1-3a8f-54d1-8c87-a4e56696c92c | note | By - SE
71011ef5-31e0-5d97-b246-1d11311696c1 | checkpoint | 4.01.02 - Subsoil Drainage Aggregate
08f26c5a-ddb7-5f41-aebf-e033745f7d70 | note | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/6 including gradings (40/20 aggregate)
46bc154b-8396-506c-a819-88adb2206f91 | note | Standard / Specification - GWS 3.2.2 & 3.4
5b88fb0c-66a1-5e49-a8d5-cdf52ccf2b07 | note | Verifying Document - PSD, CR
e2794ec9-d4ea-5a33-b94d-af86ab431f4e | note | Frequency - Prior to installation
f52c5012-1778-5580-b1ac-b7a9546f876f | note | Activity - C
b115e0dd-3911-5ce4-a236-f8e0c0966a0c | note | By - SE
6d7192d6-9061-5d38-a315-d4a8752b3fa5 | checkpoint | 4.01.03 - Filter Cloth
922f59cc-c9ee-5af3-846d-3832e8976376 | note | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings. (A14 Bidim or Equivalent)
754bd53c-6759-508d-9c9f-42b977e4a2d9 | note | Standard / Specification - GWS 3.2.3
e740d2e6-4fd6-5b6e-903e-921217257ade | note | Verifying Document - Datasheet
630075fd-f369-5692-bfda-bdfbf36ddb1a | note | Frequency - Every 1,000m3. At least two weeks prior to works.
49e776b5-1c83-5b94-a552-ee1609d1a684 | note | Activity - C
6dff5458-8576-5ab5-a9ae-2cd0058980d6 | note | By - SE
f4713bb7-3aea-5dca-b516-69272c0b56ba | section | SECTION 5 – CONSTRUCTION ACTIVITY
113d79bf-1485-508d-814d-8c7c8c221530 | checkpoint | 5.01.01 - Filter Cloth Wrap Inspection
a7f90523-9f49-5e26-ab91-47fa5191045a | note | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain.
5c00adcd-b649-524d-893b-30f87ba37b4f | note | Standard / Specification - GWS 3.2.2
14873811-9be7-5dd0-a934-8fc540eaca5e | note | Verifying Document - Site Record
91c15215-cc28-5f2e-90d9-af4254081fd5 | note | Frequency - prior to backfilling
70b304fc-caab-5b41-aa65-ba20611aef2c | note | Activity - HP
258d4f9b-854f-5091-8ede-a89602b5f9eb | note | By - ENG
a2a25648-08b8-5ac9-b1a6-269e329744a0 | signoff | AUTHORITY HOLDPOINT
543c766a-67a1-5508-b12a-a4f69b9927f3 | checkpoint | 5.01.02 - Trench Backfill
66ad9e85-7ae4-5d97-bde4-fd6893820dde | note | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard of the material previously trenched through
8ae9bdfe-7318-5d5c-acd2-e4f904e06bd3 | note | Standard / Specification - GWS 3.3
268d3ca8-6fa2-5c5a-aa75-5773709bba2c | note | Verifying Document - Site Record
feb75e03-0258-585e-a689-11cbdf8e701f | note | Frequency - Each trench
de040a19-fbe0-566c-acf3-e60467c03c18 | note | Activity - I
55ab3706-dfae-54c7-b76d-3052fcb93c10 | note | By - SE
f7142f9b-2009-59fd-9453-67a19dd7865a | checkpoint | 5.01.03 - Drainage Outlets and Inspection Points
344525eb-1d74-5815-a443-95266cb8a6a2 | note | Acceptance / Conformance Criteria - At least one temporary flush point is required for each subsoil drainage system to enable flushing of the system once the earthworks are complete.
545c0bc8-2804-5fa2-9d40-968af904fbd1 | note | Standard / Specification - GWS 3.6
d84dca0a-bd73-5dfd-a8ae-1c5fa6f17cb7 | note | Verifying Document - Site Records
8a03718e-b66f-56de-8367-759667fee5ce | note | Frequency - Each Subsoil Line
53639ece-8919-5cae-b3d2-853054daaddb | note | Activity - I
dc89290d-cdb7-5804-8bc6-c147bef29a5b | note | By - SE
fd83d42b-b8ea-5d41-8883-9e6215d99eea | checkpoint | 5.01.04 - Subsoil Flushing
4d1389a4-8de2-59a9-b825-54b9750ee56a | note | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer.
b3a0eaa6-caf8-59c8-a10d-74f5d1a1950b | note | Standard / Specification - GWS 3.6
584ba4fd-01d5-5f82-9b0c-a9d438b3ce71 | note | Verifying Document - Site Records
7256c455-ef41-567d-828b-7342b5c18c49 | note | Frequency - On completion of earthworks
c55063df-be7e-5b70-8482-b2b112768188 | note | Activity - HP
77c543ea-72b4-55d3-845a-47fb7b5fc0ea | note | By - ENG
efdabe6e-46f6-51c4-9707-34eb23acdd0d | signoff | AUTHORITY HOLDPOINT
65ee871c-3fae-5bef-8ed1-f015a6f0c4aa | checkpoint | 5.01.05 - Survey
db1a13ff-dba0-5145-8e56-f359fb847c48 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
78e8a5ad-c326-5d9a-b4c0-9541320123f3 | note | Standard / Specification - Downer
d4cfc897-ac31-5109-8f62-93afcbd35528 | note | Verifying Document - Records
d218082c-7b29-5f91-b6c0-b03dc6b27398 | note | Frequency - Post construction
c7830048-5534-5a01-bb5e-179b0df836fb | note | Activity - H
15844533-95cb-5a12-93d4-001d05753d55 | note | By - SV
cd33a7f8-9b6c-5422-93be-dcae98eaa460 | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
abaa7cc7-67ff-52ad-ae9f-e9176b336a01 | checkpoint | 6.01.01 - Construction Record Compilation
ee1978d8-0e6d-5526-b6a7-946047814c4c | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
67362158-2834-5d84-ade0-ae6f1b6d0ec8 | note | Standard / Specification - Downer
a24007a3-c872-524f-b455-163c07c8e5c8 | note | Verifying Document - Records
5a7e31a5-0820-545c-b971-e36ddbf1729c | note | Frequency - Post construction
77a7e5f8-02ef-530a-91af-e607f05c7651 | note | Activity - H
e5d35e8d-f86b-5af7-ba05-d945435e2114 | note | By - SE
f4876821-e136-54ca-95e8-27fd0f400f5d | checkpoint | 6.01.02 - Survey Records
a0ac0cc4-631a-5133-b6fd-245b319aa958 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
180a867c-7a92-5f9f-a0fd-91b82f256260 | note | Standard / Specification - Downer
f7904889-fdb4-5a7c-a63b-71ef8b5cc375 | note | Verifying Document - Records
ee7885ad-839a-50d2-8da3-d7324de5c9b0 | note | Frequency - Post construction
8e415304-8692-5b9c-ae6f-9fdacca84ec7 | note | Activity - H
01269d07-f711-5592-bd77-e4c52e9edc87 | note | By - SV
a7ece1a0-6b4a-5d51-8813-156cc41a337a | checkpoint | 6.01.03 - Redline Drawings
550c52a2-03c4-52ad-89da-69f702697ea6 | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
bbd2f293-3849-57a7-b0f4-a1cb5997d079 | note | Standard / Specification - Downer
c46c584a-56df-561d-b43a-c0c3fe670d6b | note | Verifying Document - Redlines
7c2c55cb-1dba-50a9-b56b-7f21c8f7e44b | note | Frequency - Post construction
e60bc891-dbaf-5d0d-a7dc-20912d3afc1a | note | Activity - H
6749ce7f-a61b-584d-ac29-3573b9e1fca6 | note | By - PE
406cc900-58d1-549c-813d-cb4c75c9a2be | checkpoint | 6.01.05 - Photos
a95c32cc-8cc6-5355-b4f2-5e1bb87ec90e | note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
0a4eb8cb-ee4d-505e-a512-5b983f330bba | note | Standard / Specification - Downer
f1452100-2a8d-508d-b79d-8fde17341213 | note | Verifying Document - Photo Records
c69c16fa-03e6-5513-9158-4e8e0523f491 | note | Frequency - Post construction
ebc7cd71-fbb0-547b-8b4a-7904c436de14 | note | Activity - H
c5e2515f-f88b-5bcc-b12a-51916f38e97e | note | By - SE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
e9157d8c-643d-56b7-b3fe-cc71fae4beb6 | checklist | ITP - Subsoil Drainage - Rev C | itp | ITP - Subsoil Drainage - Rev C
8c9335a7-3af5-5e47-a887-39a89ff08c27 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
d7be2db3-ea6e-5081-a3fa-9f6578272af5 | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
5936e5dc-9132-5d53-b0f0-f9edfbdd1a3e | note | Standard / Specification - Downer
cfbc549f-882c-5b41-a11d-18be0dc167f0 | note | Verifying Document - Construction Pack
0319a400-84a4-55c0-8f70-441f504d8b57 | note | Frequency - Submit 10 days prior to commencement of works
598b8731-aef4-573c-9ee4-06c6f222b97c | note | Activity - H
24ef8194-9972-500e-adc3-9b62ccb8ba7a | note | By - PE
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
0b9f3034-6658-56f0-bed8-ace15c277a22 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
9e4ed420-adcf-5040-8a91-5853fed16b09 | note | Standard / Specification - Downer
a6281da7-de12-5e2e-b68c-2038b57ad103 | note | Verifying Document - Survey Records
45bc84e6-beab-520e-969b-361fcb60ac3b | note | Frequency - Prior to Works
bbb6fcb2-e555-5583-a8a9-9810156a90e3 | note | Activity - H
d53b4c04-315b-5f54-9469-90c1e8b22600 | note | By - SV
7b8b4071-ba18-54c4-a07c-9e192aec85d8 | checkpoint | 3.01.03 - Approved Construction Drawings
bdc2842a-7d3c-5544-8137-d83b5f982a4b | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
5ef2bb59-c850-5c20-b02f-ff31fd4b6d78 | note | Standard / Specification - Downer
3b11c33a-f8b5-5aa7-91f1-10782e9fcd4c | note | Verifying Document - IFC Drawings
323def97-05b9-5489-b1f2-f8c27a4140fc | note | Frequency - Prior to works start
00cf16f7-ade9-5aed-96d5-1472f835be59 | note | Activity - H
c532f3a9-d2d4-505d-9f4f-94f7ceb8bff4 | note | By - PE
f54e7b48-3f2b-51d6-93b0-54755388f0cc | checkpoint | 3.01.04 - Topographic surveys for measurement
e089d5f4-ced8-5485-83ad-883cd2451b09 | note | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
808d2cc8-9cea-5c17-bafa-6c2345d96560 | note | Standard / Specification - PS 2.2.12
e2834ee1-8f42-5772-8411-554e951bc1c2 | note | Verifying Document - As-built
b4a1ce01-172e-511d-a93b-50253d6f1411 | note | Frequency - Prior to works and Post Works
6605b2b1-c1bd-5cb6-9e50-f19229bfb5c6 | note | Activity - H
96c2efd0-54fa-513d-a450-0bd6f9b3055f | note | By - PE
f26fef48-d615-5889-ba64-e206f54c0d34 | checkpoint | 3.01.05 - Permits
468dfa97-219c-50fd-923f-0d9544cbcf74 | note | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
49520b88-dffc-5373-8e83-2849833fa509 | note | Standard / Specification - ITP Register
919e8e00-24fc-5e88-8149-179c7690596f | note | Verifying Document - ITP Sign Off
ac6c3b17-fe3f-594c-807b-37ec131c6fa3 | note | Frequency - Prior to commencement of construction activity
300f8782-e48f-5ee4-8055-969ed04e07bf | note | Activity - R
d10c2e34-7c87-51b7-9288-001049b9f637 | note | By - SE
72a761a8-8bee-5916-91e9-a2f4ef42bc73 | checkpoint | 3.01.06 - Stakeholder Management
4037dfc7-c3bd-5aa4-9e8b-fe22489a235f | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works, Agree plans for maintaining access to properties during construction with landowners
9e03c87e-42fe-5e7a-a630-a9438155d21a | note | Standard / Specification - Project Stakeholder Management Plan
58923489-7e4e-5f9a-8035-03446e1d91ac | note | Verifying Document - ITP Sign Off
1ebff814-28de-5b91-beac-5601bddfd866 | note | Frequency - Prior to Construction with continue updates throughout the works
929d5338-bda6-5c79-9ed8-ee53912897ca | note | Activity - R
673074b5-d940-5c63-88c8-6e7532dee716 | note | By - SE
8ec62109-1664-5fbd-8086-47c125cee66d | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
08534115-94ee-5cfc-be8c-086ea7ffdd06 | checkpoint | 4.01.01 - Subsoil Pipes
d023e47e-0881-5696-b786-b671d17dc843 | note | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 160mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
c9763730-9a2a-5ad5-ba5b-077d9dc7bb95 | note | Standard / Specification - GWS 3.2.1
6b68e6b6-12fb-5968-9d52-560fe63a6581 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
c7beaa27-ccc8-5dbd-a188-c2977568a3a1 | note | Frequency - Every Delievery to Site
0cc38bc5-f539-55fd-bc56-03bf014af76d | note | Activity - C
a60f67ca-2a43-568d-af02-4a88420851c4 | note | By - SE
71011ef5-31e0-5d97-b246-1d11311696c1 | checkpoint | 4.01.02 - Subsoil Drainage Aggregate
7c9b9dfc-297e-5ddf-a2f1-b17179a69881 | note | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/6 including gradings (40/20 aggregate). Be open course grade clean durable aggregate, Have a crushing resistance of no less than 100kN when tested in accordance with NZS 4407:1991 Test 3.11
d2089a10-530f-5bea-9d97-e03f611b919a | note | • Meet the following gradings when tested in accordance with NZS 4407:1991, Test 3.8.1:
1be6988c-c61e-5bbe-9f18-091fb2c8dbf0 | note | • App B - HAM2018-0136AJ Rev. 1 Geotechnical Works Specification:
619f493e-fa37-54ff-a2d4-7dfa142ac2e9 | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
ad40829b-6deb-568e-b971-18272b95949b | note | Table 2: Filter Material Gradings (Geotextile Wrapped Aggregate)
8ac0fdb2-32b2-5131-910a-4d69cbe8d50a | note | Test Sieve Aperture (mm) Percentage Passing (%)
8b672988-c8b6-50c5-aaf2-02fc53ebf6df | note | 53 100
0e075548-0ba0-5abb-a495-2f81fee72ea4 | note | 13.2 10 (max)
cee24c29-e7a4-5fe5-9a66-851bc47a9799 | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
4497dc5e-e119-536b-8d5a-d19a998b5f97 | note | Standard / Specification - GWS 3.2.2 & 3.4
107e7486-30e9-57fd-98af-3e0ab781e9e4 | note | Verifying Document - PSD, CR
c62d37bb-463d-5741-90af-459676b5e147 | note | Frequency - Material Tests every 1000m³ or change of source. Visual inspection every load, verifying document photos of material onsite, if visual appearance changes, additional testing will be required.
6e631094-f166-58c8-8aff-d3be86d61f18 | note | Activity - C
7aa1539d-3550-53e2-a337-8fe3b40077a4 | note | By - SE
6d7192d6-9061-5d38-a315-d4a8752b3fa5 | checkpoint | 4.01.03 - Filter Cloth
5faac559-bd2e-5ffe-9de8-0fa793fdfd22 | note | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings. (A14 Bidim or Equivalent)
ef37e272-12eb-522c-b65c-9c3bfe7ca901 | note | Standard / Specification - GWS 3.2.3
ec905cb2-509e-562c-b9e8-367497b2cff9 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
6945b2fb-ae9e-5f53-a594-a73692d450c5 | note | Frequency - Every Delievery to Site
1ba31876-8f62-5f34-9b5a-5e0d22302dde | note | Activity - C
e916f350-f892-5b53-8079-3d441131cdb2 | note | By - SE
34efbf28-65bc-5d1f-b72b-f1491def807a | checkpoint | 4.01.04 - Securing Pins
fa9c9129-d300-5f24-9ca8-9893d93bff4c | note | Acceptance / Conformance Criteria - Pins for securing the geotextile shall be of steel, a minimum of 5mm in diameter and atleast 400mm in length
80f8485c-74a0-56e3-8a13-fd03950209a5 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class,.
26fc6303-993b-580e-9e94-533265455d3f | note | Frequency - Every Delievery to Site
573b3469-103f-5d64-bc95-552af65d6f39 | note | Activity - C
e6e29053-4c45-59de-8849-751676e8cd38 | note | By - SE
f4713bb7-3aea-5dca-b516-69272c0b56ba | section | SECTION 5 – CONSTRUCTION ACTIVITY
113d79bf-1485-508d-814d-8c7c8c221530 | checkpoint | 5.01.01 - Filter Cloth Wrap Inspection
c23e65e9-fd71-5526-a2cc-396855c6c195 | note | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain. TNZ F/6, PWRBSS Geotechnical Specification - The geotextile shall be placed in the tench so as to conform loosely to the shape of the trench.
ab0d7d29-29d7-569c-8d74-719e431bc677 | note | • Cloth must fully encapsulate the aggregate.
3f79a82e-4f8f-5049-acfe-605be6782794 | note | • Geotextile longitudinal overlap to be minimum 300 mm (as indicated on drawing 3051 and required by NZTA F/6).
1483e652-e91f-5bb0-9e6b-f016afc483be | note | • Additional sheets to overlap by minimum 500 mm and anchored with securing pins (F/6 requirement).
451c6d88-06a4-5e60-9a96-571e4709de1b | note | • Verifying document, photos of trench prior to backfill, every line.
a5aca90d-3526-5f03-9d4b-ea2d31054500 | note | Standard / Specification - GWS 3.2.2
8458197e-6626-5df2-a733-745266f8ce63 | note | Verifying Document - Every line
5cf81d1e-986d-5a1c-8317-123ce26560ac | note | Frequency - Photos of trench prior to backfill
236f455f-64de-5e7e-aeaa-2af1a2729ade | note | Activity - HP
5a27d893-ed13-5da5-b7cc-d0e0405b49d1 | note | By - ENG
a2a25648-08b8-5ac9-b1a6-269e329744a0 | signoff | AUTHORITY HOLDPOINT
543c766a-67a1-5508-b12a-a4f69b9927f3 | checkpoint | 5.01.02 - Trench Backfill
baa6961f-370b-5765-aa80-fe233acc44a2 | note | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard of the material previously trenched through. Drainage aggregate to be placed in layers of 150mm or less. Only light compaction such as tamping with the back of an excavator bucket is to be applied.
0ad68759-e0df-5d72-b8ff-e757fada95ef | note | Standard / Specification - GWS 3.3
8cbf68e2-3da2-5f54-9b65-4c777d4168ce | note | Verifying Document - Site Record
75aec744-3603-5fcf-b939-cea07fe6f8d9 | note | Frequency - Each trench
ddefbe9b-d63f-531a-a74c-6802bd2597cc | note | Activity - I
9b433955-7419-58fe-a75a-09c05c43ba72 | note | By - SE
f7142f9b-2009-59fd-9453-67a19dd7865a | checkpoint | 5.01.03 - Drainage Outlets and Inspection Points
fb8bfbe6-7645-5a9f-b2e1-ff0313b2f573 | note | Acceptance / Conformance Criteria - At least one temporary flush point is required for each subsoil drainage system to enable flushing of the system once the earthworks are complete.
6bd24fb9-47b1-5e5d-b005-36dc0d7659b5 | note | Standard / Specification - GWS 3.6
174559c7-247b-5d06-9388-341126234e2a | note | Verifying Document - Site Records
e1b74fef-f4c2-5be7-a0c7-42401beaae55 | note | Frequency - Each Subsoil Line
b34148a7-1ae9-549d-9c79-bb90c1a412e9 | note | Activity - I
018d7d09-84a5-51e8-9e37-149a30a9100d | note | By - SE
fd83d42b-b8ea-5d41-8883-9e6215d99eea | checkpoint | 5.01.04 - Subsoil Flushing
48f356b9-0212-5f71-9f71-4cb92ac42b4e | note | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer.
38814faf-75f9-5fb4-845a-a5f421a3e6ef | note | Standard / Specification - GWS 3.6
a5169edf-c580-5bab-8d64-598c905b9298 | note | Verifying Document - Site Records
67309611-3ec8-584a-960b-61db5f9e0a97 | note | Frequency - On completion of earthworks
2b55c223-fcfd-5c53-bb4c-8b944a45ba1d | note | Activity - HP
de3999c4-d716-56eb-bf28-b60aa9f23c25 | note | By - ENG
efdabe6e-46f6-51c4-9707-34eb23acdd0d | signoff | AUTHORITY HOLDPOINT
65ee871c-3fae-5bef-8ed1-f015a6f0c4aa | checkpoint | 5.01.05 - Survey
a58656a8-b22c-5642-b872-27a204d0207f | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
46d921b2-6be6-5646-9bcb-1afc5ce57d70 | note | Standard / Specification - Downer
934afbf8-cde1-5b5c-8f1d-c645411bc0e1 | note | Verifying Document - Records
4022de56-c619-53f2-b7c7-8b85fa5c1c0c | note | Frequency - Post construction
e67df3ba-f8e0-581a-94df-028eac8b1908 | note | Activity - H
d29b5322-9ddd-542c-a502-b679078edb5e | note | By - SV
f999ffd9-5367-57d7-994f-8ff2006b1339 | checkpoint | 5.01.06 - Excavation
9b9ea235-3ac2-5591-acd5-5f26a4bb2cfc | note | Acceptance / Conformance Criteria - Trenches shall be cut in such manner as will ensure that the geotextile wrapped aggregate subsoil drains, and pipes if included, will be laid true to the depths, grades and lines shown on the drawings
fd79cc91-a199-5010-b0b2-fcd2dedcfea4 | note | Standard / Specification - Downer
14e0668a-eb5d-569d-b10b-c1bb1d06e6fe | note | Verifying Document - Records
ac662a63-510c-54d7-a958-b3497ae10237 | note | Frequency - Prior to laying filter cloth
3863aa9b-31d1-5020-92e0-eb4d3adf62f2 | note | Activity - I
a5ad0346-0cda-551d-9482-b30eef6a49e0 | note | By - SE
78b40005-4535-58a0-8f12-10ce7328ed62 | checkpoint | 5.01.07 - Bedding
6a804908-8011-5c5e-8a96-7cb5faf734cf | note | Acceptance / Conformance Criteria - TNZ F/5 - Bedding thickness shall be no less than 100mm
fc728791-6a66-56da-b5b1-f2ba3b2a6187 | note | Standard / Specification - Downer
8c7e7c09-452a-558f-b85d-318a98193232 | note | Verifying Document - Records
4010a9fc-e5fa-5a12-9b06-62aa2b2938d4 | note | Frequency - Prior to laying Novacoil
34c5d6d8-bae3-517c-a4ad-f770fcd10460 | note | Activity - I
8b1f267b-943d-5697-8660-baaeb969238b | note | By - SE
bc02362a-9ac4-5773-899f-55a42641ec6b | checkpoint | 5.01.08 - Joining Pipes
509f6ddd-e8e7-51a6-b823-697d653eae3d | note | Acceptance / Conformance Criteria - TNZ F/5 - Joining the pipe shall be done using a purpose made pullout resistant coupling in accordance with manufacturers recommendations
c00b7388-1649-5fd0-ace2-fc8bac8049b6 | note | Verifying Document - Copy of delivery dockets, photos of pipes onsite with tag showing class
c928046d-14eb-576e-9b83-1323a75989d1 | note | Frequency - Every join
443663f7-d6b2-544e-969f-6d6289bcd7e3 | note | Activity - I
6df4a7c6-4500-5925-9856-6fef7a82c5b7 | note | By - SE
cd33a7f8-9b6c-5422-93be-dcae98eaa460 | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
abaa7cc7-67ff-52ad-ae9f-e9176b336a01 | checkpoint | 6.01.01 - Construction Record Compilation
ab1b7353-5893-57a3-80bb-d6ff1ee576a6 | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
cad1b062-3767-5bfa-82fd-1152ad2d913b | note | Standard / Specification - Downer
f76eaa0f-f821-5f5e-9139-d0530719ea8a | note | Verifying Document - Records
f1b37311-80e2-54f9-909e-6ea161a5ea09 | note | Frequency - Post construction
a1f5e8c7-2e0c-5b65-8b40-cf0f2b87d5ff | note | Activity - H
cb9dd30f-398b-5a35-b2c6-33209e628017 | note | By - SE
f4876821-e136-54ca-95e8-27fd0f400f5d | checkpoint | 6.01.02 - Survey Records
49ab85d1-17d4-52ba-8ddd-a8233292baf4 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
fde8f60a-25f2-5460-9306-ff372f6c3cf0 | note | Standard / Specification - Downer
92033783-7b4d-5d01-ac3c-84c3456207e3 | note | Verifying Document - Records
998b1506-d623-584c-be5d-cd0820fa307d | note | Frequency - As-builts taken every 10m prior to backfill
1bd29fdc-651a-5e99-aee2-e2a3b722f923 | note | Activity - H
c4047b37-a420-5d21-afc2-67c0aec5fbfb | note | By - SV
a7ece1a0-6b4a-5d51-8813-156cc41a337a | checkpoint | 6.01.03 - Redline Drawings
a066bb4e-c82e-59af-8bba-6af8f6a7e272 | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.To show all subsoils, including temporary subsoils that become part of the permanent works, to show all outlet locations
f1e52e1d-0b8c-51a4-a9e5-d2600697c49d | note | Standard / Specification - Downer
f758af7c-1c61-5a10-8a0a-aa023ffe2a87 | note | Verifying Document - Redlines
1a359c63-0963-5b55-92b9-c4cc287cb5b9 | note | Frequency - Post construction
4ac95717-eebc-5c76-b0e3-4dc3b68120fa | note | Activity - H
ab194141-d0be-5408-80eb-315e3cfc0123 | note | By - PE
406cc900-58d1-549c-813d-cb4c75c9a2be | checkpoint | 6.01.05 - Photos
b662aadc-8edf-5b86-a58b-fb6b8f1e8dbf | note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
e7decdde-99c2-5795-9a38-8f781b821623 | note | Standard / Specification - Downer
951f2ec0-db06-537b-9c6b-b338465022cb | note | Verifying Document - Photo Records
7c139195-7df4-59ba-be0b-4073a6d97f85 | note | Frequency - Post construction
5512b932-9243-5b16-afb4-6359730aba0f | note | Activity - H
32d2feae-16da-5e27-91f7-9c338fecbe5b | note | By - SE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
13c265e7-4163-581f-9dd8-58e5ad7ac8d7 | checklist | ITP - Traffic Signals - Rev B | itp | ITP - Traffic Signals - Rev B
5628a8d4-88a1-5785-a410-312c9b25dfa1 | section | 1.1 - General
44167cb4-9cba-5322-8cf8-54cda693e177 | checkpoint | 1.1.1 - Drawings
1a6e2bb1-747c-58ff-8f65-242511a5d3e1 | note | Acceptance / Conformance Criteria - Prior to starting works, ensure that the construction drawings are both IFC and the Current Version.
dabe18f4-c625-50fa-9b19-8058d312fa5d | note | Standard / Specification - Downer
64e92cf0-7324-5c15-ba3b-c5ab5715c984 | note | Verifying Document - IFC Drawings
779bfdcd-6116-55e5-9081-81eaab9b7e3d | note | Frequency - Prior to work planning and start
3b80ea29-fe30-558a-a97b-6e1446f5d021 | note | Activity - M
a34f54c2-e4d0-546e-808e-6cb59268bd8f | note | By - PE
2067bbaf-6601-575d-ae07-d5e75f30bcd0 | checkpoint | 1.1.2 - Construction Pack (1)
636c29f1-6237-5088-9697-d65a2bec8b3a | note | Acceptance / Conformance Criteria - ITP to be submitted to the Engineer and approved prior to works beginning
9c8fa9be-4db8-5c2c-bc7c-40f136388ac1 | note | Standard / Specification - Downer
a01f6c13-5d40-5e1b-a7f8-bc6467959a75 | note | Verifying Document - In-Eight Document Approval/Acknowledgement
bfafaa96-f4e3-5a3a-b9ed-edabfc598172 | note | Frequency - Submit 10 days prior to commencement of works
baaafe56-bd6f-5cf7-b8e0-fe43ecf34f78 | note | Activity - H
be0f65f1-d87b-50b6-8182-0d7800660487 | note | By - PE
48feab1d-5452-54c1-a8ef-0f48a9e5fd9b | checkpoint | 1.1.2 - Construction Pack (2)
14ea70de-6733-5891-b959-6f6552d388d8 | note | Acceptance / Conformance Criteria - Methodology and associated documents to be prepared, reviewed and approved internally prior to work commencement.
23fe48dc-768b-5272-912b-af54827973d4 | note | Standard / Specification - Downer
4d473c96-0e45-5bc5-aa81-92d9b81da588 | note | Verifying Document - Construction Pack Sign Off
e38724a5-9fd2-5ba5-a0e4-8d22d58af085 | note | Frequency - Prior to Construction & after any major incident
4a1ca06a-ab84-51b7-880e-6e1d47eaba38 | note | Activity - M
eb3d56df-ebd9-5f80-97fb-e323803eded7 | note | By - PE
2ae3ce11-8852-5eee-9bc5-f1d025ad65df | checkpoint | 1.1.3 - Survey Set-out
aa347b44-1ebd-50a2-b200-a2c20d36e451 | note | Acceptance / Conformance Criteria - Ensure traffic signal pole, access chamber, and controller cabinet locations are set out per IFC drawings/data.
b35e099a-d971-59f2-93fb-4438e5f5af1d | note | Standard / Specification - Design Drawings
98c0cd01-8203-58c3-bc5a-5a221d8bbfbd | note | Verifying Document - ITP Sign Off
21bc99bd-299c-5c2a-b900-9e0be27c2c36 | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
3795dc87-6b2d-599b-8a05-ddb0c8eeb8e8 | note | Activity - M
c0841e63-e883-53f0-938a-fa0892d30222 | note | By - PE
05daab16-2bc0-576b-b090-566136a1e76c | checkpoint | 1.1.4 - Walk-over (1)
1832c688-97be-59a8-b044-a7b25c9d7c1d | note | Acceptance / Conformance Criteria - HCC Traffic Engineer, BBO Designer and MSQA rep to walk over and confirm pole locations.
1459bbe7-403d-505d-a96c-7a4b40f4aafd | note | – – – – – – – – – – – – – – –
40a04483-7436-5d4f-9c5a-74b4eff50a48 | note | HCC 1st Contact:
c9340165-e38f-54e6-9d02-ccd653c8944e | note | ○ Brandon Harley - Senior Traffic Signal Specialist - HCC City Transport
ec49a40c-3897-5eab-8107-1315ed3d40fb | note | ○ DDI: (07) 838 6638
d5e496b6-d560-5a79-b4c0-c10700271009 | note | ○ Mob: 0278086506
a184a501-f314-5f66-8bf1-e25f76011dd9 | note | ○ Email: Brandon.Harley@HCC.govt.nz
7e0e0362-ccf2-5f07-b6ec-985761eed9f0 | note | – – – – – – – – – – – – – – –
a4c700ec-3cde-5dd2-9fe7-18da7c6bdd07 | note | HCC Alt Contact:
3d4e65f7-eb58-5645-984e-8bbef2b841f6 | note | ○ Holly Blackley - Senior Transport Network Operator HCC City Transport
6ca8c43f-d9ca-5be4-9209-6412cb048b38 | note | ○ DDI: (07) 838 6817
c381824d-576d-5788-bc8f-6af1b4852166 | note | ○ Mob: 0278087593
98794dfc-71bb-535a-9cda-4b44f3b51a6a | note | ○ Email: Holly.Blackley@hcc.govt.nz
79887ac3-b09d-53cc-8bc5-a2e8b45a5a79 | note | – – – – – – – – – – – – – – –
b8ceb4fc-f372-554d-84da-ee0b9a35d1da | note | HCC 2nd Alt Contact:
37aeffee-2895-52ae-ba62-0f3210deb86a | note | ○ John Kinghorn - HCC City Transport
50e954b2-c4dd-5185-aa14-d28eca000faa | note | ○ Mobile:
211de02f-f763-50b1-be68-c46327a91b24 | note | ○ Email: John.Kinghorn@hcc.govt.nz
9202adf3-377a-5ec0-978e-3e8dfafe3fc8 | note | – – – – – – – – – – – – – – –
2aee2570-25b4-54b0-82a5-117485d7d4ee | note | BBO MSQA Contact:
ae119fd4-f500-559d-80bf-88e7eca3fb59 | note | ○ Emil Karlsson - Intermediate Site Engineer
d8fc4015-c4bc-5175-8f55-f865cdd411db | note | ○ Mobile: 0273371065
f503bb0b-95c6-5891-a132-3a0ecbbaaa5f | note | ○ Email: ekarlsson@bbo.co.nz
225e9737-66fa-5f08-9c9c-ff28a34dc46f | note | – – – – – – – – – – – – – – –
f6f3cf06-caef-5a28-955b-b8b213f5aa9e | note | BBO MSQA Alt Contact:
4c2a6f4d-39aa-5a63-9552-af47787b9835 | note | ○ Ryan Fergusson - Senior Site Engineer
c01c80b4-8e40-5532-8b34-92cea38e8707 | note | ○ Mobile: 0274060378
c0e51264-12f6-5287-a834-5a312abab6df | note | ○ Email: rfergusson@bbo.co.nz
5a99e27b-7dec-56f0-a68a-688226ceebc8 | note | – – – – – – – – – – – – – – –
d8b2b8eb-bea8-558c-ab28-0b54de4d650b | note | BBO MSQA 2nd Alt Contact:
7f10ff8c-1154-589c-a17d-2fa750f07249 | note | ○ Zion Nordstrom -
96d15509-fba5-54be-843f-81d4598ca211 | note | ○ Email: znordstrom@bbo.co.nz
c340016b-6fa6-57de-9fbd-8fb904be52fb | note | – – – – – – – – – – – – – – –
6a5c3c8b-6248-5406-96a5-6b45ad6b9d6b | note | BBO Designer:
7769d0a6-e192-5978-a5ec-f987bf7fbca3 | note | ○ TBC - MSQA to contact/bring with.
deefc935-cca1-511f-908f-b0e6db3f88dc | note | – – – – – – – – – – – – – – –
5fad894c-4d32-57bb-b45e-0de7225b5a27 | note | Standard / Specification - Design Drawings
0c344e80-a9b2-5aa2-bb60-0950fb6ef838 | note | Verifying Document - Written correspondence / Photographs
7d75a211-1758-5d5d-87c0-190805939914 | note | Frequency - Prior to construction
fc8b277f-31b6-5c74-bedd-1067a7d813f6 | note | Activity - H
9468f4eb-48e2-568a-9ff4-6ffd1a412acf | note | By - PE
5a196d41-a9c5-5d22-aa0f-3357472935a4 | checkpoint | 1.1.4 - Walk-over (2)
afab593b-8d3b-5cbd-b9e3-d59a6d2ae234 | note | Acceptance / Conformance Criteria - BBO/HCC written confirmation of any changes made to pole positions.
d1e9eae5-d663-5988-89f9-c3e195a9c481 | note | Standard / Specification - BBO Requirement
0460501b-3fd7-5351-88bc-3760b4a9b774 | note | Verifying Document - Written Correspondence (InEight preferred)
3defeba7-8e6e-5fa2-9e6a-d3b650b670b0 | note | Frequency - Post walkover, and prior to installation
57f82451-0f3d-5e75-a8e3-be348d120262 | note | Activity - H
bddd50c6-5a0e-502f-9ba0-c058b35fb5d7 | note | By - BBO / HCC / WTOC
c38fc1a4-700d-537c-87e7-8cbac3d52996 | checkpoint | 1.1.5 - Environmental Protection
49735070-ff18-5c44-800f-3f7456b0aec4 | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans. Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events.
39f5f564-db16-5ed3-9872-0619cc6d1c3b | note | Standard / Specification - Project ESCP Plans
2004eeaf-44c8-5df7-af7d-0bf7d2737198 | note | Verifying Document - ITP Sign Off
777f47d4-a5af-5da6-87cd-f2bdfa17081e | note | Frequency - Prior to Construction. Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events.
519aaf4c-c6cb-5432-81b2-2bdf71e40823 | note | Activity - M
d914bb68-8d93-50d3-a710-ab61be805d55 | note | By - PE
b9c7d6e1-8d3e-588b-a8d5-2d79f6ca8788 | checkpoint | 1.1.6 - Stakeholder
87ed676c-547e-5965-8e5d-e0de0ebe6371 | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works. Agree plans for maintaining access to properties during construction with landowners.
c384e116-be96-5400-afad-c61549035099 | note | Standard / Specification - Project Stakeholder Management Plan
ef5e934f-db4c-55a7-99d4-a4bffadaaac8 | note | Verifying Document - ITP Sign Off
042937cd-ae6c-5ced-a50f-c8cd2a063d94 | note | Frequency - Prior to Construction with continue updates throughout the works
262aad29-09c9-5202-b8b5-934c1eab70a2 | note | Activity - M
9e5e12d0-17f9-56ae-bd78-b09fd79af3ab | note | By - PE
3cd62815-f081-5349-9ed5-20983d6b050f | checkpoint | 1.1.7 - Permits
f5c29669-c2c6-5857-94b6-89390bc8dd30 | note | Acceptance / Conformance Criteria - Ground Disturbance Permit must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip.
33c003bb-a3cb-5392-a808-9f0554c2d3b3 | note | ○ Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. Doner Permit encompasses external provider permit requirements.
90b0cfa1-53b8-5281-b6b6-08dcfb0518f6 | note | ○ All known services must be clearly marked on site and briefed to the workforce .
cddf3d35-8802-5edb-af89-0ca4b040cc64 | note | Standard / Specification - Section 2.2.10 Project Specification
f0a7b0cb-f3f4-5e07-8dae-31f300dddf47 | note | Verifying Document - Ground Disturbance Permit, DN-ZH-FM043.1
f5c8fe38-a90d-5e75-9872-3d0272b52b21 | note | Frequency - Prior to Construction. Reviewed and Reissued weekly or when site conditions change.
1ccde223-d279-51ff-8add-1056d45bee31 | note | Activity - H
a8f2d274-5a2c-52b3-b20a-3b022f77d020 | note | By - PE
4247510b-2756-559a-b5d6-1e8797938e03 | section | 2.1 - General
bc2df17b-6846-5174-a63b-3c688365b69b | checkpoint | 2.1.1 - Pole Producer Statements
25d80bdb-c272-52ca-b144-dd03717e64bf | note | Acceptance / Conformance Criteria - PS1 certificate required for all pole types.
82ce7dd2-8928-54e3-97e8-a25f3b3311ed | note | Standard / Specification - Project Specification Apendix E 3.16
13231e0a-66e7-573d-93d5-ca5ba43b8e28 | note | Verifying Document - PS1 Certificates
c0e4cfed-37da-52d8-9185-8c5ffa72ea08 | note | Frequency - Prior to pole acquisition
a569f554-5998-54f1-b80c-46d8eaba402a | note | Activity - H
53f99a72-2921-5bc0-9e32-94f6986403a5 | note | By - PE
c7af668a-d767-5588-b1b7-ab801e61ed46 | checkpoint | 2.1.2 - Controller Cabinet
465bdb9f-250a-50f5-9616-e1c7ae31966c | note | Acceptance / Conformance Criteria - Unless otherwise specified, VC6 ELV controller (compatible with latest SCATS software) fitted with a generator socket matching existing HCC controller cabinet colours.
09971c60-27e0-5727-a093-33aa48b13689 | note | ○ Must be fitted with a sticker indicating the Site ID Number.
9671bed3-752d-5920-a8fe-60cbfe13c19b | note | Standard / Specification - Project Specification Apendix E 2.3.5/2.3.6/3.6
0ea75044-d262-5a62-bdce-92a36a5e88fd | note | Verifying Document - Nil - Visual Check
64d3e65d-21d8-53fa-b444-64a1d46d48cc | note | Frequency - Each controller/intersection
71e9b313-2aa9-5236-9a84-acee2a391a8c | note | Activity - M
3d339772-de9e-58c9-8d31-be29d9d4eaa2 | note | By - PE/TSL
00016068-8b38-5355-a388-270fa75f6a66 | checkpoint | 2.1.3 - Site ID Number
b295847f-acd3-5c08-bc76-5ec8a3ba683a | note | Acceptance / Conformance Criteria - HCC to provide Site ID number.
1ce2fa45-c26e-580c-88ae-34a6f93aa804 | note | Standard / Specification - Project Specification Apendix E 3.6
b5d196f8-9c49-5da5-ac9c-1521ed46d403 | note | Verifying Document - Written correspondence
b618943c-3c13-5c35-afaf-89296a0c1a10 | note | Frequency - Prior to commissioning
4b1b1a3c-3802-5a1d-9069-8817b2cb99ed | note | Activity - M
c6b09014-2f2d-5835-9036-0e44fa193c6f | note | By - PE / HCC/WTOC
f8648bd2-be98-5bbf-bc01-8e525d3d6ebc | checkpoint | 2.1.4 - CCTV camera
2365db74-a0ca-5cec-9c44-6b23eb5b0b56 | note | Acceptance / Conformance Criteria - HCC must approve of traffic monitoring camera which should meet requirements. Hardware is required to have a minimum 12 months warranty period.
af1ef695-496e-586e-9f67-71c557bc4e20 | note | ○ HCC preference is an Axis Q6075-E along with an Axis Q6010-E, using the Axis T91L61 pole mounts.
5d6bb55b-7444-576d-a37a-7abbad9ec41b | note | Standard / Specification - Project Specification Appendix E 3.19.1
cc32f8f7-8871-5676-9e2a-b211a5d47f2d | note | Verifying Document - Written correspondence
7f7b4a6f-1ef4-5723-b396-1b73afba1d8e | note | Frequency - Prior to material acquisition
43906920-16a2-50bf-b428-6185c4996fb3 | note | Activity - M
fd24c82d-58db-5bc8-b111-f89604ce7d8f | note | By - PE/TSL
46ee019e-81d0-5daa-b39f-2b1a6829d33e | checkpoint | 2.1.5 - Communications Connection
6af1668f-a0c8-5e28-89d1-b6e8dc520cc6 | note | Acceptance / Conformance Criteria - Engage HCC to engage Lightwire. Project team to coordinate with for on-site installation.
6962bfe9-bd91-5bd3-a83e-de4b2cda376e | note | Standard / Specification - Project Specification Apendix E 3.18
83cc83b2-c3b1-5b32-bdb3-23d0d1f8469f | note | Verifying Document - Written correspondence
002dfaa6-6265-521f-a3cf-95d59d1c9ee1 | note | Frequency - 3 months prior to connection
29bd6f9a-b4a5-525d-8e19-8e0b19a7bc0a | note | Activity - M
c4c6481a-ddd6-5ed9-bc5a-d7c341e6311b | note | By - PE
d71ff87d-8d0e-54c7-8ce4-cfe903ab1b46 | checkpoint | 2.1.6 - Electrical Connection
b935a22f-96b2-51c2-bc30-eda1979d4079 | note | Acceptance / Conformance Criteria - Apply for new commercial electrical connection via the WEL Networks website/login for each new signalised intersection (NC1 Form).
e55b3cad-dda8-5a4e-9e1d-2b9c9ed97c87 | note | ○ Traffic signals subontractor to confirm electrical requirements.
4ca96c70-00f6-547d-88b8-00cc564c57f2 | note | Standard / Specification - Project Specification Appendix E 3.3
9e9dcca0-f6d2-5267-ba00-c5c60d7e9b4d | note | Verifying Document - Approval document/NC1 Form with ICP number
342b291e-ef9e-5f9d-81f5-58fd5ce40a13 | note | Frequency - 3 months prior to connection
68e139cc-f2a3-5107-8efa-9d4456f050a5 | note | Activity - M
8ea2b6e9-b8f0-5008-90c7-5e5eb61232a9 | note | By - PE
136d1084-cbeb-54a8-a233-e1dc7536132d | section | 3.1 - Software
4348dfa1-fae1-5026-8bfa-f1fdc4cf04ca | checkpoint | 3.1.1 - Software/personality files and CIS
60cde22b-6c23-5a5c-813a-4b477a912301 | note | Acceptance / Conformance Criteria - HCC to provide to contractor (Downer or TSL).
6342b3e5-13e7-5c05-95dd-b1a60b94d0fc | note | Contact (s):
f082ddc5-a221-5e9c-a9aa-8cc1f2938baf | note | – – – – – – – – – – – – – – –
8543e704-77ce-57c4-b4e9-e73f7b102bd0 | note | John Kinghorn - HCC City Transport
55f06c78-0723-519e-ae13-4d216022b32f | note | ○ Mobile:
47534d1b-9447-50d7-8e89-5346278e4a43 | note | ○ Email: John.Kinghorn@hcc.govt.nz
21c0a32c-c675-5dac-848b-83501115b66b | note | – – – – – – – – – – – – – – –
c9e65987-d52a-518b-ba5b-9a68a4715dce | note | Brandon Harley - Senior Traffic Signal Specialist - HCC City Transport
bba9017a-b2f6-5ed5-bc10-a9f4ea62acb0 | note | ○ DDI: (07) 838 6638
8182b054-1fb8-592a-9258-97a04bfe71a6 | note | ○ Mob: 0278086506
e54ee533-8490-585a-988f-535c6f0b2342 | note | ○ Email: Brandon.Harley@HCC.govt.nz
e91ea35b-d1b0-5feb-a2b0-9f09b102491c | note | – – – – – – – – – – – – – – –
5bb1260a-e7c2-5c75-86e3-c58e7d01b120 | note | Standard / Specification - Project Specification Appendix E 3.15.3
51f28f7e-1ceb-5665-abf7-6de2d4db27e6 | note | Verifying Document - In-Eight Documents/Mail
ed2cfde4-2677-596a-8c0a-e3ae7e7e0823 | note | Frequency - Requested at least 6 weeks prior to bench testing date.
154b9348-11db-54de-a8bf-385fd0859f2a | note | Activity - H
dda461fc-ee43-5414-baca-e7f4550988f2 | note | By - HCC / WTOC
93abe9cf-42a8-5817-9b96-3b93f4c6b633 | checkpoint | 3.1.2 - Bench Test
d8b7e7a4-ac89-54c5-9c42-15994d362acb | note | Acceptance / Conformance Criteria - Traffic signals contractor to bench test files.
1d00a791-144c-566e-b2e3-45b0c6259585 | note | Standard / Specification - NZTA P43 3.15.4
0578a9b8-7778-52b1-a75c-6568a171f1aa | note | Verifying Document - PDF Document
23395378-ae37-5755-92a6-48166eb4a467 | note | Frequency - Once per intersection, at least 1 week prior to comissioning
55eb0296-c074-55db-a092-4a8802037d05 | note | Activity - H
51ee8e6b-dd34-562f-a3ff-3f23212d7b8c | note | By - PE / TSL
d08ab60b-72a2-51cd-abfd-b39160c4e071 | section | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations
881052f0-3fb2-55f0-ac04-f4d6379f3b36 | checkpoint | 3.2.1 - Soil Bearing Strength
047416b0-54a6-58a8-9b35-c7d290bbd7d1 | note | Acceptance / Conformance Criteria - Report results. Check this meets poles deisgn (i.e. >= 50kPa).
88dded6f-381f-5c97-8616-a058211d5a83 | note | Standard / Specification - Drawings/PS1/NZTA P43 2.5.1.3
43655bbd-8b87-5a26-b7dc-2809b804c86d | note | Verifying Document - Shear Vane
1c28fb49-10a1-5f68-bdf3-27c184d11805 | note | Frequency - One pole per intersection corner (i.e. north-west, north-east etc)
fb54a97f-5a15-54a5-97ea-9768fb69c336 | note | Activity - M
5cc5f5c6-401c-539b-a50e-e67f87b86892 | note | By - PE / TSL
095ec1c7-f301-5b43-b886-70e999ebb12a | checkpoint | 3.2.2 - Pole Base Photograph
58f3023b-21c6-531f-a832-9c06785c5ec2 | note | Acceptance / Conformance Criteria - Photographic evidence of each pole base to be submitted as part of PS3
6367cabf-8ed3-5d8f-b2c2-4b7f64356e6c | note | Standard / Specification - Project Specification Appendix E 3.16
c0698672-7bab-5e49-a950-7961ed3471f8 | note | Verifying Document - Photographs
8b3bae35-b336-5692-bdb9-5850f40115c9 | note | Frequency - Each pole base prior to foundation pour.
49a3e8ef-a08b-54dd-9f1e-ed513875c8d3 | note | Activity - M
9454f899-82fb-56f7-ac1a-7a47cbb5a7da | note | By - TSL
0d781ce9-a04c-52b1-a5aa-063707433665 | checkpoint | 3.2.5 - Identification Numbers (1)
6d0f5826-40b3-56e1-a5b2-11f39ff7d827 | note | Acceptance / Conformance Criteria - Ensure poles are fitted with/displaying the correct number and match the CIS sheets (pole numbers match program and diagram numbers).
a29d017d-61d7-513e-b5a8-e7f2bb656a65 | note | Verifying Document - Nil - Visual Check
58b5e79c-bc8c-58fa-818c-64b1d33a2023 | note | Frequency - Each pole
9c451946-5a72-56e3-b7b2-abb1e919889b | note | Activity - M
baa14c47-4889-5191-906b-0b218feda3ce | note | By - PE
0f4ddce2-b3cd-53c5-93f4-69fc09db56cf | checkpoint | 3.2.5 - Identification Numbers (2)
0cc4b449-7ef9-52c5-8652-d03c7f6777f5 | note | Acceptance / Conformance Criteria - Controller cabinet fitted with Site ID Number sticker.
4fcf2ca3-1367-5071-9ff9-868a8ee714e7 | note | Standard / Specification - Project Specification Apendix E 3.6
6756bf93-ef86-5078-9122-e874a74bfcbf | note | Verifying Document - Nil - Visual Check
6ce36705-9e67-5d65-bff5-361528dfbedf | note | Frequency - Each controller cabinet/intersection
42a6fd31-6a20-5950-b91b-5ab42301b06d | note | Activity - M
0fa6aa6c-68bd-5bc4-8e31-9c16f0450e34 | note | By - PE
ecb34fa4-340c-5329-b662-29bacaa88633 | checkpoint | 3.2.6 - Mow Strip / Concrete Surrounds (1)
232d240e-5671-5ed6-a2b0-302ca86e85b7 | note | Acceptance / Conformance Criteria - Access chambers installed in the berm surrounded by 300mm wide concrete apron to 100mm deep. 25MPa 28-day compressive strength concrete.
f944099f-582d-5e36-a97c-763d00be0b1d | note | Standard / Specification - NZTA P43 4.4.2
cc767167-a126-59ef-b153-980e30bee1c1 | note | Verifying Document - Nil - Visual Check
e0ea8692-d4ca-5644-b352-c2056964a936 | note | Frequency - Each access chamber in the berm
1814b540-e146-59bd-b887-e37972d9220a | note | Activity - M
949cdb71-8ac2-58cd-9788-1d20b0116dbe | note | By - PE / TSL
8f790773-6c27-5c59-bbfc-4e17207d7f64 | checkpoint | 3.2.6 - Mow Strip / Concrete Surrounds (2)
ebee9d24-a526-5c3f-927a-056b812cf2e6 | note | Acceptance / Conformance Criteria - KSJB to have 150mm wide concrete surround to a depth of 150mm.
3758fb48-cf89-5c34-96ae-df1f3fa6d5a0 | note | Standard / Specification - NZTA P43 4.7
a85b7a70-77ad-5ece-9013-fb27e24b372e | note | Verifying Document - Nil - Visual Check
24b8a540-07fb-5888-97d5-131ae361f2cd | note | Frequency - Each KSJB in the berm
8938d508-2bac-5413-b699-6114a5d5f346 | note | Activity - M
77277e01-16ae-5e18-93f3-b1bd7beb1a76 | note | By - PE
66eb6a23-6c88-51a6-941a-360ed45371f8 | checkpoint | 3.2.6 - Mow Strip / Concrete Surrounds (3)
da701216-7ac8-5d5a-a478-2732b2470707 | note | Acceptance / Conformance Criteria - Controller cabinet to be surrounded by 300mm wide concrete apron around the base of the controller, widened to 900mm on the side adjacent to the door. 100mm thick, with slight fall away from conroller.
1d860cce-81b7-5a65-bdb7-788a30d57bbd | note | Standard / Specification - NZTA P43 3.6
2bf13bfa-98de-5453-b7bc-c5da6df3e0f9 | note | Verifying Document - Nil - Visual Check
efd3fe0a-0201-5301-90b3-d5a55b3e3ef3 | note | Frequency - Each controller cabinet
c68904bc-b956-5d41-a345-5a0d48dd3d20 | note | Activity - M
e4cb13f9-0391-5a88-a30e-e10f370a7e85 | note | By - PE
ec78b07b-483c-5fac-abb9-8b4be56b7fd8 | section | 3.3 - Cabling and Electrical Testing
6b4cac9d-d49d-504b-b4c1-a41e4a469720 | checkpoint | 3.3.1 - Loop Cutting (1)
1fc24752-ab2e-53ee-9538-d5795532dda4 | note | Acceptance / Conformance Criteria - Rubberised bitument adhesive sealant applied to all saw cuts in the roadway
62215710-07d8-5e5b-8482-1f579dccb943 | note | Standard / Specification - Project Specification Appendix E 3.11
485cffd0-63ee-5286-bab1-2512fcb71f05 | note | Verifying Document - Nil - Visual Check
def8ee92-d946-512b-ae01-81ca8c78166c | note | Frequency - All saw cuts
e2cbac1d-d9c7-5cea-9939-aa8e65951079 | note | Activity - M
a1cf6de2-ec56-58da-bd05-07d8baf20a0b | note | By - PE
ce975d04-5ca3-5aee-a16f-e8541532f33c | checkpoint | 3.3.1 - Loop Cutting (2)
f04a7442-47ee-54fe-a232-1e16949844ef | note | Acceptance / Conformance Criteria - Saw cuts made through kerb and channel to be sealed with epoxy resin motar.
4c9bb10d-82ee-5943-97e7-1a27787104aa | note | Standard / Specification - Project Specification Appendix E 4.7
e45a48bc-06cb-5416-b35b-0ce64ef751c7 | note | Verifying Document - Nil - Visual Check
fe0d18ea-a423-5dda-b0dc-5e7174766fcf | note | Frequency - All saw cuts
ca37ddbb-c429-51e0-a71e-f639024d5abd | note | Activity - M
6b2e05d3-d61c-592e-957e-8753220698c3 | note | By - PE
be980044-080b-5541-9c86-242339e8e835 | checkpoint | 3.3.2 - Electrical Certification (COC)/ Record of Inspection (ROI)
2211f947-11d8-56a7-8d00-7196abb09c7e | note | Acceptance / Conformance Criteria - Completed and signed certificate of electrical compliance.
1a2ac56d-141d-5682-8b67-47c1836ae0a9 | note | Standard / Specification - NZTA P43 3.16
f02677b3-dc72-51f8-8e9d-edccf4ce0a99 | note | Verifying Document - Certificate
8df7d6f7-a6d4-55b8-b1f9-b1e80d5f1341 | note | Frequency - 1 per intersection prior to commissioning.
6a334c9b-5b91-5ab5-88be-383a65b1f7e7 | note | Activity - H
933cf4a3-4ec6-5219-909b-7bb73394bbf1 | note | By - TSL
65345dc7-c186-58a7-9e67-f5e77764ceeb | section | 3.4 - Site Acceptance and Commissioning
ac150dd0-3ea4-51bb-8514-12a889adf94c | checkpoint | 3.4.1 - SCATS Connection (1)
0ee420ac-31e8-513c-9903-714658d779d0 | note | Acceptance / Conformance Criteria - Signals contractor to notify City Transportation Unit (CTU) Operations Room at least 1 week before SCATS commnications will be available from the controller.
c3b871a2-40e3-592b-9e7f-b38d5de736f3 | note | Standard / Specification - Project Specification Appendix E 3.15.4
7d10387d-44a0-56dc-aeb4-80fd2a25ba67 | note | Verifying Document - Written correspondence
64d19790-d57f-53f5-9a56-522b259836cf | note | Frequency - 1 week prior to SCATS communication being available from controller
fb357ba3-c899-5d5a-a45c-807791bea248 | note | Activity - M
ffc8c6e4-d183-5765-846c-44546ff22dea | note | By - PE / TSL
a38b3ca2-c3a0-5996-bfd1-5d8181416334 | checkpoint | 3.4.1 - SCATS Connection (2)
8acbed91-702d-50ac-a156-2c47d4139635 | note | Acceptance / Conformance Criteria - SCATS comminication achieved for a minimum of 48hours prior to comissioning.
6133450c-a625-57cb-b2fa-78d892cdf7c8 | note | Standard / Specification - Project Specification Appendix E 3.15.4
3574a399-41e8-5e79-9089-bf99a7f1071a | note | Verifying Document - Written correspondence
9a46cd34-b991-5fea-9767-ee17f74cccdb | note | Frequency - Min 48hrs prior to comissioning
3ab532b2-fa6f-5bae-a9d9-1a49665e25d4 | note | Activity - M
c34ea619-3344-5de7-ac3d-3639d893b701 | note | By - PE / HCC / TSL
8fed7548-38f8-50d2-8e17-6e4524903f80 | checkpoint | 3.4.2 - Documents
e890420e-9e7e-5a8a-8f1a-6b361132f646 | note | Acceptance / Conformance Criteria - Cable termination chart, CIS and logbook placed in document pocket inside controller cabinet.
7e6dbb80-8205-53bc-a0e9-51264719cfd1 | note | Standard / Specification - NZTA P43 3.16
fe20d126-549e-509b-9aae-61d194fa264e | note | Verifying Document - Nil - Visual Check
1ed93ae0-5283-50af-aeee-69e5daa7135b | note | Frequency - Within 2 weeks of commissioning
643e9599-57b6-5c37-a93c-35e760802400 | note | Activity - H
fb4a655e-8766-5e2d-8e72-e8290d2c148c | note | By - PE
6b060044-4b79-5185-915e-c0e2e668591a | checkpoint | 3.4.3 - Approval to Commission
6e353e84-4c25-54a8-b595-a71e3835bc71 | note | Acceptance / Conformance Criteria - RCA traffic signals representative (City Transportation) approval to switch on.
fea3e389-1286-596a-aeb0-09b7e76d04ce | note | Standard / Specification - Project Specification Appendix E 3.15.4
664aa9e4-895f-5968-9215-bb4778fb8c01 | note | Verifying Document - Written correspondence
7221bfba-f0a6-5bc9-920a-f57024bbfc14 | note | Frequency - Once per intersection
dd4b687c-67d1-542e-acd4-6c67c15c9af1 | note | Activity - H
f1efa812-174b-5d56-9a41-4d7e1e37b9f2 | note | By - PE
34a61f87-1a77-58af-8d05-3fd5563c6d1a | checkpoint | 3.4.4 - Site Acceptance Chart
ebcaad82-2973-536c-a931-0939134b9bff | note | Acceptance / Conformance Criteria - Site Acceptance Test Chart to be filled out and signed.
9c10c38f-b4ff-50ba-bd35-ee9915290da9 | note | Standard / Specification - Project Specification E 3.15.4
7ed6e949-2e70-5e96-8934-c76ca154c47e | note | Verifying Document - SAT Form
184617c7-5954-5eef-8c83-849cb6d97720 | note | Frequency - Once per intersection
755906db-2d73-546a-996a-c4440f6a7f64 | note | Activity - H
180b763b-fc04-5805-8883-26c49aae1e29 | note | By - TSL
af1d387a-e24f-53f3-98c0-b94e4af93490 | section | 4.1 - General
5ca114d7-d2c7-5141-afc8-99e0ca02cc3a | checkpoint | 4.1.1 - Producer Statements (1)
3780b149-2d4f-5eab-b002-9445521762f2 | note | Acceptance / Conformance Criteria - PS1 Design Producer Statement from Chartered Professional Engineer
73efe4a7-377c-5b90-9235-45ba20eb933b | note | Standard / Specification - Project Specification Appendix E 3.16
4005ac66-5fa0-5ea4-b869-06f1c2fe8d6a | note | Verifying Document - Producer Statement 1
7af5f26d-afa3-50d0-a821-821a69b5b35d | note | Frequency - Each Pole Type
3134b51f-a8b7-5027-8ee3-5fa2ea75674d | note | Activity - H
8bbbe2c9-72a1-5d77-9f02-d9d3cacc6194 | checkpoint | 4.1.1 - Producer Statements (2)
fdf9e640-057b-5829-9b84-9a9fc1671471 | note | Acceptance / Conformance Criteria - PS3 Certificate to be accompanied by photographic evidence of each pole (see requirement above).
c5249b0d-255e-5dbc-a792-a2534f88289c | note | Standard / Specification - Project Specification Appendix E 3.16
d88e0f00-a531-5a6b-ad27-9cf58e6c6907 | note | Verifying Document - Producer Statement 3
9378fbf1-178f-5984-9917-b44e38bb5169 | note | Frequency - Each Pole Post-Installation
1ca31bc1-1a63-556f-be68-9dc95f73e4ba | note | Activity - H
1172c052-be31-524d-8658-4999d4601ccc | checkpoint | 4.1.2 - Site Handover/Acceptance
d6f7e099-0f46-5f78-85fd-528252858142 | note | Acceptance / Conformance Criteria - Approval from Hamilton City Council and the signals maintenance contractor.
d10ecd76-9659-513d-963b-14e34984fa2b | note | Standard / Specification - Project Specification Appendix E 2.2.2
f0eea7f1-e753-5214-9732-c854bb553359 | note | Verifying Document - Written Correspondence
954403f4-97dc-5dd2-bd6a-92468c6aacda | note | Frequency - Post Signal Works Completion
734dee76-682b-5d17-8315-a242006e3ca4 | note | Activity - H
ee0a186a-9182-58fb-a973-a5e2ef0f19a7 | checkpoint | 4.1.3 - Survey Redline Drawings
9ff17772-543e-560c-856e-e2cc3ba29db2 | note | Acceptance / Conformance Criteria - Asbuilts reviewed and submitted showing final location of all poles, access chambers, KSJB, loops and cabinets.
a480559d-f93a-54ae-b37e-c7d89fe072f3 | note | Standard / Specification - Project Specification
c5a4d5a0-3ebc-5720-bb70-d7c1f5b452e3 | note | Verifying Document - Survey Data, As Built Drawings, Photographs, Red Pen As-Builts including Undercuts
90da3462-b053-52b8-a34c-6c263f765ce4 | note | Frequency - Post-installation
c5acc9be-4937-55f9-bc35-01e685937157 | note | Activity - H
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
298455f3-9c6f-5b3c-af04-bb009eb07f91 | checklist | ITP - Utility Trench | itp | ITP - Utility Trench
9dbf9507-d5c1-5f76-b0e9-632a875b7d7c | section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
40e50969-1ceb-5dd9-9b3c-01f7c53f618e | checkpoint | 1.1 - Extent of Line Setout
1a28f932-4256-53f4-8e4a-e589e1a2a356 | note | Acceptance / Conformance Criteria - Ensure line and level of Utility Trench has been marked out and agreed with Engineer in accordance with Utility drawings Identify any clashes before construction.
e9c10589-2e58-525d-9972-a8bb57e1b6ea | note | Standard / Specification - Design Drawings
6b76dc85-10ae-5e6b-8376-49e4b134b896 | note | Verifying Document - ITP Sign Off
f9922ebe-f7cb-5b0a-a655-f0e94ea3e5ca | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
2e5d0e79-8bb5-5576-9395-510ec96d4620 | note | Activity - M
5de18377-15ae-5482-9288-87089e16f418 | note | By - PE
d974f8f5-6fc2-53e5-bb0c-a5788cd00a86 | checkpoint | 1.2 - Construction Drawings- Berm
c9c9b3e2-adae-50ec-9477-5b9c379c72a0 | note | Acceptance / Conformance Criteria - Provide full construction drawings as agreed upon by the Service Providers including agreed Cross Sections
71ffa5a0-dba5-5cd6-b388-7cab3c17f796 | note | Verifying Document - Drawings
2733522c-3170-5982-8f04-83454cbef071 | note | Frequency - Prior to Construction
37adc687-791d-597c-82ea-c0f3e6523730 | note | Activity - HP
7b80468f-df7b-5bd0-84ed-190a83d4d579 | note | By - ENG
3b120ea3-c1aa-55eb-a5c8-3bd1aaf20868 | signoff | AUTHORITY HOLDPOINT
3830a3d7-d29c-5702-b913-96193a97db80 | checkpoint | 1.3 - Construction Drawings-Road Crossings
6ef1f90b-a514-5f74-b178-c3ca3c76b3e8 | note | Acceptance / Conformance Criteria - Provide agreed upon Cross Sections from Utility Providers for any road crossings
38a47eff-b723-55d6-88ac-a60f6c7ce80b | note | Verifying Document - Drawings
b36b68dd-ccb3-53ac-8fb5-241006f9ff6c | note | Frequency - Prior to Construction
0ddb8441-3937-525c-b62d-749ce21e391e | note | Activity - HP
cf0b9879-0582-5b3a-8fce-3437eb240640 | note | By - ENG
fc7bceba-e571-5ccf-9a9d-3c15e5c485bb | signoff | AUTHORITY HOLDPOINT
a37db132-6f29-5d4b-87fb-c7088dcbfcb7 | checkpoint | 1.4 - Environmental Protection
9e0ab3fc-be7c-5604-b9aa-51ea43847668 | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
239d1081-6c8f-595d-9a88-e7f1a434afec | note | Standard / Specification - Project ESCP Plans
cf6fdba6-58e7-5d42-b38f-fb7593b3d6e5 | note | Verifying Document - ITP Sign Off
b1795489-b8ec-5af5-b5ef-1a9532f6c47e | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
d102b365-417e-5f88-b2d1-aaec33477065 | note | Activity - M
a19d99c5-e611-5073-bbb5-e1886d74f59e | note | By - PE
1d33401d-a6f8-579f-8b2f-a0e1365abab4 | checkpoint | 1.5 - Stakeholder
14360796-9a7b-536b-9f8d-f74126ac8feb | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
fe08ae50-bd03-5b8b-af4c-0ec7f7634f81 | note | Standard / Specification - Project Stakeholder Management Plan
b1c20ff8-3e6c-5bb7-a4f5-3e1c100216d1 | note | Verifying Document - ITP Sign Off
ab6e4055-f100-52ba-b36a-6b93a14d7954 | note | Frequency - Prior to Construction with continue updates throughout the works
e6bf2580-1570-5fc8-980e-e6aa25c9ee25 | note | Activity - M
a86c2579-b1f2-5f9c-9bcb-d8f8eaae3ae8 | note | By - PE
99be0b5d-0192-5056-854d-713dca7bbecb | checkpoint | 1.6 - Permits
02ae71fd-9fe0-5153-96f8-7431f8b30552 | note | Acceptance / Conformance Criteria - Permit to Dig must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip. Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. All known services must be clearly marked on site and briefed to the workforce .
419aadfe-9db5-5cad-ab0f-e9876ebf69cc | note | Standard / Specification - Section 2.2.10 Project Specification
3765baed-457c-5b64-bc01-9488eff7b0d3 | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
c5994fec-79d5-5e19-a835-51e8ca8c6f6a | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
78f32b25-1076-51a0-bc10-c820e2403e07 | note | Activity - H
7bc7f061-bae2-50e5-8dd1-9fa1f9851eeb | note | By - PE
b2505ca3-943c-534d-afb7-23e310ef1e65 | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
254bb354-ecf8-5723-a187-916bfd4e2c3b | checkpoint | 2.1 - Duct Bedding
444cf632-a93a-5dcf-8297-b82fca3ec4eb | note | Acceptance / Conformance Criteria - Confirmation from service providers on bedding and shading material required
0a3b0101-aa8a-5c69-b05a-20ad1f3e289a | note | Standard / Specification - Section 10 PWRBSS Project Specification Sand from Source Specified by WEL
0a0c45ef-ce6f-5ab7-ac13-38b2bd1fbf36 | note | Verifying Document - Delivery Dockets
eca7e6d9-795a-56ac-a05d-de5961e268bb | note | Frequency - Every Delivery
52e259fc-94fa-5ac2-9e2c-b3df15087154 | note | Activity - S
ad6978ac-eb7d-5a81-9185-88b267694f46 | note | By - PE
057bd260-40bb-5fbd-b73e-b36b95ccbfa4 | checkpoint | 2.2 - Trench Backfill
07df4993-1ad4-5481-be9e-9f3c64467672 | note | Acceptance / Conformance Criteria - Native soil backfill must have no stones or "hard clods" of cohesive material. Max clod or particle size to be 7mm. Trench Backfill material in carriageway to be Pit Sand
9a606214-ee38-5637-808b-5b1d731ea7f1 | note | Standard / Specification - Section 10 PWRBSS Project Specification Utility Company Requirements
f299d433-7a82-57f0-9b2b-4a356b15b9d2 | note | Verifying Document - Visual Inspection/Pictures PSD and MDD
b9de21f8-0904-58d5-bdd1-49c59ed61c4b | note | Frequency - Ongoing
57b53d57-cfee-5dc1-bf7f-e32d3bdac779 | note | Activity - S
032bb84e-ae4f-5361-bcdd-2c3971ef799d | note | By - PE
29236671-2fee-5e65-a68d-5cc74cf30d0c | checkpoint | 2.3 - Duct / Pipe Material
7d4133ae-1b6d-5113-bba3-97d11bb91482 | note | Acceptance / Conformance Criteria - Obtain duct / pipe from Utility Provider Confirmation required from service providers on ducting size
e47d48e4-9a8f-51e4-9cf7-8232d79733a3 | note | Standard / Specification - Section 10 PWRBSS Project Specification Utility Company Requirements
392046a7-d9f1-57a5-9b4e-c6e930e9cf30 | note | Verifying Document - Delivery Dockets Email
b27fdf1a-8714-5c7e-9bae-2d1a3bb916ee | note | Frequency - Every Delivery
6e1de9e2-2fae-50c3-91eb-57f984033568 | note | Activity - S
750b4f6a-4226-5ce1-9da0-1ae038b7496f | note | By - PE
add8efc4-f0b3-51fa-9598-32af4435ede2 | checkpoint | 2.4 - Warning Tape & Mag Slabs
9c3d76f2-41f7-503f-a557-e5bbadbf185b | note | Acceptance / Conformance Criteria - Obtain warning tape and mag slabs from Utility Provider Confirmation required from service providers if mag slab and warning tape required.
b6618b37-a549-587e-909a-3b5acb2a9649 | note | Standard / Specification - Section 10 PWRBSS Project Specification Utility Company Requirements
e05cabbd-4118-5782-b951-d4bf9879d825 | note | Verifying Document - Delivery Dockets Email
51cbeb2d-7cb7-5b8b-9128-aceabf5907bf | note | Frequency - Every Delivery
89bc29c9-bdaa-5beb-ac6a-0ce5218ed3b4 | note | Activity - S
bffc547a-b7af-5006-b596-c230ed7ea3ad | note | By - PE
9cc06a11-17ee-5f49-ac50-31c36fc22fcb | section | SECTION 3 – CONSTRUCTION ACTIVITY
82621b46-3e0a-54f5-8fc3-d5fb2b4cb3ef | checkpoint | 3.1 - Excavate trench
ca5b4c07-7b26-58ec-ba8e-30c9c2f74bdc | note | Acceptance / Conformance Criteria - Excavate trench and stockpile excavation arisings. Visual inspection of excavation arisings to identify presence of stones / hard clods. Inspection of formation to identify any soft spots.
a6c1f659-2ed7-5ca7-8ada-98099357c35c | note | Standard / Specification - Section 10 PWRBSS Project Specification
030fc257-bb20-5c49-9ba8-25b478c38139 | note | Verifying Document - Visual Inspection
54c76830-99fb-5518-a371-d7df97efb890 | note | Frequency - Ongoing
13c504a9-9d2e-59df-a4fe-9fd8e57becc8 | note | Activity - S
24b694bf-079e-5b4b-aade-5cb8aabf0dd2 | note | By - PE
3b1267e2-dffe-5add-b50b-4dbe671cabcd | checkpoint | 3.2 - Install duct bedding
bf7a3739-d868-5588-adfc-63ab2de93d47 | note | Acceptance / Conformance Criteria - Place sand as per WEL detail
4cd8021f-35cc-5a06-8c06-546e4132a1c8 | note | Standard / Specification - Section 10 PWRBSS Project Specification
5d1f8269-de16-50bb-93ad-32496650b741 | note | Verifying Document - Visual Inspection/Pictures
b6b588eb-42b6-5e62-bb33-90827527af43 | note | Frequency - Ongoing
f377a399-92d5-51f0-8583-1b5c7d72033a | note | Activity - S
e861d23c-8062-5427-9707-75cd0a76d49c | note | By - PE
d274c796-c9a6-5cb2-ab65-32b2768101ba | checkpoint | 3.3 - Install Ducts
4dbc32a3-b84a-57dc-98da-5b40b9cdc1ed | note | Acceptance / Conformance Criteria - Place ducts to line and level shown on design drawings and in accordance with utility provider requirements
94ce0b08-8205-5e0b-9ca0-2c97f41808fd | note | Standard / Specification - Section 10 PWRBSS Project Specification
0c88a5ba-a134-5101-be66-0dc602cf86c9 | note | Verifying Document - Visual Inspection/Pictures
f9e36f3c-7cda-58c6-b1eb-647e8e775764 | note | Frequency - Ongoing
0e569a63-4871-5955-ac8a-8f07b69bbdca | note | Activity - S
34c4bae7-851e-5b52-b133-97f0373851af | note | By - PE
1becbeaa-46d9-5aa4-8937-7bf0d6434276 | checkpoint | 3.4 - Install Draw Cord
0a01dc1d-d4f5-5798-a683-21f160cd883b | note | Acceptance / Conformance Criteria - Install draw-cord to all service ducts
f175bd4a-e569-5d92-9fc3-a56848ca48a2 | note | Standard / Specification - Section 10 PWRBSS Project Specification
bf41177c-6e86-51de-a70c-c6eabc8f7ab2 | note | Verifying Document - Visual Inspection
c4efeddb-335e-5891-8d8b-5df5424422bb | note | Frequency - Ongoing
10573828-9cb6-5e52-bb4a-18e93abfa6c4 | note | Activity - S
70b47ba3-6fd1-5144-ac39-447299d2bd92 | note | By - PE
caebe6c1-f96a-5587-93f5-e5bf2f3422b7 | checkpoint | 3.5 - Install End Caps
57fa27a2-c6e1-5cbb-a097-a1b24f08367a | note | Acceptance / Conformance Criteria - Install end caps to all service ducts
414df3a8-84ae-55f3-a017-17db6429d45e | note | Standard / Specification - Section 10 PWRBSS Project Specification
a5269469-2d07-5dc2-b6d6-15cfcc39f1e9 | note | Verifying Document - Visual Inspection/Pictures
73ed089c-7649-5cf9-961d-b714e30a0b87 | note | Frequency - Ongoing
0520f1ba-2c93-5c96-90f4-c80216482e42 | note | Activity - S
8a792c63-b312-51df-98e4-7e2a75391244 | note | By - PE
85c82894-a77a-57bf-a5fe-5f9e9b9328f5 | checkpoint | 3.6 - Backfill
bbb881e7-094f-52af-b460-4c169d175b2d | note | Acceptance / Conformance Criteria - Backfill and compact with selected native soils (no stones or hard clods, max. size for all soil particles and clods is 7mm) Photos of Ducts prior to backfill
43072781-cf7a-5067-9ddc-f430181c43a6 | note | Standard / Specification - Section 10 PWRBSS Project Specification
e4f7f5f6-b92b-598c-adde-b645857dd598 | note | Verifying Document - Visual Inspection/Pictures
05313ce5-ff97-53c7-b1db-5149e5ba6337 | note | Frequency - Ongoing
4c778149-df86-58c7-8eb9-b90d6215b157 | note | Activity - S
7ef44f1e-7e46-58ed-9701-946cc3f3d646 | note | By - PE
85669d4b-4ff6-51e8-bc42-d69bf3073481 | checkpoint | 3.7 - Install Warning Tape & Mag Slabs
65648a43-d930-5e62-88da-60fdb6a41ae2 | note | Acceptance / Conformance Criteria - Install warning tapes and mag slabs to all service ducts Photos of Warning tape and Mag slabs prior to backfill
392f46e7-9361-55a4-8f16-be0ab5d8df21 | note | Standard / Specification - Section 10 PWRBSS Project Specification
a14c3b49-d5b2-5308-b18b-4cddf0ccc8d5 | note | Verifying Document - Visual Inspection/Pictures
239154e0-ed43-5bed-9b58-d0a1ba786e8e | note | Frequency - Ongoing
ce322fe5-f01b-5aa5-bf30-385cf6d073be | note | Activity - S
036e7290-08e0-5af2-9c6e-81b10789df74 | note | By - PE
6408e73c-7439-5ff5-9af9-8e36511035c3 | checkpoint | 3.8 - Trench Backfill (Berm)
86af2f05-aa5c-594a-9055-664c4f903fdf | note | Acceptance / Conformance Criteria - See below:
d991b9d2-a7a6-5c6d-887a-79eccf1f91dd | note | LOCATION: Within Road Corridor - SIL or within 1m of the base of SIL (Subgrade fill) GRANULAR FILL: NDM: 98% MDD; Scala: 5blows/100mm COHESIVE FILL: N/A
369ca596-9790-56c1-81f9-b5d09e93136f | note | LOCATION: Within Road Corridor - Deeper than 1m below base of SIL (Bulk fill) GRANULAR FILL: NDM: 95% MDD; Scala: 4blows/100mm COHESIVE FILL: Air Voids: Average 10%, single maximum of 12%; Sheer Vane: Average 120kPa, minimum single value of 110kPa
ff0b27e4-8370-58f4-b3f7-a401b25883ca | note | LOCATION: Berm - Beneath Footpath GRANULAR FILL: NDM: 98% MDD; Scala: 4blows/100mm COHESIVE FILL: N/A
8ef1d158-2321-53f9-8cf5-5cf3dda02a5d | note | LOCATION: Berm - Outside of Footpath GRANULAR FILL: Scala: 3blows/100mm COHESIVE FILL: Sheer Vane: 70kPa
a7340a2f-39c2-5ba7-9532-124d4fd062fd | note | Standard / Specification - As Per General Correspondence from BBO GCO-0072
f2bc8c5d-8642-5678-8ec5-0cbfee46ce3a | note | Verifying Document - Testing Reports
6d793839-d120-54e1-972d-352b30dd00f2 | note | Frequency - every 20m along trench 1 test every 5m² at driveways and footpaths
df92b3d8-9c08-5c78-b7ec-7c40c1d9e38c | note | Activity - S
441fb3cf-2c66-5172-a6c7-eff8dcaebfdc | note | By - PE
3be67758-191f-504f-902e-af7469e14149 | checkpoint | 3.8 - Trench Backfill (Road Crossings)
e3069caf-ac7b-5938-ba5e-b7af23e05ba1 | note | Acceptance / Conformance Criteria - See below:
64f5a35a-24fd-5b65-982e-293bb7ab9d3b | note | LOCATION: Within Road Corridor - SIL or within 1m of the base of SIL (Subgrade fill) GRANULAR FILL: NDM: 98% MDD; Scala: 5blows/100mm COHESIVE FILL: N/A
f971f735-834e-5f57-8210-d3aac1ebf2ae | note | LOCATION: Within Road Corridor - Deeper than 1m below base of SIL (Bulk fill) GRANULAR FILL: NDM: 95% MDD; Scala: 4blows/100mm COHESIVE FILL: Air Voids: Average 10%, single maximum of 12%; Sheer Vane: Average 120kPa, minimum single value of 110kPa
df159860-a002-5dfa-9c42-f60ca8545b9f | note | LOCATION: Berm - Beneath Footpath GRANULAR FILL: NDM: 98% MDD; Scala: 4blows/100mm COHESIVE FILL: N/A
15dbe736-f4fd-56c3-a62e-04748e3b5a7e | note | LOCATION: Berm - Outside of Footpath GRANULAR FILL: Scala: 3blows/100mm COHESIVE FILL: Sheer Vane: 70kPa
646446e1-42ed-5641-a553-f997e0b07cc9 | note | Standard / Specification - As Per General Correspondence from BBO GCO-0072
2ec6e3f8-a1fc-524a-a509-fadacc262ad6 | note | Verifying Document - Testing Reports
6c48dc5d-c3a7-5239-b270-9c799050ad89 | note | Frequency - Every 10m along trench
7fd95c35-09f9-51fa-a8e9-e81c379639ac | note | Activity - S
b919f3fd-1dcd-5342-9a40-fca4b36e9f95 | note | By - PE
9311d1dc-931b-50b6-b12b-cfb315c64f5c | checkpoint | 3.9 - Install Service
33c58a5f-ead1-560e-8234-9fd01dd58d82 | note | Acceptance / Conformance Criteria - Services installed in ducts by Utility Providers
8fa09378-46fa-56da-8ea1-8e25e99b2856 | note | Standard / Specification - Performed by Utility Provider under their QA / QC Systems and Controls
7b2545f6-36ec-50af-8442-0d8dbe9ae8d6 | note | Verifying Document - N/A
d067f1f0-dadd-52cc-a908-8dca32195346 | note | Frequency - N/A
47f313e2-5286-540f-acd3-58bc815b1c0d | checkpoint | 3.1 - Reinstate
ae1b20e6-8844-5778-baf8-35d5bf01eff6 | note | Acceptance / Conformance Criteria - Reinstate and tie-into to existing surrounds
9acb322c-e4b7-59ea-b319-1e3c41a5b5ca | note | Verifying Document - Visual Inspection/Pictures
f9b96b11-ccf2-5513-84d7-cc0dd1d0061e | note | Frequency - Upon Completion of Each Section
fc9bc56e-4c60-5d68-8bdd-8768a6bfe8f6 | note | Activity - S
10383bc4-81b4-5272-bad5-9684ca75a2d1 | note | By - PE
84c3283d-24bd-504e-b593-7adb2a662256 | section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
7ae1b87b-673c-5c28-a4bd-4b55b08e4e89 | checkpoint | 4.1 - Survey Redline Drawings
dc1c3dda-d46d-5493-83a4-ed992a74c7eb | note | Acceptance / Conformance Criteria - GPS Survey of every joint in every duct / 6m centres on continuous pipe. Survey point naming protocols to be agreed between subcontractor and Downer Survey Manager. Draft As Built Drawings. Photograph of formation, all ducts immediately before backfill, warning tape / mag slabs immediately before backfill.
f81e2f98-ab70-599e-8fab-14dd0ea09089 | note | Standard / Specification - Section 2.2.17 PWRBSS Specification
a7188ac8-db8a-5504-857c-c81ffc2501cc | note | Verifying Document - Survey Data As Built Drawings Photographs Red-Pen Asbuilt including Undercuts/Any changes from original design, including any change in road crossing locations
f73d8d9f-3c77-58f6-b89a-f0b8d113ae6f | note | Frequency - Post works completion
377e2c0a-cce7-5704-877f-d5cfb42a2d24 | note | Activity - H
b9d2b744-054c-52aa-b0ca-673b30e6246e | note | By - SV
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
49e9653e-2228-51cf-bc80-6c5fa174cbc0 | checklist | ITP - Wastewater-PVC - Rev F | itp | ITP - Wastewater-PVC - Rev F
9dbf9507-d5c1-5f76-b0e9-632a875b7d7c | section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
40e50969-1ceb-5dd9-9b3c-01f7c53f618e | checkpoint | 1.1 - Extent of Line Setout
0d5eef49-d0fc-5a1c-8a82-fd3a74f4033f | note | Acceptance / Conformance Criteria - Ensure line and level of Wastewater has been marked out and agreed with Engineer in accordance with Wastewater drawings Identify any clashes before construction.
0d071870-11c5-5eec-84c9-292c12037ea6 | note | Standard / Specification - Design Drawings
0c26aa56-26c6-57ec-a2ad-e0bcf160427c | note | Verifying Document - ITP Sign Off
3a52920e-aaf1-52da-881b-91fe241aef3f | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
63977a38-fd54-570a-b231-ab58a3755fd8 | note | Verification Activity - M
4f7e095f-a708-5e2a-93ee-5ab5f300b976 | note | Verification Activity - By: - PE
29b93ae9-4f0f-5379-a3b9-3f819c7cf4c4 | checkpoint | 1.2 - Environmental Protection
7bc6ee02-e63f-597c-b980-314821ff6b01 | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
f3e9a12d-8c5a-5a8e-bf90-8ede8d1fa0b1 | note | Standard / Specification - Project ESCP Plans
46bfa01b-553c-5913-8caf-ebdd8474fbde | note | Verifying Document - ITP Sign Off
b29f2714-073d-5b81-bd59-5a1cbe02af26 | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
93e14ecb-207f-5822-9af8-0cdb07361ee8 | note | Verification Activity - M
3ea2dbb3-c6bf-5dc0-aa59-59f7b80d4a4e | note | Verification Activity - By: - PE
c1757774-9612-5bda-8f1b-91d1e7f574f0 | checkpoint | 1.3 - Stakeholder
afaf20fc-c54e-5524-8f33-e4380c3567a9 | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
a09a546d-55fe-5f19-b899-ae01546cb169 | note | Standard / Specification - Project Stakeholder Management Plan
967077ad-1d63-5426-901a-2aa6bc33d6d4 | note | Verifying Document - ITP Sign Off
e5e9c320-9f09-5c08-9a43-e161dbb5bf39 | note | Frequency - Prior to Construction with continue updates throughout the works
0ace0bfb-bfcd-5b85-a19a-a83a01875460 | note | Verification Activity - M
e39f3135-cafb-5b0b-b29c-fb105c9bd876 | note | Verification Activity - By: - PE
2d17bcb2-0fc6-51c9-86f5-20bc7fe95d1e | checkpoint | 1.4 - Permits
bd0fe073-cba0-5f59-a016-aeda24e18447 | note | Acceptance / Conformance Criteria - Permit to Dig must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip. Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. All known services must be clearly marked on site and briefed to the workforce .
79645441-64ea-58ef-b789-aad531bc2ad6 | note | Standard / Specification - Section 2.2.10 Project Specification
b67b4743-30a9-590a-9b37-350070f50604 | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
27583fad-0c9b-50eb-8194-8c8a1b4cadbd | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
47dad4cc-2d8d-5614-bf1e-4055e6a65556 | note | Verification Activity - H
e7cd61f0-d1fa-5369-b44a-ccc53d21f64e | note | Verification Activity - By: - PE
b2505ca3-943c-534d-afb7-23e310ef1e65 | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
405352c0-5f6d-5187-918d-a540cbfd3a1d | checkpoint | 2.1 - Pipes, Fittings and Pre-cast Structures
8380fd18-221b-5c3b-b14b-e692cc846559 | note | Acceptance / Conformance Criteria - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes/manholes are correct and in good condition and compliant.
89890d6c-4980-5009-8325-2eac61e918d2 | note | Standard / Specification - PS Appendix L
825234e5-2d1d-5fcc-bee4-6ba02fbafbc4 | note | Verifying Document - Delivery Dockets
d408a0c9-efa7-5344-8e51-029ba33d35a3 | note | Frequency - Each Delivery to site
e04f09b9-b48a-57e2-b870-52ecbafd7093 | note | Verification Activity - S
f922cdaf-e2bb-5a91-824f-41c0d5865dc0 | note | Verification Activity - By: - PE
8907bdeb-f5d3-517d-9285-d6893b320753 | checkpoint | 2.2 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
5a2cfb08-ad89-50f2-91cf-4777f1275762 | note | Acceptance / Conformance Criteria - Confirm material grading and density
08a7f806-f8b9-5dc8-8aa8-cc410ee0a080 | note | Standard / Specification - PS Appendix L
382be309-4d8d-5371-87b1-05587f94db3d | note | Verifying Document - IANZ Lab Test Report
9a444a70-31d6-5dbc-8f4c-291d55f3dc8e | note | Frequency - 1 Test per 1000m3
918e6dc4-ffed-53b9-9f63-766d42c0ad5d | note | Verification Activity - H
9bdc96f3-272f-5e88-a260-7aceb61b2360 | note | Verification Activity - By: - PE
22aee86e-39c3-5dae-b364-06afb43756dc | checkpoint | 2.3 - Undercut Backfill Material
4b89be8b-43b8-59cd-815f-9acf1c08a812 | note | Acceptance / Conformance Criteria - Engineer to Specify Material to meet specifications dependant on material selected
8097d6a7-b180-5018-87b6-12ab0464a2da | note | Standard / Specification - Engineer to Specify
eb77f4cc-821b-5bf8-856a-e20ceefb325b | note | Verifying Document - IANZ Lab Test Report
d3c2e5fa-8c1a-534e-a747-67fbeb9ed6a0 | note | Frequency - 1 Test per 1000m3
953f3b31-d3fb-5be7-b265-54d13f455913 | note | Verification Activity - HP
1ffea821-fd4e-5674-be51-72fc6127f647 | note | Verification Activity - By: - ENG
1f8d7f1f-2254-58d1-b0a1-af1db979e4f5 | checkpoint | 2.4 - Geotextile/Geogrid
b083675e-9d2f-5fed-89e2-735bd98c3563 | note | Acceptance / Conformance Criteria - NZTA F/07 Strength Class C & Filter Class 1 geotextile is to be used in the undercut. Geotextile or Geogrid that is used in the undercut is to be documented / marked up on drawing
5323cb79-91c0-54e4-ba4f-641d2790f3ee | note | Standard / Specification - Project Specification
e3b2c732-9e5e-55ec-a969-076070e60ae1 | note | Verifying Document - Certification
72b70309-dbc1-5449-ab59-d58f87e9de84 | note | Frequency - Material Used
b0cb6815-4b18-5e59-beae-9613ff549fb5 | note | Verification Activity - C
ddfd5a19-6932-5ea2-b283-6fcd127b262d | note | Verification Activity - By: - PE
e08ab34e-c80e-59c0-b450-570ddd726e9d | section | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction
6060b861-66f7-50a6-931b-1a3e09522cab | checkpoint | 3.1.1 - Foundation Compliance
f9114ed8-508c-56c9-a70c-105d2888782a | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
a805edc5-2b44-584f-9213-01a09c81f559 | note | Standard / Specification - Project Specification 4.3
e67b2dea-eeca-538c-b086-d2d763af8ade | note | Verifying Document - IANZ Scala test result
76acdc33-ead8-5322-8ee5-98920d33eb07 | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
48757397-c016-5f0b-8e74-9a848cff25f1 | note | Verification Activity - H
0302830c-7332-59de-ab66-34ab747280cf | note | Verification Activity - By: - QE
27e1b1c2-fd5c-53c7-8ab8-4e7ee944dd8d | checkpoint | 3.1.2 - Undercut Backfill Compliance
f165b5fe-6212-5080-a1c4-07cc213160c4 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average 98%) of MDD
05404d60-6262-571c-ab7f-97e9889a0080 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70% or 95% of MDD AS/NZS 2566.2/2002
ada43e11-038b-5cb0-b5ba-bf0ac6a35a16 | note | Verifying Document - IANZ Lab Test Report
9fc59673-dcbd-5795-991b-f459c7995aa9 | note | Frequency - Based on Undercut Section
457b1941-1530-51c1-bb06-563a243bd414 | note | Verification Activity - H
e347b3d0-785a-5cf7-bef9-359eb06d128f | note | Verification Activity - By: - QE
e98da528-b79e-502b-b67d-feb4cee476d0 | checkpoint | 3.1.3 - Bedding Compaction Testing
4459e1c9-44f2-5a1e-b6e6-870f04c8b5f9 | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average 98%) of MDD
9fee4cc3-00a2-53f5-b535-ebb65125d555 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
d47bb5bc-3ae8-5178-bcf3-82784e72ec0b | note | Verifying Document - IANZ Lab Test Report
d95580df-35a2-5e6a-a3da-b87260e02da5 | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
9977cecc-7656-5d5a-9b70-86e5ef67f597 | note | Verification Activity - H
e4969a6f-e491-5a9e-bd68-00560b809a5d | note | Verification Activity - By: - QE
1dccb922-3a01-5c74-b4e3-aa9d6ad2e2ae | checkpoint | 3.1.4 - Haunch/Side Zone Compaction Testing
8c6f233a-cfe9-5745-abd0-57f1e432f484 | note | Acceptance / Conformance Criteria - NDM Back Scatter Minimum Compaction 95% of MDD
078c54b1-a2cc-5641-8f40-4e135e103f94 | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS-25566.2/2002
0d979ae5-b690-5c70-8586-3dcd359bc89c | note | Verifying Document - IANZ Lab Test Report
ec877efa-f836-5fce-914d-65c42133af1d | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
355f9922-7a96-5092-a53c-a6bd5a79e540 | note | Verification Activity - H
d4d8b25b-c759-58fb-a058-5867a07868db | note | Verification Activity - By: - QE
fa07aaef-f1b2-5919-98c5-2b3d4d21dc16 | checkpoint | 3.1.5 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
d7cbb21f-3c7f-5065-be72-bf6e19634a05 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95% of MDD
c3985824-6639-5243-924a-357dafeea0e7 | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS-25566.2/2002
bdab0c55-e44f-5a38-8d40-da3eb921643f | note | Verifying Document - IANZ Lab Test Report
3a706429-ce3b-5a5c-acac-d7b3c99d521d | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
a97b6fb4-2749-5197-bfd2-9893f23d2fa3 | note | Verification Activity - H
52a59d26-f675-5687-bd40-33937c0b61d1 | note | Verification Activity - By: - QE
4bd67fc6-2248-5fa2-9103-a66716a27d00 | checkpoint | 3.1.6 - Backfill Inspection
12db7e92-b9dc-5d44-b13b-fdedc2975145 | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the pipeline.
63a956f9-715e-5e8e-a332-afe4588e4d02 | note | Standard / Specification - Project Specification 4.3
60d444b2-3c15-5124-8354-6dfaf78f9c41 | note | Verifying Document - Photographs
b1ab14f6-6ece-5cb0-adf6-9ae9ae772d75 | note | Frequency - Continuous
d54c2165-d850-5b0a-b89c-5600270b3fc1 | note | Verification Activity - S
166bcfcb-cc5e-5ab0-ac87-a2b26da10865 | note | Verification Activity - By: - PE
f0ef0e4e-6639-5d9e-992e-8e179dc580bf | checkpoint | 3.1.7 - Survey
d8b2d5c6-c725-5a65-a847-243a2bf19db2 | note | Acceptance / Conformance Criteria - The pipes shall be laid with the variation between the specified invert level and invert level laid shall not exceed 10mm. Pipe invert checks shall be carried out at least once per day with a maximum of 30m between checks.
a3f876d4-dfde-5223-aecf-28ebe92dcf94 | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
939644b9-8a94-5996-9d09-89e56788d01b | note | Verifying Document - Survey Data
ee51bd9c-6cf2-561b-82dd-22c6a02b957a | note | Frequency - Continuous
be32b652-6e68-51e1-a54e-2bfb34d520dd | note | Verification Activity - C
4617b38a-d3e0-5d7a-8052-83f11b5687f0 | note | Verification Activity - By: - SV
df69972f-e5ff-59c1-a9cb-6d29805b9c2b | checkpoint | 3.1.8 - Backfill Compaction Testing
69683509-f357-55f2-b443-9e2678eda21f | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC. Minimum Compaction 95%(Average 98%) of MDD
3132503d-6548-527d-ae32-76e55cc744cf | note | Standard / Specification - MDD Average of 98% with minimum of 95% PS 4.5
3960ff87-9875-59b6-9e35-c1e15d31c11b | note | Verifying Document - IANZ Lab Test Report
01f28adc-3ecc-512a-82d4-a6d1771e7a6c | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
3d0bf983-a5b1-5f0a-ab83-067fc76bcffe | note | Verification Activity - H
f589be2b-bdcf-5825-b553-dac0aa9a08c9 | note | Verification Activity - By: - QE
f3ef653a-c404-5084-a263-be2e2bb15cfa | checkpoint | 3.1.9 - Manhole Foundation Compliance
677d09e1-70bc-5ef1-9c4a-0ad3a5e67cd3 | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa Engineer to confirm undercut depth (If Required)
cf849772-ecad-55b4-aa02-0b5fce719a44 | note | Standard / Specification - Project Specification 4.3
5aa1ed71-ef58-55c3-983f-29ac1d35e5bc | note | Verifying Document - IANZ Scala test result
5c3f2d8c-1fcb-59cf-9887-729cde761a98 | note | Frequency - 1 Test/Manhole
97cdda2f-e76e-5655-840e-23cadfc13db6 | note | Verification Activity - H
f7a9b1b8-70e2-5f25-84bf-26b7e30c2455 | note | Verification Activity - By: - QE
3f3fc7a3-9e24-59ae-8947-8d37a1705531 | checkpoint | 3.1.10 - Undercut Backfill Compliance
f5d28d44-e770-5c37-9b43-0262b26bcf56 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average 98%) of MDD
e237cff0-422d-5a3e-b95b-96ef53bed8f3 | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 3725:2012
fd7aba61-0d96-53cc-97eb-5cde4f3d2ba1 | note | Verifying Document - IANZ Lab Test Report
6fe58900-5a8b-50d7-ab64-590c7c065ad2 | note | Frequency - 1 Test/Manhole if Undercut required
800b5487-1c28-541a-8329-d8a94d8e400c | note | Verification Activity - H
917fbdb0-418e-5466-a6fe-b12d3fa9290d | note | Verification Activity - By: - QE
56be677b-237c-52f9-9b70-a5a801cf2760 | checkpoint | 3.1.11 - Bedding Compaction Testing
2d183ad2-6329-5085-8bc5-13ac4e92f2d6 | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average 98%) of MDD
e1b29de3-a730-53c7-8d76-2d7e993deabb | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 3725:2012
aebdbf95-4e5e-5d9a-bab5-737c9a2935ba | note | Verifying Document - IANZ Lab Test Report
ccdc68b2-6f5b-5697-a585-59cc69549c59 | note | Frequency - 1 Test/Manhole
b4501a13-5213-5924-ad78-9145b0b42f90 | note | Verification Activity - H
f423f03e-2f08-5bb3-b771-74422f0c3e41 | note | Verification Activity - By: - QE
b3b65b5e-7bcb-554b-9cb8-947a4ebef121 | checkpoint | 3.1.12 - Backfill Inspection
8dacf914-9b08-546f-a9e3-9b3fe5cc4935 | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the manhole
2b084272-b8b6-5df0-84fb-13f3de659b9a | note | Standard / Specification - Project Specification 4.3
489cd81e-404c-5c4b-ba53-7198caa05a74 | note | Verifying Document - Photographs
ff693eec-23da-5e77-803d-4b7e0423c663 | note | Frequency - Continuous
fe61226b-e6d3-5623-88fe-7475c5d1ae37 | note | Verification Activity - S
9dab9a60-219b-5f79-882e-27df70458dac | note | Verification Activity - By: - PE
c8b12138-899b-5c57-b584-84dc761ac3ca | checkpoint | 3.1.13 - Backfill Testing
fd68ce07-ed6f-58e1-b85d-f91538958ac6 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC. Minimum Compaction 95%(Average 98%) of MDD
19760d10-412f-548c-9738-59448210c203 | note | Standard / Specification - MDD Average of 98% with minimum of 95% PS 4.5
05f3cf0b-31a7-5f95-8904-b79bba7c79f0 | note | Verifying Document - IANZ Lab Test Report
da9eb4b7-f5d6-5ace-ba2d-717b88dfae8f | note | Frequency - 4 Density tests per layer at Quarter Points Around Structure
3b9e8475-dca7-5e35-82ed-7a6cb0da0c7d | note | Verification Activity - H
716af32b-ddd9-52de-8389-d6cab9845209 | note | Verification Activity - By: - QE
e022f314-63cb-579e-8684-330a167a444d | checkpoint | 3.1.14 - Low Air pressure Test of Pipeline
66364606-a2c3-534e-ace6-3048f1d43445 | note | Acceptance / Conformance Criteria - Low Air Pressure Testing as per Appendix C2 NZS 4404 Refer to NZ/AS 2566.2 M5 (Constant pressure tests) "NTT 009"
de612459-5f70-5818-9692-8bde69981beb | note | Standard / Specification - Pump Air to 25kpa and maintain pressure for 3 minutes
d81c550e-1daa-5078-9784-1a7264ea80d5 | note | Verifying Document - Pressure Test Report
9e335dd2-ef48-5369-8897-e27b45acb834 | note | Frequency - 1 Per Line
f35c8c92-2a0a-5072-9fde-de6d1b2d5141 | note | Verification Activity - H
856a6127-b419-5d5b-b6e4-2b248fae3ec8 | note | Verification Activity - By: - PE
4ae69c39-52c5-59c8-8b51-32763396a1fd | checkpoint | 3.1.15 - Manhole Vacuum Test
00738fef-8cb6-51f0-87dd-c30b5c6b57c3 | note | Acceptance / Conformance Criteria - Manhole Leakage Test hold time as per Table 5-12
e87bf1ec-326e-58da-82df-2ee38be298c7 | note | Standard / Specification - Draw Vacuum of -254mm Hg
3fcacb97-bdb6-5b03-be3c-d256bf3bce66 | note | Verifying Document - Vacuum Test Report
b50aef71-5614-53b4-bc87-a8e119ba010b | note | Frequency - 1 Per Manhole
606da953-b867-5a2f-87be-2d07646604e2 | note | Verification Activity - H
1aa57890-8a66-5cb1-b2f5-79a96fc4593f | note | Verification Activity - By: - PE
af7a66f6-3592-548c-bb40-c96eb478aefa | section | SECTION 3 – CONSTRUCTION ACTIVITY - 3.2 CCTV & Reinstatement
ae4e0727-0ea0-5a5b-8cdb-39371bb338f2 | checkpoint | 3.2.1 - CCTV Inspection
49f7fb21-4d94-5678-95fe-f78b9df17770 | note | Acceptance / Conformance Criteria - Quality Check on New Works
915e5944-4095-5105-869c-b21edf93b491 | note | Standard / Specification - Project Specification 4.4 NZ Pipe Inspection Manual
9f223a2a-a09e-5164-a383-f07deaf708cc | note | Verifying Document - CCTV Report
bfc6f1be-dacf-5632-8129-6326a89ba06b | note | Frequency - 1 per line
5811b338-c224-5676-8dfd-eb01666d8fb5 | note | Verification Activity - S
d67a37a1-99ff-58c0-a5d0-99876a68a702 | note | Verification Activity - By: - PE
ff7525ea-17db-5363-91eb-cb4eb20a3429 | checkpoint | 3.2.2 - Reinstatement
d84a7d3f-8416-5520-9539-6112b4667f48 | note | Acceptance / Conformance Criteria - Quality Check on New Works/All the MH Lids and Cesspit Levels should align with the pavement specification in terms of level & alignment
e1ade64f-2cba-5b1a-b0bc-5b8923388c1a | note | Standard / Specification - Reinstate and Tie into existing surrounds
7a7a35f1-5faa-523e-b6ef-c17b9712f2e8 | note | Verifying Document - Photographs & Level Checks
2a9de3dd-83d1-5702-bc8a-b157cdfdfc7b | note | Frequency - Continuous
5e940cb0-86cd-5929-bcdd-a32bb4e182a2 | note | Verification Activity - S
861e3c21-a38e-5d21-88fb-f33e9ed47378 | note | Verification Activity - By: - PE
84c3283d-24bd-504e-b593-7adb2a662256 | section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
7ae1b87b-673c-5c28-a4bd-4b55b08e4e89 | checkpoint | 4.1 - Survey Redline Drawings
591e64be-7b5b-5756-ba5c-5c480cb802b9 | note | Acceptance / Conformance Criteria - Quality Check on New Works based on the tolerances in RITS
88b6021a-3110-5045-8d91-2e60fb1249e0 | note | Standard / Specification - Project Specification
7237c198-5606-5126-876a-6ef80ae0fee9 | note | Verifying Document - Survey Data As Built Drawings Photographs Red-Pen Asbuilt Including Undercut Sections
33e15c37-82ba-5b45-b3a6-055493fdfcdb | note | Frequency - Post works completion
394dac1e-4d42-5da3-b3eb-6cd692c55060 | note | Verification Activity - H
71d6ef71-a603-5a9e-92cb-01a6dfd75c70 | note | Verification Activity - By: - SV
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
598ccadd-c12a-5026-9999-fc3b1aeec57d | checklist | ITP - Watermain PVC | itp | ITP - Watermain PVC
c3992fc7-0196-5c33-bd5f-48c26a923c63 | section | 1. Pre-construction (P&G / Establishment)
40e50969-1ceb-5dd9-9b3c-01f7c53f618e | checkpoint | 1.1 - Extent of Line Setout
2188c8af-1b0e-5f69-b95b-5375efd86476 | note | Acceptance / Conformance Criteria - Ensure line and level of Stormwater has been marked out and agreed with Engineer in accordance with Watermain drawings Identify any clashes before construction.
52de05b7-2523-5da6-8f80-d5d818ab628f | note | Standard / Specification - Design Drawings
e61c2fd1-b475-5e0b-9891-8eb078397d5c | note | Verifying Document - ITP Sign Off
4c435d60-892e-549b-ad93-35365a7448d1 | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
1b47d63b-488e-5cb4-9561-a648677e6e11 | note | Activity - M
74725284-9d13-53b3-adb8-e716dfb7ab4f | note | By - PE
29b93ae9-4f0f-5379-a3b9-3f819c7cf4c4 | checkpoint | 1.2 - Environmental Protection
2daa111b-fb92-56cb-95f0-a0893bb7d5a7 | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
90e89d68-cdce-5951-807d-af0f8df8df9d | note | Standard / Specification - Project ESCP Plans
0c7e2196-45e7-501f-b491-48fbc3679d4b | note | Verifying Document - ITP Sign Off
183c9709-e340-589b-8e50-25dde0b61fe6 | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
58063758-ff8f-5ae4-8b2f-6df8e28b5bd3 | note | Activity - M
cb9fe534-57a2-5c13-bc53-f991d52f3827 | note | By - PE
c1757774-9612-5bda-8f1b-91d1e7f574f0 | checkpoint | 1.3 - Stakeholder
9989e892-ba99-5f46-94d1-2ad757eaa13b | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
7d849347-4c2f-51c4-9572-a3141cde43c8 | note | Standard / Specification - Project Stakeholder Management Plan
92486058-ca48-5a73-8b08-5850dfbedada | note | Verifying Document - ITP Sign Off
e0d10c68-8f54-592b-ae3e-ce2b6314547a | note | Frequency - Prior to Construction with continue updates throughout the works
86e0b0bb-7529-57e6-9e4e-984c639ef986 | note | Activity - M
f0b731bf-77b1-5b67-9e5f-a719015147f2 | note | By - PE
2d17bcb2-0fc6-51c9-86f5-20bc7fe95d1e | checkpoint | 1.4 - Permits
6dc1956a-3aec-55c3-ba28-fa3b08efcdc1 | note | Acceptance / Conformance Criteria - Permit to Dig must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip. Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. All known services must be clearly marked on site and briefed to the workforce .
37f81dcf-5bd4-55f4-acf6-85e9f7454b47 | note | Standard / Specification - Section 2.2.10 Project Specification
858dc8ce-814c-557c-8854-687c8c26c1a9 | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
484256f6-9cf4-5e56-bc22-cd9ce8cca84f | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
8f71f728-3673-5fbe-9e40-0033bce41387 | note | Activity - H
c9df6b3c-5476-5a0f-a223-54b76ae6401d | note | By - PE
2b839b91-0e59-52bf-bfbc-2a6a8cc5432d | section | 2. Material, Personnel & third party approval
a01633bd-9195-57bc-b7a7-0b51939340af | checkpoint | 2.1 - Pipes & Fittings
cb6bd198-cb74-5f66-a3a6-58ecf46e544e | note | Acceptance / Conformance Criteria - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes/fittings are correct and in good condition and compliant.
25841545-1c58-586f-9e80-ecf24d1107b7 | note | Verifying Document - Delivery Dockets
0b67eb3e-77fd-5648-bc0e-f15359c84a7b | note | Frequency - Each Delivery to Site
436ec73b-2a28-5f66-a0d0-4cacba4928ce | note | Activity - S
e86680e5-61d2-5449-9f68-97554420befe | note | By - PE
16430c7e-80ff-5cf2-a225-9e09136cc5be | checkpoint | 2.2 - Bedding/Overlay
ac3ee39b-6f57-5478-a442-c7b907d45e1b | note | Acceptance / Conformance Criteria - Confirm material grading and density of pit sand or other approved material
5d3234bd-54fe-55b6-b03b-87c35187af3b | note | Verifying Document - IANZ Lab Test Reports
61ba510d-a74b-5af1-ad03-82e66121b21c | note | Frequency - 1 Test per 1000m3
f97c4424-e8b9-5ca9-a68e-bbbec2432e03 | note | Activity - H
8057e399-7390-53b4-a075-ad6c78bb59fb | note | By - PE
2934d3fb-ac0a-5be8-853d-e440230282b7 | checkpoint | 2.3 - Backfill Material Compliance
0fd748e4-0fb9-504a-adf6-f623c6b4d7af | note | Acceptance / Conformance Criteria - Confirm material grading and density of pit sand or other approved material Use selected native soils in berm
8fa15a36-e044-5740-a8a2-9311781670ef | note | Verifying Document - IANZ Lab Test Reports
77be99f0-dc14-540f-91ce-14cf9920a5d0 | note | Frequency - 1 Test per 1000m3
c80191a8-c3bd-5a2a-bc63-9e54b7a980cc | note | Activity - H
a8b7c56f-354d-5900-86a1-235d2be3eda1 | note | By - PE
92420db2-3aa9-50e5-b1d6-d56be587136a | checkpoint | 2.4 - Undercut Backfill Material
3cb47e54-1418-5622-ab41-d615c9382364 | note | Acceptance / Conformance Criteria - Engineer to Specify Material to meet specifications dependant on material selected
675eb2f7-2d4e-5dd8-9a6a-44367de039b6 | note | Verifying Document - IANZ Lab Test Reports
5c0e5624-6b46-5f4e-8374-970dee1428ec | note | Frequency - 1 Test per 1000m3
6cfa0a74-20c1-5572-80f3-2efc11be00d6 | note | Activity - HP
c075b68e-f3e8-556b-a880-b2e139659d80 | note | By - ENG
7928edd2-fe08-5f6b-ab5c-f03ae853b9da | signoff | AUTHORITY HOLDPOINT
117c1a85-87b8-5979-891c-20eb9fdb1498 | checkpoint | 2.5 - Geotextile/Geogrid
92069664-6ed8-5673-8056-9568d2bfba26 | note | Acceptance / Conformance Criteria - NZTA F/07 Strength Class C & Filter Class 1 geotextile is to be used in the undercut. Geotextile or Geogrid that is used in the undercut is to be documented / marked up on drawing
c0adf8e0-1d1f-5027-ac8a-bae157691020 | note | Standard / Specification - Project Specification
1217c2d7-7332-559c-b7f7-4a23ae4e0757 | note | Verifying Document - Certification Photos of Delivery Dockets
8ae1e8ac-9cc7-5151-a8b3-88d75e34bda1 | note | Frequency - Material Used
08f4eefd-17ae-566f-9c7a-c4931b9dc2b4 | note | Activity - C
305ec3b4-fd80-5ba6-9290-213684fa245d | note | By - PE
d947afe9-c250-55e0-9f26-e1feb944cfb2 | checkpoint | 2.6 - Warning Tape
f1e47766-a3f3-5215-a1ce-135f9e9dbb47 | note | Acceptance / Conformance Criteria - Obtain Warning Tape from supplier
b71ee51d-495e-5b89-b505-abbfb185ea0b | note | Verifying Document - Delivery Dockets
90b99526-3ed0-5be3-9aea-1e794c893eae | note | Frequency - Each Delivery to Site
c663b7c0-cb53-5627-ad7d-f5d83742f76e | note | Activity - S
1121b458-64ce-5dca-b110-8108945ceb30 | note | By - PE
249967af-1f51-5783-977d-c9f3c7c8e1d6 | section | 3. Construction Activity
7d370922-7733-519c-b084-007467ea59e9 | checkpoint | 3.1 - Trench Excavation
f12678f6-c0fd-5ed9-9d41-7545f383290c | note | Acceptance / Conformance Criteria - Excavate trench to design height, placing spoil in approved area and benching as required Visual Inspection to any hard stones or rocks to be removed Any archaeological finds to be reported Inspections to any formation of soft spots
b510b474-29a2-5d0c-81a5-9a5212a8460f | note | Standard / Specification - Project Specification 4.3
4b59d9da-33f7-53d4-8f30-f408e131b057 | note | Verifying Document - Scala test result
cda8a064-9dfd-5a8c-8458-f1134750ce46 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
78a2c85b-1eaa-5acb-bf9f-a76a82062ae1 | note | Activity - H
46695756-bbb6-58f9-8696-bed72f90f8fd | note | By - QE
01f8da51-3f6a-58b3-8693-f52e82d75129 | checkpoint | 3.2 - Foundation Compliance
276d0ce0-dfa4-5bd5-a550-9580a3b5dd3e | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
cf10a023-8a94-5086-b4a7-7c0d119805d7 | note | Standard / Specification - Project Specification 4.3
f2dc0382-c218-52d7-8977-e280dd16c5b1 | note | Verifying Document - Scala test result
d4810fc8-9e04-5194-9ec3-fc30e1853e85 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
06a8366a-dfc5-5baa-9e15-0b508bbbed80 | note | Activity - H
26295be7-846f-5ad0-9afa-1dd19a084b78 | note | By - QE
fce24abf-d983-548d-883d-e31dcfd2c304 | checkpoint | 3.3 - Undercut Backfill Compliance
34324fc7-d773-54db-8aeb-fc5b1c2f454a | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average98%) of MDD
a38999ed-4542-576e-9f74-959326a18952 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
baf96eeb-3529-5ca7-b763-cf0dfe756ffc | note | Verifying Document - IANZ Lab Test Report
1a703f4d-039c-5d00-ac58-61d47565037c | note | Frequency - Based on Undercut Section
02dcf23e-0ddf-5af9-9f2f-489a85c3bd0f | note | Activity - H
96a5d9f8-dd74-57ae-b8fd-a669eca0bac1 | note | By - QE
d0bddc7d-e5fa-5baa-94fe-1275f06be289 | checkpoint | 3.4 - Bedding Compaction Testing
08a3cf70-2b4a-517e-9869-336e34e1f911 | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average98%) of MDD
cbf448d3-5bf3-5c35-be34-24363e0e426b | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
c18f590f-57f1-5d88-b849-183772593ece | note | Verifying Document - IANZ Lab Test Report
05c60a7a-bba7-500d-bb44-44a474905a1f | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
d3c46b89-d758-5e27-b802-1ad98e98ab2b | note | Activity - H
1798524e-a004-51ef-af4b-104ac3f8c2da | note | By - QE
983a1a11-117a-5587-8e28-483d3d186c18 | checkpoint | 3.5 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
bfbf2e9a-fbc9-5fd0-973b-8095fcfb763b | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD
969fa821-e653-5c9f-8897-7ec7ae2f0083 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
028a07b5-3f8a-52e8-8de4-6fba06ab734f | note | Verifying Document - IANZ Lab Test Report
437a0105-39f6-512b-b69b-44bd64fab130 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
9260299f-8ef5-52bc-bd37-83f49bdb4e74 | note | Activity - H
a5e58f80-6f41-59e1-af0d-001fe6c370e9 | note | By - QE
d235f1f7-7d52-5cc6-838d-bb5cf530d745 | checkpoint | 3.6 - Backfill Inspection
990919b2-90bb-5bf4-bc57-bdc954877ec6 | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the pipeline.
106a340e-9051-54e1-89a9-15bf607d4d77 | note | Standard / Specification - Project Specification 4.3
7ed35f7c-4b27-5ebd-8390-370abfc9f814 | note | Verifying Document - Photographs
6b2fe735-3696-533d-bab8-16980d8f1304 | note | Frequency - Continuous
2e70d804-bb9d-5d4f-9903-b55ab30e5653 | note | Activity - S
da1687ab-91ab-58e9-91b6-1b6e97041a12 | note | By - PE
23851ce8-70e8-50f5-8a7c-b4693607ea05 | checkpoint | 3.7 - Install Warning Tape
89ad8ee1-db8e-53c5-b079-f92974f40951 | note | Acceptance / Conformance Criteria - For open trenching, detector tape shall be placed approximately 200mm below final ground level and metallic ‘detector’ tape coloured blue, stipulating ‘Danger – Water Main Below’ (or similar) shall be laid.
d0d4470d-e0c0-5649-9097-5dea6fc91f18 | note | Standard / Specification - RITS
21b7fcef-c235-5990-a6fd-f5e7757bfb27 | note | Verifying Document - Photographs
30ab73b0-3683-507d-ac37-9477ae9dc08e | note | Frequency - Continuous
1927f6e7-bf71-5f57-b600-bc4d095c4728 | note | Activity - S
ec5e7354-bd30-5124-93d6-dd96acb2018c | note | By - PE
f17dd255-5836-524d-b09e-559b70479f73 | checkpoint | 3.8 - Survey
a5d031ac-99e2-5ea8-bc94-c509b478106f | note | Acceptance / Conformance Criteria - All Water Mains shall be laid in a straight line or following street layout. The deviation from approved design alignment permitted either in plan or elevation shall be: Open Cut – ± 50mm on straight and 100mm in curves All pipes, fitting and thrust blocks to be as built prior to backfilling
681466f1-4732-5e3b-b0ea-286d982015e0 | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
2c0c5481-84e6-5bff-8007-7a844c38bedf | note | Verifying Document - Survey Data
66759fe9-2a36-5335-a22c-25c4b5dd3229 | note | Frequency - Continuous
9ba33e89-78d1-5cef-9805-8f994815413b | note | Activity - C
69778e5c-9b81-5ce5-8d17-dd4ed98cc005 | note | By - SV
b475c56c-1e51-53b0-a7b1-bcb5786f5689 | checkpoint | 3.9 - Backfill Compaction Testing
c788c146-bfb9-5a96-b95c-3518e3b3e9f7 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC.
931f3c70-962d-5967-b81f-1b19a97e7bf3 | note | Standard / Specification - RITS
c9458d99-170d-53ae-8103-b196f1f0fa35 | note | Verifying Document - IANZ Lab Test Report
e9547088-f957-51a1-8c0e-ee8a1f0b6997 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
298dad17-495a-52c9-be43-f3bbe3b937ed | note | Activity - H
c9717a72-4c7f-5c9d-a696-26defe658e28 | note | By - QE
f3176f0c-286c-506d-8552-3a9f3b62de38 | checkpoint | 3.1 - Pressure Testing
5d69a420-1957-5b1c-9290-3c51d88e388b | note | Acceptance / Conformance Criteria - At least one working day advance notice shall be given to council for pressure testing of pipelines. All pipelines shall be pressure tested and backfilled after anchor blocks, specials and fittings are completed, but with joints and connections visible. The final tests are to be witnessed by Council prior to the pipe being connected to the ‘live’ network. No further connections will be permitted after this stage. Refer to NZS 4404 Appendix C3 for the requirements or if this not available, the pipe manufacturer’s procedure.
5b2454ea-1cc6-594d-a88e-513232a2193d | note | Standard / Specification - 6.3.10 RITS
6e90bbf9-09d4-54e5-b7e6-9a44629abfc2 | note | Verifying Document - Visual Inspection & Report
f2c3c247-ebb0-5874-a6dc-294338df015c | note | Frequency - Completion of Works
5bde098e-eb81-5021-b0e8-32eedf795680 | note | Activity - S
6b55841c-7a86-5f6e-a16d-f8ba94e5ce4c | note | By - PE
682b782b-da97-511b-a451-533bb2dc1e9d | checkpoint | 3.11 - Disinfection & Flushing
a04ef4c3-e232-5cb6-bf4a-b48be7c1cbb3 | note | Acceptance / Conformance Criteria - Appendix D of NZS 4404 – Water Supply Disinfection Specification shall apply Discharge of Testing or Chlorinated Water from pipelines may require a resource consent from the regional council
72e62171-3897-5595-bacf-de1ed94ce84e | note | Standard / Specification - 6.3.11 RITS
1a077abb-5e7e-54ee-b677-bc5d79b10d96 | note | Verifying Document - Visual Inspection & Report
012e07a0-eb0d-5930-b43a-b7ed3ebb79d4 | note | Frequency - Completion of Works
480678f5-c94c-5bce-9be6-d7378074e353 | note | Activity - S
80577bfd-b617-5499-b284-b5dae1307d01 | note | By - PE
b1d7c191-8845-5cd8-bc06-9e45bfcb6347 | checkpoint | 3.12 - Bacteriological Test
ecf71ef6-9afe-54ef-b387-99bad42254b0 | note | Acceptance / Conformance Criteria - In commissioning new pipelines, Council shall be given 24 hours’ notice as to when sampling for bacteriological tests is to be carried out. Water in the pipeline shall be sampled between 12 hours and 48 hours after postchlorination flushing and the samples tested for the presence of E.coli, Coliforms and Heterotrophic Plate Count by a Ministry of Health Approved laboratory with IANZ accreditation for this type of test. The number of samples shall be at least one for projects involving less than 100m of pipe, two for projects up to 200m length, etc. “A satisfactory result is s <1 MPN/100ml for E.coli and Total Coliforms and less than 20 CFU/ml for Heterotrophic Plate Counts.” If E.coli is detected the pipeline shall be swabbed, flushed, disinfected, flushed again and then the bacteriological tests repeated. The process shall be repeated until such time a clear test is recorded. Note: There are high risks of test failure due to sample contamination so it is recommended that the testing laboratory is also involved in collecting the sample.
8458ae3b-7797-5a0a-814d-f2e6b72268ae | note | Standard / Specification - 6.3.11.2 RITS
e3bb0c54-bcd9-5b91-92e8-cb2da86ad9a5 | note | Verifying Document - Visual Inspection & Report
1c926b7a-e073-5363-94e9-287f94a4c5f7 | note | Frequency - Completion of Works
1cb5f6b7-91a6-5b74-b072-c914ba3092a9 | note | Activity - S
6a48d096-0034-56d8-868a-c78b608d8349 | note | By - PE
67389d0d-12af-5ad3-85d9-f07119c2365b | checkpoint | 3.13 - Reinstatement
8ec17bcc-d926-596a-8ec1-55e292b11670 | note | Acceptance / Conformance Criteria - Quality Check on New Works
12c240a7-5851-5a10-a894-dfc1f21a71de | note | Standard / Specification - Reinstate and Tie into existing surrounds
26665455-42e7-5cf8-af92-81a44a978efc | note | Verifying Document - Photographs
cf7cef0f-8302-5fa6-8771-1d4718d773d3 | note | Frequency - Continuous
6b0fbabb-ce6a-568c-be52-0fa22a06b6a6 | note | Activity - S
606b0568-359a-5ac7-a423-5451cf87de4f | note | By - PE
85475bb6-9a9c-571e-bdc0-15f2014da4d2 | section | 4. Post-construction (Final Inspection & Handover)
b0345a60-8f72-56e0-9331-c90c4130b0fb | checkpoint | 4.01.01 - Survey Redline Drawings
970a77da-11d9-53d6-a1c1-82d62e20424c | note | Acceptance / Conformance Criteria - Quality Check on New Works based on the tolerances in RITS
989fa426-033b-5cca-bab8-65ba09ef6e49 | note | Standard / Specification - Project Specification
f78817de-6c2e-573e-ac02-c1c19369129d | note | Verifying Document - Survey Data As Built Drawings Photographs
8c5281e5-f67d-50b7-b542-966288db2b75 | note | Frequency - Post Works Completion
45c3f513-76b5-5f0e-a367-64bc9aaa06ad | note | Activity - H
5dc829e6-c403-5afa-9d2f-41b4948b6ec6 | note | By - SV
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
c309d783-6d73-5915-962d-3c963578d324 | checklist | ITP - Watermain-PE - Rev C | itp | ITP - Watermain-PE - Rev C
9dbf9507-d5c1-5f76-b0e9-632a875b7d7c | section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
40e50969-1ceb-5dd9-9b3c-01f7c53f618e | checkpoint | 1.1 - Extent of Line Setout
0a95db99-801f-5b64-b0e4-276d1fa2e264 | note | Acceptance / Conformance Criteria - Ensure line and level of Watermain has been marked out and agreed with Engineer in accordance with Watermain drawings Identify any clashes before construction.
abc94a23-054b-5d39-b35c-be522fbf1f99 | note | Standard / Specification - Design Drawings
1e4a6c2b-0712-54b5-a084-37293bc07f79 | note | Verifying Document - ITP Sign Off
04d90d08-9c86-529d-bdc7-d7f606d767e0 | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
4e07d6b6-c8ca-5939-a4a0-b2fdc77acff1 | note | Verification Activity - M
6512d3fd-65b8-5c93-81fc-3e7f4b28fcc3 | note | Verification Activity - By: - PE
29b93ae9-4f0f-5379-a3b9-3f819c7cf4c4 | checkpoint | 1.2 - Environmental Protection
65087ed9-b989-5020-8054-6ed613639f0d | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
82587d2b-c8ca-5163-a5e7-9c3bfa2d2f18 | note | Standard / Specification - Project ESCP Plans
d5236638-585e-5e7f-9e7a-d7121a304080 | note | Verifying Document - ITP Sign Off
0fc5d5f1-98f8-5eed-b176-57002e3258b9 | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
8366b632-0a70-5798-a741-526e150ce3e0 | note | Verification Activity - M
3f118ed7-6930-568c-a87a-51e8ce7b2afa | note | Verification Activity - By: - PE
c1757774-9612-5bda-8f1b-91d1e7f574f0 | checkpoint | 1.3 - Stakeholder
a909862c-53af-5e97-a577-a7e558fc1387 | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
8b30c912-5308-515f-9011-deff2e5af2d0 | note | Standard / Specification - Project Stakeholder Management Plan
22e61624-58fb-5c44-96e6-7405784989c9 | note | Verifying Document - ITP Sign Off
56b178e3-75aa-52a2-bcd2-286ca395bd16 | note | Frequency - Prior to Construction with continue updates throughout the works
cd042eb1-e4a2-5b7f-acb5-bee68734a58c | note | Verification Activity - M
6760a1e3-a3d9-563b-b0a8-5e043a724492 | note | Verification Activity - By: - PE
2d17bcb2-0fc6-51c9-86f5-20bc7fe95d1e | checkpoint | 1.4 - Permits
bd7e3c64-3e2a-5920-be2f-4935d4539398 | note | Acceptance / Conformance Criteria - Permit to Dig must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip. Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. All known services must be clearly marked on site and briefed to the workforce .
2fdbe04a-4a53-5122-ad61-f3593e431d12 | note | Standard / Specification - Section 2.2.10 Project Specification
1d39b83d-12b7-5980-af5f-15e7f1351ef1 | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
34edf06c-9560-55bb-ad35-1bd416718184 | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
fd608052-3027-5806-80c0-b9694cfcbeb7 | note | Verification Activity - H
521e991c-018a-531f-b625-69ce492ee8b1 | note | Verification Activity - By: - PE
b2505ca3-943c-534d-afb7-23e310ef1e65 | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
b27b7bf0-a182-5300-b84a-e6d5cb49b3a5 | checkpoint | 2.1 - Pipes/Fittings/precast Units
6df1cf8d-1004-5e3d-a742-b98320906274 | note | Acceptance / Conformance Criteria - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes/fittings are correct and in good condition and compliant.
031c0d23-6b74-5de3-9375-5b4fc963eee6 | note | Standard / Specification - Project Specification
149854d4-efea-59df-8950-1b9b3855a0c5 | note | Verifying Document - Delivery Dockets
3a9c473c-e0e8-5ebb-992c-60ade1ec1262 | note | Frequency - Each Delivery to Site
45508343-caa2-5b23-9604-27047d34681d | note | Verification Activity - S
e73d70cb-5a38-5e06-b3c8-827da199cece | note | Verification Activity - By: - PE
b90ae28d-1d95-5d3e-a911-4a6a9262b7f1 | checkpoint | 2.2 - Bedding/Side/Haunch/Overlay
3a420734-f6f5-5210-bd48-c7cf30ddb976 | note | Acceptance / Conformance Criteria - Confirm material grading and density of pit sand or other approved material
75f33260-14de-5971-9893-aa995af3205e | note | Standard / Specification - AS/NZS2566
00009c7b-af45-55d2-a046-86613d201e6d | note | Verifying Document - IANZ Lab Test Reports
a99f9c72-9a71-5d7e-a194-447c96233017 | note | Frequency - 1 Test per 1000m3
681c2fad-bfa9-5648-b36c-f6de1429e902 | note | Verification Activity - H
c8944537-7fca-59e6-99ce-a66dad5e2739 | note | Verification Activity - By: - PE
2934d3fb-ac0a-5be8-853d-e440230282b7 | checkpoint | 2.3 - Backfill Material Compliance
3825299a-25b8-5dca-9c50-d60dda320558 | note | Acceptance / Conformance Criteria - Confirm material grading and density of pit sand or other approved material Use selected native soils in berm
f19d87bf-d6e5-5fa9-a4f6-2af14e24867e | note | Standard / Specification - AS/NZS2566
b6a0cd45-5a4a-5990-b006-f25f752d2a22 | note | Verifying Document - IANZ Lab Test Reports
8c338912-06e8-5281-97d2-89075e2694d6 | note | Frequency - 1 Test per 1000m3
5330899a-c227-532d-836c-d2203b881d90 | note | Verification Activity - H
f9a7db0a-0db0-52bb-9e7d-8028f23c799e | note | Verification Activity - By: - PE
92420db2-3aa9-50e5-b1d6-d56be587136a | checkpoint | 2.4 - Undercut Backfill Material
5d62f13b-d2e3-5bbe-8ebb-6190edba7f68 | note | Acceptance / Conformance Criteria - Engineer to Specify Material to meet specifications dependant on material selected
67edce20-2cbe-58dd-9fbc-e4a3dc0042fe | note | Standard / Specification - Engineer to Specify
9877596e-c4ed-50c6-a42c-cea5098163f0 | note | Verifying Document - IANZ Lab Test Reports
325f4fc4-0dcf-51e4-b273-c3021feac7ad | note | Frequency - 1 Test per 1000m3
43683a3d-d98b-5349-b20c-8bdb7293c3f8 | note | Verification Activity - HP
49593a74-948e-5827-b1fb-ad1dbd727d6a | note | Verification Activity - By: - ENG
7928edd2-fe08-5f6b-ab5c-f03ae853b9da | signoff | AUTHORITY HOLDPOINT
117c1a85-87b8-5979-891c-20eb9fdb1498 | checkpoint | 2.5 - Geotextile/Geogrid
f631587e-0e63-5d52-ae7b-6ffab6e6b11d | note | Acceptance / Conformance Criteria - NZTA F/07 Strength Class C & Filter Class 1 geotextile is to be used in the undercut. Geotextile or Geogrid that is used in the undercut is to be documented / marked up on drawing
2fa75ace-6055-55c3-a40c-3d5ec1a96d1e | note | Standard / Specification - Project Specification
32ac1128-ed5e-5ed9-9488-502f284d6511 | note | Verifying Document - Certification Photos of Delivery Dockets
2d807760-f4c3-59a1-a843-389e3e17cb23 | note | Frequency - Material Used
d41ab3eb-8b17-5d1d-b5f2-8814b53290d0 | note | Verification Activity - C
b2953535-89b8-5b39-bdfe-ffa0646ea0d4 | note | Verification Activity - By: - PE
d947afe9-c250-55e0-9f26-e1feb944cfb2 | checkpoint | 2.6 - Warning Tape
da40fc40-9a2f-5faa-b5fb-0c2ca4185b52 | note | Acceptance / Conformance Criteria - Obtain Warning Tape from supplier
1d59ac43-680f-55b0-86a5-141a8a35ca49 | note | Standard / Specification - Project Specification
6d3e8edf-e66b-5f5f-ab2a-78a7e021b887 | note | Verifying Document - Delivery Dockets
1316695c-b14e-56f8-977f-b319f1fc1d28 | note | Frequency - Each Delivery to Site
692ce30d-cceb-518e-8220-c671d05aada5 | note | Verification Activity - S
afd1ceba-7788-5d54-9c23-413cd9057004 | note | Verification Activity - By: - PE
9cc06a11-17ee-5f49-ac50-31c36fc22fcb | section | SECTION 3 – CONSTRUCTION ACTIVITY
7d370922-7733-519c-b084-007467ea59e9 | checkpoint | 3.1 - Trench Excavation
07477a63-9617-55fe-adb6-e93d735206cf | note | Acceptance / Conformance Criteria - Excavate trench to design height, placing spoil in approved area and benching as required Visual Inspection to any hard stones or rocks to be removed Any archaeological finds to be reported Inspections to any formation of soft spots
f06a3223-84cd-5d5a-9609-ec670899afad | note | Standard / Specification - Project Specification 4.3
5a7fbfbe-688e-5eeb-b7ad-2fc27a97a8fd | note | Verifying Document - Scala test result
e34b1620-5292-5b32-81ad-7a8792e3f85c | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
b0059aa8-b108-581e-b180-24bb3e22c386 | note | Verification Activity - H
fd57b629-7db9-5b42-9417-98d7db9f76de | note | Verification Activity - By: - QE
01f8da51-3f6a-58b3-8693-f52e82d75129 | checkpoint | 3.2 - Foundation Compliance
a9462c7a-cf46-5d7b-82df-bea3402e54c1 | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
6f1a316b-9b79-5dcd-999c-40cdb0a8b150 | note | Standard / Specification - Project Specification 4.3
b1d4f6de-755d-5514-a8cb-7f021fc05aa7 | note | Verifying Document - Scala test result
c28a2bf1-3c70-5baa-b8ce-f3dd98ceaa12 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
c6f79caa-eb63-5d79-b8ac-95e2d42eddc3 | note | Verification Activity - H
4028434b-9d26-5617-9fdd-438d79ac0013 | note | Verification Activity - By: - QE
fce24abf-d983-548d-883d-e31dcfd2c304 | checkpoint | 3.3 - Undercut Backfill Compliance
7289baf5-ae7e-54ed-846a-4a2383392ef2 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average 98%) of MDD
36e66f02-4614-53f2-a456-2561cb8cc4ab | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 95% of MDD AS/NZs 3725:2007
44b1bd3c-6feb-5286-881e-7f19a7d026a6 | note | Verifying Document - IANZ Lab Test Report
9f9226ea-523e-5a2b-bc38-72889a5f5bba | note | Frequency - Based on Undercut Section
035f96b5-9059-5337-a1d4-fb0b83a58c03 | note | Verification Activity - H
a2f6e221-4bf9-5a06-ba86-7797617bc26e | note | Verification Activity - By: - QE
d0bddc7d-e5fa-5baa-94fe-1275f06be289 | checkpoint | 3.4 - Bedding Compaction Testing
1df4c996-99ab-53f7-942f-6ca7ac2aff57 | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average 98%) of MDD
c28e6dab-f53d-508b-be11-e11c00e05aa9 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
f3d231c1-3db3-5089-8245-ea9d51c272f4 | note | Verifying Document - IANZ Lab Test Report
73ee2aa1-dd52-5ff3-bf59-3d7fa4631d99 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
5db05c3a-ef53-5db7-bc65-5a25040b4841 | note | Verification Activity - H
e0ef5f15-9aea-5074-a24e-658ad51bd8b1 | note | Verification Activity - By: - QE
8512aed8-c0b4-5bdd-95ca-a50815b95c66 | checkpoint | 3.5 - Haunch & Side Zone Compaction Testing
5a8cedb3-7758-52f9-ae98-349a03eb9a84 | note | Acceptance / Conformance Criteria - Side zone shall extend from top of haunch zone to 0.5 times the pipe outside diameter 100mm if >75 , <150 150mm if >150 , <300 200mm if >300 , <450 NDM DT Minimum Compaction 92% of MDD
22c67c7a-4f0f-5f27-b916-79dc9fcd70bf | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
e044652c-b18c-5d5c-97ac-f94df5e912de | note | Verifying Document - IANZ Lab Test Report
9fc2191d-c30b-56cd-b959-798fdeb8ab74 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
a7e6fd8b-8b1c-5028-b00d-f5ab364e28b8 | note | Verification Activity - H
55e5af02-e543-5e18-8b81-0f6967bb0813 | note | Verification Activity - By: - QE
e2eff8b9-7f73-518a-b234-c20b9796b76c | checkpoint | 3.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
73c47ed0-cbf2-5993-934d-120bdd476cee | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD
15511fb1-9695-53bd-88f4-1bb6eb4a68eb | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
71d57a91-6ae9-52a3-842f-a526707ddbee | note | Verifying Document - IANZ Lab Test Report
8d60ce92-fb60-5a80-b904-b95a5faaee5b | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
ef0d9e80-b8db-56c6-8afb-6cc3e21ec69d | note | Verification Activity - H
c0779ffe-29b9-5921-b18c-a5822fe94a17 | note | Verification Activity - By: - QE
0715b9f9-616e-5d14-90de-eab1faefa26e | checkpoint | 3.7 - Collection of Waipa ITPs
db16c050-4db8-553b-b5ac-c707c111faf3 | note | Acceptance / Conformance Criteria - ITP 02 Manhole and Valves ITP 04 Butt Welding ITP 05 Commissioning
a542d803-defa-5fd1-b771-2d607713ed81 | note | Standard / Specification - PWRBSS Quality Management Plan
407354aa-ee45-5aef-81cc-93cd41c63f9a | note | Verifying Document - Document Review
26782718-d70a-5d80-bd2b-82c07cf499d1 | note | Frequency - Once
0ae112fd-56f4-526f-9070-382d1a63f2a0 | note | Verification Activity - HP
8d2e5d47-b8ba-5d26-a3a6-82ce5b197b84 | note | Verification Activity - By: - ENG
0f588dd6-d4d5-57d7-b432-2e66dc5cfbf7 | signoff | AUTHORITY HOLDPOINT
4df3c69f-32d6-5ce8-9283-300b3997b531 | checkpoint | 3.8 - Backfill Inspection
dc6de0af-115b-5843-b061-6be7817ecf46 | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the pipeline.
675da3b2-fd26-56a3-a501-da6826f06731 | note | Standard / Specification - Project Specification 4.3
6965b7d0-334b-59e2-aa93-25fa3229f737 | note | Verifying Document - Photographs
e95ccae1-d1a3-52a4-9d3b-e564218e2637 | note | Frequency - Continuous
f015779c-9373-5743-a646-802c363d4478 | note | Verification Activity - S
8cf4bc20-61bc-5eeb-a074-a44f5fdd7d96 | note | Verification Activity - By: - PE
6d0efba5-6acf-5128-a807-1ab3ab9b6acf | checkpoint | 3.9 - Install Warning Tape
275cc7b9-aa03-59b1-a9ef-15d48a4251a0 | note | Acceptance / Conformance Criteria - For open trenching, detector tape shall be placed approximately 200mm below final ground level and metallic ‘detector’ tape coloured blue, stipulating ‘Danger – Water Main Below’ (or similar) shall be laid.
89fe7a2a-2b50-544d-bdad-97e00f5130ea | note | Standard / Specification - RITS
f6fa2374-a03a-5ce2-bf54-c4c85325f636 | note | Verifying Document - Photographs
afddf2df-94e0-505b-8909-48f846096047 | note | Frequency - Continuous
84edf32f-7f89-51cf-ae66-6b1336689710 | note | Verification Activity - S
f36fa6dc-2bba-5148-8f6f-6e84f2679186 | note | Verification Activity - By: - PE
76853413-39ee-5af5-afc3-fe3a4e2ceaff | checkpoint | 3.1 - Survey
a294f9b0-4c02-5c4d-a1a3-5fc5966b04b4 | note | Acceptance / Conformance Criteria - All Water Mains shall be laid in a straight line or following street layout. The deviation from approved design alignment permitted either in plan or elevation shall be: Open Cut – ± 50mm on straight and 100mm in curves All pipes, fitting and thrust blocks to be as built prior to backfilling
bd943e00-f1ef-5548-9855-abc4a6da9574 | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
e578e240-102e-52d9-8bf4-4b212aa765eb | note | Verifying Document - Survey Data
7162641a-4e07-5fd2-b4a5-1f9598843f3a | note | Frequency - Continuous
715dba86-0507-520f-9d7c-b7ff9bba058f | note | Verification Activity - C
03bed1e0-d9a5-5761-9444-e30df7766f80 | note | Verification Activity - By: - SV
b1a8a1ba-4d3e-58f2-ba0c-96893bb7956d | checkpoint | 3.11 - Backfill Compaction Testing
dcb0cf94-74d4-51d1-8687-dfbb3bd0606b | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC Average of 98%
3655ad07-7eb9-5add-99a7-f46a315bd015 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
d6ae28a0-eb28-58ef-82ea-58ef1e0541c9 | note | Verifying Document - IANZ Lab Test Report
860a494c-b3af-53b1-be11-fdc81ccaed51 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
85d03948-9207-55e4-9ec0-aeae0b9cf4a2 | note | Verification Activity - H
d5659d13-9af2-564d-b799-0641cdf4eb19 | note | Verification Activity - By: - QE
11caa917-231a-5a12-9c4b-a1cf2601809a | checkpoint | 3.12 - Manhole Foundation Compliance
d2bb9c59-ced0-5fcb-b60d-aba2e6b81c43 | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
eca8b52f-be49-5686-a1ac-7e03b5cddfd5 | note | Standard / Specification - Section 4.3 PWRBSS Project Specification
cce2838a-eb0a-530a-8a34-51b66141f36c | note | Verifying Document - IANZ Lab Test Report
f0e0bf59-c689-530f-b43b-3271b1b807bd | note | Frequency - 1Test/MH
370ed67e-4d14-5680-bfb7-0014a22de54a | note | Verification Activity - H
5c327065-fbe3-5f72-88e3-56f05f100f09 | note | Verification Activity - By: - QE
3efb3cbe-8999-5c33-8733-f7f81942565c | checkpoint | 3.13 - Undercut Backfill Compliance
69d66008-6fab-587a-9ca1-edb57a344028 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average 98%) of MDD
8989cce0-1ab5-5a3e-8bf4-8902b0256e3c | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 95% of MDD AS/NZs 3725:2007
a7b502ab-05b3-5930-8848-e1bd823626b4 | note | Verifying Document - IANZ Lab Test Report
8f433644-ef93-594d-857d-0df99d6be813 | note | Frequency - Based on Undercut Section
79b84a28-db63-5020-addd-eefa8c943bb8 | note | Verification Activity - H
975e420a-7912-5a09-be21-4e80218f9f86 | note | Verification Activity - By: - QE
f78063ed-84dd-5c6f-b9a1-849bb040c16d | checkpoint | 3.14 - Bedding Compaction Testing
38cf7141-ec8c-5604-942d-b6b72faaabbf | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average 98%) of MDD
a847bebf-1df1-581f-8304-5c4b45e6cdd7 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
1c453333-f6dd-539b-80cc-ae7863c624b9 | note | Verifying Document - IANZ Lab Test Report
1badf2d5-f6bc-57c3-aa6a-c5a45440569a | note | Frequency - 1Test/MH
627ea6e2-0f21-532f-8fe7-6770a74b9623 | note | Verification Activity - H
0d85463d-dab3-51b7-bb97-9b404dff4af2 | note | Verification Activity - By: - QE
f19695cb-1e84-53f4-b841-29cea8a6b257 | checkpoint | 3.15 - Backfill Inspection
d92fe8a3-ca3a-5430-bfc7-b1328efc2f77 | note | Acceptance / Conformance Criteria - Inspection of manhole prior to backfilling to ensure correct installation and that the joints are sealed. Check for any gaps.
0fcf5aa2-04c1-5473-8ae9-cad3834c3bb4 | note | Standard / Specification - Project Specification 4.3
71a08e1e-9f9e-5735-b9e7-974aca4bf205 | note | Verifying Document - Photographs
e1875c14-0f50-58c6-b6ef-352bf1783dad | note | Frequency - Continuous
9dcc647f-fddb-5773-90ea-778339343ecf | note | Verification Activity - S
addfe930-6991-57da-95c7-300e647696b5 | note | Verification Activity - By: - PE
f86664cc-9c9c-55e4-b8f3-2878053f2a61 | checkpoint | 3.16 - Backfill Compaction Testing
0b304461-1592-59ec-8f1c-4adbbf43cc1b | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC Average of 98%
cb84dbae-3878-5efa-8b06-b15858234554 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
97ac4fea-d9c9-5c8c-baba-96f47f0b7fde | note | Verifying Document - IANZ Lab Test Report
7fc73e23-243b-544c-a192-4cf2db61ca9a | note | Frequency - 4 Density Tests per layer at Quarter Points around structure
01211731-cc47-5c7e-9d96-455d5e38e8d5 | note | Verification Activity - H
f79276d6-10e3-52d0-80a9-20e7c5b178e5 | note | Verification Activity - By: - QE
15492269-750f-5fc1-81c3-61be85d71970 | checkpoint | 3.17 - Reinstatement
2d63696d-2d33-5c5c-ac3f-78a5a0fb3fbc | note | Acceptance / Conformance Criteria - Quality Check on New Works
a3350074-8599-5295-b334-b07bdf8c4d10 | note | Standard / Specification - Reinstate and Tie into existing surrounds
0b512309-e2c5-51c7-9586-e8a752f5e706 | note | Verifying Document - Photographs
e23e2bb4-89dc-5278-9fad-10048a6d915c | note | Frequency - Continuous
f3a7a097-a0ac-58e8-ae1b-4c6b265514b9 | note | Verification Activity - S
388eeb85-5232-5b2b-a1aa-fa731eb4176e | note | Verification Activity - By: - PE
84c3283d-24bd-504e-b593-7adb2a662256 | section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
7ae1b87b-673c-5c28-a4bd-4b55b08e4e89 | checkpoint | 4.1 - Survey Redline Drawings
fbbf0793-2870-5073-bdad-313d6c053715 | note | Acceptance / Conformance Criteria - Quality Check on New Works based on the tolerances in RITS
49d8634e-c761-5a02-8077-f2be6dbcbed0 | note | Standard / Specification - Project Specification
8f244533-d06f-5885-b00d-17430dbaf917 | note | Verifying Document - Survey Data As Built Drawings Photographs Red Pen As-Builts including Undercuts
a6bf5a44-50bf-558b-b3b2-a54478fc7244 | note | Frequency - Post Works Completion
fb594479-9802-57fc-aeed-4b92904ad9ca | note | Verification Activity - H
72121a75-77cb-536b-88c1-a40ae647a69d | note | Verification Activity - By: - SV
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
ed4d47fe-2ac6-5236-8f67-d797655b9061 | checklist | Stone Strong Wall Installation Checklist |  | Stone Strong Wall Installation Checklist
8111ace1-1386-5c1f-8290-3df28e3c8d3f | checkpoint-no-value | Details
5c56ea41-624d-5f8b-a19d-09dc67614506 | textbox | Project Name:
19e4224b-ed62-5e46-a533-cec42e4dac20 | textbox | Wall Location:
6d6bf996-b548-5dd9-9ee0-d917dd2be190 | textbox | Block Layer:
e07570dd-33f5-585f-8141-e6b9b1e94af6 | textbox | Date:
3453d87e-9319-54a9-acf6-8e0f2f4739a6 | textbox | Inspector:
0692e518-3045-51d8-be5c-39c62e4d3b14 | textbox | RL of current Block/Backfill Layer:
4505674e-5447-5073-a379-0d8f35b2da33 | checkpoint | Level foundation installed as per design. (Base layer only)
2bac39a4-c1d6-5525-80a3-16ed66d99d29 | checkpoint | 2 x Drainage pipe wraped in filter sock to be installed along the external perimeter of the Load Tramsfer Platform. (Base layer only)
22ed2239-aab5-546f-bcc9-e0ec74750490 | checkpoint | Blocks Installed within specification tollerances & block pattern as per design drawings
0dd331a6-905b-520f-85e7-1d0e1611df25 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
5e72637e-18b2-53de-82ca-d91284388021 | note | Table 4: MSE Tolerances
807cb619-9421-5d28-ab8c-bf2da6ee9b5c | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
e72d7e9e-6340-547b-aadd-a6cedcd6e744 | note | Element ¦¦ Vertical Position ¦¦ Horizontal Position ¦¦ Vertical Alignment ¦¦ Horizontal Alignment
981f8e13-85e0-5ab8-88d3-a29a943532b7 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
3747f6c4-c6b4-53db-b0a0-918d1038abda | note | Soil Surface ¦¦ ± 100mm ¦¦ N/A ¦¦ N/A ¦¦ N/A
02105b15-4ea8-52aa-aa5d-d219414087e5 | note | Facings and wall structures ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
7fb962c8-aa6b-57e4-980c-845ee2b51feb | note | Footings or supports ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
fcdfd4e1-24d9-5e33-b261-4fc8f812ee77 | checkpoint | The correct number & length of parawebs are to be installed as shown on the construction drawings.
d1b9a8dd-3c74-5dd8-92ee-ba464e7bfa9c | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
cb25453d-184c-5806-8454-04709ba3e357 | note | 24SF1.1 BLOCK PARAWEB SCHEDULE
917cf7ae-3f1c-5095-a6af-1e72e4cc8863 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
8e09984d-6f0d-50f2-abb9-cdcc9fa850cd | note | WALL HEIGHT (H) ¦¦ MINIMUM EMBEDMENT DEPTH (E) ¦¦ GRID LENGTH (L)* ¦¦ CONNECTIONS PER BLOCK
571b4987-9d20-5db7-94d0-56578e113fa8 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
cc38ae48-88bf-57fa-ba2d-32f679a79148 | note | 8.0-10.0 ¦¦ 0.5 ¦¦ 9.0 ¦¦ 4
a0f36527-892e-5c8d-868f-3b82ab3d24a3 | note | 6.0 - 8.0 ¦¦ 0.5 ¦¦ 7.0 ¦¦ 4
bd88976d-5723-503a-aab2-1dfe67a9ad8c | note | 4.0 - 6.0 ¦¦ 0.5 ¦¦ 5.0 ¦¦ 4
31674d68-f150-5e7a-abb3-b80d5b50c9a3 | note | 2.0 - 4.0 ¦¦ 0.5 ¦¦ 4.0 ¦¦ 4
2ab1aa36-57c5-574a-9159-853a9471fcc3 | note | 0 - 2.0 ¦¦ 0.5 ¦¦ 3.0 ¦¦ 4
fe80ffe6-11b3-5d48-be0b-c197bef3527b | checkpoint | Paraweb is to be placed flat or with a 1% fall toward the rear of the wall.
21d51e76-0781-5346-b566-b7bce9497e97 | note | ○ Paraweb must be free of wrinkles and lightly tensioned prior to and during placement of backfill. Shallow trench to be dug toward the end of the paraweb, pin to be used to pull paraweb taught prior to backfilling.
832e8ada-908f-5d9d-b4cc-de453519845d | checkpoint | 150mm of fill cover is required before construction equipment can travel over the area
6ab944f4-d273-5d6c-8a46-732a9623d2d4 | checkpoint | Backfill installed in max 250mm lifts
c45a62aa-67ef-5b63-8eac-3b92c5fd4b32 | checkpoint | Proof roll completed on each layer
695e7135-67e3-5ce3-9b13-f83c454af3ab | checkpoint | NDM testing completed
313e95ff-a74a-5cd3-aca0-96fdfe23b44f | note | ○ Acceptance Criteria: Minimum 95% MDD
18e05c73-4c1f-5444-a747-bda68ed498d4 | note | ○ Frequency: 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
2db75228-7d56-53b8-9b70-8668d7b842e2 | checkpoint | Clegg testing completed (GAP65 only)
1fa82988-8f1e-568e-9501-5d1fa85b3509 | note | ○ Acceptance Criteria: CIV relationship to be developed by testing alongside NDM tests
6aadb3eb-b399-5f77-82e1-875f5b6abe9a | note | ○ Frequency: 4 tests per NDM
8a9629a7-279a-5245-a13c-778a8306e9e8 | checkpoint | Scala testing completed (Sand only)
de471c65-92b2-5be9-8242-ab26586fb500 | note | ○ Acceptance Criteria: Minimum average value over 5 tests of 5 blows per 100mm, minimum single value of 4 blows per 100mm
0d72fa89-8dc8-5a3d-9dd5-e8a34b2db867 | note | ○ Frequency: 1 per 500m3, 1 test per 0.5m lift per 20m run of wall
d8586420-2bca-513a-96de-6d79dec8d9de | checkpoint-no-value | ADDITIONAL NOTES:
81dd5416-d172-51ad-8781-a20c3ac7e029 | textbox
0e5b9b66-1896-593a-9a14-48e0c0a77d05 | checklist | SYS - AREA 1B CH1740-CH1990 PAVEMENT DRAINS |  | AREA 1B CH1740-CH1990 PAVEMENT DRAINS
8c9335a7-3af5-5e47-a887-39a89ff08c27 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
eef00716-4e5d-5b03-b172-716ad54d042a | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
765b1048-c088-5b6f-9623-8c5346ff99e7 | note | Standard / Specification - Downer
397a1e6d-4464-5f66-b1bb-bdf001298e8b | note | Verifying Document - Construction Pack
05d4a935-0ef3-5cde-80aa-4d1301943a80 | note | Frequency - Submit 10 days prior to commencement of works
eac0916a-6ddb-5a54-949e-98cefbbc2210 | note | Activity - H
806a65ec-353e-5e0d-935c-204f576001c3 | note | By - PE
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
180417cf-f085-5ace-9953-f519ccf1706c | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
96347aea-037b-5640-95a4-1d4dfc132a6e | note | Standard / Specification - Downer
16eacf5e-a788-546e-a0cd-1aedc5ee8570 | note | Verifying Document - Survey Records
be32c357-44f6-529a-8363-67b4f3529304 | note | Frequency - Prior to Works
c4af63f6-c85f-59f1-809e-59bc586c641c | note | Activity - H
f104ef54-18ca-50f8-b622-564b36e5dd3e | note | By - SV
7b8b4071-ba18-54c4-a07c-9e192aec85d8 | checkpoint | 3.01.03 - Approved Construction Drawings
c494c038-e47d-5ce7-b618-58b9f20e4c67 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
c6ecdd42-653b-5c87-9072-43a0eadf906c | note | Standard / Specification - Downer
4e3ba869-ecd5-51a9-8e80-40f8a3e0199e | note | Verifying Document - IFC Drawings
988c6302-1576-5fe0-ad37-e6e63e58da1e | note | Frequency - Prior to works start
4d176dba-b452-553e-a533-5a82796a3ab1 | note | Activity - H
526d4aa1-d98f-5698-8a92-deeccd5de232 | note | By - PE
f54e7b48-3f2b-51d6-93b0-54755388f0cc | checkpoint | 3.01.04 - Topographic surveys for measurement
f927db23-c857-5010-bccb-337cc5a5dab9 | note | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
91b1b8ba-eb23-5cb1-89e8-90e6c32ba274 | note | Standard / Specification - PS 2.2.12
795d7fbf-075a-5c81-8f14-b524bc83a870 | note | Verifying Document - As-built
8e12b724-0f78-51b2-bdef-fa392fd5d083 | note | Frequency - Prior to works and Post Works
46002215-7271-508f-b388-aa1c2f73fb15 | note | Activity - H
a41ac510-4c8f-5101-a059-58a692208e38 | note | By - PE
f26fef48-d615-5889-ba64-e206f54c0d34 | checkpoint | 3.01.05 - Permits
22e6ad25-092d-5548-a2d8-51e8a1593b0a | note | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
409b7359-80e8-5acc-9198-5d34ac52ec2d | note | Standard / Specification - ITP Register
1f3e89f2-4480-5fe8-b063-4a578a27d691 | note | Verifying Document - ITP Sign Off
ad52a87c-f310-5834-bdc5-abb31ce9ac1e | note | Frequency - Prior to commencement of construction activity
5eb73539-c018-532f-b744-52ab274ca51f | note | Activity - R
a7fc22a5-8f14-5766-918d-63b3cecf0195 | note | By - SE
72a761a8-8bee-5916-91e9-a2f4ef42bc73 | checkpoint | 3.01.06 - Stakeholder Management
6772a3a5-74ae-5849-b0e0-b36ea6baf81f | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
435660c9-5625-5888-837f-0a6f88ce611a | note | Standard / Specification - Project Stakeholder Management Plan
58ea1067-5df3-58c6-9b10-edbf2c8e408c | note | Verifying Document - ITP Sign Off
74cc34a4-f0aa-5202-9a03-dd52ea46867e | note | Frequency - Prior to Construction with continue updates throughout the works
89dcf2fb-9078-588c-aaa1-bf271fd79ee4 | note | Activity - R
96a554b1-43eb-5bc7-8a17-143409cfd62e | note | By - SE
8ec62109-1664-5fbd-8086-47c125cee66d | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
08534115-94ee-5cfc-be8c-086ea7ffdd06 | checkpoint | 4.01.01 - Subsoil Pipes
6d376193-63a5-5f57-8e40-316e71973266 | note | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 100mm diameter complying with NZTA F/5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
34ad6500-373e-5051-9826-4a1d20223e96 | note | Standard / Specification - GWS 3.2.1
bc934418-5005-5ef9-bd0e-73582085601a | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
84cc8e48-b25d-50dd-b493-0872459f881f | note | Frequency - Every Delivery to Site
4d7be173-4c31-5cd2-8ec4-6235ebf15736 | note | Activity - C
c58e9fbc-5f93-5b00-8e1c-6ccd13b803d9 | note | By - SE
71011ef5-31e0-5d97-b246-1d11311696c1 | checkpoint | 4.01.02 - Subsoil Drainage Aggregate
fcc12b20-cca2-512b-a937-1f951a99ded4 | note | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/6 including gradings (40/20 aggregate). Be open course grade clean durable aggregate, Have a crushing resistance of no less than 100kN when tested in accordance with NZS 4407:1991 Test 3.11 Meet the following gradings when tested in accordance with NZS 4407:1991, Test 3.8.1: App B - HAM2018-0136AJ Rev. 1 Geotechnical Works Specification: Table 2: Filter Material Gradings (Geotextile Wrapped Aggregate) Test Sieve Aperture (mm) Percentage Passing (%) 53 100 13.2 10 (max)
fa485186-b96a-52c9-9058-24ec2e833fe9 | note | Standard / Specification - GWS 3.2.2 & 3.4
061ef45c-ffd4-58e4-87df-e8fd7f8adeb1 | note | Verifying Document - PSD, CR
b8c5182b-9ee9-5d26-aedc-1ebac092ca1b | note | Frequency - Material Tests every 1000m³ or change of source. Visual inspection every load, verifying document photos of material onsite, if visual appearance changes, additional testing will be required.
c09d35b2-6d0a-5e65-8a73-0442d1581335 | note | Activity - C
8aeb1063-a1e3-53e1-bd84-41c3848cad13 | note | By - SE
6d7192d6-9061-5d38-a315-d4a8752b3fa5 | checkpoint | 4.01.03 - Filter Cloth
4d00d963-e5b2-5ec4-bdbe-7b83a09ad16d | note | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings. (A14 Bidim or Equivalent)
3dbf25b6-cae4-5c3a-8e05-2898bf99e521 | note | Standard / Specification - GWS 3.2.3
c126941f-b768-5b30-ae2e-6798b6457186 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
4c219803-133a-5171-bab3-8ae8749045f5 | note | Frequency - Every Delivery to Site
54eaf21a-b3ea-5116-b8f4-0d0045c266e9 | note | Activity - C
b5976aef-6260-5629-816e-6e4bacaedafe | note | By - SE
34efbf28-65bc-5d1f-b72b-f1491def807a | checkpoint | 4.01.04 - Securing Pins
d845c3e0-ef7e-5b4e-838b-d83b5a360f76 | note | Acceptance / Conformance Criteria - Pins for securing the geotextile shall be of steel, a minimum of 5mm in diameter and at least 400mm in length
8521468b-b01b-5e26-93aa-3e63694682c7 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class,.
24f277e3-b638-5d86-91c5-3dd99a8884dd | note | Frequency - Every Delivery to Site
335ffb25-ee69-51f3-a9b7-28e2ed59402a | note | Activity - C
9c92a1d5-c2c7-544b-8af9-16d4f18d2241 | note | By - SE
f4713bb7-3aea-5dca-b516-69272c0b56ba | section | SECTION 5 – CONSTRUCTION ACTIVITY
113d79bf-1485-508d-814d-8c7c8c221530 | checkpoint | 5.01.01 - Filter Cloth Wrap Inspection
6811ea07-5a89-50d9-81a0-240052de7a0d | note | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain. TNZ F/6, PWRBSS Geotechnical Specification - The geotextile shall be placed in the tench so as to conform loosely to the shape of the trench. Cloth must fully encapsulate the aggregate. Geotextile longitudinal overlap to be minimum 300 mm (as indicated on drawing 3051 and required by NZTA F/6). Additional sheets to overlap by minimum 500 mm and anchored with securing pins (F/6 requirement). Verifying document, photos of trench prior to backfill, every line.
ec53cdb7-cc25-54c6-b78e-5e162d0a5055 | note | Standard / Specification - GWS 3.2.2
4fcd2436-ca61-55b6-9fe5-fe0251ec6f08 | note | Verifying Document - Every line
5b1a35ef-fdc0-5fab-867b-ab02e3ba5f75 | note | Frequency - Photos of trench prior to backfill
e8addc07-99ec-5073-b4b5-509d0438c645 | note | Activity - HP
36b45a2b-5f18-58e7-9e19-1aeca008b0c0 | note | By - ENG
a2a25648-08b8-5ac9-b1a6-269e329744a0 | signoff | AUTHORITY HOLDPOINT
543c766a-67a1-5508-b12a-a4f69b9927f3 | checkpoint | 5.01.02 - Trench Backfill
5a6ef704-1262-5cee-8cd3-1ca88e235869 | note | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard of the material previously trenched through. Drainage aggregate to be placed in layers of 150mm or less. Only light compaction such as tamping with the back of an excavator bucket is to be applied.
3948db19-ece7-585a-af0f-11b4d7488df2 | note | Standard / Specification - GWS 3.3
d255d60e-c712-5220-9d3c-cb1bb86d98e7 | note | Verifying Document - Site Record
facea8de-cba0-5eaa-81b6-121bf1de9fe3 | note | Frequency - Each trench
cfd6590f-8894-55b7-86ae-a17a69dd2407 | note | Activity - I
7c6101e5-bd07-56fa-a1d6-fc30d486d76a | note | By - SE
f7142f9b-2009-59fd-9453-67a19dd7865a | checkpoint | 5.01.03 - Drainage Outlets and Inspection Points
e0e0dfdd-c152-5d0c-9412-91a6bd87c0fb | note | Acceptance / Conformance Criteria - At least one temporary flush point is required for each subsoil drainage system to enable flushing of the system once the earthworks are complete.
bc1e3839-cba4-575f-a42b-a8f7f6333d04 | note | Standard / Specification - GWS 3.6
af9a4333-12f2-5026-b386-959aed450a8a | note | Verifying Document - Site Records
f4c8e8e7-af68-5172-8727-d91b9dd9213b | note | Frequency - Each Subsoil Line
d5c01f6c-5dd3-57ae-a617-02ae9b57ca57 | note | Activity - I
aaed1beb-c26a-539c-a9dd-5c85e83ad979 | note | By - SE
fd83d42b-b8ea-5d41-8883-9e6215d99eea | checkpoint | 5.01.04 - Subsoil Flushing
8d739b34-85cd-547a-8247-18cc3b18c86b | note | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer.
1d5f0a20-d2df-5e6f-b48a-0e7cdb078918 | note | Standard / Specification - GWS 3.6
4beb6424-e2fd-57df-a7c9-4d3712506bf3 | note | Verifying Document - Site Records
5719ebbd-4e3f-5c51-a425-06bc997661d4 | note | Frequency - On completion of earthworks
f9a6100d-206f-59c5-b591-faca25ca1a54 | note | Activity - HP
41c18113-5b1c-5d8e-8d40-7bff82d6cc82 | note | By - ENG
efdabe6e-46f6-51c4-9707-34eb23acdd0d | signoff | AUTHORITY HOLDPOINT
65ee871c-3fae-5bef-8ed1-f015a6f0c4aa | checkpoint | 5.01.05 - Survey
73f805ec-1be1-5740-aa84-faa7472fe6ac | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
719cc0d7-da0b-50cf-b857-21dac2d03368 | note | Standard / Specification - Downer
80ec50c7-3501-5099-aad9-d3107d575a5b | note | Verifying Document - Records
38279792-2520-5b5f-ad7e-c1d3dde7b3a6 | note | Frequency - Post construction
9dcc6c76-d7ee-5853-8a71-9bc96d68aa03 | note | Activity - H
0123bb12-7443-55a7-be46-bb5296d14b9d | note | By - SV
f999ffd9-5367-57d7-994f-8ff2006b1339 | checkpoint | 5.01.06 - Excavation
4f174c16-c79f-5a5f-bc71-b199753d4ed3 | note | Acceptance / Conformance Criteria - Trenches shall be cut in such manner as will ensure that the geotextile wrapped aggregate pavement drains, and pipes if included, will be laid true to the depths, grades and lines shown on the drawings
c2c9c1ae-73f5-5d4c-8575-26ff0a4b5f5a | note | Standard / Specification - Downer
6cf18612-24aa-5169-8377-5ee893f5aafa | note | Verifying Document - Records
050f8690-1a18-59af-a187-0ae929cb0cd6 | note | Frequency - Prior to laying filter cloth
59222acb-af43-5e0d-a2a8-9d1ecc17b8de | note | Activity - I
f93a0bce-6383-52de-b82c-c023bba5a452 | note | By - SE
78b40005-4535-58a0-8f12-10ce7328ed62 | checkpoint | 5.01.07 - Bedding
2876f6cf-4450-58ef-a4e2-7e7506c0a1eb | note | Acceptance / Conformance Criteria - TNZ F/5 - Bedding thickness shall be no less than 100mm
8da47c77-5900-5d5c-939a-24a45d93b9c8 | note | Standard / Specification - Downer
e1e57d95-3cfa-5486-9252-177719884e87 | note | Verifying Document - Records
99282874-7427-5646-80c4-cf2d5c909736 | note | Frequency - Prior to laying Novacoil
1cde5baa-6f9e-594b-a1a1-92fe408db88b | note | Activity - I
dec6f213-96b0-5480-b5d3-821cf0ca163b | note | By - SE
bc02362a-9ac4-5773-899f-55a42641ec6b | checkpoint | 5.01.08 - Joining Pipes
0ef64d31-9581-5189-b3ad-fac7edb017e9 | note | Acceptance / Conformance Criteria - TNZ F/5 - Joining the pipe shall be done using a purpose made pullout resistant coupling in accordance with manufacturers recommendations
def28e6a-7bc3-51ba-a899-fd9dc500b9c1 | note | Verifying Document - Copy of delivery dockets, photos of pipes onsite with tag showing class
260824f4-3576-52b7-a7c0-82ca028678f3 | note | Frequency - Every join
d30d276f-a5c3-59dc-887d-a339a38e82d2 | note | Activity - I
532c1d45-176c-5ea0-83bb-5e82f111d571 | note | By - SE
cd33a7f8-9b6c-5422-93be-dcae98eaa460 | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
abaa7cc7-67ff-52ad-ae9f-e9176b336a01 | checkpoint | 6.01.01 - Construction Record Compilation
41282f40-d6cb-5103-bf6e-958dd729ff05 | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
dd7a487e-b81d-579c-a71f-0077755339d5 | note | Standard / Specification - Downer
1b01aacd-4fa9-5e67-bcee-f13a4f84057c | note | Verifying Document - Records
93c49c84-ab62-5d90-b6fe-8220b0513eb4 | note | Frequency - Post construction
443d80b3-29dc-5bc2-9371-f8aa81bb76cb | note | Activity - H
24d1b142-e483-53ee-b2e7-c01e05550ac7 | note | By - SE
f4876821-e136-54ca-95e8-27fd0f400f5d | checkpoint | 6.01.02 - Survey Records
3989569f-afea-526f-b341-32ff9a57d0a2 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
efdca4bd-743a-5bae-a775-15a6dc53a42e | note | Standard / Specification - Downer
13d9852a-104e-5ddd-a414-a0b3c8436476 | note | Verifying Document - Records
0fddb792-cd96-5f76-99a6-ec5d92f65f44 | note | Frequency - As-builts taken every 10m prior to backfill
bd9d5d94-7a2f-5dc0-b4ab-68c25b7e617c | note | Activity - H
03d57b79-a84e-5ad6-8f79-e3d9e35c407c | note | By - SV
a7ece1a0-6b4a-5d51-8813-156cc41a337a | checkpoint | 6.01.03 - Redline Drawings
09d83736-3d59-5664-876d-9b1e1a8010df | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.To show all subsoils, including temporary subsoils that become part of the permanent works, to show all outlet locations
183aab9b-8a98-55b8-a516-5e4f702ae200 | note | Standard / Specification - Downer
f64d0f7d-04c7-5770-8bad-bc787444a8e3 | note | Verifying Document - Redlines
fa0c06a6-38af-5efd-adbf-da3e7ed08767 | note | Frequency - Post construction
62ca144a-fde4-5465-929a-b048f4828032 | note | Activity - H
e5945e0b-7d3d-5ef9-a8bf-da45d937a369 | note | By - PE
406cc900-58d1-549c-813d-cb4c75c9a2be | checkpoint | 6.01.05 - Photos
36a80c93-c9dc-55ff-b483-5aa242fff911 | note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
01466be1-a2c6-517a-8f95-3cd5e3a2c397 | note | Standard / Specification - Downer
05d2b333-6235-5b98-a18f-eaa87e514051 | note | Verifying Document - Photo Records
4b223c81-de6d-5f09-96b9-2a7a39248c1b | note | Frequency - Post construction
66ef3d51-81b5-513d-9327-50fbd4284aae | note | Activity - H
ddc4612f-097a-5490-aa75-735a94bdffde | note | By - SE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
3d7d34df-c3a3-5e74-a954-495e57e1c8d5 | checklist | SYS - AREA 1B CH1740-CH1990 SIL |  | AREA 1B CH1740-CH1990 SIL
3969119e-9d77-5427-b958-ecc82f083c46 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
4b26e7cb-ace0-58bb-a616-39483fc6b83d | note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence
39bdd60b-5a55-5725-9d44-67dc819f7e82 | note | Standard / Specification - Downer
f37b21b6-fe75-518e-99e7-441bb2e54568 | note | Verifying Document - Construction Pack
e20b4b8a-d1f3-5800-add6-1b620896d23b | note | Frequency - Prior to Works
2c256560-e7aa-55c9-98a1-86938a36f071 | note | Verification Activity - H
5aa00b7c-8cab-5b58-9c8a-a8ebcd4457f9 | note | Verification Activity By - PE
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
e3e94e95-7461-5602-8ae5-1f475a9a9372 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
a9ccfcea-23ab-5f83-98aa-01aa55f14f09 | note | Standard / Specification - Downer
bd924ba3-e98a-5a37-88f8-deb39c1915c3 | note | Verifying Document - Survey Records
21d5543a-b500-5bb2-b23b-7150daaf8fee | note | Frequency - Prior to Works
8155419d-e2cb-5987-8b90-4a5df3da5317 | note | Verification Activity - H
651d4ceb-5a87-5cee-aa2f-1d5af93f48ca | note | Verification Activity By - SV
a24a2c58-bf6f-5474-883c-40044bad1fc7 | checkpoint | 3.01.03 - Service Location
beea7a1c-046b-5fb7-91cd-46b86eb7ecfd | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
8c0340ae-3f3f-57df-8af6-8836db439d12 | note | Standard / Specification - Downer
eaababd1-32a0-5323-ad8b-8e999dafd51d | note | Verifying Document - Excavation Permit
558c19e0-5e33-5b6a-a931-c34e81e92a2c | note | Frequency - Prior to Excavation
85387089-5afd-5a2b-974f-78eb26637df0 | note | Verification Activity - H
33484b60-704b-5d44-8ca8-0d2f7803fb57 | note | Verification Activity By - SE
0a214a7a-124a-5898-a837-e29e83751df0 | checkpoint | 3.01.04 - Internal Permits
24c5b6b2-98a4-589a-a0ad-fa73c558e90d | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
f1ead7c5-425d-5829-b8d1-0edd0ebada26 | note | Standard / Specification - Downer
7bc080ae-d60d-55ed-9e48-c9efb7f6d7ce | note | Verifying Document - Internal Permits
f051067e-abc8-58c0-96b0-6932e794b31d | note | Frequency - Prior to activity being undertaken
518ffaca-a960-5750-b6b8-c85a4e56025c | note | Verification Activity - H
cfe1cce4-c9a2-53b0-9062-99d2666b7ccb | note | Verification Activity By - SE
917e2881-0901-542f-ae25-686bf9c47009 | checkpoint | 3.01.05 - External Permits
b2e25bb1-ceae-59ce-be7a-ac0fa86efbac | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
26281c77-fff7-5dd4-88f3-7e33e61e9cbf | note | Standard / Specification - Downer
fb232d0f-a63d-56c9-8cef-c489fe97494c | note | Verifying Document - External Permits
9e657bb1-bd49-5ffa-98e1-3b2ad9d187b6 | note | Frequency - Prior to commencment of activity
8037d5ba-0dd4-5d90-9102-4cba9dadd771 | note | Verification Activity - H
62198747-f56f-5a64-8a05-cde299bdfa49 | note | Verification Activity By - PE
a1302970-0389-558d-b43c-67b14bbfc27a | checkpoint | 3.01.06 - Approved Construction Drawings
bb46b8a2-0124-5764-b4dd-7bdf0e69e95c | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
f9faecd7-6ccf-5952-87fc-e7dc6b36747a | note | Standard / Specification - Downer
030bf603-8060-5f9d-9f7a-d5e4d6516677 | note | Verifying Document - IFC Drawings
73c5b094-94c7-5167-9ef9-037fd27c4209 | note | Frequency - Prior to works start
cefe589e-775b-5225-b22e-07aa1e40a577 | note | Verification Activity - H
434a1998-8714-52c5-bd16-87cddbd9fb72 | note | Verification Activity By - PE
5fe0af18-de1c-5a52-a24a-6d199c43ea87 | checkpoint | 3.01.07 - Previous Layer QA Sign Off
6983331f-cd49-553d-9d1b-2fb72a289629 | note | Acceptance / Conformance Criteria - All Previous layers signed off, QA complete. Including subgrade, SW, WW, WM. Ensuring everything up to the bottom of SIL is compliant.
915f2668-b583-53ab-a791-7764dde86a86 | note | Standard / Specification - Downer
77414674-0ef9-565c-bd1e-9e79630527df | note | Verifying Document - QA Records
f3a3f4b4-c411-555b-86c7-ecf46bcdf601 | note | Frequency - Prior to works start
c6466e5e-b003-544d-bb6f-6a7c079699e2 | note | Verification Activity - H
e1d16e4b-df18-54d6-933a-5129d5ba5833 | note | Verification Activity By - PE
f235ea97-6575-526f-981f-e1d053fa1d5c | section | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections)
7d5180df-d4eb-55e4-af4d-0e923a86f4b9 | checkpoint | 4.01.01 - SIL Inspection
589c641a-aa63-5852-9ee0-74bb69e89f17 | note | Acceptance / Conformance Criteria - Prior to placing of sub-base pavement, to include proof roll, inspection of extents of works, general shape, and tidiness, free of organic or contaminated material, review of Benkelman Beaming of the SIL and final levels.
63d5d160-5d5e-5d1c-8f98-de84fd1bffb8 | note | Standard / Specification - PS - 2.2.16
c3cb4613-e4f5-5cfc-b1af-22f8b68c2820 | note | Verifying Document - Hold Point Release
c154df35-5954-5684-b09e-81eb77940267 | note | Frequency - Min 48h Notice
af005a20-54f3-5277-886e-7af9e988939a | note | Verification Activity - HP
18fb0707-f3d9-5d50-af1f-10287369254f | note | Verification Activity By - ENG
22c63970-dca6-5fd1-8231-ea707288aa18 | signoff | AUTHORITY HOLDPOINT
62f939d2-18c6-5474-abaa-4e5cecc5daba | checkpoint | 4.01.02 - Subgrade Inspection
ccdd5453-ce4a-5556-99a1-e628c9df66ef | note | Acceptance / Conformance Criteria - Proof roll, Scalar penetrometers, and shear vanes prior to SIL fill commencing
4bc1e182-7aa8-55c3-b605-7ac285d42607 | note | Standard / Specification - PS - 2.2.16
d3d56a58-b3ff-5de8-80eb-b959f7028b02 | note | Verifying Document - Hold Point Release
daf11b30-c8b1-541a-9e0a-1f48878bd249 | note | Frequency - Min 48h Notice
3f765b21-ec87-5fc9-b2c0-516f6ba42d38 | note | Verification Activity - HP
54909fee-8367-537a-913e-c78a0b548259 | note | Verification Activity By - ENG
7ad2b75a-44c0-5e3d-b3c3-e0084f7839d0 | signoff | AUTHORITY HOLDPOINT
b3826b6c-de4b-591c-a488-5e8079ba2150 | section | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 Subgrade Materials
fcd729d9-871b-5ce2-b7a9-fc012a97901d | checkpoint | 5.01.01 - Pavement Subgrade CBR
b3e03a0d-8900-51ac-be82-923b82921d09 | note | Acceptance / Conformance Criteria - The pavement design requires a soaked CBR of not less than 10 within 1.0m of the bottom of the SIL layer and 4x DCP's to a depth of 1m below subgrade level in a 1m grid around the in-situ CBR test location and 4x NDM's DT with a probe depth of 300mm in a grid around the in-situ CBR location. CBR testing of the subgrade shall be carried out by the Contractor prior to final trimming. If the soaked CBR is less than 10 the Engineer may instruct changes to the pavement design. (Push tube for Cut and Filed sample for Fill). Invitation for engineer to witness CBR testing. To be accurate representation of site
8bc2d425-ceb7-5734-bb77-d28559cf4dd1 | note | Standard / Specification - PS 7.1
7a8b0934-9135-54fb-b2a4-e6b80a154256 | note | Verifying Document - IANZ Lab Reports
1086e7dd-eabe-514b-87d6-33b88e67f9b1 | note | Frequency - One test per 2,000m2, with a minimum of three tests per material type.
d8f0f437-a191-57db-ab63-ab5fa84405d2 | note | Verification Activity - HP
07eb9ac4-2f53-5c6b-9ec0-d3b5327d7a95 | note | Verification Activity By - ENG
93c1095a-43a9-5d7d-be8f-7a7cdce201a4 | signoff | AUTHORITY HOLDPOINT
fac294aa-8548-5fc8-bb58-2088ac62dc7f | section | 5.02 - SIL (Clean Pit Sand)
75e3c18b-3bc3-5384-a690-0b943edb28e2 | checkpoint | 5.02.01 - SIL Conformance
7b7cbf9c-e8ee-5e03-b9c4-19e9defd7ac5 | note | Acceptance / Conformance Criteria - The SIL shall be pit sand meeting the following requirements: · 4-day soaked CBR (NZS 4402:1986 Test 6.1.1): Shall be ≥ 30. · Organic Matter: It shall be free of organic matter. · PSD (NZS 4407:2015 Test 3.8.1): Shall be <7% passing the 75μm sieve.
ab9dc707-18c8-576e-aaac-433561430047 | note | Standard / Specification - PS - 7.2.1
68faef9d-392a-59d7-bcaf-6fa1bc1f1e4f | note | Verifying Document - Lab Reports
c4fedb90-397f-5d70-8393-ddd5f80bc3ef | note | Frequency - CBR and PSD testing shall be completed at the rate of 1 test per 2,500m3, and being no less than 1 test every 3,000m2 (placed).
2aa170d9-fa30-5034-aee7-9c13a2cf0362 | note | Verification Activity - HP
ff1df35a-76b1-5238-93f8-cfc823b7b0f1 | note | Verification Activity By - ENG
d189a4e6-f601-5569-9fc1-1d87e656f0fe | signoff | AUTHORITY HOLDPOINT
e318ec15-f915-557b-9af7-5c5cf6c32ccc | checkpoint | 5.02.02 - SIL Maximum Dry Density & Optimum Moisture Content
a27e8fb3-c719-5968-a595-666a016a330e | note | Acceptance / Conformance Criteria - The SIL shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density & Optimum Moisture Content
9401944b-e210-541c-9a33-a939c9d05c3e | note | Standard / Specification - PS - 7.2.1
008a0244-1f95-5a7a-9e8d-80305a50d1ed | note | Verifying Document - Lab Reports
05358614-5f37-5794-981b-b6ef430b82c7 | note | Frequency - 1 test per material type and no less than 1 test every 5,000m³ (in place)
0e569234-ac64-532c-a6a1-d7a30e8d6b76 | note | Verification Activity - HP
73f1f2dc-3ee4-55d4-a027-2e6d2c716e44 | note | Verification Activity By - ENG
efde04cf-22a7-574a-b477-9b8b7846f4a8 | signoff | AUTHORITY HOLDPOINT
5c6bf488-9018-5698-aa4c-b7cc685e8eb0 | checkpoint | 5.02.03 - Plateau Density Test
4d47d092-b781-5579-afbe-d0a041d3ac9d | note | Acceptance / Conformance Criteria - Compaction shall be undertaken using the higher of the two density targets. Plateau tests to be spread out evenly to be an accurate representation on what is coming into site.
3646b1f1-33f8-54ed-978d-3519e10c9441 | note | Verifying Document - IANZ Lab Reports
292f8656-46b5-5e25-9d81-b6c1be49f298 | note | Frequency - 5 tests per 10,000m2
cf700307-c8b6-5b85-8348-1951da8bab5f | note | Verification Activity - C
c2e994f8-60dc-5a5e-808d-82e1602f55ad | note | Verification Activity By - ENG
1cba0748-82d5-5f8d-9319-32091b6769d0 | checkpoint | 5.02.04 - NDM
a65fdecb-7522-5aef-8f72-c9c72775f831 | note | Acceptance / Conformance Criteria - Mean Value ≥ 98, and Minimum Value ≥ 95. All NDM testing shall be undertaken via Direct Transmission method at 300mm probe depth.
737f32a6-ca14-58fd-aea3-8aff714c61e6 | note | Standard / Specification - PS - 7.3.1
e55891f8-d0de-516a-b9c8-54ad6ca789e9 | note | Verifying Document - IANZ Lab Reports
df80991c-456f-5a22-94b9-66aea17bf2ea | note | Frequency - 5 tests per layer per 1,000m2
ddeea918-5e1e-53c5-bdb0-567b4a7edd31 | note | Verification Activity - C
fa4e54ea-eb3c-5011-b31b-85f88f881e0f | note | Verification Activity By - ENG
5c910787-b40b-5937-881a-26cc5ec60151 | checkpoint | 5.02.05 - Benkelman Beam
f1e57e77-c46f-5c32-a4b7-5c36a4a04f61 | note | Acceptance / Conformance Criteria - Target Benkleman Beam deflections on the top of the SIL layer are 1.6mm (90th percentile) and a maximum of 1.8mm
4f236964-6a78-58bb-a2ad-29ca204c836c | note | Standard / Specification - PS - 7.3.1
9af0f383-b583-5491-8e2a-112b9bbfe9b3 | note | Verifying Document - IANZ Lab Reports
f7a61f4b-00fa-5389-858d-3782c067994b | note | Frequency - every 10m of each lane – staggered between left and right wheel path.
70f2fcc9-b04d-51bc-a428-0e43ad15a03b | note | Verification Activity - C
e7ad119b-d74a-5d5c-b2d6-3a42d6de70a8 | note | Verification Activity By - ENG
937d3289-52f9-5ac5-8c90-59cd2914799d | checkpoint | 5.02.06 - Organic Material
b3e67920-8037-5400-8c1c-642e5ee8991f | note | Acceptance / Conformance Criteria - Ongoing visual and physical inspection for any roots/organic material, photos of clean sand, and any organic material removed.
a0c385bf-bf9c-5c1c-ac4e-583139a2d735 | note | Standard / Specification - PS - 7.3.2
936b6251-f4a7-5a3b-bf3c-24cba6f93080 | note | Verifying Document - Site Records, photos of clean sand, and any organic material removed
db82440f-7ec5-5382-8705-2ae2bae059b1 | note | Verification Activity - I
b5079f59-52f0-5920-ac35-007512183c86 | note | Verification Activity By - ENG
c269ea2a-2959-5cb8-b76b-38dd023d527b | section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.01 Construction
9b03c2bc-c48f-5466-8d4c-04b6d0c3c01c | checkpoint | 6.01.01 - Subgrade Prep
3314eb0a-8401-58d3-a782-af26e847ee14 | note | Acceptance / Conformance Criteria - The subgrade shall be prepared in accordance with the requirements of the Geotechnical Works Specification in Appendix B, including proof rolling, Scala penetrometer and NDM testing at the specified frequencies.
4832cdc2-16f0-54fb-b9f5-b13fd4db465b | note | Standard / Specification - PS 7.1 GWW
4d5bf8ee-a1ae-53dc-83a1-b890969d9705 | note | Verifying Document - Completed Earthworks ITP
81025f5f-e79f-5ae5-98f3-223c68ae7b80 | note | Frequency - Prior to Pavement Works
08eae87e-fbb1-52e4-abc1-c936b9f15f93 | note | Verification Activity - HP
531c5d6a-0940-5478-b658-d32ba101608b | note | Verification Activity By - ENG
e2d45569-ffc7-5edf-af41-be24dc51077f | signoff | AUTHORITY HOLDPOINT
565e4230-204c-5dff-9c26-c4b4d7ec8e26 | section | 6.02 SIL (Clean Pit Sand)
db9fd37d-3155-5bfc-a59e-7698b9c5a10b | checkpoint | 6.02.01 - SIL Scala Testing
dcff1fcc-0468-5c64-97ec-07f5bb15626e | note | Acceptance / Conformance Criteria - In addition, the SIL (tested in accordance with PS Clause 7.4 below) shall achieve a Scala penetrometer blow count no less than 10 blows/100mm. Depth to be 1.5m from top of SIL.
4163e9ea-e5a1-5798-9f16-4efc158777b9 | note | Standard / Specification - PS - 7.3.1
e34d2610-b9ae-5077-ba99-de1bc7d627bb | note | Verifying Document - Scala Results
9faf4a1c-754c-5fea-ade0-407e75652614 | note | Frequency - 1 test per 200m2
894e4cdf-7c9d-5780-a212-8b8d34c34071 | note | Verification Activity - I
7f61f95f-4eb2-5bcd-b43f-2b57f7050d3c | note | Verification Activity By - PE
e46181c1-7bbf-535b-8314-791da9fafd9c | checkpoint | 6.02.02 - Layer thickness
3f529307-5392-5a66-acbb-081265d82c69 | note | Acceptance / Conformance Criteria - Each layer shall be checked to ensure the required layer thickness is achieved of Maximum
0fa5048b-d270-5ea1-9593-a35fc1bbadaa | note | Standard / Specification - PS - Table 7.2 - 2.2 NZTA B/2
f5c571b2-b56a-5c59-8c5f-481204083b8b | note | Verifying Document - As-built data
5c79b190-c473-5a2d-9a81-4b6cf4384c9d | note | Frequency - 1 test per 20m
940c333f-fade-574e-82a7-6ece487ed079 | note | Verification Activity - I
da0419c8-3af1-55d4-a644-463ad1be3e53 | note | Verification Activity By - SE
1e0af15d-264a-5748-b80e-858ba1933f81 | checkpoint | 6.02.03 - Plateau Density Test
20cea371-9a84-570b-8d74-aa280094c8ab | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. Plateau tests to be spread out evenly to be an accurate representation on what is coming into site.
0aa05dd5-ffc9-504e-9a7c-60990433443a | note | Standard / Specification - PS - Table 7.2 - 2.2
51fc55fa-f4bd-5d31-af32-b4186c256bfb | note | Verifying Document - Plateau Density Report
0118de71-b76e-5cdf-8df4-d9032daf63dd | note | Frequency - 5 tests per 10,000m2
24168a1d-4d75-5639-b2fc-a4cbf8e189ca | note | Verification Activity - I
d016790e-e344-529a-93dd-38a52669b805 | note | Verification Activity By - PE
d963eff8-38eb-5e0f-8cb5-5ca02792d6bd | checkpoint | 6.02.04 - Sand SIL layer compaction
dfb1d2fa-07ef-574d-824b-bdc7ebddb7a7 | note | Acceptance / Conformance Criteria - Further to Figure 2 of NZTA B/2, the acceptance criteria for compaction of the sand SIL layer shall be a Mean Value ≥ 98, and Minimum Value ≥ 95.
80e7f2c7-ef44-58a0-a547-4edbf52dec16 | note | Standard / Specification - PS - 7.3.1
72f78430-a5d7-5df8-88f4-eb2aab833a7f | note | Verifying Document - IANZ NDMS
09a46328-eb63-5bf7-b4b2-789d16cf2ce4 | note | Frequency - 5 tests per layer per 1,000m2 (Min per lot)
aac1ee29-8af1-503f-a4ab-7102ea90cd06 | note | Verification Activity - I
b6d28b73-0c57-5903-886a-50e7c7b030f5 | note | Verification Activity By - PE
b7da25a2-1706-56d9-bf0c-ab152740d6a3 | checkpoint | 6.02.05 - Proof roll
07b326c3-ea68-549d-9128-c3000d49c9de | note | Acceptance / Conformance Criteria - The SIL shall be tested via Proof roll prior to Benkelman Beam testing. Proof roll to be under supervision of engineer and verifying document to be signed off by engineer.
f5e9d4dc-40e8-58cf-a4aa-b27c60255de8 | note | Standard / Specification - PS - Table 7.2 - 2.2
564d8205-b741-54d5-b073-d48e5d67d9c6 | note | Verifying Document - Site Notes
75ed5345-a8b0-52aa-bbc1-534c1cbcdb82 | note | Frequency - 1 test per 20m
e7f0260f-c6f5-50d7-84e5-50a351b4280e | note | Verification Activity - HP
61899164-dfe5-5bc3-b907-b5b068e82afd | note | Verification Activity By - ENG
8aeb4571-3694-52c9-a22e-a9dd129ae2d7 | signoff | AUTHORITY HOLDPOINT
a0785380-fd61-5bfd-8678-a44a68ec5f7a | checkpoint | 6.02.06 - SIL Benkelman Beam test
1474a3bc-5812-5d34-93c3-2a76dbcbc6d8 | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be carried out on the top of the SIL layer at the rate specified in PS Clause 7.4 and reported to the Engineer. Target Benkleman Beam deflections on the top of the SIL layer are 1.6mm (90th percentile) and a maximum of 1.8mm. Performance verification of these target deflections shall be confirmed by the Engineer on review of results from within the pavement Stabilisation trial (PS Clause 7.3.3).
04c2be5d-e694-5630-ae8f-3cd00f7c3b8f | note | Standard / Specification - PS - 7.3.1 PS - 2.2.16
b519543d-4049-5ba0-bd30-397138d05564 | note | Verifying Document - Benkelman Beam Report
2acdff5b-4e24-5f1d-87a6-475ceff0ac5b | note | Frequency - every 10m of each lane – staggered between left and right wheel path. Min 48h Notice
e4b7f0ea-806f-538d-9a07-d162c6b4f901 | note | Verification Activity - HP
62e03724-57d9-548c-9937-de3062eaf727 | note | Verification Activity By - ENG
3c89b0ec-4be3-513e-abf0-367c5d158a5c | signoff | AUTHORITY HOLDPOINT
10f025ff-7251-5430-bf3b-56f5dcf76850 | checkpoint | 6.02.07 - SIL Inspection
add1780d-3465-530b-bd7c-6b3040e3182b | note | Acceptance / Conformance Criteria - Before laying of any pavement SIL and metal courses. SIL inspection to be carried out under supervision of engineer, verifying document to be signed off by engineer.
aaa691c7-ddbd-559c-b7d2-ece1f6df8a75 | note | Standard / Specification - PS - 2.2.16
62109f41-cacd-5114-9387-f25dd7090a0b | note | Verifying Document - Hold Point Release
53749f59-1a97-5155-aa0f-01f9dede2b1c | note | Frequency - Min 48h Notice
8cf9b4d1-106e-5b75-8410-1d614ffa90d2 | note | Verification Activity - HP
c500ca95-c927-5ef8-8063-ff8836fab8fe | note | Verification Activity By - ENG
97bb6f89-11b3-5fc7-a453-48b0f0ec5d36 | signoff | AUTHORITY HOLDPOINT
9e953047-9f70-59b5-9189-aff3fc3bb70f | checkpoint | 6.02.08 - Topography
bb8d94d0-cad7-5b1c-8c9b-72bfccbba337 | note | Acceptance / Conformance Criteria - Carry out level check on trimmed SIL. Survey conformance with Total Station. Tolerance = -30mm +0mm (NZTA F/2).
dfea0969-3fe2-5fb8-b6e2-71a12b4b8f40 | note | Verifying Document - Survey PDF against IFC or similar
c4f76caa-a1e7-5193-a040-20aa641b2936 | note | Frequency - every 1m across the road (avoiding islands) at 20m intervals
9af73578-466b-5e6f-8458-cf20471145cb | note | Verification Activity - I
0f251313-de06-520b-8bad-69923864004d | note | Verification Activity By - ENG
b4bfcba9-7ebb-50d5-ac19-ccbd0eaf5f97 | section | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
8d4e531c-688a-5145-b348-98da13114f31 | checkpoint | 7.01.01 - Construction Record Compilation
e33b7f2d-364e-554c-bbc9-71565eeabdcd | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
02cb16d6-62a9-5c07-b1fd-9212d27af6d9 | note | Standard / Specification - Downer
d5242ce2-72cf-5b1b-93ee-f2289178affc | note | Verifying Document - Records
89f45c46-bd82-5272-9f96-7c18301858fe | note | Frequency - Post construction
e3b23594-8fa7-5800-9495-7772a6d9da38 | note | Verification Activity - H
1f3b92d1-88f6-5192-86a8-d876bfc05b8f | note | Verification Activity By - SE
19dccd2f-6441-5680-bbbb-459afb3e1dd8 | checkpoint | 7.01.02 - Survey Records
09ede6c8-4248-52cc-ab76-a1b266afc9e7 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
64e2281b-04ef-5dd0-a95a-ed86a87e480f | note | Standard / Specification - Downer
c7cbca71-5e4d-5ee2-9c7e-338c155a00cc | note | Verifying Document - Records
6bfdd8a6-0e45-5a32-b543-6abfceba1022 | note | Frequency - Post construction
b936ae2a-5b7f-575c-b00c-96f40edeb440 | note | Verification Activity - H
239d20eb-1cda-5151-8ee0-a1a37fa759ad | note | Verification Activity By - SV
b068bae6-2ef0-5d88-81c8-4fb6749be6b3 | checkpoint | 7.01.03 - Redline Drawings
4d55e902-6fc9-5949-bd90-3718360ae31b | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red line to show any increase in SIL depth.
92347465-5877-5da6-87bb-b262af7857d7 | note | Standard / Specification - Downer
9dcd9ed1-320f-5caa-9c10-bea4580085c4 | note | Verifying Document - Redlines
3bb64a96-941d-58a0-8054-c7df7e8a417b | note | Frequency - Post construction
34016d76-9cb7-5f99-ac70-5ccdd07ac80a | note | Verification Activity - H
dc0a719b-c026-5d33-b5c3-421f855beb57 | note | Verification Activity By - PE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
a2841ce4-e544-5c5d-ada6-fd646cde876b | checklist | SYS - AREA 1A CH1520-1740 BULK EARTHWORKS |  | AREA 1A CH1520-1740 BULK EARTHWORKS
6195b1b8-fa1e-5a7d-97fc-dbd972d19217 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements
66aab68a-f757-5648-805e-fcd3004146e4 | checkpoint | 3.04.01 - Construction Pack
bfee9e2d-a6b7-5f70-91c0-be5382ad9749 | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
73019707-9e2c-534c-a05b-3fcde5672553 | note | Standard / Specification - Downer
fc46177b-d6da-5e5f-b473-8975092b2048 | note | Verifying Document - Construction Pack
cf028689-ebb3-5192-9152-61a6781b2e1b | note | Frequency - Submit 10 days prior to commencement of works
1053d10a-8bc4-5c7e-b34e-717289b9bdf0 | note | Verification Activity - H
769b19e6-25c2-51ef-b6c5-d49c93eb7c7b | note | Verification Activity By - PE
26f60828-4451-5309-8d3b-0249cb8b6985 | checkpoint | 3.04.02 - Survey Setout
cf831fa4-9e72-5f6f-93bc-7b92ee6d3e7a | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
51686e4f-ea10-57de-b465-280fbf293317 | note | Standard / Specification - Downer
a56c6f04-de46-5fb8-aa75-7917dc94c8f6 | note | Verifying Document - Survey Records
77d6aa06-edd2-51e5-b4d1-f50385252962 | note | Frequency - Prior to Works
e9e2ae26-142d-55ca-80ae-2a4d6a362454 | note | Verification Activity - H
5ac007ba-46a3-5bdd-84ea-5f8829d48733 | note | Verification Activity By - SV
d8eb320e-d9df-5647-adeb-94fd61bee34b | checkpoint | 3.04.03 - Approved Construction Drawings
adac429a-f7e2-5e63-80d0-730d50cbd484 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
3b02b1a1-aed9-5211-a134-9a04eeffc8ce | note | Standard / Specification - Downer
3fdf891e-3ead-5017-b89f-18cf138d101c | note | Verifying Document - IFC Drawings
4173a28d-0312-5795-9c8c-5dbbcc1476d8 | note | Frequency - Prior to works start
cfa53cbe-96bf-5d97-a692-51a01ce4fd25 | note | Verification Activity - H
457bb499-0401-57d1-a2a5-f9335bba738f | note | Verification Activity By - PE
c41c9d11-3ba8-577c-b861-3303c0fbbdeb | checkpoint | 3.04.05 - Topographic surveys for measurement
b0ac2514-a724-594e-9ebc-d4a1ce86bf41 | note | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
aa70e3c8-aabb-5a4e-bbe9-5a344f485278 | note | Standard / Specification - PS 2.2.12
f4e73635-e745-53ec-9c27-42e5b3f88ffa | note | Verifying Document - As-built
c95d9ef2-4b07-5466-a47b-37893c42864a | note | Frequency - Prior to works and Post Works
e0c41ef4-e1d7-542e-b948-53432b22e03a | note | Verification Activity - H
666286b2-083d-59cc-9c48-2306a176d1d0 | note | Verification Activity By - PE
1ee852b3-c73f-5268-a975-3c912a92cb7c | checkpoint | 3.04.06 - Permits
1086a7b0-b8fe-576d-8430-21b79737c40c | note | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
5795d95a-16ee-5ff4-9521-bbea691dbe15 | note | Standard / Specification - ITP Register
abf5a4ad-1f5e-5db4-adc9-de90fce74b16 | note | Verifying Document - ITP Sign Off
d59d5929-0aa7-5d0b-89cb-e4bd1357d609 | note | Frequency - Prior to commencement of construction activity
4c981c6f-8b77-5d6e-8556-3aabf085e93c | note | Verification Activity - R
412821e0-a96c-5a47-92ad-7cf6c94f8d6b | note | Verification Activity By - SE
f3ef973a-42cb-52b5-8ea7-66cbfcf256e9 | checkpoint | 3.04.07 - Stakeholder Management
07f0300b-dee9-5f28-9128-a0d9daf1509f | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
66cd92a6-7a53-540f-9e88-afdef00c9aed | note | Standard / Specification - Project Stakeholder Management Plan
e422661f-e345-5a54-8688-d7cd237acb92 | note | Verifying Document - ITP Sign Off
4b556bcf-42b1-56a5-bfdf-aff9f8fc919d | note | Frequency - Prior to Construction with continue updates throughout the works
b486a5da-ac9f-5a37-89a1-e4205d6f2fb7 | note | Verification Activity - R
f1c12282-a223-563a-b4af-025210d3be65 | note | Verification Activity By - SE
005c296d-25f0-5738-a789-b97cd604b77f | section | 3.05 Engineer Nominated Hold Points (Engineer’s inspections)
a1b580bf-5e0e-529d-af5f-81de8644feb8 | checkpoint | 3.05.01 - Environmental Controls Inspection
220fb01b-d745-5045-be14-134205e9c4ca | note | Acceptance / Conformance Criteria - After installing measures to meet environmental requirements, before any earthworks begin.
12810a36-7076-5fa3-9309-fa15bd838414 | note | Standard / Specification - PS 2.2.16
b6e38161-1c28-58dd-8003-e06fc54c07b5 | note | Verifying Document - Site Records
2468b7fa-2b30-5143-9a17-d0cf723c63b6 | note | Frequency - Min 48h Notice
82fc3266-7242-50e7-adfc-5b87a9456b0a | note | Verification Activity - HP
6fe76645-582f-5023-93da-ab8501b34efd | note | Verification Activity By - ENG
45ce02c6-4c82-5ac3-aed2-668e7589b94b | signoff | Hold Point (Engineer)
397e246e-d5bd-577a-8f6b-81ec01a01ad6 | checkpoint | 3.05.02 - Bulk Fill Inspection
39705f9c-e934-5b3b-8800-e537f4d47d3c | note | Acceptance / Conformance Criteria - Prior to beginning bulk filling operations.
bd28e4f6-5513-5ca5-b0b9-8f398af9b0bf | note | Standard / Specification - PS 2.2.16
7f620750-7037-5f90-b423-8458b93e4bfd | note | Verifying Document - Site Records
4cc87978-3af0-54f2-a37c-2861c60b4f3f | note | Frequency - Min 48h Notice
bcaf12cf-0efa-51ad-9ded-5b8f62c0353f | note | Verification Activity - HP
4c8ec7d8-3e90-5a24-957b-45c963ead5e2 | note | Verification Activity By - ENG
d8cd9a3d-90ca-5b10-9fe2-8f39698d26cf | signoff | Hold Point (Engineer)
3db3366d-0d88-57aa-bded-c077e09e64d1 | checkpoint | 3.05.03 - Service Ducting Bedding Inspection
57a8445d-fd38-5977-b749-a3db5394a8c6 | note | Acceptance / Conformance Criteria - Prior to laying any service duct, drainage/water/sewer pipeline and associated pits, fittings and structures
0bd2a218-cf77-58c3-be8b-00842a9fa36c | note | Standard / Specification - PS 2.2.16
241bcb23-ff2f-5e2e-bd32-1b66435db087 | note | Verifying Document - Site Records/ Refer to Services ITP for testing requirements
305f24c2-0703-584a-9e40-ce3157339d1e | note | Frequency - Min 48h Notice
1bc05559-a503-5c5f-8fd1-27d0207c0609 | note | Verification Activity - W
f5ac7004-e040-5094-b259-35cbbf4b3574 | note | Verification Activity By - ENG
26f735b3-30f0-54da-b96e-22b8e5c765ea | checkpoint | 3.05.04 - Service Ducting Backfill Inspection
7e4a7988-03c3-5c7e-87af-ed5a4d520a43 | note | Acceptance / Conformance Criteria - After laying, before backfilling any service duct, drainage/water/sewer pipeline and associated pits, fittings and structures.
5397b13e-25a0-53f7-90e6-21d21174ffa1 | note | Standard / Specification - PS 2.2.16
38f7b901-ce61-5b82-ba86-2c9d95552aab | note | Verifying Document - Site Records/ Refer to Services ITP for testing requirements
e019faaf-8fe0-58e4-a4b1-8950d688b682 | note | Frequency - Min 48h Notice
d6a597bf-c1ae-5f05-a332-0e409159e8ac | note | Verification Activity - W
9abd5920-382a-5c80-a2b5-d604334cd91e | note | Verification Activity By - ENG
aacdafb1-ce5f-5662-9207-c4b7ab197387 | checkpoint | 3.05.05 - Geotextile Inspection
30235357-ba2a-5d0d-bf32-e108465a9ab7 | note | Acceptance / Conformance Criteria - Before placement of any geotextile.
af850139-ab11-59d3-8d6a-5ded512dd2e8 | note | Standard / Specification - PS 2.2.16
0ce6ff77-7be6-5200-8852-5d53e2272e01 | note | Verifying Document - Site Records
5cc966d5-e906-56ef-8ad4-2635435e73de | note | Frequency - Min 48h Notice
2e6fd158-bfe1-590a-9fbb-55341e4c9b58 | note | Verification Activity - HP
f63cd949-8628-5163-86d2-5e2ab51aae46 | note | Verification Activity By - ENG
a8c91dec-fc11-597c-8d05-68a26a62e131 | signoff | Hold Point (Engineer)
48749a16-2f17-50e3-a581-2454b8601df7 | checkpoint | 3.05.06 - Subgrade Inspection
bea3bd3e-1a67-59b3-b150-ca5c3595fab9 | note | Acceptance / Conformance Criteria - Subgrade inspection/stripped surface inspection, to include proof roll, scalar penetrometer and/or shear vanes.
70fc358c-d354-5c6c-8df9-908d48a52f10 | note | Standard / Specification - PS 2.2.16
714db9ad-f46f-52ef-a07e-a27fc0f7ea8d | note | Verifying Document - Site Records/ Test Results
089e3007-f9b2-53da-8767-6fb0c3a01dd8 | note | Frequency - After surface is stripped
40c00e8f-59e9-50f6-b11f-195e2cab0563 | note | Verification Activity - HP
fb26b3b6-d7be-55a5-b920-f8455c493cc5 | note | Verification Activity By - ENG
2c2d55b5-3df4-59c1-91e3-ee43ce6a39af | signoff | Hold Point (Engineer)
7d7e7aa1-ae37-54cb-b094-9943cfe254a2 | checkpoint | 3.05.07 - Undercut Inspection
205f430b-1d40-5338-820a-fc895c69c6b2 | note | Acceptance / Conformance Criteria - Undercut (if required) inspection, to include proof roll, scalar penetrometer and/or shear vanes.
04d27b24-5e7b-5476-a7ea-cd82483eb3f5 | note | Standard / Specification - PS 2.2.16
65d11e86-28dd-584c-80fe-f09a9af7f41b | note | Verifying Document - Site Records/ Test Results
3ff38dd2-5471-58e4-ae4a-e9a347932bd0 | note | Frequency - Prior to Subgrade Fill
cc051a3c-b0ae-58ed-85a3-2f3963327f46 | note | Verification Activity - HP
1feae0c2-2658-5f77-98b9-3f71b3aea196 | note | Verification Activity By - ENG
39632f99-b15b-5214-adee-cd16315c8d2f | signoff | Hold Point (Engineer)
c25d7356-8bb0-53c1-8727-2361fcf330cf | checkpoint | 3.05.08 - Settlement Monitoring
977450d1-fc9f-55e5-817a-1b9283275032 | note | Acceptance / Conformance Criteria - Settlement monitoring (Settlement pins & Targets) to be assessed by Geotechnical Engineer.
6d2a8eb6-7a7b-5db6-b4f9-6b3941313504 | note | Standard / Specification - Drawing 5200
70cf0c56-fdd1-5590-bef1-518c0f108a8c | note | Verifying Document - Site Records
1a1b650a-d510-553b-b01c-32e36162d83f | note | Frequency - Prior to constructing pavement and wall
f7da49b3-2c9b-5dd0-bd85-3aeaf35709bb | note | Verification Activity - HP
111c8e86-e703-5fd2-8eb8-e9bc46da9b4a | note | Verification Activity By - ENG
cd0ccdef-ce99-5ee8-9f3c-c9e95bbe82bb | signoff | Hold Point (Engineer)
de84f0d7-e75e-53ab-93ee-2a886ebb2ee7 | checkpoint | 3.05.09 - Subgrade Fill
3b6d39e4-aded-5525-9a05-2f3ba7d4111b | note | Acceptance / Conformance Criteria - Inspection of completion of sub grade fill prior to placing SIL, to include proof roll.
1e9e7ca8-b008-5387-b5a7-47972e295356 | note | Standard / Specification - PS 2.2.16
53267922-2588-5542-83ec-dcce3f7fd14f | note | Verifying Document - Site Records
9c59b01f-1e26-5caf-bc10-e68acc082366 | note | Frequency - Prior to placing SIL
c72eeff7-163c-5f7e-80c2-3f277204adcb | note | Verification Activity - HP
a33638a4-2802-5015-8b04-2758f810735c | note | Verification Activity By - ENG
7a8e1a7e-4fc8-54fa-b5d0-050a773d5a8e | signoff | Hold Point (Engineer)
de2c1e9a-cd69-5b10-8fa2-10046a6dd4a0 | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials
7ac3fd82-2973-5391-8d47-ef653930dfb0 | checkpoint | Imported Fill Approval
45fd01c7-e910-54d4-bec7-c51dc5e869fb | note | Acceptance / Conformance Criteria - Due to the fill-deficit on this project, imported fill will be required and should be discussed with and approved by the Engineer to verify its appropriateness and quality control testing requirements prior to use.
00224ad9-b44c-5c64-925b-0bdf2c3ad0b9 | note | Standard / Specification - GWS 2.4.1
034eb994-bff4-5dce-a8f5-5ca2e39e8efb | note | Verifying Document - Lab Tests
7bda6704-2e88-5a6c-903a-5abc136f5367 | note | Frequency - At least 2 days prior to placement and compaction.
be698d53-8e18-584e-b59e-5008a430fece | note | Verification Activity - HP
1b3a4554-bdab-544a-b0fe-2f429c05b292 | note | Verification Activity By - ENG
78f70bf6-2c06-5035-b60e-a22f6883679e | signoff | Hold Point (Engineer)
2e7287c7-4587-51f8-855e-cfbf51bf5280 | checkpoint | Re-Use Suitability Approval
41060b61-19fa-58c6-8795-3e53e1d8ca7d | note | Acceptance / Conformance Criteria - The Contractor shall test representative samples of the site-won material to be used as Bulk Fill and Subgrade Fill and the results are to be sent to the Engineer for approval.
71239f25-057a-5495-a65b-8059f502eb40 | note | Standard / Specification - GWS 2.4.2.1
91ac6848-60d0-5318-9a00-ed4c631f5ddb | note | Verifying Document - MDD, OMC, Shear Vane, PSD
51318647-1fc0-5090-a5bb-df5e632715e4 | note | Frequency - At least 2 days prior to placement and compaction.
4017e19b-6c59-58e0-a358-c2fb46c5bd2f | note | Verification Activity - HP
2738daad-13e6-56e2-850b-dbfe698f6491 | note | Verification Activity By - ENG
7449aaf7-2b71-58d8-9829-b0496e095d2c | signoff | Hold Point (Engineer)
4ee2b052-c438-5f8b-a38c-87ef2aad7f10 | checkpoint | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
13cb71d6-c1af-54a6-b7bd-21510996a303 | note | Standard / Specification - GWS
aa43c410-4e9d-5b14-a06b-357e23903553 | checkpoint | Eastern Gully Weir Cohesive Fill Material Testing
7e475385-e59b-545a-a386-0317f85d7e4f | note | Acceptance / Conformance Criteria - Eastern Gully Weir Fill shall be tested for Standard Compaction, Solid Density, Plasticity Index (PI), Particle Size Distribution, and Liquid Limit for
5599aacf-9b19-556b-8071-03ee88a79288 | note | Standard / Specification - GWS 2.9.4
291d7143-24d1-5bea-a541-b52e6e678f66 | note | Verifying Document - Test Results
c80900c5-6f26-514c-925c-08033d42fde0 | note | Frequency - At least 2 days prior to placement and compaction.
5e1dd57d-db29-5032-93c2-fc611966f113 | note | Verification Activity - I
2acb792c-7756-591a-9291-3d52f360c47d | note | Verification Activity By - SE
e2c74411-283e-5dcb-92e5-1ad4c8673db8 | section | Subsoil Drainage
0ad51274-e32e-5a34-bc29-557e5134bdeb | checkpoint | Subsoil Pipes
3f94bf73-bf5b-5437-9da8-17e3ae97576d | note | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 160mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
f9a94957-2d43-5bcb-b341-3538bb894ea7 | note | Standard / Specification - GWS 3.2.1
b629c8f6-6dfd-5ea2-b72e-17917646bbc1 | note | Verifying Document - Datasheet
f4e1f338-8fa7-504b-a4cb-56b41896398e | note | Frequency - Prior to installation
1a71e582-8f83-564e-92ab-12f86985a0e1 | note | Verification Activity - C
33c9ad80-23dd-5d83-a970-60e5f6105c12 | note | Verification Activity By - SE
50199267-31d3-5c23-904e-350146494d70 | checkpoint | Subsoil Drainage Aggregate
157dd5fd-3914-5a7d-b6cd-82a7e9a4aafb | note | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/6 including gradings
aa2baf26-c5d7-5049-ab44-ef2f743b3ebe | note | Standard / Specification - GWS 3.2.2 & 3.4
1248aa8d-7bc1-58cb-a514-3c47b2467f19 | note | Verifying Document - PSD, CR
7a23c5b4-57d0-5aa9-9f7e-07c02b92409f | note | Frequency - Prior to installation
5e0a201a-911e-5ee8-b97a-d9332fbdcfe8 | note | Verification Activity - C
506f0618-6e1c-5102-87bc-d361e1022c7b | note | Verification Activity By - SE
4cf2d249-01dd-583a-b300-ee9c0fdca73b | checkpoint | Filter Cloth
40786ed1-1abb-5eab-b26d-821b1c62bf75 | note | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings.
a0219122-25d9-528f-ae9a-22dbaf87c7a8 | note | Standard / Specification - GWS 3.2.3
f610f319-f379-53fa-8154-8b4d5bca6c13 | note | Verifying Document - Datasheet
2e3e366f-ba60-5836-9a55-28f1ba3a5d70 | note | Frequency - Every 1,000m3. At least two weeks prior to works.
951ef335-8d62-5c06-be73-7eec18ac3d1f | note | Verification Activity - C
fe3a95d8-88a3-576f-aa42-613286c0653d | note | Verification Activity By - SE
dd05ab25-8ed9-58ff-8c52-86614831d043 | section | Geotextile and Geogrid
c1949a02-aaa7-5fa3-8791-d10472398429 | checkpoint | Geotextile Approval
9a3d2597-ebe2-539a-aa42-61368c2611c3 | note | Acceptance / Conformance Criteria - The Contractor shall submit to the Engineer for approval the details of the filter fabric they propose to use at least two weeks prior to commencement of works, including compliance certificates.
a79a093a-64b5-5be4-812d-9f9f7aa9450c | note | Standard / Specification - GWS 4.1
561e97cf-103c-5838-ac55-be14acc86d5e | note | Verifying Document - Compliance certificates
79bd7770-6037-5577-8954-1c2bdc4582d9 | note | Frequency - At least two weeks prior to works
067be5b6-4d6d-5483-92ea-3e46a124d9a9 | note | Verification Activity - HP
967372ea-a3a3-54c8-9a64-18ddb723d059 | note | Verification Activity By - ENG
d8ea6ffc-c3de-5ea8-b878-175ea6e2f0e7 | signoff | Hold Point (Engineer)
aa4c0f31-7cfb-50e2-8525-6c6810829d61 | checkpoint | Uniaxial, Biaxial and Triaxial Geogrid
20af9f1b-6c10-5787-a2c6-f3c6221c2cc6 | note | Acceptance / Conformance Criteria - All uniaxial, biaxial and triaxial geogrid shall be manufactured in accordance with a management system that complies with BS EN ISO 9001 and BS 14001 and shall submit to the Engineer for approval.
ef41addc-1cbe-5c0d-9ca5-8d1ef6fdbe67 | note | Standard / Specification - GWS 4.2
0c7958a6-3ee8-5743-b5ce-19e007a5a8f6 | note | Verifying Document - Datasheet
913b2d66-4c18-5767-a5e9-17b67944114f | note | Frequency - At least two weeks prior to works.
aea6a083-cef0-5f4f-85d7-58111f8e5b2e | note | Verification Activity - HP
2fb75c33-4757-5988-8eb9-2f85068131e8 | note | Verification Activity By - ENG
80934c9c-deae-58f1-8340-4294589c22ea | signoff | Hold Point (Engineer)
e8dd58e3-026c-58f5-a27a-a9b089d1dc75 | section | Settlement Monitoring
84c5c33f-c8d3-5a40-9527-0b33b83cd8b1 | checkpoint | Settlement Baseplate Design
b2e13714-0793-5134-9aba-dff3f3e49e11 | note | Acceptance / Conformance Criteria - Equipment shall consist of 600mm x 600mm base plate (typically 20mm thickness),150mm PVC duct, 32mm diameter threaded bar with couplers for extensions at 1m intervals and waratahs and coloured flagging for protection following installation.
ab58a620-29e1-5cd5-9913-2c7857009c45 | note | Standard / Specification - GWS 6.2
9dc5bee6-37ba-5834-afe8-f7ef22fcf6eb | note | Verifying Document - Datasheet
177044c2-7b5a-56d8-b467-6a11c2a05f8d | note | Frequency - Prior to installation
38c7b763-7106-5ffc-9cab-8f619cc54550 | note | Verification Activity - I
9d733ae1-3eec-549d-8aba-40c2e14e2c81 | note | Verification Activity By - SE
958c01f8-566d-5276-933d-837d8aa231fc | checkpoint | Settlement Pin Design
4993c9e1-6514-5af4-8698-bf4bb1ef0f04 | note | Acceptance / Conformance Criteria - Settlement pins are to comprise 32mm diameter Reidbar rods driven a minimum depth of 0.5m into the ground surface. The top of the pin shall be domed to ensure repeatable survey measurements.
8280e55b-aaec-5527-b3ea-2bd24da7ac4e | note | Standard / Specification - GWS 6.3
6a86ff42-72c4-56ff-9fe0-eff5fd9492fd | note | Verifying Document - Datasheet
f069dae9-7360-5fcb-a785-701687cc1afc | note | Frequency - Installed within 24 hours of reaching design subgrade level
c73ca30a-597f-5a40-b41f-829e4cedbddd | note | Verification Activity - I
33be6f18-8792-5920-bf9d-de4009c5069b | note | Verification Activity By - SE
8e750017-49c9-59c2-921e-3d272003461e | checkpoint | Settlement Pin Bedding
2e1cfb65-6bc6-5474-a42d-b8ec2e0429ff | note | Acceptance / Conformance Criteria - Installation of the settlement markers shall occur at the base of the fill embankment, prior to placement of any fill. They shall be installed on a 100mm thick sand layer to form an even and smooth foundation which will be levelled using a spirit level.
2e80c0cf-b430-5cf6-8078-e90a77e6de23 | note | Standard / Specification - GWS 6.2
bb88f167-2eac-5ea1-a07a-4edb43311454 | note | Verifying Document - Site Record
433e324e-7e70-5607-946b-81fc02328d45 | note | Frequency - Prior to placement of fill
f0211247-806a-5652-b84e-408b2ce9da48 | note | Verification Activity - I
8c69d77c-c146-5a3b-9c0b-2d63827771a2 | note | Verification Activity By - SE
e7f9565e-269c-5b8f-bea7-bbe3f8910040 | section | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance
e53738b9-4ea0-5a1e-932b-1e909db7f934 | checkpoint | 5.01.01 - Clearing
78082b3a-e12b-5c21-a358-53d24b788896 | note | Acceptance / Conformance Criteria - All surface objects including fences, gates, debris, wood, dumped rubbish, concrete and other protruding obstructions shall be cleared and disposed of
9da1e544-eed3-519d-91c1-83240462c755 | note | Standard / Specification - PS 3.1
b50dac47-4fde-59b0-813f-56d6371997cc | note | Verifying Document - Site Records
a64d2405-c9fc-5811-a16d-dfcafa596de9 | note | Frequency - Prior to earthworks
1ca5d8fa-084f-53ca-b716-8880263ff1fd | note | Verification Activity - C
783b14cd-f41b-5af2-ab9a-9cdee83f416d | note | Verification Activity By - SE
c1229a05-a5ba-5ee3-9dc8-50f6b66bd874 | checkpoint | 5.01.02 - Demolition
898e6b66-9ffd-5630-8dcf-66d7cdd5cb4e | note | Acceptance / Conformance Criteria - Remove all buildings from the site including foundations, buried services and any other remnants.
1e4b5000-6877-5ca4-84b0-743bc492ac42 | note | Standard / Specification - PS 3.2
24b04cf3-b6ce-5360-8034-99e455efb90d | note | Verifying Document - Site Records
0f5cac53-5c09-5007-b349-9f02b07fb230 | note | Frequency - Prior to earthworks
676ec549-3b82-5463-b42f-70db12e7831d | note | Verification Activity - C
0937604e-d956-5db1-bf39-00d54c56fc50 | note | Verification Activity By - SE
d6abbe19-411e-547a-a0a0-c76f30ed53d4 | checkpoint | 5.01.03 - Septic tanks
f8c973f8-deef-5746-94a7-f251b5a2a71d | note | Acceptance / Conformance Criteria - Septic tanks shall be pumped out prior to removal and backfilling
b49d37c8-cb6e-501b-a4fc-a478b803a512 | note | Standard / Specification - PS 3.2
df2c9c6a-22a3-5041-8d6d-32a328bfb5ce | note | Verifying Document - Site Records
c6bf3dbd-30cf-5317-9142-90b0a2dd1c2d | note | Frequency - Prior to earthworks
f5499a7d-03ba-57c9-b1ef-2012a2864ca5 | note | Verification Activity - C
c011ed82-15bf-5f55-9f4c-d8313d37f9ce | note | Verification Activity By - SE
d94ec936-ad7a-558b-ab87-be3d2cfca838 | checkpoint | 5.01.04 - Plant Clearance
6d4d6e9c-4028-5c04-8cc4-6787c37ba964 | note | Acceptance / Conformance Criteria - Vegetation, Tree stumps, shrubs, plants, logs, including any roots greater than 25mm in diameter shall be cleared and disposed of
e513f065-fdac-5f75-a44b-2e4108a6638a | note | Standard / Specification - GWS 2.5
89f3f0b4-9bed-5b89-9ee8-bc47e57cad46 | note | Verifying Document - Site Records
dfdf7fa0-228d-51d6-a8d7-2b99f126969c | note | Frequency - Prior to earthworks
705917af-f81b-547e-848b-02cbfb8e0005 | note | Verification Activity - C
88634bea-cf7c-5452-9202-e6787e9c447d | note | Verification Activity By - SE
404c1584-e2f2-5e4b-82ac-ce76d71ee460 | section | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General
e4cd585c-3579-52e1-ab41-43c6db555cc0 | checkpoint | 6.1.1 - Groundwater Management
eb0e86e5-e733-5223-bbb9-927510d23d9b | note | Acceptance / Conformance Criteria - The Contractor shall provide all pumping plant and drainage systems required to ensure excavations are always free from water.
7e7617fa-fae5-5875-b604-3d92f1ae9a02 | note | Standard / Specification - PS 3.4
e28a6666-2864-58ac-b2be-d03fe009182d | note | Verifying Document - Correspondence
3c59ca22-9750-56f4-9528-71508147a1a2 | note | Frequency - Prior to excavation
963a9310-1758-5ef2-b107-9ca62263c7a2 | note | Verification Activity - W
6dad533d-9d56-562d-a873-7ac544b09ff9 | note | Verification Activity By - ENG
2888ef0a-7c95-5d4e-bd48-630d613dcbf2 | checkpoint | 6.1.2 - Cut to Waste Approval
4d18e52c-8158-562d-a166-7fae841d5a02 | note | Acceptance / Conformance Criteria - The Contractor shall obtain written approval from the Engineer prior to cutting any material to waste. To include evidence and extents of cut to waste. Topography survey data of all material to leave site, photographs of material and any material test reports.
e1a13489-9a5d-55a8-902e-237a7c4a31e1 | note | Standard / Specification - GWS 2.4.3
f68f05fa-aac4-5343-bc89-5a71a59747d5 | note | Verifying Document - Correspondence/Photos/Survey
db47406d-a14b-5988-af96-e4bde7d4b0ae | note | Frequency - Prior to cut to waste
1f8dfc8b-94b1-5db0-91bf-802c87634719 | note | Verification Activity - HP
d1e607a9-75e4-5ccc-9495-77974ca634ce | note | Verification Activity By - ENG
65c0bdd2-bca3-5890-b3b2-29a6b8be52f5 | signoff | Hold Point (Engineer)
5d512cb0-d81c-57fe-96ea-99a87cd34b09 | checkpoint | 6.1.3 - Foundation Suitability
8f52a174-1f14-5d9c-8f84-53832a38af69 | note | Acceptance / Conformance Criteria - The foundation on which filling is to be placed must be observed by the Engineer following clearing and prior to the placement of any filling to confirm the strength of the underlying soils is sufficient.
403a8560-3fe5-5d70-8ba0-4889dd83f554 | note | Standard / Specification - GWS 2.7
190f3aa6-7334-5f5f-a3ee-8d073c6c01ad | note | Verifying Document - Site Record
9fe9f93a-da52-5774-aa98-f6a1d17205aa | note | Frequency - Prior to the placement of any filling
49c4a9bc-2a33-58b4-aa32-18d9c49e9425 | note | Verification Activity - HP
55a75d49-9d4c-53ae-b04c-d26ae7dc6395 | note | Verification Activity By - ENG
05516c9b-7277-5725-bbb8-65d807611241 | signoff | Hold Point (Engineer)
44d96a88-c557-52f2-9d73-305345d8c03e | checkpoint | 6.1.4 - Unsuitable ground
f74e983f-b3f1-52d2-a6da-8feacdfc6948 | note | Acceptance / Conformance Criteria - Unsuitable ground shall be defined as any pre-existing uncertified filling or natural silts/clays having an undrained shear strength of less than 70kPa or natural sands having less than 3 blows per 100mm penetration when tested with a Scala penetrometer. The contractor shall obtain instruction from Engineer around extent and depth of undercut.
72b8a517-2c2f-576c-ab22-8a5927e27db0 | note | Standard / Specification - GWS 2.7
20f3605a-ef82-5349-8b91-838106d91174 | note | Verifying Document - Shear Vane / Scala penetrometer
6e495bf5-1e22-523d-9860-9240145d4445 | note | Frequency - Prior to the placement of any filling
b650b8b5-6206-5b56-9962-d2e1a99ce04e | note | Verification Activity - I
5bd7b186-b7b2-5740-b0cd-6b7cd6829b31 | note | Verification Activity By - SE
0c657410-b5a5-5209-824c-1299c15fa6c7 | checkpoint | 6.1.5 - Preparation for Filling
a6040fbd-88ee-5361-8734-01f4b7fd8f51 | note | Acceptance / Conformance Criteria - Preparation of the firm to stiff / medium dense subgrade beneath the proposed fill areas should comprise stripping of all vegetation, topsoil, any pre-existing fill materials or weak alluvium followed by benching of the exposed subgrade where natural slopes beneath the fill exceed gradients of nominally 1:5 (vertical to horizontal).
7c91a7c3-4bf8-5b9f-be81-ab10b9428ed3 | note | Standard / Specification - GWS 2.9.2
fc234cf2-875c-50a9-bd15-e27556849159 | note | Verifying Document - Site Record
22f53065-82e3-5ab6-ae5a-39840a6267b4 | note | Frequency - Prior to placement and compaction of fill
239279e4-1553-5a57-b7d5-a078fa61cec6 | note | Verification Activity - I
aa3d6ba2-bde8-57a5-aefa-e21d85e5b1ea | note | Verification Activity By - SE
5fbfc25b-ac41-5dd5-8870-2eca385a779a | checkpoint | 6.1.6 - Subgrade Conditioning and Proof Rolling
bd14a369-a5e5-53fe-af67-b8de5e4943c4 | note | Acceptance / Conformance Criteria - The subgrade shall be scarified and moisture conditioned where necessary and then proof rolled to verify the subgrade stiffness and consistency.
c9327137-4cde-584e-9d31-f301eced2c4f | note | Standard / Specification - GWS 2.9.2
5a215d15-4350-5e0a-b384-5db64abf102b | note | Verifying Document - Proof Rolling Sheet
437a76a4-fcbb-5fb8-b9c0-dba79aa678b3 | note | Frequency - Prior to the placement of any filling
5e876cd9-e4c1-583b-bce3-5c43af9e35ff | note | Verification Activity - V
51ccb122-fc8c-5e98-9471-2075d87f0242 | note | Verification Activity By - SE/QE/ENG
090dadc5-301d-552a-b293-aab6dbc64307 | checkpoint | 6.1.7 - Undercut Backill Compliance
34b385b3-2355-59e7-876f-ff44ad010bdd | note | Acceptance / Conformance Criteria - Test results for undercut backfill prior to bulk fill commencing, NDM, scala penetrometer, shear vane or cleggs, material dependant. TBC instruction from engineer. Undercut backfill QA to be filed/captured separately from bulk earthworks fill QA.
f2d5b609-ffe3-5060-90eb-b2aeb2b22cc6 | note | Standard / Specification - GWS 2.9.2
2a5ceae4-6204-56b2-af74-f7b852dc82ec | note | Verifying Document - Test Results
3d85fe98-17a1-5ba1-8548-1faff69eb73f | note | Frequency - Prior to bulk fill commencing
ec2b9ddc-86b4-5199-a84a-b585302e0d67 | note | Verification Activity - R
f06ec382-6ae1-5540-b7b0-49c345564686 | note | Verification Activity By - SE
c9bbd24f-6b19-57f9-91fc-1ac6c8d49ec3 | checkpoint | 6.1.8 - Topographic Survey
a5561c5b-ca9e-5395-be42-bdfcd8eb8c4f | note | Acceptance / Conformance Criteria - All subgrades and undercuts to be captured via topographic survey (GPS)
972f635b-ad00-5e9d-a764-3df28e80d140 | note | Standard / Specification - PS 2.2.12
67096b30-70fa-568b-8ca7-5c4476661a15 | note | Verifying Document - Survey Results
f665dbf1-e4ae-555a-a155-8f872335b31f | note | Frequency - Prior to cutting or filling.
4e3075c0-3f73-5c5e-acea-53b9ff9dc3aa | note | Verification Activity - R
0dd85854-02b3-5db4-9210-0eb8f56a5c43 | note | Verification Activity By - SE
2b19974b-beb5-5ee1-ac63-a62d27aebcc0 | section | Stockpiles
17f3c35f-f53f-5024-885d-1b98e7d342ad | checkpoint | 6.2.1 - Stockpiles
bef39443-7d85-52f7-8d0c-66f2e56b1f58 | note | Acceptance / Conformance Criteria - The location of all temporary stockpiles must be approved by the Engineer prior to placement. Where stockpiles cannot be avoided above sloping ground, they should be placed over a wide area with the height restricted under the direction of the Engineer.
25ca6fa2-218e-58ee-bfc3-2c5a7c30c9df | note | Standard / Specification - GWS 2.9.3
0234ee50-2cac-5b79-8bc4-e97d89f84622 | note | Verifying Document - Stockpile Map
db7cde91-35c2-5185-9e3b-b29a79f2176d | note | Frequency - Prior to placement.
48298222-1d4e-5d30-932c-06dd5fa4628d | note | Verification Activity - HP
1497dad8-abb9-5023-a8ca-f94c8ff694a8 | note | Verification Activity By - ENG
2bf26bc7-1a18-562a-8703-832bc250e5d6 | signoff | Hold Point (Engineer)
2192d811-69e9-5a25-bb8c-201a8e17f817 | section | Earthfill
f119c352-904c-5f3f-8f85-ce61625e357e | checkpoint | 6.3.1 - Earthfill Placement and Compaction
286ede01-a444-59af-8320-caa3012c88cc | note | Acceptance / Conformance Criteria - Earthfill must be placed, spread and compacted in controlled lifts under the direction of the Engineer. All earthfill must be placed to ensure adequate knitting of successive fill lifts by ripping any surfaces that have become dry prior to placing the following fill lift.
b3cf298a-4b4e-50e8-92bc-e06a06b5c243 | note | Standard / Specification - GWS 2.9.4
0ba917b5-eebf-5035-abc0-0e37abe8cbed | note | Verifying Document - Site Record
0e81b6c5-9757-515a-b91b-e69f20515b83 | note | Frequency - Per lift
d3f4f4d1-826c-579d-b32f-e6b543e41cf7 | note | Verification Activity - HP
4406eb78-5b4b-5bc2-ac14-4fb5ba61d892 | note | Verification Activity By - ENG
1e7f594d-dcca-55b1-b520-89726427772b | signoff | Hold Point (Engineer)
51bbabf3-a2ac-517d-96c6-d269197bde8f | section | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
3628e322-55b2-56ab-85b5-2aca3175c1e0 | checkpoint | 6.4.1 - Proof roll Testing
81e47988-85b7-532a-bae1-1a12e72c1d69 | note | Acceptance / Conformance Criteria - Each layer shall be tested via Proof roll to: 7mm maximum impression
881f0569-d51a-5ef7-8ef0-d3678621cee8 | note | Standard / Specification - GWS 2.9.4
71c058e2-0e0e-5335-9f4a-00d696132c0b | note | Verifying Document - Proof Rolling Sheet
d2cdd97d-44a2-54ec-8461-90172cb8a3be | note | Frequency - 100% of each layer
a3cf788c-318e-5cbc-adc4-8104048747c7 | note | Verification Activity - I
a6b88ab0-b9d8-5dd7-8d79-5c1cdfb29ad2 | note | Verification Activity By - SE/ENG
28d9577b-1def-5be9-a5ae-0130db5993ab | checkpoint | 6.4.2 - Compaction Testing
0361ad6d-e77a-5d58-81fe-394dbecd915c | note | Acceptance / Conformance Criteria - Bulk fill shall be tested by DT at 300mm probe depth 95% MDD. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick.
702d3671-8874-54ae-904e-c2b546422874 | note | Standard / Specification - GWS 2.9.4
84133fc7-b8f9-55b3-a993-09885b7c8b41 | note | Verifying Document - Test Results
9d017020-3c0e-553d-b800-f863103cd6c3 | note | Frequency - 1 set / 500m3 (1 set to include 1 x 0.5m deep Scala and 1 x DT within a 3m radius)
e73f6f4f-173e-5265-a670-bd32cc5dbb1d | note | Verification Activity - R
2c57898f-d1f2-505a-abc6-d6dda53bcda1 | note | Verification Activity By - SE/ENG
65b26fb1-8ee6-524e-91c3-159b39e4b199 | checkpoint | 6.4.3 - Scala Penetrometer Testing
f1331738-3f66-562e-aab4-9f1c14cd166a | note | Acceptance / Conformance Criteria - Bulk fill shall be tested by Scala Penetrometer every 500m3 to: 4 blows per 100mm. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick.
3ecfb16a-a9fc-5056-9e5c-bed455d0694e | note | Standard / Specification - GWS 2.9.4
e7df00a3-4bb3-5329-b09e-c11d8a7e7f46 | note | Verifying Document - Test Results
c5a4782b-328c-5561-92b4-2ad8f96d9ddf | note | Frequency - 1 set / 500m3 (1 set to include 1 x 0.5m deep Scala and 1 x NDM within a 3m radius)
3b2bf319-1640-5979-bca2-736dc8f5952c | note | Verification Activity - R
11826f75-4718-5556-89d7-4887d9c2d9d7 | note | Verification Activity By - SE/ENG
cc08febf-128a-537b-80e4-30bf18b2dac8 | section | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend)
1d857413-cd45-5e2e-ba04-4e49e77f5ba8 | checkpoint | 6.5.1 - Vane Shear Strength Testing
dbbc0a18-ae6a-5cf7-9ce0-18ec7a7ed771 | note | Acceptance / Conformance Criteria - Bulk fill shall be tested for Vane Shear Strength to: Minimum average 120kPa over 10 tests, minimum single value 110kPa. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm.
36bcc3d7-db98-5639-af85-741172812629 | note | Standard / Specification - GWS 2.9.4
251ea5e9-0ef2-5550-9457-1743ce45a70b | note | Verifying Document - Test Results
1d857961-37ac-5b77-a66c-91f514f529e0 | note | Frequency - 1 set / 500m3 (1 set to include 5 x shear vanes and 1 x air voids within a 3m radius)
56d13354-9e3c-5cfb-91f0-04b5ea52b5e7 | note | Verification Activity - R
2f5aef00-2b4f-5282-a689-66479c32e70b | note | Verification Activity By - SE
80b3b8a5-692f-561b-8930-bca892c54e74 | checkpoint | 6.5.2 - Air Voids Testing
9901dfd8-8abf-5c33-9555-ffa623f92f70 | note | Acceptance / Conformance Criteria - Bulk fill shall be tested for Air Voids to: Maximum average 10% over 10 tests, maximum single value 12%. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm.
f3da272a-2c60-5787-9a8d-72ddfd15ed6c | note | Standard / Specification - GWS 2.9.4
36bf09f3-2f3e-56ec-8617-e97bc6b90620 | note | Verifying Document - Test Results
0a4d47d7-3840-5c0a-a55d-504f47de1df7 | note | Frequency - 1 set / 500m3 (1 set to include 5 x shear vanes and 1 x air voids within a 3m radius)
c3c6cc28-d947-5fc1-bac2-97a43d11f29e | note | Verification Activity - R
8267f1ef-1ee0-56f7-bf44-85d36163dbe2 | note | Verification Activity By - SE
7d5b1c9a-3904-5ba1-84d5-335eb6c5663d | section | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
91de5557-94fc-563b-8e74-6032ee8dec93 | checkpoint | 6.6.1 - Proof roll Testing
b633fc11-6f49-5738-ae16-b70fd989c7e5 | note | Acceptance / Conformance Criteria - Each layer shall be tested via Proof roll to: 5mm maximum impression
bde7cd76-353a-543d-81ea-5b47ef0877e2 | note | Standard / Specification - GWS 2.9.4
2f034ce5-f965-53c1-9f07-ab3c43bb4201 | note | Verifying Document - Proof Rolling Sheet
bbc95283-876f-534a-a57e-454ecf07ca08 | note | Frequency - 100% of each layer
b884386a-1912-518f-82fa-88e7ffc3a8ab | note | Verification Activity - I
a9e47c7c-12af-5d6a-a677-b116b4721333 | note | Verification Activity By - SE
06b7dc4d-9fe4-54e2-be84-0fc93ed0deaa | checkpoint | 6.6.2 - Compaction Testing
72f4e1d4-2714-5bad-b61b-a89df2751088 | note | Acceptance / Conformance Criteria - Subgrade fill shall be tested by DT every 500m3 to: 98% MDD. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm.
90c5da6a-fd57-519a-af68-7f03ff4eeae2 | note | Standard / Specification - GWS 2.9.4
65582f1c-08a9-5ed4-9cca-7ae57b6fd2b2 | note | Verifying Document - Test Results
7d1f3f80-e554-5f08-8f36-5f61dd240c55 | note | Frequency - 1 set / 400m3 (1 set to include 1 x 0.5m deep Scala and 1 x NDM within a 3m radius)
fb7d72f3-6266-5d2f-a84a-b8ef5a9bfb43 | note | Verification Activity - I
abf82fab-4d37-580d-834e-df632b56edbd | note | Verification Activity By - SE
b5a557cc-1d11-5a26-a9f0-d4d9f12c9eb1 | checkpoint | 6.6.3 - Scala Penetrometer Testing
fa73c0bd-67ed-5c81-b9f6-bcf874f36e76 | note | Acceptance / Conformance Criteria - Subgrade fill shall be tested by Scala Penetrometer every 500m3 to: 5 blows per 100mm. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick.
b52aed14-7a5f-5c32-b592-ad178c6a4ba8 | note | Standard / Specification - GWS 2.9.4
cbf75fa7-f933-50e9-81ab-d8fe0557bba2 | note | Verifying Document - Test Results
7c9d20af-a460-54be-8d2d-db9494b4edc4 | note | Frequency - 1 set / 400m3 (1 set to include 1 x 0.5m deep Scala and 1 x NDM within a 3m radius)
d6175d17-dc53-576e-92fe-4c625f891373 | note | Verification Activity - I
b98e763c-d8e0-5357-ab9e-fbe30cc17c2e | note | Verification Activity By - SE
2dbda8a6-8b6c-4018-a065-870d41ee5b50 | section | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
6011d492-ae66-5da1-a554-20d696e97488 | checkpoint | 6.7.1 - Shear Vane Testing
97b9b3e5-db79-59b2-b466-0b008ccff789 | note | Acceptance / Conformance Criteria - The Cohesive Fill shall be tested by Vane shear strength to: Minimum average 140kPa over 10 tests, minimum single value 120kPa
5caf5c28-8adb-5986-ac40-117c055eb178 | note | Standard / Specification - GWS 2.9.4
08babd25-b5e1-5a0e-ab73-99303ff9fc43 | note | Verifying Document - Test Results
e2d0c240-a3cd-5182-a990-b731d77ba303 | note | Frequency - set / 500m3 and every 0.5m lift (1 set comprises 4 x shear vanes and 1 x air voids within 3m radius)
76397b3a-dd0b-59ae-b0c7-b18f4785fcd5 | note | Verification Activity - I
cb0b7c5b-f49c-59af-ab6f-04fa7cf3847b | note | Verification Activity By - SE
4a52de1c-d79a-5f08-90c6-db4398518336 | checkpoint | 6.7.2 - Air Voids Testing
4db17005-7815-5b97-af65-a2d559d0b55c | note | Acceptance / Conformance Criteria - The Cohesive Fill shall be tested for Air Voids to: Maximum average 5% over 10 tests, maximum single value 6%. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm.
9e4e2f34-58e8-5cba-8f25-809593f7e3b4 | note | Standard / Specification - GWS 2.9.4
b94e47d1-f994-5e12-9c5a-ca666b8a440e | note | Verifying Document - Test Results
33c1e730-fd7a-5790-b721-486d1a8144f6 | note | Frequency - set / 500m3 and every 0.5m lift (1 set comprises 4 x shear vanes and 1 x air voids within 3m radius)
8f1e6d8b-95ee-55cc-ab21-e7ba2bff47aa | note | Verification Activity - I
b2000c16-2302-5b4f-a14b-e4c0f973756c | note | Verification Activity By - SE
cfea36e2-72da-5eb6-8f4c-85af1908ec79 | checkpoint | 6.7.3 - Water Content Testing
5a8fb55b-62f9-5e81-87cf-23c8f3f5f47e | note | Acceptance / Conformance Criteria - The Cohesive Fill shall be tested for Water Content to: Minimum 2% dry and maximum 6% wet of optimum water content. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm.
04845150-aafd-5748-987d-ec3e37a628f5 | note | Standard / Specification - GWS 2.9.4
a24404f7-d7be-5b60-acf0-37f389166146 | note | Verifying Document - Test Results
b4089446-2691-5cae-af41-2c84000040ba | note | Frequency - set / 500m3 and every 0.5m lift (1 set comprises 4 x shear vanes and 1 x air voids within 3m radius)
607ffd22-9ae7-5e38-92d4-cdfc2d60fd38 | note | Verification Activity - I
0eb417e8-c6f3-58b8-9ce6-33a9fbcc8a53 | note | Verification Activity By - SE
f2ef1e0d-4c71-51b5-b671-5bbd19f04b08 | section | Cut Batter
344471b0-ed20-5733-9b72-3ab5307d3074 | checkpoint | 6.8.1 - Cut Batter Inspections
4d324204-dd12-5e34-b757-a5805d8ba4ae | note | Acceptance / Conformance Criteria - The Contractor will need to regularly inspect the exposed soils and check for any seepages that may occur due to the layered profile of the natural soils. All inspection records are to be submitted to the Engineer within 24 hours.
2759f9f1-0521-5f18-9d18-423ac5f16661 | note | Standard / Specification - GWS 2.9.6
ce5cab41-2c26-5482-96c2-3d22d43139ce | note | Verifying Document - Inspection Programme and Records
5c505c18-e993-51f7-949a-5b47156856cc | note | Frequency - Submitted to the Engineer within 24 hours.
a43347cf-95d7-5b0a-9e04-e6157f5a29d0 | note | Verification Activity - H
eb00df9a-b10b-5382-9e6b-464ee4e94717 | note | Verification Activity By - SE
8d672582-9e3e-536a-a565-c2a9b85d6ab5 | checkpoint | Cut Batters- temporary cut
82b32635-e0da-5dbe-96c9-9eb5a24df6f3 | note | Acceptance / Conformance Criteria - The temporary cut buffer shall be maintained for 2 weeks to see if the seepage drains out, after which it may be cut to the final profile or additional drainage measures installed subject to review by the Engineer.
73e4728b-5fd1-5e00-a3de-757a7f39c0e9 | note | Standard / Specification - GWS 2.9.6
d4b60330-816d-503d-8f99-630ff7c072c6 | note | Verifying Document - Site Record
f141fdc1-eaa1-5721-93e2-10a3bf9531bd | note | Frequency - Each Cut Batter
08a7b0a1-3bd6-52cb-a687-8fd6eec5a3ed | note | Verification Activity - I
b7d155b5-2a16-51db-b7e9-418daa45c1cb | note | Verification Activity By - SE/ENG
13a6ac74-1741-5e78-a060-6ff18a0ba665 | section | Surcharge Fill
dc74b895-83a7-5278-8bbb-885f83b87f5b | checkpoint | 6.9.1 - Surcharge Fill Installation
f8d6420c-f10e-5e92-8f1b-1938b79fc563 | note | Acceptance / Conformance Criteria - Surcharge filling shall be placed, spread and track rolled in 300mm layers. Surcharge fill will only be required if the settlement monitoring results exceed what was anticipated in the design. Under Engineer’s direction.
bea58f9c-832b-54dd-91d1-7738ce2a1847 | note | Standard / Specification - GWS 2.9.7
11e1b7c8-63f1-5b19-b041-37ef1a1a8150 | note | Verifying Document - Site Record
be46eeb9-b88f-5e12-adb3-e15853fa82ea | note | Frequency - Per 300mm layer
89c48506-43db-5c3d-aa52-bf114025d184 | note | Verification Activity - I
ac13cdb7-dc86-52f2-b78a-f98e874d68bc | note | Verification Activity By - SE
3362fc22-d85b-5472-a551-b29831ecf61f | section | Respread Topsoil
675454bd-86af-52a4-90b9-4d92fe27414d | checkpoint | 6.10.1 - Topsoil Respread on Steep Ground
612645e2-276d-5142-9b35-0c856ea5d03c | note | Acceptance / Conformance Criteria - On ground steeper than 1V:3H the surface should be roughened under the supervision of the Engineer prior to topsoil placement.
6e7f7b5a-7ed7-5cf2-9964-ab15f2fd2dfc | note | Standard / Specification - GWS 2.9.9
f6c2c4c1-e3aa-52d0-b069-b8bfb728a650 | note | Verifying Document - Site Record
28b6f014-6695-5478-a0ab-d75596c438bf | note | Frequency - Prior to topsoil placement
27f50561-beb4-53c0-85fd-f9ca434bb6ec | note | Verification Activity - HP
b0f3ff82-752c-51a9-aaa9-99a25793f796 | note | Verification Activity By - ENG
1d1cc3d7-34c3-545b-8ccd-3653008dd3e5 | signoff | Hold Point (Engineer)
dd88eedd-dc8c-43ca-aa8a-39b3e72b3045 | section | Subsoil Drainage
60dea67b-10ef-56e6-a440-025a78fbac7a | checkpoint | 6.11.1 - Filter Cloth Wrap Inspection
e85fb9f6-7d2b-513a-bd83-0e4c00c9f8d7 | note | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain.
246d901e-41b6-508b-a982-d57b285d48f6 | note | Standard / Specification - GWS 3.2.2
14272c52-0910-574a-8e68-1a008caaea01 | note | Verifying Document - Site Record
4b416b83-4d74-5080-9f4a-780e2dd7ea80 | note | Frequency - prior to backfilling
b07a666c-cab0-5dc9-b74a-e8928840c5da | note | Verification Activity - HP
2a503a6b-ecda-532e-8198-34ada9d17cca | note | Verification Activity By - ENG
0d3a7fb3-9b6f-5112-873f-0d6ca9de26e1 | signoff | Hold Point (Engineer)
49d7e32c-154f-59ea-b421-fd8abab9d209 | checkpoint | 6.11.2 - Trench Backfill
9be62d94-669d-56c5-98df-f0655e525d22 | note | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard above
9943da35-02d8-5462-9871-d8df0642290e | note | Standard / Specification - GWS 3.3
14fbb3eb-8b9a-5333-af1a-fb278cb4f91d | note | Verifying Document - Site Record
71250cca-3f46-5d4d-8b23-78956c6b7201 | note | Frequency - Each trench
63f9d961-89a4-582b-8e63-ba924b5a4aa5 | note | Verification Activity - I
e9ff29db-9280-5bcb-8127-113818b5c8f5 | note | Verification Activity By - SE
b5153075-1228-599c-8105-75e3c1df8afa | checkpoint | 6.11.3 - Drainage Outlets and Inspection Points
e249ae11-1c7d-5447-bc71-995f46050380 | note | Acceptance / Conformance Criteria - At least one temporary flush point is required for each subsoil drainage system to enable flushing of the system once the earthworks are complete.
e46ceacf-cb8b-505d-8b15-1dc555be327f | note | Standard / Specification - GWS 3.6
85052b17-54d4-5a95-9cbb-ef0d6c71f674 | note | Verifying Document - Site Records
5ba4c355-4959-5072-8fd9-0aaf4250d5fb | note | Frequency - Each Subsoil Line
8a2d0f43-d8cf-5b99-be4a-77de64ccae73 | note | Verification Activity - I
ee8b451c-21ab-5f86-ba49-8c33a487de18 | note | Verification Activity By - SE
16e0a2a8-3ab2-5d22-ab09-f770bceda824 | checkpoint | 6.11.4 - Subsoil Flushing
ac40c030-449b-542a-af1b-0220426fe171 | note | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer.
b407e655-141b-5767-955c-3c2aa89b6d64 | note | Standard / Specification - GWS 3.6
e23d0fc8-d955-5bdd-9a2e-739dea834f0e | note | Verifying Document - Site Records
08a98415-27ac-5d92-accf-d6f9681783cf | note | Frequency - On completion of earthworks
8c87024e-7a19-523d-9d24-d7539bbdb6c3 | note | Verification Activity - HP
4f23f32d-52cd-557e-8dc4-002c5a2eda2c | note | Verification Activity By - ENG
4d0d1afd-4388-5c88-a38a-c74d25c23729 | signoff | Hold Point (Engineer)
b9013253-72a7-5b8d-bd30-a533437504c3 | checkpoint | 6.11.5 - Survey
157333d0-9f65-58aa-be41-2fc45a3a2cdd | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
1b3f7c5e-1e01-5a0e-a9e7-06bc3b3a5f3a | note | Standard / Specification - Downer
a335245c-0a90-5993-a7e9-27775cd90fca | note | Verifying Document - Records
ef32fdb5-96c4-5a3f-8230-c5c1f956c7f7 | note | Frequency - Post construction
343e4729-0a43-541b-963c-5e036c02f45f | note | Verification Activity - H
74b2f7ff-37a5-576d-8c7d-82789d0323f5 | note | Verification Activity By - SV
e31c7c1b-8b92-4c89-a88a-71fde8df7627 | section | Geotextile and Geogrid
1d37a543-483b-546a-8497-529e1f2639b5 | checkpoint | 6.12.1 - Geotextile Installation and Lap Length
76225046-1c0e-5471-957a-bb64165abba8 | note | Acceptance / Conformance Criteria - All geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets.
66d8fa5b-a442-549a-bea5-c3cb7452c2ad | note | Standard / Specification - GWS 4.1
de2fd70a-1a13-5c27-a39c-70f8eed0732e | note | Verifying Document - Site Records
c2acaba6-1ca8-5cac-8371-503ab5be89c7 | note | Frequency - Between each sheet
0067de7e-b9fc-5b67-8136-0342c39ff969 | note | Verification Activity - I
f5d827bb-f426-5371-a150-e95a31726758 | note | Verification Activity By - SE
a7c0d67c-1e3c-507f-bbb8-8d4fb78ed76b | checkpoint | 6.12.2 - Geotextile Inspection
5fce79e7-daa5-53c5-ad32-308b9a5bc3c4 | note | Acceptance / Conformance Criteria - Before placement of any geotextile should form an Engineers inspection hold point
b95f0b90-c3e4-514b-835d-2f189a655d86 | note | Standard / Specification - PS 2.2.16
f3c2b170-0327-54e3-b456-bc5cc93ab321 | note | Verifying Document - Site Records
b2d0e962-99a2-5b14-8134-5a715d35b1d2 | note | Frequency - Min 48h Notice
4ca5ca69-f231-5784-abee-83eeca3a889b | note | Verification Activity - HP
a8b167fb-fa63-5a5a-a9b8-2948ec01afe8 | note | Verification Activity By - ENG
e935c170-7db3-5df1-a707-7b58b919ad66 | signoff | Hold Point (Engineer)
3c2d33c0-e5f3-5aea-a629-633a37922b59 | checkpoint | 6.12.3 - Geogrid Prep Inspection
08108f8c-c97e-553e-9698-ffa2ad50e42c | note | Acceptance / Conformance Criteria - Prior to placement of the geogrid, verification of the grade, length, orientation and layout is required against the drawings.
5123368d-8f9e-559a-b60f-86578ebb8743 | note | Standard / Specification - GWS 4.2
80170ccc-66d3-58b2-b5d7-f14349acad85 | note | Verifying Document - Checksheet / Survey
0a1db885-bc81-5f42-85ea-012546cd27bf | note | Frequency - Prior to placement
d17f58fa-a7fc-5a1b-a210-e9612db174c1 | note | Verification Activity - I
b5070777-cb7a-5829-bc76-2a395a322d46 | note | Verification Activity By - SE
1a87f51f-dc8e-4397-93b8-8b9d47e3bc63 | section | Settlement Monitoring
43fcc8d7-6125-53b6-9a5b-035d7dea05ea | checkpoint | 6.13.1 - Settlement Pin Installation
99a3f15f-8fc2-5bf6-9524-d6389239a71b | note | Acceptance / Conformance Criteria - Protective waratahs and coloured flagging shall be installed around all settlement pins for protection. Settlement pins shall be installed within 24 hours of reaching design subgrade level.
2f1d0c7e-7ded-524d-9789-d329ecdea150 | note | Standard / Specification - GWS 6.3
7a072403-7d6d-584f-b3d8-2d79756c7e87 | note | Verifying Document - Checksheet
248f1536-fe7a-5a91-887f-1bd1ed65900a | note | Frequency - within 24 hours of reaching design subgrade level.
b4f59ffe-eb6b-5ea4-80c8-cf2ba8ab3538 | note | Verification Activity - C
0cef5e12-9dee-51e8-b40d-6b3fb1589e5d | note | Verification Activity By - SE
b303cc8d-cc79-55b4-a909-2d00242f9edd | checkpoint | 6.13.2 - Settlement Survey
112e7f80-767f-5636-946f-3932d2c8e479 | note | Acceptance / Conformance Criteria - Survey measurements are to be undertaken regularly by the Contractor as specified on the drawings, to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
212ea4ee-e52a-546b-808c-745bac8d928a | note | Standard / Specification - GWS 6.3
f1489eab-003c-5a56-a03f-13ad0877b9b2 | note | Verifying Document - Both paper and electronic formats
571d823b-77b5-53aa-8f3b-cc51567a9717 | note | Frequency - within 24 hours of each reading.
d4b9d21a-a50a-5a45-8ad8-0771fa0b609e | note | Verification Activity - H
539fae9f-0f46-5cb7-ac3e-84c6f799cda3 | note | Verification Activity By - SV/SE
cb2f4838-a069-568a-bec3-af9d57ca1e5e | checkpoint | 6.13.3 - Retaining Wall Settlement Targets
b493ddef-686b-59cb-a6fa-20ce8a77e630 | note | Acceptance / Conformance Criteria - Targets shall be fixed immediately after completion of the first row of retaining wall blocks at each location and the initial baseline survey reading made prior to the subsequent row of retaining wall blocks placed.
3eeed169-5910-546d-849f-0c6770ded3bc | note | Standard / Specification - GWS 6.4
4fa0ca17-2e43-50c7-8881-fe23558af58b | note | Verifying Document - Checksheet
90ae0198-a4e3-5455-90ed-a258561cd1fc | note | Frequency - prior & after completion of first row of retaining blocks
be7c7a7f-d127-535b-ad98-78270c9a6907 | note | Verification Activity - I
a8e6571c-2ea6-520b-b643-50014469a9b8 | note | Verification Activity By - SV/SE
7d2dc634-7e36-5133-8be8-f2ca2cd3e99d | section | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities
2b19c0a6-1f40-54a8-bd0a-961674cf52c7 | checkpoint | 8.1.1 - Construction Record Compilation
9e865959-c88a-5190-9f5f-9aead8c19ce6 | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
f4dfd5a4-d771-5aff-a69f-4c87ca9911bb | note | Standard / Specification - Downer
89b72ad1-0a2c-5e13-a797-a0d4a5b77ccf | note | Verifying Document - Records
855af0eb-08d2-530f-a975-5f08114d94c3 | note | Frequency - Post construction
0c644f99-c56e-54d0-b27f-54f286afe727 | note | Verification Activity - H
271d3bf3-544b-50e2-a020-72c91450dfda | note | Verification Activity By - SE
87cddc19-8875-541a-8ee5-925099bb07f2 | checkpoint | 8.1.2 - Survey Records
e04a5f03-809c-5321-856b-6c14bbe078c7 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
ea054228-80af-5478-8e11-c723f5ec1539 | note | Standard / Specification - Downer
fcc41489-f8ba-5261-96c6-b0f25fa9d847 | note | Verifying Document - Records
0e8d161d-391b-5bc0-a9cf-621caa90b000 | note | Frequency - Post construction
606b5e65-7591-5355-8b6f-2c9e2ee4738f | note | Verification Activity - H
a10d33be-0636-5363-b915-0104e692bbbe | note | Verification Activity By - SV
274b2337-f656-5f3f-b183-089ebbccbb69 | checkpoint | 8.1.3 - Redline Drawings
c8dc263f-8b1e-52a7-beee-97d562069bee | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
e3d9d811-9f48-50aa-ad2d-fbcb143b84ad | note | Standard / Specification - Downer
c8d3d189-33f3-5e6e-a349-a2f6a1c86fce | note | Verifying Document - Redlines
bb6a84e8-3c2f-500a-8396-acf0711ef71f | note | Frequency - Post construction
fbb1edf2-dd6f-53ab-abb0-02caa90ae961 | note | Verification Activity - H
c8c2a577-65bf-5aed-9279-6ba112957dfc | note | Verification Activity By - PE
35c4da15-00e2-5c64-9258-453572b5f83e | checkpoint | 8.1.5 - Photos
94e37964-f4ea-55f7-843c-d9cff1cab647 | note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
4bbb697c-8d21-5a96-8dda-190c8bb6e3e5 | note | Standard / Specification - Downer
613458d8-44b8-5f7b-aa36-ddd3ce4f2886 | note | Verifying Document - Photo Records
706b1d90-4936-5f76-ab5e-a6ac12da6b19 | note | Frequency - Post construction
88958877-a040-53a7-a425-18f857a2b216 | note | Verification Activity - H
b80fc67a-8a18-5aef-addc-224f7da47377 | note | Verification Activity By - SE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
0f134822-e5e9-519f-a500-5f3884b5f95f | checklist | SYS - AREA 1A CH1540-CH1740 SIL |  | AREA 1A CH1540-CH1740 SIL
3969119e-9d77-5427-b958-ecc82f083c46 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
4b26e7cb-ace0-58bb-a616-39483fc6b83d | note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence
39bdd60b-5a55-5725-9d44-67dc819f7e82 | note | Standard / Specification - Downer
f37b21b6-fe75-518e-99e7-441bb2e54568 | note | Verifying Document - Construction Pack
e20b4b8a-d1f3-5800-add6-1b620896d23b | note | Frequency - Prior to Works
2c256560-e7aa-55c9-98a1-86938a36f071 | note | Verification Activity - H
5aa00b7c-8cab-5b58-9c8a-a8ebcd4457f9 | note | Verification Activity By - PE
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
e3e94e95-7461-5602-8ae5-1f475a9a9372 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
a9ccfcea-23ab-5f83-98aa-01aa55f14f09 | note | Standard / Specification - Downer
bd924ba3-e98a-5a37-88f8-deb39c1915c3 | note | Verifying Document - Survey Records
21d5543a-b500-5bb2-b23b-7150daaf8fee | note | Frequency - Prior to Works
8155419d-e2cb-5987-8b90-4a5df3da5317 | note | Verification Activity - H
651d4ceb-5a87-5cee-aa2f-1d5af93f48ca | note | Verification Activity By - SV
a24a2c58-bf6f-5474-883c-40044bad1fc7 | checkpoint | 3.01.03 - Service Location
beea7a1c-046b-5fb7-91cd-46b86eb7ecfd | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
8c0340ae-3f3f-57df-8af6-8836db439d12 | note | Standard / Specification - Downer
eaababd1-32a0-5323-ad8b-8e999dafd51d | note | Verifying Document - Excavation Permit
558c19e0-5e33-5b6a-a931-c34e81e92a2c | note | Frequency - Prior to Excavation
85387089-5afd-5a2b-974f-78eb26637df0 | note | Verification Activity - H
33484b60-704b-5d44-8ca8-0d2f7803fb57 | note | Verification Activity By - SE
0a214a7a-124a-5898-a837-e29e83751df0 | checkpoint | 3.01.04 - Internal Permits
24c5b6b2-98a4-589a-a0ad-fa73c558e90d | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
f1ead7c5-425d-5829-b8d1-0edd0ebada26 | note | Standard / Specification - Downer
7bc080ae-d60d-55ed-9e48-c9efb7f6d7ce | note | Verifying Document - Internal Permits
f051067e-abc8-58c0-96b0-6932e794b31d | note | Frequency - Prior to activity being undertaken
518ffaca-a960-5750-b6b8-c85a4e56025c | note | Verification Activity - H
cfe1cce4-c9a2-53b0-9062-99d2666b7ccb | note | Verification Activity By - SE
917e2881-0901-542f-ae25-686bf9c47009 | checkpoint | 3.01.05 - External Permits
b2e25bb1-ceae-59ce-be7a-ac0fa86efbac | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
26281c77-fff7-5dd4-88f3-7e33e61e9cbf | note | Standard / Specification - Downer
fb232d0f-a63d-56c9-8cef-c489fe97494c | note | Verifying Document - External Permits
9e657bb1-bd49-5ffa-98e1-3b2ad9d187b6 | note | Frequency - Prior to commencment of activity
8037d5ba-0dd4-5d90-9102-4cba9dadd771 | note | Verification Activity - H
62198747-f56f-5a64-8a05-cde299bdfa49 | note | Verification Activity By - PE
a1302970-0389-558d-b43c-67b14bbfc27a | checkpoint | 3.01.06 - Approved Construction Drawings
bb46b8a2-0124-5764-b4dd-7bdf0e69e95c | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
f9faecd7-6ccf-5952-87fc-e7dc6b36747a | note | Standard / Specification - Downer
030bf603-8060-5f9d-9f7a-d5e4d6516677 | note | Verifying Document - IFC Drawings
73c5b094-94c7-5167-9ef9-037fd27c4209 | note | Frequency - Prior to works start
cefe589e-775b-5225-b22e-07aa1e40a577 | note | Verification Activity - H
434a1998-8714-52c5-bd16-87cddbd9fb72 | note | Verification Activity By - PE
5fe0af18-de1c-5a52-a24a-6d199c43ea87 | checkpoint | 3.01.07 - Previous Layer QA Sign Off
6983331f-cd49-553d-9d1b-2fb72a289629 | note | Acceptance / Conformance Criteria - All Previous layers signed off, QA complete. Including subgrade, SW, WW, WM. Ensuring everything up to the bottom of SIL is compliant.
915f2668-b583-53ab-a791-7764dde86a86 | note | Standard / Specification - Downer
77414674-0ef9-565c-bd1e-9e79630527df | note | Verifying Document - QA Records
f3a3f4b4-c411-555b-86c7-ecf46bcdf601 | note | Frequency - Prior to works start
c6466e5e-b003-544d-bb6f-6a7c079699e2 | note | Verification Activity - H
e1d16e4b-df18-54d6-933a-5129d5ba5833 | note | Verification Activity By - PE
f235ea97-6575-526f-981f-e1d053fa1d5c | section | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections)
7d5180df-d4eb-55e4-af4d-0e923a86f4b9 | checkpoint | 4.01.01 - SIL Inspection
589c641a-aa63-5852-9ee0-74bb69e89f17 | note | Acceptance / Conformance Criteria - Prior to placing of sub-base pavement, to include proof roll, inspection of extents of works, general shape, and tidiness, free of organic or contaminated material, review of Benkelman Beaming of the SIL and final levels.
63d5d160-5d5e-5d1c-8f98-de84fd1bffb8 | note | Standard / Specification - PS - 2.2.16
c3cb4613-e4f5-5cfc-b1af-22f8b68c2820 | note | Verifying Document - Hold Point Release
c154df35-5954-5684-b09e-81eb77940267 | note | Frequency - Min 48h Notice
af005a20-54f3-5277-886e-7af9e988939a | note | Verification Activity - HP
18fb0707-f3d9-5d50-af1f-10287369254f | note | Verification Activity By - ENG
22c63970-dca6-5fd1-8231-ea707288aa18 | signoff | AUTHORITY HOLDPOINT
62f939d2-18c6-5474-abaa-4e5cecc5daba | checkpoint | 4.01.02 - Subgrade Inspection
ccdd5453-ce4a-5556-99a1-e628c9df66ef | note | Acceptance / Conformance Criteria - Proof roll, Scalar penetrometers, and shear vanes prior to SIL fill commencing
4bc1e182-7aa8-55c3-b605-7ac285d42607 | note | Standard / Specification - PS - 2.2.16
d3d56a58-b3ff-5de8-80eb-b959f7028b02 | note | Verifying Document - Hold Point Release
daf11b30-c8b1-541a-9e0a-1f48878bd249 | note | Frequency - Min 48h Notice
3f765b21-ec87-5fc9-b2c0-516f6ba42d38 | note | Verification Activity - HP
54909fee-8367-537a-913e-c78a0b548259 | note | Verification Activity By - ENG
7ad2b75a-44c0-5e3d-b3c3-e0084f7839d0 | signoff | AUTHORITY HOLDPOINT
b3826b6c-de4b-591c-a488-5e8079ba2150 | section | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 Subgrade Materials
fcd729d9-871b-5ce2-b7a9-fc012a97901d | checkpoint | 5.01.01 - Pavement Subgrade CBR
b3e03a0d-8900-51ac-be82-923b82921d09 | note | Acceptance / Conformance Criteria - The pavement design requires a soaked CBR of not less than 10 within 1.0m of the bottom of the SIL layer and 4x DCP's to a depth of 1m below subgrade level in a 1m grid around the in-situ CBR test location and 4x NDM's DT with a probe depth of 300mm in a grid around the in-situ CBR location. CBR testing of the subgrade shall be carried out by the Contractor prior to final trimming. If the soaked CBR is less than 10 the Engineer may instruct changes to the pavement design. (Push tube for Cut and Filed sample for Fill). Invitation for engineer to witness CBR testing. To be accurate representation of site
8bc2d425-ceb7-5734-bb77-d28559cf4dd1 | note | Standard / Specification - PS 7.1
7a8b0934-9135-54fb-b2a4-e6b80a154256 | note | Verifying Document - IANZ Lab Reports
1086e7dd-eabe-514b-87d6-33b88e67f9b1 | note | Frequency - One test per 2,000m2, with a minimum of three tests per material type.
d8f0f437-a191-57db-ab63-ab5fa84405d2 | note | Verification Activity - HP
07eb9ac4-2f53-5c6b-9ec0-d3b5327d7a95 | note | Verification Activity By - ENG
93c1095a-43a9-5d7d-be8f-7a7cdce201a4 | signoff | AUTHORITY HOLDPOINT
fac294aa-8548-5fc8-bb58-2088ac62dc7f | section | 5.02 - SIL (Clean Pit Sand)
75e3c18b-3bc3-5384-a690-0b943edb28e2 | checkpoint | 5.02.01 - SIL Conformance
7b7cbf9c-e8ee-5e03-b9c4-19e9defd7ac5 | note | Acceptance / Conformance Criteria - The SIL shall be pit sand meeting the following requirements: · 4-day soaked CBR (NZS 4402:1986 Test 6.1.1): Shall be ≥ 30. · Organic Matter: It shall be free of organic matter. · PSD (NZS 4407:2015 Test 3.8.1): Shall be <7% passing the 75μm sieve.
ab9dc707-18c8-576e-aaac-433561430047 | note | Standard / Specification - PS - 7.2.1
68faef9d-392a-59d7-bcaf-6fa1bc1f1e4f | note | Verifying Document - Lab Reports
c4fedb90-397f-5d70-8393-ddd5f80bc3ef | note | Frequency - CBR and PSD testing shall be completed at the rate of 1 test per 2,500m3, and being no less than 1 test every 3,000m2 (placed).
2aa170d9-fa30-5034-aee7-9c13a2cf0362 | note | Verification Activity - HP
ff1df35a-76b1-5238-93f8-cfc823b7b0f1 | note | Verification Activity By - ENG
d189a4e6-f601-5569-9fc1-1d87e656f0fe | signoff | AUTHORITY HOLDPOINT
e318ec15-f915-557b-9af7-5c5cf6c32ccc | checkpoint | 5.02.02 - SIL Maximum Dry Density & Optimum Moisture Content
a27e8fb3-c719-5968-a595-666a016a330e | note | Acceptance / Conformance Criteria - The SIL shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density & Optimum Moisture Content
9401944b-e210-541c-9a33-a939c9d05c3e | note | Standard / Specification - PS - 7.2.1
008a0244-1f95-5a7a-9e8d-80305a50d1ed | note | Verifying Document - Lab Reports
05358614-5f37-5794-981b-b6ef430b82c7 | note | Frequency - 1 test per material type and no less than 1 test every 5,000m³ (in place)
0e569234-ac64-532c-a6a1-d7a30e8d6b76 | note | Verification Activity - HP
73f1f2dc-3ee4-55d4-a027-2e6d2c716e44 | note | Verification Activity By - ENG
efde04cf-22a7-574a-b477-9b8b7846f4a8 | signoff | AUTHORITY HOLDPOINT
5c6bf488-9018-5698-aa4c-b7cc685e8eb0 | checkpoint | 5.02.03 - Plateau Density Test
4d47d092-b781-5579-afbe-d0a041d3ac9d | note | Acceptance / Conformance Criteria - Compaction shall be undertaken using the higher of the two density targets. Plateau tests to be spread out evenly to be an accurate representation on what is coming into site.
3646b1f1-33f8-54ed-978d-3519e10c9441 | note | Verifying Document - IANZ Lab Reports
292f8656-46b5-5e25-9d81-b6c1be49f298 | note | Frequency - 5 tests per 10,000m2
cf700307-c8b6-5b85-8348-1951da8bab5f | note | Verification Activity - C
c2e994f8-60dc-5a5e-808d-82e1602f55ad | note | Verification Activity By - ENG
1cba0748-82d5-5f8d-9319-32091b6769d0 | checkpoint | 5.02.04 - NDM
a65fdecb-7522-5aef-8f72-c9c72775f831 | note | Acceptance / Conformance Criteria - Mean Value ≥ 98, and Minimum Value ≥ 95. All NDM testing shall be undertaken via Direct Transmission method at 300mm probe depth.
737f32a6-ca14-58fd-aea3-8aff714c61e6 | note | Standard / Specification - PS - 7.3.1
e55891f8-d0de-516a-b9c8-54ad6ca789e9 | note | Verifying Document - IANZ Lab Reports
df80991c-456f-5a22-94b9-66aea17bf2ea | note | Frequency - 5 tests per layer per 1,000m2
ddeea918-5e1e-53c5-bdb0-567b4a7edd31 | note | Verification Activity - C
fa4e54ea-eb3c-5011-b31b-85f88f881e0f | note | Verification Activity By - ENG
5c910787-b40b-5937-881a-26cc5ec60151 | checkpoint | 5.02.05 - Benkelman Beam
f1e57e77-c46f-5c32-a4b7-5c36a4a04f61 | note | Acceptance / Conformance Criteria - Target Benkleman Beam deflections on the top of the SIL layer are 1.6mm (90th percentile) and a maximum of 1.8mm
4f236964-6a78-58bb-a2ad-29ca204c836c | note | Standard / Specification - PS - 7.3.1
9af0f383-b583-5491-8e2a-112b9bbfe9b3 | note | Verifying Document - IANZ Lab Reports
f7a61f4b-00fa-5389-858d-3782c067994b | note | Frequency - every 10m of each lane – staggered between left and right wheel path.
70f2fcc9-b04d-51bc-a428-0e43ad15a03b | note | Verification Activity - C
e7ad119b-d74a-5d5c-b2d6-3a42d6de70a8 | note | Verification Activity By - ENG
937d3289-52f9-5ac5-8c90-59cd2914799d | checkpoint | 5.02.06 - Organic Material
b3e67920-8037-5400-8c1c-642e5ee8991f | note | Acceptance / Conformance Criteria - Ongoing visual and physical inspection for any roots/organic material, photos of clean sand, and any organic material removed.
a0c385bf-bf9c-5c1c-ac4e-583139a2d735 | note | Standard / Specification - PS - 7.3.2
936b6251-f4a7-5a3b-bf3c-24cba6f93080 | note | Verifying Document - Site Records, photos of clean sand, and any organic material removed
db82440f-7ec5-5382-8705-2ae2bae059b1 | note | Verification Activity - I
b5079f59-52f0-5920-ac35-007512183c86 | note | Verification Activity By - ENG
c269ea2a-2959-5cb8-b76b-38dd023d527b | section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.01 Construction
9b03c2bc-c48f-5466-8d4c-04b6d0c3c01c | checkpoint | 6.01.01 - Subgrade Prep
3314eb0a-8401-58d3-a782-af26e847ee14 | note | Acceptance / Conformance Criteria - The subgrade shall be prepared in accordance with the requirements of the Geotechnical Works Specification in Appendix B, including proof rolling, Scala penetrometer and NDM testing at the specified frequencies.
4832cdc2-16f0-54fb-b9f5-b13fd4db465b | note | Standard / Specification - PS 7.1 GWW
4d5bf8ee-a1ae-53dc-83a1-b890969d9705 | note | Verifying Document - Completed Earthworks ITP
81025f5f-e79f-5ae5-98f3-223c68ae7b80 | note | Frequency - Prior to Pavement Works
08eae87e-fbb1-52e4-abc1-c936b9f15f93 | note | Verification Activity - HP
531c5d6a-0940-5478-b658-d32ba101608b | note | Verification Activity By - ENG
e2d45569-ffc7-5edf-af41-be24dc51077f | signoff | AUTHORITY HOLDPOINT
565e4230-204c-5dff-9c26-c4b4d7ec8e26 | section | 6.02 SIL (Clean Pit Sand)
db9fd37d-3155-5bfc-a59e-7698b9c5a10b | checkpoint | 6.02.01 - SIL Scala Testing
dcff1fcc-0468-5c64-97ec-07f5bb15626e | note | Acceptance / Conformance Criteria - In addition, the SIL (tested in accordance with PS Clause 7.4 below) shall achieve a Scala penetrometer blow count no less than 10 blows/100mm. Depth to be 1.5m from top of SIL.
4163e9ea-e5a1-5798-9f16-4efc158777b9 | note | Standard / Specification - PS - 7.3.1
e34d2610-b9ae-5077-ba99-de1bc7d627bb | note | Verifying Document - Scala Results
9faf4a1c-754c-5fea-ade0-407e75652614 | note | Frequency - 1 test per 200m2
894e4cdf-7c9d-5780-a212-8b8d34c34071 | note | Verification Activity - I
7f61f95f-4eb2-5bcd-b43f-2b57f7050d3c | note | Verification Activity By - PE
e46181c1-7bbf-535b-8314-791da9fafd9c | checkpoint | 6.02.02 - Layer thickness
3f529307-5392-5a66-acbb-081265d82c69 | note | Acceptance / Conformance Criteria - Each layer shall be checked to ensure the required layer thickness is achieved of Maximum
0fa5048b-d270-5ea1-9593-a35fc1bbadaa | note | Standard / Specification - PS - Table 7.2 - 2.2 NZTA B/2
f5c571b2-b56a-5c59-8c5f-481204083b8b | note | Verifying Document - As-built data
5c79b190-c473-5a2d-9a81-4b6cf4384c9d | note | Frequency - 1 test per 20m
940c333f-fade-574e-82a7-6ece487ed079 | note | Verification Activity - I
da0419c8-3af1-55d4-a644-463ad1be3e53 | note | Verification Activity By - SE
1e0af15d-264a-5748-b80e-858ba1933f81 | checkpoint | 6.02.03 - Plateau Density Test
20cea371-9a84-570b-8d74-aa280094c8ab | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. Plateau tests to be spread out evenly to be an accurate representation on what is coming into site.
0aa05dd5-ffc9-504e-9a7c-60990433443a | note | Standard / Specification - PS - Table 7.2 - 2.2
51fc55fa-f4bd-5d31-af32-b4186c256bfb | note | Verifying Document - Plateau Density Report
0118de71-b76e-5cdf-8df4-d9032daf63dd | note | Frequency - 5 tests per 10,000m2
24168a1d-4d75-5639-b2fc-a4cbf8e189ca | note | Verification Activity - I
d016790e-e344-529a-93dd-38a52669b805 | note | Verification Activity By - PE
d963eff8-38eb-5e0f-8cb5-5ca02792d6bd | checkpoint | 6.02.04 - Sand SIL layer compaction
dfb1d2fa-07ef-574d-824b-bdc7ebddb7a7 | note | Acceptance / Conformance Criteria - Further to Figure 2 of NZTA B/2, the acceptance criteria for compaction of the sand SIL layer shall be a Mean Value ≥ 98, and Minimum Value ≥ 95.
80e7f2c7-ef44-58a0-a547-4edbf52dec16 | note | Standard / Specification - PS - 7.3.1
72f78430-a5d7-5df8-88f4-eb2aab833a7f | note | Verifying Document - IANZ NDMS
09a46328-eb63-5bf7-b4b2-789d16cf2ce4 | note | Frequency - 5 tests per layer per 1,000m2 (Min per lot)
aac1ee29-8af1-503f-a4ab-7102ea90cd06 | note | Verification Activity - I
b6d28b73-0c57-5903-886a-50e7c7b030f5 | note | Verification Activity By - PE
b7da25a2-1706-56d9-bf0c-ab152740d6a3 | checkpoint | 6.02.05 - Proof roll
07b326c3-ea68-549d-9128-c3000d49c9de | note | Acceptance / Conformance Criteria - The SIL shall be tested via Proof roll prior to Benkelman Beam testing. Proof roll to be under supervision of engineer and verifying document to be signed off by engineer.
f5e9d4dc-40e8-58cf-a4aa-b27c60255de8 | note | Standard / Specification - PS - Table 7.2 - 2.2
564d8205-b741-54d5-b073-d48e5d67d9c6 | note | Verifying Document - Site Notes
75ed5345-a8b0-52aa-bbc1-534c1cbcdb82 | note | Frequency - 1 test per 20m
e7f0260f-c6f5-50d7-84e5-50a351b4280e | note | Verification Activity - HP
61899164-dfe5-5bc3-b907-b5b068e82afd | note | Verification Activity By - ENG
8aeb4571-3694-52c9-a22e-a9dd129ae2d7 | signoff | AUTHORITY HOLDPOINT
a0785380-fd61-5bfd-8678-a44a68ec5f7a | checkpoint | 6.02.06 - SIL Benkelman Beam test
1474a3bc-5812-5d34-93c3-2a76dbcbc6d8 | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be carried out on the top of the SIL layer at the rate specified in PS Clause 7.4 and reported to the Engineer. Target Benkleman Beam deflections on the top of the SIL layer are 1.6mm (90th percentile) and a maximum of 1.8mm. Performance verification of these target deflections shall be confirmed by the Engineer on review of results from within the pavement Stabilisation trial (PS Clause 7.3.3).
04c2be5d-e694-5630-ae8f-3cd00f7c3b8f | note | Standard / Specification - PS - 7.3.1 PS - 2.2.16
b519543d-4049-5ba0-bd30-397138d05564 | note | Verifying Document - Benkelman Beam Report
2acdff5b-4e24-5f1d-87a6-475ceff0ac5b | note | Frequency - every 10m of each lane – staggered between left and right wheel path. Min 48h Notice
e4b7f0ea-806f-538d-9a07-d162c6b4f901 | note | Verification Activity - HP
62e03724-57d9-548c-9937-de3062eaf727 | note | Verification Activity By - ENG
3c89b0ec-4be3-513e-abf0-367c5d158a5c | signoff | AUTHORITY HOLDPOINT
10f025ff-7251-5430-bf3b-56f5dcf76850 | checkpoint | 6.02.07 - SIL Inspection
add1780d-3465-530b-bd7c-6b3040e3182b | note | Acceptance / Conformance Criteria - Before laying of any pavement SIL and metal courses. SIL inspection to be carried out under supervision of engineer, verifying document to be signed off by engineer.
aaa691c7-ddbd-559c-b7d2-ece1f6df8a75 | note | Standard / Specification - PS - 2.2.16
62109f41-cacd-5114-9387-f25dd7090a0b | note | Verifying Document - Hold Point Release
53749f59-1a97-5155-aa0f-01f9dede2b1c | note | Frequency - Min 48h Notice
8cf9b4d1-106e-5b75-8410-1d614ffa90d2 | note | Verification Activity - HP
c500ca95-c927-5ef8-8063-ff8836fab8fe | note | Verification Activity By - ENG
97bb6f89-11b3-5fc7-a453-48b0f0ec5d36 | signoff | AUTHORITY HOLDPOINT
9e953047-9f70-59b5-9189-aff3fc3bb70f | checkpoint | 6.02.08 - Topography
bb8d94d0-cad7-5b1c-8c9b-72bfccbba337 | note | Acceptance / Conformance Criteria - Carry out level check on trimmed SIL. Survey conformance with Total Station. Tolerance = -30mm +0mm (NZTA F/2).
dfea0969-3fe2-5fb8-b6e2-71a12b4b8f40 | note | Verifying Document - Survey PDF against IFC or similar
c4f76caa-a1e7-5193-a040-20aa641b2936 | note | Frequency - every 1m across the road (avoiding islands) at 20m intervals
9af73578-466b-5e6f-8458-cf20471145cb | note | Verification Activity - I
0f251313-de06-520b-8bad-69923864004d | note | Verification Activity By - ENG
b4bfcba9-7ebb-50d5-ac19-ccbd0eaf5f97 | section | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
8d4e531c-688a-5145-b348-98da13114f31 | checkpoint | 7.01.01 - Construction Record Compilation
e33b7f2d-364e-554c-bbc9-71565eeabdcd | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
02cb16d6-62a9-5c07-b1fd-9212d27af6d9 | note | Standard / Specification - Downer
d5242ce2-72cf-5b1b-93ee-f2289178affc | note | Verifying Document - Records
89f45c46-bd82-5272-9f96-7c18301858fe | note | Frequency - Post construction
e3b23594-8fa7-5800-9495-7772a6d9da38 | note | Verification Activity - H
1f3b92d1-88f6-5192-86a8-d876bfc05b8f | note | Verification Activity By - SE
19dccd2f-6441-5680-bbbb-459afb3e1dd8 | checkpoint | 7.01.02 - Survey Records
09ede6c8-4248-52cc-ab76-a1b266afc9e7 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
64e2281b-04ef-5dd0-a95a-ed86a87e480f | note | Standard / Specification - Downer
c7cbca71-5e4d-5ee2-9c7e-338c155a00cc | note | Verifying Document - Records
6bfdd8a6-0e45-5a32-b543-6abfceba1022 | note | Frequency - Post construction
b936ae2a-5b7f-575c-b00c-96f40edeb440 | note | Verification Activity - H
239d20eb-1cda-5151-8ee0-a1a37fa759ad | note | Verification Activity By - SV
b068bae6-2ef0-5d88-81c8-4fb6749be6b3 | checkpoint | 7.01.03 - Redline Drawings
4d55e902-6fc9-5949-bd90-3718360ae31b | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red line to show any increase in SIL depth.
92347465-5877-5da6-87bb-b262af7857d7 | note | Standard / Specification - Downer
9dcd9ed1-320f-5caa-9c10-bea4580085c4 | note | Verifying Document - Redlines
3bb64a96-941d-58a0-8054-c7df7e8a417b | note | Frequency - Post construction
34016d76-9cb7-5f99-ac70-5ccdd07ac80a | note | Verification Activity - H
dc0a719b-c026-5d33-b5c3-421f855beb57 | note | Verification Activity By - PE
ca736c77-5920-4e0f-82e8-146475b3817d | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
b5fd08b2-ee88-5ce1-91b3-6c1fd4ac0545 | textbox | Contractor's Rep Name:
53c21e80-33ce-5f6b-b9a2-88aaf40ec97d | textbox | Engineer's Rep. Name:
d2d065a7-7178-5fcd-8495-f61b9960bc30 | date | Date:
379ce9b3-911e-4712-b425-4c54a06f9792 | signoff | Add Signature
99ed02bc-8a41-5d23-8ba4-07b1a5ad16b8 | checklist | SYS - Beam A1 | itp | Beam A1
6c8b6b73-6473-5f13-adda-ca5e8c131c88 | section | A. Pre-Construction
d0b118bf-4866-5dfd-a7a4-3cb57a95fc8e | checkpoint | 1 - Shop Drawing Approval
7f551341-4092-5f41-b608-365d16f7af0a | note | ACTION (Hold, Monitor, Witness) - Hold
21a25c85-7669-5e43-b881-cb382d0cdcf1 | note | Detail - Shop drawings to be submitted for approval.
bffa2df9-33f7-511b-b3fc-ab1be1a76bea | note | Reference - Structural drawings
665c516d-76b1-5aa6-9126-10f6537864fd | note | Frequency - Prior to casting
f573a840-2c00-5fb2-b5ab-a06cf4dd26d7 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
94e10edb-c26e-5561-a211-7af1d2f73c9a | note | Conformance Criteria - Approved IFC Shop Drawings
a578b38c-a938-5cc7-a081-f444b003b6cc | note | Records - Client approval
0eb78f61-f25f-583d-9e72-ec868b88f33f | note | Responsibility - Project Manager
46a3e53b-75cc-5a54-afb9-d71434340129 | signoff | HOLD POINT
f19fea31-2d56-544c-8b5c-1d88d82f2dca | checkpoint | 2 - Concrete Mix Design Approval
b4a7e83d-f7e2-5386-a8d0-bdce94a58340 | note | ACTION (Hold, Monitor, Witness) - Hold
a361c484-876b-5df1-ab52-16c3d4d3a3d1 | note | Detail - Concrete mix design to be submitted for approval prior to concrete being supplied to site.
1742277d-7193-50aa-8080-d6b50de0bcde | note | Frequency - Prior to casting
9dc02ba3-edcd-52e5-ae2e-27beb06afe27 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
8aed14d2-9e72-5d42-9292-552147cc8c76 | note | Conformance Criteria - Minimum compressive strength at 28 days 60MPa. The mix design to comply with aspects of the contract specification.
3eb4a396-88d9-5085-a6a0-3eff50c8f8db | note | Records - Client approval
8c70c253-b98f-5db0-aa4d-6fe8b1c7b33c | note | Responsibility - Project Manager
42a2780b-6b9b-5f60-ba21-16129f643dea | signoff | HOLD POINT
f429301c-ca52-577c-ac36-680c886f0f24 | checkpoint | 3 - Lift Design
72a3e126-69fe-5331-8d3c-3cb9bed90c53 | note | ACTION (Hold, Monitor, Witness) - Hold
8e3c3373-6ac1-5937-81fe-bad027c8e376 | note | Detail - Lift design provided for units demoulding, storage and transportation.
247154f6-4b94-573f-b348-c9c4696d731f | note | Frequency - Prior to casting
e2060d2f-34fe-57ac-b22f-dc007a76e3d5 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
a79b995c-26bc-5e0f-9381-9f98a434f799 | note | Conformance Criteria - Specific Lift design (Lifting eyes and position) produced and followed
3483a0fd-cc1f-59a7-b920-e5e057f9c41b | note | Records - Lift design Shop Drawings
b905620a-4d8d-5d4e-a3a7-53824569a358 | note | Responsibility - Project Manager
d8703e80-0411-5b56-918e-675a5eb7b7e9 | signoff | HOLD POINT
0a8c134b-db66-5671-ab98-07875080f8ec | checkpoint | 4 - Steel Reinforcement compliance
8a87d0fa-e2d7-5382-abbb-7559965df98c | note | ACTION (Hold, Monitor, Witness) - Hold
dc2aa740-0704-5c57-9315-5bd3434e5084 | note | Detail - Mill certificates for steel reinforcing to be provided
84b89b85-f301-5869-80df-0741626d9978 | note | Reference - AS/NZS 4671
0be59b34-46b4-59f8-be20-5324c088df7b | note | Frequency - Prior to casting
e18e88e4-798f-5709-9d17-caeba780f4f5 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
435840fc-5c7e-5ed7-8196-c57795815028 | note | Conformance Criteria - Steel to be manufactured with ACRS certificate details and verification
9aef982d-f1ee-5d4b-8c43-aa4585465456 | note | ○ Mill certificates to match ACRS certificates.
4a9eef66-564d-52e1-bdb1-749ac415648e | note | Records - Mill Certificates Detail sheets Test Certificates
224e08df-d43c-5baa-850c-365e78cbec56 | note | Responsibility - Production / Quality Coordinator
6416c12c-d6f1-5877-99c9-3798aa512c21 | signoff | HOLD POINT
feaffeb9-02cf-5eff-a2da-f2aba24f5112 | checkpoint | 5 - Steel pre-stressing material (Strands) compliance
31c2bab4-6967-5982-8252-679329640788 | note | ACTION (Hold, Monitor, Witness) - Hold
e6226ee2-84ea-510d-a413-1f05e36cbfda | note | Detail - Mill certificates for prestressing strand coils to be provided
32cd856e-af64-555b-bbcb-beafca175edb | note | Reference - AS/NZS 4672
0d6a44bf-7515-528e-b9ff-e27410caf60a | note | Frequency - Prior to casting
24a4e194-84f5-5cc7-bc56-9844e407437b | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
ad0406fe-662b-544c-87dc-3fa17e11c21e | note | Conformance Criteria - Prestressing strands (coils) to be supplied by ACRS accredited Manufacturer.
e681fcf6-ed21-5216-bdd0-c80ff47f280a | note | ○ Mill certificates checked against size, type and strand - mill certificate to match ACRS certificate
661a7406-1789-5ca9-8dd1-9ff81b2232f8 | note | Records - Mill Certificates ACRS Certificate
f3e0a21c-8f19-552d-acf6-27af1d03f4df | note | Responsibility - Production / Quality Coordinator
613c6cdd-2b14-54c6-91fb-ff2b855bb469 | signoff | HOLD POINT
b7d4cbf2-f5ad-5ae7-ab1c-e12d844f077f | checkpoint | 6 - Design Stressing calculation
02e5ba00-1841-508e-88e9-39d62acb03da | note | ACTION (Hold, Monitor, Witness) - Hold
b61dc034-995f-5a8f-b50b-d857eafda1d1 | note | Detail - Design stressing calculation and calibration certificates to be submitted to the Design Engineer
c04a58dc-439f-5d7d-8fa1-63ff20c0c2d8 | note | Reference - Structural drawings
22e98be8-f1e3-57fc-a027-d820b4865448 | note | Frequency - Prior to casting
84a194d4-cd04-59ef-bc72-be360077947b | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
23dbf582-8563-551b-b047-6676ee83726d | note | Conformance Criteria - Expected extensions and gauge readings to be calculated for each cast.
0460bfcb-18af-53d5-84e9-334ab18aa823 | note | Records - Design Stressing Calculation Calibration Certificates Client Approval
b7f2b866-abde-5ca0-9e68-6218a4aed178 | note | Responsibility - Project Manager
d11d0c5b-a9a2-5352-8a9a-8040f61d2da4 | signoff | HOLD POINT
cc6ef693-d53c-5381-8589-6b47637220de | section | B. During Casting
ae49fb65-5ec8-5106-a68e-1fa4bdb19de1 | checkpoint | 7 - Steel Reinforcement cage assembly
bbb86996-1306-53de-92bd-7b21db04436e | note | ACTION (Hold, Monitor, Witness) - Monitor
d6e9e554-3562-5659-b411-0a6dbf8fd943 | note | Detail - Steel reinforcing cage to be assembled and inspected.
d724b6cc-c017-5e9a-9bea-8e52bbcf82ee | note | Reference - Approved shop drawings
d7ab26fa-5758-5365-8712-d8e50b24bf35 | note | Frequency - Prior to each cast
3f6e926d-9ab1-5a6e-bdcc-89f9f4436e82 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
15bc6d2f-fa18-5f0b-ad6a-c27f4c806501 | note | Conformance Criteria - Cage assembly to comply with correct size, class, length, shape and location/spacing as specified in shop Dwgs.
a5492493-815d-5d4a-900f-e4bce94a1b05 | note | ○ Free from visual damage.
022fa99d-8580-5db1-94d3-9fbbb8691e3b | note | Records - Pre-Pour Inspection sheet REO detail sheets
9cfbf8d0-b2c5-52d9-bb65-65a95a91455f | note | Responsibility - Production / Quality Coordinator
20fdc9c5-8386-5839-a7a9-a01dc047c7df | checkpoint | 8 - Mould Preparation
43fe340e-b9b0-538d-8621-ba7f3318bfb9 | note | ACTION (Hold, Monitor, Witness) - Witness
fe206031-d2ba-5e19-857b-d0740b5960e0 | note | Detail - Before casting ensure mould has been prepared to comply with tolerances.
0c681922-0513-523e-bd51-52e5225d4a57 | note | Reference - NZS3109 Table 5.1
91ae295d-84a2-5001-8bba-931750dbddd5 | note | Frequency - Prior to each cast
4663dd7a-dc7f-5241-a762-c541366ac4a8 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Measure
c26ea311-eda5-540f-89f0-1c218f3670a9 | note | Conformance Criteria - Tolerance on placement of moulds shall be a per NZS 3109
00d231e6-2d84-5b52-b840-9513bd292965 | note | Records - Pre-Pour Inspection sheet
76e7dcf0-de89-5a71-b6bf-23284989ec0c | note | Responsibility - Production / Quality Coordinator
3e4b9585-9ca9-5197-acc4-c8df288417f1 | checkpoint | 9 - Pre-Stressing
9c5e267f-852c-5784-bb06-b77b0f341dd4 | note | ACTION (Hold, Monitor, Witness) - Monitor
156da291-3e2f-538c-a6f1-8f01b26d7867 | note | Detail - Review actual strand extension/pressure compliance with approved design calculation. Draw-in measurements to be taken and recorded
89d5f0b4-87a3-513c-a8bb-fde46de78203 | note | ○ Check that debonding has been included as required. Debonding shell be by plastic sleeves around the strand.
53513eea-415b-5397-bace-18380b39200a | note | Reference - Approved shop drawings Design Stressing calculation
f6443357-0e8a-5be2-920f-9388d9a4ce65 | note | Frequency - Prior to each cast
dc95e6dd-a9f5-513b-ac08-2eb177d117ce | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection/Measure
ee1c4d01-6f3b-50de-a259-994acbbcca4a | note | Conformance Criteria - Stressing data/records reported on stressing calculation sheet.
d94f394f-2237-54c6-ba30-aaa4093be6d7 | note | Records - Stressing Calculation sheet Pre-Pour Inspection sheet
6c33327f-4ece-5777-8fbe-9a8e26d44332 | note | Responsibility - Stressing Controller
fa37f0bd-e6ea-55a3-96b8-11656964e3e5 | checkpoint | 10 - Steel Reinforcement Placement
71101c6f-a534-50b3-9511-2c6063359adb | note | ACTION (Hold, Monitor, Witness) - Witness
f1dd1e46-5c1b-5492-8045-ebc58b503aa4 | note | Detail - Reinforcing steel shall be handled, placed as per NZS 3109.
340e129f-d759-5aab-bbf0-6227e531e49b | note | Reference - Approved shop drawings NZS 3109
b691864c-eca4-5a3e-8d5e-a3aa6ddb08bd | note | Frequency - Prior to each cast
6c971a7b-073f-51bc-b5a5-0e8064f8f469 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
697d608b-a8b9-5e91-9866-7308204ce618 | note | Conformance Criteria - Steel reinforcing cage placed as per approved shop drawings.
c043c1fb-3973-50ca-80a1-8f4434cc8a56 | note | ○ Spacers shall be installed evenly to ensure correct cover as per shop drawings achieved.
4d4e6ca6-fc8c-567f-8dad-6d34b9197e87 | note | Records - Pre-Pour Inspection sheet
7f2a04b5-c7b0-53ef-b90e-14b915df5dc7 | note | Responsibility - Production / Quality Coordinator
778a00b0-3496-571a-93d9-dc583bfe2a5b | checkpoint | 11 - Cast-in Items
fe536922-ec0a-562b-8b32-da5cfe699326 | note | ACTION (Hold, Monitor, Witness) - Witness
7e6518c4-5902-5d48-880a-df652300e336 | note | Detail - All cast in items positioned as per shop drawings Lifters positioned as per lift design
fd745cbd-6b98-54d4-962f-e79c3285daac | note | Reference - NZS3109 Table 5.1 Approved shop drawings Approved Lift Design
f6f59f88-e7d5-54ce-9107-a68ee4b8806c | note | Frequency - Prior to each cast
662e8aa6-b9aa-58e6-9bb8-f5657702a15d | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
aca746dd-5131-5204-9a2b-f1cc75f1b6e6 | note | Conformance Criteria - Correct type and number of cast in items used Correct Lifters used, positioned in accordance with approved lift design
2ef43b5d-e49e-58dd-bb51-00dc5a337802 | note | Records - Pre-Pour Inspection sheet
eab0fc36-07a8-5e5a-b470-6c5fe90648d8 | note | Responsibility - Production / Quality Coordinator
7fbac7e8-a6c6-5c26-b4fc-6094fd0eaff5 | checkpoint | 12 - Pre Pour Inspections
9610250c-a6e8-5748-a901-50d9ec1f58d5 | note | ACTION (Hold, Monitor, Witness) - Hold
e169089e-503c-584e-a545-6ea525b5872e | note | Detail - Pre Pour Inspection shall be carried out before casting.
a73a93b7-54bf-577d-b463-728716aa1f09 | note | ○ The Engineer's Rep shall be advised at least 48 hours before the proposed pour.
5b7e1687-4e07-5373-ae80-e6e4c22163a3 | note | Reference - Approved shop drawings
ea266cef-f33e-5e17-8cb4-cddabe92dbd0 | note | Frequency - Prior to each cast
1a8e14fa-821b-5cbe-aba4-f90cedbbed80 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Measure, Document review
019ed32d-6966-5225-8f76-2a67e4bf6b5d | note | Conformance Criteria - Confirmation that the unit has been cast in accordance with approved shop drawings and NZ standards for tolerances.
a01183aa-1c69-5ad0-8267-d0479f1bcdb3 | note | Records - Pre Pour inspection sheet Marked up shop drawing, Stressing records
b5baa92c-78a5-5ac1-8c60-3f962fd9fa84 | note | Responsibility - Foreman & Production / Quality Coordinator
dfd8ab0f-53a2-55d2-81f5-18bdd3ddf2b5 | signoff | HOLD POINT
7d3a59d2-dc2a-573f-8a58-aa95cae36daa | checkpoint | 13 - Concrete Mix Conformance
311117ac-3155-5539-a777-674b996bf619 | note | ACTION (Hold, Monitor, Witness) - Hold
6db8b1b3-2817-561e-bf0c-593f1b25912e | note | Detail - All concrete dockets reviewed at time of delivery.
a165b695-2965-535c-bc57-2d3d04cb5ace | note | Reference - Approved mix design
9370f9fa-3cf8-5619-a925-3d62e5b8fe41 | note | Frequency - Prior to placement of concrete
6148a39e-7d5d-5efa-9bcb-455615636d8b | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
0c458253-3efd-59d6-8e91-7791f4319959 | note | Conformance Criteria - All concrete delivered to site shall be produced in accordance with the approved mix design
b811b79f-2d25-572e-975a-a02276a48af2 | note | Records - Concrete Delivery Dockets
4c842c98-2566-5e00-ad8c-cc5d77f34cd3 | note | Responsibility - Supervisor & Production / Quality Coordinator
ad1e779b-95bc-5a97-a643-d8f4dbc0ac59 | signoff | HOLD POINT
ec1444bf-f270-525a-bc56-e9c0aea58c32 | checkpoint | 14 - Concrete Mix Workability
7a334b4b-7737-5c51-866a-9c853b5cf709 | note | ACTION (Hold, Monitor, Witness) - Hold
fd3bc877-8753-5f64-9e66-453baed60ccd | note | Detail - Fresh concrete to be visually assessed for its workability compliance.
e46c0b51-3685-5315-8d13-c30cdecb41a5 | note | Reference - Approved mix design
0142e3c7-3508-5acc-9f85-df8e25e44292 | note | Frequency - Prior to placement of concrete
768a44ca-4a4a-5073-8b4f-c7328566a890 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
92f4fa5e-031d-5a99-ac4d-b449dec86fb0 | note | Conformance Criteria - Workability as per mix design.
90070146-4e54-5605-a12f-dcd06ee86053 | note | ○ Concrete slump test to be performed by concrete supplier before delivery
b6789452-9098-557d-b59a-48a6433402e6 | note | Records - Concrete Delivery Dockets
8595d649-ab63-5660-a481-42756681bb5b | note | Responsibility - Supervisor & Production / Quality Coordinator
3eb04312-7b4b-52b5-8734-9e952c1f6412 | signoff | HOLD POINT
0b42768e-638b-5ce9-a65f-50b098b8e7fc | checkpoint | 15 - Concrete Finish
ffda2a76-6528-5d93-a851-c9706278b15e | note | ACTION (Hold, Monitor, Witness) - Witness
48b8c739-dca4-5c03-b99a-a6d0e0aa3f04 | note | Detail - Concrete to be placed to achieve the specified formed and unformed finishes
42cd536b-8b98-5dbb-a933-2ab4e9951e9e | note | Reference - Approved shop drawings NZS3114
319497f6-1355-533d-b8d1-69845caef18f | note | Frequency - During and after placement of concrete
561d4630-0862-5e59-ad24-4fe0a5e8d775 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
47874d4f-1668-58a0-a01a-346d8df68456 | note | Conformance Criteria - ST Beam to be Type F4 finish
3ad84433-4b23-5d29-ba07-1b5d516cb884 | note | ○ All construction joints - Type B / UNO
d8c14651-d0e7-5a17-b51c-a4ff74c0bb2c | note | ○ Top surface Type B / CJ and U2 where specified
333da850-fdda-5870-9d8c-89652d76e88e | note | Records - Pre-Pour Inspection sheet
f7cb8e4d-b176-500d-9ca2-f77e871b02c6 | note | Responsibility - Foreman & Production / Quality Coordinator
c58e9127-52d5-57bf-9ba3-f187fd87775b | section | C. Post-Construction
6f20b392-5a93-5ee9-bfc6-936f7c903340 | checkpoint | 16 - Curing and Release Strength
83fe2645-c52a-5ed2-b008-4d454814155d | note | ACTION (Hold, Monitor, Witness) - Hold
67eb983b-0580-5566-84c6-27120456b012 | note | Detail - Heat accelerrated curing as per approved methodology.
71c95f64-4e80-52b8-9214-c5d34640cd49 | note | ○ 7 Day post mould water curing as per approved methodology
2e1e5b66-8947-5034-8df6-9cace7b9ee3e | note | Reference - NZS 3109, NZS 3112
1b3bb031-68ca-5dce-9cee-1faf40c0532e | note | Frequency - Prior to every unit transfer
29171571-516c-5465-aa92-036c69d303c3 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Testing (Schmidt hammer or Compressive strength test)
75ce6f2f-056e-5814-9266-d4528833d946 | note | Conformance Criteria - Minimum compressive strength at transfer of prestressed units to be 40MPa prior to stripping and demoulding.
a6a1b21e-1b8d-5ec7-8363-c7038caef5c4 | note | Records - Post-Pour Inspection sheet
35e0f182-6c39-5260-b30a-0f1e47a13019 | note | Responsibility - Production Manager
3ec34be8-0667-52d2-85e4-f9836add7efd | signoff | HOLD POINT
1f9a1267-9b7b-5001-a031-4440573331f2 | checkpoint | 17 - Transfer
dca831aa-0a41-55d3-bdb9-23f9f12f80a4 | note | ACTION (Hold, Monitor, Witness) - Monitor
86efa140-caa3-5d23-a936-c12143ffdc1e | note | Detail - Visual inspection to ensure strands are tight and no slippage of strand into concrete. Locallised spalling around full bonded strand at transer as result of excessive slippage will be identified as non conformance and the unit will be rejected and remade.
2c15f307-7610-5f79-928a-5f76b2be7231 | note | Reference - Approved shop drawings
2f770336-c37d-5921-88d2-d5adbe33ac34 | note | Frequency - Prior to transfer
7c20d68e-d849-53fe-a90a-9e62feba776e | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
e2c67bcd-cc11-595d-81dc-e2a00aff1b10 | note | Conformance Criteria - Stressing data/records reported on stressing calculation sheet.
e4cb9fd6-82be-54a2-8137-19bf8139eb78 | note | Responsibility - Production / Quality Coordinator
6b5d4cec-0d9b-5448-9da1-c734f865a051 | checkpoint | 18 - Draw-in
7a0c13e9-093c-5682-8d1b-e60370172781 | note | ACTION (Hold, Monitor, Witness) - Monitor
1e2fe925-028d-5379-890f-a0bd96d228bb | note | Detail - Strand draw-in to be measured on each cast. If ave draw-in for group exceeds 2mm, or 4mm for single strand, then results to be submitted to Eng
bff52761-f10d-5b32-9a96-c2e6f259adf6 | note | Reference - NZS3109 C8.72.3
66b150d8-cf4d-5c53-a9a8-19989e9dc75e | note | Frequency - Every unit - at transfer
941faba9-d19c-563d-a257-c361b146104c | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Measure
868bbe88-0540-544f-bde0-c635769310b0 | note | Conformance Criteria - Draw-in to be measured on each beam at transfer
efc87e3d-5551-5bc7-8473-64158b9bb748 | note | Records - Post-Pour Inspection sheet
3f5e4a31-7372-5378-8977-0209a93256c0 | note | Responsibility - Production / Quality Coordinator
ebb71627-7643-5d5f-961f-0e920d05b5ac | checkpoint | 19 - Lifting
c49d51f6-a795-5014-b414-bd86d118b587 | note | ACTION (Hold, Monitor, Witness) - Monitor
13ede2b5-5b4c-5a09-8046-aef69baa9e0e | note | Detail - Units are to be demoulded following lift design
60dab494-c2a1-50de-bfa2-3dc3b9ff4694 | note | Reference - Approved lift design
46f2cc6e-738f-5188-9f4b-ba8db6bbfd7e | note | Frequency - Every unit
7bfb66b1-e02d-576a-a838-e48e020d9746 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
ea91a55e-6c8b-59bb-9f0b-92c4eebc6c0e | note | Conformance Criteria - Approved lift design to be followed.
00d14c8c-7757-5442-8152-ec5f786dcde2 | note | Responsibility - Production / Quality Coordinator
157b3f4a-e957-520e-8ccb-c7e705cfdef7 | checkpoint | 20 - Marking
6ff1f621-a675-540a-aae3-a86d79a29035 | note | ACTION (Hold, Monitor, Witness) - Hold
c7fd609e-b2ac-5f38-885c-beb54ed5a4a5 | note | Detail - Units are to be clearly marked each end with unique number, cast date and installation direction (Super T).
161bd468-0322-5036-93be-26ac20754dc0 | note | Reference - Approved shop drawings
27d71e1f-5d89-55d0-8cc6-b04510b589b7 | note | Frequency - Every unit - after demoulding, prior storing
4abfe7b5-7b7c-5e98-b96d-29b109203c9e | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
abc4c0ea-d7ac-580a-9dbf-539e63312f44 | note | Conformance Criteria - Ensure every unit is clearly marked
80cebd3c-1d86-5073-baf7-4db5179ad035 | note | Responsibility - Production / Quality Coordinator
790c9791-a515-52ba-ae0f-aa22af613964 | signoff | HOLD POINT
a7534f13-6f0d-5649-9f91-d056faf87402 | checkpoint | 21 - Concrete Supply Testing
a50a5106-58ac-5154-b636-4e9d9baf5168 | note | ACTION (Hold, Monitor, Witness) - Hold
524723cd-0b10-5b32-a705-0aaf1f106914 | note | Detail - Concrete compressive strength test to be carried out by supplier. 1 Set per beam with additional set for any truck with water added after leaving the batch plant
3fe6190e-caa7-5090-99f8-40eaaf9458cb | note | Reference - NZS 3112, Part 2
331227d1-8d3c-5dc4-b1b8-7ec0f3ee2639 | note | Frequency - 1 test sample for every beam [1 cylinder - at 7 days age, 3 cylinders - at 28 days age, 3 cylinders - transfer strength]
ef3e12d0-76f2-5b65-9cfb-0b4f1a44dc33 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Testing
025465c7-5017-563b-a711-8ca08e0408b2 | note | Conformance Criteria - Compressive Strength result to be a minimum orf 60MPa at 28 days
0f0c4a8d-861c-5471-969e-3658197a17f5 | note | Records - Concrete suppliers Test Reports
ee7efde4-c434-5036-a461-9dcb8ab13561 | note | Responsibility - Concrete Supplier + Production / Quality Coordinator
3b0b38d5-d5de-5b88-8a39-edee17a6c732 | signoff | HOLD POINT
4288a69d-fabb-520a-a506-67c8b8d010d8 | checkpoint | 22 - Post Pour Inspection
721abcd0-5901-5c3e-b54f-0ea4ebb89e4e | note | ACTION (Hold, Monitor, Witness) - Hold
f8c468dd-cbfc-59fa-840e-626b72f8d26d | note | Detail - All units shall be inspected for its compliance prior to delivery
139fc4d8-86d9-5641-a088-8d6a6481b470 | note | Reference - Approved shop drawings
f176d10f-98c5-5a13-b724-be54170c4ad9 | note | Frequency - Every unit - prior delivery
8d5e7b13-a589-5f24-9b46-c5b8cbcd54fe | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
a403cc31-9e23-5f4a-9c73-ac4489955d3b | note | Conformance Criteria - Confirmation that the unit has been cast in accordance with approved shop drawings and NZ standards
8b0f1bbd-a572-581f-953d-7b495ef12b98 | note | Records - Post-Pour Inspection sheet (red pen mark-up - as-built)
f321ff1b-89d3-5b73-b0d5-a61c496aa4bd | note | Responsibility - Production / Quality Coordinator
5076d25e-bc7e-5a9e-ba97-3ef4d68a99c1 | signoff | HOLD POINT
ec61566e-039d-5374-9586-f0a4d7509568 | checkpoint | 23 - QA Package / Redline Drawings
2f204df4-bf44-5875-8ed5-2fc070b896f3 | note | ACTION (Hold, Monitor, Witness) - Hold
e5e86938-3e39-559e-b0f1-f12261960b37 | note | Detail - Compliance documentation is to be collated as per project requirements
9b670fca-7b98-5440-a777-b5d556f58b3f | note | Frequency - At Delivery and installation
b6d92ed9-8b0d-58f3-b32e-7c0f31b46779 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
308eecf0-d585-5ce6-9006-1532ba7cb0b0 | note | Conformance Criteria - Compliance documentation is to be submitted to the Engineer.
9c00f19f-17d7-56d7-a209-5abed1961002 | note | Records - Post Pour inspection sheet Marked up shop drawings - as built
3a897618-00a4-59f5-88ac-593de51db2e6 | note | Responsibility - Production / Quality Coordinator
6faff287-504f-5594-90a8-afa8ce6fff97 | signoff | HOLD POINT
6fc860d8-4ebf-5b25-98f6-b10a5f2476e5 | checklist | SYS - ITP - Hollowcore Beam A1 | itp | ITP - Hollowcore Beam A1
0f66e61d-af39-55d7-a549-551996ec17ca | section | 1.0 Pre Construction Tests
16741c32-4133-5e37-a426-b83d943044fe | checkpoint | 1.1 - Concrete Mix Design Approval
78f211aa-5a6d-5d2e-952f-d156b3567228 | note | Acceptance Criteria - 60 MPa at 28 days (S6014PC)
aa858af4-1c11-5fec-9807-c8bf6701d980 | note | Inspection or Test: Method - Review
d2c184e8-b5f4-5905-b93d-788ab91ca0db | note | Inspection or Test: Freq. - Once per Mix design / per supplier
17809666-3917-5c98-a776-b11dfa4ff31c | note | Inspection or Test: Responsible Person - PRECO
7fcbf47b-08ac-57d4-8bb0-1afe56b12559 | note | Verifying Document - Confirmation of Approval
3a201943-a2a7-5359-9283-ea1ac7d0928d | note | Records required for handover package: Yes/No - Y
eca077c5-ed8a-5b97-9a5e-cdf67be56ace | note | Inspection / Test Authority: Conduct - 1
cb8fb411-2aa4-5950-8709-3a3592e01c28 | note | Inspection / Test Authority: Witness - D
ab4ec765-bf98-5ad9-a7c4-5858a57c8569 | note | Inspection / Test Authority: Produce Record - 1
ffd7e38e-39d7-51a4-a0e2-e393ee9f3d6a | note | Inspection / Test Authority: Approval - D
12b13299-31df-5e0f-8a3d-1c23f32e0df1 | note | Hold Point - Y
bc850914-d12b-5672-bff8-389cfa142964 | signoff | HOLD POINT
c754f42f-db38-5d2c-9d86-50120e867cca | checkpoint | 1.2 - Reinforcement Supply
c3138b85-2b05-5574-a3a6-a2e04a6675a3 | note | Acceptance Criteria - Micro Alloying Deformed Bars Grade 500E (HD)
14abb13d-df41-55f5-9965-079418bf4584 | note | Inspection or Test: Method - Review
017175fb-024a-571d-8bc6-53d393f584c2 | note | Inspection or Test: Freq. - Per Size, Per Supplier
1c69872e-6d91-5364-849d-51759dbd028a | note | Inspection or Test: Responsible Person - PRECO
70142f81-b14b-5339-ba6e-ca12006cd9e4 | note | Verifying Document - Supplier Mill Certificates
98f163b4-fae4-5b01-a913-d13ec9072468 | note | Records required for handover package: Yes/No - Y
a86b2e81-f72c-5ede-82ea-29331059eb45 | note | Inspection / Test Authority: Conduct - 4
8cca54ad-ae01-5eaa-ba78-9a4ebd814399 | note | Inspection / Test Authority: Witness - D
3f1214ed-d4af-5cd2-b9e7-7438fb04eb89 | note | Inspection / Test Authority: Produce Record - C
73d8ecd9-f1e6-524d-89af-5c9fdf3d6927 | note | Inspection / Test Authority: Approval - D
8cc5fdc0-8b51-54b7-a5c5-f6e9b2d88efa | note | Hold Point - Y
36b26065-b8ab-516d-9d52-c286a7e630d8 | signoff | HOLD POINT
16fd4035-90c4-5fc2-9f2d-008a965903e4 | checkpoint | 1.3 - Strand Supplier Verification
4255b8e1-7562-54e5-9b12-d10442fcc85e | note | Acceptance Criteria - ACRS accredited supplier
867cf9d8-c10b-58e5-afcd-c49485bd82f8 | note | Inspection or Test: Method - Review
121bd0c4-24de-5c78-8319-dfa08a2d08c3 | note | Inspection or Test: Freq. - Per Supplier
1f928294-bd9a-58d3-9820-099b51484fcb | note | Inspection or Test: Responsible Person - PRECO
ea7943bd-f313-59cc-9d64-d02695513371 | note | Verifying Document - ACRS Accreditation
d661eee4-fff8-5c68-a2dd-5cbc821d7825 | note | Records required for handover package: Yes/No - Y
9ece86f8-116f-5b4e-ab33-20db39efcaae | note | Inspection / Test Authority: Conduct - 4
fedf724f-dd9f-50fc-9f5d-3b1ad3296fad | note | Inspection / Test Authority: Witness - D
af4df6dd-cf0c-5cc4-9bf0-f29f3fd06cf2 | note | Inspection / Test Authority: Produce Record - C
f27b0868-6259-51c2-b8d4-57ea5c1652c8 | note | Inspection / Test Authority: Approval - D
cf2a1c14-b965-53b9-ae4e-47d7133f1bbf | note | Hold Point - Y
5f9413f4-d534-5dc8-a0c7-8ddb719256b1 | signoff | HOLD POINT
91ada194-9d85-5cf8-8f94-ef40154adeeb | checkpoint | 1.4 - Strand Supply
d5831ee0-71a7-52e2-bec8-36e284be9840 | note | Controlling Documents - NZS 3109
214a8a5c-c23a-5aad-80bb-b71fba686a79 | note | Acceptance Criteria - 15.2mm diam. Prestressing superstrand
4997169f-dac4-54b3-97eb-791c68fa8684 | note | Inspection or Test: Method - Review
721a8e30-e897-53a4-9c2c-d656c7765c60 | note | Inspection or Test: Freq. - Per Size, Per Supplier
1c599276-26d7-54b6-995a-2fbf01dfb740 | note | Inspection or Test: Responsible Person - PRECO
57792685-2729-5a0e-b18f-8f70006bbe90 | note | Verifying Document - Supplier Mill Certificates
a49d69ed-5b55-567a-9f10-5ed2fbd98508 | note | Records required for handover package: Yes/No - Y
72e2b36c-de11-5d10-8e79-8724da027cc1 | note | Inspection / Test Authority: Conduct - 4
286462b3-aa49-5f42-8bb2-3945620a72f2 | note | Inspection / Test Authority: Witness - D
f7a2b0f5-5fed-5c04-a321-1e58b66cbe3f | note | Inspection / Test Authority: Produce Record - C
24164605-5635-550c-b0f1-bfc4f5cd702e | note | Inspection / Test Authority: Approval - D
3e178ecb-70b8-5db9-8bc5-e9342cbd7384 | note | Hold Point - Y
611cc3db-b365-5e76-abcf-690a96eb0ec2 | signoff | HOLD POINT
dcbea265-f2b8-5855-9d6c-c9f2aa8b6855 | checkpoint | 1.5 - Strand Certification
8dfef4d5-d92c-526e-9fa6-9601130558b1 | note | Controlling Documents - AS/NZS 4672
7e6982e4-94b6-548f-ad67-108003a3a0b5 | note | Acceptance Criteria - Conformance to AS/NZS 4672 in relation to:
4ab239d3-ccca-5821-9c30-2522ff9ea8d8 | note | ○ Chemical analysis
f801015e-c684-5f3d-81af-9a989c6bf888 | note | ○ Geometrical characteristics
6680d36a-67e8-5105-b2d1-df651faad111 | note | ○ Breaking force or tensile strength
6bd53a41-3a23-5b28-b2c4-2cfff7519141 | note | ○ Proof load or proof stress
6ba44543-2775-5a07-857c-e7c719cd7e0d | note | ○ Elongation at maximum load
8689ff12-aed6-5bac-83f6-908935756478 | note | ○ Load extension diapgram
a5bdc635-cac4-59f8-8203-4209902dc1c4 | note | ○ Ductility
2c5e90a6-933b-5cd5-b6c8-6cfbe18c960f | note | ○ Relaxation
5d19aab5-7d19-5c52-a24c-8aeec7741395 | note | Inspection or Test: Method - Review
958460c4-0198-51fc-920c-462c63ee5024 | note | Inspection or Test: Freq. - Per Size, Per Supplier
e2d1b5b3-1c0a-525d-a81b-a05b984bd7e1 | note | Inspection or Test: Responsible Person - PRECO
15936079-2d8c-520a-af28-448cfe987c26 | note | Verifying Document - Material Test Certificates
bfdf3393-8341-5999-998a-d2735a598c0f | note | Records required for handover package: Yes/No - Y
307908f2-fb06-5ef2-ba11-fc63bb9efe67 | note | Inspection / Test Authority: Conduct - 4
31b58e15-b7bc-5d95-aef4-f912fd8bc2a3 | note | Inspection / Test Authority: Witness - D
392c27e9-938c-5e17-a0b9-61668440771f | note | Inspection / Test Authority: Produce Record - C
cb9ba18e-2436-50fb-a937-167b8367d118 | note | Inspection / Test Authority: Approval - D
d1711e2b-a249-53e0-9908-a4e885436191 | note | Hold Point - Y
06e62339-34ea-506f-bea9-6091835db93c | signoff | HOLD POINT
405405d3-be37-56e4-b1a0-839cb34aea7e | checkpoint | 1.6 - Shop Drawing Approval
d81037e6-4cfd-59f6-88d8-0adca4305fac | note | Controlling Documents - IFC drawing
db0fa714-a011-5b85-b0c9-658975aa0039 | note | Acceptance Criteria - Shop drawings including strand type, arrangement and stressing notes, details of debonding lengths, concrete strengths, surface finishes, location of cast in items and set-out information
b8d6e591-4cf9-585e-a730-1862fb7924e5 | note | Inspection or Test: Method - Review
054cb47b-59e4-501a-a990-f771ee88e529 | note | Inspection or Test: Freq. - Once Prior to Casting
ce166315-bb6e-5ca4-8679-0383c87297b6 | note | Inspection or Test: Responsible Person - PRECO
a45c3f2a-0cd5-50b4-bed9-cb4c47078bdc | note | Verifying Document - Approved Shop Drawings, Issued for Construction
29014ed0-46ce-5fb5-b72f-17479d57fcf2 | note | Records required for handover package: Yes/No - Y
89e8fd82-8ecd-5ef5-a4fa-572afc64881c | note | Inspection / Test Authority: Conduct - C
0be08783-6b2c-5068-964f-61ab966f482e | note | Inspection / Test Authority: Witness - D
9bad79f3-7095-5b16-be96-c68c07c5953c | note | Inspection / Test Authority: Produce Record - C
1e55555d-5f65-5029-97ad-db570de73f9d | note | Inspection / Test Authority: Approval - D
9d941f41-78fc-5299-85e9-44f1f8a921a5 | note | Hold Point - Y
702db023-a927-57ea-9c0f-452773a19d7d | signoff | HOLD POINT
d9ee4a45-9c24-54e8-995a-f76b5f9add04 | checkpoint | 1.7 - Stressing Calculations
4142e4e5-f1ad-5627-9e33-d40bf29187f7 | note | Acceptance Criteria - Force remaining in each 15.2 mm dia. strand at midpoint of beam immediately after release of tensioning jacks
26fd898b-b0f5-5dd6-b3e1-6a81f4df8d9d | note | Inspection or Test: Method - Review
2125f996-2afa-5c9b-bc65-24a87238ecb8 | note | Inspection or Test: Freq. - 5 Days Prior to Casting
40427a1d-5c44-52d7-8417-b474dba02533 | note | Inspection or Test: Responsible Person - PRECO
0a3172c5-7508-5e53-847e-3213b5f29a5a | note | Verifying Document - Approved Stressing Calculations
8de58f1f-2e0e-5d67-a886-ef2d7360f8b6 | note | Records required for handover package: Yes/No - Y
698e7976-4c4a-562c-a5af-00ec5dca396d | note | Inspection / Test Authority: Conduct - C
c8e399ef-8561-5cb6-b5c6-5ca02bd6bce3 | note | Inspection / Test Authority: Witness - D
6b5065be-2022-5538-b577-8240c957fc7d | note | Inspection / Test Authority: Produce Record - C
943c788e-a1f4-5e22-869b-904e215411b3 | note | Inspection / Test Authority: Approval - D
e5d40d4a-6c54-5927-9d2d-14a8667156ae | note | Hold Point - Y
51ed43c9-40e5-5aca-b7be-3415e0723fc7 | signoff | HOLD POINT
ef23489f-eb00-5f3b-b643-deaae7a7e9dc | checkpoint | 1.8 - Jack Calibration
4912747c-2bce-5136-babf-2c5ef48c651d | note | Acceptance Criteria - Calibrated within tolerance
25e0f232-4bd1-517b-9285-35d662af5218 | note | Inspection or Test: Method - Certificate Inspection
c74194b3-f0c2-5267-aeca-fbb84bb25b1e | note | Inspection or Test: Freq. - Every 6 Months, Per Jack
a3976cd2-6eba-5e77-8a63-1f5b81365120 | note | Inspection or Test: Responsible Person - PRECO
d1724d1b-2de4-50e4-a7b4-db0ec34db939 | note | Verifying Document - Calibration Certificate
6687e253-a060-5987-93e6-45cc92317bfc | note | Records required for handover package: Yes/No - Y
5da45a7a-f9b6-5eee-8f02-d1e2502013f5 | note | Inspection / Test Authority: Conduct - C
5a6cfbc4-f71e-55cf-9638-1cffcab231c5 | note | Inspection / Test Authority: Produce Record - C
5b7d0374-3060-5c70-b637-56c03fb20930 | note | Inspection / Test Authority: Approval - C
ac280ed7-60d4-5318-9c00-e527014ce062 | note | Hold Point - Y
770ad0d6-9c93-5227-ba83-68cacef816d5 | signoff | HOLD POINT
17bd4489-7071-57a4-9a3a-3e10f5f3dfc1 | checkpoint | 1.9 - Form Release Agent
4a2f920f-06fa-5ca5-9440-2d784383edfc | note | Acceptance Criteria - Not detrimental to the application of any subsequent finishes
929a89b7-7a51-512f-a27b-dc18d97f6602 | note | Inspection or Test: Method - Review
3595fc7d-8930-5042-b0a6-bb4e2198d229 | note | Inspection or Test: Freq. - Once
3e905d85-7513-531e-8bf7-aaa26a8e6b8f | note | Inspection or Test: Responsible Person - PRECO
f13606ae-27d3-5641-bf45-a7c1536b7fb3 | note | Verifying Document - Material Data Sheet
9a6b2806-6e07-58fe-8a46-2fb8720007f5 | note | Records required for handover package: Yes/No - Y
bb7392da-1876-52b1-b66c-4332597659b9 | note | Inspection / Test Authority: Conduct - C
a11e2481-f601-5d2b-9949-dd42b7d87f04 | note | Inspection / Test Authority: Produce Record - C
0a89bb81-a0a4-5da9-9180-1e2537240abc | note | Inspection / Test Authority: Approval - C
8b999de5-2dd0-55a6-8c77-eda64208c51e | note | Hold Point - Y
baae1eae-8748-5092-8f37-9c430c6a38dc | signoff | HOLD POINT
254d676b-9c6a-5c89-bbdd-1e9524316f24 | section | 2.0 In Process Testing
9676fb04-593b-528b-8ca5-f04616a18093 | checkpoint | 2.1 - Reinforcement Traceability
61ccf0a1-8c43-5f03-ab35-a3c7e776a72e | note | Acceptance Criteria - Mill Certificate, Heat Number and Bend Schedule traceability
d1191534-d8b5-5a18-ab8f-9683ebb998b1 | note | Inspection or Test: Method - Review
e0f9d9c5-9dd9-5fce-ad34-5f3bc667a60d | note | Inspection or Test: Freq. - Per Unit
936505a9-7a6c-5f3f-8e24-0ad2c911c846 | note | Inspection or Test: Responsible Person - PRECO
79a6200d-a523-5ba8-bf8a-d8c222392f92 | note | Verifying Document - Pre-Pour Check Sheet
a2529bb7-64a7-5f1c-9f48-8fc49fe5e1d1 | note | Records required for handover package: Yes/No - Y
c06454a1-11cd-587b-8afc-f3091ffc8473 | note | Inspection / Test Authority: Conduct - C
100a881a-2b07-5500-8986-e757666b171a | note | Inspection / Test Authority: Witness - C
133786a1-f514-5b7a-b002-ef08f5898a12 | note | Inspection / Test Authority: Produce Record - C
b68e1c03-cf17-5cb6-9316-db5166e91af3 | note | Inspection / Test Authority: Approval - C
fb2e7852-2574-5cd3-ad63-6811ed026e03 | note | Hold Point - N
131c5882-9696-5e3c-8041-3f4b4b66a3a2 | checkpoint | 2.2 - Reinforcement Fixing
6d21fe64-6a0a-5282-99bf-2e718a847467 | note | Controlling Documents - NZS 3109
348f0eea-a018-5038-bf44-b5b8d3539582 | note | Acceptance Criteria - clear cover as per drawing to all reinforcing including stirrups and ties
47db6c98-d89e-5e0f-8df3-8cf606190dc2 | note | ○ Steel to be securely tied and fixed with no movement
91ba1cf8-25d4-59c5-97e9-7cc8f53ffe8b | note | Inspection or Test: Method - Inspect
b9149e45-01b4-5203-9eeb-3a2de6ff413b | note | Inspection or Test: Freq. - Per Unit
386d206d-d2c5-5da1-824a-1080525fc590 | note | Inspection or Test: Responsible Person - PRECO
52e37810-5c7f-5a82-96e5-05fd9b7853bc | note | Verifying Document - Pre pour checksheet, photos
eb431f8e-5183-57ee-9da9-e63271c0eb6c | note | Records required for handover package: Yes/No - Y
1ccf093b-81ca-591f-89b9-eee4a5a2084c | note | Inspection / Test Authority: Conduct - C
e0d5d116-4616-5a98-8058-45ed77b042d5 | note | Inspection / Test Authority: Witness - D
0f221cfb-6b22-56da-8523-eeabfec6955c | note | Inspection / Test Authority: Produce Record - C
a14218b6-312d-5ea1-ad99-a57fd49b362d | note | Inspection / Test Authority: Approval - D
80b3119a-03c3-5c6a-a60c-a208d6c10ad0 | note | Hold Point - N
6e14d553-73d1-562e-8c3c-c3a67188fd2d | checkpoint | 2.3 - Pre Pour Inspection
d636d527-87a5-59bd-a560-2e45f82dffdf | note | Acceptance Criteria - Completed pre-pour inspection (dimension/inserts/ reo) permission to commence concrete placement
1ce3f275-5a5a-5ad5-ad39-0e8c1c6aa2a5 | note | Inspection or Test: Method - Inspect
b22b9cc4-ebad-53ca-9105-c89f97d45417 | note | Inspection or Test: Freq. - Per Beam, Per Pour
e28ca6b4-e0e2-5f69-bb6f-0c16a10e0eba | note | Inspection or Test: Responsible Person - PRECO
3f42244e-32c9-5520-b6ac-2b7f00939e36 | note | Verifying Document - Approved Pre-Pour Checksheet
429807ba-ab0c-51d3-a509-f182bc3fada0 | note | Records required for handover package: Yes/No - Y
2ee5eb8f-a096-5e8b-b2c7-2a27643b9c07 | note | Inspection / Test Authority: Conduct - D
b2709ce4-a224-523b-919a-db37d24f51b1 | note | Inspection / Test Authority: Witness - D
4bc57f2f-9ba0-5b43-b5dc-e85d3acbc1d3 | note | Inspection / Test Authority: Produce Record - C
fc9ab214-1fa1-5317-9cf0-49661b16d828 | note | Inspection / Test Authority: Approval - C
7e57bdb0-35a3-5ab9-9eca-17fde2f2be2a | note | Hold Point - Y
9ade320c-3742-5d12-8889-a9169e1643b7 | signoff | HOLD POINT
4ae29e84-f0c1-5a7c-9625-654ddcc77c29 | checkpoint | 2.4 - Concrete Placement
39fafecd-b2e9-5b48-8c7b-daf98a4d5755 | note | Controlling Documents - NZS-3109
3a3612b0-39ea-5b3c-95d5-86105f296f6c | note | Acceptance Criteria - Slump within target 120 +/-40, all concrete to be properly vibrated
cc2863c6-eb35-512c-88ee-d78aac832397 | note | Inspection or Test: Method - Inspect
b5ae8a11-7555-51c9-a5b0-828f6b61015c | note | Inspection or Test: Freq. - Per Concrete Delivery / Per Placement
97cc9910-052d-5ee8-8fe0-979d2b08d2fe | note | Inspection or Test: Responsible Person - PRECO
d0d71ce8-ae9f-568b-b2e1-01ab7409b823 | note | Verifying Document - In-Pour Checksheet / Delivery Docket
dd891b55-3834-559f-a59c-f5a4d769d5d3 | note | Records required for handover package: Yes/No - Y
1863c022-8047-5deb-8720-aa7a43389550 | note | Inspection / Test Authority: Conduct - C
de9063fe-7287-5f4b-8ab9-6fe3e1ecc0a0 | note | Inspection / Test Authority: Witness - C
92efaba6-6645-5395-8bff-9c46a435f71b | note | Inspection / Test Authority: Produce Record - C
7acaa081-f417-528c-9e45-3c8341c68e11 | note | Inspection / Test Authority: Approval - C
2721098c-0c32-5e5f-88de-48ba461fd82b | note | Hold Point - Y
10d61ffc-fb4b-5165-8a31-89dd1fb6737a | signoff | HOLD POINT
4040dba9-523c-5c38-ada6-bdc18c543e67 | checkpoint | 2.5 - Concrete Sampling/Testing
15f240f6-87cc-500e-b08d-3abc9de99072 | note | Acceptance Criteria - Compressive test 1 x 7d and 3 x 28d results + 2 stress transfer cylinder (1 for test + 1 spare) stored at curing temperature
c17174e3-fd7c-599b-bbe5-c57e91af8e4c | note | ○ 60 MPa at 28 days
d118ff8f-c305-5261-93e2-b9629fa6eaae | note | Inspection or Test: Method - Concrete Sampling/Testing
396500ee-9dd4-50cd-a15d-cd478f6fa682 | note | Inspection or Test: Freq. - One set per precast beam with an additional set taken from any truck which has water added after leaving the plant
e4182f51-8d06-50ff-b4ff-f7c4e06fb709 | note | Inspection or Test: Responsible Person - Subcontractor
9646702c-0876-5348-9c9e-85b19ba2767f | note | Verifying Document - Concrete Sample Test Results (IANZ Accredited Laboratory for 7 & 28days test)
529fd1b4-3428-5e49-8b72-571ea73d607e | note | Records required for handover package: Yes/No - Y
2721c42e-3120-5942-9935-c29f8a846037 | note | Inspection / Test Authority: Conduct - C
c5c55d80-f4d4-5c14-9844-81e70258326f | note | Inspection / Test Authority: Witness - C
672acacb-5ee7-53fe-8c14-1bb41c1c7e33 | note | Inspection / Test Authority: Produce Record - 3
0bc79d63-84e3-532c-9e7b-cc29788e9d9f | note | Inspection / Test Authority: Approval - C
339cdc9e-5a98-5236-8e67-62fa19d28db1 | note | Hold Point - Y (Designer to be notified immediately if specimen fails)
899d3e45-155b-5a33-aa6f-0921390acf26 | signoff | HOLD POINT
df309f6a-7887-58d3-878a-bba3dd5420af | checkpoint | 2.6 - Heat Curing
0e5ebd5c-2e94-5ca3-bb7c-08e2ee65d371 | note | Controlling Documents - Approved Heat Curing Methodology
88a03694-72e0-5798-91f1-ab548320b5b1 | note | Acceptance Criteria - Concrete core temperature shall not exceed 70 degrees
d13251b0-a197-5602-8154-d1632a8eab7c | note | ○ Steady state inlet and outlet water temperatures recorded
85ada80e-9c11-56e1-95d2-2e0b7844af20 | note | Inspection or Test: Method - Temperature Monitoring
620b90c4-8f34-56d4-8094-0c3d4fc5af36 | note | Inspection or Test: Freq. - Per Beam
d36788b1-ca10-5785-a3e1-dde4fd2f2d22 | note | Inspection or Test: Responsible Person - PRECO
02bed0c0-3d6f-507d-a6c8-268d3c1283c3 | note | Verifying Document - In Pour Checksheet, Hot Water Curing Methodology
d53be086-79b2-5f5b-9004-641ef88b5803 | note | Records required for handover package: Yes/No - Y
dc210e64-5df0-55b3-883c-d9091295358f | note | Inspection / Test Authority: Conduct - C
7c9c17dd-5718-5b5b-af55-ba56a659fe14 | note | Inspection / Test Authority: Witness - C
13cf92ff-5eca-5ffc-86a3-70d3bc30ff36 | note | Inspection / Test Authority: Produce Record - C
7b832ff4-8065-5318-a882-b758b5faa0df | note | Inspection / Test Authority: Approval - C
0acf477d-6168-5666-9c59-a90a8d7aab75 | note | Hold Point - Y (Designer to be notified if anomalous temperature readings encountered)
7f081628-06d7-5ebd-94ff-244894e17897 | signoff | HOLD POINT
e36e8123-5d2f-5c62-a846-565547b4f2bf | checkpoint | 2.7 - Concrete Curing
f8bd1996-0eff-587c-82c9-cec2c936c860 | note | Controlling Documents - NZS 3109
8b4376c3-5eba-576e-a6d8-96e199a7ea80 | note | Acceptance Criteria - 7 days wet curing required following completion of accelerated curing
4ecd5945-223d-581e-84dc-40724e292517 | note | Inspection or Test: Method - Inspect
3bd1cb23-136b-580e-8d8a-2158babb60e9 | note | Inspection or Test: Freq. - Per Beam
110ce892-d8d3-5df4-9439-61440d31d9f8 | note | Inspection or Test: Responsible Person - PRECO
b7dfb368-43bb-5749-a772-93f869e24543 | note | Verifying Document - Post Pour Checksheet
cce69b92-0f21-556c-9148-62ae914dcd4a | note | Records required for handover package: Yes/No - Y
c6115285-18c6-566c-81e5-f777e6ba92ca | note | Inspection / Test Authority: Conduct - C
ac33b12b-2462-5132-9745-b874f4c18405 | note | Inspection / Test Authority: Witness - C
f2312730-daa7-5a4f-98dd-ffaaea72abe4 | note | Inspection / Test Authority: Produce Record - C
4c534583-6546-5a29-9845-4a06701677a7 | note | Inspection / Test Authority: Approval - C
9b5b94a7-929b-5d7c-9fbf-e4121869caad | note | Hold Point - Y (Designer to be notified immediately if water supply interrupted)
69f434ae-e20e-50e3-acf5-25565db9e441 | signoff | HOLD POINT
b33a8884-6633-53c1-a97e-902b5a676f90 | checkpoint | 2.8 - Type B Construction Joint
a74ae819-b8ef-5103-a472-48df91c81149 | note | Controlling Documents - NZS 3109
9dad99db-896b-5d9b-8671-6fce30d46560 | note | Acceptance Criteria - 5mm amplitude and free of latinece, cut with water blaster and with use of High Strength Spray on Retarder
48aacd0f-fa6b-51d2-8872-2b9d3e01e1fb | note | ○ Top surface of all beams and end blocks of integral beams
0b775548-e859-5652-89c9-b74b9c3e2233 | note | Inspection or Test: Method - Inspect
18393de2-a168-5ff5-9392-02646e26fe44 | note | Inspection or Test: Freq. - Per Beam
939edf25-0e76-5021-9b62-66ab7e966c1a | note | Inspection or Test: Responsible Person - PRECO
0e01020b-276a-5a0b-b2f6-4a095c5a6ebc | note | Verifying Document - Post Pour Checksheet
5deaeff2-7c53-50c7-84d4-5d4e1d103bd9 | note | Records required for handover package: Yes/No - Y
6ee08dfe-6301-5250-80f5-f3c9a38730f3 | note | Inspection / Test Authority: Conduct - C
5c2e87b9-0789-503f-9f77-ce612bd5fb38 | note | Inspection / Test Authority: Witness - C
91362d65-3729-5f6e-a392-aeee07db5b54 | note | Inspection / Test Authority: Produce Record - C
12d8baf7-0b1f-539b-9636-d888095d76a0 | note | Inspection / Test Authority: Approval - C
1432c686-83b0-5622-966b-a7651bdfff37 | note | Hold Point - N
5359042a-5aa3-58b9-b873-189580f1072f | checkpoint | 2.9 - Post Pour Inspection / Draw-in Measurement
9162f016-8ac8-5c03-bc38-5f1ff150c065 | note | Controlling Documents - IFC Drawings
88c3de0b-d061-58f5-9399-b331de92a632 | note | Acceptance Criteria - Surface Finish Requirements- (F5 for seen faces) / Dimension/inserts/cut-outs as per drawing
169eb815-1eaf-5621-bea3-46009f60330a | note | Inspection or Test: Method - Inspect
e9ad51b9-25a7-5890-b286-1e69b09effdc | note | Inspection or Test: Freq. - Per Beam
cce9461e-a042-595e-8200-93f01be1ea29 | note | Inspection or Test: Responsible Person - PRECO
326621a2-1858-5b67-8699-5f659c336dc8 | note | Verifying Document - Post Pour Checksheet
240ec643-e959-55e3-a014-efd764f512a1 | note | Records required for handover package: Yes/No - Y
c22e7cd1-4c7d-5b5b-8e97-e48c349827b8 | note | Inspection / Test Authority: Conduct - C
74c592b4-0d91-5e89-8cd9-88c8ada682eb | note | Inspection / Test Authority: Witness - C
838c00c9-44e5-5c3e-b1f7-dd9dd7686d73 | note | Inspection / Test Authority: Produce Record - C
ffa656c5-4f03-544f-bf7b-96edd380595f | note | Inspection / Test Authority: Approval - C
cf5c2e86-f608-5900-8099-9073be5f505e | note | Hold Point - Y
74e69685-83c8-55fa-85e7-952fd33a8b09 | signoff | HOLD POINT
e87484e3-671e-58fb-83a7-69415848c6c7 | section | 3.0 Stessing Related Operations
e7eb7633-94d3-5f3c-abc3-5ba7749bfd54 | checkpoint | 3.1 - Strand Positioning
6258448c-266c-50e8-b3cc-379f62795012 | note | Acceptance Criteria - +/- 3 mm in any direction
9efca5fe-1b6c-5003-abbd-77e03a1c4096 | note | Inspection or Test: Method - Inspect
95b32a57-8d78-53c4-8a3e-2bdf6503ef42 | note | Inspection or Test: Freq. - Per Beam
6ec0141b-4772-5f01-a262-7057c7578087 | note | Inspection or Test: Responsible Person - PRECO
d5ffe661-b0a9-508a-99eb-a60b5512324d | note | Verifying Document - Pre Pour Checksheet
48f5a84c-3824-5589-bace-f0f5e71023d8 | note | Records required for handover package: Yes/No - Y
515d378c-5c2f-5665-8908-3eb8f667a100 | note | Inspection / Test Authority: Conduct - C
9d3926c5-bb15-571a-84c5-9b4a3303e59b | note | Inspection / Test Authority: Witness - C
9de33223-6efa-5178-8d3f-d08f599672e3 | note | Inspection / Test Authority: Produce Record - C
39a6e795-e02d-52ea-bdd6-0ebb48890c67 | note | Inspection / Test Authority: Approval - C
78d81136-4187-5599-b59d-ced444f5274e | note | Hold Point - N
5f6f00e1-7f7e-5715-aad8-7eea83acdde9 | checkpoint | 3.2 - Stressing
3d9002a8-01c5-516f-aa32-0b7fbb69148e | note | Acceptance Criteria - Collation of stressing records incl unit ID, strand extention, jack pressures and general comments
3fcf964a-2ab3-5f98-aefc-c745ecd0ec08 | note | Inspection or Test: Method - Review
b9cb5ece-c8fa-5d67-a4fc-aec54a035324 | note | Inspection or Test: Freq. - Per Beam
32ddf547-fd9e-5fe2-9fce-5db1916fb135 | note | Inspection or Test: Responsible Person - PRECO
920bcc17-41da-5147-8c8d-46b9929ec7c9 | note | Verifying Document - Stressing Checksheet
847a6442-5d0a-579a-9d48-12af8e079d8d | note | Records required for handover package: Yes/No - Y
884a3bd6-187e-5df1-a4d6-591ca9a59f33 | note | Inspection / Test Authority: Conduct - C
69daa57c-2297-5e68-bfb1-3ea07e1dcc5f | note | Inspection / Test Authority: Witness - C
4bcbbc71-5099-5261-bbf6-597958e0ffb9 | note | Inspection / Test Authority: Produce Record - C
91eb012b-17b4-5312-9c72-30df09ecf63b | note | Inspection / Test Authority: Approval - C
a74e6dfd-0701-5fdd-89d5-3ad8a1343262 | note | Hold Point - Y (All anomalous readings not in line with Stressing calculations to be submitted)
0d2c5141-2961-571f-9f38-7f34e477a7a1 | signoff | HOLD POINT
3e05d759-6456-5149-8192-52c4f3b8f746 | checkpoint | 3.3 - Stress Transfer
49cbe5f3-da5c-55af-96a5-7d9ba9842cd8 | note | Acceptance Criteria - Concrete Cylinder Tests to be minimum 40MPa
94a4b5d2-3479-5f60-8649-f3fedcf16812 | note | ○ Cylinder to be kept in similar conditions to beam
4338d86d-a09b-5178-84cd-b178bfcf332d | note | Inspection or Test: Method - Cylinder Compressive Strength Test
a9408e8b-177c-5e74-a06b-f6120a3e38ae | note | Inspection or Test: Freq. - Once Per Beam
2f960902-c5a4-553a-af13-74ba7f058bfc | note | Inspection or Test: Responsible Person - PRECO
83b30231-3f61-5b9b-99b7-33a17af6eaf3 | note | Verifying Document - Cylinder Compressive Strength Report (In-house)
914099fa-62cd-5cb7-8d1e-ae7aceed26f3 | note | Records required for handover package: Yes/No - Y
72a7b8e9-2617-5b6f-bf5d-6fe73f980db7 | note | Inspection / Test Authority: Conduct - S
90565c20-cf1a-5784-b374-1500459228bc | note | Inspection / Test Authority: Witness - S
2d8519bc-02a3-51a4-bbd8-2ae414fa9f56 | note | Inspection / Test Authority: Produce Record - S
1a8e7152-089a-5022-be09-417f308fb7ef | note | Inspection / Test Authority: Approval - C
f660713d-289f-590f-8588-9bcd8b850288 | note | Hold Point - Y (No Stress transfer before 30MPa)
7370b437-499c-5294-9efa-2758ade68688 | signoff | HOLD POINT
d6414604-7524-5f08-8657-37dd944288f1 | section | 4.0 Final Documentation
505020bb-1b69-5b4f-a162-52036bd0140c | checkpoint | 4.2 - Producer Statement (PS3)
39010b13-1dce-56dd-9210-021be341f937 | note | Acceptance Criteria - Signed PS3
653b297f-415d-5526-b08f-50bafe58ab16 | note | Inspection or Test: Method - Report Production
b857b720-45a1-5c30-88a0-04a89f5612f3 | note | Inspection or Test: Freq. - Once
7e428ed8-e363-517f-ab8d-7ea9d283d61a | note | Inspection or Test: Responsible Person - PRECO
30d3f47b-a99b-5876-bf16-2658598ec75d | note | Verifying Document - Signed PS3
d1299c2a-f6f5-5998-a93b-64a67b2444f5 | note | Records required for handover package: Yes/No - Y
d6022bd2-cf41-569b-abb4-6a8bbe2b83fa | note | Inspection / Test Authority: Conduct - C
61dbf0dc-a414-5c3d-850d-70db3894c313 | note | Inspection / Test Authority: Witness - C
6e753d30-ec20-52bf-8bb2-dec744d82f34 | note | Inspection / Test Authority: Produce Record - C
23b51786-85de-550e-99b2-67773f6dfc58 | note | Inspection / Test Authority: Approval - D
560f212d-257b-50b8-9024-4318b05d7c13 | note | Hold Point - N
a89d80df-d40a-59b8-b3c4-4089f5c635db | checklist | SYS - ITP - Pavement & Surfacing - AP40 Material - Rev 1 | itp | ITP - Pavement & Surfacing - AP40 Material - Rev 1
624c9523-567e-5961-bcbb-c2696781b917 | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
b0529998-93c5-5453-a2e5-2c44366e9f2c | checkpoint | 2.01.01 - Basecourse CBR
dbbd429c-71bb-5812-85da-dcc9a18eedc9 | note | Acceptance / Conformance Criteria - (a) compacted in accordance with NZS 4402 : 1986, Test 4.1.3 New Zealand Vibrating Hammer Compaction Test at Optimum Water Content and;
a371278e-8f76-5b57-b0e1-d6b44c03d6d2 | note | (b) tested in accordance with NZS 4407 : 1991, Test 3.15 The California Bearing Ratio Test (without a surcharge for at least 4 days). The soaked CBR of the basecourse aggregate shall not be less than 80%.
b40b0852-21dd-5607-a013-f8e6812c5725 | note | Standard / Specification - TNZ M/4: 2006
8ead24d5-9c8f-5d9f-b807-27ff02162e82 | note | Verifying Document - IANZ Lab Reports
030068ab-38a5-5036-82f6-7ac7a7c1bd1e | note | Frequency - 10,000m3
659025bf-5cfa-55f8-856f-5b915f8d83d3 | note | Activity - HP
a35891e0-edbc-595c-9be3-8427f6ef9c14 | note | By - ENG
29ed9ccb-712c-50ab-9d42-c0fd44745cb4 | signoff | AUTHORITY HOLDPOINT
b837b78b-b0a4-557a-8a87-e178b07b8903 | checkpoint | 2.01.02 - Running Course Material Approval
9fb00a71-854c-50c7-beeb-d555fad763b0 | note | Acceptance / Conformance Criteria - The running course shall have a crushing resistance of not less than 130 kN when tested in accordance with NZS 4407: 1991, Crushing Resistance Test, Test 3.10. It shall be free from all non-mineral matter.
d7dcc15a-3087-5bd3-8abd-001433a8da70 | note | • The grading of the running course shall conform with Figure 3 of TNZ B/2:2005, 10.2, when tested in the same manner as required for the parent basecourse. (IF USED)
9938c1d4-af1e-54ec-ab05-56cbfcbe7dab | note | Standard / Specification - TNZ B/02: 2005 - 10.2
97c4a02d-759c-5772-a5d0-568ae3601e2a | note | Verifying Document - IANZ Lab Reports
667eba4a-5457-54fb-b177-accc707507cc | note | Frequency - 1 test every stockpile
02b79946-e421-55fa-8f12-ece77e587346 | note | Activity - HP
2f400810-37b2-5c86-8734-bfb55b54c3d5 | note | By - ENG
694bbc49-b523-5ff7-a549-6e3e5d78408f | signoff | AUTHORITY HOLDPOINT
548ad985-2ecf-52ce-8844-2be0a9fd6e9f | checkpoint | 2.01.03 - Basecourse MDD and OMC
92929d68-63f0-57fb-ac65-531cb6e97659 | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). Test on heavy compaction, vibrating hammer.
7ae1ef54-9208-5e9a-9fa2-285c104c3707 | note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
80a36b75-0644-57d6-b71a-01cbf8adf488 | note | Verifying Document - IANZ Lab Reports
1c6e177a-3638-54ba-b5da-acd2905a56f3 | note | Frequency - 1 test per material type
23d37c95-78a9-507c-934c-2f3070031b71 | note | Activity - H
45af7d7f-9458-53aa-8eec-57f4e7c57ee8 | note | By - PE
75ece572-d277-549f-97f5-9d2eea646d14 | checkpoint | 2.01.04 - Crushing Resistance
e71f59ac-edd0-5e70-beca-82c70dca5b37 | note | Acceptance / Conformance Criteria - The crushing resistance shall not be less than 130kN when the aggregate is tested
b86b747b-e06f-56e2-b657-241efaf003a0 | note | Standard / Specification - NZS 4407: 1991 Test 3.10.
c489a8b1-a8ea-5f82-80ba-4ff4eded1c9a | note | Verifying Document - IANZ Lab Reports
d0adc64e-bcd5-5457-86b4-ec52e3ab0aa1 | note | Frequency - 2 tests per source 4 weeks before use in the works
90bd30ec-e53e-5268-94dc-d9959a20dc19 | note | Activity - HP
a78cabee-87cf-590d-9de2-bf174b81ae9d | note | By - ENG
a003c3fc-8627-5101-be25-bc6c38bfe92a | signoff | AUTHORITY HOLDPOINT
4b4fe5d4-91f3-5027-a33b-636e1248f7a0 | checkpoint | 2.01.05 - Weathering Resistance
3a8afc40-bfb2-549a-9089-5e6cbffcfc0d | note | Acceptance / Conformance Criteria - The aggregate shall have a quality index of AA, AB, AC, BA, or CA when tested
18e72bbf-5f3e-5c0a-b3e4-b741b323ed91 | note | Standard / Specification - NZS 4407: 1991 Test 3.11
2cfd3280-099b-589e-b0ad-7f3ef4136fe4 | note | Verifying Document - IANZ Lab Reports
f2948c97-c966-5ad9-a79d-7bcb312db057 | note | Frequency - 2 tests per source 4 weeks before use in the works
3d3935ec-fb55-5601-bae8-b23d5ec8039c | note | Activity - HP
512ba664-826d-5b63-aede-02a1b8d62ee4 | note | By - ENG
0755029e-495b-5e5b-9bc5-ce9ec5b00d8a | signoff | AUTHORITY HOLDPOINT
1be2a772-ef73-5a20-9f7b-ff55584b77db | checkpoint | 2.01.06 - Particle Size Distribution
e166ae74-624b-5e5b-8d9a-3a8218aff852 | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 2 and 3 from TNZ M/4:2006.
de055241-e1a2-5d0b-af5e-54efa88d6216 | note | Standard / Specification - TNZ M/4: 2006
3bcda7c7-cfe0-5d4e-9e67-ea1bf377c756 | note | Verifying Document - IANZ Lab Reports
c0544496-3ce2-5232-addd-e6938e540abe | note | Frequency - 0 to 400m³ - 2 tests
95f11bf1-a8e0-5084-9d61-adb3d2756506 | note | • 400 to 1,500m³ - 3 tests
a9ad710d-e165-5ea8-9e4a-195b132d5d53 | note | • 1,500 to 4,000m³ - 4 tests
dc69b47a-7de9-58a0-8dc6-5dfc49859c1a | note | • >4,000m³ - 1 test for each additional 1,000m³
9a56c638-031b-545e-9eb5-c0d4183f3245 | note | Activity - HP
282114fb-13aa-5084-ab72-3c09c1f08c61 | note | By - ENG
78a21ef1-b7d3-5597-95ee-fba52abdc91d | signoff | AUTHORITY HOLDPOINT
2c48e4c6-f0da-570a-b0f9-774b3da00b3c | checkpoint | 2.01.07 - Sand Equivalent
dc243aeb-782c-5f73-b035-5d90192571f4 | note | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 40 when the aggregate is tested according to NZS 4407 : 1991, Test 3.6 Sand Equivalent Test.
b0c97723-290e-5e45-b606-54c180dd52e6 | note | • If Sand Equivalence is < 40, then Clay Index shall not be > 3 and Plasticity Index shall not be > 5 (both being tested in accordance with the methods described above).
c9462b1e-4a16-5f8f-a838-4b695ad099c3 | note | • The Sand Equivalent shall be determined using the Wet Method in NZS 4407: 1991 Test 3.6
de976264-2028-5f1e-8b40-58405ee4b2d9 | note | Standard / Specification - TNZ M/4: 2006, 4.2.1.1
b5a313f0-8f07-5136-8235-a6fc300ace71 | note | Verifying Document - IANZ Lab Reports
b094c546-d0d7-50d0-91ac-5751b343c6f2 | note | Frequency - 0 to 400m³ - 2 tests
63050626-6c95-5026-82a3-995cfa0ad37c | note | • 400 to 1,500m³ - 3 tests
11d0194c-7dd2-5a24-ba3b-3914d16c2c9c | note | • 1,500 to 4,000m³ - 4 tests
5075cb26-5316-5c35-b943-3c3389df5642 | note | • >4,000m³ - 1 test for each additional 1,000m³
eb21c904-de19-506e-a6d7-a5f4bfdd9438 | note | Activity - HP
17607f79-1af7-545b-97b2-a7dccc8a076a | note | By - ENG
b7f2b347-0e8d-5e6f-b844-c75eb8ea8162 | signoff | AUTHORITY HOLDPOINT
454d072b-71d1-59c6-b531-512bf3793c41 | checkpoint | 2.01.08 - Liquid Limit
8450682a-d54d-54ca-a371-5bb0648b9165 | note | Acceptance / Conformance Criteria - The Liquid Limit shall be ≤ 25 when tested in accordance with NZS 4402 Test 2.2.
8e0dcf5b-a8df-5f00-b697-e5b4bce57cf6 | note | Standard / Specification - PS - 7.2.3
b8033767-e17d-51ab-bb92-a013d34318a7 | note | Verifying Document - IANZ Lab Reports
bab4c537-af20-54f8-af38-8deb39ed41a2 | note | Frequency - 0 to 400m³ - 2 tests
278f4a50-e7d8-5134-80fb-5ad235f4576a | note | • 400 to 1,500m³ - 3 tests
3423ebfa-0c74-5182-b8a1-5bd4e9ada4e3 | note | • 1,500 to 4,000m³ - 4 tests
9fa9f428-e6a4-5101-a662-97844c9a622b | note | • >4,000m³ - 1 test for each additional 1,000m³
e0e7bccd-4b87-5d6c-9289-5819baf1887c | note | Activity - HP
4870641c-355e-51da-897b-78e73a111d11 | note | By - ENG
e812b52f-9fe9-518a-8788-a0160c62bc55 | signoff | AUTHORITY HOLDPOINT
16ce7ace-e77c-5302-99e6-731cd605e2a3 | checkpoint | 2.01.09 - Plasticity Index
aa160684-d90c-5c2f-8670-9c7345013797 | note | Acceptance / Conformance Criteria - The Plasticity Index shall be ≤ 8 when tested in accordance with NZS 4407 Test 3.4
6fd83484-45a3-58f8-9dfb-7c1c0a96d94b | note | Standard / Specification - PS - 7.2.3
96340ffb-3e65-5eac-96b6-68c84daeac5e | note | Verifying Document - IANZ Lab Reports
baf33aa0-13cb-5856-9ee2-6358746e87ea | note | Frequency - 0 to 400m³ - 2 tests
c7ebfe0c-56a3-53c5-927d-4715673a2ac2 | note | • 400 to 1,500m³ - 3 tests
2e63751b-2609-5a3d-a6ec-0035cf8985f6 | note | • 1,500 to 4,000m³ - 4 tests
c3006d0d-325f-559f-a85a-fbdb8b8bf5d4 | note | • >4,000m³ - 1 test for each additional 1,000m³
d3e0e39c-c80d-5977-892a-84f380b69882 | note | Activity - HP
ad281e7d-78b9-5e34-a2bc-d46572f79532 | note | By - ENG
8068389f-81b5-5e5c-add9-417418b5ff36 | signoff | AUTHORITY HOLDPOINT
52a5e716-c19f-5ad8-8370-8bbc35daeeb5 | checkpoint | 2.01.10 - Clay Index
9d5e3f97-39f7-5393-8985-e46df7d9353c | note | Acceptance / Conformance Criteria - The Clay Index shall be ≤ 5 when tested in accordance with NZS 4407 Test 3.5.
9e6d2939-557c-5f76-9ccd-0aaf26976c71 | note | Standard / Specification - PS - 7.2.3
e2d3939b-60a7-5161-99e9-c40aa73acc53 | note | Verifying Document - IANZ Lab Reports
a9885a41-188f-5625-9424-581588ef206f | note | Frequency - 0 to 400m³ - 2 tests
c2a0b25b-48f3-5d30-9933-3bc05f48181c | note | • 400 to 1,500m³ - 3 tests
a5393c6e-4bf8-5dc9-b8a0-9fe9bf6779f0 | note | • 1,500 to 4,000m³ - 4 tests
952ea3f9-ef8c-55ac-9a0c-f75ebc319466 | note | • >4,000m³ - 1 test for each additional 1,000m³
0b7ea872-5971-5448-acee-b363c516d9bc | note | Activity - HP
090588ed-6242-57a0-b608-4e8b82de9a5a | note | By - ENG
37c9d3b1-676e-5e35-87a1-efb852bd8594 | signoff | AUTHORITY HOLDPOINT
3243bdbe-628e-5c36-8ebd-fd3becd9b18b | checkpoint | 2.01.11 - Accelerated Weathering Testing
c54a8880-c803-53c9-905e-907270e1e49d | note | Acceptance / Conformance Criteria - If the difference between the tested sample and the control is >30% in the accelerated weathering test, the Contractor shall undertake additional x-ray diffraction analysis
4f2614cf-5d0f-5220-b839-2250b118dac0 | note | • The levels of smectite clay minerals are not classified as “abundant”
0a07615c-bdc7-587d-93e7-0fa6ef846f00 | note | Standard / Specification - In accordance with NZTA Standard Specification T20 Draft Specification
509cb0c4-b4c6-5133-83a7-abddb21b59b5 | note | Verifying Document - IANZ Lab Reports
8546fa8e-8880-5859-9034-8b5f93cc0f54 | note | Frequency - 2 tests per source 4 weeks before use in the works.
88f457ae-d9e2-5dda-96de-604c02b89acd | note | Activity - HP
1b214982-fb22-5d0e-ad43-16521eead8bc | note | By - ENG
6ab4e183-98ed-530e-bb16-371ac278c73f | signoff | AUTHORITY HOLDPOINT
d0430dca-b283-5720-b469-62a57fdf94d1 | checkpoint | 2.01.12 - Repeat Load Triaxial Test
b4a7ebbb-018c-5af9-9c36-b41eb6e36384 | note | Acceptance / Conformance Criteria - In accordance with NZTA T15
a908229c-118d-555b-8caa-30536f9ea3d8 | note | Standard / Specification - NZTA T15
2a799e2e-2862-583b-9ee6-f85293c43566 | note | Verifying Document - IANZ Lab Reports
f7bac258-a191-5284-b56a-383259c8f3bc | note | Frequency - 2 tests per source 4 weeks before use in the works.
b45a69e9-5f6f-5327-84db-99e2e8e8e8ac | note | Activity - HP
d88b2f97-bb88-5415-8669-2314cddde2d5 | note | By - ENG
740b30b9-cfca-5337-a89e-aca4c87f0759 | signoff | AUTHORITY HOLDPOINT
fced821f-9140-5acb-adeb-311c37d3b39f | checkpoint | 2.01.13 - Broken Face Content
5c67f160-a2f0-52f8-bd42-ca23ee461ed7 | note | Acceptance / Conformance Criteria - The aggregate broken face content in each of the three aggregate fractions between the 37.5mm and 4.75mm sieves shall not be less than 70% by weight and shall have two or more broken faces, when tested according to NZS 4407: 1991, Test 3.14 Broken Face Test.
ea889ddb-0e1d-5c83-bc77-c98178a4b221 | note | Standard / Specification - TNZ M/4: 2006, 4.2.2
9c527da4-f334-5def-9908-16581146a1d7 | note | Verifying Document - IANZ Lab Reports
12ebf109-2be6-5908-ab45-7c266f20332a | note | Frequency - 1 Test per Source
11e72989-7bc6-5b31-9135-f0d7b62160fe | note | Activity - HP
888d745c-7ad7-5f0a-9f6e-38e8a8b6c5ca | note | By - ENG
a3df93d1-6c56-587a-86a1-2946c4363d06 | signoff | AUTHORITY HOLDPOINT
03635e0c-99d6-5d68-b693-2154f48da3fd | checklist | SYS - ITP - Pavement & Surfacing - AP65 Material - Rev E | itp | ITP - Pavement & Surfacing - AP65 Material - Rev E
d9ad54c1-a038-5152-8598-fb6c422dc437 | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 General Materials
60a57887-488e-553a-9235-dee549dad0fa | checkpoint | 5.01.01 - Sampling and testing
f168b349-b948-59e0-834f-0b2ba45e5df5 | note | Acceptance / Conformance Criteria - For all aggregates, test information confirming compliance shall be supplied to the Engineer not less than five working days prior to delivery of the material to site.
94791044-7035-5d70-836b-5bd471f60add | note | Standard / Specification - PS - 7.2.4
72003631-2a30-59ed-9ccd-8bb41b9e6939 | note | Verifying Document - IANZ Lab Reports
a294e292-acfa-5d4d-8bb2-ac429ec82d86 | note | Frequency - five working days prior to delivery of the material to site.
f3890077-fa2d-5c9d-ac37-159c3531b5d4 | note | Activity - HP
a55f805a-3e05-57ce-9887-0771a0f2e46b | note | By - ENG
def14926-a024-5a92-85d5-c6280e455630 | signoff | AUTHORITY HOLDPOINT
44bbb52e-eb08-5fb4-9a98-c4769a88e409 | checkpoint | 5.01.02 - Sampling and testing
1a02b294-b8c7-54a8-88ad-4b2eadf677b4 | note | Acceptance / Conformance Criteria - Water to be used in stabilisation - The Contractor shall be responsible for ensuring that the water for stabilisation, construction and curing of stabilised layers is free from impurities that may deleteriously affect the setting, hardening, strength or durability of the bound aggregate layer.
de15fba3-2af3-5447-92e4-0ff93b28081b | note | • Water from sources other than public supply may have its suitability established to the satisfaction of the Engineer by repeating the final approved laboratory based mix design tests with the water now being considered for use.
c8b38c01-7756-58f6-b0f0-b99d29d920dc | note | • The results of these subsequent mix verification tests shall be greater than 90% of the final results from the previously verified mix design. In addition, work shall be stopped if any discolouration or residue is observed when adding or sprinkling water into or onto the material.”
bfa862fa-eabc-5114-9532-f6da19c44f1a | note | • Verifying documents to be dockets from fill up station, or proof of using public water supply. Or Lab reports for alternative supply.
bb7cea44-7b13-513c-8a99-abf001a2a74e | note | Standard / Specification - NZTA B/6 item 5
eadf6b0e-0f1f-54ef-b126-27840805effb | note | Verifying Document - Lab reports
2e2bf3d8-49b0-592e-bc51-775d11041343 | note | Frequency - Prior to Works start, per source
2b4890f2-3351-5dd2-ae9a-5f9515c05422 | note | Activity - HP
80f049ce-3bc5-58f0-8bd7-7c9c9d3deeeb | note | By - ENG
9e0439f0-b29c-5ad6-b128-ee827b0bc0be | signoff | AUTHORITY HOLDPOINT
899bfcc4-56fb-51f7-a6a0-b3bf3866f97d | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate
dcf4666f-ed3b-5158-a808-679d32a007f3 | checkpoint | 5.02.01 - Sub-base MDD and OMC
c9ddb8f7-8811-5c24-a98e-4a7b7bde9d00 | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
da0f5c1e-3efd-569f-b2ef-0d62230cc56f | note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
503a87ad-53dc-5338-b7d6-41d39018bdad | note | Verifying Document - IANZ Lab Reports
4b686472-ead5-5dca-9e19-e1a7af89afd6 | note | Frequency - 1 test per material type
cb4be3d2-1fc8-5f91-99ab-ff9da052c5f2 | note | Activity - H
abad576a-df96-543f-9ab1-765a1ff468b2 | note | By - PE
08dc85f6-1e83-5eb9-95c8-9381d1b2b315 | checkpoint | 5.02.02 - Cement for sub-base stabilisation
f2cfb2e7-40b5-5204-868e-224c0ffe7c5f | note | Acceptance / Conformance Criteria - Cement for stabilisation shall meet the requirements of NZTA B6.
7b7caba1-a9c4-5c5d-a3af-5fea17a64691 | note | Standard / Specification - PS - 7.3.2, PS - 7.2.6
1ac5d31f-9758-50ae-9f72-48d864679110 | note | Verifying Document - Datasheets
9af7f4d5-44b2-586a-b84d-14083db10bdc | note | Frequency - Prior to Use
703a7061-48ec-50a2-bf67-28fd4c8b61f9 | note | Activity - H
3ecbad6b-6769-52d3-8371-9bae9e3e68bc | note | By - PE
78ae2b7a-c28e-5b57-a046-1fdb2eff521d | checkpoint | 5.02.05 - Crushing Resistance
aaf3fcc6-69cf-5107-bdd2-324afb462409 | note | Acceptance / Conformance Criteria - The crushing resistance shall not be less than 130kN when the aggregate is tested
32d89166-cc92-5257-8a02-b42deb788bcf | note | Standard / Specification - NZS 4407: 1991 Test 3.10.
fc6cde74-b4bb-53b0-8942-0552487547d2 | note | Verifying Document - IANZ Lab Reports
835b815b-b849-51c9-8abc-91b75b5897e4 | note | Frequency - 2 tests per source 4 weeks before use in the works
10b65111-54b2-5545-b5b5-be46c4838f88 | note | Activity - HP
c72f6072-5eca-5743-b96b-117fc11d2cf9 | note | By - ENG
fefe6c68-50e3-5203-b081-fc14cfcc29be | signoff | AUTHORITY HOLDPOINT
9022871e-5b68-5285-8105-45564ce8225d | checkpoint | 5.02.06 - Weathering Resistance
b85e3249-9895-5172-a001-1466f4265669 | note | Acceptance / Conformance Criteria - The aggregate shall have a quality index of AA, AB, AC, BA, or CA when tested
1ee3589b-5081-5efc-bdad-6aba26d6e9a5 | note | Standard / Specification - NZS 4407: 1991 Test 3.11
a3776b5d-7d91-53eb-bb08-1af17fb325a2 | note | Verifying Document - IANZ Lab Reports
3b65390a-1386-58dd-8d6a-5e763cde91a7 | note | Frequency - 2 tests per source 4 weeks before use in the works
88a73c18-536b-5f46-bb46-d7b80e90b423 | note | Activity - HP
83e5610e-6576-5395-a4fa-7274e96a60c7 | note | By - ENG
8d6baafb-7a8d-5d80-9269-13464595db51 | signoff | AUTHORITY HOLDPOINT
85ee47d1-ad42-5e77-9b51-b0b7d10ea380 | checkpoint | 5.02.07 - Particle size distribution
4892293b-c97e-5f7b-8af6-863f1c449d64 | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1.
b82eadfd-0943-56e1-8a03-094e7c34f50c | note | Standard / Specification - NZS 4407: 1991 Test 3.8.1 Standard Method by Wet Sieving
3551a47b-12a0-5a1a-8ea5-7b63cff98b4c | note | Verifying Document - IANZ Lab Reports
8251bbf9-5e57-58ad-aee4-43bbe9f37c78 | note | Frequency - 0 to 400m³ - 2 tests
a4146f77-cb32-5f0c-9c04-6338cd5be9c9 | note | • 400 to 1,500m³ - 3 tests
21f6550a-d45f-508e-b98b-d3e37a65df52 | note | • 1,500 to 4,000m³ - 4 tests
331f9d0f-783e-5e9f-b806-2a9a12477903 | note | • >4,000m³ - 1 test for each additional 1,000m³
2f965ecd-3d80-5c1e-b02f-bacb5b4dbeb4 | note | Activity - HP
75b5399a-dc99-5dfa-963c-e1fb07b29c37 | note | By - ENG
129b8835-7d77-5545-af8f-f202ea555b78 | signoff | AUTHORITY HOLDPOINT
c0dcf9e2-6abe-544f-b671-04d7121ee831 | checkpoint | 5.02.08 - Sand Equivalent
04e2ce5c-fc23-51ac-b996-8b395cb81ee1 | note | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 25 when the aggregate is tested
c79417a1-d3da-5554-8196-a20418d2f028 | note | Standard / Specification - NZS 4407: 1991 Test 3.6 (Wet Method)
be91c280-43e7-5a2f-b532-dea6df56a8d0 | note | Verifying Document - IANZ Lab Reports
7ce457fc-836f-5cc6-a269-ba8371d1833a | note | Frequency - 0 to 400m³ - 2 tests
84a096bf-3ee3-5f72-a1d9-f550bc29364f | note | • 400 to 1,500m³ - 3 tests
038c979c-acff-5c79-bdf8-95a17d456d70 | note | • 1,500 to 4,000m³ - 4 tests
25a6b6d3-0568-511b-98c0-be8b869b3e71 | note | • >4,000m³ - 1 test for each additional 1,000m³
80588976-67d6-54ca-9d40-618b6fdcc383 | note | Activity - HP
04ab84ac-2b34-54a7-83a8-ae3a2671554f | note | By - ENG
1cfc74a4-63e3-58ba-a4fb-88a40554c1c8 | signoff | AUTHORITY HOLDPOINT
ae882592-6535-5217-89b2-b66f7d161cf7 | checkpoint | 5.02.09 - Liquid Limit
57abe783-f1ed-53d3-84cc-34e27300e213 | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Liquid Limit shall be ≤ 25 when tested - The LL may also be inferred (where appropriate) from the Cone Penetrometer Limit (CPL).
f3e06d3b-2107-5ca4-ab1d-8e980c44d108 | note | Standard / Specification - NZS 4402 Test 2.2, NZS4407:2015 Test 3.2.
b91bd336-8e5c-532c-ad9d-fea08ac6590e | note | Verifying Document - IANZ Lab Reports
46a082e0-947d-55f6-9700-208f12e701e9 | note | Frequency - 0 to 400m³ - 2 tests
b0e66bd0-e4af-5d26-8d47-bf34fe7b8ca6 | note | • 400 to 1,500m³ - 3 tests
7b9507c3-415a-57b6-ad99-2fa7d63f6ca9 | note | • 1,500 to 4,000m³ - 4 tests
6508a44f-453c-5a9b-9892-a3c9a4715ac5 | note | • >4,000m³ - 1 test for each additional 1,000m³
af0c1297-5477-5cdc-8dd4-ebec258aa331 | note | Activity - HP
ad6cdfd4-a91c-5346-8f1d-c169cd1087b2 | note | By - ENG
523797f1-355d-5b2b-98ca-c9f9f751c1cd | signoff | AUTHORITY HOLDPOINT
a21cc376-5cf7-5d74-91c9-7c1733c3fd7d | checkpoint | 5.02.10 - Plasticity Index
2de608fd-6034-5977-8b48-ace7c120a2de | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Plasticity Index shall be ≤ 8 when tested
c076cd42-6e8e-5b46-a0df-e078704d7870 | note | Standard / Specification - NZS 4407 Test 3.4
f288a3ff-d1e2-5f20-920c-7fa4a3abc914 | note | Verifying Document - IANZ Lab Reports
f0c423cb-1eba-5011-80ac-05005e695439 | note | Frequency - 0 to 400m³ - 2 tests
35184592-ddea-5789-9628-76295e981225 | note | • 400 to 1,500m³ - 3 tests
5948452b-0aae-5278-993c-de000a64b387 | note | • 1,500 to 4,000m³ - 4 tests
937a1689-6e30-514e-b5a1-1790273f2d37 | note | • >4,000m³ - 1 test for each additional 1,000m³
1854c9f6-3b9b-5c63-82e5-a9666a9dd2a2 | note | Activity - HP
fc35ac17-93f1-5400-aa20-a74b5557447b | note | By - ENG
5196aee7-d9f1-55aa-b012-a6ce06f7ee5c | signoff | AUTHORITY HOLDPOINT
cb3bf6ca-20c8-5a7c-847e-d41f73e602ed | checkpoint | 5.02.11 - Clay Index
7dcc80a1-3999-5c00-bfc3-bf293b8a8647 | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Clay Index shall be ≤ 5 when tested
cf25e97d-2159-5462-a6ce-4196b9d4293a | note | Standard / Specification - NZS 4407 Test 3.5
3b2b548d-399e-519d-9d69-9a2927c0b6b1 | note | Verifying Document - IANZ Lab Reports
5303e7de-4445-5c0f-9266-790d456b0644 | note | Frequency - 0 to 400m³ - 2 tests
de272e7d-a2c4-580c-9190-796fa51c3638 | note | • 400 to 1,500m³ - 3 tests
ca2a2111-0158-5182-be1b-445174fedcb3 | note | • 1,500 to 4,000m³ - 4 tests
70cecf18-9657-5d43-bafb-b89341c01cc6 | note | • >4,000m³ - 1 test for each additional 1,000m³
b7dbf86f-bc15-5ca8-aa3a-7e41cd34899b | note | Activity - HP
b985f042-7de4-52a8-b779-c1e47281412f | note | By - ENG
94cd9054-2ac2-5d95-86eb-2a71edade0c7 | signoff | AUTHORITY HOLDPOINT
00a049c7-fa08-5eaa-a1c1-4286cf25b2b3 | checkpoint | 5.02.12 - Proportion of Broken Rock
8f8865c0-7ffc-5b16-807d-503d621cbc5a | note | Acceptance / Conformance Criteria - In each of the aggregate fractions between the 63.0mm and 4.75mm sieves not less than 50% by weight shall have two or more broken faces
cf749d9a-5bf1-50bf-a203-7e3c464d3673 | note | Standard / Specification - PS - 7.2.2
aa34d7ad-4e05-5677-b27c-5f6f1411f00b | note | Verifying Document - IANZ Lab Reports
69f6c763-0a03-51d9-bfa5-534ccacaf6ef | note | Frequency - 1 Test per source of the coarse aggregate. Additional samples if source is changed
d91ec8a3-6ce2-52e2-80f0-1b03438f13ee | note | Activity - HP
87e701c1-161f-5285-9b2e-cd20ebb3e36d | note | By - ENG
4fac71dd-be3d-5be6-a8e7-ade3236dd1f1 | signoff | AUTHORITY HOLDPOINT
b87390da-e8b4-5066-b43c-5d098cda23ee | checkpoint | 5.02.13 - Organic Matter
da3f72b4-b1e3-5657-808e-2bc54fe47d04 | note | Acceptance / Conformance Criteria - It shall be free of organic matter
24f9b6df-5b16-5895-9f6b-b49960501d8d | note | Standard / Specification - PS - 7.2.2
94fee484-a5b3-5490-bb40-6bf4b0938f69 | note | Verifying Document - Photos
99cdf68f-0152-5f34-b1a5-3760076113bb | note | Frequency - Continuous
7ddb2bae-c964-5cf3-8183-009d7060c3bb | note | Activity - I
1cfad76f-afa0-56a5-94e6-cd4c58e6b657 | note | By - SE/PE
cafccf67-d4a4-52ce-86ca-59031142aa61 | checkpoint | 5.02.14 - Accelerated Weathering Testing
201f6146-1817-5edb-a22c-c29f7f45f2a0 | note | Acceptance / Conformance Criteria - If the difference between the tested sample and the control is >30% in the accelerated weathering test, the Contractor shall undertake additional x-ray diffraction analysis
f17dd1db-7f20-5312-b139-97755128b80c | note | • The levels of smectite clay minerals are not classified as “abundant”
749b65f8-ccd4-520b-90d3-1e9fdbd250c1 | note | Standard / Specification - In accordance with NZTA Standard Specification T20 Draft Specification
6586c6f9-d9c7-524c-beaf-40df78cc4131 | note | Verifying Document - Lab Reports
914cde35-1363-5dfb-920a-556fed6e74b9 | note | Frequency - 2 tests per source 4 weeks before use in the works.
658e3f08-7984-52e5-8b16-f6fa47795fdf | note | Activity - HP
225138d5-1d17-52dd-9634-c4b08fb236a4 | note | By - ENG
4fc46efe-5434-5360-aeea-81ccc050ba8c | signoff | AUTHORITY HOLDPOINT
52a5baa6-7252-5829-85ae-9f01011c7607 | checkpoint | 5.02.15 - Repeat Load Triaxial Test
46b9f88e-99c9-5a60-a968-15cc96292ceb | note | Acceptance / Conformance Criteria - In accordance with NZTA T15
8f09f694-78a6-5532-93a0-59f7ad96ba2a | note | Standard / Specification - NZTA T15
4afa3e59-c79c-5e6c-b5c5-86d8c9c5c9b0 | note | Verifying Document - IANZ Lab Reports
2be0fa1c-b437-5b11-a13e-69e22b6f8b08 | note | Frequency - 2 tests per source 4 weeks before use in the works.
ce80a921-3335-5a15-a8f6-c9b7326838fd | note | Activity - HP
5f9d6dc1-3b64-5181-89c5-19a73f488add | note | By - ENG
44646cc1-0805-5206-8ff2-ad2805cd38d2 | signoff | AUTHORITY HOLDPOINT
0b3c41da-9864-553d-886c-e0e0f1bdd386 | checkpoint | 5.02.16 - Unconfined Compressive Strength (UCS)
decd180e-26e7-56c8-a3c1-c00f8720c9e0 | note | Acceptance / Conformance Criteria - Unconfined Compressive Strength (UCS) testing of source aggregate for modified layers to test sensitivity to additives.
c865ae35-c13e-5881-99c9-18bc78a225a6 | note | Standard / Specification - PS - Table No. 7.2
f64e7a3a-7098-52be-8784-a85fae85996e | note | Verifying Document - IANZ Lab Reports
177e1bb7-f470-50c1-bb79-20e420d6426e | note | Frequency - 1 set of tests per stockpile at source. Set of tests to include proposed mix plus tests with 0.5% more and 0.5% less additive than proposed.
f69b2107-9d61-5d1d-afc0-990e1ee682b7 | note | Activity - HP
572e474c-67c5-55ad-aa87-750d7a624c7e | note | By - ENG
03cf8542-b3b1-5080-a4b3-84858ca10066 | signoff | AUTHORITY HOLDPOINT
74060e22-bf57-5ae1-9306-20409b4430fa | checkpoint | 5.02.17 - Indirect Tensile Strength (ITS)
9a4fb5ed-bd27-535b-a022-bebf285b6004 | note | Acceptance / Conformance Criteria - In accordance with draft NZTA T/19 at the rate specified in Table A7.4 using 4.0%, 4.5% and 5.0% cement (with 7 days curing) and results forwarded to the Engineer not less than 7 Working Days prior to construction for confirmation or adjustment of the additive contents.
00eb80fa-3200-5417-b532-c46d18a37a6a | note | Standard / Specification - NZTA T/19 - Table A7.4
c1e6242b-b982-5e22-a725-33ef54319773 | note | Verifying Document - IANZ Lab Reports
d2116d61-7adf-57d3-8106-1c51336749a8 | note | Frequency - 1 set of tests per stockpile at source. Set of tests to include proposed mix plus tests with 0.5% more and 0.5% less additive than proposed.
a2dcec01-55c7-552c-b0b0-ddc1a435ae63 | note | Activity - HP
ca9469bb-b5fa-592e-b002-a0f30567b1c6 | note | By - ENG
69dfb56e-21ee-5ddd-a6dc-cf1b2b495b33 | signoff | AUTHORITY HOLDPOINT
ab504289-340e-52a3-a440-30ccf878bfc3 | checklist | SYS - ITP - Pavement & Surfacing - Basecourse - Rev 1 | itp | ITP - Pavement & Surfacing - Basecourse - Rev 1
9dbf9507-d5c1-5f76-b0e9-632a875b7d7c | section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
cefa3a25-1c25-5ccc-88ec-7d7d361477ea | checkpoint | 1.01.01 - Construction Pack
86b41d6e-7a57-54f0-acd4-9e40ed52643f | note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled, uploaded and transmitted on InEight before works commence
48b32bc9-0a62-50c7-92a9-de4758e2d5b9 | note | Standard / Specification - Downer
c2407745-6aec-5335-a45f-487d44e0628d | note | Verifying Document - Construction Pack
635d558b-83ae-53b6-8c28-324ff841586c | note | Frequency - Prior to Works start
179c0622-56ca-569d-ba6e-cef8dd739f70 | note | Activity - H
07f5d58b-597f-5e2a-9f4c-03dbb5fe0c94 | note | By - PE
7d7484e5-7e1f-5fce-9b75-f8e21eb19c86 | checkpoint | 1.01.02 - Survey Setout
ec56372d-7f16-5af7-9f23-164babafc370 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
28cbcb6f-c9fb-5f99-97ef-82f133603fab | note | Standard / Specification - Downer
571e6655-cf54-56a2-9cc4-32c6cf1b01a8 | note | Verifying Document - Survey Records
f8e4441a-1fc7-5887-bc24-e5e60ee6611a | note | Frequency - Prior to Works start
b24be07a-99c7-505d-bcb1-651936634b9e | note | Activity - H
eb0f9fe1-4d71-5775-8d5e-50050bef0de8 | note | By - SV
79e2e2cc-742b-5773-8fd6-174684bde5a5 | checkpoint | 1.01.03 - Service Location
cd865226-1847-5604-87bf-c74fdf0f19a3 | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
806a9f08-5828-5c64-bc3e-a0cb61d5562b | note | Standard / Specification - Downer
5ddce83b-fb05-5414-958c-e8cb3781aa33 | note | Verifying Document - Excavation Permit
867bcb55-3fec-55a1-b73e-5f950b8c745d | note | Frequency - Prior to Excavation
f7a63b5b-8d8b-5f81-ba95-3bfcd9af5f72 | note | Activity - H
b2a6ad39-f65a-58c5-b7c7-7bde258f6dd4 | note | By - SE
ad83f4fc-998f-5888-aac1-cc53c7027f3f | checkpoint | 1.01.04 - Internal Permits
8ef54786-5417-587e-b131-af96f335f981 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. if applicable.
d05b2ec1-4b76-5f23-95bc-f96aab74703d | note | Standard / Specification - Downer
3480ef1e-9618-5dc4-a9a1-7d1d972a0262 | note | Verifying Document - Internal Permits
5674f571-bbd2-58e6-ae20-7a40c27a268a | note | Frequency - Prior to activity being undertaken
21fbf00a-0cdf-5c56-b06f-31055c0966db | note | Activity - H
c5e199e6-c2fe-53c2-9477-f27de993e720 | note | By - SE
e11cb217-f08d-5dc6-99ac-594e90eeba14 | checkpoint | 1.01.05 - External Permits
61f5d04c-2805-5c3f-abc9-de003443ecb3 | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc, if applicable.
fe163655-f22f-5068-bc08-29a102908d62 | note | Standard / Specification - Downer
9f87a84d-c1e7-5534-9993-4b54a1767bfd | note | Verifying Document - External Permits
843356da-df80-5dec-8e71-df4baaa2d60a | note | Frequency - Prior to commencment of activity
33c77b62-d5e6-5d1d-bf39-72822d0fa627 | note | Activity - H
093b1822-81bb-5110-af70-8af678b7a11e | note | By - PE
43363844-3b56-5615-9c65-3fbf47407c1a | checkpoint | 1.01.06 - Approved Construction Drawings
faadc6af-5fc5-5d53-850f-a7ec9dc5cd62 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
4bb0d13c-160f-5d2a-8221-f236cbe9a59b | note | Standard / Specification - Downer
ce420d1e-c0ed-5cdd-aa45-43bd7850568d | note | Verifying Document - IFC Drawings
5e753f69-7365-5fc6-9c5a-7b100bcdf085 | note | Frequency - Prior to works start
4b246132-854c-59e0-b14e-8bf9a1b68ab3 | note | Activity - H
b25acc76-bd2a-5e63-a65f-bfc35c711d0e | note | By - PE
65941cbf-2f0f-533b-8392-c7461b71c15e | checkpoint | 1.01.07 - Subbase Approval
0c114bd5-9799-56e0-b63a-0ad5d4fb9e0b | note | Acceptance / Conformance Criteria - All subbase QA to be sent to Engineer for review 48 hours prior to placing basecourse. Final inspection of subbase required, looking for any cracks in stabilised pavement and pavement is clean, free of and contamination
22226472-fa19-56c0-a111-b205214c4dad | note | Standard / Specification - PS - Page 42
854702a8-e776-568c-a112-a6486a17a17f | note | Verifying Document - ConQA
a90e1905-ceb6-558f-80c3-6a4abce9955a | note | Frequency - Before proceeding to the next layer
29b3dba1-842b-5a4e-8b73-4613dc36d483 | note | Activity - HP
a16e36c3-e5cd-5bfe-99b1-d56bc2c4dbae | note | By - ENG
4de458ee-d43a-5185-b6f3-d9955ae6749c | signoff | AUTHORITY HOLDPOINT
2099df3b-c276-5838-a49f-4a50752ce07c | section | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
352fed59-897f-5876-9fd2-24566b9b76ad | checkpoint | 3.01.01 - Average Uncompacted Layer Thickness
dbbd429c-71bb-5812-85da-dcc9a18eedc9 | note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
a371278e-8f76-5b57-b0e1-d6b44c03d6d2 | note | Standard / Specification - TNZ B/02: 2005 - 7.3
b40b0852-21dd-5607-a013-f8e6812c5725 | note | Verifying Document - Survey / Level Checks
8ead24d5-9c8f-5d9f-b807-27ff02162e82 | note | Frequency - 1 test per 20m
030068ab-38a5-5036-82f6-7ac7a7c1bd1e | note | Activity - I
659025bf-5cfa-55f8-856f-5b915f8d83d3 | note | By - SV / PE
6bff0f11-9f30-55fa-ad6d-a9738b399ec2 | checkpoint | 3.01.02 - Basecourse MDD and OMC
9fb00a71-854c-50c7-beeb-d555fad763b0 | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). Test to be at heavy compaction vibrating hammer, Test on Mat Samples on site.
d7dcc15a-3087-5bd3-8abd-001433a8da70 | note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
9938c1d4-af1e-54ec-ab05-56cbfcbe7dab | note | Verifying Document - IANZ Lab Reports
97c4a02d-759c-5772-a5d0-568ae3601e2a | note | Frequency - No less than 1 test every 5,000m³ (in place)
667eba4a-5457-54fb-b177-accc707507cc | note | Activity - R
02b79946-e421-55fa-8f12-ece77e587346 | note | By - PE
2720a964-8fc8-5970-9840-dd73e5fd0868 | checkpoint | 3.01.03 - Plateau Density Test
92929d68-63f0-57fb-ac65-531cb6e97659 | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC.
7ae1ef54-9208-5e9a-9fa2-285c104c3707 | note | • Every plateau to be completed at start of works and witnessed by a member of BBO.
80a36b75-0644-57d6-b71a-01cbf8adf488 | note | Standard / Specification - PS - Table 7.2 - 2.3
1c6e177a-3638-54ba-b5da-acd2905a56f3 | note | Verifying Document - Plateau Density Report
23d37c95-78a9-507c-934c-2f3070031b71 | note | Frequency - 5 tests per 10,000m2
45af7d7f-9458-53aa-8eec-57f4e7c57ee8 | note | Activity - I
d61ec9d0-c82c-5d5b-b51c-8d408366ffc7 | note | By - PE
4e14b0f0-c185-58d4-9839-d9056137f0a5 | checkpoint | 3.01.04 - Plasticity Index
e71f59ac-edd0-5e70-beca-82c70dca5b37 | note | Acceptance / Conformance Criteria - The Plasticity Index shall be ≤ 8 when tested in accordance with NZS 4407 Test 3.4
b86b747b-e06f-56e2-b657-241efaf003a0 | note | Standard / Specification - PS - 7.2.3
c489a8b1-a8ea-5f82-80ba-4ff4eded1c9a | note | Verifying Document - IANZ Lab Reports
d0adc64e-bcd5-5457-86b4-ec52e3ab0aa1 | note | Frequency - 2 tests per 1000m3 (in place)
90bd30ec-e53e-5268-94dc-d9959a20dc19 | note | Activity - R
a78cabee-87cf-590d-9de2-bf174b81ae9d | note | By - PE
8a2c0976-e84e-5cf4-b6b0-3ac926fe3e13 | checkpoint | 3.01.05 - Clay Index
3a8afc40-bfb2-549a-9089-5e6cbffcfc0d | note | Acceptance / Conformance Criteria - The Clay Index shall be ≤ 5 when tested in accordance with NZS 4407 Test 3.5.
18e72bbf-5f3e-5c0a-b3e4-b741b323ed91 | note | Standard / Specification - PS - 7.2.3
2cfd3280-099b-589e-b0ad-7f3ef4136fe4 | note | Verifying Document - IANZ Lab Reports
f2948c97-c966-5ad9-a79d-7bcb312db057 | note | Frequency - 2 tests per 1000m3 (in place)
3d3935ec-fb55-5601-bae8-b23d5ec8039c | note | Activity - R
512ba664-826d-5b63-aede-02a1b8d62ee4 | note | By - PE
b88285ba-0f34-5cb7-a186-5c9887a7c5ef | checkpoint | 3.01.06 - Sand Equivalent
e166ae74-624b-5e5b-8d9a-3a8218aff852 | note | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 40 when the aggregate is tested according to NZS 4407 : 1991, Test 3.6 Sand Equivalent Test.
de055241-e1a2-5d0b-af5e-54efa88d6216 | note | • If Sand Equivalence is < 40, then Clay Index shall not be > 3 and Plasticity Index shall not be > 5 (both being tested in accordance with the methods described above).
3bcda7c7-cfe0-5d4e-9e67-ea1bf377c756 | note | • The Sand Equivalent shall be determined using the Wet Method in NZS 4407: 1991 Test 3.6
c0544496-3ce2-5232-addd-e6938e540abe | note | Standard / Specification - TNZ M/4: 2006, 4.2.1.1
95f11bf1-a8e0-5084-9d61-adb3d2756506 | note | Verifying Document - IANZ Lab Reports
a9ad710d-e165-5ea8-9e4a-195b132d5d53 | note | Frequency - 2 tests per 1000m3 (in place)
dc69b47a-7de9-58a0-8dc6-5dfc49859c1a | note | Activity - R
9a56c638-031b-545e-9eb5-c0d4183f3245 | note | By - PE
449c088a-3ebf-54be-9533-ad0513888c3d | checkpoint | 3.01.07 - Particle size distribution
dc243aeb-782c-5f73-b035-5d90192571f4 | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 2 and 3 from TNZ M/4:2006.
b0c97723-290e-5e45-b606-54c180dd52e6 | note | Standard / Specification - TNZ M/4: 2006
c9462b1e-4a16-5f8f-a838-4b695ad099c3 | note | Verifying Document - IANZ Lab Reports
de976264-2028-5f1e-8b40-58405ee4b2d9 | note | Frequency - 2 tests per 1000m3 (in place)
b5a313f0-8f07-5136-8235-a6fc300ace71 | note | Activity - R
b094c546-d0d7-50d0-91ac-5751b343c6f2 | note | By - PE
e50d581c-ff5c-5a8b-9090-af0dbfd70512 | checkpoint | 3.01.08 - Basecourse Pavement Layer Compaction
8450682a-d54d-54ca-a371-5bb0648b9165 | note | Acceptance / Conformance Criteria - Mean Value ≥ 98 Minimum Value ≥ 95, Backscatter.
8e0dcf5b-a8df-5f00-b697-e5b4bce57cf6 | note | Standard / Specification - TNZ B/02: 2005 - 7.6
b8033767-e17d-51ab-bb92-a013d34318a7 | note | Verifying Document - NDM Report
bab4c537-af20-54f8-af38-8deb39ed41a2 | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
278f4a50-e7d8-5134-80fb-5ad235f4576a | note | Activity - I
3423ebfa-0c74-5182-b8a1-5bd4e9ada4e3 | note | By - PE
076acd1a-d68c-56e6-8e09-9d28fe8e6eea | checkpoint | 3.01.09 - Surface Shape
aa160684-d90c-5c2f-8670-9c7345013797 | note | Acceptance / Conformance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual..
6fd83484-45a3-58f8-9dfb-7c1c0a96d94b | note | Standard / Specification - TNZ B/02: 2005 - 7.7
96340ffb-3e65-5eac-96b6-68c84daeac5e | note | Verifying Document - Survey / Straight edge Report
baf33aa0-13cb-5856-9ee2-6358746e87ea | note | Frequency - Prior to sealing
c7ebfe0c-56a3-53c5-927d-4715673a2ac2 | note | Activity - I
2e63751b-2609-5a3d-a6ec-0035cf8985f6 | note | By - SV / PE
68647e04-f177-5bf8-ae53-a691675b2ae3 | checkpoint | 3.01.10 - Holding Water
9d5e3f97-39f7-5393-8985-e46df7d9353c | note | Acceptance / Conformance Criteria - No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1%
9e6d2939-557c-5f76-9ccd-0aaf26976c71 | note | Standard / Specification - TNZ B/02: 2005 - 7.7
e2d3939b-60a7-5161-99e9-c40aa73acc53 | note | Verifying Document - Visual Inspection / Site Note
a9885a41-188f-5625-9424-581588ef206f | note | Frequency - Prior to sealing
c2a0b25b-48f3-5d30-9933-3bc05f48181c | note | Activity - I
a5393c6e-4bf8-5dc9-b8a0-9fe9bf6779f0 | note | By - SV / PE
114181ad-1d3e-5704-8bad-57e55e62cc3f | checkpoint | 3.01.11 - Maximum Width Variation
c54a8880-c803-53c9-905e-907270e1e49d | note | Acceptance / Conformance Criteria - Unconstrained : –20 mm +100 mm
4f2614cf-5d0f-5220-b839-2250b118dac0 | note | • Constrained : Zero
0a07615c-bdc7-587d-93e7-0fa6ef846f00 | note | Standard / Specification - TNZ B/02: 2005 - 5.1
509cb0c4-b4c6-5133-83a7-abddb21b59b5 | note | Verifying Document - Survey / Level Checks
8546fa8e-8880-5859-9034-8b5f93cc0f54 | note | Frequency - Before Next layer or Surfacing
88f457ae-d9e2-5dda-96de-604c02b89acd | note | Activity - I
1b214982-fb22-5d0e-ad43-16521eead8bc | note | By - SV / PE
0ac7854a-15e5-5cba-9b22-49dac0fe46f5 | checkpoint | 3.01.12 - Maximum Vertical Basecourse With Concrete Channel Variation
b4a7ebbb-018c-5af9-9c36-b41eb6e36384 | note | Acceptance / Conformance Criteria - At or close to the lip of channel: –5 mm +5 mm
a908229c-118d-555b-8caa-30536f9ea3d8 | note | • At other locations on pavement: –5 mm +15 mm
2a799e2e-2862-583b-9ee6-f85293c43566 | note | Standard / Specification - TNZ B/02: 2005 - 5.1
f7bac258-a191-5284-b56a-383259c8f3bc | note | Verifying Document - Survey / Level Checks
b45a69e9-5f6f-5327-84db-99e2e8e8e8ac | note | Frequency - Before Surfacing
d88b2f97-bb88-5415-8669-2314cddde2d5 | note | Activity - I
732ddd51-a403-5cbd-8243-c72ee577856a | note | By - SV / PE
60f50fac-f8d5-5660-82a2-c867c3e1eeb4 | checkpoint | 3.01.13 - Maximum Crossfall Variation
5c67f160-a2f0-52f8-bd42-ca23ee461ed7 | note | Acceptance / Conformance Criteria - The crossfall between any two points more than 2m apart, transverse to the centreline, shall not depart from the crossfall shown in the documents by more than 0.5%
ea889ddb-0e1d-5c83-bc77-c98178a4b221 | note | Standard / Specification - TNZ B/02: 2005 - 5.1
9c527da4-f334-5def-9908-16581146a1d7 | note | Verifying Document - Survey / Level Checks
12ebf109-2be6-5908-ab45-7c266f20332a | note | Frequency - Before Surfacing
11e72989-7bc6-5b31-9135-f0d7b62160fe | note | Activity - I
888d745c-7ad7-5f0a-9f6e-38e8a8b6c5ca | note | By - SV / PE
5d9724b3-36dc-5598-895e-a900378b0ac2 | checkpoint | 3.01.14 - Benkelman Beam
4b5b3f0a-183d-5bad-a8f7-b0818fd4feff | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer. Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY
8126b007-cc77-532a-bd21-14c073978c8d | note | Standard / Specification - PS - 7.3.2
44fa1f00-8205-5566-8533-f958b07c388e | note | Verifying Document - Benkelman Beam Report
09ab0245-b2b2-5a04-ace4-d10a308c257c | note | Frequency - every 10m of each lane – staggered between left and right wheel path.
be216873-42cc-5f8a-9ca4-94e7e2d5e346 | note | Activity - R
678cb500-e4e0-5f55-a9d7-eae559b8cca6 | note | By - PE
d9a818f0-8e9a-541c-9894-3a3f6a089dea | checkpoint | 3.01.15 - NAASRA roughness
cbc72159-c7a3-5248-b9fa-4b94345cd365 | note | Acceptance / Conformance Criteria - The longitudinal smoothness of the final surfacing layer shall comply with the maximum NAASRA roughness value detailed in the specific contract requirements. (Recommended but not required)
e65d3e44-613d-58e9-815d-8d6ee333a610 | note | Standard / Specification - TNZ B/02: 2005 - 7.7
f1bbe188-bfad-554e-9963-e3f3b39545ba | note | Verifying Document - Test Report
802ff844-fdea-55c2-93c0-8ab81c71a1f2 | note | Frequency - Prior to sealing
b5a75739-990b-5360-a212-bfef6bf93040 | note | Activity - R
f6c7ac08-c956-5cb3-9ea3-82b27ff339de | note | By - PE
2422f5b8-6c41-5a92-8059-73c45dd7ed52 | checkpoint | 3.01.16 - Running Course
6ddc7923-4ea0-538c-ae2e-d8a58e7ee576 | note | Acceptance / Conformance Criteria - If running course is used it shall be spread uniformly over the pavement surface and maintained until removed. During working hours traffic shall be channelised by suitably defined traffic lanes with frequent transverse shifts of the defined lanes to obtain an even spread of traffic over the entire surface.
97ad3067-b7f0-5183-9345-e0fee5d98b01 | note | Standard / Specification - TNZ B/02: 2005 - 10.1
02bd5c5e-5d29-59e1-8ff6-cae122d46f05 | note | Verifying Document - Site Notes
f865adc9-6ac9-5412-824c-c1bc4657fe59 | note | Frequency - Prior to sealing
4f958e86-7437-5460-81fa-2c20b405c6af | note | Activity - S
307c7f07-0e69-5b30-9a9c-742cac6987f0 | note | By - SUP
8e7858c9-873d-51d1-a21b-ad5d40fe337a | checkpoint | 3.01.17 - Surface Finish post sweeping
79301678-cdc5-526b-92a5-ec40a58b15ca | note | Acceptance / Conformance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
f1193419-55d8-5a46-bbc4-268999939f01 | note | Standard / Specification - TNZ B/02: 2005 - 7.8
2c5eaac8-6be2-5db5-9e07-971bcecf801f | note | Verifying Document - Photos
f4da713c-d90c-560a-bec2-643d270444e3 | note | Frequency - Prior to sealing
06cb4779-3c73-5927-bd81-50253589081b | note | Activity - R
650e5f29-2aab-5136-a6e5-352e41824e4c | note | By - PE
935cb117-67ba-5982-9257-c1cb9a890a02 | checkpoint | 3.01.18 - Tie in into Existing Pavement
e47c839e-10ab-52bc-9da5-4b3f5302db06 | note | Acceptance / Conformance Criteria - Where tapering of basecourse including finishing layer aggregate is necessary to provide a smooth transition from the new surface to an existing surface, placement of the basecourse or finishing layer shall be stopped at the minimum uncompacted thickness specified in clause 7.3(a).
f49955e8-2930-5eaa-8fff-4aa29fef0f12 | note | • The Contractor shall then saw cut the existing seal at the tie-in (end of taper), remove existing pavement material and replace it with approved basecourse to an average uncompacted thickness of greater than 2.5 times the maximum particle size of the basecourse used.
79ff790a-0eb1-5f0b-bdb3-8bd78d10ad67 | note | Standard / Specification - TNZ B/02: 2005, 7.4
29ad3d21-5e2a-5945-88fa-8b02f6537760 | note | Verifying Document - photos, and survey data of undercut
bd7ebd18-69e0-5efd-ba7c-bb5f6c987414 | note | Frequency - Every tying into existing pavements
91296060-7787-5b8d-8503-893e4f648768 | note | Activity - I
623ed7a7-5277-5241-9051-22912d88a908 | note | By - SV / PE
84c3283d-24bd-504e-b593-7adb2a662256 | section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
3b5a624e-1a11-5114-9440-fe27a39734f1 | checkpoint | 4.01.01 - Survey Records
61996f2a-360d-58ca-b002-d0ec112979d3 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and record.
ef33a047-ce94-5d83-9ec1-97210b4bb05d | note | Standard / Specification - PS - Page 42
9f15b713-aa3c-537d-a7c5-4acc6e9e898e | note | Verifying Document - Records
ee3094fe-e7d2-51aa-bc36-b1fa4b41ea8e | note | Frequency - Post construction
ce7486bf-d5e6-58ba-9bf6-7f600631abc4 | note | Activity - H
beea42b2-951f-576f-9550-2639c1a409ef | note | By - SV
e8ea0340-b993-5d44-af71-763ab2d18509 | checkpoint | 4.01.02 - Redline Drawings
6b4ad168-19a5-5e59-baa8-dd5981f8c644 | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
e38cab94-b76a-53bd-a428-60832ee679fb | note | Standard / Specification - Downer
95e8391a-7508-5b76-8a26-3cf9c3b3a58b | note | Verifying Document - Redlines
1808be42-969c-5144-9ffb-757393ac708f | note | Frequency - Post construction
5e63c918-6e2f-5606-9087-3b173c5b56a6 | note | Activity - H
a8b3b982-00ae-54bb-bc28-91cd1ff00f38 | note | By - PE
fb2a5852-cb3f-5e91-bef4-8cf786a594fb | checklist | SYS - ITP - Pavement & Surfacing - Basecourse Rev A | itp | ITP - Pavement & Surfacing - Basecourse Rev A
9dbf9507-d5c1-5f76-b0e9-632a875b7d7c | section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
cefa3a25-1c25-5ccc-88ec-7d7d361477ea | checkpoint | 1.01.01 - Construction Pack
86b41d6e-7a57-54f0-acd4-9e40ed52643f | note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled, uploaded and transmitted on InEight before works commence
48b32bc9-0a62-50c7-92a9-de4758e2d5b9 | note | Standard / Specification - Downer
c2407745-6aec-5335-a45f-487d44e0628d | note | Verifying Document - Construction Pack
635d558b-83ae-53b6-8c28-324ff841586c | note | Frequency - Prior to Works start
179c0622-56ca-569d-ba6e-cef8dd739f70 | note | Activity - H
07f5d58b-597f-5e2a-9f4c-03dbb5fe0c94 | note | By - PE
7d7484e5-7e1f-5fce-9b75-f8e21eb19c86 | checkpoint | 1.01.02 - Survey Setout
ec56372d-7f16-5af7-9f23-164babafc370 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
28cbcb6f-c9fb-5f99-97ef-82f133603fab | note | Standard / Specification - Downer
571e6655-cf54-56a2-9cc4-32c6cf1b01a8 | note | Verifying Document - Survey Records
f8e4441a-1fc7-5887-bc24-e5e60ee6611a | note | Frequency - Prior to Works start
b24be07a-99c7-505d-bcb1-651936634b9e | note | Activity - H
eb0f9fe1-4d71-5775-8d5e-50050bef0de8 | note | By - SV
79e2e2cc-742b-5773-8fd6-174684bde5a5 | checkpoint | 1.01.03 - Service Location
cd865226-1847-5604-87bf-c74fdf0f19a3 | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
806a9f08-5828-5c64-bc3e-a0cb61d5562b | note | Standard / Specification - Downer
5ddce83b-fb05-5414-958c-e8cb3781aa33 | note | Verifying Document - Excavation Permit
867bcb55-3fec-55a1-b73e-5f950b8c745d | note | Frequency - Prior to Excavation
f7a63b5b-8d8b-5f81-ba95-3bfcd9af5f72 | note | Activity - H
b2a6ad39-f65a-58c5-b7c7-7bde258f6dd4 | note | By - SE
ad83f4fc-998f-5888-aac1-cc53c7027f3f | checkpoint | 1.01.04 - Internal Permits
8ef54786-5417-587e-b131-af96f335f981 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. if applicable.
d05b2ec1-4b76-5f23-95bc-f96aab74703d | note | Standard / Specification - Downer
3480ef1e-9618-5dc4-a9a1-7d1d972a0262 | note | Verifying Document - Internal Permits
5674f571-bbd2-58e6-ae20-7a40c27a268a | note | Frequency - Prior to activity being undertaken
21fbf00a-0cdf-5c56-b06f-31055c0966db | note | Activity - H
c5e199e6-c2fe-53c2-9477-f27de993e720 | note | By - SE
e11cb217-f08d-5dc6-99ac-594e90eeba14 | checkpoint | 1.01.05 - External Permits
61f5d04c-2805-5c3f-abc9-de003443ecb3 | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc, if applicable.
fe163655-f22f-5068-bc08-29a102908d62 | note | Standard / Specification - Downer
9f87a84d-c1e7-5534-9993-4b54a1767bfd | note | Verifying Document - External Permits
843356da-df80-5dec-8e71-df4baaa2d60a | note | Frequency - Prior to commencment of activity
33c77b62-d5e6-5d1d-bf39-72822d0fa627 | note | Activity - H
093b1822-81bb-5110-af70-8af678b7a11e | note | By - PE
43363844-3b56-5615-9c65-3fbf47407c1a | checkpoint | 1.01.06 - Approved Construction Drawings
faadc6af-5fc5-5d53-850f-a7ec9dc5cd62 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
4bb0d13c-160f-5d2a-8221-f236cbe9a59b | note | Standard / Specification - Downer
ce420d1e-c0ed-5cdd-aa45-43bd7850568d | note | Verifying Document - IFC Drawings
5e753f69-7365-5fc6-9c5a-7b100bcdf085 | note | Frequency - Prior to works start
4b246132-854c-59e0-b14e-8bf9a1b68ab3 | note | Activity - H
b25acc76-bd2a-5e63-a65f-bfc35c711d0e | note | By - PE
65941cbf-2f0f-533b-8392-c7461b71c15e | checkpoint | 1.01.07 - Subbase Approval
0c114bd5-9799-56e0-b63a-0ad5d4fb9e0b | note | Acceptance / Conformance Criteria - All subbase QA to be sent to Engineer for review 48 hours prior to placing basecourse. Final inspection of subbase required, looking for any cracks in stabilised pavement and pavement is clean, free of and contamination
22226472-fa19-56c0-a111-b205214c4dad | note | Standard / Specification - PS - Page 42
854702a8-e776-568c-a112-a6486a17a17f | note | Verifying Document - ConQA
a90e1905-ceb6-558f-80c3-6a4abce9955a | note | Frequency - Before proceeding to the next layer
29b3dba1-842b-5a4e-8b73-4613dc36d483 | note | Activity - HP
a16e36c3-e5cd-5bfe-99b1-d56bc2c4dbae | note | By - ENG
4de458ee-d43a-5185-b6f3-d9955ae6749c | signoff | AUTHORITY HOLDPOINT
2099df3b-c276-5838-a49f-4a50752ce07c | section | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
352fed59-897f-5876-9fd2-24566b9b76ad | checkpoint | 3.01.01 - Average Uncompacted Layer Thickness
61996f2a-360d-58ca-b002-d0ec112979d3 | note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
ef33a047-ce94-5d83-9ec1-97210b4bb05d | note | Standard / Specification - TNZ B/02: 2005 - 7.3
9f15b713-aa3c-537d-a7c5-4acc6e9e898e | note | Verifying Document - Survey / Level Checks
ee3094fe-e7d2-51aa-bc36-b1fa4b41ea8e | note | Frequency - 1 test per 20m
ce7486bf-d5e6-58ba-9bf6-7f600631abc4 | note | Activity - I
beea42b2-951f-576f-9550-2639c1a409ef | note | By - SV / PE
6bff0f11-9f30-55fa-ad6d-a9738b399ec2 | checkpoint | 3.01.02 - Basecourse MDD and OMC
6b4ad168-19a5-5e59-baa8-dd5981f8c644 | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). Test to be at heavy compaction vibrating hammer, Test on Mat Samples on site.
e38cab94-b76a-53bd-a428-60832ee679fb | note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
95e8391a-7508-5b76-8a26-3cf9c3b3a58b | note | Verifying Document - IANZ Lab Reports
1808be42-969c-5144-9ffb-757393ac708f | note | Frequency - No less than 1 test every 5,000m³ (in place)
5e63c918-6e2f-5606-9087-3b173c5b56a6 | note | Activity - R
a8b3b982-00ae-54bb-bc28-91cd1ff00f38 | note | By - PE
2720a964-8fc8-5970-9840-dd73e5fd0868 | checkpoint | 3.01.03 - Plateau Density Test
4c70738b-9945-5d8e-9935-1b4f479b74a6 | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC.
f2b848ee-5123-51ba-b59f-430481f5cca9 | note | • Every plateau to be completed at start of works and witnessed by a member of BBO.
df7f97e0-c86a-50d9-9ad4-16669a8c3bc3 | note | Standard / Specification - PS - Table 7.2 - 2.3
c5dfae8a-731d-5b7b-b105-cf67c923f7f0 | note | Verifying Document - Plateau Density Report
e4fb35dc-fd06-5de3-8839-30a51aefab23 | note | Frequency - 5 tests per 10,000m2
fab8ea6f-9794-5a7a-806f-1ae67d59f91a | note | Activity - I
b5097cc0-28f7-54d6-ba91-b73181bd57c3 | note | By - PE
4e14b0f0-c185-58d4-9839-d9056137f0a5 | checkpoint | 3.01.04 - Plasticity Index
9428cb25-c660-571a-83c2-48f65d10d708 | note | Acceptance / Conformance Criteria - The Plasticity Index shall be ≤ 8 when tested in accordance with NZS 4407 Test 3.4
832e680e-3779-5406-b410-37105d9d6b3b | note | Standard / Specification - PS - 7.2.3
c92385f1-b279-5b48-8ab4-b79e3a41a8e8 | note | Verifying Document - IANZ Lab Reports
53aeb8e0-be89-59d3-94d0-baae5ffc0ebc | note | Frequency - 2 tests per 1000m3 (in place)
9dae6715-81e9-5641-9843-062f4b9d4d70 | note | Activity - R
a1135677-c7ff-593d-aaae-6c7b3fe06789 | note | By - PE
8a2c0976-e84e-5cf4-b6b0-3ac926fe3e13 | checkpoint | 3.01.05 - Clay Index
980aa591-371c-5620-b0c3-c300e1cd0ef7 | note | Acceptance / Conformance Criteria - The Clay Index shall be ≤ 5 when tested in accordance with NZS 4407 Test 3.5.
f1143f60-5e96-587f-a81c-7729b13857b2 | note | Standard / Specification - PS - 7.2.3
4e12179c-b8d6-534e-9f37-b1355ae75c2c | note | Verifying Document - IANZ Lab Reports
d3f892f5-49d5-5728-8ea8-f4b1912aa06d | note | Frequency - 2 tests per 1000m3 (in place)
042b83b0-dbad-5905-8d31-d5a8b13977a9 | note | Activity - R
3c0b4c4c-cdd4-5a34-a994-fb7f704589e8 | note | By - PE
b88285ba-0f34-5cb7-a186-5c9887a7c5ef | checkpoint | 3.01.06 - Sand Equivalent
726621d7-27f6-52b2-927b-43b2cc1100d6 | note | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 40 when the aggregate is tested according to NZS 4407 : 1991, Test 3.6 Sand Equivalent Test.
7e160bc1-eaae-5ccb-b5f7-1db6f97701e5 | note | • If Sand Equivalence is < 40, then Clay Index shall not be > 3 and Plasticity Index shall not be > 5 (both being tested in accordance with the methods described above).
5c137323-6a75-5ba1-a10a-8b4f2bae16f2 | note | • The Sand Equivalent shall be determined using the Wet Method in NZS 4407: 1991 Test 3.6
d43dc0c9-dd42-5541-a1be-00315e4309d0 | note | Standard / Specification - TNZ M/4: 2006, 4.2.1.1
23fc90d9-344d-5993-8473-ca1d9831b407 | note | Verifying Document - IANZ Lab Reports
8bb6be96-edce-5cfb-aea9-ef4593bfaeb9 | note | Frequency - 2 tests per 1000m3 (in place)
e5a8a33d-779a-54d4-93b8-824d28c8e286 | note | Activity - R
c98c3686-6b39-52f3-b429-3efe7972c05d | note | By - PE
449c088a-3ebf-54be-9533-ad0513888c3d | checkpoint | 3.01.07 - Particle size distribution
0cc42aba-7f48-5c7e-a020-01d44689fa1e | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 2 and 3 from TNZ M/4:2006.
a3209b3a-9025-5ca0-a31a-eaa7d83ba3bf | note | Standard / Specification - TNZ M/4: 2006
b5fd9a6e-080e-52b6-9ab0-f373a77006cf | note | Verifying Document - IANZ Lab Reports
900bdd6f-80e5-5333-8070-b6a3ca1926a6 | note | Frequency - 2 tests per 1000m3 (in place)
46ac7b09-238b-568f-985b-441e021dd201 | note | Activity - R
45dd3903-6a5b-54c5-9558-3a45434e4f0f | note | By - PE
e50d581c-ff5c-5a8b-9090-af0dbfd70512 | checkpoint | 3.01.08 - Basecourse Pavement Layer Compaction
0abbb9e8-c654-57aa-9d07-086307f3d830 | note | Acceptance / Conformance Criteria - Mean Value ≥ 98 Minimum Value ≥ 95, Backscatter.
56d94450-db35-50aa-9bcd-d40269206152 | note | Standard / Specification - TNZ B/02: 2005 - 7.6
9bd72395-a5ad-5363-8bcd-5053935b0f4b | note | Verifying Document - NDM Report
01c21d07-37ee-5134-a66e-03efec994413 | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
12c98615-6f6e-5838-9aa6-45f2accabd63 | note | Activity - I
2d9328c6-726b-5751-85b0-58b28779c7c6 | note | By - PE
076acd1a-d68c-56e6-8e09-9d28fe8e6eea | checkpoint | 3.01.09 - Surface Shape
3e108854-18a8-5a4b-9ac5-ed42765cdce9 | note | Acceptance / Conformance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual..
b79fbe38-bb69-5d66-8f75-de5247d7b89e | note | Standard / Specification - TNZ B/02: 2005 - 7.7
f87b6b0b-8604-5f0e-a75d-4188758dd27e | note | Verifying Document - Survey / Straight edge Report
1348249b-3430-50f4-9605-fe348f91a085 | note | Frequency - Prior to sealing
051e0e0c-7d7a-5b10-a0ce-02a3778bb72d | note | Activity - I
b151c7b9-d4f2-5e01-b082-b8a4a33560ff | note | By - SV / PE
68647e04-f177-5bf8-ae53-a691675b2ae3 | checkpoint | 3.01.10 - Holding Water
154fdef1-406d-5ee4-ae81-2acbab551fa8 | note | Acceptance / Conformance Criteria - No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1%
26a65ad3-5b47-5908-b666-9faca739c33f | note | Standard / Specification - TNZ B/02: 2005 - 7.7
fa6566bc-209a-5e60-b3c7-276a11b25cd5 | note | Verifying Document - Visual Inspection / Site Note
37ac38ee-41be-519b-8411-6a2558ae90a3 | note | Frequency - Prior to sealing
242c5792-550b-52b5-bb5c-841f087217d3 | note | Activity - I
960d525d-f9ad-5ce4-ab12-214328a64bc6 | note | By - SV / PE
114181ad-1d3e-5704-8bad-57e55e62cc3f | checkpoint | 3.01.11 - Maximum Width Variation
9142b453-73fb-50cf-b2bc-eff548533226 | note | Acceptance / Conformance Criteria - Unconstrained : –20 mm +100 mm
271825ce-fa16-5b03-9ddc-e148a170a6f9 | note | • Constrained : Zero
406592a8-59a6-57e6-84a8-7c7e05277778 | note | Standard / Specification - TNZ B/02: 2005 - 5.1
b62f91af-a25f-55f5-9354-480fc10a5db3 | note | Verifying Document - Survey / Level Checks
e68cba31-420c-5e35-aa16-2866607d7493 | note | Frequency - Before Next layer or Surfacing
ef37a10f-288b-5d39-aa24-b99164e64f6d | note | Activity - I
174255dc-9dff-5603-9601-12afc7c1a4da | note | By - SV / PE
0ac7854a-15e5-5cba-9b22-49dac0fe46f5 | checkpoint | 3.01.12 - Maximum Vertical Basecourse With Concrete Channel Variation
9f400d02-0abc-575d-89e3-5fb2c13568e8 | note | Acceptance / Conformance Criteria - At or close to the lip of channel: –5 mm +5 mm
7edc3e38-432a-5212-bd2e-4e130ca9451d | note | • At other locations on pavement: –5 mm +15 mm
9f40236e-36eb-5d19-8d25-fb749f867569 | note | Standard / Specification - TNZ B/02: 2005 - 5.1
345b9fff-2c79-5776-b054-6a1dd2cfd083 | note | Verifying Document - Survey / Level Checks
0b839d2d-84d5-5689-bd62-a0824a516152 | note | Frequency - Before Surfacing
c4b347ed-7baa-5221-8d2b-060dc5d63237 | note | Activity - I
97d823d2-c018-5b8a-bf41-1282fbd78dc6 | note | By - SV / PE
60f50fac-f8d5-5660-82a2-c867c3e1eeb4 | checkpoint | 3.01.13 - Maximum Crossfall Variation
c1456c7e-818a-5613-b496-5b89897b86d4 | note | Acceptance / Conformance Criteria - The crossfall between any two points more than 2m apart, transverse to the centreline, shall not depart from the crossfall shown in the documents by more than 0.5%
55e8fa41-c27c-50de-9324-ff786d76e8b7 | note | Standard / Specification - TNZ B/02: 2005 - 5.1
f806c0d2-7fc3-5d54-bec1-e0d32465d9ad | note | Verifying Document - Survey / Level Checks
8bfcdf84-7a36-5fa6-afdb-636a1c6fc33c | note | Frequency - Before Surfacing
093b1a85-c32a-54be-b35f-d7f348e5c474 | note | Activity - I
7b707584-375b-53e4-a727-65feda861e7d | note | By - SV / PE
5d9724b3-36dc-5598-895e-a900378b0ac2 | checkpoint | 3.01.14 - Benkelman Beam
c300c6a8-6fab-5a5f-9fcf-e2f425fd5602 | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer. Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY
f05ebbea-2284-5e14-b8ad-d144d9d7f232 | note | Standard / Specification - PS - 7.3.2
89b79aa1-2a34-5a86-847c-29f5a9c118cc | note | Verifying Document - Benkelman Beam Report
3136a25d-d966-54a6-ad29-ee210414e27b | note | Frequency - every 10m of each lane – staggered between left and right wheel path.
8c8ff8d9-5578-58d5-902b-2afba13faf8e | note | Activity - R
72b2f681-b3bf-54c8-aa2d-8a5ba212a8bd | note | By - PE
d9a818f0-8e9a-541c-9894-3a3f6a089dea | checkpoint | 3.01.15 - NAASRA roughness
f8f1ddc5-9e43-5599-994c-ccd40e5f9e5c | note | Acceptance / Conformance Criteria - The longitudinal smoothness of the final surfacing layer shall comply with the maximum NAASRA roughness value detailed in the specific contract requirements. (Recommended but not required)
c51d781c-d35c-595b-8151-ff9e2edb37e5 | note | Standard / Specification - TNZ B/02: 2005 - 7.7
cec28093-1825-5a86-9ef8-d2407c923d92 | note | Verifying Document - Test Report
8ed99439-051c-5652-a5c7-0d60785b4150 | note | Frequency - Prior to sealing
ba3640ab-78a1-5000-bcb7-05b7068b785c | note | Activity - R
66d15c5a-6da5-514f-a044-676419733b21 | note | By - PE
2422f5b8-6c41-5a92-8059-73c45dd7ed52 | checkpoint | 3.01.16 - Running Course
2dd4af7e-ff52-5213-8bfe-ffb78279ba4c | note | Acceptance / Conformance Criteria - If running course is used it shall be spread uniformly over the pavement surface and maintained until removed. During working hours traffic shall be channelised by suitably defined traffic lanes with frequent transverse shifts of the defined lanes to obtain an even spread of traffic over the entire surface.
32656b25-5d12-5603-9bf7-3f4ca11f4c9a | note | Standard / Specification - TNZ B/02: 2005 - 10.1
957a4355-2ad9-59a5-8d54-ef85539f0502 | note | Verifying Document - Site Notes
e6842af1-a2d2-551c-a976-8b1ca4f8a932 | note | Frequency - Prior to sealing
ba3d3d9f-1946-5c9f-83e5-f60013e2028e | note | Activity - S
dd5c100d-a6ee-5a14-83e3-df536a28335e | note | By - SUP
8e7858c9-873d-51d1-a21b-ad5d40fe337a | checkpoint | 3.01.17 - Surface Finish post sweeping
0bab8ac7-214c-53a8-b6f3-fc37c1f593c9 | note | Acceptance / Conformance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
ae1a6ffe-f8d6-5746-8b78-8a4c14666516 | note | Standard / Specification - TNZ B/02: 2005 - 7.8
54c3d283-cbd4-5445-86f0-9449a268456a | note | Verifying Document - Photos
c7a00108-4435-5253-a8e6-2b7a1107ea48 | note | Frequency - Prior to sealing
6795d351-a015-5a9b-a9f3-d1b6df24b139 | note | Activity - R
b5f2efb1-7761-506f-a8df-ebce9a6fe815 | note | By - PE
935cb117-67ba-5982-9257-c1cb9a890a02 | checkpoint | 3.01.18 - Tie in into Existing Pavement
652d3e11-4724-5b20-825b-81fe0e512d70 | note | Acceptance / Conformance Criteria - Where tapering of basecourse including finishing layer aggregate is necessary to provide a smooth transition from the new surface to an existing surface, placement of the basecourse or finishing layer shall be stopped at the minimum uncompacted thickness specified in clause 7.3(a).
8edaf6b0-bac1-577a-9644-64b4d379fe85 | note | • The Contractor shall then saw cut the existing seal at the tie-in (end of taper), remove existing pavement material and replace it with approved basecourse to an average uncompacted thickness of greater than 2.5 times the maximum particle size of the basecourse used.
ff9b05df-44a6-56a8-aec5-82f6661bd5c4 | note | Standard / Specification - TNZ B/02: 2005, 7.4
945fe912-55e9-51d9-9669-0838f13fd3a7 | note | Verifying Document - photos, and survey data of undercut
c8cb2a36-5694-5397-a387-a36f12e64e01 | note | Frequency - Every tying into existing pavements
6700a753-2406-51c2-9936-cbb0b6a5cf49 | note | Activity - I
4873d3a8-969d-5215-84b3-dc3aa83e0a53 | note | By - SV / PE
84c3283d-24bd-504e-b593-7adb2a662256 | section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
3b5a624e-1a11-5114-9440-fe27a39734f1 | checkpoint | 4.01.01 - Survey Records
16578cc6-60c3-5d10-ab2c-22be493fed40 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and record.
cc2e27e9-294f-506d-97e6-588dd29da185 | note | Standard / Specification - PS - Page 42
b6d45862-114a-5bc3-b4f0-4bced80526a2 | note | Verifying Document - Records
6f9fbdd1-fd5b-5ad2-8279-779052017a72 | note | Frequency - Post construction
436b177d-ca8b-580d-b3cb-a1d836493bf9 | note | Activity - H
eae26cd8-4a3e-55e4-afc2-5f2d4c4615ae | note | By - SV
e8ea0340-b993-5d44-af71-763ab2d18509 | checkpoint | 4.01.02 - Redline Drawings
f591d672-58aa-5bc1-9243-68db3142cc57 | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
a0aabbe2-3844-551f-ae99-547260b93abd | note | Standard / Specification - Downer
daf5470d-fa25-5f04-9bee-954081867981 | note | Verifying Document - Redlines
44073ab8-caed-5176-8830-2c7f60e5d0a6 | note | Frequency - Post construction
9ae52ebc-4f6b-5ea3-8e2d-e1f8c91fdbc6 | note | Activity - H
b01e3621-33e9-5e48-aa2c-1582be2e6727 | note | By - PE
ada40b11-d492-516e-ad4f-84dc3dad7622 | checklist | SYS - ITP - Pavement & Surfacing - Kerb - Rev C |  | ITP - Pavement & Surfacing - Kerb - Rev C
cdc14ca8-f130-5a81-8492-a1c271a003a1 | section | SECTION 1– PRELIMINARY - KERBING
8453d9d0-a56c-5a53-a197-8b2f7f5761bd | checkpoint | 1.01 - Survey Set out
7d955466-29de-5316-9cfa-6c42ea873290 | note | Acceptance / Conformance Criteria - As per design, the surveyor to install lift pegs
97b6a2ab-3b99-59f3-9237-51a91370b802 | note | Standard / Specification - PS - 2.2.12
26c38dfb-9763-53d5-b10c-409bef813166 | note | Verifying Document - As per design
4d3edfad-dd12-5daf-a5a1-d1bc12648f78 | note | Frequency - As required for Kerb construction
3826f264-8d56-5387-b812-a1268fcd05e7 | note | Activity - A
16ed9906-4cce-57a0-82c8-faa1220be6e5 | note | By - SV
ec6b68b6-398a-5362-9431-48ddad7f9a83 | checkpoint | 1.02 - Kerb construction Set out
7348ea96-65f5-52e4-927c-1588f047e9f4 | note | Acceptance / Conformance Criteria - Ensure that steel pins and string line are in accordance with design levels and entranceways and kerb transitions have been marked. Tolerance +/- 5mm (basecourse level tolerance at channel edge)
9adb5bc4-eace-5244-a0fe-0a5e2bc7736a | note | Standard / Specification - RITS - Page 201
e2521931-9bbb-5066-8e60-a7482a2fc932 | note | Verifying Document - Visual inspection and measurement
a516095d-e0e6-5907-8bd3-1ba4d085c40c | note | Frequency - Prior to slip forming
dc8af7b1-bae9-5b97-903e-dc56e1da1340 | note | Activity - I
b1aa47bb-a769-516e-8eaf-3faecb7c4708 | note | By - SE
0b888b88-3be9-589e-9033-069487cddb43 | checkpoint | 1.03 - Approved kerb and Channel profiles
8c78ac23-1bb6-51fc-afb5-2f1a9c74b6b5 | note | Acceptance / Conformance Criteria - As per drawing no. 146000-002A-1901
18fcfc32-240f-5474-adc9-80409f710992 | note | Standard / Specification - As per drawing
464ca852-6c7f-522f-8227-540c92e95b91 | note | Verifying Document - As per drawing
0949db91-0086-5b5d-ab2d-a8f6802232df | note | Frequency - Prior to construction
3515316a-d3d8-5a40-882d-b135bce1d1ee | note | Activity - I
b69c62b9-f656-5e4a-a6c7-a27855f15ba1 | note | By - SE
033b3647-f5f1-5bf7-baf7-399d874f5df5 | section | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING
27c72069-19ec-52ce-adee-b19aed2e4830 | checkpoint | 2.01 - Approve mix design from Certified batch Plant
e9ef93c1-b0c1-5fd7-9d24-64764cef673b | note | Acceptance / Conformance Criteria - Material meets project requirements - 20Mpa Kerbing Mix
5a0ef905-ea0d-5046-bcce-41ec7bcddaff | note | Standard / Specification - Refer to RITS - 3.4.5.2 / 3.4.5.6
ef13bb40-cf14-58bf-bbb8-a682222869bf | note | Verifying Document - INSERT APPROVED MIX CODE
55cbc80b-03cd-5e9c-8a5d-801836757880 | note | Frequency - Prior to construction commencing
83948472-7d3f-5c90-8b83-f23ecd63605d | note | Activity - C
2465b951-f961-5f00-a62a-e1a9ced4f074 | note | By - SE
719e57fd-6345-5aac-a1f3-c909a0dc1dcc | section | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING
774acca9-538d-5356-ab81-dbc0ca40defb | checkpoint | 3.01 - Survey Set out Confirmation
97b3a708-4ec3-5ea4-964c-3f03734ab723 | note | Acceptance / Conformance Criteria - Ensure kerb preparation is to design level.
923bc9bc-8d0e-535f-8ab2-f2d5c9e2bec6 | note | Standard / Specification - As per design
16f6083f-6ca4-5c31-988f-54abfaca1e06 | note | Verifying Document - Survey Records
792c7781-ea5f-555d-aebe-33c0d2cdf6e8 | note | Frequency - Every steel pin
1009bd04-9c5d-5563-9afe-afb34af2ca8d | note | Activity - I
8b77a263-a130-583b-a57d-6898303d9bff | note | By - SE
308f08a1-4d4a-51d9-a1e5-2b2612caf3b4 | checkpoint | 3.02 - Clegg Hammer Test
3e6f909a-0839-5771-b87d-7ce49744648f | note | Acceptance / Conformance Criteria - Only if kerb and channel is constructed separate to the road, the base that the kerb and channel is founded on - Clegg Hammer must be tested every 15m at 25 CIV (where applicable)
fb0bfa8f-da6d-54cb-a3cb-70013c6fdcbc | note | Standard / Specification - Refer to RITS - 3.8.2.10
2ef0d09c-ce74-5972-bd92-777b04b6e82b | note | Verifying Document - Test Records
4ec4f351-5c24-5ba7-8c69-1ece04a4c8bf | note | Frequency - Every 15m prior to slip forming
be6223ce-c3d6-59d0-a02d-464d8ffbb2dc | note | Activity - C
d025571d-7664-5551-b043-b5225791faf4 | note | By - SE
9e60e85d-45af-5685-b945-345381fb2de6 | checkpoint | 3.03 - Pre-pour inspection
45af77d9-6b82-5f2f-a0de-f716e11e7cb1 | note | Acceptance / Conformance Criteria - As per RITS specification 3.4.5.3, BBO Engineer approval to proceed. / reo-inspection with 24 hours’ notice prior to pouring
f03b22cb-36fc-5e0d-9952-4a8e452058fb | note | Standard / Specification - Refer to RITS - 3.4.5.3 PS - 2.2.16
be021b70-d6ba-5cf3-93ba-158dc14da3ca | note | Verifying Document - Visual inspection / Photos
bf852721-07f3-534b-8942-39cc933eba36 | note | Frequency - Prior slip forming
21a22d89-90da-54d7-b43c-0dadef67a690 | note | Activity - HP
8001cba0-7ef9-5746-9d63-52760940e199 | note | By - ENG
aa095e2d-cd18-55cd-b312-cc90f265b12f | signoff | AUTHORITY HOLDPOINT
dea8f8d1-2346-595d-9723-c588db945421 | checkpoint | 3.04 - Concrete Cylinders/Slump
ddb9f5a2-1b90-5712-9e78-932c193136ba | note | Acceptance / Conformance Criteria - Minimum 20MPa strength, 1@7-days and 3@28-days
f8ebdf82-eed3-5dde-a8dd-6f55c7ce0d94 | note | Standard / Specification - RITS requirement (Drawing D3.3.3, Note 1)
5da12b5e-1aed-553b-903a-b2fb4fe361ea | note | Verifying Document - IANZ Test Records
d7d20e1a-f544-582c-9f56-08e2a8eae494 | note | Frequency - Each pour day
1ed0ab54-0805-545d-9def-36e384b5e2ba | note | Activity - I
d6de34f8-b1bd-533c-8817-8055611e107c | note | By - SE
dba6abea-e77c-54a1-b48e-7480193017da | checkpoint | 3.05 - Curing Of Concrete
2d7e457a-1623-518d-9b8b-a99d89e0a4d1 | note | Acceptance / Conformance Criteria - Curing period shall not be less than 36 hours
b3ff426b-615e-5670-8c03-c611187b5513 | note | Standard / Specification - Refer to RITS - 3.4.5.5 / 3.4.5.9
90535db4-5f9b-5af8-b3fd-b755221f2044 | note | Verifying Document - Visual inspection
75f8cc93-2962-5300-b563-0f9e23f9fee8 | note | Frequency - Throughout the activity
69ea095c-57d5-5861-a60c-8c201100e1e2 | note | Activity - I
398ec7d8-bfa2-56ec-a231-3e0b6ae49899 | note | By - SE
1f0c2293-e94e-57ec-bf45-41f99084e0f0 | checkpoint | 3.06 - Post-pour level check
cb1f1576-ba0f-5896-bed6-e6e7e8b0115b | note | Acceptance / Conformance Criteria - As per drawings
39811371-720c-5a52-8bfc-b16b362c0efe | note | Standard / Specification - PS - 2.2.12
28bc6470-95ac-59d5-833f-033cb02967a4 | note | Verifying Document - Total station topo and check prior to carrying on with further pavement layers
1f2a57e0-d01e-5bb3-abd5-3245436761c5 | note | Frequency - Every survey peg
ee1fe224-ff61-51df-b342-f316a7f93d55 | note | Activity - I
1c5b9fe2-4120-5d6e-a238-36aefb19ccde | note | By - SV/SE
692fdb81-91c4-5d69-bf2d-1ac0c49c007a | checkpoint | 3.07 - Contraction/Expansion Joints
ac9db46b-4000-5c9a-80ee-f2ac39bb4a78 | note | Acceptance / Conformance Criteria - Contraction/Expansion joints shall be formed or cut along the kerb at a maximum spacing of 3.0m.
5a4c419d-4412-5b68-90ec-12aacb6786c7 | note | Standard / Specification - Refer to RITS - 3.4.5.8
bec91869-f51b-524a-9605-bd5f610022dc | note | Verifying Document - Visual inspection
0492c58f-995b-5fc7-b03b-1a99b0dc1fdb | note | Frequency - Every 3m.
ca5bb3a1-1e2a-5278-beca-5bb81b49f4f2 | note | Activity - I
be0b39af-554b-5a1f-b5d2-8b6597f4d8b8 | note | By - SE
d439609d-e2d9-59c7-9a4b-c7012e656f55 | checkpoint | 3.08 - Concrete Mix Dockets
c9399c42-c5a4-5deb-81c7-357117b23aff | note | Acceptance / Conformance Criteria - Matches approved mix code
13d4a077-ec71-502a-a1b6-21162c175b8a | note | Standard / Specification - As per approved mix
5bf57c96-5735-5dde-b4a4-c6d7f111b5d4 | note | Verifying Document - Dockets
b6326348-0f0d-5545-9428-805af4e2b492 | note | Frequency - Every truck load
1c065f24-baba-5f32-8ac5-e99b9f1fc80b | note | Activity - R
273e9cba-6eca-542d-bd1d-cba2738f7296 | note | By - SE
135542d8-784f-5c4d-8a96-ae6d725ae438 | section | SECTION 4 – POST CONSTRUCTION – KERBING
dc3fbf65-7210-5b9c-8d1e-64e4bd132529 | checkpoint | 4.01 - Post pour inspection
0f047b9f-8ee3-5bed-bca6-d64c1e72f853 | note | Acceptance / Conformance Criteria - Acceptance and sign off by the client Engineer.
83e48047-0b11-5148-b984-ddbddbd42a89 | note | Standard / Specification - Surface finish and levels acceptable
65bb29c0-80b3-5be3-af8d-d2bac7629509 | note | Verifying Document - Review of total station topo
7f87d946-d5b3-5d3f-ae15-7bbc4d7301c6 | note | Frequency - When work is complete
bdae422c-284e-5c67-b1f0-ebc7fa266e5d | note | Activity - I
169369f3-d955-5506-be6d-13c132ead951 | note | By - ENG
804eb43b-8914-57f5-88ed-27ac22d9ca25 | checkpoint | 4.02 - Redline Drawings
8b1b8286-6eed-5797-a9a9-39828abdaf1b | note | Acceptance / Conformance Criteria - Electronic points file to be provided
0d50a8b1-6c63-596e-9ab1-a03435d3780f | note | Standard / Specification - PS - 2.2.17
e5705a29-9315-5b47-bd59-c92ee73bb244 | note | Verifying Document - Total station asbuilts
96c33f0b-bf83-5f1c-b914-125971f39f41 | note | Frequency - When work is complete
b93fa637-87ea-53b9-8322-c0f6c07828c0 | note | Activity - A
bf15c63c-7bb5-5654-9fd9-d3b4d797c932 | note | By - SV
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
56d609bc-a0cf-56ec-a47b-15763950ffa1 | checklist | SYS - ITP - Pavement & Surfacing - Kerb - Rev C - v1 |  | ITP - Pavement & Surfacing - Kerb - Rev C
cdc14ca8-f130-5a81-8492-a1c271a003a1 | section | SECTION 1– PRELIMINARY - KERBING
8453d9d0-a56c-5a53-a197-8b2f7f5761bd | checkpoint | 1.01 - Survey Set out
7d955466-29de-5316-9cfa-6c42ea873290 | note | Acceptance / Conformance Criteria - As per design, the surveyor to install lift pegs
97b6a2ab-3b99-59f3-9237-51a91370b802 | note | Standard / Specification - PS - 2.2.12
26c38dfb-9763-53d5-b10c-409bef813166 | note | Verifying Document - As per design
4d3edfad-dd12-5daf-a5a1-d1bc12648f78 | note | Frequency - As required for Kerb construction
3826f264-8d56-5387-b812-a1268fcd05e7 | note | Activity - A
16ed9906-4cce-57a0-82c8-faa1220be6e5 | note | By - SV
ec6b68b6-398a-5362-9431-48ddad7f9a83 | checkpoint | 1.02 - Kerb construction Set out
7348ea96-65f5-52e4-927c-1588f047e9f4 | note | Acceptance / Conformance Criteria - Ensure that steel pins and string line are in accordance with design levels and entranceways and kerb transitions have been marked. Tolerance +/- 5mm (basecourse level tolerance at channel edge)
9adb5bc4-eace-5244-a0fe-0a5e2bc7736a | note | Standard / Specification - RITS - Page 201
e2521931-9bbb-5066-8e60-a7482a2fc932 | note | Verifying Document - Visual inspection and measurement
a516095d-e0e6-5907-8bd3-1ba4d085c40c | note | Frequency - Prior to slip forming
dc8af7b1-bae9-5b97-903e-dc56e1da1340 | note | Activity - I
b1aa47bb-a769-516e-8eaf-3faecb7c4708 | note | By - SE
0b888b88-3be9-589e-9033-069487cddb43 | checkpoint | 1.03 - Approved kerb and Channel profiles
8c78ac23-1bb6-51fc-afb5-2f1a9c74b6b5 | note | Acceptance / Conformance Criteria - As per drawing no. 146000-002A-1901
18fcfc32-240f-5474-adc9-80409f710992 | note | Standard / Specification - As per drawing
464ca852-6c7f-522f-8227-540c92e95b91 | note | Verifying Document - As per drawing
0949db91-0086-5b5d-ab2d-a8f6802232df | note | Frequency - Prior to construction
3515316a-d3d8-5a40-882d-b135bce1d1ee | note | Activity - I
b69c62b9-f656-5e4a-a6c7-a27855f15ba1 | note | By - SE
033b3647-f5f1-5bf7-baf7-399d874f5df5 | section | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING
27c72069-19ec-52ce-adee-b19aed2e4830 | checkpoint | 2.01 - Approve mix design from Certified batch Plant
e9ef93c1-b0c1-5fd7-9d24-64764cef673b | note | Acceptance / Conformance Criteria - Material meets project requirements - 20Mpa Kerbing Mix
5a0ef905-ea0d-5046-bcce-41ec7bcddaff | note | Standard / Specification - Refer to RITS - 3.4.5.2 / 3.4.5.6
ef13bb40-cf14-58bf-bbb8-a682222869bf | note | Verifying Document - INSERT APPROVED MIX CODE
55cbc80b-03cd-5e9c-8a5d-801836757880 | note | Frequency - Prior to construction commencing
83948472-7d3f-5c90-8b83-f23ecd63605d | note | Activity - C
2465b951-f961-5f00-a62a-e1a9ced4f074 | note | By - SE
719e57fd-6345-5aac-a1f3-c909a0dc1dcc | section | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING
774acca9-538d-5356-ab81-dbc0ca40defb | checkpoint | 3.01 - Survey Set out Confirmation
97b3a708-4ec3-5ea4-964c-3f03734ab723 | note | Acceptance / Conformance Criteria - Ensure kerb preparation is to design level.
923bc9bc-8d0e-535f-8ab2-f2d5c9e2bec6 | note | Standard / Specification - As per design
16f6083f-6ca4-5c31-988f-54abfaca1e06 | note | Verifying Document - Survey Records
792c7781-ea5f-555d-aebe-33c0d2cdf6e8 | note | Frequency - Every steel pin
1009bd04-9c5d-5563-9afe-afb34af2ca8d | note | Activity - I
8b77a263-a130-583b-a57d-6898303d9bff | note | By - SE
308f08a1-4d4a-51d9-a1e5-2b2612caf3b4 | checkpoint | 3.02 - Clegg Hammer Test
3e6f909a-0839-5771-b87d-7ce49744648f | note | Acceptance / Conformance Criteria - Only if kerb and channel is constructed separate to the road, the base that the kerb and channel is founded on - Clegg Hammer must be tested every 15m at 25 CIV (where applicable)
fb0bfa8f-da6d-54cb-a3cb-70013c6fdcbc | note | Standard / Specification - Refer to RITS - 3.8.2.10
2ef0d09c-ce74-5972-bd92-777b04b6e82b | note | Verifying Document - Test Records
4ec4f351-5c24-5ba7-8c69-1ece04a4c8bf | note | Frequency - Every 15m prior to slip forming
be6223ce-c3d6-59d0-a02d-464d8ffbb2dc | note | Activity - C
d025571d-7664-5551-b043-b5225791faf4 | note | By - SE
9e60e85d-45af-5685-b945-345381fb2de6 | checkpoint | 3.03 - Pre-pour inspection
45af77d9-6b82-5f2f-a0de-f716e11e7cb1 | note | Acceptance / Conformance Criteria - As per RITS specification 3.4.5.3, BBO Engineer approval to proceed. / reo-inspection with 24 hours’ notice prior to pouring
f03b22cb-36fc-5e0d-9952-4a8e452058fb | note | Standard / Specification - Refer to RITS - 3.4.5.3 PS - 2.2.16
be021b70-d6ba-5cf3-93ba-158dc14da3ca | note | Verifying Document - Visual inspection / Photos
bf852721-07f3-534b-8942-39cc933eba36 | note | Frequency - Prior slip forming
21a22d89-90da-54d7-b43c-0dadef67a690 | note | Activity - HP
8001cba0-7ef9-5746-9d63-52760940e199 | note | By - ENG
aa095e2d-cd18-55cd-b312-cc90f265b12f | signoff | AUTHORITY HOLDPOINT
dea8f8d1-2346-595d-9723-c588db945421 | checkpoint | 3.04 - Concrete Cylinders/Slump
ddb9f5a2-1b90-5712-9e78-932c193136ba | note | Acceptance / Conformance Criteria - Minimum 20MPa strength, 1@7-days and 3@28-days
f8ebdf82-eed3-5dde-a8dd-6f55c7ce0d94 | note | Standard / Specification - RITS requirement (Drawing D3.3.3, Note 1)
5da12b5e-1aed-553b-903a-b2fb4fe361ea | note | Verifying Document - IANZ Test Records
d7d20e1a-f544-582c-9f56-08e2a8eae494 | note | Frequency - Each pour day
1ed0ab54-0805-545d-9def-36e384b5e2ba | note | Activity - I
d6de34f8-b1bd-533c-8817-8055611e107c | note | By - SE
dba6abea-e77c-54a1-b48e-7480193017da | checkpoint | 3.05 - Curing Of Concrete
2d7e457a-1623-518d-9b8b-a99d89e0a4d1 | note | Acceptance / Conformance Criteria - Curing period shall not be less than 36 hours
b3ff426b-615e-5670-8c03-c611187b5513 | note | Standard / Specification - Refer to RITS - 3.4.5.5 / 3.4.5.9
90535db4-5f9b-5af8-b3fd-b755221f2044 | note | Verifying Document - Visual inspection
75f8cc93-2962-5300-b563-0f9e23f9fee8 | note | Frequency - Throughout the activity
69ea095c-57d5-5861-a60c-8c201100e1e2 | note | Activity - I
398ec7d8-bfa2-56ec-a231-3e0b6ae49899 | note | By - SE
1f0c2293-e94e-57ec-bf45-41f99084e0f0 | checkpoint | 3.06 - Post-pour level check
cb1f1576-ba0f-5896-bed6-e6e7e8b0115b | note | Acceptance / Conformance Criteria - As per drawings
39811371-720c-5a52-8bfc-b16b362c0efe | note | Standard / Specification - PS - 2.2.12
28bc6470-95ac-59d5-833f-033cb02967a4 | note | Verifying Document - Total station topo and check prior to carrying on with further pavement layers
1f2a57e0-d01e-5bb3-abd5-3245436761c5 | note | Frequency - Every survey peg
ee1fe224-ff61-51df-b342-f316a7f93d55 | note | Activity - I
1c5b9fe2-4120-5d6e-a238-36aefb19ccde | note | By - SV/SE
692fdb81-91c4-5d69-bf2d-1ac0c49c007a | checkpoint | 3.07 - Contraction/Expansion Joints
ac9db46b-4000-5c9a-80ee-f2ac39bb4a78 | note | Acceptance / Conformance Criteria - Contraction/Expansion joints shall be formed or cut along the kerb at a maximum spacing of 3.0m.
5a4c419d-4412-5b68-90ec-12aacb6786c7 | note | Standard / Specification - Refer to RITS - 3.4.5.8
bec91869-f51b-524a-9605-bd5f610022dc | note | Verifying Document - Visual inspection
0492c58f-995b-5fc7-b03b-1a99b0dc1fdb | note | Frequency - Every 3m.
ca5bb3a1-1e2a-5278-beca-5bb81b49f4f2 | note | Activity - I
be0b39af-554b-5a1f-b5d2-8b6597f4d8b8 | note | By - SE
d439609d-e2d9-59c7-9a4b-c7012e656f55 | checkpoint | 3.08 - Concrete Mix Dockets
c9399c42-c5a4-5deb-81c7-357117b23aff | note | Acceptance / Conformance Criteria - Matches approved mix code
13d4a077-ec71-502a-a1b6-21162c175b8a | note | Standard / Specification - As per approved mix
5bf57c96-5735-5dde-b4a4-c6d7f111b5d4 | note | Verifying Document - Dockets
b6326348-0f0d-5545-9428-805af4e2b492 | note | Frequency - Every truck load
1c065f24-baba-5f32-8ac5-e99b9f1fc80b | note | Activity - R
273e9cba-6eca-542d-bd1d-cba2738f7296 | note | By - SE
135542d8-784f-5c4d-8a96-ae6d725ae438 | section | SECTION 4 – POST CONSTRUCTION – KERBING
dc3fbf65-7210-5b9c-8d1e-64e4bd132529 | checkpoint | 4.01 - Post pour inspection
0f047b9f-8ee3-5bed-bca6-d64c1e72f853 | note | Acceptance / Conformance Criteria - Acceptance and sign off by the client Engineer.
83e48047-0b11-5148-b984-ddbddbd42a89 | note | Standard / Specification - Surface finish and levels acceptable
65bb29c0-80b3-5be3-af8d-d2bac7629509 | note | Verifying Document - Review of total station topo
7f87d946-d5b3-5d3f-ae15-7bbc4d7301c6 | note | Frequency - When work is complete
bdae422c-284e-5c67-b1f0-ebc7fa266e5d | note | Activity - I
169369f3-d955-5506-be6d-13c132ead951 | note | By - ENG
804eb43b-8914-57f5-88ed-27ac22d9ca25 | checkpoint | 4.02 - Redline Drawings
8b1b8286-6eed-5797-a9a9-39828abdaf1b | note | Acceptance / Conformance Criteria - Electronic points file to be provided
0d50a8b1-6c63-596e-9ab1-a03435d3780f | note | Standard / Specification - PS - 2.2.17
e5705a29-9315-5b47-bd59-c92ee73bb244 | note | Verifying Document - Total station asbuilts
96c33f0b-bf83-5f1c-b914-125971f39f41 | note | Frequency - When work is complete
b93fa637-87ea-53b9-8322-c0f6c07828c0 | note | Activity - A
bf15c63c-7bb5-5654-9fd9-d3b4d797c932 | note | By - SV
4771253d-9012-5cc5-aeb2-5b6d51e403ba | checklist | SYS - ITP - Pavement & Surfacing - Sealing - Rev 1 | itp | ITP - Pavement & Surfacing - Sealing - Rev 1
8b5943c0-4539-550c-8dad-5350406ef755 | section | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
adfc0f61-f139-5650-a9a6-bf02e023e388 | checkpoint | 16.08.01 - Sealing Chip - Source Property Tests and Sampling
f72cc165-27da-5cd3-a2a3-8738244d63b5 | note | Acceptance / Conformance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV
423c1f2c-1b85-59ee-8837-db3ca86913c7 | note | Standard / Specification - TNZ M/6: 2019 - 4, PS - 7.2.8
1e6e13d0-5040-53d8-a28e-9351742ac8da | note | Verifying Document - IANZ Lab Reports
b5fef9e4-b133-5ca3-aebb-24d6529f7588 | note | Frequency - 10,000m3
0702d244-1f93-5b2d-8150-2e02e09d0069 | note | Activity - HP
656e0c67-8bf9-5da6-a7f0-979ef2070a8f | note | By - ENG
91706b27-4b16-5cc3-af8c-8bc6d225db80 | signoff | AUTHORITY HOLDPOINT
aa95eb07-07b0-5907-8ee6-62cec7a8e155 | checkpoint | 16.08.02 - Sealing Chip - Production Property Test Sampling
59d0648b-965c-593d-8c54-ee1f33d05fdf | note | Acceptance / Conformance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6
0778486d-802b-5642-b787-54b28b889813 | note | Standard / Specification - TNZ M/6: 2019 - 5, PS - 7.2.8
71a87208-8ff3-548d-b433-5608c6ddf464 | note | Verifying Document - IANZ Lab Reports
7224cf73-2afe-5bed-822b-111c2b0a2550 | note | Frequency - 500m3
66a555cc-52d6-5318-9e0e-990e309fedc7 | note | Activity - HP
c9c0dd8c-5162-5885-93bc-dfc24d77576e | note | By - ENG
b8564601-7c3b-5437-9cd0-864739bac510 | signoff | AUTHORITY HOLDPOINT
63bb7db5-2824-50b2-a76c-2d37e5833c76 | checkpoint | 16.08.03 - Bitumen
a4923ef6-0f75-58cb-87e4-5fab4ca68408 | note | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01-A specification.
9407e156-6df1-5d9d-b127-2eea90e91ff0 | note | Standard / Specification - NZTA M10:2020 - 2.3.1, NZTA M01-A, PS - 7.2.8
54c4067b-6883-5adb-9b44-8a1a385fb181 | note | Verifying Document - IANZ Lab Reports
94a8dcbe-885f-567a-8ca3-44642a550665 | note | Frequency - Prior to use
2b3e5074-080a-5dd8-8c22-8959c9398141 | note | Activity - H
6de56487-3a96-5453-bffc-225d597963ff | note | By - PE
0cfb900b-774e-522d-8382-11f45ee6c95c | checkpoint | 16.08.04 - Sprayer E-2 certification
c1ed1d90-0a52-5602-b37e-1d951a9dedb8 | note | Acceptance / Conformance Criteria - E-2 certification and is up to date
750c4b85-0fdc-555e-9f7c-71e36e534785 | note | Standard / Specification - BCA E/2 Specification
8deada11-0ecf-5e45-8b19-e048947f9d87 | note | Verifying Document - Certificate
66742a5f-1fe3-5787-b935-c3b3e56445d7 | note | Frequency - Prior to use
d2acc12a-3ccd-5ded-91be-d3335f36ff2a | note | Activity - C
e315cf47-680d-58f6-a2a8-6ccd76b1ee3d | note | By - PE
b88cbcdc-0ec4-5cd6-adad-045aa1042702 | checkpoint | 16.08.05 - Sealing Design
9c9a2b3a-3972-5a7d-8895-4e4ec59e36cd | note | Acceptance / Conformance Criteria - Chip seal type, chip source, bitumen and/or emulsion grade, % kerosene, AGO and diluents, polymer (if applicable), sand report reports, hot application rate(s) including spray rates
85646657-8972-5bc1-a519-126ae5edaaba | note | Standard / Specification - PS 7.3.4.
17074ecd-fecd-57f9-92a3-b9081866afc3 | note | Verifying Document - Design Document
08a63143-714b-548f-927f-4814682e7088 | note | Frequency - Prior to use
c651762d-d5d2-5bda-8cb5-b9edd01dc852 | note | Activity - HP
66421952-0624-562d-af31-bae357bd0170 | note | By - ENG
ffa400a2-8ccb-5b46-8866-fcdb01e56bc0 | signoff | AUTHORITY HOLDPOINT
17d9b8eb-c728-5b6c-89b8-b5fe39466667 | checkpoint | 16.08.06 - Bitumen approval
ef41b259-4f32-5713-aaf4-8c949aa03238 | note | Acceptance / Conformance Criteria - Applications for approval shall contain the information required by NZTA Q05 clause 4 and the testing information required by Table 5.1
b9cb265a-75c9-5f3e-a319-bc00a27e782d | note | Standard / Specification - table 5.1 of NZTA M1:2022
8a9787cf-c73f-5593-b9e7-8034e115c3c4 | note | Verifying Document - Report
3494da08-2937-55d7-be14-8cb442e30733 | note | Frequency - Prior to use
1ace09e4-9546-575a-86ac-9231abcff70f | note | Activity - C
8adbad93-1366-5fbf-9710-0a3b9e97c223 | note | By - PE
f7b3c20d-9dec-50ad-9de5-6ba1c8224201 | checkpoint | 16.08.07 - Bitumen Quality
61d2add7-8f3f-529f-a4c6-2c9bdeeab619 | note | Acceptance / Conformance Criteria - All bitumens used for road pavements construction, supplied or blended by New Zealand-based bitumen blending facilities shall meet all the requirements of Table 6.1 or M01-A specification for the grade supplied.
3f47ea2d-af01-517a-b556-fa1a953cb7f2 | note | Standard / Specification - table 6.1 of NZTA M1:2022
3fa8115b-491d-5715-9759-01bb6995f189 | note | Verifying Document - Report
ae50f405-62a6-56c2-9693-183b399ada46 | note | Frequency - at least one test per grade supplied following delivery of a shipment into a bulk blending facility.
09b80dd6-dd9f-5329-a000-96a30cec77c1 | note | Activity - C
02ad4278-edce-5860-939c-4aa811a1de72 | note | By - PE
ae7c919c-800b-54bb-8ce4-d650657fb70e | section | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
2871bb8b-9370-54cd-81be-076ea005324e | checkpoint | 28.07.01 - Sealing Procedure
dba6e33f-1c8b-5569-9fda-1cd45f031f5a | note | Acceptance / Conformance Criteria - Sealing shall be carried out in accordance with TNZ or NZTA Specifications M/1, M/6, M/13, P/3, and Q/1.
a4a4f0c9-6e21-5f44-b95d-433b8ef1d6b7 | note | Standard / Specification - M/1, M/6, M/13, P/3, and Q/1.
5fc5d2df-ff01-5bd2-9ffb-10b00f3635f5 | note | Verifying Document - Methodology / Construction Pack
ed9de7e0-e62a-5439-b8a5-e510536d69f3 | note | Frequency - Prior to sealing
9f8e4f9f-c752-51d7-8bdb-f6a4a9129f2d | note | Activity - H
272e3268-25e7-5506-8897-5d0b5eb0b69e | note | By - PE
987da8d6-869a-52f8-82a6-64d9d019be20 | checkpoint | 28.07.02 - Sealing Inspection
e13f8aab-ed03-55f5-8e78-f98b839e92bf | note | Acceptance / Conformance Criteria - Before sealing and resealing. A pre-seal walkover with the Engineer to ensure that the surface is swept clean of loose aggregate, dust, dirt and other deleterious matter and the sweepings shall be removed to the satisfaction of the Engineer.
281850fc-cf15-536b-9f5f-324fb470bcf2 | note | Standard / Specification - PS - 2.2.16
0f39351b-d7e3-58fa-b711-5f9a347a6ac9 | note | Verifying Document - Hold Point Release
112d7768-c8f8-57bb-ad76-f1cf1b734677 | note | Frequency - Min 48h Notice
f44c5759-933f-5e05-a26f-09374ba9092f | note | Activity - HP
157cd6f5-9fae-5594-9f70-b18acffa1e96 | note | By - ENG
e8de70ad-25a8-50ee-a86e-ee732888188d | signoff | AUTHORITY HOLDPOINT
97f74a51-90b2-591d-9d46-97b788789ecc | checkpoint | 28.07.03 - Presealing Requirements
6bfc3f46-9301-5932-903b-18a175248417 | note | Acceptance / Conformance Criteria - Further to Clause 12 of NZTA B2, the degree of saturation of the basecourse prior to sealing shall be less than 60%.
e43ae18f-91be-5454-a63a-b509872abb85 | note | Standard / Specification - PS - 7.3.4
481fc55c-a247-558a-abe5-eef34f4994ac | note | Verifying Document - NDM Report
7e15df9c-a8d2-5ecc-adfc-72c8a3ed2d1b | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
2a6f4a94-045d-5ea9-8ab1-787a40b218e3 | note | Activity - HP
cc0fc382-4bdc-54b7-acb7-8d673f72ea57 | note | By - ENG
147512ba-bbe7-59c7-b55f-f9d4c0992a25 | signoff | AUTHORITY HOLDPOINT
600fb3f6-6266-58ed-9a50-762110113d0f | checkpoint | 28.07.04 - Adhesion Agents
714e7f71-3f88-5c80-b683-ebba7a9bc233 | note | Acceptance / Conformance Criteria - An adhesion agent approved and blended in accordance with the requirements of TNZ M/13 Specification for Adhesion Agents shall be incorporated in the sealing binder.
9fcef9d2-abf5-544d-966d-7797e5229986 | note | Standard / Specification - TNZ M13
5a1c992a-9d0e-54bb-b63c-2f47a5134230 | note | Verifying Document - Site Notes
9a6c9667-0e13-5c8f-bf79-8ba0f02bbb4f | note | Frequency - Prior to sealing
957e939a-0437-509b-9cd1-d721bd205a3a | note | Activity - R
9c44be23-e462-51a2-a526-12d7653abe12 | note | By - SE
7be6ce73-a318-5599-8798-e17614ccf289 | checkpoint | 28.07.05 - Post Seal Inspections
4de718da-c59f-5c40-8b3e-057ea10e2816 | note | Acceptance / Conformance Criteria - The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed.
0f87b092-2b0d-5b7e-a8a5-64a8d21119e3 | note | Standard / Specification - TNZ P3
0dce8072-911c-516a-9a63-42116abbb3b3 | note | Verifying Document - Engineers Acceptance
b8cb5257-62e6-54ed-bd7e-097972155e2d | note | Frequency - Prior to TM removal and after final sweeping
c39f97eb-0abf-51ec-84e4-bd67e0b31185 | note | Activity - HP
30538ae5-fdf0-507d-84f3-4cb464919235 | note | By - ENG
15d3cd20-59ee-55bf-8a8f-397ca3be1d64 | signoff | AUTHORITY HOLDPOINT
04954196-eee5-5f02-b55f-cc4acc6713ca | checkpoint | 28.07.06 - Bedding in Chip
73313444-c073-515b-88db-5885511e9ac4 | note | Acceptance / Conformance Criteria - If no traffic on site to bed in Chipseal, 3 days of constant rolling with PTR's and laden HCV's will be applied to bed in the Chipseal.
f4f59b8c-77bb-5856-a645-e4801f47a3e2 | note | Standard / Specification - PS - 7.3.4
11d7b076-b24b-566a-9534-0d19043973b9 | note | Verifying Document - Site Notes
f72333df-bde2-5b2d-aeeb-28a6b881847b | note | Frequency - Post Sealing
81931cdd-bf2c-5546-b7ee-38044ba55f72 | note | Activity - R
4ddec918-3ba6-5820-8ba0-fddba1a45d6f | note | By - SE
82dadf7e-bf2d-5092-b40b-132dd3b2a700 | checkpoint | 28.07.07 - Surplus Chip Removal
ef706484-67aa-5993-8ad5-a5d28c1bc76c | note | Acceptance / Conformance Criteria - If no traffic on site, removal of surplus chip will occur 2-3 days after rolling has been completed. If traffic on site, sweeping and removal of chip will be within 48hrs.
2d0127d6-6d7d-5ab8-b035-c9fb11052ce8 | note | Standard / Specification - TNZ P3
0019d5cd-a080-599a-bf39-6dbee283253c | note | Verifying Document - Site notes
2e4999ee-a3e4-5d3a-80ba-71327225d785 | note | Frequency - 24 hours of completion of any section of seal.
7c70c37b-7cdb-5548-8118-d8554ac64740 | note | Activity - R
777fa846-33d2-508b-b217-ca42693a2721 | note | By - SE
387048ba-8198-5c54-a002-cb9830e7474f | checkpoint | 28.07.08 - Chipseal Repairs
01937e39-1bfb-59ba-95cf-cfd96da7518d | note | Acceptance / Conformance Criteria - The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used
42158fc7-a86e-52a8-9201-74679aeb85d9 | note | Standard / Specification - TNZ P3
0bf8e279-9ac8-50a4-a204-62abf8cf26b6 | note | Verifying Document - Approved repair Methodology
ee3b471d-6939-5602-9644-fd38c86c7090 | note | Frequency - Prior to repairs
c0d25fdd-a140-5c55-b79c-71845879df7e | note | Activity - HP
0eda0423-5ccc-58ca-9b86-55421513367d | note | By - ENG
6eec2a1c-2298-5d1c-bfaa-7f4d2470f385 | signoff | AUTHORITY HOLDPOINT
5a5a3ab7-b98b-515e-8829-c6b77dcde4a6 | checkpoint | 28.07.09 - Weather
2b32c452-707f-5c90-8adf-e5750f1e15d6 | note | Acceptance / Conformance Criteria - Ensure that weather is suitable prior to spraying & pavement temperature checked. Pavement surface temperature ≥ 10C.
8859ee9a-271b-54c7-9124-9a3ab5113dfa | note | Standard / Specification - Requested by BBO
c9d1dee2-1f09-54e4-9743-1ace0a24604f | note | Verifying Document - Site Notes
6195f572-a5aa-5e68-b3d2-b075afb7b1af | note | Frequency - Prior to sealing
c0d4ec4c-7ad4-5001-8a51-1a76af47a494 | note | Activity - C
ff877007-8fb3-5893-a34e-f93cbf8806f1 | note | By - PE
c52674b3-5735-530c-a4c6-a6fbb45598fc | checkpoint | 28.07.10 - Protect Road Furniture
33905c35-66dc-5422-bca0-d10eba9003dd | note | Acceptance / Conformance Criteria - Paper cover any concrete that could get sprayed by bitumen such as kerbs and barriers
813f33b5-0cc5-54d5-bae0-6d8c6db63a43 | note | Standard / Specification - NZTA (2005) Chip sealing in New Zealand – 11.2.5.
1ae76e23-a4e2-5798-9c4e-a7d3daab8da7 | note | Verifying Document - Site Notes
02b452e3-3c94-547a-925b-3721bb9b11d9 | note | Frequency - Prior to sealing
ae6f69cf-c324-5cca-980e-1cc39acec6a2 | note | Activity - C
38846de8-a4de-51fc-8ce9-b2da71097d02 | note | By - PE
efc43278-19a3-56ee-b7ee-7febad520026 | checkpoint | 28.07.11 - Joins, Overlaps & Hand Spraying
5b9230a4-10bd-582c-bdd1-7427ce9045f6 | note | Acceptance / Conformance Criteria - Set up Spray Plan ensuring joins, overlaps and hand spraying is kept to a minimum; joins are not in wheel paths and overlaps are appropriate for curves, channels, straights
ef6da712-6974-5b5f-9560-3774b85e7112 | note | Standard / Specification - NZTA (2005) Chip sealing in New Zealand – Section 11
ac3922fc-604e-5bf5-a54c-858085c3c2f0 | note | Verifying Document - Site Notes
380f76ed-c2ca-5f93-8d62-d09c60583e4a | note | Frequency - Prior to sealing
3cd1d841-702e-556f-8455-3c4a6a081375 | note | Activity - C
a6f72d9f-ead0-5257-bb80-bd4acd5db742 | note | By - PE
e4115331-b361-565b-8e30-16b24b56d977 | checkpoint | 28.07.12 - Binder Temperature
0369770c-20bf-5e77-9cbc-4c9b666ce9af | note | Acceptance / Conformance Criteria - Temp. appropriate to base binder and additives +/- 10 degrees. Daily records
dd4e915f-62e4-5296-9b92-4a7572e088ae | note | Standard / Specification - NZTA (2005) Chip sealing in New Zealand – Section 11
f9948422-218b-57c0-a169-db3d459da9f7 | note | Verifying Document - Site Notes
e2481c47-962d-5dd4-a274-5239383c5218 | note | Frequency - Prior to sealing
e514c9ce-b115-5273-afd5-6ccc70480e1b | note | Activity - C
9d75c0b4-1a1b-5a7c-ae77-8edd53c6ae5e | note | By - PE
9dd523a7-748d-5edb-8e82-5cb13e3876a4 | checkpoint | 28.07.13 - Binder Application Rates
16b8e348-6a57-51aa-9757-4e828599a2c8 | note | Acceptance / Conformance Criteria - Confirm spray rate is correct by comparing actual spray rate to that calculated. Note error in measurement increases as area reduces. Within 0.1l/m² from target on spray run.
8fe8f093-73ea-5fc8-bb93-56349251e1e6 | note | Standard / Specification - Requested by BBO
68c9a18f-0b99-505a-a999-e43d898af2e0 | note | Verifying Document - Site Notes
a2d0ac60-2a79-540d-b9d4-cf395a3e735b | note | Frequency - Daily
89d74fa4-a686-5c5f-b459-13ce3afb2eae | note | Activity - C
f18395c8-2757-5cd9-ad6b-67b6412136dc | note | By - PE
4c005acc-c507-5b7f-88f6-0f990950d26f | checkpoint | 28.07.14 - Chip Application Rate
cebefc05-edac-519a-a52d-ba7f6e15b3c1 | note | Acceptance / Conformance Criteria - Monitor chip spread rate and compared to target, record volume of chip used
134a9b0d-32ef-515d-b97f-4f8762d20b07 | note | Standard / Specification - NZTA (2005) Chip sealing in New Zealand – Section 11.3.7
60861daf-849e-59b6-8747-c19ed36c06b1 | note | Verifying Document - Site Notes
0784a178-482e-5ee7-ba3c-8a3d13346758 | note | Frequency - Daily
1d6ed067-6108-5e8e-87de-b6d4278e8d60 | note | Activity - C
39a55291-edb7-56fb-8bea-114c65df0b67 | note | By - PE
1d0c86fa-55c8-59a6-b2c2-78f4eef40d45 | checklist | SYS - ITP - Pavement & Surfacing - Subbase - Rev E - v1 | itp | ITP - Pavement & Surfacing - Subbase - Rev E
3969119e-9d77-5427-b958-ecc82f083c46 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
ec4e551b-3f47-528c-ae6c-fdfb3458be34 | note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence
eb1c5ab0-d958-5aff-9e01-8f56d5db5c3c | note | Standard / Specification - Downer
95e813a5-8719-5ac9-9ed3-db95c88daa4f | note | Verifying Document - Construction Pack
805d2c95-dc1c-508e-8b9e-fbca9c1eeaf6 | note | Frequency - Prior to Works start
fc39fb4d-ffff-5e1f-8d56-399758b18a65 | note | Activity - H
802be262-7e7e-53e8-b8bf-6038d6e34751 | note | By - PE
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
27f3be6b-b818-5263-817f-5ba924480d35 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
1f441f83-2c34-577a-90e0-73818924a2cf | note | Standard / Specification - Downer
a4fa1ba9-6110-5364-ab83-c9684041414a | note | Verifying Document - Survey Records
7fe5d102-a89b-537b-849f-5cc7bf99618c | note | Frequency - Prior to Works start
d378e4fb-1992-5af0-8e29-ab8e511f0e7e | note | Activity - H
ed48a75e-9faa-5783-b481-e3f0f2090547 | note | By - SV
a24a2c58-bf6f-5474-883c-40044bad1fc7 | checkpoint | 3.01.03 - Service Location
07cf3e6e-2226-5ee4-b1f5-8fff7d3c89fe | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
e5694d8a-f45f-52e8-b573-2ce535af9e31 | note | Standard / Specification - Downer
b2970209-fe08-5050-ba93-b0537bd69e94 | note | Verifying Document - Excavation Permit
e872e4d7-566c-548c-8e05-f649772197fa | note | Frequency - Prior to Excavation
0ef56c5b-7c85-56e8-9a7e-aab9f6807218 | note | Activity - H
53f0bb53-59d4-5d30-9a93-b3b481462cec | note | By - SE
0a214a7a-124a-5898-a837-e29e83751df0 | checkpoint | 3.01.04 - Internal Permits
8f9ece01-d727-5876-8560-edbd9d82bcf8 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. if applicable.
a7ee36d2-9b73-5f58-b71b-db5ca41fe4a2 | note | Standard / Specification - Downer
85ad478e-6552-52d0-b8b4-54e1f7ffbc8d | note | Verifying Document - Internal Permits
93d4943e-f796-520a-9124-ecb481319afe | note | Frequency - Prior to activity being undertaken
ea702c86-97c6-5605-ba1e-bfeeb7f387ec | note | Activity - H
a2718418-fc15-5b59-89c6-07251b3f0c0b | note | By - SE
917e2881-0901-542f-ae25-686bf9c47009 | checkpoint | 3.01.05 - External Permits
f23abc2d-c8ee-50ea-854a-9f64a7d9d86a | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc, if applicable.
6b62d5fe-af97-5ca3-b301-bd92f2791dc8 | note | Standard / Specification - Downer
a02559dc-175e-589a-9b8a-8eab68d69cad | note | Verifying Document - External Permits
b2f5d673-8cc4-5dbc-8d75-deccfbe742fe | note | Frequency - Prior to commencment of activity
d3a90524-e3a6-5f9e-b9d3-b83ba77aa7bf | note | Activity - H
13bc7be9-6edd-55c9-a267-e302e9aee166 | note | By - PE
a1302970-0389-558d-b43c-67b14bbfc27a | checkpoint | 3.01.06 - Approved Construction Drawings
f56d4abb-1946-538b-aad6-86aea7955913 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
09117102-46e6-57a9-9743-cdcaf0e4e481 | note | Standard / Specification - Downer
46964b83-84c6-5336-b6bd-922be5cef306 | note | Verifying Document - IFC Drawings
39dfba69-75f7-5742-968e-a4c90dbb0b22 | note | Frequency - Prior to works start
68e4c5de-58e0-5dec-91c6-170e024e015a | note | Activity - H
3d527e69-1c47-5f3d-8273-fc7878a3c156 | note | By - PE
4dd36031-ce9c-52f9-bfbc-d1541a841138 | checkpoint | 3.01.07 - Stabilising Methodology
f31947ca-c372-52b1-9187-bb4248d3254b | note | Acceptance / Conformance Criteria - Written approval of the Engineer with the approval of the methodology
a161a67c-8a7a-5dd1-9557-f02e91f6b027 | note | Standard / Specification - PS - 7.3.3
07fd60c0-fd43-5cf7-befe-31b3417972ce | note | Verifying Document - Correspondence
5f17963d-05de-50a8-9578-9003dcf71a00 | note | Frequency - Prior to stabilisation start
4c607593-a8eb-5c32-8ec8-95b0db6dee42 | note | Activity - HP
b8772278-c47a-56b1-a98c-0284beffbb55 | note | By - ENG
bcc75d59-fda9-5665-870d-6406349e1ed2 | signoff | AUTHORITY HOLDPOINT
9ffb2cc0-a1b6-5e07-aa7c-34ea633a63b0 | checkpoint | 3.01.08 - Acceptance of the SIL layer
f6339289-345f-5f4c-9a10-88376f46e5fd | note | Acceptance / Conformance Criteria - Written approval of the Engineer - All compliant test results for subgrade, SIL, all road crossings, storm water, wastewater, watermain, subsoil/pavement drains and any other activity that has been completed in the pavement area.
02730cba-a67f-5416-abdc-90b5998957c6 | note | Standard / Specification - PS - 4.8.3, Table 4.3
847b87f3-2330-5a62-abcc-ad8b65920f34 | note | Verifying Document - Hold point relesed / Testing reports
683e6528-9871-5c86-b102-a59b4f362661 | note | Frequency - All sections before proceeding to the next layer
c2f09181-52a5-56b6-a1b5-1c437cb54f45 | note | Activity - HP
ad1d82fa-b960-58f5-b406-029832fbcf42 | note | By - ENG
d3949fe3-b334-5e1c-a2b3-f23ab054269d | signoff | AUTHORITY HOLDPOINT
bc43c978-69d8-5f48-8b7f-ecbcce31a7dc | section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65
ca87e1fb-7246-51ad-9189-73e2340ccb26 | checkpoint | 6.02.01 - Sub-base MDD and OMC
f168b349-b948-59e0-834f-0b2ba45e5df5 | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
94791044-7035-5d70-836b-5bd471f60add | note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
72003631-2a30-59ed-9ccd-8bb41b9e6939 | note | Verifying Document - IANZ Lab Reports
a294e292-acfa-5d4d-8bb2-ac429ec82d86 | note | Frequency - No less than 1 test every 5,000m³ (in place)
f3890077-fa2d-5c9d-ac37-159c3531b5d4 | note | Activity - R
a55f805a-3e05-57ce-9887-0771a0f2e46b | note | By - PE
70fabdf0-7745-50be-96bf-2ded7dc55eed | checkpoint | 6.02.02 - Plasticity Index
1a02b294-b8c7-54a8-88ad-4b2eadf677b4 | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Liquid Limit shall be ≤ 25 when tested
de15fba3-2af3-5447-92e4-0ff93b28081b | note | Standard / Specification - Table 7.2
c8b38c01-7756-58f6-b0f0-b99d29d920dc | note | Verifying Document - IANZ Lab Reports
bfa862fa-eabc-5114-9532-f6da19c44f1a | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
bb7cea44-7b13-513c-8a99-abf001a2a74e | note | Activity - R
eadf6b0e-0f1f-54ef-b126-27840805effb | note | By - PE
22886128-c2cb-5f11-b511-007c412fa0ae | checkpoint | 6.02.03 - Clay Index
d48bd89a-2cde-500f-a65a-9c0ead3920c3 | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Plasticity Index shall be ≤ 8 when tested
24123e95-13ac-553f-becd-8e344e653d5b | note | Standard / Specification - Table 7.2
5041442d-2667-52e6-a388-347fcd1cc8bc | note | Verifying Document - IANZ Lab Reports
864c5f20-dd61-50e0-9e7c-7c6a82ee48d0 | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
2c66b3e5-64c2-50ca-add7-1f48a636da59 | note | Activity - R
84b352e3-3712-5479-adda-d025a9ad206a | note | By - PE
39fe01b4-f08b-5b33-9943-aadecfa5826a | checkpoint | 6.02.04 - Sand Equivalent
ee50526c-e9ec-5c79-91e8-670f2c1bb39e | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Clay Index shall be ≤ 5 when tested
c3d6c15e-6c07-5af7-84c6-1527766f8f9a | note | Standard / Specification - Table 7.2
8181ba8f-30d8-5506-b06d-a29546a00eb8 | note | Verifying Document - IANZ Lab Reports
7f791590-653e-5bbc-b299-61b3e8ad6c10 | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
d7befb75-e056-5ad0-9068-054f15d42590 | note | Activity - R
068d12a9-5531-5e68-ad78-ad8c0ed428d7 | note | By - PE
4aff0413-9e3c-530c-b97a-0793ec692f9c | checkpoint | 6.02.05 - Particle size distribution
1a8c69dd-c0e2-5b47-94bb-913d372659c7 | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1
ceeab263-cfbd-5a84-ae44-c53ca329d997 | note | Standard / Specification - Table 7.1
7ea3aa39-7de2-5b9f-a333-ab9d10071ce9 | note | Verifying Document - IANZ Lab Reports
836f527e-24cd-55ae-8a9c-b4fcff7cf69f | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
4df9e8bd-bbda-58ac-aec9-614f3c35ec32 | note | Activity - R
519ac218-21ef-581c-bc55-b73daef7619a | note | By - PE
e8905abc-1647-5fbc-9fa2-b0958848732e | checkpoint | 6.02.06 - Average Uncompacted Layer Thickness
6b32e036-d252-594f-8ce0-3eb80aff0240 | note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
648b2fed-46ce-540e-9f51-a18bfb12ba86 | note | Standard / Specification - TNZ B/02: 2005 - 7.3
a42810de-1507-53dc-be0f-446a8c7d0ee8 | note | Verifying Document - Survey / Level Checks
a0f4bd8f-6e11-51e8-bc6d-c882447e2666 | note | Frequency - 1 test per 20m
67978ffa-b835-59d4-9b56-3c8a6dad8a32 | note | Activity - I
72a4512d-e758-58f5-9856-07e0d6ca6500 | note | By - SV / PE
50dc97be-5c04-59c3-8703-cd318c3ee35e | checkpoint | 6.02.07 - Plateau Density Test
bc29dd99-a71a-51dc-8d02-33bf0f61312d | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
a31f8a84-a71e-59ae-80d8-12cc4a5710e9 | note | • Testing shall be at OWC.
a79e6939-4ab3-5aa1-a23e-dc5097a70f43 | note | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
4db60e69-808f-52cd-b326-970523d0b24a | note | Standard / Specification - PS - Table 7.2 - 2.3
d156f274-aee5-52c1-bb6b-8c7211c6a105 | note | Verifying Document - Plateau Density Report
22cb08a8-dbdb-5f03-aa42-cd222fd52a80 | note | Frequency - 5 tests per 10,000m2
0da96e90-93be-5ae0-8294-d4d6764a24d9 | note | Activity - I
bd2aacaa-57e0-578e-ab16-49fcbb5e5588 | note | By - PE
3ee4467b-b164-5546-a4a6-7cc3c4ecf208 | checkpoint | 6.02.08 - Sub-basecourse Pavement Layer Compaction
a565c723-69ac-5886-b35c-2693ff3155e2 | note | Acceptance / Conformance Criteria - Mean Value ≥ 95 Minimum Value ≥ 92
3051c527-6171-5f07-a895-8e8d848accaf | note | Standard / Specification - TNZ B/02: 2005
fbf04794-d375-5824-a102-a8516cf4f602 | note | Verifying Document - NDM Report
001719f7-47b0-537b-8df8-97351cfd4bb3 | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
4b955460-5c4e-5883-ab40-c8250043fc8c | note | Activity - I
6329ddc7-ac2c-5ed4-9026-9cdc6dfcb567 | note | By - PE
b152466a-921e-56d5-9032-1b468cc0597c | checkpoint | 6.02.09 - Surface shape control
f6d19746-988e-53c0-bd07-7cf2bbecfe30 | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
4a673db2-094e-5953-9808-6c7c3a311467 | note | • Vertical: - 25mm +5mm
3bda55bc-9b4e-5f0b-8a0e-8913bca49280 | note | • Cross fall: 0.5% on 2m straight edge
f0699e7d-4488-5930-bc24-e6bde8144145 | note | Standard / Specification - TNZ B/2
1b64c389-5f95-5892-ab77-39b0c10f8109 | note | Verifying Document - Total station Topo showing levels compared to design
2c19adde-02f1-5f99-b87f-abae30ebd503 | note | Frequency - Continuous
d69e2e2d-e889-5d9e-9ec6-25206323c908 | note | Activity - I
e95c8e22-5607-581f-acaf-8299ff2bd117 | note | By - SV / PE
7c9c928b-9d6d-55e2-9057-4eae9a377090 | section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial
6c098115-ed50-5770-83bf-79ab8107d3a0 | checkpoint | 6.03.01 - Stabilization Production Plan
c9ddb8f7-8811-5c24-a98e-4a7b7bde9d00 | note | Acceptance / Conformance Criteria - Production plan sent to engineer for review 48 hours prior to stabilising commencing. This is to include all information set out in NZTA B/6 7.2.3.
da0f5c1e-3efd-569f-b2ef-0d62230cc56f | note | Standard / Specification - NZTA B/6 7.2.3
503a87ad-53dc-5338-b7d6-41d39018bdad | note | Verifying Document - Correspondence
4b686472-ead5-5dca-9e19-e1a7af89afd6 | note | Frequency - 48H hours prior sabilising commencing
cb4be3d2-1fc8-5f91-99ab-ff9da052c5f2 | note | Activity - HP
abad576a-df96-543f-9ab1-765a1ff468b2 | note | By - ENG
efaac3d4-313c-53da-9b8a-af70649a58b8 | signoff | AUTHORITY HOLDPOINT
33bc697f-3ee0-5632-94ad-1cc6ea4d8aff | checkpoint | 6.03.02 - Longitudinal Joints
f2cfb2e7-40b5-5204-868e-224c0ffe7c5f | note | Acceptance / Conformance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by a minimum of 200 mm or half the layer thickness, whichever is the greater.
7b7caba1-a9c4-5c5d-a3af-5fea17a64691 | note | Standard / Specification - NZTA B/6 7.5.2
1ac5d31f-9758-50ae-9f72-48d864679110 | note | Verifying Document - Stabilisation Prodution Plan
9af7f4d5-44b2-586a-b84d-14083db10bdc | note | Frequency - 48H hours prior sabilising commencing
703a7061-48ec-50a2-bf67-28fd4c8b61f9 | note | Activity - H
3ecbad6b-6769-52d3-8371-9bae9e3e68bc | note | By - PE
f2fd84d9-a211-565e-a0e0-957d8630417c | checkpoint | 6.03.03 - Stabilisation trial
aaf3fcc6-69cf-5107-bdd2-324afb462409 | note | Acceptance / Conformance Criteria - A trial shall be conducted on a minimum stabilised area of 2,000m2 to verify the performance of the stabilising operation and finished product prior to full scale production.
32d89166-cc92-5257-8a02-b42deb788bcf | note | Standard / Specification - PS - 7.3.3
fc6cde74-b4bb-53b0-8942-0552487547d2 | note | Verifying Document - Triall Report
835b815b-b849-51c9-8abc-91b75b5897e4 | note | Frequency - prior to full scale production
10b65111-54b2-5545-b5b5-be46c4838f88 | note | Activity - HP
c72f6072-5eca-5743-b96b-117fc11d2cf9 | note | By - ENG
836a28a7-55e3-5ddb-91a4-e7dccd925e7a | signoff | AUTHORITY HOLDPOINT
c77ae1a3-eb3d-5fdd-85c2-176a01d6eedf | checkpoint | 6.03.04 - Stabilising Equipment
b85e3249-9895-5172-a001-1466f4265669 | note | Acceptance / Conformance Criteria - The Contractor shall use stabilising plant purpose built and appropriately adjusted for the in-situ stabilisation of roading aggregates, as opposed to plant designed for soil stabilisation or re-cycling.
1ee3589b-5081-5efc-bdad-6aba26d6e9a5 | note | • The stabiliser drum shall have a straight tooth pattern and the drum speed must be adjustable in real time during stabilisation.
a3776b5d-7d91-53eb-bb08-1af17fb325a2 | note | Standard / Specification - PS - 7.3.2
3b65390a-1386-58dd-8d6a-5e763cde91a7 | note | Verifying Document - Plant Approval
88a73c18-536b-5f46-bb46-d7b80e90b423 | note | Frequency - Prior to works
83e5610e-6576-5395-a4fa-7274e96a60c7 | note | Activity - H
64cc6353-220e-5907-bfcd-449c0bc979dc | note | By - PE
65357786-cd6f-5367-a375-639ab3f50f85 | checkpoint | 6.03.05 - Stabilising Supervisor
4892293b-c97e-5f7b-8af6-863f1c449d64 | note | Acceptance / Conformance Criteria - During stabilisation the Contractor shall employ a suitably experienced person to continuously walk behind the stabiliser to assess the uniformity of the mixture and water distribution and to check the stabilisation depth every 100m.
b82eadfd-0943-56e1-8a03-094e7c34f50c | note | Standard / Specification - PS - 7.3.2
3551a47b-12a0-5a1a-8ea5-7b63cff98b4c | note | Verifying Document - Supervisor Approval
8251bbf9-5e57-58ad-aee4-43bbe9f37c78 | note | Frequency - Prior to works
a4146f77-cb32-5f0c-9c04-6338cd5be9c9 | note | Activity - H
21f6550a-d45f-508e-b98b-d3e37a65df52 | note | By - PE
b2e16153-370f-553c-9fbe-4d6c94095131 | checkpoint | 6.03.06 - Before Stabilisation Surface shape control, layer thickness
04e2ce5c-fc23-51ac-b996-8b395cb81ee1 | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
c79417a1-d3da-5554-8196-a20418d2f028 | note | • Vertical: - 25mm +5mm
be91c280-43e7-5a2f-b532-dea6df56a8d0 | note | • Cross fall: 0.5% on 2m straight edge
7ce457fc-836f-5cc6-a269-ba8371d1833a | note | Standard / Specification - TNZ B/2
84a096bf-3ee3-5f72-a1d9-f550bc29364f | note | Verifying Document - Total station Topo showing levels compared to design
038c979c-acff-5c79-bdf8-95a17d456d70 | note | Frequency - 1 test per 20m
25a6b6d3-0568-511b-98c0-be8b869b3e71 | note | Activity - I
80588976-67d6-54ca-9d40-618b6fdcc383 | note | By - SV / PE
61811b90-1233-52f7-81cc-b19f731dbfcd | checkpoint | 6.03.07 - Average Uncompacted Layer Thickness
57abe783-f1ed-53d3-84cc-34e27300e213 | note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
f3e06d3b-2107-5ca4-ab1d-8e980c44d108 | note | Standard / Specification - TNZ B/02: 2005 - 7.3
b91bd336-8e5c-532c-ad9d-fea08ac6590e | note | Verifying Document - Survey / Level Checks
46a082e0-947d-55f6-9700-208f12e701e9 | note | Frequency - 1 test per 20m
b0e66bd0-e4af-5d26-8d47-bf34fe7b8ca6 | note | Activity - I
7b9507c3-415a-57b6-ad99-2fa7d63f6ca9 | note | By - SV / PE
0f3c4886-911f-570e-9380-945bb931b659 | checkpoint | 6.03.08 - Pre Stabilisation Compaction
2de608fd-6034-5977-8b48-ace7c120a2de | note | Acceptance / Conformance Criteria - The full thickness of the layer to be modified shall be compacted between Value ≥ 95% and Minimum Value ≥ 90% Prior to stabilisation, this will be reviewed following the stabilising trial and adjusted to suit and the updated target shall be added after the stabilising trail. DN1205-DOW-RFI-0043.01
c076cd42-6e8e-5b46-a0df-e078704d7870 | note | Standard / Specification - PS - 7.3.2
f288a3ff-d1e2-5f20-920c-7fa4a3abc914 | note | Verifying Document - IANZ NDMS
f0c423cb-1eba-5011-80ac-05005e695439 | note | Frequency - Min 5 Tests per lot 1000m2 max lot size (Prior to stabilisation)
35184592-ddea-5789-9628-76295e981225 | note | Activity - I
5948452b-0aae-5278-993c-de000a64b387 | note | By - PE
03cc060f-e525-5da1-b4a4-927a2c816637 | checkpoint | 6.03.09 - Pre Stabilisation Crossfall
7dcc80a1-3999-5c00-bfc3-bf293b8a8647 | note | Acceptance / Conformance Criteria - Before stabilisation the Contractor shall check the crossfall by string line to confirm compliance with the design.
cf25e97d-2159-5462-a6ce-4196b9d4293a | note | Standard / Specification - PS - 7.3.2
3b2b548d-399e-519d-9d69-9a2927c0b6b1 | note | Verifying Document - Total station Topo showing levels compared to design
5303e7de-4445-5c0f-9266-790d456b0644 | note | Frequency - 1 test per 20m Prior to stabilisation
de272e7d-a2c4-580c-9190-796fa51c3638 | note | Activity - I
ca2a2111-0158-5182-be1b-445174fedcb3 | note | By - SV / PE
dd46457d-0574-5b56-b7ac-f21afadaed60 | checkpoint | 6.03.10 - Stabilising Visual appearance
8f8865c0-7ffc-5b16-807d-503d621cbc5a | note | Acceptance / Conformance Criteria - The stabiliser shall produce a uniform particle size distribution behind the stabiliser, both laterally, vertically and longitudinally and produce minimal break down of the coarse aggregate particles during mixing.
cf749d9a-5bf1-50bf-a203-7e3c464d3673 | note | Standard / Specification - PS - 7.3.2
aa34d7ad-4e05-5677-b27c-5f6f1411f00b | note | Verifying Document - Site Notes
69f6c763-0a03-51d9-bfa5-534ccacaf6ef | note | Frequency - every 100m
d91ec8a3-6ce2-52e2-80f0-1b03438f13ee | note | Activity - I
87e701c1-161f-5285-9b2e-cd20ebb3e36d | note | By - PE
6eed5d81-e5b0-55cf-bece-401f93ecd9b8 | checkpoint | 6.03.11 - Cement Mat Test / Spread Rate
da3f72b4-b1e3-5657-808e-2bc54fe47d04 | note | Acceptance / Conformance Criteria - The stabilising agent shall be uniformly spread at the specified application rate across the pavement to Within ±0.5 kg/m2 of the specified rate
24f9b6df-5b16-5895-9f6b-b49960501d8d | note | Standard / Specification - Table 7.2
94fee484-a5b3-5490-bb40-6bf4b0938f69 | note | Verifying Document - Stab. Sheet
99cdf68f-0152-5f34-b1a5-3760076113bb | note | Frequency - One per each run of cement spreading, until the Contractor can demonstrate consistency in cement spreading and/or demonstrate accuracy of on-board computer equipment calibrated/compared against weighing cement mats.
7ddb2bae-c964-5cf3-8183-009d7060c3bb | note | • Upon successful demonstration of this, the 1 per 500m2 minimum can applya
1cfad76f-afa0-56a5-94e6-cd4c58e6b657 | note | Activity - I
e92ba43f-b2f2-5c8a-9649-ee66f9671721 | note | By - PE
58788175-0c81-55f7-8c9c-122dc5a74310 | checkpoint | 6.03.12 - Cement Average usage test
201f6146-1817-5edb-a22c-c29f7f45f2a0 | note | Acceptance / Conformance Criteria - Compare tonnes used (from delivery docket) with measured area Within ±2.5 % of the specified rate
f17dd1db-7f20-5312-b139-97755128b80c | note | Standard / Specification - TNZ B6
749b65f8-ccd4-520b-90d3-1e9fdbd250c1 | note | Verifying Document - Stab. Sheet / Delivery Doc.
6586c6f9-d9c7-524c-beaf-40df78cc4131 | note | Frequency - Upon emptying the spreader and bulk tanker
914cde35-1363-5dfb-920a-556fed6e74b9 | note | Activity - R
658e3f08-7984-52e5-8b16-f6fa47795fdf | note | By - SE
8dd5c234-a389-5dfe-8991-b7486bab77cb | checkpoint | 6.03.13 - Control of cut depth
46b9f88e-99c9-5a60-a968-15cc96292ceb | note | Acceptance / Conformance Criteria - Maximum variation from the specified depth of cut is –5 mm and +15 mm. Without picking up sand from SIL
8f09f694-78a6-5532-93a0-59f7ad96ba2a | note | Standard / Specification - TNZ B6
4afa3e59-c79c-5e6c-b5c5-86d8c9c5c9b0 | note | Verifying Document - Stab. Sheet
2be0fa1c-b437-5b11-a13e-69e22b6f8b08 | note | Frequency - First check of cut depth should be immediately behind the stabiliser at the start of each run, then again every 200m, or as requested by the Engineer
ce80a921-3335-5a15-a8f6-c9b7326838fd | note | Activity - R
5f9d6dc1-3b64-5181-89c5-19a73f488add | note | By - SE
19eac722-f22d-5929-8126-b167f6613939 | checkpoint | 6.03.14 - Plateau Density Test
decd180e-26e7-56c8-a3c1-c00f8720c9e0 | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
c865ae35-c13e-5881-99c9-18bc78a225a6 | note | • Testing shall be at OWC.
f64e7a3a-7098-52be-8784-a85fae85996e | note | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
177e1bb7-f470-50c1-bb79-20e420d6426e | note | Standard / Specification - PS - Table 7.2 - 2.4
f69b2107-9d61-5d1d-afc0-990e1ee682b7 | note | Verifying Document - Plateau Density Report
572e474c-67c5-55ad-aa87-750d7a624c7e | note | Frequency - 5 tests per 10,000m2
1e50156b-7f28-5a92-98ef-c62f718b4864 | note | Activity - I
f832f683-84fa-54d1-b808-402011fa634a | note | By - PE
2ee5ae31-1ce2-5318-b785-95fce0922ca9 | checkpoint | 6.03.15 - Particle size distribution behind stabilizer (Wet Sieve)
9a4fb5ed-bd27-535b-a022-bebf285b6004 | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1. A Wet sieve analysis will be completed within 4 hours after stabilizing
00eb80fa-3200-5417-b532-c46d18a37a6a | note | Standard / Specification - NZS 4407: 1991 Test 3.8.1 Standard Method by Wet Sieving
c1e6242b-b982-5e22-a725-33ef54319773 | note | Verifying Document - IANZ Lab Reports
d2116d61-7adf-57d3-8106-1c51336749a8 | note | Frequency - 3 samples bag per stabilise day post hoe
a2dcec01-55c7-552c-b0b0-ddc1a435ae63 | note | Activity - I
ca9469bb-b5fa-592e-b002-a0f30567b1c6 | note | By - PE
3744d9ba-d8e1-5383-9d2c-5335ed0cf31b | checkpoint | 6.03.16 - Mixed material testing (ITS)
e2b5c14a-af27-5eb6-b955-0adb175e234a | note | Acceptance / Conformance Criteria - During mixing, the contractor shall take a pair of representative samples behind the mixing plant per lot or at a minimum of 2 pairs of representative samples per day.
d688278a-6706-534e-8852-c900e1806fab | note | • These samples shall be placed in a sealed plastic bag and cured for 1 hour before compacting into a mould and testing the indirect tensile strength (ITS) of the mixed material according to NZTA T/19
47d240fd-1755-530d-8cb6-4e1fc7b7bf94 | note | Standard / Specification - TNZ B6 7.5
773ab540-931e-5436-96b7-b637f29e940a | note | Verifying Document - Test Results
b5a4545b-eeba-56b5-ac7c-309e3f13ba69 | note | Frequency - 2 tests per stabilise day
9405b5d3-7923-5d1c-ab1e-7daadd0fb3c8 | note | Activity - R
a81873b5-9bab-5d3c-bab6-8f7d512b6321 | note | By - PE
9b3b1023-6a86-5a49-9ba8-c3eceb03ddce | checkpoint | 6.03.17 - NDM Water correction
c25bbffd-26b9-5cd1-9007-ea0430d5425a | note | Acceptance / Conformance Criteria - Daily Laboratory water content tests shall be carried out on samples taken and used to correct the NDM measured dry density.
7094f35a-7333-5c0e-a9fd-b35dd164b270 | note | • Will get the Moisture correction factor from the Plateau report itself. That is the difference between the Moisture reading on the NDM vs the actual moisture when dried in the oven.
a4a8ac4a-1615-59b8-a711-d27a3ceeb43a | note | Standard / Specification - NZS 4407
d9b5523a-05b2-58fd-9e57-a9303f0304c4 | note | Verifying Document - Corrected NDM Results
9249129b-f15a-54ce-b381-d81ad35dac4b | note | Frequency - Per Stabilise day
245a86d9-a73e-59fa-aa80-37e87cd97e1e | note | Activity - R
8af1dd0a-24d3-5a19-a2b8-7017f0a60f45 | note | By - PE
189483f5-5c2e-5d24-8c0e-4762ac1f0541 | checkpoint | 6.03.18 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
5d68a0f4-4196-5761-9790-d8be3e07e987 | note | Acceptance / Conformance Criteria - The sub-base compaction requirements in Table 2 of B/6 shall be replaced with a Mean Value ≥ 98% and Minimum Value ≥ 95%. - Direct Transmission
71e6b7a8-57ce-5ca8-a855-be653ee16563 | note | Standard / Specification - PS - 7.3.2
c38c893e-c4af-5435-8b10-5cea4af66292 | note | Verifying Document - IANZ Lab Reports
09c7affc-1350-5f10-b8e6-a01c82222f60 | note | Frequency - Min 5 Tests per lot 1000m2, minimum 7 days after stab.
f13edf28-3a07-5e5e-8f90-380006fa79fa | note | Activity - I
766ab5be-df67-5b77-9a8a-613a23d83192 | note | By - PE
4eafc89d-3d95-5e4e-b4f9-e4c39a2227af | checkpoint | 6.03.19 - Post Stabilisation Surface shape control, layer thickness
8b976792-3213-50e1-9b79-b17bfa92e2cd | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
bb1aaf06-ac2a-5c01-b59c-99c125149d3d | note | • Vertical: - 5mm +10mm
826abe9c-7624-52b5-81ae-9dba7f27ccbe | note | • Cross fall: 0.5% on 2m straight edge
c94a6cad-a425-5c8c-b31f-1d39bfc23390 | note | Standard / Specification - TNZ B/2
504e543b-ebf4-5caa-97da-11e2e571a421 | note | Verifying Document - Total station Topo showing levels compared to design
844977c8-ff1d-5b87-8ce8-15c352b20022 | note | Frequency - 1 test per 20m
d1b3ec14-8717-5fd1-aff6-6d207298a937 | note | Activity - I
7badf766-988c-53cd-9bbf-3c397b0a935d | note | By - SV / PE
72280022-fd87-5882-b3d4-4682359acdc4 | checkpoint | 6.03.20 - Protection, Curing and Maintenance before Overlaying
3d71e903-b505-5839-85cf-cc631955ea52 | note | Acceptance / Conformance Criteria - The Contractor shall protect, maintain and cure the completed cement bound sub-base until the next layer is applied. Besides construction traffic required for the above curing no other construction traffic shall be permitted onto the layer within 7 days of stabilisation
2ccf6b0a-db10-5b23-b23c-8b040512c59a | note | Standard / Specification - TNZ B6 - 7.8
a1ab7aa0-62a0-586d-85bb-84e441f89c33 | note | Verifying Document - Site Notes
13fbbedb-5f36-5063-a677-5482008a00f9 | note | Frequency - For 7 days after stabilisation / Photos
aafc97a3-8cfb-53f8-b823-b6d7c5d4fecc | note | Activity - R
54e81eef-18ff-5283-8882-1692dfd66af4 | note | By - PE
80726abb-7f00-5a67-ad5c-4f9961a101e8 | checkpoint | 6.03.21 - Benkelman Beam
86073cf5-cb7d-5788-8fad-6c6c432370b0 | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer.
f46ea1ac-e9f1-5874-9372-f9aea3a5d9c8 | note | • Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY
3efa5857-763b-54d3-8278-799e35daacd2 | note | Standard / Specification - PS - 7.3.2
9e77db51-97a0-5170-bcaa-6857975a2049 | note | Verifying Document - Benkelman Beam Report
265fb537-4cec-53b7-86ff-39b6861b114d | note | Frequency - Every 10m of each lane – staggered between left and right wheel path.
96390e81-b614-50bb-93c7-f3d2b0c95b35 | note | Activity - R
eb2d27cd-0b0d-5dd3-b96e-e4eb2ff8392a | note | By - SE
00ccd532-6cdc-5994-8bfb-114564ace123 | checkpoint | 6.03.22 - MDD / OMC / SD
4f4ed41d-cb8c-59e9-8606-f95b6bac1490 | note | Acceptance / Conformance Criteria - Post hoe, stabilised MDD, OMC, and SD. 1 test per 2000m² or a days work whichever gives the greater number of testing.
8ed938ff-2157-5aa2-ba7c-f6efdb4d2cfc | note | Standard / Specification - NZS 4402:1986, Test 4.1.3
ec991d8f-7516-5322-a5ea-fb77853e2a97 | note | Verifying Document - Lab Report
f69218dc-8c78-51c4-8c14-62b6a43378b7 | note | Frequency - 1 test per 2000m² or a days work whichever gives the greater number of testing.
8330547e-cf6f-5e95-ae6d-e1e3125e40a5 | note | Activity - I
8e65f206-c8d3-53c9-9d6e-4c3adf41f08d | note | By - PE
ba7d06af-c7af-5c9d-8ab4-2e3c21a61daf | checkpoint | 6.03.23 - Sub-base stabilisation trial
33db0125-cfac-51c2-bb13-8f2039ec729c | note | Acceptance / Conformance Criteria - After the sub-base stabilisation trial, prior to proceeding with further stabilisation.
97852424-7570-5606-b7c8-390f1c5314de | note | Standard / Specification - PS - 2.2.16
1b5a9b91-a178-56d2-a4d1-b6f3efed76b6 | note | Verifying Document - Hold Point Release
09d9073d-8a0f-5d5e-afa6-7c41e1c3daed | note | Frequency - Min 48h Notice
f548d775-5ebc-56b3-bf85-04c9216f346a | note | Activity - HP
bf8a7659-4300-5770-8079-4c595911ef49 | note | By - ENG
944ea1fd-b7c9-5949-95b5-51c9f13d6c6b | signoff | AUTHORITY HOLDPOINT
3ed998ef-a740-59b5-a205-c17d1ea4ae1e | section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base
bfa46ea3-f62a-522a-aeaa-762b5defdaf1 | checkpoint | 6.04.01 - Stabilization Production Plan
4bc5963e-cd2c-51c9-aca5-69592b28e7b2 | note | Acceptance / Conformance Criteria - Production plan sent to engineer for review 48 hours prior to stabilising commencing. This is to include all information set out in NZTA B/6 7.2.3.
71cb6c20-295f-57d5-a171-0161932e085a | note | Standard / Specification - NZTA B/6 7.2.3
a63946e0-13fc-5f8f-af3f-dd8702db5ce8 | note | Verifying Document - Correspondence
21058093-260c-502c-9a10-4289560be62c | note | Frequency - 48H hours prior sabilising commencing
e8b8790c-3ca2-5fdb-89d4-45c8244f3825 | note | Activity - HP
3f7f445d-4e23-5bda-9bff-1d2d926e9369 | note | By - ENG
e4ed9518-8669-550c-8d69-a36a5a98261d | signoff | AUTHORITY HOLDPOINT
718a330a-7558-52f6-be9b-f238816a905a | checkpoint | 6.04.02 - Longitudinal Joints
22db6f42-ec9d-5643-90f1-7b79fa348ab3 | note | Acceptance / Conformance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by a minimum of 200 mm or half the layer thickness, whichever is the greater.
719e890d-d568-55b5-84e6-bed77f0f46a3 | note | Standard / Specification - NZTA B/6 7.5.2
78c93c41-abe6-58db-a342-afd7b48c2a61 | note | Verifying Document - Stabilisation Prodution Plan
6c9b5431-1a5a-52bb-9e62-0e81f150c6d6 | note | Frequency - 48H hours prior sabilising commencing
f59876a0-5a1f-53f6-b4bf-cb2e0bcdacd0 | note | Activity - H
1ced5c1f-5106-5c18-8962-145b62d99b22 | note | By - PE
3057a053-0fa8-5141-99e1-8805c8143030 | checkpoint | 6.04.03 - Stabilising Equipment
b8341bd7-673c-5dc2-808a-b5591245a41d | note | Acceptance / Conformance Criteria - The Contractor shall use stabilising plant purpose built and appropriately adjusted for the in-situ stabilisation of roading aggregates, as opposed to plant designed for soil stabilisation or re-cycling.
13969d9f-b85a-5f7a-9aa8-66e1e0edae96 | note | • The stabiliser drum shall have a straight tooth pattern and the drum speed must be adjustable in real time during stabilisation.
2deb8519-49c2-5487-9cf7-444377be1b25 | note | Standard / Specification - PS - 7.3.2
20980237-258c-5659-ade7-2366ac0b8b3f | note | Verifying Document - Plant Approval
5cdb0063-1c4f-5b26-af41-f8037bdb887a | note | Frequency - Prior to works
fd180c27-27ce-546e-80c4-4d43ec441f4b | note | Activity - H
3524338e-2ce4-5f52-b118-b96a05ccca61 | note | By - PE
d10c1293-8308-5402-8f5a-943d59292a90 | checkpoint | 6.04.04 - Stabilising Supervisor
840c29c2-0a8c-5ea5-ba9e-1cbbf8bf56ed | note | Acceptance / Conformance Criteria - During stabilisation the Contractor shall employ a suitably experienced person to continuously walk behind the stabiliser to assess the uniformity of the mixture and water distribution and to check the stabilisation depth every 100m.
459a0a17-3115-50b1-8574-e577b9fa3289 | note | Standard / Specification - PS - 7.3.2
4931d8f6-9541-5ae3-bcab-bf8298c7c272 | note | Verifying Document - Supervisor Approval
527ee89c-1792-57ee-a5a9-287bcfcbc472 | note | Frequency - Prior to works
5f19806f-af48-5c20-b1eb-99d26cdcd076 | note | Activity - H
ed8cc6f7-ff4c-5eed-9210-4c62bf32bba9 | note | By - PE
1c51f95a-b88f-562b-b314-9008bea93499 | checkpoint | 6.04.05 - Before Stabilisation Surface shape control, layer thickness
9d8c8e5e-11ce-58a7-860d-c33d6c7859b2 | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
616c8ede-e9b2-5437-b1f6-ce66bcd2f0e7 | note | • Vertical: - 25mm +5mm
bdb504a7-1ca9-50f7-b822-c9b3a4acf4c6 | note | • Cross fall: 0.5% on 2m straight edge
f92c3ee3-0fce-5b0f-8b35-7932831125a2 | note | Standard / Specification - TNZ B/2
71e702c3-1afe-5980-aab7-e902f1ec27f2 | note | Verifying Document - String sheet
69ce19e3-2200-5312-b708-210d89c586eb | note | Frequency - 1 test per 20m
5f7c86d0-2816-5f16-b69f-5c2bed0014c7 | note | Activity - I
16cf3505-f954-591c-92f1-db3b12cd003e | note | By - SV / PE
0d6f6583-baee-5c8d-8dea-ee479453f289 | checkpoint | 6.04.06 - Average Uncompacted Layer Thickness
9570be19-0fe8-57ce-bcb1-ef4816b0e78c | note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
3aa0923e-f1c9-58dc-a8ae-da58cae7c067 | note | Standard / Specification - TNZ B/02: 2005 - 7.3
876ae953-7cdc-56d4-b12f-0969f34eb79e | note | Verifying Document - Survey / Level Checks
7eb6d98c-375e-576e-ac51-7e0c32aeb52e | note | Frequency - 1 test per 20m
1364f684-6351-556e-8189-03544cf0bdf0 | note | Activity - I
15f9afb4-4f6e-561c-9b64-85ec16932a31 | note | By - SV / PE
917f88ba-1bf1-5687-b499-860c1cb7ca16 | checkpoint | 6.04.07 - Pre Stabilisation Compaction
395eae28-4c8d-59bc-bd7b-7283b16b67bb | note | Acceptance / Conformance Criteria - The full thickness of the layer to be modified shall be compacted between Value ≥ 95% and Minimum Value ≥ 90% Prior to stabilisation, this will be reviewed following the stabilising trial and adjusted to suit and the updated target shall be added after the stabilising trail. DN1205-DOW-RFI-0043.01
614970bc-9f95-51d2-85d7-240c03166f66 | note | Standard / Specification - TNZ B/02: 2005
03cd9565-736a-5c41-b2bb-2c62bef5a03a | note | Verifying Document - IANZ NDMS
7d062746-9063-552a-8600-70c701e6de9c | note | Frequency - Min 5 Tests per lot 1000m2 max lot size (Prior to stabilisation)
819a1ad6-5e53-520b-ad5f-c702560be83c | note | Activity - I
ec31e201-c41b-5fc2-9b67-fefc9467feff | note | By - PE
609cd901-d33f-51ea-8bf0-2ac755e5ea9a | checkpoint | 6.04.08 - Pre Stabilisation Crossfall
9e8fe53f-a4f1-5780-8ccb-6c86d9016322 | note | Acceptance / Conformance Criteria - Before stabilisation the Contractor shall check the crossfall by string line to confirm compliance with the design.
71360f74-312e-57d7-bb04-30fff5aea2e0 | note | Standard / Specification - PS - 7.3.2
de23d183-7039-5637-980c-457a089db70b | note | Verifying Document - Total station Topo showing levels compared to design
60c78e68-7cc6-5c38-8fa6-1f1e015f1735 | note | Frequency - 1 test per 20m Prior to stabilisation
fc9d3184-55ac-5435-a416-d61089d7c36f | note | Activity - I
a514a1b0-5d8e-57ef-b0a0-53b72199740d | note | By - SV / PE
c5459efa-5597-5eb0-a767-a817864c6611 | checkpoint | 6.04.09 - Stabilising Visual appearance
5271a85c-4033-5182-87d5-e949d8805412 | note | Acceptance / Conformance Criteria - The stabiliser shall produce a uniform particle size distribution behind the stabiliser, both laterally, vertically and longitudinally and produce minimal break down of the coarse aggregate particles during mixing.
7099c8a2-8d24-5440-a12e-deca0db77cbc | note | Standard / Specification - PS - 7.3.2
ea995418-cd6c-5018-87a7-dbda26d9543b | note | Verifying Document - Site Notes
51ab3f3a-0703-53a4-909f-ab0246c7ba52 | note | Frequency - every 100m
bbb26c31-a3d5-5e57-9c1f-0918ac1187c8 | note | Activity - I
26a05264-4d7b-5c54-8b74-ae3956ac22bd | note | By - PE
7fa669a4-d877-59f3-a991-2960916f29d5 | checkpoint | 6.04.10 - Cement Mat Test
46c51070-6f39-5c90-b926-7f40ec685408 | note | Acceptance / Conformance Criteria - The stabilising agent shall be uniformly spread at the specified application rate across the pavement to Within ±0.5 kg/m2 of the specified rate
f4280e81-30e6-5494-bf91-f3f1fd2bf034 | note | Standard / Specification - TNZ B6
e50e070d-6787-5c4a-9684-171f12480f21 | note | Verifying Document - Site Notes
797abd0c-2fe3-51b1-a8c0-306322b0abdb | note | Frequency - One per each run of cement spreading, until the Contractor can demonstrate consistency in cement spreading and/or demonstrate accuracy of on-board computer equipment calibrated/compared against weighing cement mats.
6377a24c-c013-5ceb-a8f8-7b0711433e34 | note | • Upon successful demonstration of this, the 1 per 500m2 minimum can apply
991cd70b-faf9-5183-8e93-ca3425890e1e | note | Activity - R
e201a738-c914-5bbe-ada2-7f7d94fe58ed | note | By - SE
0fabe193-9a41-532d-98d6-aa037b156014 | checkpoint | 6.04.11 - Cement Average usage test
68b97820-43ef-5f18-975e-3fc3c9960e38 | note | Acceptance / Conformance Criteria - Compare tonnes used (from delivery docket) with measured area Within ±2.5 % of the specified rate
aca9e915-5aec-53eb-bc48-4f755a7c2c21 | note | Standard / Specification - TNZ B6
e3228326-a428-5903-8a5f-45c605273519 | note | Verifying Document - Site Notes
d679f51e-32a8-5a92-bb32-fecca5ba6b2c | note | Frequency - Upon emptying the spreader and bulk tanker
d541f030-6686-527f-a67e-eb3922abd445 | note | Activity - R
75111d96-39ac-520b-bbad-af92c278c2f1 | note | By - SE
74caf95c-5000-5bc8-b4b2-04774c703212 | checkpoint | 6.04.12 - Maintain OMC during stabilising
67a7bf6e-5925-5f91-8b98-58f13ec66fc4 | note | Acceptance / Conformance Criteria - The water content during compaction shall be in the range of 90% to 100% of the material’s optimum water content by NDM
221c45c9-9783-5127-ae8a-4d9fdc76cb94 | note | Standard / Specification - TNZ B6
df070077-c6a5-5b64-b8fe-57ffd4c9d52e | note | Verifying Document - Site Notes
1d3ac4db-33db-5204-be5b-4cce824f0fa7 | note | Frequency - Continuous
afc29ce6-1580-50c0-875a-7d3aab9a5e13 | note | Activity - R
9db2b5c8-defd-582c-a4ca-837200747cbb | note | By - SE
7b488497-b6e3-515a-a2cd-a6fa3fd2f415 | checkpoint | 6.04.13 - Control of cut depth
0ddfa63a-fd18-5bae-a74a-6c98f04519f3 | note | Acceptance / Conformance Criteria - Maximum variation from the specified depth of cut is –5 mm and +15 mm.
25ee1494-9d5b-5d4d-b5a3-a40e2a8cd101 | note | Standard / Specification - TNZ B6
ca9c51c8-b702-5df5-bf81-99449144462d | note | Verifying Document - Site Notes
37d1ce92-57b8-5546-b45e-95aa72e6d33d | note | Frequency - First check of cut depth should be immediately behind the stabiliser at the start of each run, then again every 200m, or as requested by the Engineer
9b9978ae-2445-5c30-b771-a7c7e932bc80 | note | Activity - R
479a411d-566d-5a03-84db-2ef8e0048266 | note | By - SE
a7d56f3a-97b2-545b-8bfb-724ae17d31c5 | checkpoint | 6.04.14 - Mixed material testing (ITS)
182a9fe4-2949-5d3e-b7d3-fa5b4add3c9e | note | Acceptance / Conformance Criteria - During mixing, the contractor shall take a pair of representative samples behind the mixing plant per lot or at a minimum of 2 pairs of representative samples per day.
a16b5584-eb92-5996-a447-640616a6119e | note | • These samples shall be placed in a sealed plastic bag and cured for 1 hour before compacting into a mould and testing the indirect tensile strength (ITS) of the mixed material according to NZTA T/19
794886b0-a9e7-5160-9efb-77c08cfa7659 | note | Standard / Specification - TNZ B6 7.5
d8b792e0-ef84-513a-be03-c931ca889de2 | note | Verifying Document - Test Results
aa8aa106-429b-510b-8ded-44d4974a6b19 | note | Frequency - 2 pairs of representative samples per day
2cce68a2-8e49-577d-8452-1338d837f301 | note | Activity - R
d9dd5959-3630-54c0-be19-04a149b58bc7 | note | By - PE
3cedef64-08d4-5b77-aec2-06e0043b20c5 | checkpoint | 6.04.15 - Particle size distribution behind stabilizer (Wet Sieve)
1595fc51-d5fc-5df3-a8b1-0773e76f8c91 | note | Acceptance / Conformance Criteria - A Wet sieve analysis will be completed within 4 hours after stabilizing, and consist of a minimum of 3 sample bags per lot.
e177ed60-e00e-51b1-895a-acc923dfc0f0 | note | Standard / Specification - TNZ B6 7.5
b07b0c57-20d3-5c59-9388-46d75e9923ed | note | Verifying Document - Test Results
0c70ede9-d3ba-5994-b6d1-9957929423c4 | note | Frequency - 3 sample bags per lot.
574bf161-e84e-5d84-ae04-3162922faf6f | note | Activity - R
f1ad340c-ef06-5def-a22c-94cd6377d488 | note | By - PE
d62ad979-e997-5694-a31c-92d3522dc172 | checkpoint | 6.04.16 - Plateau Density Test
68a2ad58-5808-5d0c-819d-28b10696645c | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
6d0085de-57cf-557c-91b6-4672f368d027 | note | • Testing shall be at OWC.
d22a0b2c-00d9-5356-b5e9-2c972d6ecf9f | note | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
7bea7d1c-f70f-56a2-8442-27215f842acc | note | Standard / Specification - PS - Table 7.2 - 2.3
068b6962-d280-59ef-82e1-3d35849927d3 | note | Verifying Document - Plateau Density Report
6adfe101-3863-5448-b479-fed6fb6eecfd | note | Frequency - 5 tests per 10,000m2
6077f9fc-e466-501e-83cb-2e4a91af231b | note | Activity - I
87cbce07-02e0-52d7-a53f-d13045dca5c8 | note | By - PE
5fce28a7-9260-5974-9b51-6a9f0890352a | checkpoint | 6.04.17 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
b1a1c4c4-a226-5240-9436-4b643503254b | note | Acceptance / Conformance Criteria - The sub-base compaction requirements in Table 2 of B/6 shall be replaced with a Mean Value ≥ 98% and Minimum Value ≥ 95%. - Direct transmission
227b8354-585b-5405-b88c-7c7fcdcfeec4 | note | Standard / Specification - PS - 7.3.2
f36eb166-000e-58bf-be19-f92bb30d703b | note | Verifying Document - IANZ NDMS
cd6f29e3-2a32-5b63-ab04-d66b4b185db8 | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
d9507bce-a48c-50aa-ab82-c8811ad35072 | note | Activity - I
58b68c5a-e4b7-5f89-a3b2-685edfa044cd | note | By - PE
4aa55dcd-a656-5a26-8180-ba5534462e9c | checkpoint | 6.04.18 - NDM Water correction
f071d565-d785-572a-922d-f08a064dbc0b | note | Acceptance / Conformance Criteria - Daily Laboratory water content tests shall be carried out on samples taken and used to correct the NDM measured dry density
2e044633-d7c7-5d9e-b5dd-dafff9d7c0bd | note | Standard / Specification - NZS 4407
836d50b3-7c26-50b4-baaf-bbe5282e1ec4 | note | Verifying Document - Corrected NDM Results
c8f85b5b-bbd3-5b8c-ab68-033d78da6733 | note | Frequency - Per Stabilise day
7e936f2b-4eb0-5b41-ab57-92180a1d77ef | note | Activity - R
83e332d0-a668-5154-84ac-e7fbc301bf14 | note | By - PE
ba631b52-5dc2-5c4a-87ff-800c5e357854 | checkpoint | 6.04.19 - Post Stabilisation Surface shape control, layer thickness
9526862f-91c5-5dac-95ad-70cd020f619e | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
6522fc0e-4196-5f03-afbd-9b75927f8d6d | note | • Vertical: - 5mm +10mm
f4863cc8-486b-5be9-a731-8bfa42984a1e | note | • Cross fall: 0.5% on 2m straight edge
6954ac89-9caf-5018-b91d-b28e25c03733 | note | Standard / Specification - TNZ B6 8.2
3daf20d1-728d-5007-97c3-0bb9105461f6 | note | Verifying Document - Total station Topo showing levels compared to design
d07c63a7-48c1-5be3-b5cc-1adac4534f34 | note | Frequency - Continuous
98fcf74d-8e60-596d-8907-88b9d7ef90f9 | note | Activity - R
bc888039-e7fd-5dc3-aee8-ae317a7d7b11 | note | By - SV / PE
eeb24f51-2626-5cc0-a95a-e896cb9f7dc9 | checkpoint | 6.04.20 - Protection, Curing and Maintenance before Overlaying
e92392ec-97c2-50e1-821a-33d79ed2472f | note | Acceptance / Conformance Criteria - The Contractor shall protect, maintain and cure the completed cement bound sub-base until the next layer is applied.
c8bc45de-bc79-5b30-864f-5bf260d7c2d1 | note | • Besides construction traffic required for the above curing no other construction traffic shall be permitted onto the layer within 7 days of stabilisation
e0059b71-6b51-5fd4-8250-d3218d19768e | note | Standard / Specification - TNZ B6 - 7.8
c2673520-0068-526c-b733-bd1c5e249159 | note | Verifying Document - Site Notes with photos
c4df2b91-2813-55d7-a6f8-582b3ae81f62 | note | Frequency - For 7 days after stabilisation
5b871b77-b3c3-5fbe-b180-46fc780076ee | note | Activity - R
565020ac-19d7-5868-a1ba-35b0f8e9edd9 | note | By - PE
8895530f-a026-5a64-aa6e-d3d4b0b121b6 | checkpoint | 6.04.21 - Benkelman Beam
70de7fe9-6b26-586f-899f-398eec09a3f7 | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer.
e954676f-2098-54d1-ab59-fe6251457716 | note | • Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY
68252c7e-3e47-53cf-bf1d-ef2c070c1ef6 | note | Standard / Specification - PS - 7.3.2
81139e68-a273-5646-81ae-6695ea090e1f | note | Verifying Document - Benkelman Beam Report
053563ae-5872-575a-8948-c0b3e4514eb3 | note | Frequency - Every 10m of each lane – staggered between left and right wheel path.
bdccd325-dd78-5064-9cc2-edf57d634663 | note | Activity - HP
93770925-a868-5d26-a5e0-1f1fd3e3eb92 | note | By - ENG
69352328-8f56-52c5-bce0-ccf55cf27bbb | signoff | AUTHORITY HOLDPOINT
42dd6dc9-09fe-578b-bfbb-13b10408700c | checkpoint | 6.04.22 - MDD / OMC / SD
2630dcc7-1a5c-52aa-a82f-67d5bf7350e1 | note | Acceptance / Conformance Criteria - Post hoe, stabilised MDD, OMC, and SD. 1 test per 2000m² or a days work whichever gives the greater number of testing.
173d78d7-805d-513b-b61d-766211856e8c | note | Standard / Specification - NZS 4402:1986, Test 4.1.3
290efdc4-fa23-54c6-85e0-bab5dc5134d8 | note | Verifying Document - Lab Report
44cbef68-a14f-5753-a329-5e07e7fc9006 | note | Frequency - 1 test per 2000m² or a days work whichever gives the greater number of testing.
b0f23bc1-17a6-5c33-b386-f2fee8d0dfe5 | note | Activity - I
fbe34ad3-62fb-5820-bbff-e6bdea491916 | note | By - PE
b4bfcba9-7ebb-50d5-ac19-ccbd0eaf5f97 | section | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
2c7daec9-a3b9-5141-9709-d474c280ddfa | checkpoint | 7.02.01 - Redline Drawings
e9831178-47b0-59a6-9d3e-db8fe82d67ba | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen mark up showing lot numbers and areas stabilised in different days including clear delineation of all joins.
42ae6479-0812-5f6c-9c07-a74a778776a8 | note | Standard / Specification - Downer
46a567d6-e788-5ef8-9b53-7728cb226c3d | note | Verifying Document - Redlines
52a691ee-b7b7-55cf-b940-d4a415e252dd | note | Frequency - Post construction
e23418a8-3819-5731-b4b1-40b53b1be0dc | note | Activity - H
c5e2fca2-dd50-5ce1-b220-2d2b1f521bff | note | By - PE
64b76a32-8a2d-5b0a-a391-f8b4cddcdb10 | checklist | SYS - ITP - Pavement & Surfacing - Subbase - Rev E (v1) | itp | ITP - Pavement & Surfacing - Subbase - Rev E
3969119e-9d77-5427-b958-ecc82f083c46 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
ec4e551b-3f47-528c-ae6c-fdfb3458be34 | note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence
eb1c5ab0-d958-5aff-9e01-8f56d5db5c3c | note | Standard / Specification - Downer
95e813a5-8719-5ac9-9ed3-db95c88daa4f | note | Verifying Document - Construction Pack
805d2c95-dc1c-508e-8b9e-fbca9c1eeaf6 | note | Frequency - Prior to Works start
fc39fb4d-ffff-5e1f-8d56-399758b18a65 | note | Activity - H
802be262-7e7e-53e8-b8bf-6038d6e34751 | note | By - PE
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
27f3be6b-b818-5263-817f-5ba924480d35 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
1f441f83-2c34-577a-90e0-73818924a2cf | note | Standard / Specification - Downer
a4fa1ba9-6110-5364-ab83-c9684041414a | note | Verifying Document - Survey Records
7fe5d102-a89b-537b-849f-5cc7bf99618c | note | Frequency - Prior to Works start
d378e4fb-1992-5af0-8e29-ab8e511f0e7e | note | Activity - H
ed48a75e-9faa-5783-b481-e3f0f2090547 | note | By - SV
a24a2c58-bf6f-5474-883c-40044bad1fc7 | checkpoint | 3.01.03 - Service Location
07cf3e6e-2226-5ee4-b1f5-8fff7d3c89fe | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
e5694d8a-f45f-52e8-b573-2ce535af9e31 | note | Standard / Specification - Downer
b2970209-fe08-5050-ba93-b0537bd69e94 | note | Verifying Document - Excavation Permit
e872e4d7-566c-548c-8e05-f649772197fa | note | Frequency - Prior to Excavation
0ef56c5b-7c85-56e8-9a7e-aab9f6807218 | note | Activity - H
53f0bb53-59d4-5d30-9a93-b3b481462cec | note | By - SE
0a214a7a-124a-5898-a837-e29e83751df0 | checkpoint | 3.01.04 - Internal Permits
8f9ece01-d727-5876-8560-edbd9d82bcf8 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. if applicable.
a7ee36d2-9b73-5f58-b71b-db5ca41fe4a2 | note | Standard / Specification - Downer
85ad478e-6552-52d0-b8b4-54e1f7ffbc8d | note | Verifying Document - Internal Permits
93d4943e-f796-520a-9124-ecb481319afe | note | Frequency - Prior to activity being undertaken
ea702c86-97c6-5605-ba1e-bfeeb7f387ec | note | Activity - H
a2718418-fc15-5b59-89c6-07251b3f0c0b | note | By - SE
917e2881-0901-542f-ae25-686bf9c47009 | checkpoint | 3.01.05 - External Permits
f23abc2d-c8ee-50ea-854a-9f64a7d9d86a | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc, if applicable.
6b62d5fe-af97-5ca3-b301-bd92f2791dc8 | note | Standard / Specification - Downer
a02559dc-175e-589a-9b8a-8eab68d69cad | note | Verifying Document - External Permits
b2f5d673-8cc4-5dbc-8d75-deccfbe742fe | note | Frequency - Prior to commencment of activity
d3a90524-e3a6-5f9e-b9d3-b83ba77aa7bf | note | Activity - H
13bc7be9-6edd-55c9-a267-e302e9aee166 | note | By - PE
a1302970-0389-558d-b43c-67b14bbfc27a | checkpoint | 3.01.06 - Approved Construction Drawings
f56d4abb-1946-538b-aad6-86aea7955913 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
09117102-46e6-57a9-9743-cdcaf0e4e481 | note | Standard / Specification - Downer
46964b83-84c6-5336-b6bd-922be5cef306 | note | Verifying Document - IFC Drawings
39dfba69-75f7-5742-968e-a4c90dbb0b22 | note | Frequency - Prior to works start
68e4c5de-58e0-5dec-91c6-170e024e015a | note | Activity - H
3d527e69-1c47-5f3d-8273-fc7878a3c156 | note | By - PE
4dd36031-ce9c-52f9-bfbc-d1541a841138 | checkpoint | 3.01.07 - Stabilising Methodology
f31947ca-c372-52b1-9187-bb4248d3254b | note | Acceptance / Conformance Criteria - Written approval of the Engineer with the approval of the methodology
a161a67c-8a7a-5dd1-9557-f02e91f6b027 | note | Standard / Specification - PS - 7.3.3
07fd60c0-fd43-5cf7-befe-31b3417972ce | note | Verifying Document - Correspondence
5f17963d-05de-50a8-9578-9003dcf71a00 | note | Frequency - Prior to stabilisation start
4c607593-a8eb-5c32-8ec8-95b0db6dee42 | note | Activity - HP
b8772278-c47a-56b1-a98c-0284beffbb55 | note | By - ENG
bcc75d59-fda9-5665-870d-6406349e1ed2 | signoff | AUTHORITY HOLDPOINT
9ffb2cc0-a1b6-5e07-aa7c-34ea633a63b0 | checkpoint | 3.01.08 - Acceptance of the SIL layer
f6339289-345f-5f4c-9a10-88376f46e5fd | note | Acceptance / Conformance Criteria - Written approval of the Engineer - All compliant test results for subgrade, SIL, all road crossings, storm water, wastewater, watermain, subsoil/pavement drains and any other activity that has been completed in the pavement area.
02730cba-a67f-5416-abdc-90b5998957c6 | note | Standard / Specification - PS - 4.8.3, Table 4.3
847b87f3-2330-5a62-abcc-ad8b65920f34 | note | Verifying Document - Hold point relesed / Testing reports
683e6528-9871-5c86-b102-a59b4f362661 | note | Frequency - All sections before proceeding to the next layer
c2f09181-52a5-56b6-a1b5-1c437cb54f45 | note | Activity - HP
ad1d82fa-b960-58f5-b406-029832fbcf42 | note | By - ENG
d3949fe3-b334-5e1c-a2b3-f23ab054269d | signoff | AUTHORITY HOLDPOINT
bc43c978-69d8-5f48-8b7f-ecbcce31a7dc | section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65
ca87e1fb-7246-51ad-9189-73e2340ccb26 | checkpoint | 6.02.01 - Sub-base MDD and OMC
4bc5963e-cd2c-51c9-aca5-69592b28e7b2 | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
71cb6c20-295f-57d5-a171-0161932e085a | note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
a63946e0-13fc-5f8f-af3f-dd8702db5ce8 | note | Verifying Document - IANZ Lab Reports
21058093-260c-502c-9a10-4289560be62c | note | Frequency - No less than 1 test every 5,000m³ (in place)
e8b8790c-3ca2-5fdb-89d4-45c8244f3825 | note | Activity - R
3f7f445d-4e23-5bda-9bff-1d2d926e9369 | note | By - PE
70fabdf0-7745-50be-96bf-2ded7dc55eed | checkpoint | 6.02.02 - Plasticity Index
22db6f42-ec9d-5643-90f1-7b79fa348ab3 | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Liquid Limit shall be ≤ 25 when tested
719e890d-d568-55b5-84e6-bed77f0f46a3 | note | Standard / Specification - Table 7.2
78c93c41-abe6-58db-a342-afd7b48c2a61 | note | Verifying Document - IANZ Lab Reports
6c9b5431-1a5a-52bb-9e62-0e81f150c6d6 | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
f59876a0-5a1f-53f6-b4bf-cb2e0bcdacd0 | note | Activity - R
1ced5c1f-5106-5c18-8962-145b62d99b22 | note | By - PE
22886128-c2cb-5f11-b511-007c412fa0ae | checkpoint | 6.02.03 - Clay Index
b8341bd7-673c-5dc2-808a-b5591245a41d | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Plasticity Index shall be ≤ 8 when tested
13969d9f-b85a-5f7a-9aa8-66e1e0edae96 | note | Standard / Specification - Table 7.2
2deb8519-49c2-5487-9cf7-444377be1b25 | note | Verifying Document - IANZ Lab Reports
20980237-258c-5659-ade7-2366ac0b8b3f | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
5cdb0063-1c4f-5b26-af41-f8037bdb887a | note | Activity - R
fd180c27-27ce-546e-80c4-4d43ec441f4b | note | By - PE
39fe01b4-f08b-5b33-9943-aadecfa5826a | checkpoint | 6.02.04 - Sand Equivalent
840c29c2-0a8c-5ea5-ba9e-1cbbf8bf56ed | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Clay Index shall be ≤ 5 when tested
459a0a17-3115-50b1-8574-e577b9fa3289 | note | Standard / Specification - Table 7.2
4931d8f6-9541-5ae3-bcab-bf8298c7c272 | note | Verifying Document - IANZ Lab Reports
527ee89c-1792-57ee-a5a9-287bcfcbc472 | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
5f19806f-af48-5c20-b1eb-99d26cdcd076 | note | Activity - R
ed8cc6f7-ff4c-5eed-9210-4c62bf32bba9 | note | By - PE
4aff0413-9e3c-530c-b97a-0793ec692f9c | checkpoint | 6.02.05 - Particle size distribution
9d8c8e5e-11ce-58a7-860d-c33d6c7859b2 | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1
616c8ede-e9b2-5437-b1f6-ce66bcd2f0e7 | note | Standard / Specification - Table 7.1
bdb504a7-1ca9-50f7-b822-c9b3a4acf4c6 | note | Verifying Document - IANZ Lab Reports
f92c3ee3-0fce-5b0f-8b35-7932831125a2 | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
71e702c3-1afe-5980-aab7-e902f1ec27f2 | note | Activity - R
69ce19e3-2200-5312-b708-210d89c586eb | note | By - PE
e8905abc-1647-5fbc-9fa2-b0958848732e | checkpoint | 6.02.06 - Average Uncompacted Layer Thickness
9570be19-0fe8-57ce-bcb1-ef4816b0e78c | note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
3aa0923e-f1c9-58dc-a8ae-da58cae7c067 | note | Standard / Specification - TNZ B/02: 2005 - 7.3
876ae953-7cdc-56d4-b12f-0969f34eb79e | note | Verifying Document - Survey / Level Checks
7eb6d98c-375e-576e-ac51-7e0c32aeb52e | note | Frequency - 1 test per 20m
1364f684-6351-556e-8189-03544cf0bdf0 | note | Activity - I
15f9afb4-4f6e-561c-9b64-85ec16932a31 | note | By - SV / PE
50dc97be-5c04-59c3-8703-cd318c3ee35e | checkpoint | 6.02.07 - Plateau Density Test
395eae28-4c8d-59bc-bd7b-7283b16b67bb | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
614970bc-9f95-51d2-85d7-240c03166f66 | note | • Testing shall be at OWC.
03cd9565-736a-5c41-b2bb-2c62bef5a03a | note | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
7d062746-9063-552a-8600-70c701e6de9c | note | Standard / Specification - PS - Table 7.2 - 2.3
819a1ad6-5e53-520b-ad5f-c702560be83c | note | Verifying Document - Plateau Density Report
ec31e201-c41b-5fc2-9b67-fefc9467feff | note | Frequency - 5 tests per 10,000m2
21ad2544-ab57-55a5-971e-41a12e355954 | note | Activity - I
80faab0d-83f3-503a-9158-a9a09d8dfaf0 | note | By - PE
3ee4467b-b164-5546-a4a6-7cc3c4ecf208 | checkpoint | 6.02.08 - Sub-basecourse Pavement Layer Compaction
9e8fe53f-a4f1-5780-8ccb-6c86d9016322 | note | Acceptance / Conformance Criteria - Mean Value ≥ 95 Minimum Value ≥ 92
71360f74-312e-57d7-bb04-30fff5aea2e0 | note | Standard / Specification - TNZ B/02: 2005
de23d183-7039-5637-980c-457a089db70b | note | Verifying Document - NDM Report
60c78e68-7cc6-5c38-8fa6-1f1e015f1735 | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
fc9d3184-55ac-5435-a416-d61089d7c36f | note | Activity - I
a514a1b0-5d8e-57ef-b0a0-53b72199740d | note | By - PE
b152466a-921e-56d5-9032-1b468cc0597c | checkpoint | 6.02.09 - Surface shape control
5271a85c-4033-5182-87d5-e949d8805412 | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
7099c8a2-8d24-5440-a12e-deca0db77cbc | note | • Vertical: - 25mm +5mm
ea995418-cd6c-5018-87a7-dbda26d9543b | note | • Cross fall: 0.5% on 2m straight edge
51ab3f3a-0703-53a4-909f-ab0246c7ba52 | note | Standard / Specification - TNZ B/2
bbb26c31-a3d5-5e57-9c1f-0918ac1187c8 | note | Verifying Document - Total station Topo showing levels compared to design
26a05264-4d7b-5c54-8b74-ae3956ac22bd | note | Frequency - Continuous
c70cb08a-ddc3-5280-bbe8-f078b3077f4e | note | Activity - I
8b54b2c0-f2d1-5214-83b0-fdec710c6b66 | note | By - SV / PE
7c9c928b-9d6d-55e2-9057-4eae9a377090 | section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial
6c098115-ed50-5770-83bf-79ab8107d3a0 | checkpoint | 6.03.01 - Stabilization Production Plan
e9831178-47b0-59a6-9d3e-db8fe82d67ba | note | Acceptance / Conformance Criteria - Production plan sent to engineer for review 48 hours prior to stabilising commencing. This is to include all information set out in NZTA B/6 7.2.3.
42ae6479-0812-5f6c-9c07-a74a778776a8 | note | Standard / Specification - NZTA B/6 7.2.3
46a567d6-e788-5ef8-9b53-7728cb226c3d | note | Verifying Document - Correspondence
52a691ee-b7b7-55cf-b940-d4a415e252dd | note | Frequency - 48H hours prior sabilising commencing
e23418a8-3819-5731-b4b1-40b53b1be0dc | note | Activity - HP
c5e2fca2-dd50-5ce1-b220-2d2b1f521bff | note | By - ENG
efaac3d4-313c-53da-9b8a-af70649a58b8 | signoff | AUTHORITY HOLDPOINT
33bc697f-3ee0-5632-94ad-1cc6ea4d8aff | checkpoint | 6.03.02 - Longitudinal Joints
c3da4913-cf3f-5467-a425-e19830da3ced | note | Acceptance / Conformance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by a minimum of 200 mm or half the layer thickness, whichever is the greater.
3187bd79-3bbd-5d8e-8581-e66206fee0b3 | note | Standard / Specification - NZTA B/6 7.5.2
c421fd54-cc40-52cf-8425-3c13eae03934 | note | Verifying Document - Stabilisation Prodution Plan
c55c6d23-9dc7-5f3a-9c97-c1513e529d8f | note | Frequency - 48H hours prior sabilising commencing
e9367a12-81c3-525e-974c-38c03a4f729f | note | Activity - H
0ec96b79-f1b1-53b6-a1ae-d3836cbe0350 | note | By - PE
f2fd84d9-a211-565e-a0e0-957d8630417c | checkpoint | 6.03.03 - Stabilisation trial
e08756e0-d528-5aad-9c69-21fe5f648cf6 | note | Acceptance / Conformance Criteria - A trial shall be conducted on a minimum stabilised area of 2,000m2 to verify the performance of the stabilising operation and finished product prior to full scale production.
0dbbcc25-5157-5beb-9e6a-9e92f6b99aa9 | note | Standard / Specification - PS - 7.3.3
81929707-068f-59b8-89f2-92df889e8a1c | note | Verifying Document - Triall Report
07fa29ac-31f2-5924-b389-c70ec5e9ece2 | note | Frequency - prior to full scale production
5821f127-a9b7-5b6b-b356-c7fec3b1afda | note | Activity - HP
38635240-5a2c-5eff-849f-e19f22cfc73b | note | By - ENG
836a28a7-55e3-5ddb-91a4-e7dccd925e7a | signoff | AUTHORITY HOLDPOINT
c77ae1a3-eb3d-5fdd-85c2-176a01d6eedf | checkpoint | 6.03.04 - Stabilising Equipment
a174ca72-dddc-5558-a278-5236cc481e6e | note | Acceptance / Conformance Criteria - The Contractor shall use stabilising plant purpose built and appropriately adjusted for the in-situ stabilisation of roading aggregates, as opposed to plant designed for soil stabilisation or re-cycling.
b6711173-5d7b-5401-bbb6-9f87711a72ae | note | • The stabiliser drum shall have a straight tooth pattern and the drum speed must be adjustable in real time during stabilisation.
8f6c961c-4b1d-5317-8a01-834092d8eb17 | note | Standard / Specification - PS - 7.3.2
63b65329-56d2-5f94-a4f4-50a223f256ec | note | Verifying Document - Plant Approval
75aecaf6-730c-55fe-8a0d-904f68457493 | note | Frequency - Prior to works
facb13e7-f88e-5306-9aaf-1a4193048ed3 | note | Activity - H
c36b7a69-c597-5379-9bf9-b7dc0c7dcbff | note | By - PE
65357786-cd6f-5367-a375-639ab3f50f85 | checkpoint | 6.03.05 - Stabilising Supervisor
ab15ab4d-6a1b-5ad6-a23e-5d89fec1d1a1 | note | Acceptance / Conformance Criteria - During stabilisation the Contractor shall employ a suitably experienced person to continuously walk behind the stabiliser to assess the uniformity of the mixture and water distribution and to check the stabilisation depth every 100m.
9c9c2035-4b24-52e8-9403-393b2235ccfa | note | Standard / Specification - PS - 7.3.2
34656b4f-1439-5386-9ebc-007176f0ccea | note | Verifying Document - Supervisor Approval
23985ea7-a28f-521e-b69b-259ca26e5f2b | note | Frequency - Prior to works
6e66a8ad-9649-5ff7-b952-feb4cc32cc56 | note | Activity - H
4696b9df-831d-5d97-bb0b-f320ba34c6f6 | note | By - PE
b2e16153-370f-553c-9fbe-4d6c94095131 | checkpoint | 6.03.06 - Before Stabilisation Surface shape control, layer thickness
563a3feb-7b54-525e-8eac-b1d9487bbfea | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
9d1b46f2-1d5a-5d76-bec6-2b88b1c5133d | note | • Vertical: - 25mm +5mm
52acc506-7c4e-5f5e-98cb-79bd2fa11070 | note | • Cross fall: 0.5% on 2m straight edge
a8362e42-1666-5b47-b72b-f781c161a505 | note | Standard / Specification - TNZ B/2
eec71e29-c07f-5bac-89cf-25793285c630 | note | Verifying Document - Total station Topo showing levels compared to design
bad201eb-bd3b-55fd-b978-1ec43fd60bc2 | note | Frequency - 1 test per 20m
bd9c102d-880a-5230-bf6a-5691f03c6130 | note | Activity - I
3685d3c4-54d2-53ae-b6e5-578e5ceded3c | note | By - SV / PE
61811b90-1233-52f7-81cc-b19f731dbfcd | checkpoint | 6.03.07 - Average Uncompacted Layer Thickness
43ffede8-eb80-524b-a01a-db135ed8ba8d | note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
c3046233-92bc-58b5-8195-b158fbcc75e7 | note | Standard / Specification - TNZ B/02: 2005 - 7.3
b259e3ac-c1de-5106-a7a3-83e9e9831aef | note | Verifying Document - Survey / Level Checks
26dc4776-c0f9-52c0-af0c-1509545d7f62 | note | Frequency - 1 test per 20m
b5bf0d7d-85a3-59cb-a307-090dab4d6d7e | note | Activity - I
6473d183-8207-5544-bafe-0c54b5eb607b | note | By - SV / PE
0f3c4886-911f-570e-9380-945bb931b659 | checkpoint | 6.03.08 - Pre Stabilisation Compaction
6f7bd7dc-cdae-5a56-9c2d-ca632a2e7753 | note | Acceptance / Conformance Criteria - The full thickness of the layer to be modified shall be compacted between Value ≥ 95% and Minimum Value ≥ 90% Prior to stabilisation, this will be reviewed following the stabilising trial and adjusted to suit and the updated target shall be added after the stabilising trail. DN1205-DOW-RFI-0043.01
465d47a0-b711-5cb1-96c4-f6d85a1b465a | note | Standard / Specification - PS - 7.3.2
7fe17492-23f7-501f-aa40-fcdb349e7514 | note | Verifying Document - IANZ NDMS
1297e1e0-3a45-5d69-b973-55da0fde25a0 | note | Frequency - Min 5 Tests per lot 1000m2 max lot size (Prior to stabilisation)
e6d1b948-87ad-5b28-98e5-bc82d3f2d156 | note | Activity - I
b2f3be24-86b7-57a3-aaf5-1d27e822bdd7 | note | By - PE
03cc060f-e525-5da1-b4a4-927a2c816637 | checkpoint | 6.03.09 - Pre Stabilisation Crossfall
cff7e8a0-7b7c-5a63-83ff-5ae38d022a53 | note | Acceptance / Conformance Criteria - Before stabilisation the Contractor shall check the crossfall by string line to confirm compliance with the design.
610f8fec-3aea-51db-bfa6-bf12ba54f71a | note | Standard / Specification - PS - 7.3.2
aca61598-044e-5199-afcd-e74ff6325165 | note | Verifying Document - Total station Topo showing levels compared to design
7d376523-ba8a-5097-8002-2e7f76bf4875 | note | Frequency - 1 test per 20m Prior to stabilisation
4516ac7a-7ea7-5e79-b46b-aeba1ccaa920 | note | Activity - I
6be639a0-0a72-5493-afba-e5ebedcc5d2d | note | By - SV / PE
dd46457d-0574-5b56-b7ac-f21afadaed60 | checkpoint | 6.03.10 - Stabilising Visual appearance
998a76a4-7c5a-5d3b-a8c8-9870c0245259 | note | Acceptance / Conformance Criteria - The stabiliser shall produce a uniform particle size distribution behind the stabiliser, both laterally, vertically and longitudinally and produce minimal break down of the coarse aggregate particles during mixing.
17a111e0-7eb4-57fd-bb60-84b1d9c9cbc4 | note | Standard / Specification - PS - 7.3.2
6839efa3-7b64-53d1-86b2-740fe4b8ebeb | note | Verifying Document - Site Notes
1869331e-c80c-5598-8b8c-6617b50b05ff | note | Frequency - every 100m
7389bc60-0085-59a0-83c9-2282da0bb60d | note | Activity - I
355db957-3967-5ecd-97f7-25887562ce3a | note | By - PE
6eed5d81-e5b0-55cf-bece-401f93ecd9b8 | checkpoint | 6.03.11 - Cement Mat Test / Spread Rate
76919ea6-ce78-5c8c-9508-eee14727b092 | note | Acceptance / Conformance Criteria - The stabilising agent shall be uniformly spread at the specified application rate across the pavement to Within ±0.5 kg/m2 of the specified rate
4ccb5c6e-e888-5bfb-8e21-4d805f05ea26 | note | Standard / Specification - Table 7.2
b90dc178-c767-52a8-a71e-488d65d88a23 | note | Verifying Document - Stab. Sheet
9f414802-aeb1-5406-92a7-ad6f8f64f2dd | note | Frequency - One per each run of cement spreading, until the Contractor can demonstrate consistency in cement spreading and/or demonstrate accuracy of on-board computer equipment calibrated/compared against weighing cement mats.
f542fe89-663f-5869-b318-5f8c7a3a8add | note | • Upon successful demonstration of this, the 1 per 500m2 minimum can applya
62cc9b71-67cb-5d36-a424-b8e8a822c60f | note | Activity - I
25135d59-b80a-5e1a-86e3-7f7007b18bab | note | By - PE
58788175-0c81-55f7-8c9c-122dc5a74310 | checkpoint | 6.03.12 - Cement Average usage test
06e0f300-76b8-535f-a655-00c6988371c9 | note | Acceptance / Conformance Criteria - Compare tonnes used (from delivery docket) with measured area Within ±2.5 % of the specified rate
08836960-1982-5462-b01b-a7b79a1a9a62 | note | Standard / Specification - TNZ B6
5577f49f-f312-5dfc-93fd-90890480cc65 | note | Verifying Document - Stab. Sheet / Delivery Doc.
56bafdfd-c441-5f6e-8935-2ae508c5c46c | note | Frequency - Upon emptying the spreader and bulk tanker
03f51aed-e2ec-5730-9e23-bb59d90303bd | note | Activity - R
ba98f297-2534-5c8e-9905-3ee4e0aed89e | note | By - SE
8dd5c234-a389-5dfe-8991-b7486bab77cb | checkpoint | 6.03.13 - Control of cut depth
ce798d42-6fea-5ed8-9fa4-7953f2de7e91 | note | Acceptance / Conformance Criteria - Maximum variation from the specified depth of cut is –5 mm and +15 mm. Without picking up sand from SIL
0d545cb3-19ca-551f-99b2-10f878522509 | note | Standard / Specification - TNZ B6
f50302f5-9336-5550-b886-eb591a3d1715 | note | Verifying Document - Stab. Sheet
9d05222c-25f8-5924-ae26-1b4dc85e1c8f | note | Frequency - First check of cut depth should be immediately behind the stabiliser at the start of each run, then again every 200m, or as requested by the Engineer
d1660d76-db41-5c8b-b632-25bc504b33b3 | note | Activity - R
b0901765-faf3-567d-bde0-c733dfb61059 | note | By - SE
19eac722-f22d-5929-8126-b167f6613939 | checkpoint | 6.03.14 - Plateau Density Test
d1a0cf10-f2f8-5613-8b93-b8107c2cb304 | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
71842105-60c2-5587-b4bb-6eb3f62f6389 | note | • Testing shall be at OWC.
89b5526a-a443-5577-ba5c-c00445ee5784 | note | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
69bcb218-106c-5fdf-b8df-84644ed7f1de | note | Standard / Specification - PS - Table 7.2 - 2.4
8f92fb7f-f8ba-5542-afaa-19692161a505 | note | Verifying Document - Plateau Density Report
0e69e2c0-eec9-5031-9972-d5f0b3a84fdc | note | Frequency - 5 tests per 10,000m2
db77b510-73b1-56e3-9b66-265e5d55626d | note | Activity - I
f746d0d8-3425-5d24-ba8b-9e8cddbf8144 | note | By - PE
2ee5ae31-1ce2-5318-b785-95fce0922ca9 | checkpoint | 6.03.15 - Particle size distribution behind stabilizer (Wet Sieve)
383e3b43-141d-57dc-ac27-0a1fbef0fe50 | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1. A Wet sieve analysis will be completed within 4 hours after stabilizing
dbbf8b52-48c3-5a65-a471-76774bafb6bb | note | Standard / Specification - NZS 4407: 1991 Test 3.8.1 Standard Method by Wet Sieving
584c1ec8-a297-541b-bdab-57da71f20e59 | note | Verifying Document - IANZ Lab Reports
1e01bb28-8a81-5739-84db-19f894d76d5d | note | Frequency - 3 samples bag per stabilise day post hoe
cb473351-9320-51d2-b9a1-5415dc2edaf0 | note | Activity - I
46ac7a5b-489e-5c61-9a81-a094103ee355 | note | By - PE
3744d9ba-d8e1-5383-9d2c-5335ed0cf31b | checkpoint | 6.03.16 - Mixed material testing (ITS)
ef0988cd-8048-5ec1-a1fb-011cc4af972c | note | Acceptance / Conformance Criteria - During mixing, the contractor shall take a pair of representative samples behind the mixing plant per lot or at a minimum of 2 pairs of representative samples per day.
7bbe5d1b-3f5a-5798-992c-00376e3df314 | note | • These samples shall be placed in a sealed plastic bag and cured for 1 hour before compacting into a mould and testing the indirect tensile strength (ITS) of the mixed material according to NZTA T/19
28a40525-2abb-549d-ad9a-a76a44342996 | note | Standard / Specification - TNZ B6 7.5
b2a08e69-aefb-502f-9667-60a10a79052e | note | Verifying Document - Test Results
98e935ed-c18f-5ac9-807c-0b85a7c17b7d | note | Frequency - 2 tests per stabilise day
4a43f0c5-a6aa-5816-a174-8dad3fc58c70 | note | Activity - R
2d4c1bcd-af9d-592d-9721-35e530c03d3f | note | By - PE
9b3b1023-6a86-5a49-9ba8-c3eceb03ddce | checkpoint | 6.03.17 - NDM Water correction
990ab85d-0a87-598e-b9f1-a7a68a6e620a | note | Acceptance / Conformance Criteria - Daily Laboratory water content tests shall be carried out on samples taken and used to correct the NDM measured dry density.
de4e8571-20b6-5a14-9d53-baa31c703993 | note | • Will get the Moisture correction factor from the Plateau report itself. That is the difference between the Moisture reading on the NDM vs the actual moisture when dried in the oven.
0d089788-33e3-5066-aa7c-135fd94ff095 | note | Standard / Specification - NZS 4407
3071916f-187f-5def-b4e9-22f4955e0ded | note | Verifying Document - Corrected NDM Results
4cc4a890-9e9e-5ebb-92e1-7c4a53685685 | note | Frequency - Per Stabilise day
0d9ef0e8-6cc6-5c94-a284-965d465bde6e | note | Activity - R
82279123-d95f-5b65-af9f-12a326c2b733 | note | By - PE
189483f5-5c2e-5d24-8c0e-4762ac1f0541 | checkpoint | 6.03.18 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
240233fa-df7e-566e-855f-f0d745ebb023 | note | Acceptance / Conformance Criteria - The sub-base compaction requirements in Table 2 of B/6 shall be replaced with a Mean Value ≥ 98% and Minimum Value ≥ 95%. - Direct Transmission
cb3cedb3-af0c-5ab5-926a-e09de0acd80f | note | Standard / Specification - PS - 7.3.2
b54eaec6-cfb5-501b-94fe-32483a79da38 | note | Verifying Document - IANZ Lab Reports
073fd872-05d3-5add-bcef-22bb304d219a | note | Frequency - Min 5 Tests per lot 1000m2, minimum 7 days after stab.
0d5458e2-1d29-5b8a-9fc0-73cbc1390d82 | note | Activity - I
be609c1b-c730-5a5d-9331-f1805b8f2002 | note | By - PE
4eafc89d-3d95-5e4e-b4f9-e4c39a2227af | checkpoint | 6.03.19 - Post Stabilisation Surface shape control, layer thickness
b0e5eaa7-9aa0-56a9-a866-6dcdd20ff39e | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
229c03ae-40f8-5fa5-9dad-7a3c83cc7554 | note | • Vertical: - 5mm +10mm
d405757b-42ec-5e57-93dd-b09d6f0a6917 | note | • Cross fall: 0.5% on 2m straight edge
404e5815-0714-5900-94a5-df1ebd722e10 | note | Standard / Specification - TNZ B/2
1cc3008b-3838-5deb-b0b6-70bc233ba267 | note | Verifying Document - Total station Topo showing levels compared to design
036f6297-a2f4-5805-9740-38c29acec8b1 | note | Frequency - 1 test per 20m
8c7b77e5-dd28-5d52-ba12-5bdd29328047 | note | Activity - I
680c3d1d-5ea8-5211-8945-472116ab03e0 | note | By - SV / PE
72280022-fd87-5882-b3d4-4682359acdc4 | checkpoint | 6.03.20 - Protection, Curing and Maintenance before Overlaying
d476d473-f525-5d01-867f-f2faa131a6aa | note | Acceptance / Conformance Criteria - The Contractor shall protect, maintain and cure the completed cement bound sub-base until the next layer is applied. Besides construction traffic required for the above curing no other construction traffic shall be permitted onto the layer within 7 days of stabilisation
8ab3c95e-0340-54bb-b616-56fe2bd76ff1 | note | Standard / Specification - TNZ B6 - 7.8
03475675-6d72-5fc3-9161-eaf51e553853 | note | Verifying Document - Site Notes
3807fd43-1c09-53a6-ba7a-374d49bdb964 | note | Frequency - For 7 days after stabilisation / Photos
e6932548-f213-5348-8570-33cf2030e6b6 | note | Activity - R
53bd01e6-24dd-5959-a3ac-c5a36ea4ff6b | note | By - PE
80726abb-7f00-5a67-ad5c-4f9961a101e8 | checkpoint | 6.03.21 - Benkelman Beam
28184ac9-114c-5685-bb7d-1142a911fc4a | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer.
795c713c-4e9f-5ef7-b471-3341fdcd79d4 | note | • Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY
aa986cfe-3d53-5204-b89e-2cc347065016 | note | Standard / Specification - PS - 7.3.2
129cc3b7-071e-5882-8f23-62f271e39754 | note | Verifying Document - Benkelman Beam Report
fcf841d3-46f0-5f72-adc9-738ca5df7660 | note | Frequency - Every 10m of each lane – staggered between left and right wheel path.
4db6bf4b-efbb-5b7b-852f-0c1d1513e683 | note | Activity - R
61494ce3-d9ab-5ef3-96dc-037932673c7a | note | By - SE
00ccd532-6cdc-5994-8bfb-114564ace123 | checkpoint | 6.03.22 - MDD / OMC / SD
6cb0d5d2-2347-50ff-83fb-1767f7e6259f | note | Acceptance / Conformance Criteria - Post hoe, stabilised MDD, OMC, and SD. 1 test per 2000m² or a days work whichever gives the greater number of testing.
2324b341-3fca-550c-be2d-f2fee1891bb6 | note | Standard / Specification - NZS 4402:1986, Test 4.1.3
0fcd1e05-a5ef-57ed-86ba-d8eb03e1c467 | note | Verifying Document - Lab Report
4ab74e9c-0267-5baf-9744-f76545b6797e | note | Frequency - 1 test per 2000m² or a days work whichever gives the greater number of testing.
a030ca09-717b-586f-a8e0-261f9cee5ff1 | note | Activity - I
fd20476b-574f-57f9-b4af-d031ba892c66 | note | By - PE
ba7d06af-c7af-5c9d-8ab4-2e3c21a61daf | checkpoint | 6.03.23 - Sub-base stabilisation trial
df6deb4d-1c5a-5968-baa6-f0e980e4f308 | note | Acceptance / Conformance Criteria - After the sub-base stabilisation trial, prior to proceeding with further stabilisation.
edd0ff47-8205-5183-8180-288e0827fb8e | note | Standard / Specification - PS - 2.2.16
86b78705-c8c2-5ae6-93d4-6792aab8fd7f | note | Verifying Document - Hold Point Release
fa0ca9ec-cd50-5ced-b603-ed26108d19be | note | Frequency - Min 48h Notice
09dbfdef-8287-50c0-8ebe-7b9a88336a52 | note | Activity - HP
be3ef2f4-f4c4-5cf2-af4a-7a7c41f76645 | note | By - ENG
944ea1fd-b7c9-5949-95b5-51c9f13d6c6b | signoff | AUTHORITY HOLDPOINT
3ed998ef-a740-59b5-a205-c17d1ea4ae1e | section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base
bfa46ea3-f62a-522a-aeaa-762b5defdaf1 | checkpoint | 6.04.01 - Stabilization Production Plan
e331197a-079e-548b-ae21-38202960f70f | note | Acceptance / Conformance Criteria - Production plan sent to engineer for review 48 hours prior to stabilising commencing. This is to include all information set out in NZTA B/6 7.2.3.
3bd09bd0-1b02-5865-b251-d7e3000bf3f3 | note | Standard / Specification - NZTA B/6 7.2.3
e440d32f-4a97-5f6c-b9c0-8aa4e04d873f | note | Verifying Document - Correspondence
7d61d0f9-37f1-5f53-8b90-89bcb80b5b51 | note | Frequency - 48H hours prior sabilising commencing
b149cbb1-8acb-518a-94f1-e7d1a3574902 | note | Activity - HP
60f2c249-9926-5512-8191-b0ae8e066099 | note | By - ENG
e4ed9518-8669-550c-8d69-a36a5a98261d | signoff | AUTHORITY HOLDPOINT
718a330a-7558-52f6-be9b-f238816a905a | checkpoint | 6.04.02 - Longitudinal Joints
4ad532f8-b83a-5298-9bfc-00106a8809d9 | note | Acceptance / Conformance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by a minimum of 200 mm or half the layer thickness, whichever is the greater.
3d84dc43-e313-5471-8481-2da0e196ee05 | note | Standard / Specification - NZTA B/6 7.5.2
59d1a76d-ca94-54d5-91e7-3ffac84d1a5a | note | Verifying Document - Stabilisation Prodution Plan
2eee2feb-131e-5701-8cf4-a9c2975247f7 | note | Frequency - 48H hours prior sabilising commencing
e0dcba3f-d644-5e77-8487-82e72f688b3f | note | Activity - H
7a0901de-7235-5f80-9c0b-cf437a8c3e99 | note | By - PE
3057a053-0fa8-5141-99e1-8805c8143030 | checkpoint | 6.04.03 - Stabilising Equipment
a3fac771-cff3-5313-a05f-011029358c19 | note | Acceptance / Conformance Criteria - The Contractor shall use stabilising plant purpose built and appropriately adjusted for the in-situ stabilisation of roading aggregates, as opposed to plant designed for soil stabilisation or re-cycling.
c1cb7dbd-f209-5e4f-9a1a-261d4589428a | note | • The stabiliser drum shall have a straight tooth pattern and the drum speed must be adjustable in real time during stabilisation.
9fffda08-b991-58f9-937e-8b4c35cc9289 | note | Standard / Specification - PS - 7.3.2
e9358d44-4b4e-568a-96b3-4d97c22c9276 | note | Verifying Document - Plant Approval
1c0b01a4-3a75-52e8-a978-619581de7785 | note | Frequency - Prior to works
a3f7c09a-10a0-5bf0-b435-3e9e719ef9d8 | note | Activity - H
82be9b68-996c-5463-8128-ace8bb528401 | note | By - PE
d10c1293-8308-5402-8f5a-943d59292a90 | checkpoint | 6.04.04 - Stabilising Supervisor
2159ee00-e8d7-55f2-8434-e4fff7bc6d67 | note | Acceptance / Conformance Criteria - During stabilisation the Contractor shall employ a suitably experienced person to continuously walk behind the stabiliser to assess the uniformity of the mixture and water distribution and to check the stabilisation depth every 100m.
1f229947-cb75-5935-9dc8-34ada7b5f79d | note | Standard / Specification - PS - 7.3.2
9ac7d520-98ae-5a19-b8d4-fc2d7d130664 | note | Verifying Document - Supervisor Approval
e0da6256-f3d9-51ac-a068-23477a1df678 | note | Frequency - Prior to works
3862352b-5487-5229-a277-f68d34df474e | note | Activity - H
e51cdc71-f085-5d2f-87bc-8bc4cb6f3245 | note | By - PE
1c51f95a-b88f-562b-b314-9008bea93499 | checkpoint | 6.04.05 - Before Stabilisation Surface shape control, layer thickness
ad7d8450-019d-5924-91fc-7f75792e2c7c | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
61e696f0-d4d9-5a31-9843-c4b2ad91151c | note | • Vertical: - 25mm +5mm
ace72e05-4bb7-50b8-aa59-f9be03ae084a | note | • Cross fall: 0.5% on 2m straight edge
840a0e0a-4cdd-56a3-bcc3-951064a43a04 | note | Standard / Specification - TNZ B/2
085082f9-b471-5e86-8024-d53bc0443173 | note | Verifying Document - String sheet
a7010fcd-99bc-5547-bf29-6f0234e0d49f | note | Frequency - 1 test per 20m
967f5c59-aeb8-5789-854f-4450c243c53f | note | Activity - I
722bd66e-759d-58da-ba7b-a1506b86e6d3 | note | By - SV / PE
0d6f6583-baee-5c8d-8dea-ee479453f289 | checkpoint | 6.04.06 - Average Uncompacted Layer Thickness
e52c36b8-1c0c-5cbe-9548-87cca371bf06 | note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
c51b15cc-7302-5ff9-a8c7-3bf668d8d187 | note | Standard / Specification - TNZ B/02: 2005 - 7.3
c9c05c81-b8ec-5b76-bb23-c8a85c4fb760 | note | Verifying Document - Survey / Level Checks
7818a860-08a3-5f88-85b8-68186532a008 | note | Frequency - 1 test per 20m
90023c98-d614-58fc-8362-aba793ca8138 | note | Activity - I
0449a779-ebe7-5529-b8bf-51786bb11e48 | note | By - SV / PE
917f88ba-1bf1-5687-b499-860c1cb7ca16 | checkpoint | 6.04.07 - Pre Stabilisation Compaction
86c30ff3-ab07-5fd8-b80d-4950fd4af9e5 | note | Acceptance / Conformance Criteria - The full thickness of the layer to be modified shall be compacted between Value ≥ 95% and Minimum Value ≥ 90% Prior to stabilisation, this will be reviewed following the stabilising trial and adjusted to suit and the updated target shall be added after the stabilising trail. DN1205-DOW-RFI-0043.01
b281908b-351e-56b9-b98d-270c663c7417 | note | Standard / Specification - TNZ B/02: 2005
7358af75-1748-56aa-aad2-30dfa72dbad9 | note | Verifying Document - IANZ NDMS
b612d03e-5e33-55a7-afd7-d53b0fb4aeae | note | Frequency - Min 5 Tests per lot 1000m2 max lot size (Prior to stabilisation)
f90a1ca2-f2a4-572f-a21c-f53ddf5e2b35 | note | Activity - I
4c6ead81-0fa9-5ed1-acda-a0edcf7cc443 | note | By - PE
609cd901-d33f-51ea-8bf0-2ac755e5ea9a | checkpoint | 6.04.08 - Pre Stabilisation Crossfall
5712cd5c-3966-5227-b2ba-7abd955dd93a | note | Acceptance / Conformance Criteria - Before stabilisation the Contractor shall check the crossfall by string line to confirm compliance with the design.
a4b9acab-25d7-53b7-9392-5b3728bc68b5 | note | Standard / Specification - PS - 7.3.2
cad94b7b-e6aa-55f1-a7c6-c3377391eae4 | note | Verifying Document - Total station Topo showing levels compared to design
b3e4d679-7713-582b-baf3-e31de68257ae | note | Frequency - 1 test per 20m Prior to stabilisation
355afcca-2dff-5693-97b5-7a9f71770b1e | note | Activity - I
563ccdf6-0817-5fb3-b46f-18abe37cd0a2 | note | By - SV / PE
c5459efa-5597-5eb0-a767-a817864c6611 | checkpoint | 6.04.09 - Stabilising Visual appearance
800f5c03-3bf2-52b5-83b8-0c37648a0a1f | note | Acceptance / Conformance Criteria - The stabiliser shall produce a uniform particle size distribution behind the stabiliser, both laterally, vertically and longitudinally and produce minimal break down of the coarse aggregate particles during mixing.
4387fdc8-5025-5848-bb4c-4bb10ef49da4 | note | Standard / Specification - PS - 7.3.2
0e773199-5e6f-55ca-a1a8-6195084d55e4 | note | Verifying Document - Site Notes
95a08c3f-ac10-537d-9357-9509e61bd11b | note | Frequency - every 100m
1835d486-50b7-50ab-b6fc-1b90a2bb5a41 | note | Activity - I
e5a553a7-676b-52c6-a86f-1339ffab2e24 | note | By - PE
7fa669a4-d877-59f3-a991-2960916f29d5 | checkpoint | 6.04.10 - Cement Mat Test
1dd3baff-ebe6-52d3-aab5-5a71f6db452f | note | Acceptance / Conformance Criteria - The stabilising agent shall be uniformly spread at the specified application rate across the pavement to Within ±0.5 kg/m2 of the specified rate
6bb41df6-8e09-5cc1-90da-7d93b76d80ff | note | Standard / Specification - TNZ B6
4bc48b69-7d17-59bc-ba33-4bc072b1c274 | note | Verifying Document - Site Notes
caf22b2e-9132-5974-89dd-84763a71e332 | note | Frequency - One per each run of cement spreading, until the Contractor can demonstrate consistency in cement spreading and/or demonstrate accuracy of on-board computer equipment calibrated/compared against weighing cement mats.
99c42675-6204-5c45-bb1f-3323cfe3b8f1 | note | • Upon successful demonstration of this, the 1 per 500m2 minimum can apply
70fce067-560c-566d-981b-11d8561156bd | note | Activity - R
5950ce26-bd3d-56bb-822c-985257c79146 | note | By - SE
0fabe193-9a41-532d-98d6-aa037b156014 | checkpoint | 6.04.11 - Cement Average usage test
f03fe172-618a-58c5-ba9a-e9aac16b5aac | note | Acceptance / Conformance Criteria - Compare tonnes used (from delivery docket) with measured area Within ±2.5 % of the specified rate
66092715-822b-5410-899b-b687652907bc | note | Standard / Specification - TNZ B6
364975bb-4818-5864-9a07-e76bebf48b94 | note | Verifying Document - Site Notes
c1caace8-c5a5-51f3-84cf-106207d1d6c0 | note | Frequency - Upon emptying the spreader and bulk tanker
74ddba70-549d-5f7b-86e0-244b166f6bf9 | note | Activity - R
a661758e-3f66-5cb6-a729-d11cccc9db0d | note | By - SE
74caf95c-5000-5bc8-b4b2-04774c703212 | checkpoint | 6.04.12 - Maintain OMC during stabilising
1dcc992d-d8a9-5d5d-b4ae-493ee61eebe9 | note | Acceptance / Conformance Criteria - The water content during compaction shall be in the range of 90% to 100% of the material’s optimum water content by NDM
e6917687-c03e-537f-a930-be6f46d42a91 | note | Standard / Specification - TNZ B6
2f500fe9-6514-527e-af94-281fb398a558 | note | Verifying Document - Site Notes
cf79c2e8-1985-50b6-81a9-6830fc4aa25d | note | Frequency - Continuous
85cb0c5f-0d79-5664-b138-7ddd2515143b | note | Activity - R
18add451-e01b-5089-a807-b1c283dabb7f | note | By - SE
7b488497-b6e3-515a-a2cd-a6fa3fd2f415 | checkpoint | 6.04.13 - Control of cut depth
9ef1cbcf-2090-580f-bd4e-b5a66fdf4333 | note | Acceptance / Conformance Criteria - Maximum variation from the specified depth of cut is –5 mm and +15 mm.
68e9f95f-0f6a-5a2d-86f8-451bb17e3db9 | note | Standard / Specification - TNZ B6
b3b3732c-1733-5223-8224-549b9db4b687 | note | Verifying Document - Site Notes
23ee10d2-55ce-55b5-8ed2-fdaa14d17904 | note | Frequency - First check of cut depth should be immediately behind the stabiliser at the start of each run, then again every 200m, or as requested by the Engineer
2555ffc8-798f-5f24-9f0e-affa62653877 | note | Activity - R
06b56834-3a3e-5597-ba9f-d39df45fa7d6 | note | By - SE
a7d56f3a-97b2-545b-8bfb-724ae17d31c5 | checkpoint | 6.04.14 - Mixed material testing (ITS)
0e12b5a9-cdeb-5ed7-b6e9-e89caf02e02c | note | Acceptance / Conformance Criteria - During mixing, the contractor shall take a pair of representative samples behind the mixing plant per lot or at a minimum of 2 pairs of representative samples per day.
c77ba25c-c214-51ab-8c42-7d7ceeb8991b | note | • These samples shall be placed in a sealed plastic bag and cured for 1 hour before compacting into a mould and testing the indirect tensile strength (ITS) of the mixed material according to NZTA T/19
3dc5cac6-b594-528b-b622-fb2b1caa9974 | note | Standard / Specification - TNZ B6 7.5
2b6f08fc-fd58-5f31-93ff-0063cf5b065d | note | Verifying Document - Test Results
0ce12f6b-032c-54c7-91b7-f9376ff7e092 | note | Frequency - 2 pairs of representative samples per day
4cefa690-ca8a-5db4-908f-95a89c3f60f8 | note | Activity - R
e3635531-3e0e-572b-a048-05b9a2869ef1 | note | By - PE
3cedef64-08d4-5b77-aec2-06e0043b20c5 | checkpoint | 6.04.15 - Particle size distribution behind stabilizer (Wet Sieve)
61f69f7b-99a8-52d9-82bd-d783d7cb2661 | note | Acceptance / Conformance Criteria - A Wet sieve analysis will be completed within 4 hours after stabilizing, and consist of a minimum of 3 sample bags per lot.
06e40bbc-b1ab-5cdf-a1fd-3c06bfd40603 | note | Standard / Specification - TNZ B6 7.5
b69c7454-ce52-5c10-8e24-9f7439fd1402 | note | Verifying Document - Test Results
962723f2-30f9-5bbd-be28-18d2a8bf284b | note | Frequency - 3 sample bags per lot.
1031727c-b9ad-5b8a-9d40-3b9b93b1691e | note | Activity - R
a8eb847b-b380-5659-a333-b5520289437c | note | By - PE
d62ad979-e997-5694-a31c-92d3522dc172 | checkpoint | 6.04.16 - Plateau Density Test
30d25dbe-db72-5f3a-bdaa-fff0ea8ef7fe | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
7e553060-7e2c-5c01-a28c-e650d27b2867 | note | • Testing shall be at OWC.
81eedbf7-4933-541d-ba37-561ba28e0009 | note | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
8692cc05-5985-58e8-a913-9de719d06995 | note | Standard / Specification - PS - Table 7.2 - 2.3
e55cf95c-d13b-5e91-97c5-beb7b9dc5994 | note | Verifying Document - Plateau Density Report
54a1ddfe-8386-5843-abed-98c8c2ece050 | note | Frequency - 5 tests per 10,000m2
9eac50a7-a916-5ef4-8e31-dd9400b981ba | note | Activity - I
146ca572-8057-5163-a5e2-4776c54e3ec1 | note | By - PE
5fce28a7-9260-5974-9b51-6a9f0890352a | checkpoint | 6.04.17 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
b6ac8401-a08d-55c9-9e92-b9374e3876cf | note | Acceptance / Conformance Criteria - The sub-base compaction requirements in Table 2 of B/6 shall be replaced with a Mean Value ≥ 98% and Minimum Value ≥ 95%. - Direct transmission
d5306be5-b743-514c-9fa7-4590f2e9fa5c | note | Standard / Specification - PS - 7.3.2
c0a142d5-833f-58bb-ae99-d595abe1f3d6 | note | Verifying Document - IANZ NDMS
34d12926-5e10-5c21-8067-d0092dbdd36f | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
d5994b74-2ca4-5c1a-8012-ed6062e29225 | note | Activity - I
94ea3ed2-0629-5e23-8cdd-5a0d599186ba | note | By - PE
4aa55dcd-a656-5a26-8180-ba5534462e9c | checkpoint | 6.04.18 - NDM Water correction
772c704b-f01a-50fe-9dc2-b3d10440cb5e | note | Acceptance / Conformance Criteria - Daily Laboratory water content tests shall be carried out on samples taken and used to correct the NDM measured dry density
835a86f9-8720-5ac8-8b07-18b667fa08b3 | note | Standard / Specification - NZS 4407
c9fa9fbf-9f3c-5dc3-b430-e866ab97feb9 | note | Verifying Document - Corrected NDM Results
ff40fbba-7239-516a-a3bb-212ccac8d49d | note | Frequency - Per Stabilise day
cdc78ed1-88c7-52df-8c47-87c86bfad990 | note | Activity - R
e2852971-2b16-55ac-a09e-dfb29eeb8819 | note | By - PE
ba631b52-5dc2-5c4a-87ff-800c5e357854 | checkpoint | 6.04.19 - Post Stabilisation Surface shape control, layer thickness
df5e37ae-acca-5b4f-a215-0166a8723139 | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
fc83da38-f1d5-58fb-a5ec-5eab04a9de4f | note | • Vertical: - 5mm +10mm
6331826f-59e0-57bf-96f4-32ef680715bd | note | • Cross fall: 0.5% on 2m straight edge
411545d9-66c0-51e8-8401-b1d8e0c2e4ad | note | Standard / Specification - TNZ B6 8.2
6d3f906e-4a39-5372-b3f0-0493f02f27a6 | note | Verifying Document - Total station Topo showing levels compared to design
7e124d93-aad0-5922-bdad-4b41e965d28b | note | Frequency - Continuous
7e02d4e2-617f-53b0-bcb6-d3777b20e4e9 | note | Activity - R
f22c2999-b75b-53ec-91bc-05bad9755c4e | note | By - SV / PE
eeb24f51-2626-5cc0-a95a-e896cb9f7dc9 | checkpoint | 6.04.20 - Protection, Curing and Maintenance before Overlaying
871102c7-020c-5463-a83d-7991e732abfa | note | Acceptance / Conformance Criteria - The Contractor shall protect, maintain and cure the completed cement bound sub-base until the next layer is applied.
6035c99a-af4b-5b7c-b19a-cfe7de24a223 | note | • Besides construction traffic required for the above curing no other construction traffic shall be permitted onto the layer within 7 days of stabilisation
d4787fb0-ea59-5912-805f-68e21e628f69 | note | Standard / Specification - TNZ B6 - 7.8
ce3d3d52-2855-5b32-a747-c1ae3e37e793 | note | Verifying Document - Site Notes with photos
611a5d3b-62d9-5e71-83a1-8d34b8c015c0 | note | Frequency - For 7 days after stabilisation
62061290-a9e8-54c6-9458-aa077ffd4cd1 | note | Activity - R
1f8753c5-7423-5a59-b6c2-8fb74a6ddd5c | note | By - PE
8895530f-a026-5a64-aa6e-d3d4b0b121b6 | checkpoint | 6.04.21 - Benkelman Beam
a726fa8e-3b85-5dd0-b062-8df19e4938d6 | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer.
669782df-f2ee-5b84-8119-cf95cfc13fc3 | note | • Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY
8d415580-85c4-58e2-8421-4049db1fd69a | note | Standard / Specification - PS - 7.3.2
f9c4f85a-8619-5cec-9129-04b57ac38ce5 | note | Verifying Document - Benkelman Beam Report
75198ad1-c3c1-52ff-a442-083d24f4d16b | note | Frequency - Every 10m of each lane – staggered between left and right wheel path.
fa63b9b7-742f-574f-9e4f-0cda0ecce321 | note | Activity - HP
bc6fbd4e-8d2a-5c15-a128-2e26f80beffe | note | By - ENG
69352328-8f56-52c5-bce0-ccf55cf27bbb | signoff | AUTHORITY HOLDPOINT
42dd6dc9-09fe-578b-bfbb-13b10408700c | checkpoint | 6.04.22 - MDD / OMC / SD
3015bf33-2735-5199-94d9-0375cefd22fd | note | Acceptance / Conformance Criteria - Post hoe, stabilised MDD, OMC, and SD. 1 test per 2000m² or a days work whichever gives the greater number of testing.
992155ae-17f6-5ae7-bb44-8bf8726ced39 | note | Standard / Specification - NZS 4402:1986, Test 4.1.3
d4114ab3-d904-5a73-9e97-6a00a0abbe2f | note | Verifying Document - Lab Report
5690faab-08ab-547d-be18-4e56c28a245f | note | Frequency - 1 test per 2000m² or a days work whichever gives the greater number of testing.
12f09bd0-2584-5a7c-a04a-59c34dd6c42c | note | Activity - I
62c91b75-1fe0-592c-870c-82fdb212fcf3 | note | By - PE
b4bfcba9-7ebb-50d5-ac19-ccbd0eaf5f97 | section | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
2c7daec9-a3b9-5141-9709-d474c280ddfa | checkpoint | 7.02.01 - Redline Drawings
728b5480-8bce-5e57-8220-4dc597578b1a | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen mark up showing lot numbers and areas stabilised in different days including clear delineation of all joins.
a0629c46-97b8-540a-9ab9-4a0d383f8d3c | note | Standard / Specification - Downer
8ac2a939-d8f9-5b48-a4f1-1467045a83ab | note | Verifying Document - Redlines
c5ca150e-c56c-5888-8abc-110ae84ec185 | note | Frequency - Post construction
e54ebb86-b19f-55bc-a788-af0879150f2b | note | Activity - H
d03de430-9238-5275-83a2-bdcde07e88d8 | note | By - PE
caff110a-8d86-5cd3-adae-88cf9a8da87d | checklist | SYS - ITP - Pavement & Surfacing - Subbase - Rev E (v2) | itp | ITP - Pavement & Surfacing - Subbase - Rev E
3969119e-9d77-5427-b958-ecc82f083c46 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
ec4e551b-3f47-528c-ae6c-fdfb3458be34 | note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence
eb1c5ab0-d958-5aff-9e01-8f56d5db5c3c | note | Standard / Specification - Downer
95e813a5-8719-5ac9-9ed3-db95c88daa4f | note | Verifying Document - Construction Pack
805d2c95-dc1c-508e-8b9e-fbca9c1eeaf6 | note | Frequency - Prior to Works start
fc39fb4d-ffff-5e1f-8d56-399758b18a65 | note | Activity - H
802be262-7e7e-53e8-b8bf-6038d6e34751 | note | By - PE
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
27f3be6b-b818-5263-817f-5ba924480d35 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
1f441f83-2c34-577a-90e0-73818924a2cf | note | Standard / Specification - Downer
a4fa1ba9-6110-5364-ab83-c9684041414a | note | Verifying Document - Survey Records
7fe5d102-a89b-537b-849f-5cc7bf99618c | note | Frequency - Prior to Works start
d378e4fb-1992-5af0-8e29-ab8e511f0e7e | note | Activity - H
ed48a75e-9faa-5783-b481-e3f0f2090547 | note | By - SV
a24a2c58-bf6f-5474-883c-40044bad1fc7 | checkpoint | 3.01.03 - Service Location
07cf3e6e-2226-5ee4-b1f5-8fff7d3c89fe | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
e5694d8a-f45f-52e8-b573-2ce535af9e31 | note | Standard / Specification - Downer
b2970209-fe08-5050-ba93-b0537bd69e94 | note | Verifying Document - Excavation Permit
e872e4d7-566c-548c-8e05-f649772197fa | note | Frequency - Prior to Excavation
0ef56c5b-7c85-56e8-9a7e-aab9f6807218 | note | Activity - H
53f0bb53-59d4-5d30-9a93-b3b481462cec | note | By - SE
0a214a7a-124a-5898-a837-e29e83751df0 | checkpoint | 3.01.04 - Internal Permits
8f9ece01-d727-5876-8560-edbd9d82bcf8 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. if applicable.
a7ee36d2-9b73-5f58-b71b-db5ca41fe4a2 | note | Standard / Specification - Downer
85ad478e-6552-52d0-b8b4-54e1f7ffbc8d | note | Verifying Document - Internal Permits
93d4943e-f796-520a-9124-ecb481319afe | note | Frequency - Prior to activity being undertaken
ea702c86-97c6-5605-ba1e-bfeeb7f387ec | note | Activity - H
a2718418-fc15-5b59-89c6-07251b3f0c0b | note | By - SE
917e2881-0901-542f-ae25-686bf9c47009 | checkpoint | 3.01.05 - External Permits
f23abc2d-c8ee-50ea-854a-9f64a7d9d86a | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc, if applicable.
6b62d5fe-af97-5ca3-b301-bd92f2791dc8 | note | Standard / Specification - Downer
a02559dc-175e-589a-9b8a-8eab68d69cad | note | Verifying Document - External Permits
b2f5d673-8cc4-5dbc-8d75-deccfbe742fe | note | Frequency - Prior to commencment of activity
d3a90524-e3a6-5f9e-b9d3-b83ba77aa7bf | note | Activity - H
13bc7be9-6edd-55c9-a267-e302e9aee166 | note | By - PE
a1302970-0389-558d-b43c-67b14bbfc27a | checkpoint | 3.01.06 - Approved Construction Drawings
f56d4abb-1946-538b-aad6-86aea7955913 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
09117102-46e6-57a9-9743-cdcaf0e4e481 | note | Standard / Specification - Downer
46964b83-84c6-5336-b6bd-922be5cef306 | note | Verifying Document - IFC Drawings
39dfba69-75f7-5742-968e-a4c90dbb0b22 | note | Frequency - Prior to works start
68e4c5de-58e0-5dec-91c6-170e024e015a | note | Activity - H
3d527e69-1c47-5f3d-8273-fc7878a3c156 | note | By - PE
4dd36031-ce9c-52f9-bfbc-d1541a841138 | checkpoint | 3.01.07 - Stabilising Methodology
f31947ca-c372-52b1-9187-bb4248d3254b | note | Acceptance / Conformance Criteria - Written approval of the Engineer with the approval of the methodology
a161a67c-8a7a-5dd1-9557-f02e91f6b027 | note | Standard / Specification - PS - 7.3.3
07fd60c0-fd43-5cf7-befe-31b3417972ce | note | Verifying Document - Correspondence
5f17963d-05de-50a8-9578-9003dcf71a00 | note | Frequency - Prior to stabilisation start
4c607593-a8eb-5c32-8ec8-95b0db6dee42 | note | Activity - HP
b8772278-c47a-56b1-a98c-0284beffbb55 | note | By - ENG
bcc75d59-fda9-5665-870d-6406349e1ed2 | signoff | AUTHORITY HOLDPOINT
9ffb2cc0-a1b6-5e07-aa7c-34ea633a63b0 | checkpoint | 3.01.08 - Acceptance of the SIL layer
f6339289-345f-5f4c-9a10-88376f46e5fd | note | Acceptance / Conformance Criteria - Written approval of the Engineer - All compliant test results for subgrade, SIL, all road crossings, storm water, wastewater, watermain, subsoil/pavement drains and any other activity that has been completed in the pavement area.
02730cba-a67f-5416-abdc-90b5998957c6 | note | Standard / Specification - PS - 4.8.3, Table 4.3
847b87f3-2330-5a62-abcc-ad8b65920f34 | note | Verifying Document - Hold point relesed / Testing reports
683e6528-9871-5c86-b102-a59b4f362661 | note | Frequency - All sections before proceeding to the next layer
c2f09181-52a5-56b6-a1b5-1c437cb54f45 | note | Activity - HP
ad1d82fa-b960-58f5-b406-029832fbcf42 | note | By - ENG
d3949fe3-b334-5e1c-a2b3-f23ab054269d | signoff | AUTHORITY HOLDPOINT
bc43c978-69d8-5f48-8b7f-ecbcce31a7dc | section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65
ca87e1fb-7246-51ad-9189-73e2340ccb26 | checkpoint | 6.02.01 - Sub-base MDD and OMC
4bc5963e-cd2c-51c9-aca5-69592b28e7b2 | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
71cb6c20-295f-57d5-a171-0161932e085a | note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
a63946e0-13fc-5f8f-af3f-dd8702db5ce8 | note | Verifying Document - IANZ Lab Reports
21058093-260c-502c-9a10-4289560be62c | note | Frequency - No less than 1 test every 5,000m³ (in place)
e8b8790c-3ca2-5fdb-89d4-45c8244f3825 | note | Activity - R
3f7f445d-4e23-5bda-9bff-1d2d926e9369 | note | By - PE
70fabdf0-7745-50be-96bf-2ded7dc55eed | checkpoint | 6.02.02 - Plasticity Index
22db6f42-ec9d-5643-90f1-7b79fa348ab3 | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Liquid Limit shall be ≤ 25 when tested
719e890d-d568-55b5-84e6-bed77f0f46a3 | note | Standard / Specification - Table 7.2
78c93c41-abe6-58db-a342-afd7b48c2a61 | note | Verifying Document - IANZ Lab Reports
6c9b5431-1a5a-52bb-9e62-0e81f150c6d6 | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
f59876a0-5a1f-53f6-b4bf-cb2e0bcdacd0 | note | Activity - R
1ced5c1f-5106-5c18-8962-145b62d99b22 | note | By - PE
22886128-c2cb-5f11-b511-007c412fa0ae | checkpoint | 6.02.03 - Clay Index
b8341bd7-673c-5dc2-808a-b5591245a41d | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Plasticity Index shall be ≤ 8 when tested
13969d9f-b85a-5f7a-9aa8-66e1e0edae96 | note | Standard / Specification - Table 7.2
2deb8519-49c2-5487-9cf7-444377be1b25 | note | Verifying Document - IANZ Lab Reports
20980237-258c-5659-ade7-2366ac0b8b3f | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
5cdb0063-1c4f-5b26-af41-f8037bdb887a | note | Activity - R
fd180c27-27ce-546e-80c4-4d43ec441f4b | note | By - PE
39fe01b4-f08b-5b33-9943-aadecfa5826a | checkpoint | 6.02.04 - Sand Equivalent
840c29c2-0a8c-5ea5-ba9e-1cbbf8bf56ed | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Clay Index shall be ≤ 5 when tested
459a0a17-3115-50b1-8574-e577b9fa3289 | note | Standard / Specification - Table 7.2
4931d8f6-9541-5ae3-bcab-bf8298c7c272 | note | Verifying Document - IANZ Lab Reports
527ee89c-1792-57ee-a5a9-287bcfcbc472 | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
5f19806f-af48-5c20-b1eb-99d26cdcd076 | note | Activity - R
ed8cc6f7-ff4c-5eed-9210-4c62bf32bba9 | note | By - PE
4aff0413-9e3c-530c-b97a-0793ec692f9c | checkpoint | 6.02.05 - Particle size distribution
9d8c8e5e-11ce-58a7-860d-c33d6c7859b2 | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1
616c8ede-e9b2-5437-b1f6-ce66bcd2f0e7 | note | Standard / Specification - Table 7.1
bdb504a7-1ca9-50f7-b822-c9b3a4acf4c6 | note | Verifying Document - IANZ Lab Reports
f92c3ee3-0fce-5b0f-8b35-7932831125a2 | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
71e702c3-1afe-5980-aab7-e902f1ec27f2 | note | Activity - R
69ce19e3-2200-5312-b708-210d89c586eb | note | By - PE
e8905abc-1647-5fbc-9fa2-b0958848732e | checkpoint | 6.02.06 - Average Uncompacted Layer Thickness
9570be19-0fe8-57ce-bcb1-ef4816b0e78c | note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
3aa0923e-f1c9-58dc-a8ae-da58cae7c067 | note | Standard / Specification - TNZ B/02: 2005 - 7.3
876ae953-7cdc-56d4-b12f-0969f34eb79e | note | Verifying Document - Survey / Level Checks
7eb6d98c-375e-576e-ac51-7e0c32aeb52e | note | Frequency - 1 test per 20m
1364f684-6351-556e-8189-03544cf0bdf0 | note | Activity - I
15f9afb4-4f6e-561c-9b64-85ec16932a31 | note | By - SV / PE
50dc97be-5c04-59c3-8703-cd318c3ee35e | checkpoint | 6.02.07 - Plateau Density Test
395eae28-4c8d-59bc-bd7b-7283b16b67bb | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
614970bc-9f95-51d2-85d7-240c03166f66 | note | • Testing shall be at OWC.
03cd9565-736a-5c41-b2bb-2c62bef5a03a | note | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
7d062746-9063-552a-8600-70c701e6de9c | note | Standard / Specification - PS - Table 7.2 - 2.3
819a1ad6-5e53-520b-ad5f-c702560be83c | note | Verifying Document - Plateau Density Report
ec31e201-c41b-5fc2-9b67-fefc9467feff | note | Frequency - 5 tests per 10,000m2
21ad2544-ab57-55a5-971e-41a12e355954 | note | Activity - I
80faab0d-83f3-503a-9158-a9a09d8dfaf0 | note | By - PE
3ee4467b-b164-5546-a4a6-7cc3c4ecf208 | checkpoint | 6.02.08 - Sub-basecourse Pavement Layer Compaction
9e8fe53f-a4f1-5780-8ccb-6c86d9016322 | note | Acceptance / Conformance Criteria - Mean Value ≥ 95 Minimum Value ≥ 92
71360f74-312e-57d7-bb04-30fff5aea2e0 | note | Standard / Specification - TNZ B/02: 2005
de23d183-7039-5637-980c-457a089db70b | note | Verifying Document - NDM Report
60c78e68-7cc6-5c38-8fa6-1f1e015f1735 | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
fc9d3184-55ac-5435-a416-d61089d7c36f | note | Activity - I
a514a1b0-5d8e-57ef-b0a0-53b72199740d | note | By - PE
b152466a-921e-56d5-9032-1b468cc0597c | checkpoint | 6.02.09 - Surface shape control
5271a85c-4033-5182-87d5-e949d8805412 | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
7099c8a2-8d24-5440-a12e-deca0db77cbc | note | • Vertical: - 25mm +5mm
ea995418-cd6c-5018-87a7-dbda26d9543b | note | • Cross fall: 0.5% on 2m straight edge
51ab3f3a-0703-53a4-909f-ab0246c7ba52 | note | Standard / Specification - TNZ B/2
bbb26c31-a3d5-5e57-9c1f-0918ac1187c8 | note | Verifying Document - Total station Topo showing levels compared to design
26a05264-4d7b-5c54-8b74-ae3956ac22bd | note | Frequency - Continuous
c70cb08a-ddc3-5280-bbe8-f078b3077f4e | note | Activity - I
8b54b2c0-f2d1-5214-83b0-fdec710c6b66 | note | By - SV / PE
7c9c928b-9d6d-55e2-9057-4eae9a377090 | section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial
6c098115-ed50-5770-83bf-79ab8107d3a0 | checkpoint | 6.03.01 - Stabilization Production Plan
e9831178-47b0-59a6-9d3e-db8fe82d67ba | note | Acceptance / Conformance Criteria - Production plan sent to engineer for review 48 hours prior to stabilising commencing. This is to include all information set out in NZTA B/6 7.2.3.
42ae6479-0812-5f6c-9c07-a74a778776a8 | note | Standard / Specification - NZTA B/6 7.2.3
46a567d6-e788-5ef8-9b53-7728cb226c3d | note | Verifying Document - Correspondence
52a691ee-b7b7-55cf-b940-d4a415e252dd | note | Frequency - 48H hours prior sabilising commencing
e23418a8-3819-5731-b4b1-40b53b1be0dc | note | Activity - HP
c5e2fca2-dd50-5ce1-b220-2d2b1f521bff | note | By - ENG
efaac3d4-313c-53da-9b8a-af70649a58b8 | signoff | AUTHORITY HOLDPOINT
33bc697f-3ee0-5632-94ad-1cc6ea4d8aff | checkpoint | 6.03.02 - Longitudinal Joints
c3da4913-cf3f-5467-a425-e19830da3ced | note | Acceptance / Conformance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by a minimum of 200 mm or half the layer thickness, whichever is the greater.
3187bd79-3bbd-5d8e-8581-e66206fee0b3 | note | Standard / Specification - NZTA B/6 7.5.2
c421fd54-cc40-52cf-8425-3c13eae03934 | note | Verifying Document - Stabilisation Prodution Plan
c55c6d23-9dc7-5f3a-9c97-c1513e529d8f | note | Frequency - 48H hours prior sabilising commencing
e9367a12-81c3-525e-974c-38c03a4f729f | note | Activity - H
0ec96b79-f1b1-53b6-a1ae-d3836cbe0350 | note | By - PE
f2fd84d9-a211-565e-a0e0-957d8630417c | checkpoint | 6.03.03 - Stabilisation trial
e08756e0-d528-5aad-9c69-21fe5f648cf6 | note | Acceptance / Conformance Criteria - A trial shall be conducted on a minimum stabilised area of 2,000m2 to verify the performance of the stabilising operation and finished product prior to full scale production.
0dbbcc25-5157-5beb-9e6a-9e92f6b99aa9 | note | Standard / Specification - PS - 7.3.3
81929707-068f-59b8-89f2-92df889e8a1c | note | Verifying Document - Triall Report
07fa29ac-31f2-5924-b389-c70ec5e9ece2 | note | Frequency - prior to full scale production
5821f127-a9b7-5b6b-b356-c7fec3b1afda | note | Activity - HP
38635240-5a2c-5eff-849f-e19f22cfc73b | note | By - ENG
836a28a7-55e3-5ddb-91a4-e7dccd925e7a | signoff | AUTHORITY HOLDPOINT
c77ae1a3-eb3d-5fdd-85c2-176a01d6eedf | checkpoint | 6.03.04 - Stabilising Equipment
a174ca72-dddc-5558-a278-5236cc481e6e | note | Acceptance / Conformance Criteria - The Contractor shall use stabilising plant purpose built and appropriately adjusted for the in-situ stabilisation of roading aggregates, as opposed to plant designed for soil stabilisation or re-cycling.
b6711173-5d7b-5401-bbb6-9f87711a72ae | note | • The stabiliser drum shall have a straight tooth pattern and the drum speed must be adjustable in real time during stabilisation.
8f6c961c-4b1d-5317-8a01-834092d8eb17 | note | Standard / Specification - PS - 7.3.2
63b65329-56d2-5f94-a4f4-50a223f256ec | note | Verifying Document - Plant Approval
75aecaf6-730c-55fe-8a0d-904f68457493 | note | Frequency - Prior to works
facb13e7-f88e-5306-9aaf-1a4193048ed3 | note | Activity - H
c36b7a69-c597-5379-9bf9-b7dc0c7dcbff | note | By - PE
65357786-cd6f-5367-a375-639ab3f50f85 | checkpoint | 6.03.05 - Stabilising Supervisor
ab15ab4d-6a1b-5ad6-a23e-5d89fec1d1a1 | note | Acceptance / Conformance Criteria - During stabilisation the Contractor shall employ a suitably experienced person to continuously walk behind the stabiliser to assess the uniformity of the mixture and water distribution and to check the stabilisation depth every 100m.
9c9c2035-4b24-52e8-9403-393b2235ccfa | note | Standard / Specification - PS - 7.3.2
34656b4f-1439-5386-9ebc-007176f0ccea | note | Verifying Document - Supervisor Approval
23985ea7-a28f-521e-b69b-259ca26e5f2b | note | Frequency - Prior to works
6e66a8ad-9649-5ff7-b952-feb4cc32cc56 | note | Activity - H
4696b9df-831d-5d97-bb0b-f320ba34c6f6 | note | By - PE
b2e16153-370f-553c-9fbe-4d6c94095131 | checkpoint | 6.03.06 - Before Stabilisation Surface shape control, layer thickness
563a3feb-7b54-525e-8eac-b1d9487bbfea | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
9d1b46f2-1d5a-5d76-bec6-2b88b1c5133d | note | • Vertical: - 25mm +5mm
52acc506-7c4e-5f5e-98cb-79bd2fa11070 | note | • Cross fall: 0.5% on 2m straight edge
a8362e42-1666-5b47-b72b-f781c161a505 | note | Standard / Specification - TNZ B/2
eec71e29-c07f-5bac-89cf-25793285c630 | note | Verifying Document - Total station Topo showing levels compared to design
bad201eb-bd3b-55fd-b978-1ec43fd60bc2 | note | Frequency - 1 test per 20m
bd9c102d-880a-5230-bf6a-5691f03c6130 | note | Activity - I
3685d3c4-54d2-53ae-b6e5-578e5ceded3c | note | By - SV / PE
61811b90-1233-52f7-81cc-b19f731dbfcd | checkpoint | 6.03.07 - Average Uncompacted Layer Thickness
43ffede8-eb80-524b-a01a-db135ed8ba8d | note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
c3046233-92bc-58b5-8195-b158fbcc75e7 | note | Standard / Specification - TNZ B/02: 2005 - 7.3
b259e3ac-c1de-5106-a7a3-83e9e9831aef | note | Verifying Document - Survey / Level Checks
26dc4776-c0f9-52c0-af0c-1509545d7f62 | note | Frequency - 1 test per 20m
b5bf0d7d-85a3-59cb-a307-090dab4d6d7e | note | Activity - I
6473d183-8207-5544-bafe-0c54b5eb607b | note | By - SV / PE
0f3c4886-911f-570e-9380-945bb931b659 | checkpoint | 6.03.08 - Pre Stabilisation Compaction
6f7bd7dc-cdae-5a56-9c2d-ca632a2e7753 | note | Acceptance / Conformance Criteria - The full thickness of the layer to be modified shall be compacted between Value ≥ 95% and Minimum Value ≥ 90% Prior to stabilisation, this will be reviewed following the stabilising trial and adjusted to suit and the updated target shall be added after the stabilising trail. DN1205-DOW-RFI-0043.01
465d47a0-b711-5cb1-96c4-f6d85a1b465a | note | Standard / Specification - PS - 7.3.2
7fe17492-23f7-501f-aa40-fcdb349e7514 | note | Verifying Document - IANZ NDMS
1297e1e0-3a45-5d69-b973-55da0fde25a0 | note | Frequency - Min 5 Tests per lot 1000m2 max lot size (Prior to stabilisation)
e6d1b948-87ad-5b28-98e5-bc82d3f2d156 | note | Activity - I
b2f3be24-86b7-57a3-aaf5-1d27e822bdd7 | note | By - PE
03cc060f-e525-5da1-b4a4-927a2c816637 | checkpoint | 6.03.09 - Pre Stabilisation Crossfall
cff7e8a0-7b7c-5a63-83ff-5ae38d022a53 | note | Acceptance / Conformance Criteria - Before stabilisation the Contractor shall check the crossfall by string line to confirm compliance with the design.
610f8fec-3aea-51db-bfa6-bf12ba54f71a | note | Standard / Specification - PS - 7.3.2
aca61598-044e-5199-afcd-e74ff6325165 | note | Verifying Document - Total station Topo showing levels compared to design
7d376523-ba8a-5097-8002-2e7f76bf4875 | note | Frequency - 1 test per 20m Prior to stabilisation
4516ac7a-7ea7-5e79-b46b-aeba1ccaa920 | note | Activity - I
6be639a0-0a72-5493-afba-e5ebedcc5d2d | note | By - SV / PE
dd46457d-0574-5b56-b7ac-f21afadaed60 | checkpoint | 6.03.10 - Stabilising Visual appearance
998a76a4-7c5a-5d3b-a8c8-9870c0245259 | note | Acceptance / Conformance Criteria - The stabiliser shall produce a uniform particle size distribution behind the stabiliser, both laterally, vertically and longitudinally and produce minimal break down of the coarse aggregate particles during mixing.
17a111e0-7eb4-57fd-bb60-84b1d9c9cbc4 | note | Standard / Specification - PS - 7.3.2
6839efa3-7b64-53d1-86b2-740fe4b8ebeb | note | Verifying Document - Site Notes
1869331e-c80c-5598-8b8c-6617b50b05ff | note | Frequency - every 100m
7389bc60-0085-59a0-83c9-2282da0bb60d | note | Activity - I
355db957-3967-5ecd-97f7-25887562ce3a | note | By - PE
6eed5d81-e5b0-55cf-bece-401f93ecd9b8 | checkpoint | 6.03.11 - Cement Mat Test / Spread Rate
76919ea6-ce78-5c8c-9508-eee14727b092 | note | Acceptance / Conformance Criteria - The stabilising agent shall be uniformly spread at the specified application rate across the pavement to Within ±0.5 kg/m2 of the specified rate
4ccb5c6e-e888-5bfb-8e21-4d805f05ea26 | note | Standard / Specification - Table 7.2
b90dc178-c767-52a8-a71e-488d65d88a23 | note | Verifying Document - Stab. Sheet
9f414802-aeb1-5406-92a7-ad6f8f64f2dd | note | Frequency - One per each run of cement spreading, until the Contractor can demonstrate consistency in cement spreading and/or demonstrate accuracy of on-board computer equipment calibrated/compared against weighing cement mats.
f542fe89-663f-5869-b318-5f8c7a3a8add | note | • Upon successful demonstration of this, the 1 per 500m2 minimum can applya
62cc9b71-67cb-5d36-a424-b8e8a822c60f | note | Activity - I
25135d59-b80a-5e1a-86e3-7f7007b18bab | note | By - PE
58788175-0c81-55f7-8c9c-122dc5a74310 | checkpoint | 6.03.12 - Cement Average usage test
06e0f300-76b8-535f-a655-00c6988371c9 | note | Acceptance / Conformance Criteria - Compare tonnes used (from delivery docket) with measured area Within ±2.5 % of the specified rate
08836960-1982-5462-b01b-a7b79a1a9a62 | note | Standard / Specification - TNZ B6
5577f49f-f312-5dfc-93fd-90890480cc65 | note | Verifying Document - Stab. Sheet / Delivery Doc.
56bafdfd-c441-5f6e-8935-2ae508c5c46c | note | Frequency - Upon emptying the spreader and bulk tanker
03f51aed-e2ec-5730-9e23-bb59d90303bd | note | Activity - R
ba98f297-2534-5c8e-9905-3ee4e0aed89e | note | By - SE
8dd5c234-a389-5dfe-8991-b7486bab77cb | checkpoint | 6.03.13 - Control of cut depth
ce798d42-6fea-5ed8-9fa4-7953f2de7e91 | note | Acceptance / Conformance Criteria - Maximum variation from the specified depth of cut is –5 mm and +15 mm. Without picking up sand from SIL
0d545cb3-19ca-551f-99b2-10f878522509 | note | Standard / Specification - TNZ B6
f50302f5-9336-5550-b886-eb591a3d1715 | note | Verifying Document - Stab. Sheet
9d05222c-25f8-5924-ae26-1b4dc85e1c8f | note | Frequency - First check of cut depth should be immediately behind the stabiliser at the start of each run, then again every 200m, or as requested by the Engineer
d1660d76-db41-5c8b-b632-25bc504b33b3 | note | Activity - R
b0901765-faf3-567d-bde0-c733dfb61059 | note | By - SE
19eac722-f22d-5929-8126-b167f6613939 | checkpoint | 6.03.14 - Plateau Density Test
d1a0cf10-f2f8-5613-8b93-b8107c2cb304 | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
71842105-60c2-5587-b4bb-6eb3f62f6389 | note | • Testing shall be at OWC.
89b5526a-a443-5577-ba5c-c00445ee5784 | note | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
69bcb218-106c-5fdf-b8df-84644ed7f1de | note | Standard / Specification - PS - Table 7.2 - 2.4
8f92fb7f-f8ba-5542-afaa-19692161a505 | note | Verifying Document - Plateau Density Report
0e69e2c0-eec9-5031-9972-d5f0b3a84fdc | note | Frequency - 5 tests per 10,000m2
db77b510-73b1-56e3-9b66-265e5d55626d | note | Activity - I
f746d0d8-3425-5d24-ba8b-9e8cddbf8144 | note | By - PE
2ee5ae31-1ce2-5318-b785-95fce0922ca9 | checkpoint | 6.03.15 - Particle size distribution behind stabilizer (Wet Sieve)
383e3b43-141d-57dc-ac27-0a1fbef0fe50 | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1. A Wet sieve analysis will be completed within 4 hours after stabilizing
dbbf8b52-48c3-5a65-a471-76774bafb6bb | note | Standard / Specification - NZS 4407: 1991 Test 3.8.1 Standard Method by Wet Sieving
584c1ec8-a297-541b-bdab-57da71f20e59 | note | Verifying Document - IANZ Lab Reports
1e01bb28-8a81-5739-84db-19f894d76d5d | note | Frequency - 3 samples bag per stabilise day post hoe
cb473351-9320-51d2-b9a1-5415dc2edaf0 | note | Activity - I
46ac7a5b-489e-5c61-9a81-a094103ee355 | note | By - PE
3744d9ba-d8e1-5383-9d2c-5335ed0cf31b | checkpoint | 6.03.16 - Mixed material testing (ITS)
ef0988cd-8048-5ec1-a1fb-011cc4af972c | note | Acceptance / Conformance Criteria - During mixing, the contractor shall take a pair of representative samples behind the mixing plant per lot or at a minimum of 2 pairs of representative samples per day.
7bbe5d1b-3f5a-5798-992c-00376e3df314 | note | • These samples shall be placed in a sealed plastic bag and cured for 1 hour before compacting into a mould and testing the indirect tensile strength (ITS) of the mixed material according to NZTA T/19
28a40525-2abb-549d-ad9a-a76a44342996 | note | Standard / Specification - TNZ B6 7.5
b2a08e69-aefb-502f-9667-60a10a79052e | note | Verifying Document - Test Results
98e935ed-c18f-5ac9-807c-0b85a7c17b7d | note | Frequency - 2 tests per stabilise day
4a43f0c5-a6aa-5816-a174-8dad3fc58c70 | note | Activity - R
2d4c1bcd-af9d-592d-9721-35e530c03d3f | note | By - PE
9b3b1023-6a86-5a49-9ba8-c3eceb03ddce | checkpoint | 6.03.17 - NDM Water correction
990ab85d-0a87-598e-b9f1-a7a68a6e620a | note | Acceptance / Conformance Criteria - Daily Laboratory water content tests shall be carried out on samples taken and used to correct the NDM measured dry density.
de4e8571-20b6-5a14-9d53-baa31c703993 | note | • Will get the Moisture correction factor from the Plateau report itself. That is the difference between the Moisture reading on the NDM vs the actual moisture when dried in the oven.
0d089788-33e3-5066-aa7c-135fd94ff095 | note | Standard / Specification - NZS 4407
3071916f-187f-5def-b4e9-22f4955e0ded | note | Verifying Document - Corrected NDM Results
4cc4a890-9e9e-5ebb-92e1-7c4a53685685 | note | Frequency - Per Stabilise day
0d9ef0e8-6cc6-5c94-a284-965d465bde6e | note | Activity - R
82279123-d95f-5b65-af9f-12a326c2b733 | note | By - PE
189483f5-5c2e-5d24-8c0e-4762ac1f0541 | checkpoint | 6.03.18 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
240233fa-df7e-566e-855f-f0d745ebb023 | note | Acceptance / Conformance Criteria - The sub-base compaction requirements in Table 2 of B/6 shall be replaced with a Mean Value ≥ 98% and Minimum Value ≥ 95%. - Direct Transmission
cb3cedb3-af0c-5ab5-926a-e09de0acd80f | note | Standard / Specification - PS - 7.3.2
b54eaec6-cfb5-501b-94fe-32483a79da38 | note | Verifying Document - IANZ Lab Reports
073fd872-05d3-5add-bcef-22bb304d219a | note | Frequency - Min 5 Tests per lot 1000m2, minimum 7 days after stab.
0d5458e2-1d29-5b8a-9fc0-73cbc1390d82 | note | Activity - I
be609c1b-c730-5a5d-9331-f1805b8f2002 | note | By - PE
4eafc89d-3d95-5e4e-b4f9-e4c39a2227af | checkpoint | 6.03.19 - Post Stabilisation Surface shape control, layer thickness
b0e5eaa7-9aa0-56a9-a866-6dcdd20ff39e | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
229c03ae-40f8-5fa5-9dad-7a3c83cc7554 | note | • Vertical: - 5mm +10mm
d405757b-42ec-5e57-93dd-b09d6f0a6917 | note | • Cross fall: 0.5% on 2m straight edge
404e5815-0714-5900-94a5-df1ebd722e10 | note | Standard / Specification - TNZ B/2
1cc3008b-3838-5deb-b0b6-70bc233ba267 | note | Verifying Document - Total station Topo showing levels compared to design
036f6297-a2f4-5805-9740-38c29acec8b1 | note | Frequency - 1 test per 20m
8c7b77e5-dd28-5d52-ba12-5bdd29328047 | note | Activity - I
680c3d1d-5ea8-5211-8945-472116ab03e0 | note | By - SV / PE
72280022-fd87-5882-b3d4-4682359acdc4 | checkpoint | 6.03.20 - Protection, Curing and Maintenance before Overlaying
d476d473-f525-5d01-867f-f2faa131a6aa | note | Acceptance / Conformance Criteria - The Contractor shall protect, maintain and cure the completed cement bound sub-base until the next layer is applied. Besides construction traffic required for the above curing no other construction traffic shall be permitted onto the layer within 7 days of stabilisation
8ab3c95e-0340-54bb-b616-56fe2bd76ff1 | note | Standard / Specification - TNZ B6 - 7.8
03475675-6d72-5fc3-9161-eaf51e553853 | note | Verifying Document - Site Notes
3807fd43-1c09-53a6-ba7a-374d49bdb964 | note | Frequency - For 7 days after stabilisation / Photos
e6932548-f213-5348-8570-33cf2030e6b6 | note | Activity - R
53bd01e6-24dd-5959-a3ac-c5a36ea4ff6b | note | By - PE
80726abb-7f00-5a67-ad5c-4f9961a101e8 | checkpoint | 6.03.21 - Benkelman Beam
28184ac9-114c-5685-bb7d-1142a911fc4a | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer.
795c713c-4e9f-5ef7-b471-3341fdcd79d4 | note | • Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY
aa986cfe-3d53-5204-b89e-2cc347065016 | note | Standard / Specification - PS - 7.3.2
129cc3b7-071e-5882-8f23-62f271e39754 | note | Verifying Document - Benkelman Beam Report
fcf841d3-46f0-5f72-adc9-738ca5df7660 | note | Frequency - Every 10m of each lane – staggered between left and right wheel path.
4db6bf4b-efbb-5b7b-852f-0c1d1513e683 | note | Activity - R
61494ce3-d9ab-5ef3-96dc-037932673c7a | note | By - SE
00ccd532-6cdc-5994-8bfb-114564ace123 | checkpoint | 6.03.22 - MDD / OMC / SD
6cb0d5d2-2347-50ff-83fb-1767f7e6259f | note | Acceptance / Conformance Criteria - Post hoe, stabilised MDD, OMC, and SD. 1 test per 2000m² or a days work whichever gives the greater number of testing.
2324b341-3fca-550c-be2d-f2fee1891bb6 | note | Standard / Specification - NZS 4402:1986, Test 4.1.3
0fcd1e05-a5ef-57ed-86ba-d8eb03e1c467 | note | Verifying Document - Lab Report
4ab74e9c-0267-5baf-9744-f76545b6797e | note | Frequency - 1 test per 2000m² or a days work whichever gives the greater number of testing.
a030ca09-717b-586f-a8e0-261f9cee5ff1 | note | Activity - I
fd20476b-574f-57f9-b4af-d031ba892c66 | note | By - PE
ba7d06af-c7af-5c9d-8ab4-2e3c21a61daf | checkpoint | 6.03.23 - Sub-base stabilisation trial
df6deb4d-1c5a-5968-baa6-f0e980e4f308 | note | Acceptance / Conformance Criteria - After the sub-base stabilisation trial, prior to proceeding with further stabilisation.
edd0ff47-8205-5183-8180-288e0827fb8e | note | Standard / Specification - PS - 2.2.16
86b78705-c8c2-5ae6-93d4-6792aab8fd7f | note | Verifying Document - Hold Point Release
fa0ca9ec-cd50-5ced-b603-ed26108d19be | note | Frequency - Min 48h Notice
09dbfdef-8287-50c0-8ebe-7b9a88336a52 | note | Activity - HP
be3ef2f4-f4c4-5cf2-af4a-7a7c41f76645 | note | By - ENG
944ea1fd-b7c9-5949-95b5-51c9f13d6c6b | signoff | AUTHORITY HOLDPOINT
3ed998ef-a740-59b5-a205-c17d1ea4ae1e | section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base
bfa46ea3-f62a-522a-aeaa-762b5defdaf1 | checkpoint | 6.04.01 - Stabilization Production Plan
e331197a-079e-548b-ae21-38202960f70f | note | Acceptance / Conformance Criteria - Production plan sent to engineer for review 48 hours prior to stabilising commencing. This is to include all information set out in NZTA B/6 7.2.3.
3bd09bd0-1b02-5865-b251-d7e3000bf3f3 | note | Standard / Specification - NZTA B/6 7.2.3
e440d32f-4a97-5f6c-b9c0-8aa4e04d873f | note | Verifying Document - Correspondence
7d61d0f9-37f1-5f53-8b90-89bcb80b5b51 | note | Frequency - 48H hours prior sabilising commencing
b149cbb1-8acb-518a-94f1-e7d1a3574902 | note | Activity - HP
60f2c249-9926-5512-8191-b0ae8e066099 | note | By - ENG
e4ed9518-8669-550c-8d69-a36a5a98261d | signoff | AUTHORITY HOLDPOINT
718a330a-7558-52f6-be9b-f238816a905a | checkpoint | 6.04.02 - Longitudinal Joints
4ad532f8-b83a-5298-9bfc-00106a8809d9 | note | Acceptance / Conformance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by a minimum of 200 mm or half the layer thickness, whichever is the greater.
3d84dc43-e313-5471-8481-2da0e196ee05 | note | Standard / Specification - NZTA B/6 7.5.2
59d1a76d-ca94-54d5-91e7-3ffac84d1a5a | note | Verifying Document - Stabilisation Prodution Plan
2eee2feb-131e-5701-8cf4-a9c2975247f7 | note | Frequency - 48H hours prior sabilising commencing
e0dcba3f-d644-5e77-8487-82e72f688b3f | note | Activity - H
7a0901de-7235-5f80-9c0b-cf437a8c3e99 | note | By - PE
3057a053-0fa8-5141-99e1-8805c8143030 | checkpoint | 6.04.03 - Stabilising Equipment
a3fac771-cff3-5313-a05f-011029358c19 | note | Acceptance / Conformance Criteria - The Contractor shall use stabilising plant purpose built and appropriately adjusted for the in-situ stabilisation of roading aggregates, as opposed to plant designed for soil stabilisation or re-cycling.
c1cb7dbd-f209-5e4f-9a1a-261d4589428a | note | • The stabiliser drum shall have a straight tooth pattern and the drum speed must be adjustable in real time during stabilisation.
9fffda08-b991-58f9-937e-8b4c35cc9289 | note | Standard / Specification - PS - 7.3.2
e9358d44-4b4e-568a-96b3-4d97c22c9276 | note | Verifying Document - Plant Approval
1c0b01a4-3a75-52e8-a978-619581de7785 | note | Frequency - Prior to works
a3f7c09a-10a0-5bf0-b435-3e9e719ef9d8 | note | Activity - H
82be9b68-996c-5463-8128-ace8bb528401 | note | By - PE
d10c1293-8308-5402-8f5a-943d59292a90 | checkpoint | 6.04.04 - Stabilising Supervisor
2159ee00-e8d7-55f2-8434-e4fff7bc6d67 | note | Acceptance / Conformance Criteria - During stabilisation the Contractor shall employ a suitably experienced person to continuously walk behind the stabiliser to assess the uniformity of the mixture and water distribution and to check the stabilisation depth every 100m.
1f229947-cb75-5935-9dc8-34ada7b5f79d | note | Standard / Specification - PS - 7.3.2
9ac7d520-98ae-5a19-b8d4-fc2d7d130664 | note | Verifying Document - Supervisor Approval
e0da6256-f3d9-51ac-a068-23477a1df678 | note | Frequency - Prior to works
3862352b-5487-5229-a277-f68d34df474e | note | Activity - H
e51cdc71-f085-5d2f-87bc-8bc4cb6f3245 | note | By - PE
1c51f95a-b88f-562b-b314-9008bea93499 | checkpoint | 6.04.05 - Before Stabilisation Surface shape control, layer thickness
ad7d8450-019d-5924-91fc-7f75792e2c7c | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
61e696f0-d4d9-5a31-9843-c4b2ad91151c | note | • Vertical: - 25mm +5mm
ace72e05-4bb7-50b8-aa59-f9be03ae084a | note | • Cross fall: 0.5% on 2m straight edge
840a0e0a-4cdd-56a3-bcc3-951064a43a04 | note | Standard / Specification - TNZ B/2
085082f9-b471-5e86-8024-d53bc0443173 | note | Verifying Document - String sheet
a7010fcd-99bc-5547-bf29-6f0234e0d49f | note | Frequency - 1 test per 20m
967f5c59-aeb8-5789-854f-4450c243c53f | note | Activity - I
722bd66e-759d-58da-ba7b-a1506b86e6d3 | note | By - SV / PE
0d6f6583-baee-5c8d-8dea-ee479453f289 | checkpoint | 6.04.06 - Average Uncompacted Layer Thickness
e52c36b8-1c0c-5cbe-9548-87cca371bf06 | note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
c51b15cc-7302-5ff9-a8c7-3bf668d8d187 | note | Standard / Specification - TNZ B/02: 2005 - 7.3
c9c05c81-b8ec-5b76-bb23-c8a85c4fb760 | note | Verifying Document - Survey / Level Checks
7818a860-08a3-5f88-85b8-68186532a008 | note | Frequency - 1 test per 20m
90023c98-d614-58fc-8362-aba793ca8138 | note | Activity - I
0449a779-ebe7-5529-b8bf-51786bb11e48 | note | By - SV / PE
917f88ba-1bf1-5687-b499-860c1cb7ca16 | checkpoint | 6.04.07 - Pre Stabilisation Compaction
86c30ff3-ab07-5fd8-b80d-4950fd4af9e5 | note | Acceptance / Conformance Criteria - The full thickness of the layer to be modified shall be compacted between Value ≥ 95% and Minimum Value ≥ 90% Prior to stabilisation, this will be reviewed following the stabilising trial and adjusted to suit and the updated target shall be added after the stabilising trail. DN1205-DOW-RFI-0043.01
b281908b-351e-56b9-b98d-270c663c7417 | note | Standard / Specification - TNZ B/02: 2005
7358af75-1748-56aa-aad2-30dfa72dbad9 | note | Verifying Document - IANZ NDMS
b612d03e-5e33-55a7-afd7-d53b0fb4aeae | note | Frequency - Min 5 Tests per lot 1000m2 max lot size (Prior to stabilisation)
f90a1ca2-f2a4-572f-a21c-f53ddf5e2b35 | note | Activity - I
4c6ead81-0fa9-5ed1-acda-a0edcf7cc443 | note | By - PE
609cd901-d33f-51ea-8bf0-2ac755e5ea9a | checkpoint | 6.04.08 - Pre Stabilisation Crossfall
5712cd5c-3966-5227-b2ba-7abd955dd93a | note | Acceptance / Conformance Criteria - Before stabilisation the Contractor shall check the crossfall by string line to confirm compliance with the design.
a4b9acab-25d7-53b7-9392-5b3728bc68b5 | note | Standard / Specification - PS - 7.3.2
cad94b7b-e6aa-55f1-a7c6-c3377391eae4 | note | Verifying Document - Total station Topo showing levels compared to design
b3e4d679-7713-582b-baf3-e31de68257ae | note | Frequency - 1 test per 20m Prior to stabilisation
355afcca-2dff-5693-97b5-7a9f71770b1e | note | Activity - I
563ccdf6-0817-5fb3-b46f-18abe37cd0a2 | note | By - SV / PE
c5459efa-5597-5eb0-a767-a817864c6611 | checkpoint | 6.04.09 - Stabilising Visual appearance
800f5c03-3bf2-52b5-83b8-0c37648a0a1f | note | Acceptance / Conformance Criteria - The stabiliser shall produce a uniform particle size distribution behind the stabiliser, both laterally, vertically and longitudinally and produce minimal break down of the coarse aggregate particles during mixing.
4387fdc8-5025-5848-bb4c-4bb10ef49da4 | note | Standard / Specification - PS - 7.3.2
0e773199-5e6f-55ca-a1a8-6195084d55e4 | note | Verifying Document - Site Notes
95a08c3f-ac10-537d-9357-9509e61bd11b | note | Frequency - every 100m
1835d486-50b7-50ab-b6fc-1b90a2bb5a41 | note | Activity - I
e5a553a7-676b-52c6-a86f-1339ffab2e24 | note | By - PE
7fa669a4-d877-59f3-a991-2960916f29d5 | checkpoint | 6.04.10 - Cement Mat Test
1dd3baff-ebe6-52d3-aab5-5a71f6db452f | note | Acceptance / Conformance Criteria - The stabilising agent shall be uniformly spread at the specified application rate across the pavement to Within ±0.5 kg/m2 of the specified rate
6bb41df6-8e09-5cc1-90da-7d93b76d80ff | note | Standard / Specification - TNZ B6
4bc48b69-7d17-59bc-ba33-4bc072b1c274 | note | Verifying Document - Site Notes
caf22b2e-9132-5974-89dd-84763a71e332 | note | Frequency - One per each run of cement spreading, until the Contractor can demonstrate consistency in cement spreading and/or demonstrate accuracy of on-board computer equipment calibrated/compared against weighing cement mats.
99c42675-6204-5c45-bb1f-3323cfe3b8f1 | note | • Upon successful demonstration of this, the 1 per 500m2 minimum can apply
70fce067-560c-566d-981b-11d8561156bd | note | Activity - R
5950ce26-bd3d-56bb-822c-985257c79146 | note | By - SE
0fabe193-9a41-532d-98d6-aa037b156014 | checkpoint | 6.04.11 - Cement Average usage test
f03fe172-618a-58c5-ba9a-e9aac16b5aac | note | Acceptance / Conformance Criteria - Compare tonnes used (from delivery docket) with measured area Within ±2.5 % of the specified rate
66092715-822b-5410-899b-b687652907bc | note | Standard / Specification - TNZ B6
364975bb-4818-5864-9a07-e76bebf48b94 | note | Verifying Document - Site Notes
c1caace8-c5a5-51f3-84cf-106207d1d6c0 | note | Frequency - Upon emptying the spreader and bulk tanker
74ddba70-549d-5f7b-86e0-244b166f6bf9 | note | Activity - R
a661758e-3f66-5cb6-a729-d11cccc9db0d | note | By - SE
74caf95c-5000-5bc8-b4b2-04774c703212 | checkpoint | 6.04.12 - Maintain OMC during stabilising
1dcc992d-d8a9-5d5d-b4ae-493ee61eebe9 | note | Acceptance / Conformance Criteria - The water content during compaction shall be in the range of 90% to 100% of the material’s optimum water content by NDM
e6917687-c03e-537f-a930-be6f46d42a91 | note | Standard / Specification - TNZ B6
2f500fe9-6514-527e-af94-281fb398a558 | note | Verifying Document - Site Notes
cf79c2e8-1985-50b6-81a9-6830fc4aa25d | note | Frequency - Continuous
85cb0c5f-0d79-5664-b138-7ddd2515143b | note | Activity - R
18add451-e01b-5089-a807-b1c283dabb7f | note | By - SE
7b488497-b6e3-515a-a2cd-a6fa3fd2f415 | checkpoint | 6.04.13 - Control of cut depth
9ef1cbcf-2090-580f-bd4e-b5a66fdf4333 | note | Acceptance / Conformance Criteria - Maximum variation from the specified depth of cut is –5 mm and +15 mm.
68e9f95f-0f6a-5a2d-86f8-451bb17e3db9 | note | Standard / Specification - TNZ B6
b3b3732c-1733-5223-8224-549b9db4b687 | note | Verifying Document - Site Notes
23ee10d2-55ce-55b5-8ed2-fdaa14d17904 | note | Frequency - First check of cut depth should be immediately behind the stabiliser at the start of each run, then again every 200m, or as requested by the Engineer
2555ffc8-798f-5f24-9f0e-affa62653877 | note | Activity - R
06b56834-3a3e-5597-ba9f-d39df45fa7d6 | note | By - SE
a7d56f3a-97b2-545b-8bfb-724ae17d31c5 | checkpoint | 6.04.14 - Mixed material testing (ITS)
0e12b5a9-cdeb-5ed7-b6e9-e89caf02e02c | note | Acceptance / Conformance Criteria - During mixing, the contractor shall take a pair of representative samples behind the mixing plant per lot or at a minimum of 2 pairs of representative samples per day.
c77ba25c-c214-51ab-8c42-7d7ceeb8991b | note | • These samples shall be placed in a sealed plastic bag and cured for 1 hour before compacting into a mould and testing the indirect tensile strength (ITS) of the mixed material according to NZTA T/19
3dc5cac6-b594-528b-b622-fb2b1caa9974 | note | Standard / Specification - TNZ B6 7.5
2b6f08fc-fd58-5f31-93ff-0063cf5b065d | note | Verifying Document - Test Results
0ce12f6b-032c-54c7-91b7-f9376ff7e092 | note | Frequency - 2 pairs of representative samples per day
4cefa690-ca8a-5db4-908f-95a89c3f60f8 | note | Activity - R
e3635531-3e0e-572b-a048-05b9a2869ef1 | note | By - PE
3cedef64-08d4-5b77-aec2-06e0043b20c5 | checkpoint | 6.04.15 - Particle size distribution behind stabilizer (Wet Sieve)
61f69f7b-99a8-52d9-82bd-d783d7cb2661 | note | Acceptance / Conformance Criteria - A Wet sieve analysis will be completed within 4 hours after stabilizing, and consist of a minimum of 3 sample bags per lot.
06e40bbc-b1ab-5cdf-a1fd-3c06bfd40603 | note | Standard / Specification - TNZ B6 7.5
b69c7454-ce52-5c10-8e24-9f7439fd1402 | note | Verifying Document - Test Results
962723f2-30f9-5bbd-be28-18d2a8bf284b | note | Frequency - 3 sample bags per lot.
1031727c-b9ad-5b8a-9d40-3b9b93b1691e | note | Activity - R
a8eb847b-b380-5659-a333-b5520289437c | note | By - PE
d62ad979-e997-5694-a31c-92d3522dc172 | checkpoint | 6.04.16 - Plateau Density Test
30d25dbe-db72-5f3a-bdaa-fff0ea8ef7fe | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
7e553060-7e2c-5c01-a28c-e650d27b2867 | note | • Testing shall be at OWC.
81eedbf7-4933-541d-ba37-561ba28e0009 | note | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
8692cc05-5985-58e8-a913-9de719d06995 | note | Standard / Specification - PS - Table 7.2 - 2.3
e55cf95c-d13b-5e91-97c5-beb7b9dc5994 | note | Verifying Document - Plateau Density Report
54a1ddfe-8386-5843-abed-98c8c2ece050 | note | Frequency - 5 tests per 10,000m2
9eac50a7-a916-5ef4-8e31-dd9400b981ba | note | Activity - I
146ca572-8057-5163-a5e2-4776c54e3ec1 | note | By - PE
5fce28a7-9260-5974-9b51-6a9f0890352a | checkpoint | 6.04.17 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
b6ac8401-a08d-55c9-9e92-b9374e3876cf | note | Acceptance / Conformance Criteria - The sub-base compaction requirements in Table 2 of B/6 shall be replaced with a Mean Value ≥ 98% and Minimum Value ≥ 95%. - Direct transmission
d5306be5-b743-514c-9fa7-4590f2e9fa5c | note | Standard / Specification - PS - 7.3.2
c0a142d5-833f-58bb-ae99-d595abe1f3d6 | note | Verifying Document - IANZ NDMS
34d12926-5e10-5c21-8067-d0092dbdd36f | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
d5994b74-2ca4-5c1a-8012-ed6062e29225 | note | Activity - I
94ea3ed2-0629-5e23-8cdd-5a0d599186ba | note | By - PE
4aa55dcd-a656-5a26-8180-ba5534462e9c | checkpoint | 6.04.18 - NDM Water correction
772c704b-f01a-50fe-9dc2-b3d10440cb5e | note | Acceptance / Conformance Criteria - Daily Laboratory water content tests shall be carried out on samples taken and used to correct the NDM measured dry density
835a86f9-8720-5ac8-8b07-18b667fa08b3 | note | Standard / Specification - NZS 4407
c9fa9fbf-9f3c-5dc3-b430-e866ab97feb9 | note | Verifying Document - Corrected NDM Results
ff40fbba-7239-516a-a3bb-212ccac8d49d | note | Frequency - Per Stabilise day
cdc78ed1-88c7-52df-8c47-87c86bfad990 | note | Activity - R
e2852971-2b16-55ac-a09e-dfb29eeb8819 | note | By - PE
ba631b52-5dc2-5c4a-87ff-800c5e357854 | checkpoint | 6.04.19 - Post Stabilisation Surface shape control, layer thickness
df5e37ae-acca-5b4f-a215-0166a8723139 | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
fc83da38-f1d5-58fb-a5ec-5eab04a9de4f | note | • Vertical: - 5mm +10mm
6331826f-59e0-57bf-96f4-32ef680715bd | note | • Cross fall: 0.5% on 2m straight edge
411545d9-66c0-51e8-8401-b1d8e0c2e4ad | note | Standard / Specification - TNZ B6 8.2
6d3f906e-4a39-5372-b3f0-0493f02f27a6 | note | Verifying Document - Total station Topo showing levels compared to design
7e124d93-aad0-5922-bdad-4b41e965d28b | note | Frequency - Continuous
7e02d4e2-617f-53b0-bcb6-d3777b20e4e9 | note | Activity - R
f22c2999-b75b-53ec-91bc-05bad9755c4e | note | By - SV / PE
eeb24f51-2626-5cc0-a95a-e896cb9f7dc9 | checkpoint | 6.04.20 - Protection, Curing and Maintenance before Overlaying
871102c7-020c-5463-a83d-7991e732abfa | note | Acceptance / Conformance Criteria - The Contractor shall protect, maintain and cure the completed cement bound sub-base until the next layer is applied.
6035c99a-af4b-5b7c-b19a-cfe7de24a223 | note | • Besides construction traffic required for the above curing no other construction traffic shall be permitted onto the layer within 7 days of stabilisation
d4787fb0-ea59-5912-805f-68e21e628f69 | note | Standard / Specification - TNZ B6 - 7.8
ce3d3d52-2855-5b32-a747-c1ae3e37e793 | note | Verifying Document - Site Notes with photos
611a5d3b-62d9-5e71-83a1-8d34b8c015c0 | note | Frequency - For 7 days after stabilisation
62061290-a9e8-54c6-9458-aa077ffd4cd1 | note | Activity - R
1f8753c5-7423-5a59-b6c2-8fb74a6ddd5c | note | By - PE
8895530f-a026-5a64-aa6e-d3d4b0b121b6 | checkpoint | 6.04.21 - Benkelman Beam
a726fa8e-3b85-5dd0-b062-8df19e4938d6 | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer.
669782df-f2ee-5b84-8119-cf95cfc13fc3 | note | • Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY
8d415580-85c4-58e2-8421-4049db1fd69a | note | Standard / Specification - PS - 7.3.2
f9c4f85a-8619-5cec-9129-04b57ac38ce5 | note | Verifying Document - Benkelman Beam Report
75198ad1-c3c1-52ff-a442-083d24f4d16b | note | Frequency - Every 10m of each lane – staggered between left and right wheel path.
fa63b9b7-742f-574f-9e4f-0cda0ecce321 | note | Activity - HP
bc6fbd4e-8d2a-5c15-a128-2e26f80beffe | note | By - ENG
69352328-8f56-52c5-bce0-ccf55cf27bbb | signoff | AUTHORITY HOLDPOINT
42dd6dc9-09fe-578b-bfbb-13b10408700c | checkpoint | 6.04.22 - MDD / OMC / SD
3015bf33-2735-5199-94d9-0375cefd22fd | note | Acceptance / Conformance Criteria - Post hoe, stabilised MDD, OMC, and SD. 1 test per 2000m² or a days work whichever gives the greater number of testing.
992155ae-17f6-5ae7-bb44-8bf8726ced39 | note | Standard / Specification - NZS 4402:1986, Test 4.1.3
d4114ab3-d904-5a73-9e97-6a00a0abbe2f | note | Verifying Document - Lab Report
5690faab-08ab-547d-be18-4e56c28a245f | note | Frequency - 1 test per 2000m² or a days work whichever gives the greater number of testing.
12f09bd0-2584-5a7c-a04a-59c34dd6c42c | note | Activity - I
62c91b75-1fe0-592c-870c-82fdb212fcf3 | note | By - PE
b4bfcba9-7ebb-50d5-ac19-ccbd0eaf5f97 | section | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
2c7daec9-a3b9-5141-9709-d474c280ddfa | checkpoint | 7.02.01 - Redline Drawings
728b5480-8bce-5e57-8220-4dc597578b1a | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen mark up showing lot numbers and areas stabilised in different days including clear delineation of all joins.
a0629c46-97b8-540a-9ab9-4a0d383f8d3c | note | Standard / Specification - Downer
8ac2a939-d8f9-5b48-a4f1-1467045a83ab | note | Verifying Document - Redlines
c5ca150e-c56c-5888-8abc-110ae84ec185 | note | Frequency - Post construction
e54ebb86-b19f-55bc-a788-af0879150f2b | note | Activity - H
d03de430-9238-5275-83a2-bdcde07e88d8 | note | By - PE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
97fc30da-f013-5ea8-b7ed-235c87b6240a | checklist | SYS - ITP - Piling Western Gully | itp | ITP - Piling Western Gully
e631fd1c-c7ec-5455-943c-2624fae3e7e6 | section | 1.0 Pre-Construction
6f43080d-629b-5e1b-8c1f-67f555a9f9e1 | checkpoint | 1.1 - Accepted Method Statement
62f24d58-7b8d-5c3c-877a-87b9c30bd50d | note | Standard / Spec Reference - Project specification
a0b5d7c8-4a0d-5607-8b54-315563f25d70 | note | Acceptance Criteria - Engineer’s acceptance
28af8229-fd5f-5619-8cd4-8a74166f2400 | note | Frequency - Once prior to commencement of piling
cdf61e20-5f96-5025-bb8b-a720e08c10d0 | note | Responsibility - CLL
42dbd898-35a4-5d93-9470-cbe81a90cfc2 | note | Hold Point H/W/S - DO: H
a1ec3af8-c244-5f77-86b8-956c98095f24 | note | Hold Point H/W/S - BBO: H
70b032bf-215e-54b0-aa18-0d92e380695b | note | Hold Point H/W/S - CLL: H
3c8ff899-625e-54c0-8499-92db7435fcbc | note | Verifying Record - Email Confirmation
4a44b871-e815-52b1-ad16-4142fb42906c | note | Comment - To be submitted at least 10 days in advance.
a2a0b4f0-e0f3-59a1-bad1-49d7ee3d895a | signoff | HOLD POINT (DO/BBO/CLL)
f4810438-62df-5388-8725-f411da743d4e | checkpoint | 1.2 - Accepted Inspection and Test Plan
2ce3b27d-4838-5fdf-8ea1-5777c3137557 | note | Acceptance Criteria - Issue
06dee5e8-d630-5c38-8931-a607754c1810 | note | Frequency - Once prior to commencement of piling
dc72a423-376b-5cae-937b-223b0a105f3c | note | Responsibility - CLL
0c173d62-8c26-58af-a7a3-39f4347d19c7 | note | Hold Point H/W/S - DO: H
3df5f23f-af35-55a9-9587-e32a590ad958 | note | Hold Point H/W/S - BBO: H
5f9fee3e-3c65-5efa-9192-259130cafef3 | note | Verifying Record - Email Confirmation
6d80a3a1-dc7c-5efb-8e5d-c48eccde4217 | signoff | HOLD POINT (DO/BBO)
3cc18b14-a7bc-537e-89b0-e7dddf8e0405 | checkpoint | 1.3 - Accepted Safety Plan - SSSP
ff600164-3277-50b6-94a3-86ea098289f5 | note | Acceptance Criteria - Issue
06052266-f1f1-54b6-a031-cb2d8e0c405d | note | Frequency - Once prior to commencement of piling
bf30a35e-ff8b-5b6f-9447-5647b88ecdf7 | note | Responsibility - CLL
97ebb5fd-1f19-5b3e-8f91-58c1104c5a15 | note | Hold Point H/W/S - DO: H
eca49034-bb54-5944-af21-bcd279d2168a | note | Verifying Record - Email Confirmation
f22188a5-0382-5eaf-80dc-15667845b3b1 | signoff | HOLD POINT (DO)
4168a7aa-2162-590e-89df-55c2652f1eea | checkpoint | 1.4 - Accepted support fluid details
9d9e6f8d-9bfd-52de-bbdc-1f7f1dc34fce | note | Acceptance Criteria - Issue
841f33af-4eb0-587a-88aa-b73cd866eb6d | note | Frequency - Once prior to commencement of piling
d5496b4c-34d2-531a-beb3-ae08c31d0301 | note | Responsibility - CLL
f3f25f47-92c5-56a5-b797-8c25e7eca7f7 | note | Hold Point H/W/S - DO: H
1aee7c34-a76d-50c3-8ffa-ed0ce8228d6c | note | Hold Point H/W/S - BBO: H
44f5d988-5199-51e2-bc00-c0aa67df1d6b | note | Verifying Record - Email Confirmation
8923a83b-3f93-5cbe-9157-af59ace73531 | signoff | HOLD POINT (DO/BBO)
ab8845fe-974c-5c2d-b7ba-bd306b249cc1 | checkpoint | 1.5 - Permits issued
33d41727-c9f2-5083-9bd9-49bba94dbb0e | note | Acceptance Criteria - Issue
4c345aab-e5df-5b13-a11f-0b728c28b7e9 | note | Frequency - Once at commencement of piling
fb36ee4d-02af-585e-889c-13435199ceda | note | Responsibility - DO
439a55e4-8990-5dd9-9727-13cdb6f987e9 | note | Hold Point H/W/S - DO: H
57a2c843-280f-5427-9e97-d1a4df1a33ad | note | Hold Point H/W/S - CLL: H
296af5e8-e172-5439-9015-be08147b2c9c | note | Verifying Record - Site Hardcopy
8f136149-2587-506a-bba1-6e1440bb081d | signoff | HOLD POINT (DO/CLL)
1fe8a6a6-7cd8-5282-b2be-5498e29c032a | checkpoint | 1.6 - Concrete Design Mix Verification
9fe70b6a-6f02-56e1-bb40-4a94473b735a | note | Acceptance Criteria - Issue
9cc52df2-2af2-5401-94e7-bf56e94fb584 | note | Frequency - Once prior to commencement of piling
942686fb-326b-5357-831a-0ea14c4b61de | note | Responsibility - DO/BBO
7ad59786-5dd0-52fd-81bf-5124f748ce8f | note | Hold Point H/W/S - DO: H
7a6a55e0-45ce-557d-9deb-ec74e6509fef | note | Hold Point H/W/S - BBO: H
6882a143-762d-5a98-8b9f-902ff910d6af | note | Verifying Record - Email Confirmation
b1b80037-1c57-587f-b42e-6fb24abbe9b2 | signoff | HOLD POINT (DO/BBO)
3345c9ea-7673-503d-8d45-f0719eecd85d | checkpoint | 1.7 - Reinforcement Steel – mill cert
f6de07d6-4d18-5c75-81da-f08f6fb541bd | note | Acceptance Criteria - Project specification
141b17c5-9fc2-586b-9410-b96125cc12a9 | note | Frequency - Post Construction for every pile
b80a6d66-54c7-55bd-95eb-f59fff342051 | note | Responsibility - CLL
cad41ae2-3493-53ae-b614-f1959efe03f1 | note | Hold Point H/W/S - DO: H
d26751fd-462b-5396-a946-21163b38326a | note | Hold Point H/W/S - BBO: H
02860350-2e3b-59fb-83e4-62c11e383e7e | note | Verifying Record - Issued by supplier - email confirmation
76f84977-d7a8-5150-8552-80556ac814f1 | signoff | HOLD POINT (DO/BBO)
1b04b2f5-a1f9-522d-b749-815e5b9edc57 | section | 2.0 Pile Boring
3b4421f0-8da0-5669-a934-aed355ded325 | checkpoint | 2.1 - Client Notification
127d74af-39ee-57b4-a28a-8cf89457a511 | note | Acceptance Criteria - Issue
49626cce-3ba4-5b4b-8e30-da4c6b2583bc | note | Frequency - Once at commencement of piling
17ffa176-be6e-5b07-ba5c-b7dd57754998 | note | Responsibility - DO
130ab38d-2a4f-5193-a58a-f7e4a2988b03 | note | Hold Point H/W/S - DO: H
f3b265fb-d836-5d1f-8d1c-866a9f0de264 | note | Hold Point H/W/S - BBO: H
21e632d0-2534-530c-871b-2a9bdf651709 | note | Hold Point H/W/S - CLL: H
77455024-dec7-509f-b8d8-de5cf34c0984 | note | Verifying Record - Email Confirmation
fdb7c117-096d-5971-a534-fcbd3b2e8936 | note | Comment - 48 hours’ notice of pile drilling commencement.
c5c2169c-5bbc-5c8b-acff-03bb7d0a17e1 | signoff | HOLD POINT (DO/BBO/CLL)
d71966cd-c8cb-57dd-bbdc-0ab16870f1b7 | checkpoint | 2.2 - Check drill tool diameter
d89977b4-e455-589d-bda2-95d41c40471b | note | Standard / Spec Reference - As per HCC 1298/2022
02263750-9fb4-5713-9e34-ab9cc0be1904 | note | Acceptance Criteria - Visual Inspection
84df2b0a-dbe3-594f-aad1-ec57437387ad | note | Frequency - Prior to commencement of piling
6df99fc9-0967-5811-acba-87a73fc2c335 | note | Responsibility - CLL
2933e753-6f07-5d06-8e7a-e42ae959ac36 | note | Hold Point H/W/S - DO: W/S
393df755-3739-5884-9e6c-94e1f8fadaea | note | Hold Point H/W/S - CLL: W/S
0d6ee654-a922-56c2-8592-9d75ffecf944 | note | Verifying Record - As per pile QAC
6d6df6d9-b3b8-519c-b879-061a4b65ada3 | note | Comment - Minimum agreed diameter is 870 mm for 900 DIA piles, due to ID of permanent casing supplied by DO, and 1200 mm for 1200 DIA piles.
87eb682d-76bd-5714-83ed-ade24669de4e | checkpoint | 2.3 - Check depth gauge/instrumentation of piling rig
d6a54a60-5171-50d0-a2fb-bbf927dcb062 | note | Standard / Spec Reference - Operators Manual
065bc6b8-60ce-578b-af89-e217a11acdcb | note | Acceptance Criteria - Visual Inspection
a2d08314-7d81-5714-80c3-c8f1bc580566 | note | Frequency - Daily
db42a45b-c24c-5d96-bbde-0abc33e268e1 | note | Responsibility - Rig Operator
99da9c5d-0d27-543e-a1bf-2f05b9b06576 | note | Hold Point H/W/S - DO: W/S
740ec1ab-51f6-5ac2-900f-93198bfac9d9 | note | Hold Point H/W/S - CLL: H
a31142ee-a7b2-52b4-972f-ffc06e078136 | note | Comment - Operator daily checks
033d1e71-1a92-5ccf-b696-c15bf3e46633 | signoff | HOLD POINT (CLL)
0ed639e4-eced-56cf-be4e-1ccfb7dcf320 | checkpoint | 2.4 - Ground penetration and extraction with due diligence
f8c37aee-8bcf-566e-a8f8-a9904e57e933 | note | Standard / Spec Reference - Operators Manual
8d566718-caad-5858-81ad-cc6ea83eaf2d | note | Acceptance Criteria - Visual Monitoring
0a48287b-b7a0-5a5f-9fa3-bc09c323b0aa | note | Frequency - Every Pile
356f007f-dde7-5250-8a44-73fe0a500963 | note | Responsibility - Rig Operator
ee6e25eb-084a-523b-9584-20acecc2b8e1 | note | Hold Point H/W/S - DO: W/S
b3f2d9ff-8a74-5efe-9170-f5230537c108 | note | Hold Point H/W/S - BBO: S
8886fd93-785d-5ce6-9209-95c655a90763 | note | Hold Point H/W/S - CLL: S
ea32cdba-2701-54b6-9e29-f89140d2a1e9 | note | Comment - Operator to penetrate/extract with due diligence, no adverse effect on bore integrity.
ba64cb2c-ed2d-5c10-98dd-3ebdaf61f7c6 | checkpoint | 2.5 - Check pile position/pile numbers
cc8a5683-4085-548b-a06d-f7650d7005d9 | note | Standard / Spec Reference - Drawings
92a5ffa7-ae71-57cc-85b8-cffec705debf | note | Acceptance Criteria - Visual Inspection
2cef91b0-b80f-5093-8153-34079e147fb8 | note | Frequency - Every Pile
476f8d0a-1369-57ff-88e7-0f0ac2ec346e | note | Responsibility - CLL
ed3b6a51-fe04-5388-8892-b10ac93febc3 | note | Hold Point H/W/S - DO: W/S
c59e9228-3d42-55b0-a461-1f58e181c916 | note | Hold Point H/W/S - CLL: W/S
4944f1a3-446c-519f-bcd5-33fafc434a70 | checkpoint | 2.6 - Pile Setout/Offsets
5265d5f9-82d3-5dd6-9a58-f8eff57c8283 | note | Standard / Spec Reference - Drawings
f24a2128-74bc-5847-8af6-c497eeafbfa7 | note | Acceptance Criteria - Hz +/- 10mm
7c7906c8-387d-5188-9b49-236c00fa0047 | note | Frequency - Every Pile
8e098ff8-97b2-5f13-ab15-adcf0b176acb | note | Responsibility - DO
84f8b9a2-ac2c-5ebd-a7ca-4c37f2f7bdb6 | note | Hold Point H/W/S - DO: W
00f62530-9241-5485-bf60-6e174363a69d | note | Hold Point H/W/S - CLL: W
d425f2f4-e41d-532b-b7f6-71474f6300f4 | note | Verifying Record - Survey record
d29e8f1c-a503-5d7b-a47b-10953ba557eb | note | Comment - Due to tight plan tolerances set-out is critical
dd2ba2e9-7691-5018-a2f9-d42a13ad30c1 | checkpoint | 2.7 - Casing Inspection
b1d70420-7211-5b5d-a523-795c11cee7fa | note | Standard / Spec Reference - As per HCC 1298/2022 – note minimum agreed diameters at ITP item 2.2
2a09fa2c-6c38-537f-88a4-0b7f4d770363 | note | Acceptance Criteria - Visual Inspection
1e31b424-6d87-54fe-95c5-21c32676d495 | note | Frequency - Length/diameter/Wall thickness at start of piling, RL every pile
19666f1f-b9e2-5641-93d7-5a1a94cf3d38 | note | Responsibility - CLL
d7248886-5235-5b47-938a-355fca0b2588 | note | Hold Point H/W/S - DO: H
27468874-90c7-5246-bae6-faccfa31dcab | note | Hold Point H/W/S - CLL: H
a34bd4c1-a19f-5bb3-9e49-e017835f383b | note | Verifying Record - QAC - Pile Card
3ac82270-8df9-5a7a-af3e-2ded1a6f9e18 | note | Comment - RL check pre-concrete & pre- drill
d2b56091-a501-532b-a85f-bc1ae59b9bec | signoff | HOLD POINT (DO/CLL)
e7f79d2b-ba69-50e2-b1de-bb90f8c43187 | checkpoint | 2.8 - Measure and check position and verticality
23eddc2e-82ab-516b-92d0-61bbdcfeecfd | note | Standard / Spec Reference - As per ASGPILES - Rev G
38af7733-fcbe-538e-ae27-d87df6ad910a | note | Acceptance Criteria - Visual Inspection Permitted deviation from vertical shall be not more than 1:75 or 0.8 degree.
f96ea33d-aa2a-5392-8fcc-36c22987bf7f | note | Frequency - Every Pile
f89ccee3-f773-50f8-80e1-ba63b89582f5 | note | Responsibility - CLL
1bcaf796-ce95-5492-b124-fd429a98dfdf | note | Hold Point H/W/S - DO: W
f2a11210-b84a-5872-8699-0eae8aeedcd2 | note | Hold Point H/W/S - CLL: H
145715cb-ad7b-58c5-8371-d3a2c6719f7d | note | Verifying Record - QAC - Pile Card
69c0eac7-e7d5-504b-aba6-266beb30f2f6 | note | Comment - Spirit level has a +-0.5 degree accuracy. Verticality of pile to be checked via use of electronic level on the side of the casings & against Kelly bar.
0f8b87af-1047-55e7-ad3c-846f0598b540 | signoff | HOLD POINT (CLL)
71c7c42c-6155-5afd-9bb2-efa351147076 | checkpoint | 2.9 - Bentonite checks
062d9b9d-4b1d-56b5-9efd-059c3b888bec | note | Standard / Spec Reference - Fluid Specification
5fe673aa-6ab8-5bb8-af0d-76175afc840c | note | Acceptance Criteria - Visual Inspection/Testing
86b6f252-d5b4-5f79-80ac-39e90ae7c1b9 | note | Frequency - Per batch, each pile prior to concreting
dc20cc6e-41b5-5948-a9f3-0d2a2b13cefa | note | Responsibility - CLL
4d57e3db-de1d-56e9-9095-d4f971652c07 | note | Hold Point H/W/S - DO: W
fccbd892-06f0-5f86-97c1-e84026cf31b1 | note | Hold Point H/W/S - CLL: H
80030517-2764-5cfb-98fe-42a66de35365 | note | Verifying Record - QAC - Pile Card
fba28799-ccbc-57df-8746-229dcebbe296 | signoff | HOLD POINT (CLL)
b45c7ad1-0ee0-5790-a39a-8764545e3d10 | checkpoint | 2.10 - Bentonite level
7110409d-ae16-5282-86de-3aa5ca979499 | note | Standard / Spec Reference - As per construction specification - Methodology
aada31d1-5145-5d1d-96f4-e39f66fd25b4 | note | Acceptance Criteria - Visual Inspection Bentonite head to be maintained at 0.5m above groundwater level or adjusted as required.
6a7aaae7-3195-5b64-9426-50157cf84b48 | note | Frequency - Each pile
6b92b846-b8e7-5b82-8593-683a180e5ef0 | note | Responsibility - CLL
ea1f1680-0813-5a0b-8b60-50e9e28c2657 | note | Hold Point H/W/S - DO: W
28a4502f-6369-56c9-bf97-85320653eacf | note | Hold Point H/W/S - CLL: H
99e7656a-56b5-587f-8b3f-d755d44ad5cf | note | Verifying Record - QAC - Pile Card
e22b5738-9a18-534e-931c-ee4065ed4aaa | note | Comment - Any significant fluid loss/stability will be addressed with Project Engineer.
c410c9e4-c988-52bc-894b-68478bbbacde | signoff | HOLD POINT (CLL)
3c73a5eb-731d-5cfe-9e84-556300112151 | checkpoint | 2.11 - Soil logging and bagging
05a5cf28-2374-5f59-9c31-3616a8a99710 | note | Standard / Spec Reference - As per HCC 1298/2022 11.7
fbd76925-eca8-59d2-a939-d88d07abe294 | note | Acceptance Criteria - Visual Inspection Engineer Inspection
0a151c42-9cdf-530d-bee4-76c07ab75bf1 | note | Frequency - Every Pile
7356630e-687f-5d18-a2bb-5d85ce4ea06c | note | Responsibility - DO/CLL
1702070a-6cc6-5e5c-b0ef-d303f17de8fc | note | Hold Point H/W/S - DO: S
643415d9-95d7-5382-a7c1-9e4fab189209 | note | Hold Point H/W/S - BBO: S
2d8e6ed3-f642-558f-8257-536dd4a3f482 | note | Hold Point H/W/S - CLL: S
eb6034dd-7c82-5fbc-9d02-e8f393445fc1 | note | Verifying Record - QAC - Pile Card Labelled, bagged core samples
f1fdf6c2-d77c-55c9-a0ef-1e61e7398409 | note | Comment - Boreholes are to be continuously logged on QAC - Pile Card. Material from the base will be bagged, labelled and securely stored on site for Engineer’s inspection.
e7b4547d-122f-538b-80fc-c8ba34fb4010 | checkpoint | 2.12 - Confirmation design minimum toe depth achieved
f50e9dec-3595-5314-ae00-dd46e1835e51 | note | Standard / Spec Reference - Construction Specification/ Drawings
adb9a044-27ee-5b93-afda-4c2160bd656a | note | Acceptance Criteria - By means of weighted tape Designer Hold Point: Maximum depth exceedance
b0040e5d-93ff-57bb-9c57-0322b1aa89c1 | note | Frequency - Every Pile
c3fdff0a-1bf1-5832-a0cc-5d34b56ba509 | note | Responsibility - BBO & DO Rep/CLL
545a7558-dd79-53b1-b2af-9bac40f9f4db | note | Hold Point H/W/S - DO: H
6544d048-4b5e-57ee-9cd1-d0d118c09b42 | note | Hold Point H/W/S - BBO: H
90620fbf-5ac0-5b79-a5c2-f951fd7f12ba | note | Hold Point H/W/S - CLL: H
2a3ddc38-bb98-51d1-98e0-68311e26d69f | note | Verifying Record - QAC - Pile Card
35ac5247-116a-50fd-a332-d2212b87d98a | note | Comment - Visual inspection not possible due to drilling under fluid. Engineer to agree correct drill depth. Designer to be notified if drilling reaches >300mm below design RL for pile toe. Maximum depth exceedance to be 40m from piling platform.
c5835909-1009-5ddf-a0e1-5fe7560b622b | signoff | HOLD POINT (DO/BBO/CLL)
1466b6ea-8333-5218-bacb-d052d88fcf46 | checkpoint | 2.13 - Base cleanliness
e1f9cbcd-2a01-5ebe-bb7c-269e23ae51e1 | note | Standard / Spec Reference - Construction Specification
82257d50-4b95-5b95-9d48-328d7f1c16da | note | Acceptance Criteria - By means of weighted tape
ee5d6323-0a66-52d8-9bc0-e825aa8ff225 | note | Frequency - Every Pile
30bdf695-1094-5aee-9fb2-eca1e3b47259 | note | Responsibility - BBO & DO Rep/CLL
98e336f8-cdf7-55c4-b3bb-cde97b83c563 | note | Hold Point H/W/S - DO: H
c3bd29d6-5ba4-537b-bdb1-ad8279ec335b | note | Hold Point H/W/S - BBO: H
8fbb5c9f-d190-5f21-bd03-c9ce09194916 | note | Hold Point H/W/S - CLL: H
6457918b-7bef-52a5-b94f-5d9dd88a9dc1 | note | Verifying Record - QAC - Pile Card
09fa7eea-a4cd-5d30-b66d-1618849fd90d | note | Comment - Visual inspection not possible due to drilling under fluid.
b804ed3e-bce8-5f15-9c80-14c4ce8663a8 | signoff | HOLD POINT (DO/BBO/CLL)
c2746085-9a50-522a-b189-9a0ffe6773c6 | checkpoint | 2.14 - Pile Boring Monitoring
da5690c2-364c-54ba-b5bb-c44b04b0d497 | note | Standard / Spec Reference - Construction specification
a6065435-836f-5a15-8633-d9964351b9cc | note | Acceptance Criteria - Visual Monitoring
f6f28ca6-10a8-549b-888c-201999d02812 | note | Frequency - Every Pile
3a3807e6-8ce3-5acf-97a5-9c3a73876454 | note | Responsibility - Rig Operator
9b483e89-f254-5424-99b4-94ba331da17f | note | Hold Point H/W/S - DO: S
e4e7c507-d7e4-5582-849a-f80b0dcf2c7a | note | Hold Point H/W/S - BBO: S
6a180e2b-611a-5e21-be53-009e8f2c2989 | note | Hold Point H/W/S - CLL: S
6eb9b0f5-7f5c-56ba-b44b-618e668925ae | note | Verifying Record - QAC - Pile Card
66c0ec2a-e112-57cd-bd96-8583d38bf0c4 | note | Comment - Depth check, possible collapse, changing ground conditions, any unexpected occurrences
7c935674-82a6-53c3-b3e8-df3abc90f83c | section | 3.0 Pre-Pour Inspection
d953a050-a6b7-52ae-9001-6d8f111ca051 | checkpoint | 3.1 - QA check on previous pile
d9ffa3b0-f2fc-5ffb-856b-d9d0845faecb | note | Standard / Spec Reference - Engineer Specification
9a7315d4-da70-50ea-8600-34cee05752e2 | note | Acceptance Criteria - Client notification/Engineer’s Approval
dcefb148-106b-5e4f-8706-4172893e6f2c | note | Frequency - Every Pile Ongoing Engineer’s approval
e8801f3e-fb09-57f6-9efc-2d002ec58f1d | note | Responsibility - DO Rep/CLL
da467a95-7061-5faf-9080-31eea866c4a1 | note | Hold Point H/W/S - DO: H
ffd50456-cf6e-5bb2-beed-fbf83ed7e06a | note | Hold Point H/W/S - BBO: S
66620fd5-c1e0-54d9-9de7-342197c68564 | note | Hold Point H/W/S - CLL: H
9063f978-984c-53db-958a-bd6fe16cbb1c | note | Verifying Record - QAC - Pile Card
91ce59a3-8964-5126-94c0-09cb8f71bdf3 | note | Comment - Engineer’s approval to proceed with subsequent piles
bffddf96-fcf5-5cc1-b267-facf012d0f6e | signoff | HOLD POINT (DO/CLL)
434d2641-9e45-551c-a35a-2d7e12dde700 | checkpoint | 3.2 - Reinforcement Cage inspection/ check spacers, pile bore tolerances
32332388-f3b4-55a2-9d5c-c08b1c59ed2c | note | Standard / Spec Reference - BBO SS 2110 Rev 9
48b7e1b9-800d-56cf-83a8-c0e4f9770b27 | note | Acceptance Criteria - Alignment lesser of +- 4% DIA or +-75mm
d5540b5f-3471-5520-9228-6539eb73f067 | note | • Height +- 50mm
e72c4a70-0261-5b44-9219-ded85717bbf0 | note | • Reinforcement Type- As per drawings
553844e0-efd1-5c21-8bfe-bf0e46735eb0 | note | • Concrete cover: 75mm, 50mm minimum
ec2f10f5-139d-59cd-ad7c-18817e2a9d83 | note | • Bottom of pile position lesser of +-1% pile length, +-12.5% of shaft diameter, or +-400mm
0377f0a6-1588-5155-80df-064446b2858d | note | Frequency - Every Pile
b2c5375a-93e3-5631-bb55-b566d619b2bf | note | Responsibility - DO Rep/CLL
edc040f2-1b2a-5360-b2fe-f9d6b91be355 | note | Hold Point H/W/S - DO: H
c2ad4d47-631d-5ab3-8369-f005614c714b | note | Hold Point H/W/S - BBO: S
08169f5b-32ca-5a6d-9a2f-c323e831759d | note | Hold Point H/W/S - CLL: H
b7c36495-da2e-5fca-ba1f-b0783430ad08 | note | Verifying Record - QAC - Pile Card
818a252f-b1d9-5349-a139-880703f85f88 | note | Comment - Pre-installation check required of all pile sections
f2892bd9-85b7-5ec9-bb7a-a768688b39dd | signoff | HOLD POINT (DO/BBO/CLL)
b65f5ce9-fc79-52d9-84a7-91d525dbe893 | checkpoint | 3.3 - Stabilising Fluid Verification
5db9a565-4b7d-520a-ab7a-5002ffb8ec92 | note | Standard / Spec Reference - Construction Specification
61003af8-6099-572f-878d-f618d906d86a | note | Acceptance Criteria - <4% sand content acceptable
96895dee-5600-5b2f-899a-5649edfadb0d | note | Frequency - Every Pile
1b730cb4-d0e4-5279-aabd-d0ae4e97bf0c | note | Responsibility - DO Rep/CLL
5d5d8ccd-c809-5a56-b041-88f09e37347a | note | Hold Point H/W/S - DO: H
abe3398c-d030-5b8b-89e8-32292c3e894f | note | Hold Point H/W/S - BBO: S
17422081-e128-5f7e-af79-f85ad3432e47 | note | Hold Point H/W/S - CLL: H
e042cbd3-73aa-5b5d-a1bf-188e90bb416b | note | Verifying Record - QAC - Pile Card
03377fca-a7c5-560b-9e9d-b131a800afa7 | signoff | HOLD POINT (DO/CLL)
e552fec4-73ee-5d9d-8552-4914d74ed513 | checkpoint | 3.4 - Pile cage installation
c14f16e2-c6e0-5fe2-9a6a-c08be4f34bed | note | Standard / Spec Reference - BBO SS 2110 Rev 9
a366130f-a6ec-5928-b165-74f227cf6450 | note | Acceptance Criteria - Engineer Inspection
2f85f743-0569-5391-804e-03a846d65820 | note | Frequency - Every Pile
2ffb28ec-ad8b-5994-8c3c-8cd898a3b850 | note | Responsibility - BBO/CLL
d2f62d4b-a998-5546-84f9-cfe0f3c21dc2 | note | Hold Point H/W/S - DO: H
c4c98d6c-9521-536c-9071-c2245c4f36df | note | Hold Point H/W/S - BBO: H
b7c7ccec-7d4f-5066-a1aa-488ab9fa68e4 | note | Hold Point H/W/S - CLL: H
d282ff52-af4e-5eb2-a129-3fb0d079f068 | note | Verifying Record - QAC - Pile Card
5d35f620-2870-5913-9055-a5c03c33d726 | note | Comment - Pile cage to be installed immediately after Engineer inspection and acceptance
a878fc0a-6ed0-5f22-9c93-439cb5fcd982 | signoff | HOLD POINT (DO/BBO/CLL)
8ca18c17-4604-5af4-989a-cfc9ac9338cd | section | 4.0 Concrete Placement
23df560f-8d0b-581e-9bb5-fdeae8a124e3 | checkpoint | 4.1 - Verify Concrete Mix – batch times, mix
987a0787-d2b3-5b07-9263-e7e9494c1061 | note | Standard / Spec Reference - BBO SS 2140 Rev 5
103db8b0-60cb-5751-9268-1b15d271c6b0 | note | Acceptance Criteria - 401T4504R
2be52e69-9efb-5473-8caf-f9bc414ab1d7 | note | Frequency - Each delivery
33819dc0-5bb9-5115-88db-863b5140a336 | note | Responsibility - DO Rep/CLL
d23d2690-5722-5931-b595-fee021a5f480 | note | Hold Point H/W/S - DO: W/S
43bd3a62-328b-5f77-a0cb-b0132d6b601a | note | Hold Point H/W/S - BBO: S
a4459d03-2dc6-5823-a5ba-cd9e516f3176 | note | Hold Point H/W/S - CLL: W/S
f8d935ff-2af5-5d7e-b866-f9d9e2dbeae4 | note | Verifying Record - Concrete Docket
78485264-f0e4-54b8-ac4b-477c6df97791 | checkpoint | 4.2 - Slump/ Spread test
fa08a831-c5de-53eb-9558-6f592339dead | note | Standard / Spec Reference - BBO SS 2140 Rev 5
45987288-bffe-5d95-8ebe-2a340eccaec8 | note | Acceptance Criteria - Slump 100-130mm +- 25mm
dbe3811c-1311-5d5f-a209-c1cd9ff2821f | note | • Spread 500mm +-100mm
2415bb64-12b8-5cfb-ab35-82ebf82ed75f | note | Frequency - Each delivery
80f8af05-ec45-587d-a244-c2ed7ba804fd | note | Responsibility - DO Rep/CLL
d5b5124b-2f99-50ca-9008-15ff5672228e | note | Hold Point H/W/S - DO: H
689c9610-76fd-5b70-9a87-5b00a6e3df64 | note | Hold Point H/W/S - BBO: S
61c250cd-15f7-5e49-91ae-e4c2264ed653 | note | Hold Point H/W/S - CLL: H
85ef6231-6847-5b11-ab6e-38c97f93da77 | note | Verifying Record - QAC - Pile Card
a961e012-3d81-537c-b38d-db8d73cea422 | signoff | HOLD POINT (DO/CLL)
9fba1f14-cfc3-5695-b685-e4690fd1364f | checkpoint | 4.3 - Concrete level
cf5c32d9-8b2e-5212-87e3-a22f3b3a6b60 | note | Standard / Spec Reference - BBO SS 2140 Rev 5
616a5865-4d49-5b8f-90bf-938f9945c06f | note | Acceptance Criteria - Design +50mm
d1462899-cdaa-5978-924c-52b8512a87a9 | note | Frequency - Every Pile
bdc77f32-0256-5520-a294-f327d7b77df6 | note | Responsibility - DO Rep/CLL
a3393c8c-6837-5251-ada2-d9b693e96a0c | note | Hold Point H/W/S - DO: H
8920593f-b999-56b4-bb76-4988cac6b525 | note | Hold Point H/W/S - BBO: S
74fd1a5b-2a16-5da8-9dca-a87ff8167a7d | note | Hold Point H/W/S - CLL: H
02286bfc-65f6-52c1-8372-112c2bf4c366 | note | Verifying Record - QAC - Pile Card
301ce10c-e0f8-5c36-a47c-33191b4de49a | signoff | HOLD POINT (DO/CLL)
7f1856f7-f74e-5f60-ae0d-98bde995d6c8 | checkpoint | 4.4 - Concrete placement
4b2d27f3-d304-5954-97ca-42e3ad806688 | note | Standard / Spec Reference - HCC 1298/2022
50ec78e8-7a60-590b-880a-90d07cb85e3d | note | Acceptance Criteria - ITP Item 3.3
b99e46f2-3d8f-5c8f-97ba-a1b6aaada3e5 | note | Frequency - Every Pile
aadd7598-b457-5050-bb50-1e4909442eac | note | Responsibility - BBO/CLL
5ec50698-bb96-5c58-90fc-e33bbec12743 | note | Hold Point H/W/S - DO: W/S
b2c8600c-42f1-543e-b39d-2871d135a7cc | note | Hold Point H/W/S - BBO: S
2b2362b2-b4ac-5f42-858d-9d482142d396 | note | Hold Point H/W/S - CLL: W/S
f7a9c4b9-b545-533f-8e2a-85395f12c4e5 | note | Verifying Record - QAC - Pile Card
8296c2e6-2872-5b02-b7e0-6bdbca76b520 | note | Comment - Pile to be concreted within the same day as Engineer’s acceptance of reinforcing cage installation, ITP Item 3.3.
e61c6faa-a7aa-59fc-9f15-51df6c3c54fd | checkpoint | 4.5 - Concrete pouring – Check volume
f3e683a1-f21f-5432-b184-5ac50c69bd57 | note | Standard / Spec Reference - Construction Specification
cce7751b-fd79-593a-a271-f53492199ba3 | note | Acceptance Criteria - As per QAC - Pile card
983417f3-6810-5eef-a4b7-f594983ade3a | note | Frequency - Each delivery
26737af6-8647-5ac3-8e1c-e95412dc9700 | note | Responsibility - DO Rep/CLL
384298bd-f756-5bfc-83da-38bfaaeb5852 | note | Hold Point H/W/S - DO: W
28138a08-16cb-5f31-a057-4da8dd96c255 | note | Hold Point H/W/S - BBO: S
145cef34-c356-59b3-a213-248300218be7 | note | Hold Point H/W/S - CLL: W
78cb32b7-ba2d-59e8-bffb-afc56409d1a0 | note | Verifying Record - Concrete docket, QAC - Pile Card
4bd8d361-e465-5bed-8717-bfa87d4bcb5c | note | Comment - Concrete volumes and Tremie records to be maintained as per QAC - Pile Card
34841c95-3f50-59ad-abca-ea5991b7b24e | checkpoint | 4.6 - Pile concrete overpour
6b7c9fec-bb14-52a8-966e-2c2739099dfd | note | Standard / Spec Reference - HCC 1298/2022
fba889d8-b628-516c-9809-6f56ff55c148 | note | Acceptance Criteria - Visual check - Sign off by Engineer
6c87a0ad-b23b-52d9-a9f0-3b007a8513f0 | note | Frequency - Every Pile
13a64774-e81c-53d5-b24a-bac36a2941d4 | note | Responsibility - BBL/CLL
ba236230-a27e-53a6-9dcb-4239f6ee7a1e | note | Hold Point H/W/S - DO: W
5a84510a-0eda-5b08-9220-d0e33b82945d | note | Hold Point H/W/S - BBO: W
6f3a1949-8b26-5c23-9f67-fb6e263dc4c4 | note | Hold Point H/W/S - CLL: W
5fbfce19-4d3e-5a01-abaa-3efa57f45c03 | note | Verifying Record - QAC - Pile Card
8536857f-2eab-5bad-9af8-1141c44eae76 | note | Comment - Pile to be overpoured and slurry at the top of the head removed until only sound concrete is present.
3b387d27-4e8f-5bf5-a611-a36cd9ac758c | checkpoint | 4.7 - Formation of construction joint
f581d9e2-cf40-5b7c-9b91-1cee11e67b4f | note | Frequency - Every Pile
79fb3271-da92-539e-9432-4c34ce89a05a | note | Responsibility - DO Rep/CLL
6b7303eb-5980-5128-8213-65756c332029 | note | Comment - Formation of construction joint by others.
36319a26-0d74-5320-b2d4-025a269fd3db | checkpoint | 4.8 - Concrete curing (tops of piles)
3ab9db28-18b1-58b9-8375-29b082114500 | note | Standard / Spec Reference - BBO SS 2146 Rev 4
adeffec9-e085-532b-b412-08212435cc08 | note | Acceptance Criteria - 7-day wet curing required
47ea7a56-bad4-5e05-83d5-65cfcfc01141 | note | Frequency - Every Pile
348082e8-a6fd-58d0-b953-7227dbd8ff1a | note | Comment - Concrete curing by others. Curing requirements will depend on the thickness of concrete which to be removed after concreting and weather conditions.
b2dfdc1a-0799-5ded-abb7-0d34bdf4b9d6 | checkpoint | 4.9 - Compressive Strength Sampling
522b68f4-7f1a-5bd3-adbe-25fbf41c7d31 | note | Standard / Spec Reference - NZS 3112
c3c8a389-8e3f-5e23-ac9e-53b49815cf55 | note | Acceptance Criteria - 28 day - 40MPa
c5b425b0-91f0-5222-af98-f0b2dc7b10bd | note | Frequency - Batch plant sampling and testing per piles – 4no cylinders – 1no @7 days, 3no @ 28 days
3c52277d-9bc0-545f-b820-abddd70359a4 | note | Responsibility - Concrete Supplier – samples cast at plant
67d5fa2a-2c19-5428-913e-81ca3f22e876 | note | Hold Point H/W/S - Sub: H
62e37f45-5d3b-56a4-be03-47ee6d03fb66 | note | Hold Point H/W/S - DO: S
92a92103-e907-5e5b-af77-1c42ce1d2964 | note | Hold Point H/W/S - BBO: S
bff9179e-3d25-5c50-b266-6d4335e05e1f | note | Hold Point H/W/S - CLL: S
b9194c85-45aa-537b-90aa-386b69c592a8 | note | Verifying Record - Lab. Test Record
6e5ebf70-a293-5979-8666-1c5743f59f04 | note | Comment - On site independent testing to be done by others. Samples to be taken at batch plant.
518e1be3-0530-582f-87a7-25c343e683e5 | signoff | HOLD POINT (Sub)
b5dfdef5-a300-5b32-99ff-12f5244d5c2f | checkpoint | 4.10 - Post pour/ Post casing removal - Reinforcement and concrete RL, orientation check.
5da39c36-338e-5d61-a610-cad927166bfc | note | Standard / Spec Reference - As per Auckland Structural Group Piling Specification
988a0b99-7530-5211-a1ea-809b054a8511 | note | Acceptance Criteria - Alignment lesser of +- 4% DIA or +-75mm Height +- 50mm Concrete cover: 75mm, 50mm minimum
445109f9-c35c-5735-afb4-9bf9e584066d | note | Frequency - Every Pile
dfbcc84e-ca31-5d63-a996-cedd4ed942ac | note | Responsibility - DO Rep/CLL
f805c3db-43a5-528a-848f-dcfcdb3914b8 | note | Hold Point H/W/S - DO: W
63899f76-220b-5c2a-ae75-8e9eb90a4f96 | note | Hold Point H/W/S - BBO: S
0c25cf28-8d08-5695-a159-a4380545d5b7 | note | Hold Point H/W/S - CLL: W
f3708420-2a35-54c9-aa00-3b636a2bb2fc | note | Verifying Record - QAC - Pile Card
79d0df54-b810-5bfd-ae22-b36a0dc1cbeb | note | Comment - As builts by others.
dd75deed-8bee-573b-8fa3-73588bc89154 | section | 5.0 Close out
d5fa4318-166b-51a6-96cd-c786a5350aad | checkpoint | 5.1 - Pile Cut off level verification
60e6bef7-48b9-5403-bec6-e68922ffa1d3 | note | Standard / Spec Reference - Construction Specification
d1dff8dd-ad15-57db-94c3-8538a13d2789 | note | Acceptance Criteria - +/- 10mm
ac152506-9a0d-558b-8ab6-d519b419ff0e | note | Frequency - Every Pile
1dc3fc39-ff34-5147-aef0-8828f79642ab | note | Responsibility - DO Rep
fa793d5d-0fbc-523e-b022-a779407e78a5 | note | Hold Point H/W/S - DO: S
4c0297bb-3fc0-50a4-9bf7-e53e27873c43 | note | Hold Point H/W/S - BBO: S
08375f72-a0fc-53ff-b22c-04f7c7b8cc76 | note | Verifying Record - Survey Record
034f27c1-41c4-5d8e-80f3-fcfbc00596a4 | checkpoint | 5.2 - Pile & Reinforcement Cleaning
f10bacc4-6c83-59dc-ae57-0e47e11d700a | note | Standard / Spec Reference - Construction Specification
bbc7e2a8-6728-5dc4-ae5d-9f4d738d5319 | note | Acceptance Criteria - Visual
54efc8f7-eac3-5e18-861f-28439453975b | note | Frequency - Every Pile
55699227-4f9c-56b9-996a-f2468339df0c | note | Responsibility - DO Rep
25389885-052a-54dd-83c3-ef60830d729f | note | Hold Point H/W/S - DO: S
98f9e32b-e020-5b9d-ac8b-befaf733daae | note | Hold Point H/W/S - BBO: S
67785e7e-86e3-5d48-97e6-e288a24d6435 | note | Verifying Record - QAC - Pile Card
15547e0d-3fc9-57a5-8b6e-4156c19e1f82 | checkpoint | 5.3 - Reinforcement to specification
e2231008-11df-5670-ab3f-458806c1c46d | note | Standard / Spec Reference - Construction Specification
cd4704b4-6f33-50e1-92b0-7e2d5e19ca43 | note | Acceptance Criteria - Visual
4a0b20bc-43a1-50e6-ad70-4be701ee1b8a | note | Frequency - Every Pile
eaaaf82c-5480-50e5-9298-582fac5dcd44 | note | Responsibility - DO Rep
e2c90418-6ab8-594b-a1d3-8c51b06d6859 | note | Hold Point H/W/S - DO: S
75e11b29-a15b-5b1f-a177-b23bfa350852 | note | Hold Point H/W/S - BBO: S
cc52a099-c4a8-5d40-9fab-5352cf304efc | note | Verifying Record - QAC - Pile Card
5a047b61-e09b-5a34-ba03-2f64cba1794a | checkpoint | 5.4 - Pile records
c027e63f-fd56-5676-a6d3-e5084e17b286 | note | Standard / Spec Reference - Construction Specification
efd3822b-78c4-56fb-a0a2-4afec4dd0e0d | note | Acceptance Criteria - Collation and Submission of records
4abf990d-cf56-502c-94fa-403039ac85d0 | note | Frequency - Within 24hrs of completion, Every Pile
cf5d8ca2-1b61-55d9-9a96-c2d50d40a909 | note | Responsibility - CLL
75c2c23e-5b26-5df6-8591-b673e576d090 | note | Hold Point H/W/S - DO: H
243147c3-4704-5bb6-a66c-ab5c836f8356 | note | Hold Point H/W/S - BBO: S
3a6b8d88-311d-5206-92a9-770062142582 | note | Verifying Record - Email Confirmation
03da7126-7c0f-552c-9b83-1da110831867 | signoff | HOLD POINT (DO)
14185836-1b06-5f86-9ad7-c6daeb2a4eaa | checklist | SYS - ITP - Retaining Walls |  | ITP - Retaining Walls
8c9335a7-3af5-5e47-a887-39a89ff08c27 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
dfb723bb-584a-5713-be6d-07b0f19feadc | note | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
e2830cdf-362b-5f0e-8d22-f68f1a98219d | note | Standard / Specification - Downer
14282032-c33f-55dc-9ae6-ba093f01c0fa | note | Verifying Document - Construction Pack
9e7ee91d-d82a-5694-af12-0f67083b3c87 | note | Frequency - Submit 10 days prior to commencement of works
2a4ab9d4-071d-53fa-ac91-77f26febe2a2 | note | Activity - HP
d5d6a8c7-50e2-54b9-96ba-d6ed63ed046c | note | By - ENG
ca255811-cbe5-57f5-8b49-d49ad30655f3 | signoff | AUTHORITY HOLDPOINT
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
dc572b14-0ed6-54c7-bc8f-85ed00c03dfe | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
3e946a9d-b5c8-50e7-96e0-0400e8f6e89c | note | Standard / Specification - Downer
34bb53e5-aed2-52e3-a5c2-9f81d0a823ca | note | Verifying Document - Survey Records
61d76f5d-0ad9-583f-ac76-86ad184fa739 | note | Frequency - Prior to Works
376f33df-3b2b-5b0c-ab68-eb1a544a497d | note | Activity - H
c900da17-59f9-5691-b9d1-3bcd5996d491 | note | By - SV
a24a2c58-bf6f-5474-883c-40044bad1fc7 | checkpoint | 3.01.03 - Service Location
b9f21eeb-7675-5741-9a79-4af249ac51cd | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
434102cd-5777-54cc-b4b5-32744d498024 | note | Standard / Specification - Downer
07a728fa-eece-56e9-af95-f512783809d3 | note | Verifying Document - Excavation Permit
077eeafa-3bad-5034-9687-5e46d0d70d1b | note | Frequency - Prior to Excavation
f621f899-2387-5113-900d-6bf9fc014ca0 | note | Activity - H
765fd8e2-b34a-5911-8b80-bd9e215f5033 | note | By - SE
0a214a7a-124a-5898-a837-e29e83751df0 | checkpoint | 3.01.04 - Internal Permits
b356337b-ff8b-5218-b916-0250a1283683 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
a1b106e9-f9c2-5c82-9b78-bc7a5e36b3d8 | note | Standard / Specification - Downer
62309b3c-27a8-5c74-8629-890633f13944 | note | Verifying Document - Internal Permits
83e97ed8-8c87-565f-9e65-f307d506c6a2 | note | Frequency - Prior to Excavation
d9a60eb7-5a01-5a8f-8f3f-6ce4ccaaa502 | note | Activity - H
3d563ef1-3b79-577d-b94f-308e34e1ca4e | note | By - SE
917e2881-0901-542f-ae25-686bf9c47009 | checkpoint | 3.01.05 - External Permits
b3b0e978-a810-584e-aa53-c42ce3c97641 | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
da4f0b71-5efa-5c01-ad1a-988c4ed5ce74 | note | Standard / Specification - Downer
9637f9ab-b7c6-54c8-8436-24c62804f0c4 | note | Verifying Document - External Permits
86a70157-a919-5dd5-aa32-c8681501a34c | note | Frequency - Prior to Excavation
bdcdc434-1b5d-5073-8411-b8512f1171ba | note | Activity - H
9a96dd8f-f51a-5d85-90aa-2277fca1a9b8 | note | By - PE
a1302970-0389-558d-b43c-67b14bbfc27a | checkpoint | 3.01.06 - Approved Construction Drawings
9ff0acba-9273-52f4-a0a4-2ab6d34c8a37 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
35f67329-e2c7-5487-a6d4-58b982b7c249 | note | Standard / Specification - Downer
3dfe5430-9c4a-5998-aade-3c0355af63af | note | Verifying Document - IFC Drawings
2b7e4a6a-c00a-5a00-ac72-61e46e5f805a | note | Frequency - Prior to works start
64beb55c-164d-586e-993a-71bf994ecd03 | note | Activity - H
16b491c1-6520-5184-a1cd-e89a84b6dddc | note | By - PE
34b3d838-f63d-5499-aad4-14b7c1eb24ae | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS
1437ac3f-e25b-5932-8866-3f1e2bab518b | checkpoint | 4.01.01 - Stone Strong Block Molds
24a4862f-20e9-5858-9e47-682e8ebdcd0f | note | Acceptance / Conformance Criteria - Stonestrong blocks to be supplied by an approved supplier. The Contractor shall liaise with the Principal-appointed Cultural Artist to coordinate carving of the supplied blanks and the production of moulds & blocks
b7e1ac9b-4fd0-5aed-91f1-207545543544 | note | Standard / Specification - PS - 12
4fbb56e2-610f-5ab3-b571-8d5a95c19942 | note | Verifying Document - Conforming Molds Post Carving
4ea6de2e-aec5-50b2-a438-bd4bd870e686 | note | Frequency - Before Installation
d4a2256c-c353-57e5-9fce-3979c4f41a52 | note | Activity - H
1c7d0313-833b-5b02-8452-76e926b94d30 | note | By - PE
a3cd3258-fb54-5b31-83f8-74d9198b64d1 | checkpoint | 4.01.02 - MSE retaining wall backfill Material
cc3d6c38-7cdf-5ccc-b3de-82e5fa7d81b3 | note | Acceptance / Conformance Criteria - Backfill is to comprise a well graded, granular material such as GAP65 or site won Hinuera Sand, which must be free of any deleterious material. Sand backfill shall have a fines content (less than 0.075mm diameter) of no more than 10%. Labratory MDD (x2 per material type) at standard compaction
22721888-49d4-5ebd-a823-b786fde9c2dd | note | Standard / Specification - GWS - 5.3.3
f760ee7e-3e30-5748-ac8d-dd6f4cff2189 | note | Verifying Document - Lab Results
ac1f5c71-71b7-5418-a6b3-d83649055b3c | note | Frequency - Prior to works
951e9d5f-bd61-5982-b242-bf9f0c0caffb | note | Activity - H
8ebf4f1b-07e1-53f7-b331-bcd4af254b27 | note | By - PE
05bce6c9-76c8-5aeb-94f0-6addb618072e | checkpoint | 4.01.03 - Geogrid
a5ac5972-5125-5559-af6d-1c6c4e7dedcc | note | Acceptance / Conformance Criteria - Geogrid to be Miragrid GX200/30 or similar approved
9f8013ff-90e1-57c2-9d72-3a9dffbf0e78 | note | Standard / Specification - GWS - 5.3.1
0a7a8e2c-6643-54d0-a7a9-d2756a3ae4b4 | note | Verifying Document - Datasheet
8616060a-d369-50b8-aaba-ef3009718c94 | note | Frequency - Before Installation
a58b35f4-bec7-526e-a186-cb8cfac7ff0c | note | Activity - H
96867ef7-72bf-5c39-9276-a8fa57a392dc | note | By - PE
6e039cf8-38d9-583d-81da-a16916cec0db | checkpoint | 4.01.04 - Para web
1caebfdf-02c1-5487-a1c2-99494d3a7d32 | note | Acceptance / Conformance Criteria - Paraweb to be the correct grade: Paraweb 2D-50
fc6b5ecc-9ae5-5429-b362-4e4e740b858a | note | Standard / Specification - GWS - 5.3.2
c6a61179-13b0-5cce-86df-0b2aee73ba18 | note | Verifying Document - Datasheet
d6d44771-ac67-536d-add9-852624175da7 | note | Frequency - Before Installation
9d9aac6a-b187-50c7-bcbc-e7f671b406f3 | note | Activity - H
55508e0c-9e1b-52b3-a5d1-64da039c0ec6 | note | By - PE
e132fae1-e9b4-511f-a4c3-4d0a9e983806 | checkpoint | 4.01.05 - Drainage Pipes
7a5b659a-8903-53d2-923a-b6d92a4b1645 | note | Acceptance / Conformance Criteria - Shall be 110mm diameter NZTA F/2 compliant smooth bore perforated corrugated pipe with filter sock
7794d7ea-668a-5c32-bb0f-3680b36f6de3 | note | Standard / Specification - GWS - 5.3.4
ea8e0216-d0f1-54d5-92d8-9b9fa06b7076 | note | Verifying Document - Datasheet
d56eee96-b50c-5a01-acdc-8056d052ceaa | note | Frequency - Before Installation
395116fd-81ab-5fbc-8151-6255ffeb4a71 | note | Activity - H
8fb5b411-f437-5583-8180-b42cdf2a2a99 | note | By - PE
e7adda1d-89e3-5dee-b757-9e3f5f015cac | checkpoint | 4.01.06 - Geocomposite drainage board
cd6be02c-c749-5f25-acc3-4ffb2cefa944 | note | Acceptance / Conformance Criteria - Shall be Cirtex Armour flow, or similar accepted by the Engineer
ebf65b67-521d-5975-ac96-0b04a5a626cd | note | Standard / Specification - PS - 12
1de52d81-e41e-553d-9c21-f0f6340ab64c | note | Verifying Document - Datasheet
0987a3f2-09ee-5a15-a403-5dac4b2b4eb3 | note | Frequency - Before Installation
f2e98e9e-bba5-51b9-b10c-728c27a797b5 | note | Activity - H
29b83dfe-e46e-5abc-a914-d0df434d4e6f | note | By - PE
7d04c6ae-3cb1-5c0a-9796-1cc24d0858ea | section | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS
838e6cd4-76c0-5235-b72d-9a0f1a44ed66 | checkpoint | 5.01.01 - Excavation to subgrade
a44eca19-0903-53b8-b909-f430fbf6b9bf | note | Acceptance / Conformance Criteria - The foundation materials are to comprise natural Hinuera sand material, stiff Hinuera Silt or imported clean sand and must achieve a minimum of 4 blows per 100mm when tested with a Scala penetrometer. Any exposed silts must have vane shear strengths greater than 70kPa.
5722bcfc-454b-577a-9ad1-d3e3205134b4 | note | Standard / Specification - GWS - 5.2
915e6908-c8fe-5ac1-9db4-a947962d0041 | note | Verifying Document - Scala Results
a490c5fe-167a-5b44-ab44-b30841d751aa | note | Frequency - Every 10m
6289dc62-ab20-571f-9d3e-14f5140d96a5 | note | Activity - H
b7a8ce23-7996-5bcd-af78-3797ae943025 | note | By - SE
c4674b26-69c0-5262-a38b-746e46d5825b | checkpoint | 5.01.02 - Foundation Approval
88bbf40b-3a7e-5106-a1eb-b04cac8b3276 | note | Acceptance / Conformance Criteria - Results of the foundation material testing shall be supplied to the Engineer for approval and the prepared ground shall be inspected by the Engineer. Construction may not proceed until receiving Engineer’s approval.
87cf84f3-b265-54c8-91f4-8fe99cf580ac | note | Standard / Specification - GWS - 5.2
1686d54b-8287-51df-86cf-43bc7127c4b6 | note | Verifying Document - Approval
92f82e7a-8f29-5590-9360-08dca36f2305 | note | Frequency - Prior to proceeding. Min 48h notice to Engineer
75d2a1b0-4525-5583-9519-6b0bab956b25 | note | Activity - HP
13ca0be8-8086-5cfa-835c-649526f18337 | note | By - ENG
2ddb755a-f329-5467-ab5f-6a7fca5b3f95 | signoff | AUTHORITY HOLDPOINT
19ca66fa-e5a2-5cfc-b467-61317531b98d | checkpoint | 5.01.03 - Undercut subgrade
3a1426c3-4a4b-50d6-8c92-de9a0f129814 | note | Acceptance / Conformance Criteria - Any unsuitable materials, such as uncontrolled fill, contaminated materials or any weak or organic materials, shall be undercut and replaced with compacted granular fill (WHAP65 or equivalent) or Hinuera Sand. Surveyor to capture extent of undercut (if any) to include in asbuilt.
a162c6e4-10cd-5f4e-aee1-19aebcb4c8b1 | note | Standard / Specification - GWS - 5.2
f1f6c15f-6596-5cfe-9cd1-5734db4e100b | note | Verifying Document - Survey Record/ Photo record
37cd6678-71f7-5b8a-aaae-7266b0c53b90 | note | Frequency - If required
09fca302-cdb5-5d57-a109-7acf55153583 | note | Activity - I
839acd88-9afc-5d25-87e1-5dc15047bc55 | note | By - SE
11e626b6-30f1-58a8-84fd-9bad3add61ff | checkpoint | 5.01.04 - Undercut backfill compaction
686827fe-56ed-5bab-9d64-495ebf6340bf | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
e5515d9a-8cc8-5f73-9ca8-e055c4cc041f | note | Standard / Specification - GWS - Table 3
08c502fa-14b9-5b61-b1a0-0533d2b91f20 | note | Verifying Document - NDM Results
49be031b-95ea-5b55-97e3-3536950c4134 | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
14a27680-1a25-52b8-bd00-1fab40f44075 | note | Activity - H
c95dd2e2-6397-5c53-ba34-465a08f15a20 | note | By - SE
429c469f-d0be-5299-88a0-616d51d283a0 | checkpoint | 5.01.05 - Geogrid Installation
7c06f150-6a83-5a7f-bf9e-26add933060a | note | Acceptance / Conformance Criteria - Geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets. Engineer to inspect 1 layer prior to backfill.
8150c2df-f463-5e1e-9900-9baeb8241b95 | note | Standard / Specification - GWS - 4.1
502aec9f-4e98-5c7b-ade9-d8d49f08c81f | note | Verifying Document - Photo record
956b32f9-ff13-55e8-a916-4c3f79f7faac | note | Frequency - Each layer - 1 layer per abutment to be inspected
1f4aba03-43ec-52d8-9410-bef8fd128ad6 | note | Activity - HP
2ce0bc49-bf59-54a7-a221-56df0205defd | note | By - ENG
80a3b809-4a16-5781-8b97-a04ae2c7abfa | signoff | AUTHORITY HOLDPOINT
bd17909b-24fc-567d-8e74-41ab189fc4b3 | checkpoint | 5.01.06 - Backfill Installation
c7c2d1b0-c2f8-5768-8d67-067103ab63da | note | Acceptance / Conformance Criteria - All backfill is to be installed in 250mm lifts and compacted to the following standards.
523bffe5-aaee-5a9b-8e89-14e05f013cba | note | Standard / Specification - GWS - 5.3.3
11658044-8281-56e6-9f67-20faad0299fb | note | Verifying Document - Photo record
ac859c0c-278d-5b8e-a292-46ad56fb0962 | note | Frequency - Each layer
ef9db130-4c9f-5391-867a-972b372090fa | note | Activity - I
a3687b6e-7c6b-53f0-b274-e31e41cd696f | note | By - SUP
a62858e4-ea20-5ed9-923e-9ca82c01b7a0 | checkpoint | 5.01.07 - Backfill Compaction (NDM) (Gap 65)
f8d240d7-018f-5b3f-8c5e-fe7537ae63e0 | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
ad7fa407-e378-5634-ab93-1828e1f82e34 | note | Standard / Specification - GWS - Table 3
84067f73-90f3-5c9f-bcc9-3412062ae46f | note | Verifying Document - NDM Results
215fd151-1567-5313-ab16-40cc8c973c76 | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
b1904192-86c4-5dc0-983d-0c4625692197 | note | Activity - H
1759d2ab-8aaf-5e44-8271-0bca9708cfa4 | note | By - SE
8ecddfdf-b738-562d-924c-6d9e94ab9029 | checkpoint | 5.01.08 - Clegg/Proofroll (Gap 65)
98614c55-f750-506f-9503-10c3e30e1881 | note | Acceptance / Conformance Criteria - Proofroll of each layer. 4 Cleggs to be undertaken per NDM test. Engineer to proofroll/inspect final layer of load transfer platform.
2f9fe1ac-2fbc-57be-ac76-85de65fe652e | note | Standard / Specification - GWS - Table 3
4e604154-4a81-55e9-b377-2b88c923b018 | note | Verifying Document - Clegg Result sheet
bd438c47-31e5-566a-944c-a5b5c76088c7 | note | Frequency - Each layer - final layer to be inspected
774d86f1-ba7c-50b6-94d6-30bf5a948c3f | note | Activity - HP
7364a921-2ff7-5c35-9159-3054bb9afa4c | note | By - ENG
bb7a1071-2609-5dff-a667-8d15d7b69bbd | signoff | AUTHORITY HOLDPOINT
79e53a18-7c06-522e-b64b-df9faebbb82e | checkpoint | 5.01.09 - Scala Penetrometer (Hinuera Sand)
0de6b358-0f29-58af-ad62-e6befe37e01e | note | Acceptance / Conformance Criteria - Minimum average value over 5 tests of 5 blows per 100mm, minimum single value of 4 blows per 100mm
723574f2-3e35-56ba-972d-31c4f942de55 | note | Standard / Specification - GWS - Table 3
950d9fe5-4c1e-50e8-b794-ead1b2cf7d81 | note | Verifying Document - Scala Results
1f645c31-308b-548f-8dde-196580b6b892 | note | Frequency - 1 per 500m3, 1 test per 0.5m lift per 20m run of wall
6720fe90-9a00-56ad-8968-01ae35b290ac | note | Activity - H
714be469-f8be-5424-9050-e3ecf0a94400 | note | By - SE
1fa40bf2-514b-5091-af6a-f9081489cccb | checkpoint | 5.02.01 - Level founding platform
9c8eb987-df2c-50a7-95ae-edac73b9c3d4 | note | Acceptance / Conformance Criteria - The Contractor shall construct a 200 mm thick levelling pad on top of the load transfer platform to create a level founding platform to accept the MSE retaining wall.
ca1e2ed9-2c2b-5b18-a741-e994b2b723df | note | Standard / Specification - PS - 12
43ce2579-fec0-5318-87c6-4a8e9b3a20bb | note | Verifying Document - Site Photo / Checksheet
1b680dd9-e479-578f-bbde-69c1729e3ee9 | note | Frequency - Prior to Stone Strong block installation
a9c7ed43-8613-5ebc-857e-690eca1a5585 | note | Activity - I
b5fbdddf-aa08-5620-83bd-7340b7acd380 | note | By - SUP
70fcc93e-5f6b-523c-8390-a613fc5c0dd4 | checkpoint | 5.02.02 - Installation of blocks
90ef02e4-593b-5fb9-a2a3-b68fe5c81ecb | note | Acceptance / Conformance Criteria - Blocks to be installed to the height and location as detailed on the construction drawings. The table below details acceptable tollerances.
32d1b68c-0bfe-5bb2-abd7-26cb71e423d5 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
b12d3329-7987-5247-b922-ec1c92c9ed00 | note | Table 4: MSE Tolerances
dfcb71bb-f02b-56d1-bd66-3ef672ac4eab | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
8d01ee4b-e521-522d-8a7a-9bd9cf9cf39e | note | Element ¦¦ Vertical Position ¦¦ Horizontal Position ¦¦ Vertical Alignment ¦¦ Horizontal Alignment
c9b8de3b-7e7d-54be-a648-be447dff7dc0 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
18339fca-9026-508b-96e4-2fb4655e0c6a | note | Soil Surface ¦¦ ± 100mm ¦¦ N/A ¦¦ N/A ¦¦ N/A
7e0bf557-a381-509d-8795-4822c3e0c715 | note | Facings and wall structures ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
a3fbd331-d3ef-513a-8a89-9470f7fdb303 | note | Footings or supports ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
3c7b2ddd-a24b-5b7f-9049-436a8e69bce4 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
07037d56-3fae-5229-bb84-bcd2d797e781 | note | Standard / Specification - GWS - 5.4
48c1e9a8-8b89-527a-91c8-f72b261b72e0 | note | Verifying Document - Site Photo / Checksheet
54fda68a-448a-5dcd-8ed6-0a86c20b0e5a | note | Frequency - Each layer
913f0a58-b1ca-5bfb-8468-b952a9389447 | note | Activity - I
2396be86-4697-57ce-b7b9-b3a1d1c2257a | note | By - SUP
0738a9e4-1da3-543c-acc0-e874f185dfd9 | checkpoint | 5.02.03 - Paraweb Installation
0bef5334-c77a-5d85-8b74-f29c3c8ca7fc | note | Acceptance / Conformance Criteria - The correct number of parawebs are to be installed as shown on the construction drawings.
622c6a80-827b-564b-a1b0-826cc8553560 | note | ○ Para web is to be placed flat or with a 1% fall toward the rear of the wall. The Para web must be free of wrinkles and lightly tensioned prior to and during placement of backfill. Shallow trench to be dug toward the end of the paraweb, pin to be used to pull paraweb taught prior to backfilling.
50d68f77-c004-52f2-a57e-49698bdf2f38 | note | ○ The Para web must be continuous over the design embedment length and no joins are permitted unless adequately lapped and spliced according to the Manufacturer’s instructions.
8668a89a-332f-5adb-87ff-04813367b41f | note | ○ 150mm of fill cover is required before construction equipment can travel over the area
302495c3-5f3f-555b-bf19-8ba352b3798f | note | Standard / Specification - GWS - 5.3.2
e0f8ebd4-b7ce-5d74-8e8e-61d1497a1d0e | note | Verifying Document - Site Photo / Checksheet
19a36404-73ee-57c2-ad94-ea23f2a50577 | note | Frequency - Each layer
4ed90da9-8014-54fc-aff4-4d93fce754c9 | note | Activity - I
62c634e1-5096-505b-a986-ddb7ae13ae72 | note | By - SUP
d7e05ad4-017a-5c53-8850-a7a729d14f34 | checkpoint | 5.02.04 - Geotextile
f1a8bb54-9914-5908-800a-019f85bc7027 | note | Acceptance / Conformance Criteria - Geotextile to be placed against rear excavated face with a minimum overlap of 400mm between adjacent geotextile strips. Further Geotextile required to separate drainage aggeragate and MSE wall backfill, if sand is used. Short widths of geotextile to be placed across the internal open join area on the rear face of each Stonestrong block join to contain internal block void hardfill. Geotextile to be used to block paraweb voids within Stonestrong blocks that are not in use.
94cc05b3-7ed4-549e-b03a-e2ee7b360416 | note | Standard / Specification - SS - 5
647f2bf3-b023-5467-aedc-97bbb0515d40 | note | Verifying Document - Site Photo
7279ff2c-aff4-5b1d-a3f4-f63375d504cb | note | Frequency - Each Layer
a7b243d3-c6cb-535d-90b5-65a181495255 | note | Activity - I
bd118e8a-bc42-5377-b62a-9b6acb61244a | note | By - SUP
2eb38c46-8cb7-54e6-b99a-4b79e2de53ac | checkpoint | 5.02.05 - Drainage Outlet Installation
9ee8df9f-b706-55ee-8519-02e9f3ab549c | note | Acceptance / Conformance Criteria - Two x 160mm Drainage pipe wraped in filter sock to be installed along the external perimeter of the Load Transfer Platform.
a8364235-fc92-5b0f-b783-499970ee5864 | note | ○ Drainage aggregate to be placed along external perimeter of Load Transfer Platform for each MSE wall layer backfill, forming a Chimney Drain. Chimney Drain to be a minimum width of 300mm and extend to the base of the Load Transfer Platform.
bfdccc2a-f87a-559a-a09d-f22ca6b2550d | note | ○ Internal block void hardfill to be 20/40 drainage aggregate or similar approved by engineer.
f50624df-79b1-5d2c-a119-85e58c1d959e | note | ○ Additional Drainage pipe wrapped in 0.75m3/m run of drainage metal only required beneath wall embedment at toe of the outside of the wall if the slope doesn’t grade away from the toe of the wall.
a9df338d-dd93-5a01-b470-27f025b047c8 | note | ○ Drainage outlets shall be connected to the reticulated stormwater system or other approved outlet structure at the discretion of the design engineer
ba32300a-18c6-51ad-9b3e-f5c37464fe0b | note | Standard / Specification - SS - 5
53567f00-05db-5a58-917d-b1a978e56890 | note | Verifying Document - Site Photo / Checksheet
6be29782-2749-5e9e-acd2-446695c190cf | note | Frequency - During Installation
342b7fa8-1803-5fd1-9c9b-a45f3d56f346 | note | Activity - I
fd19484e-4527-5d4c-ba92-996f5eaf5baa | note | By - SUP
1034be8f-e2b5-5d56-ad2f-7ae17d328c57 | checkpoint | 5.02.06 - Backfill Installation
68b82bbb-bd2b-500a-9ace-74ec7c5ebb50 | note | Acceptance / Conformance Criteria - All backfill is to be installed in 250mm lifts adnd compacted to the following standards.
31c539fd-4460-53ad-bfdf-2e97fcb8b655 | note | Standard / Specification - GWS - 5.3.3
633cfa75-f662-58c2-a120-4024e3c6b0a4 | note | Verifying Document - Site Photo / Checksheet
6d4d0c18-479a-58d2-a5ec-cf710b5f1faa | note | Frequency - Each layer
5972cd9e-2fb0-509b-bef1-f765dd7cccb7 | note | Activity - I
b83ffa94-0016-517c-bb97-f82c899c2703 | note | By - SUP
35abd0c3-22bf-5ac6-b46a-a8a9993e38f8 | checkpoint | 5.02.07 - Nuclear Densometer (NDM) (Gap 65)
f13ff92b-3515-51d0-a988-a8689f2dd02b | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
4a4d2b6a-8a2e-5174-a75c-a0f7cf753f69 | note | Standard / Specification - GWS - Table 3
6554928e-3918-5c68-b1ac-81e6cb332423 | note | Verifying Document - NDM Results
98493087-ecca-5702-9b92-25f0664f918b | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
554f611d-c99e-592d-bee2-843015f016da | note | Activity - H
ccf5b3da-cdf5-5795-9145-2a6b32d69f7e | note | By - SE
bbcbe397-d3aa-5f25-b343-5d2e0f43e6f8 | checkpoint | 5.02.08 - Clegg/Proofroll (Gap 65)
003d8931-bc62-5135-b7be-32aa75313eac | note | Acceptance / Conformance Criteria - Proofroll of each layer. 4 Cleggs to be undertaken per NDM test.
3874ad51-8f8b-575e-9170-0695e7fdc9bc | note | Standard / Specification - GWS - Table 3
4d765a6d-f986-55ae-a453-6684618ffc0e | note | Verifying Document - Clegg Result sheet
12a070cf-7dac-57ab-a68e-41e36105e8a1 | note | Frequency - Each layer
0313e548-65cb-50f0-85a4-231e5e4b576b | note | Activity - H
dcd71dcd-85cb-5dee-945b-745855383c9a | note | By - SE
e466154a-3525-5208-8981-a1953fc53c31 | checkpoint | 5.02.09 - Scala Penetrometer (Hinuera Sand)
4efbde40-a847-5874-adf2-744ee100a9d9 | note | Acceptance / Conformance Criteria - Minimum average value over 5 tests of 5 blows per 100mm, minimum single value of 4 blows per 100mm
78e0595b-f746-5ce0-b84e-30718f228843 | note | Standard / Specification - GWS - Table 3
afe343f9-b761-5bae-855e-8f1669892985 | note | Verifying Document - Scala Results
3242c858-14d8-526d-8fce-da11c78994d1 | note | Frequency - 1 per 500m3, 1 test per 0.5m lift per 20m run of wall
3b61ccc5-55eb-529c-ab6e-c36b4195619a | note | Activity - H
f0eff603-e0e2-56fe-a76e-7f727936301e | note | By - SE
60d12d54-946a-5d14-a179-44f6b0bbe1c4 | checkpoint | 5.03.01 - Tensar Triaxial 170
b7b6b90d-c046-44f6-84e9-98097ed32631 | note | Acceptance / Conformance Criteria - Geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 300mm is required between sheets. Engineer to inspect layer prior to backfill.
24628f91-905b-4919-9547-c3db25e1e6db | note | Standard / Specification - GWS - 4.2
54840355-d1ea-4777-9d5b-6ad907f4fc01 | note | Verifying Document - Photo record
e4c27b20-14a0-466b-932c-f2bfe6c5a0b5 | note | Frequency - Each layer - 1 layer per abutment to be inspected
92855898-8fd4-41e9-9ffc-b8cdb7a3f09f | note | Activity - HP
136c3b84-b512-41df-87e1-dba880b264ca | note | By - ENG
514384b9-8a6a-50c3-9354-b04bfb25986b | signoff | AUTHORITY HOLDPOINT
4d8b933a-5957-55bb-8b21-ef93921ef05e | checkpoint | 5.03.02 - Tensar Uniaxial RE580
0ea32e00-9760-40e8-9fe5-b080daf044a9 | note | Acceptance / Conformance Criteria - Geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. No overlapping requirements when connected with Bodkin joints. Engineer to inspect each layer prior to backfill. Grids must be taut prior to backffilling
8fb0fc4e-66e4-4c9c-b0e4-e4b8640e477c | note | Standard / Specification - GWS - 4.2
f13ceb32-2533-41ac-bfeb-dca8e273f776 | note | Verifying Document - Photo record
022bcb15-4959-4678-b859-596c2cd1f642 | note | Frequency - Each layer - 1 layer per abutment to be inspected
b48fd9c3-bfcf-450e-b240-2de1ae9976fc | note | Activity - HP
f15f51f3-5909-43a2-9ce0-74db5d1700c4 | note | By - ENG
1749caf0-95ae-558d-9e40-0cb21ba1a8ff | signoff | AUTHORITY HOLDPOINT
68eb27de-28a0-5c6b-b80b-1a0b3a7dabaf | checkpoint | 5.04.01 - Settlement Pins
6be00cc8-35f7-58b4-9aac-3e2f7da37af6 | note | Acceptance / Conformance Criteria - Settlement pins shall be installed within 24 hours of reaching design subgrade level. Survey measurements are to be undertaken to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
a15120ed-c718-5d31-baef-0c8bf1202b40 | note | Standard / Specification - GWS - 6.3
c328b2c9-2589-5ea8-a5a5-29f4fbb679b6 | note | Verifying Document - Survey Results (in paper as well as electronic format)
c44e4189-f4cd-5c8a-94c5-7045748d766f | note | Frequency - Weekly for the first month, then monthly
976b9f25-82ac-5367-a238-3dc87271bf9f | note | Activity - R
f42af643-c395-58bc-a22e-585a9ebaf8f8 | note | By - SV, ENG
65bdb657-7dd2-575b-8068-4d8a3bbf8080 | checkpoint | 5.04.02 - Settlement Targets
08507682-93c4-5452-97e2-8150c20bfab6 | note | Acceptance / Conformance Criteria - Targets shall be fixed immediately after completion of the first row of retaining wall blocks at each location and the initial baseline survey reading made prior to the subsequent row of retaining wall blocks placed.
480b8b47-6145-593e-9237-ad72d6db0cee | note | ○ Survey measurements are to be undertaken to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
28d6069c-16cb-52bf-8b0f-2855091f5e5d | note | Standard / Specification - GWS - 6.4
4d86ed34-2564-57a8-98f7-1460af0da7f9 | note | Verifying Document - Survey Results (in paper as well as electronic format)
ee49474b-e7c1-5904-abb4-5613386fddb2 | note | Frequency - Weekly for the first month, then monthly
67d177c4-6ae0-544d-8cca-4963c96f1e14 | note | Activity - R
cd844407-15dc-5abf-ab6a-581e0b72a97e | note | By - SV, ENG
19e8c979-4bbd-5b44-b6f1-f5f0c60cc435 | checkpoint | 5.04.03 - Engineers Approval
129d7748-60d8-5b2a-9b1a-b1ea68c4b7f9 | note | Acceptance / Conformance Criteria - Geotechnical engineer assesment required before commencement of Pavement construction
9c535da8-1110-57cf-bd8b-4b3a4cb67048 | note | Standard / Specification - BBO
c03b5ad1-5238-50bf-94b3-a6d95d7561a5 | note | Verifying Document - Written approval
43a8c2cd-762b-5905-a363-f38629034b45 | note | Frequency - Prior to pavement construction
e735b9e1-02c3-5526-9bcd-5fbbcfc69b4f | note | Activity - HP
655aedea-3982-579f-8070-73df15d33ff2 | note | By - ENG
2ef33948-5bbc-5304-bec0-43db699435f7 | signoff | AUTHORITY HOLDPOINT
cd33a7f8-9b6c-5422-93be-dcae98eaa460 | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
c67c36c3-6604-547c-97e6-f35b09622953 | checkpoint | 6.01.02 - Draft Redline Drawings
fa2526ab-b8b9-509f-b4ec-43a5d96dfe8c | note | Acceptance / Conformance Criteria - Draft as-builts completed on the completion of MSE wall including red pen mark up to IFC drawing changes.
1b08806c-38dd-54fa-9d51-79482791edaf | note | ○ The draft as-builts shall be provided on a continual basis throughout the project for verification by the Engineer, and as a minimum shall be provided in electronic form prior to application for Practical Completion.
71c7e106-4037-5b64-8bc7-4d64f708bf04 | note | Standard / Specification - PS 2.2.17
a9791038-927a-56e8-92bc-092094da73cb | note | Verifying Document - Draft As-Builts Drawings
8b640c55-480e-521c-b672-75b78b29968d | note | Frequency - Prior to PC
66bc92ec-3655-5cdd-82f9-c85ade2d83b3 | note | Activity - H
0f0c9cf5-c28d-5026-9f36-cb989728faad | note | By - SV / PE
a850fe28-a059-5334-ba21-4885b69661b0 | checklist | SYS - ITP - Retaining Walls - v1 |  | ITP - Retaining Walls
8c9335a7-3af5-5e47-a887-39a89ff08c27 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
dfb723bb-584a-5713-be6d-07b0f19feadc | note | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
e2830cdf-362b-5f0e-8d22-f68f1a98219d | note | Standard / Specification - Downer
14282032-c33f-55dc-9ae6-ba093f01c0fa | note | Verifying Document - Construction Pack
9e7ee91d-d82a-5694-af12-0f67083b3c87 | note | Frequency - Submit 10 days prior to commencement of works
2a4ab9d4-071d-53fa-ac91-77f26febe2a2 | note | Activity - HP
d5d6a8c7-50e2-54b9-96ba-d6ed63ed046c | note | By - ENG
ca255811-cbe5-57f5-8b49-d49ad30655f3 | signoff | AUTHORITY HOLDPOINT
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
dc572b14-0ed6-54c7-bc8f-85ed00c03dfe | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
3e946a9d-b5c8-50e7-96e0-0400e8f6e89c | note | Standard / Specification - Downer
34bb53e5-aed2-52e3-a5c2-9f81d0a823ca | note | Verifying Document - Survey Records
61d76f5d-0ad9-583f-ac76-86ad184fa739 | note | Frequency - Prior to Works
376f33df-3b2b-5b0c-ab68-eb1a544a497d | note | Activity - H
c900da17-59f9-5691-b9d1-3bcd5996d491 | note | By - SV
a24a2c58-bf6f-5474-883c-40044bad1fc7 | checkpoint | 3.01.03 - Service Location
b9f21eeb-7675-5741-9a79-4af249ac51cd | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
434102cd-5777-54cc-b4b5-32744d498024 | note | Standard / Specification - Downer
07a728fa-eece-56e9-af95-f512783809d3 | note | Verifying Document - Excavation Permit
077eeafa-3bad-5034-9687-5e46d0d70d1b | note | Frequency - Prior to Excavation
f621f899-2387-5113-900d-6bf9fc014ca0 | note | Activity - H
765fd8e2-b34a-5911-8b80-bd9e215f5033 | note | By - SE
0a214a7a-124a-5898-a837-e29e83751df0 | checkpoint | 3.01.04 - Internal Permits
b356337b-ff8b-5218-b916-0250a1283683 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
a1b106e9-f9c2-5c82-9b78-bc7a5e36b3d8 | note | Standard / Specification - Downer
62309b3c-27a8-5c74-8629-890633f13944 | note | Verifying Document - Internal Permits
83e97ed8-8c87-565f-9e65-f307d506c6a2 | note | Frequency - Prior to Excavation
d9a60eb7-5a01-5a8f-8f3f-6ce4ccaaa502 | note | Activity - H
3d563ef1-3b79-577d-b94f-308e34e1ca4e | note | By - SE
917e2881-0901-542f-ae25-686bf9c47009 | checkpoint | 3.01.05 - External Permits
b3b0e978-a810-584e-aa53-c42ce3c97641 | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
da4f0b71-5efa-5c01-ad1a-988c4ed5ce74 | note | Standard / Specification - Downer
9637f9ab-b7c6-54c8-8436-24c62804f0c4 | note | Verifying Document - External Permits
86a70157-a919-5dd5-aa32-c8681501a34c | note | Frequency - Prior to Excavation
bdcdc434-1b5d-5073-8411-b8512f1171ba | note | Activity - H
9a96dd8f-f51a-5d85-90aa-2277fca1a9b8 | note | By - PE
a1302970-0389-558d-b43c-67b14bbfc27a | checkpoint | 3.01.06 - Approved Construction Drawings
9ff0acba-9273-52f4-a0a4-2ab6d34c8a37 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
35f67329-e2c7-5487-a6d4-58b982b7c249 | note | Standard / Specification - Downer
3dfe5430-9c4a-5998-aade-3c0355af63af | note | Verifying Document - IFC Drawings
2b7e4a6a-c00a-5a00-ac72-61e46e5f805a | note | Frequency - Prior to works start
64beb55c-164d-586e-993a-71bf994ecd03 | note | Activity - H
16b491c1-6520-5184-a1cd-e89a84b6dddc | note | By - PE
34b3d838-f63d-5499-aad4-14b7c1eb24ae | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS
1437ac3f-e25b-5932-8866-3f1e2bab518b | checkpoint | 4.01.01 - Stone Strong Block Molds
24a4862f-20e9-5858-9e47-682e8ebdcd0f | note | Acceptance / Conformance Criteria - Stonestrong blocks to be supplied by an approved supplier. The Contractor shall liaise with the Principal-appointed Cultural Artist to coordinate carving of the supplied blanks and the production of moulds & blocks
b7e1ac9b-4fd0-5aed-91f1-207545543544 | note | Standard / Specification - PS - 12
4fbb56e2-610f-5ab3-b571-8d5a95c19942 | note | Verifying Document - Conforming Molds Post Carving
4ea6de2e-aec5-50b2-a438-bd4bd870e686 | note | Frequency - Before Installation
d4a2256c-c353-57e5-9fce-3979c4f41a52 | note | Activity - H
1c7d0313-833b-5b02-8452-76e926b94d30 | note | By - PE
a3cd3258-fb54-5b31-83f8-74d9198b64d1 | checkpoint | 4.01.02 - MSE retaining wall backfill Material
cc3d6c38-7cdf-5ccc-b3de-82e5fa7d81b3 | note | Acceptance / Conformance Criteria - Backfill is to comprise a well graded, granular material such as GAP65 or site won Hinuera Sand, which must be free of any deleterious material. Sand backfill shall have a fines content (less than 0.075mm diameter) of no more than 10%. Labratory MDD (x2 per material type) at standard compaction
22721888-49d4-5ebd-a823-b786fde9c2dd | note | Standard / Specification - GWS - 5.3.3
f760ee7e-3e30-5748-ac8d-dd6f4cff2189 | note | Verifying Document - Lab Results
ac1f5c71-71b7-5418-a6b3-d83649055b3c | note | Frequency - Prior to works
951e9d5f-bd61-5982-b242-bf9f0c0caffb | note | Activity - H
8ebf4f1b-07e1-53f7-b331-bcd4af254b27 | note | By - PE
05bce6c9-76c8-5aeb-94f0-6addb618072e | checkpoint | 4.01.03 - Geogrid
a5ac5972-5125-5559-af6d-1c6c4e7dedcc | note | Acceptance / Conformance Criteria - Geogrid to be Miragrid GX200/30 or similar approved
9f8013ff-90e1-57c2-9d72-3a9dffbf0e78 | note | Standard / Specification - GWS - 5.3.1
0a7a8e2c-6643-54d0-a7a9-d2756a3ae4b4 | note | Verifying Document - Datasheet
8616060a-d369-50b8-aaba-ef3009718c94 | note | Frequency - Before Installation
a58b35f4-bec7-526e-a186-cb8cfac7ff0c | note | Activity - H
96867ef7-72bf-5c39-9276-a8fa57a392dc | note | By - PE
6e039cf8-38d9-583d-81da-a16916cec0db | checkpoint | 4.01.04 - Para web
1caebfdf-02c1-5487-a1c2-99494d3a7d32 | note | Acceptance / Conformance Criteria - Paraweb to be the correct grade: Paraweb 2D-50
fc6b5ecc-9ae5-5429-b362-4e4e740b858a | note | Standard / Specification - GWS - 5.3.2
c6a61179-13b0-5cce-86df-0b2aee73ba18 | note | Verifying Document - Datasheet
d6d44771-ac67-536d-add9-852624175da7 | note | Frequency - Before Installation
9d9aac6a-b187-50c7-bcbc-e7f671b406f3 | note | Activity - H
55508e0c-9e1b-52b3-a5d1-64da039c0ec6 | note | By - PE
e132fae1-e9b4-511f-a4c3-4d0a9e983806 | checkpoint | 4.01.05 - Drainage Pipes
7a5b659a-8903-53d2-923a-b6d92a4b1645 | note | Acceptance / Conformance Criteria - Shall be 110mm diameter NZTA F/2 compliant smooth bore perforated corrugated pipe with filter sock
7794d7ea-668a-5c32-bb0f-3680b36f6de3 | note | Standard / Specification - GWS - 5.3.4
ea8e0216-d0f1-54d5-92d8-9b9fa06b7076 | note | Verifying Document - Datasheet
d56eee96-b50c-5a01-acdc-8056d052ceaa | note | Frequency - Before Installation
395116fd-81ab-5fbc-8151-6255ffeb4a71 | note | Activity - H
8fb5b411-f437-5583-8180-b42cdf2a2a99 | note | By - PE
e7adda1d-89e3-5dee-b757-9e3f5f015cac | checkpoint | 4.01.06 - Geocomposite drainage board
cd6be02c-c749-5f25-acc3-4ffb2cefa944 | note | Acceptance / Conformance Criteria - Shall be Cirtex Armour flow, or similar accepted by the Engineer
ebf65b67-521d-5975-ac96-0b04a5a626cd | note | Standard / Specification - PS - 12
1de52d81-e41e-553d-9c21-f0f6340ab64c | note | Verifying Document - Datasheet
0987a3f2-09ee-5a15-a403-5dac4b2b4eb3 | note | Frequency - Before Installation
f2e98e9e-bba5-51b9-b10c-728c27a797b5 | note | Activity - H
29b83dfe-e46e-5abc-a914-d0df434d4e6f | note | By - PE
7d04c6ae-3cb1-5c0a-9796-1cc24d0858ea | section | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS
838e6cd4-76c0-5235-b72d-9a0f1a44ed66 | checkpoint | 5.01.01 - Excavation to subgrade
a44eca19-0903-53b8-b909-f430fbf6b9bf | note | Acceptance / Conformance Criteria - The foundation materials are to comprise natural Hinuera sand material, stiff Hinuera Silt or imported clean sand and must achieve a minimum of 4 blows per 100mm when tested with a Scala penetrometer. Any exposed silts must have vane shear strengths greater than 70kPa.
5722bcfc-454b-577a-9ad1-d3e3205134b4 | note | Standard / Specification - GWS - 5.2
915e6908-c8fe-5ac1-9db4-a947962d0041 | note | Verifying Document - Scala Results
a490c5fe-167a-5b44-ab44-b30841d751aa | note | Frequency - Every 10m
6289dc62-ab20-571f-9d3e-14f5140d96a5 | note | Activity - H
b7a8ce23-7996-5bcd-af78-3797ae943025 | note | By - SE
c4674b26-69c0-5262-a38b-746e46d5825b | checkpoint | 5.01.02 - Foundation Approval
88bbf40b-3a7e-5106-a1eb-b04cac8b3276 | note | Acceptance / Conformance Criteria - Results of the foundation material testing shall be supplied to the Engineer for approval and the prepared ground shall be inspected by the Engineer. Construction may not proceed until receiving Engineer’s approval.
87cf84f3-b265-54c8-91f4-8fe99cf580ac | note | Standard / Specification - GWS - 5.2
1686d54b-8287-51df-86cf-43bc7127c4b6 | note | Verifying Document - Approval
92f82e7a-8f29-5590-9360-08dca36f2305 | note | Frequency - Prior to proceeding. Min 48h notice to Engineer
75d2a1b0-4525-5583-9519-6b0bab956b25 | note | Activity - HP
13ca0be8-8086-5cfa-835c-649526f18337 | note | By - ENG
2ddb755a-f329-5467-ab5f-6a7fca5b3f95 | signoff | AUTHORITY HOLDPOINT
19ca66fa-e5a2-5cfc-b467-61317531b98d | checkpoint | 5.01.03 - Undercut subgrade
3a1426c3-4a4b-50d6-8c92-de9a0f129814 | note | Acceptance / Conformance Criteria - Any unsuitable materials, such as uncontrolled fill, contaminated materials or any weak or organic materials, shall be undercut and replaced with compacted granular fill (WHAP65 or equivalent) or Hinuera Sand. Surveyor to capture extent of undercut (if any) to include in asbuilt.
a162c6e4-10cd-5f4e-aee1-19aebcb4c8b1 | note | Standard / Specification - GWS - 5.2
f1f6c15f-6596-5cfe-9cd1-5734db4e100b | note | Verifying Document - Survey Record/ Photo record
37cd6678-71f7-5b8a-aaae-7266b0c53b90 | note | Frequency - If required
09fca302-cdb5-5d57-a109-7acf55153583 | note | Activity - I
839acd88-9afc-5d25-87e1-5dc15047bc55 | note | By - SE
11e626b6-30f1-58a8-84fd-9bad3add61ff | checkpoint | 5.01.04 - Undercut backfill compaction
686827fe-56ed-5bab-9d64-495ebf6340bf | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
e5515d9a-8cc8-5f73-9ca8-e055c4cc041f | note | Standard / Specification - GWS - Table 3
08c502fa-14b9-5b61-b1a0-0533d2b91f20 | note | Verifying Document - NDM Results
49be031b-95ea-5b55-97e3-3536950c4134 | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
14a27680-1a25-52b8-bd00-1fab40f44075 | note | Activity - H
c95dd2e2-6397-5c53-ba34-465a08f15a20 | note | By - SE
429c469f-d0be-5299-88a0-616d51d283a0 | checkpoint | 5.01.05 - Geogrid Installation
7c06f150-6a83-5a7f-bf9e-26add933060a | note | Acceptance / Conformance Criteria - Geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets. Engineer to inspect 1 layer prior to backfill.
8150c2df-f463-5e1e-9900-9baeb8241b95 | note | Standard / Specification - GWS - 4.1
502aec9f-4e98-5c7b-ade9-d8d49f08c81f | note | Verifying Document - Photo record
956b32f9-ff13-55e8-a916-4c3f79f7faac | note | Frequency - Each layer - 1 layer per abutment to be inspected
1f4aba03-43ec-52d8-9410-bef8fd128ad6 | note | Activity - HP
2ce0bc49-bf59-54a7-a221-56df0205defd | note | By - ENG
80a3b809-4a16-5781-8b97-a04ae2c7abfa | signoff | AUTHORITY HOLDPOINT
bd17909b-24fc-567d-8e74-41ab189fc4b3 | checkpoint | 5.01.06 - Backfill Installation
c7c2d1b0-c2f8-5768-8d67-067103ab63da | note | Acceptance / Conformance Criteria - All backfill is to be installed in 250mm lifts and compacted to the following standards.
523bffe5-aaee-5a9b-8e89-14e05f013cba | note | Standard / Specification - GWS - 5.3.3
11658044-8281-56e6-9f67-20faad0299fb | note | Verifying Document - Photo record
ac859c0c-278d-5b8e-a292-46ad56fb0962 | note | Frequency - Each layer
ef9db130-4c9f-5391-867a-972b372090fa | note | Activity - I
a3687b6e-7c6b-53f0-b274-e31e41cd696f | note | By - SUP
a62858e4-ea20-5ed9-923e-9ca82c01b7a0 | checkpoint | 5.01.07 - Backfill Compaction (NDM) (Gap 65)
f8d240d7-018f-5b3f-8c5e-fe7537ae63e0 | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
ad7fa407-e378-5634-ab93-1828e1f82e34 | note | Standard / Specification - GWS - Table 3
84067f73-90f3-5c9f-bcc9-3412062ae46f | note | Verifying Document - NDM Results
215fd151-1567-5313-ab16-40cc8c973c76 | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
b1904192-86c4-5dc0-983d-0c4625692197 | note | Activity - H
1759d2ab-8aaf-5e44-8271-0bca9708cfa4 | note | By - SE
8ecddfdf-b738-562d-924c-6d9e94ab9029 | checkpoint | 5.01.08 - Clegg/Proofroll (Gap 65)
98614c55-f750-506f-9503-10c3e30e1881 | note | Acceptance / Conformance Criteria - Proofroll of each layer. 4 Cleggs to be undertaken per NDM test. Engineer to proofroll/inspect final layer of load transfer platform.
2f9fe1ac-2fbc-57be-ac76-85de65fe652e | note | Standard / Specification - GWS - Table 3
4e604154-4a81-55e9-b377-2b88c923b018 | note | Verifying Document - Clegg Result sheet
bd438c47-31e5-566a-944c-a5b5c76088c7 | note | Frequency - Each layer - final layer to be inspected
774d86f1-ba7c-50b6-94d6-30bf5a948c3f | note | Activity - HP
7364a921-2ff7-5c35-9159-3054bb9afa4c | note | By - ENG
bb7a1071-2609-5dff-a667-8d15d7b69bbd | signoff | AUTHORITY HOLDPOINT
79e53a18-7c06-522e-b64b-df9faebbb82e | checkpoint | 5.01.09 - Scala Penetrometer (Hinuera Sand)
0de6b358-0f29-58af-ad62-e6befe37e01e | note | Acceptance / Conformance Criteria - Minimum average value over 5 tests of 5 blows per 100mm, minimum single value of 4 blows per 100mm
723574f2-3e35-56ba-972d-31c4f942de55 | note | Standard / Specification - GWS - Table 3
950d9fe5-4c1e-50e8-b794-ead1b2cf7d81 | note | Verifying Document - Scala Results
1f645c31-308b-548f-8dde-196580b6b892 | note | Frequency - 1 per 500m3, 1 test per 0.5m lift per 20m run of wall
6720fe90-9a00-56ad-8968-01ae35b290ac | note | Activity - H
714be469-f8be-5424-9050-e3ecf0a94400 | note | By - SE
1fa40bf2-514b-5091-af6a-f9081489cccb | checkpoint | 5.02.01 - Level founding platform
9c8eb987-df2c-50a7-95ae-edac73b9c3d4 | note | Acceptance / Conformance Criteria - The Contractor shall construct a 200 mm thick levelling pad on top of the load transfer platform to create a level founding platform to accept the MSE retaining wall.
ca1e2ed9-2c2b-5b18-a741-e994b2b723df | note | Standard / Specification - PS - 12
43ce2579-fec0-5318-87c6-4a8e9b3a20bb | note | Verifying Document - Site Photo / Checksheet
1b680dd9-e479-578f-bbde-69c1729e3ee9 | note | Frequency - Prior to Stone Strong block installation
a9c7ed43-8613-5ebc-857e-690eca1a5585 | note | Activity - I
b5fbdddf-aa08-5620-83bd-7340b7acd380 | note | By - SUP
70fcc93e-5f6b-523c-8390-a613fc5c0dd4 | checkpoint | 5.02.02 - Installation of blocks
90ef02e4-593b-5fb9-a2a3-b68fe5c81ecb | note | Acceptance / Conformance Criteria - Blocks to be installed to the height and location as detailed on the construction drawings. The table below details acceptable tollerances.
32d1b68c-0bfe-5bb2-abd7-26cb71e423d5 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
b12d3329-7987-5247-b922-ec1c92c9ed00 | note | Table 4: MSE Tolerances
dfcb71bb-f02b-56d1-bd66-3ef672ac4eab | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
8d01ee4b-e521-522d-8a7a-9bd9cf9cf39e | note | Element ¦¦ Vertical Position ¦¦ Horizontal Position ¦¦ Vertical Alignment ¦¦ Horizontal Alignment
c9b8de3b-7e7d-54be-a648-be447dff7dc0 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
18339fca-9026-508b-96e4-2fb4655e0c6a | note | Soil Surface ¦¦ ± 100mm ¦¦ N/A ¦¦ N/A ¦¦ N/A
7e0bf557-a381-509d-8795-4822c3e0c715 | note | Facings and wall structures ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
a3fbd331-d3ef-513a-8a89-9470f7fdb303 | note | Footings or supports ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
3c7b2ddd-a24b-5b7f-9049-436a8e69bce4 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
07037d56-3fae-5229-bb84-bcd2d797e781 | note | Standard / Specification - GWS - 5.4
48c1e9a8-8b89-527a-91c8-f72b261b72e0 | note | Verifying Document - Site Photo / Checksheet
54fda68a-448a-5dcd-8ed6-0a86c20b0e5a | note | Frequency - Each layer
913f0a58-b1ca-5bfb-8468-b952a9389447 | note | Activity - I
2396be86-4697-57ce-b7b9-b3a1d1c2257a | note | By - SUP
0738a9e4-1da3-543c-acc0-e874f185dfd9 | checkpoint | 5.02.03 - Paraweb Installation
0bef5334-c77a-5d85-8b74-f29c3c8ca7fc | note | Acceptance / Conformance Criteria - The correct number of parawebs are to be installed as shown on the construction drawings.
622c6a80-827b-564b-a1b0-826cc8553560 | note | ○ Para web is to be placed flat or with a 1% fall toward the rear of the wall. The Para web must be free of wrinkles and lightly tensioned prior to and during placement of backfill. Shallow trench to be dug toward the end of the paraweb, pin to be used to pull paraweb taught prior to backfilling.
50d68f77-c004-52f2-a57e-49698bdf2f38 | note | ○ The Para web must be continuous over the design embedment length and no joins are permitted unless adequately lapped and spliced according to the Manufacturer’s instructions.
8668a89a-332f-5adb-87ff-04813367b41f | note | ○ 150mm of fill cover is required before construction equipment can travel over the area
302495c3-5f3f-555b-bf19-8ba352b3798f | note | Standard / Specification - GWS - 5.3.2
e0f8ebd4-b7ce-5d74-8e8e-61d1497a1d0e | note | Verifying Document - Site Photo / Checksheet
19a36404-73ee-57c2-ad94-ea23f2a50577 | note | Frequency - Each layer
4ed90da9-8014-54fc-aff4-4d93fce754c9 | note | Activity - I
62c634e1-5096-505b-a986-ddb7ae13ae72 | note | By - SUP
d7e05ad4-017a-5c53-8850-a7a729d14f34 | checkpoint | 5.02.04 - Geotextile
f1a8bb54-9914-5908-800a-019f85bc7027 | note | Acceptance / Conformance Criteria - Geotextile to be placed against rear excavated face with a minimum overlap of 400mm between adjacent geotextile strips. Further Geotextile required to separate drainage aggeragate and MSE wall backfill, if sand is used. Short widths of geotextile to be placed across the internal open join area on the rear face of each Stonestrong block join to contain internal block void hardfill. Geotextile to be used to block paraweb voids within Stonestrong blocks that are not in use.
94cc05b3-7ed4-549e-b03a-e2ee7b360416 | note | Standard / Specification - SS - 5
647f2bf3-b023-5467-aedc-97bbb0515d40 | note | Verifying Document - Site Photo
7279ff2c-aff4-5b1d-a3f4-f63375d504cb | note | Frequency - Each Layer
a7b243d3-c6cb-535d-90b5-65a181495255 | note | Activity - I
bd118e8a-bc42-5377-b62a-9b6acb61244a | note | By - SUP
2eb38c46-8cb7-54e6-b99a-4b79e2de53ac | checkpoint | 5.02.05 - Drainage Outlet Installation
9ee8df9f-b706-55ee-8519-02e9f3ab549c | note | Acceptance / Conformance Criteria - Two x 160mm Drainage pipe wraped in filter sock to be installed along the external perimeter of the Load Transfer Platform.
a8364235-fc92-5b0f-b783-499970ee5864 | note | ○ Drainage aggregate to be placed along external perimeter of Load Transfer Platform for each MSE wall layer backfill, forming a Chimney Drain. Chimney Drain to be a minimum width of 300mm and extend to the base of the Load Transfer Platform.
bfdccc2a-f87a-559a-a09d-f22ca6b2550d | note | ○ Internal block void hardfill to be 20/40 drainage aggregate or similar approved by engineer.
f50624df-79b1-5d2c-a119-85e58c1d959e | note | ○ Additional Drainage pipe wrapped in 0.75m3/m run of drainage metal only required beneath wall embedment at toe of the outside of the wall if the slope doesn’t grade away from the toe of the wall.
a9df338d-dd93-5a01-b470-27f025b047c8 | note | ○ Drainage outlets shall be connected to the reticulated stormwater system or other approved outlet structure at the discretion of the design engineer
ba32300a-18c6-51ad-9b3e-f5c37464fe0b | note | Standard / Specification - SS - 5
53567f00-05db-5a58-917d-b1a978e56890 | note | Verifying Document - Site Photo / Checksheet
6be29782-2749-5e9e-acd2-446695c190cf | note | Frequency - During Installation
342b7fa8-1803-5fd1-9c9b-a45f3d56f346 | note | Activity - I
fd19484e-4527-5d4c-ba92-996f5eaf5baa | note | By - SUP
1034be8f-e2b5-5d56-ad2f-7ae17d328c57 | checkpoint | 5.02.06 - Backfill Installation
68b82bbb-bd2b-500a-9ace-74ec7c5ebb50 | note | Acceptance / Conformance Criteria - All backfill is to be installed in 250mm lifts adnd compacted to the following standards.
31c539fd-4460-53ad-bfdf-2e97fcb8b655 | note | Standard / Specification - GWS - 5.3.3
633cfa75-f662-58c2-a120-4024e3c6b0a4 | note | Verifying Document - Site Photo / Checksheet
6d4d0c18-479a-58d2-a5ec-cf710b5f1faa | note | Frequency - Each layer
5972cd9e-2fb0-509b-bef1-f765dd7cccb7 | note | Activity - I
b83ffa94-0016-517c-bb97-f82c899c2703 | note | By - SUP
35abd0c3-22bf-5ac6-b46a-a8a9993e38f8 | checkpoint | 5.02.07 - Nuclear Densometer (NDM) (Gap 65)
f13ff92b-3515-51d0-a988-a8689f2dd02b | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
4a4d2b6a-8a2e-5174-a75c-a0f7cf753f69 | note | Standard / Specification - GWS - Table 3
6554928e-3918-5c68-b1ac-81e6cb332423 | note | Verifying Document - NDM Results
98493087-ecca-5702-9b92-25f0664f918b | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
554f611d-c99e-592d-bee2-843015f016da | note | Activity - H
ccf5b3da-cdf5-5795-9145-2a6b32d69f7e | note | By - SE
bbcbe397-d3aa-5f25-b343-5d2e0f43e6f8 | checkpoint | 5.02.08 - Clegg/Proofroll (Gap 65)
003d8931-bc62-5135-b7be-32aa75313eac | note | Acceptance / Conformance Criteria - Proofroll of each layer. 4 Cleggs to be undertaken per NDM test.
3874ad51-8f8b-575e-9170-0695e7fdc9bc | note | Standard / Specification - GWS - Table 3
4d765a6d-f986-55ae-a453-6684618ffc0e | note | Verifying Document - Clegg Result sheet
12a070cf-7dac-57ab-a68e-41e36105e8a1 | note | Frequency - Each layer
0313e548-65cb-50f0-85a4-231e5e4b576b | note | Activity - H
dcd71dcd-85cb-5dee-945b-745855383c9a | note | By - SE
e466154a-3525-5208-8981-a1953fc53c31 | checkpoint | 5.02.09 - Scala Penetrometer (Hinuera Sand)
4efbde40-a847-5874-adf2-744ee100a9d9 | note | Acceptance / Conformance Criteria - Minimum average value over 5 tests of 5 blows per 100mm, minimum single value of 4 blows per 100mm
78e0595b-f746-5ce0-b84e-30718f228843 | note | Standard / Specification - GWS - Table 3
afe343f9-b761-5bae-855e-8f1669892985 | note | Verifying Document - Scala Results
3242c858-14d8-526d-8fce-da11c78994d1 | note | Frequency - 1 per 500m3, 1 test per 0.5m lift per 20m run of wall
3b61ccc5-55eb-529c-ab6e-c36b4195619a | note | Activity - H
f0eff603-e0e2-56fe-a76e-7f727936301e | note | By - SE
60d12d54-946a-5d14-a179-44f6b0bbe1c4 | checkpoint | 5.03.01 - Tensar Triaxial 170
b7b6b90d-c046-44f6-84e9-98097ed32631 | note | Acceptance / Conformance Criteria - Geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 300mm is required between sheets. Engineer to inspect layer prior to backfill.
24628f91-905b-4919-9547-c3db25e1e6db | note | Standard / Specification - GWS - 4.2
54840355-d1ea-4777-9d5b-6ad907f4fc01 | note | Verifying Document - Photo record
e4c27b20-14a0-466b-932c-f2bfe6c5a0b5 | note | Frequency - Each layer - 1 layer per abutment to be inspected
92855898-8fd4-41e9-9ffc-b8cdb7a3f09f | note | Activity - HP
136c3b84-b512-41df-87e1-dba880b264ca | note | By - ENG
514384b9-8a6a-50c3-9354-b04bfb25986b | signoff | AUTHORITY HOLDPOINT
4d8b933a-5957-55bb-8b21-ef93921ef05e | checkpoint | 5.03.02 - Tensar Uniaxial RE580
0ea32e00-9760-40e8-9fe5-b080daf044a9 | note | Acceptance / Conformance Criteria - Geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. No overlapping requirements when connected with Bodkin joints. Engineer to inspect each layer prior to backfill. Grids must be taut prior to backffilling
8fb0fc4e-66e4-4c9c-b0e4-e4b8640e477c | note | Standard / Specification - GWS - 4.2
f13ceb32-2533-41ac-bfeb-dca8e273f776 | note | Verifying Document - Photo record
022bcb15-4959-4678-b859-596c2cd1f642 | note | Frequency - Each layer - 1 layer per abutment to be inspected
b48fd9c3-bfcf-450e-b240-2de1ae9976fc | note | Activity - HP
f15f51f3-5909-43a2-9ce0-74db5d1700c4 | note | By - ENG
1749caf0-95ae-558d-9e40-0cb21ba1a8ff | signoff | AUTHORITY HOLDPOINT
68eb27de-28a0-5c6b-b80b-1a0b3a7dabaf | checkpoint | 5.04.01 - Settlement Pins
6be00cc8-35f7-58b4-9aac-3e2f7da37af6 | note | Acceptance / Conformance Criteria - Settlement pins shall be installed within 24 hours of reaching design subgrade level. Survey measurements are to be undertaken to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
a15120ed-c718-5d31-baef-0c8bf1202b40 | note | Standard / Specification - GWS - 6.3
c328b2c9-2589-5ea8-a5a5-29f4fbb679b6 | note | Verifying Document - Survey Results (in paper as well as electronic format)
c44e4189-f4cd-5c8a-94c5-7045748d766f | note | Frequency - Weekly for the first month, then monthly
976b9f25-82ac-5367-a238-3dc87271bf9f | note | Activity - R
f42af643-c395-58bc-a22e-585a9ebaf8f8 | note | By - SV, ENG
65bdb657-7dd2-575b-8068-4d8a3bbf8080 | checkpoint | 5.04.02 - Settlement Targets
08507682-93c4-5452-97e2-8150c20bfab6 | note | Acceptance / Conformance Criteria - Targets shall be fixed immediately after completion of the first row of retaining wall blocks at each location and the initial baseline survey reading made prior to the subsequent row of retaining wall blocks placed.
480b8b47-6145-593e-9237-ad72d6db0cee | note | ○ Survey measurements are to be undertaken to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
28d6069c-16cb-52bf-8b0f-2855091f5e5d | note | Standard / Specification - GWS - 6.4
4d86ed34-2564-57a8-98f7-1460af0da7f9 | note | Verifying Document - Survey Results (in paper as well as electronic format)
ee49474b-e7c1-5904-abb4-5613386fddb2 | note | Frequency - Weekly for the first month, then monthly
67d177c4-6ae0-544d-8cca-4963c96f1e14 | note | Activity - R
cd844407-15dc-5abf-ab6a-581e0b72a97e | note | By - SV, ENG
19e8c979-4bbd-5b44-b6f1-f5f0c60cc435 | checkpoint | 5.04.03 - Engineers Approval
129d7748-60d8-5b2a-9b1a-b1ea68c4b7f9 | note | Acceptance / Conformance Criteria - Geotechnical engineer assesment required before commencement of Pavement construction
9c535da8-1110-57cf-bd8b-4b3a4cb67048 | note | Standard / Specification - BBO
c03b5ad1-5238-50bf-94b3-a6d95d7561a5 | note | Verifying Document - Written approval
43a8c2cd-762b-5905-a363-f38629034b45 | note | Frequency - Prior to pavement construction
e735b9e1-02c3-5526-9bcd-5fbbcfc69b4f | note | Activity - HP
655aedea-3982-579f-8070-73df15d33ff2 | note | By - ENG
2ef33948-5bbc-5304-bec0-43db699435f7 | signoff | AUTHORITY HOLDPOINT
cd33a7f8-9b6c-5422-93be-dcae98eaa460 | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
c67c36c3-6604-547c-97e6-f35b09622953 | checkpoint | 6.01.02 - Draft Redline Drawings
fa2526ab-b8b9-509f-b4ec-43a5d96dfe8c | note | Acceptance / Conformance Criteria - Draft as-builts completed on the completion of MSE wall including red pen mark up to IFC drawing changes.
1b08806c-38dd-54fa-9d51-79482791edaf | note | ○ The draft as-builts shall be provided on a continual basis throughout the project for verification by the Engineer, and as a minimum shall be provided in electronic form prior to application for Practical Completion.
71c7e106-4037-5b64-8bc7-4d64f708bf04 | note | Standard / Specification - PS 2.2.17
a9791038-927a-56e8-92bc-092094da73cb | note | Verifying Document - Draft As-Builts Drawings
8b640c55-480e-521c-b672-75b78b29968d | note | Frequency - Prior to PC
66bc92ec-3655-5cdd-82f9-c85ade2d83b3 | note | Activity - H
0f0c9cf5-c28d-5026-9f36-cb989728faad | note | By - SV / PE
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
b5a8070f-60a1-546c-b07d-5745ff489108 | checklist | SYS - ITP - Stainless Steel Pipe Site Welding | itp | ITP - Stainless Steel Pipe Site Welding
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
d23d82c5-8f42-50c7-ba8f-162334c64ec9 | checkpoint | Inspect all pipe & fittings are correct to job requirements and no signs of damage
8cfe2aaf-721a-5de5-9d1a-7d5b55c6e849 | note | Quality: Hold Point - W
e0977afa-d426-5857-842c-23fd26825696 | note | Quality: Sign - LS
cef4f7e8-5081-521d-a422-a39a187081b8 | note | Quality: Witness - AG
748b8aa5-78ea-481d-a9f0-0f60d31beddd | checkpoint | Inspect all pipe & fittings are correct to job requirements and no signs of damage
72a70939-b2c8-590e-90e6-d08793e3aeef | note | Quality: Sign - AK
aadb0693-2cc2-5620-bcae-9782278a34ce | checkpoint | Familiarise yourself with the job
1a4133f3-4614-55df-9511-34b140e3f468 | note | Quality: Sign - AK
b20a0af7-73e9-556a-947d-4febc223c156 | checkpoint | Setup worksite, welding equipment & rollers
b4843adb-3502-560e-91d4-3dfc76e06e39 | note | Quality: Sign - AK
db1eb665-1185-5020-8156-938e4e296812 | checkpoint | Load length into rollers
129a13a7-b545-5beb-a3d2-0d8925781ce1 | note | Quality: Sign - AK
ac284ff4-ba0d-57fd-84b8-4c67bf94f5a2 | checkpoint | Bevel pipe ends
473dbab3-66ee-5c3d-a29c-eaee14e9c98a | note | Quality: Sign - AK
eb4c3f44-45fb-5baf-8863-b657653af373 | checkpoint | Tack weld 6m lengths into instructed lengths
b45fc73e-8716-53ab-92b5-e7a8a1a0b5df | note | Quality: Sign - AK
e902e8af-3dd1-557e-a6c1-e7f9c93d3961 | note | Quality: ID - AK1
f6c4ac93-8c52-5b74-bf2a-509593377415 | checkpoint | Check for straightness alignment
78322bd6-9015-5260-bb56-66680edddc32 | note | Quality: Hold Point - C
8914a38e-7940-5245-9eca-ade47d2a3cef | note | Quality: Sign - AK
94417a05-32cc-5f95-ba16-ae92d19d480c | note | Quality: Witness - AG
b6dc238d-4f49-593e-8bb1-363dd19f1c8e | checkpoint | Setup purge baloons & purge with nitrogen
30e8af7c-20ab-56a4-ac60-9026171eb594 | note | Quality: Hold Point - C
94450fec-d239-5009-8039-6d06ba261720 | note | Quality: Sign - AK
c8798ef9-cc48-58fa-9f9f-19832a405769 | note | Quality: Witness - AG
da78b9c3-df9d-5c79-b8a5-5c3e549de77e | checkpoint | Peform butt welds
6d740a76-6493-502c-8e18-89499b172d16 | note | Quality: Sign - AK
bfb56a40-f0b0-5414-bd9f-6f648d08d6aa | note | Quality: ID - AK1
d0293b09-81ec-5139-89ce-1472088e276a | checkpoint | Tack flanges on spool lengths & check for square
cd5e67a7-8a32-5bf1-af3a-cf55de6a0735 | note | Quality: Hold Point - C
87c1b39f-af85-58f3-95ba-7c5000f5c432 | note | Quality: Sign - AK
b6efe9d1-d180-572e-a3f8-02b35bb3be75 | note | Quality: ID - AK1
375df33c-659c-5bbd-889d-35b60819e097 | note | Quality: Witness - AG
e500a9ca-8d75-5125-aaa7-4af5c648b4fa | checkpoint | Weld flanges on ends
955dca95-c19e-53d2-89b5-f92d19e3c3c0 | note | Quality: Sign - AK
ff1e457f-c928-5fef-8ad6-44e417044c94 | note | Quality: ID - AK1
c3e43bd3-aed5-5eac-87f4-bddef998735b | checkpoint | Passivate all welds
e5848a77-4422-5ff7-b891-234cca2dbe7e | note | Quality: Sign - AK
44e33adf-c562-5da7-bc81-19c849279ec7 | checkpoint | Remove from rollers and move to lay down area
f6879104-c440-5809-af28-607ea958a40e | note | Quality: Sign - AK
f0ffd1e2-3dab-50f3-be12-aeb1ec69baa9 | checkpoint | Final inspection
34ec5d81-65ec-5b91-ae74-6f51f5e930c6 | note | Quality: Hold Point - H
f9e5c8b0-7a12-5793-b652-770c6f2697ae | note | Quality: Sign - AG
a17d4418-f643-5665-b00b-1016f21de2ba | note | Quality: Witness - LS
8a8c980b-e46c-5f30-bf74-bcf638dccb81 | signoff | HOLD POINT
5d834e87-0719-5f7f-90bf-e17a22cf225c | checklist | SYS - ITP - Stormwater |  | ITP - Stormwater
250f8899-b0a3-538c-87fa-1443b890324b | section | 1. Pre-construction (P&G / EStablishment
40e50969-1ceb-5dd9-9b3c-01f7c53f618e | checkpoint | 1.1 - Extent of Line Setout
447440a5-2c0a-5624-85c7-5c5695b6237d | note | Acceptance / Conformance Criteria - Ensure line and level of Stormwater has been marked out and agreed with Engineer in accordance with Stormwater drawings Identify any clashes before construction.
c2a79509-fed9-5e36-b6c2-55161fc3b698 | note | Standard / Specification - Design Drawings
ca3ef045-41f3-51eb-926d-2360a7098b93 | note | Verifying Document - ITP Sign Off
98ad0bfb-34bb-5a09-9755-5781e4c3ebe3 | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
9f6fba78-f4fa-5da9-aba5-069ad45174ef | note | Activity - M
8de4d596-b054-5659-bc84-16e38ba8fb5f | note | By - PE
29b93ae9-4f0f-5379-a3b9-3f819c7cf4c4 | checkpoint | 1.2 - Environmental Protection
6612df47-d954-53c4-b894-edb8ce9af6f9 | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
062afe7b-306f-5969-b9db-f7d2dc2afc15 | note | Standard / Specification - Project ESCP Plans
7a2cc52d-ca2a-57de-905e-1840593283b1 | note | Verifying Document - ITP Sign Off
b38eb8cb-5d9d-5cd6-aae7-aace11a0a128 | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
de4a0ce0-290c-5f62-9d8d-6caf8dc1f487 | note | Activity - M
052d5bf8-5a20-5976-ac01-5a2ef8b5e4f3 | note | By - PE
c1757774-9612-5bda-8f1b-91d1e7f574f0 | checkpoint | 1.3 - Stakeholder
964041ce-8f47-5f43-9ecb-4bc963a55457 | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
8b5fbeb7-f07a-5d9a-8009-c74944313641 | note | Standard / Specification - Project Stakeholder Management Plan
eb2ede20-7062-5ae6-ae42-6281a683f1fd | note | Verifying Document - ITP Sign Off
d15bcff4-95f0-5150-accf-6527317b301c | note | Frequency - Prior to Construction with continue updates throughout the works
5ec3de2c-4b7c-5ade-a197-bd5ea77fcabe | note | Activity - M
4c067108-806e-5e92-9370-1ad1b8a35d89 | note | By - PE
2d17bcb2-0fc6-51c9-86f5-20bc7fe95d1e | checkpoint | 1.4 - Permits
4c825895-8c78-55b8-b08e-a8351d233bd8 | note | Acceptance / Conformance Criteria - Permit to Dig must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip. Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. All known services must be clearly marked on site and briefed to the workforce .
1d27dde7-938b-501b-832f-694ad3898bab | note | Standard / Specification - Section 2.2.10 Project Specification
ebcd1d8c-89e5-5cf8-892d-b66059936aa9 | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
e8bbb9a1-2854-5867-a418-82b8a8d75d70 | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
50b252e4-9a1b-55a1-8fcd-272b57170589 | note | Activity - H
05b3ff20-3c01-57de-94a8-610a07e19afa | note | By - PE
b0124294-c375-5468-89f3-32274ca5d856 | signoff | AUTHORITY HOLDPOINT
2b839b91-0e59-52bf-bfbc-2a6a8cc5432d | section | 2. Material, Personnel & third party approval
405352c0-5f6d-5187-918d-a540cbfd3a1d | checkpoint | 2.1 - Pipes, Fittings and Pre-cast Structures
8cc73743-a549-5b8a-9972-bd0ed83002b2 | note | Acceptance / Conformance Criteria - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes/manholes/catchpits are correct and in good condition and compliant.
99c3e5ae-e54f-5495-9913-be9258ec6a39 | note | Verifying Document - Delivery Dockets
c00daa9a-8446-5e5a-80c6-f2424b52f9d1 | note | Frequency - Each Delivery to site
a6e87c58-81fd-59d2-a37c-c5b5ea4ddfbd | note | Activity - S
34dca5cd-53ed-5e78-9eca-2b4049551dea | note | By - PE
8907bdeb-f5d3-517d-9285-d6893b320753 | checkpoint | 2.2 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
2f2b959f-0b91-593e-af76-befcf5d8037b | note | Acceptance / Conformance Criteria - Confirm material grading and density
df46ccd2-8662-5f7d-b6ba-bec7f384f640 | note | Verifying Document - IANZ Lab Test Report
9c4db143-fb28-5f31-bc3c-43f6c7034508 | note | Frequency - 1 Test per 1000m3
245aee90-a07b-5d58-8087-a5a14ee20ed3 | note | Activity - H
f3b05688-3c15-54c6-8fba-318cf71f63e7 | note | By - PE
c30b6c14-92f7-5ed2-a6a8-3f7e8a154f8f | signoff | AUTHORITY HOLDPOINT
22aee86e-39c3-5dae-b364-06afb43756dc | checkpoint | 2.3 - Undercut Backfill Material
fe88c77f-3e70-515d-bb22-3fd140cb3a92 | note | Acceptance / Conformance Criteria - Engineer to Specify Material to meet specifications dependant on material selected
07567e87-88a2-541c-b30e-632f15b06a13 | note | Verifying Document - IANZ Lab Test Report
54e4e4a8-5298-504a-a852-f33bcd7d4d87 | note | Frequency - 1 Test per 1000m3
8c66e4e0-bc8f-506b-a85f-f5d65b949fb1 | note | Activity - HP
3d96e459-1e65-5754-b945-41afc0373867 | note | By - ENG
76eff2ac-dcf6-53be-bbec-f153144f0126 | signoff | AUTHORITY HOLDPOINT
1f8d7f1f-2254-58d1-b0a1-af1db979e4f5 | checkpoint | 2.4 - Geotextile/Geogrid
d07e6c50-2ff7-59c3-8fea-34e730e14a76 | note | Acceptance / Conformance Criteria - NZTA F/07 Strength Class C & Filter Class 1 geotextile is to be used in the undercut. Geotextile or Geogrid that is used in the undercut is to be documented / marked up on drawing
6dbbe61e-6416-5303-b213-94a8c466f688 | note | Standard / Specification - Project Specification
e0bf4fe2-31b6-5f29-9c4a-9c35585633c8 | note | Verifying Document - Certification
9db1ab35-a02a-50b0-a859-3077e8340c2f | note | Frequency - Material Used
14c378a1-3d7d-5e88-b0b4-dc90aa22f05a | note | Activity - C
3fd12297-a538-5970-b61b-2ca319e65cd8 | note | By - PE
9df583ab-155b-5efc-bfef-074fd09cf696 | section | 3.1 SW Pipeline Construction
6060b861-66f7-50a6-931b-1a3e09522cab | checkpoint | 3.1.1 - Foundation Compliance
7a04d12b-d747-5ffd-b944-2bd05ad77fc9 | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
4f0e99a5-bfaf-5f02-a719-5a24a42d5913 | note | Standard / Specification - Project Specification 4.3
a9f17d3b-c88e-50fe-8d6f-ab8064428d69 | note | Verifying Document - IANZ Scala test result
f3841af3-80ba-5c41-8777-03f1b887719b | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
3575732c-7133-5f5c-849a-1c506255b232 | note | Activity - H
ff25d653-974a-54e0-a0d3-32abec523435 | note | By - QE
261a9718-d291-5946-8039-995e6b970cd3 | signoff | AUTHORITY HOLDPOINT
27e1b1c2-fd5c-53c7-8ab8-4e7ee944dd8d | checkpoint | 3.1.2 - Undercut Backfill Compliance
e1ff91fe-c3fb-58ee-9e70-19bef3c46199 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average98%) of MDD
a64090ac-0958-5091-b76f-c28c35eb76a9 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
93d8490e-c5e1-5da8-888e-c2e3ae4d55d2 | note | Verifying Document - IANZ Lab Test Report
8b1bde27-f241-50c2-a50d-193151536635 | note | Frequency - Based on Undercut Section
021146ef-473d-5414-88e2-ce3b10842f12 | note | Activity - H
905f63e2-3f0e-5d40-8280-5163a1b608af | note | By - QE
3b42b8af-9265-5fcf-bc40-7a447dcc1e0a | signoff | AUTHORITY HOLDPOINT
e98da528-b79e-502b-b67d-feb4cee476d0 | checkpoint | 3.1.3 - Bedding Compaction Testing
e3797ba1-d525-5fd9-a978-8a5831163f09 | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average98%) of MDD
a2064d5a-38c8-55fd-a7dc-82c5a0133fc2 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
1d9d16c0-cfa7-5e49-8d48-39ef0a0d8c21 | note | Verifying Document - IANZ Lab Test Report
499bcee3-0521-5833-b992-397bfa037601 | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
730ed117-3d39-5268-949a-02db9efa951e | note | Activity - H
82f85a51-88c4-5669-8e7c-07d8953148f8 | note | By - QE
f6f7cc71-a5d8-563e-9557-337605059128 | signoff | AUTHORITY HOLDPOINT
98147742-c8f1-5506-a60d-ea4b86794e0e | checkpoint | 3.1.4 - Haunch Zone Compaction Testing Haunch Zone shall extend from top of bedding to 0.3 times the outside dia of pipe
943c75a0-548a-5877-b083-6d8b113d77be | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD
98d9189b-0f93-5541-86a3-f57e2e828180 | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
b6029590-f98f-5925-9315-855030e5fe08 | note | Verifying Document - IANZ Lab Test Report
db6a89fc-c15b-5eaf-9b4e-48577b15dbce | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
aa4f8012-e8f7-54c9-a4ac-7df2a309121b | note | Activity - H
c1462d73-a82d-5e15-9b73-6b6f3fd47075 | note | By - QE
c86c5a9e-3030-5e16-8e37-17489dd9db4f | signoff | AUTHORITY HOLDPOINT
31a94ebb-2103-56ee-a677-646d0ec2ea45 | checkpoint | 3.1.5 - Side Zone Compaction Testing Side Zone shall extend from top of Haunch Zone to 0.5 times the outside dia of pipe
c71bafd6-9b9a-586e-a9c4-1a21adf96b38 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD
24f21671-d0d3-5a9e-bc01-b6a76b22570d | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
13b55999-794e-5122-af3b-a8aa97997815 | note | Verifying Document - IANZ Lab Test Report
32feea1a-ae98-558d-9737-dbd1f32fab48 | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
4a48af67-2ab9-5de9-9c40-82b43aee0a97 | note | Activity - H
fd47be6f-6c6a-5ff9-94b2-800c521a7759 | note | By - QE
a7cf3fdc-ffec-569d-97cd-8b9702c88056 | signoff | AUTHORITY HOLDPOINT
adad8470-6db5-5f41-8ecb-c7e2c95cd14f | checkpoint | 3.1.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
05192b11-1a31-586d-905f-5659d3cebd1e | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD
50b2983f-227f-536d-b0eb-3584ee19e873 | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
8a3c30b9-73dc-5a8a-838b-86b5b0bd2ed5 | note | Verifying Document - IANZ Lab Test Report
3d025453-8849-5aed-8278-b85d2c7e3df9 | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
bea3a1ac-8116-579e-9399-b859af1663b6 | note | Activity - H
b5599516-b1eb-5110-99be-fa5c76828b21 | note | By - QE
f0e2effc-94d3-5057-b41d-c7f3b97e2844 | signoff | AUTHORITY HOLDPOINT
12d805c7-e9b5-5c8e-87a9-36632fb2d485 | checkpoint | 3.1.7 - Backfill Inspection
1adaab6a-26da-5cfd-b3e6-23db6fc87b44 | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the pipeline.
3084c2a0-39cc-51ad-a0a2-094544a82dc1 | note | Standard / Specification - Project Specification 4.3
57109279-457b-5e21-a601-66ebf67dfde3 | note | Verifying Document - Photographs
191df840-3870-5720-a4de-26fffe4f3f34 | note | Frequency - Continuous
8feee862-4ff9-5b2c-96aa-b341303a3086 | note | Activity - S
398a1038-926f-5031-b65a-f2b2a115b4ea | note | By - PE
a6195f87-84e2-5fbd-a630-649970446481 | checkpoint | 3.1.8 - Survey
74d6bc52-ea28-5f9e-a46e-d8a11a8a62aa | note | Acceptance / Conformance Criteria - Invert Levels The permissible deviation from the designated level of the invert at each manhole or structure shall be ± 50mm, provided that the fall between successive manholes or structures shall be at least 90% of that specified. Horizontal Alignment The permissible deviation of the horizontal alignment between manholes or structures shall be ± 100mm. Gradient For straight gradients, the permissible deviation from the specified gradient shall be ± 50mm from a straight line drawn between the inverts of successive manholes, provided that no point in the pipeline is lower than any downstream point.
377dd711-8851-5fde-899f-26d3b19d6e49 | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
779ac31a-8be8-5b43-a12a-7ce6784654ce | note | Verifying Document - Survey Data
0758b277-e14d-5292-8882-bfddd9492976 | note | Frequency - Continuous
666f3657-a9b9-5643-8c00-9d8c5e540590 | note | Activity - C
7c5f006f-2bf8-54b5-bf65-9f6706fc2204 | note | By - SV
91e3a928-56b8-54e5-a782-8bb9063a0c3b | checkpoint | 3.1.9 - Backfill Compaction Testing
dd1b4c81-03ce-519d-86b6-a52d4bb8409b | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC.
5a0adf60-74ff-5fe6-b4d0-bd4064d2a01e | note | Standard / Specification - Project Specification 4.3
57b31059-a1ef-5138-ac81-a2c861002c3d | note | Verifying Document - IANZ Lab Test Report
2ca7f613-162c-5ee2-83fc-db1a58a8a44f | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
3ca2a53a-d16f-538d-8f33-c2e7d8481abf | note | Activity - H
ba3f57e7-fa79-5100-999c-4e83448459c4 | note | By - QE
b320de80-8843-5e19-8d19-01ff011794aa | signoff | AUTHORITY HOLDPOINT
fdd741d2-6577-58d6-8c1e-2d0c043b5480 | section | 3.2 SW Manhole Construction
8a67bad2-49a0-5b3e-9e07-3e95e06d76d3 | checkpoint | 3.2.1 - Foundation Compliance
dcec4b76-a35a-5a06-9a8d-29d8238c9847 | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
00c8b96c-19a5-5475-912e-4316d41e6e37 | note | Standard / Specification - Project Specification 4.3
7d677d75-abd9-53e8-b241-5dcf600e67ef | note | Verifying Document - IANZ Scala test result
5d063390-2611-5165-8299-86528408eea5 | note | Frequency - 1 Test/Manhole
dbd0670e-e320-5db0-84a5-dd06c660d2bf | note | Activity - H
bd3b026b-9a06-55d4-bdb5-132aa5be49ca | note | By - QE
1d9c8c56-63b0-51a5-9a79-b07c71904f6b | signoff | AUTHORITY HOLDPOINT
bba225a9-0f80-59b4-9bef-ab1078d3c8c6 | checkpoint | 3.2.2 - Undercut Backfill Compliance
39adc7b4-7c09-5d68-b4de-2afda2fef248 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average98%) of MDD
2e017776-83f1-57c1-b446-0ea74d0331e5 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
97f1d62b-680b-5711-ba4b-7f5b0f2b1450 | note | Verifying Document - IANZ Lab Test Report
b82b0243-c431-5bf6-bef2-54f9e9604ed4 | note | Frequency - 1 Test/Manhole if Undercut required
db6d6ab5-d974-5cc2-b57c-e9036d4fe47f | note | Activity - H
51b8047d-5ab9-52d7-b996-5a03129f824d | note | By - QE
af94d21a-5271-5425-9f08-ed410f981ce9 | signoff | AUTHORITY HOLDPOINT
add54623-858b-5fb5-ae1b-e4f44b3957d6 | checkpoint | 3.2.3 - Bedding Compaction Testing
2ae700cd-cdff-561f-9c54-c990abd4899e | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average98%) of MDD
8eb8191a-61be-5741-99e3-a38fa32a2bd4 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
15e97f48-55d1-5511-b25c-c3910dd31d24 | note | Verifying Document - IANZ Lab Test Report
6596043b-5c4a-581d-b4bd-86665c83b1dd | note | Frequency - 1 Test/Manhole
003075f7-e290-5eb6-a26a-9457ff57961c | note | Activity - H
75d1fa86-4533-5a8f-b029-aec3817e6ed7 | note | By - QE
9a0b64af-4c06-5035-a1a7-ffdc00e72ca6 | signoff | AUTHORITY HOLDPOINT
23f98f0a-b4da-5918-8708-f0ec9ba2ce0a | checkpoint | 3.2.4 - Backfill Inspection
80e98b3b-70ee-589d-99a7-8585136c48f5 | note | Acceptance / Conformance Criteria - Inspection of manhole prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the manhole
c72fb28c-e022-5303-a650-9e008cf50310 | note | Standard / Specification - Project Specification 4.3
87c71e3f-7a35-5568-bb19-d8524210f6d0 | note | Verifying Document - Photographs
6e2b4e89-bad4-5a42-96c2-1a70cf38076d | note | Frequency - Continuous
c5f29725-7a10-5c82-a80d-e13fc08c62b8 | note | Activity - S
5ea80f2a-4b35-53da-a64f-0b12bc74d1c2 | note | By - PE
971e11e1-7485-5df2-ad2e-34c9f843d784 | checkpoint | 3.2.5 - Survey
6b93d645-4ecf-56be-a7fa-df9892ec778e | note | Acceptance / Conformance Criteria - Invert Levels The permissible deviation from the designated level of the invert at each manhole or structure shall be ± 50mm, provided that the fall between successive manholes or structures shall be at least 90% of that specified. Horizontal Alignment The permissible deviation of the horizontal alignment between manholes or structures shall be ± 100mm. Gradient For straight gradients, the permissible deviation from the specified gradient shall be ± 50mm from a straight line drawn between the inverts of successive manholes, provided that no point in the pipeline is lower than any downstream point.
1ac3f541-1f81-5dc6-8556-14d6f56de1d6 | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
2ef1a085-438f-59d5-b3fd-50ead3ef546b | note | Verifying Document - Survey Data
235d4e1e-4ebb-569d-b7c5-6ef33aa85739 | note | Frequency - Continuous
5483ddd0-7ac7-592a-bc95-d7f40b712b95 | note | Activity - C
caf7d5bb-97cc-5104-9b91-f1fdf092b1af | note | By - SV
51a08071-576d-586e-a242-7407b41b31bd | checkpoint | 3.2.6 - Backfill Compaction Testing
318dea9e-f21a-516d-998f-cefd11329da4 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC.
3fcf6580-7b80-5d37-8434-4a4bf5773b2f | note | Standard / Specification - Project Specification 4.3
41973aa3-f55c-5b99-af6c-3e7072fe92c3 | note | Verifying Document - IANZ Lab Test Report
085388e7-2c92-5ba2-a83e-694ebd60d6ab | note | Frequency - 4 Density test per layer at Quarter Points around the Structure
c006baea-7876-523a-b03d-5b741204d653 | note | Activity - H
6e4a94cc-536c-56b9-9988-83741cadbbc5 | note | By - QE
4b1913c1-d7cf-5611-8bb8-1cfb1a20ddf0 | signoff | AUTHORITY HOLDPOINT
63c09d65-2137-531e-91b3-c1d0a8339711 | checkpoint | 3.2.7 - Haunching
5659e5ec-fb84-5ec0-9f8c-a5b25af378c7 | note | Acceptance / Conformance Criteria - All the MH's needs to be haunched as per the specifications
40a23dd4-539d-586c-b1b7-6b350a9581dc | note | Standard / Specification - RITS
d9a6375d-0eef-528f-9a15-48556a44142e | note | Verifying Document - Photographs
2799a095-3978-5051-aa95-4d0db01a222c | note | Frequency - Continuous
6f9a12d4-fd19-5973-8db6-606ab7a73450 | note | Activity - S
08a70049-a942-524f-91d4-b28a82d75d02 | note | By - PE
daa43319-258f-5c35-a641-e55348d73e9f | section | 3.3 SW Catchpit Construction
300b8fa1-28bb-53b2-8f55-761644c8d091 | checkpoint | 3.3.1 - Foundation Compliance
b5bcd2e4-2d17-56bd-a5db-81d297579443 | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
6bbdf8da-2c8e-5d2b-b460-d0096881e4c4 | note | Standard / Specification - Project Specification 4.3
18d529ea-89eb-59fb-97f7-391b734c33f8 | note | Verifying Document - IANZ Scala test result
87595e9e-bb05-5747-87d5-a4ed3ece4f65 | note | Frequency - 1 Test/Catchpit
e726b3b3-be6d-5a7c-a618-aa07aebbec81 | note | Activity - H
bd723658-bc76-5c1f-bc44-f3eca7d562d1 | note | By - QE
5d6e6d8d-55e5-5479-9783-aa0b5e657ed4 | signoff | AUTHORITY HOLDPOINT
528b8a8c-c255-597a-a5aa-ccae7f5d2756 | checkpoint | 3.3.2 - Undercut Backfill Compliance
80cc47a7-b6e1-5136-81bd-f07069b91b8e | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average98%) of MDD
c4c34550-803d-55f4-838d-e8392fdf9fd2 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
b7643824-0758-5387-ac1b-54ba81825658 | note | Verifying Document - IANZ Lab Test Report
f9947440-9d2b-53b7-832d-0d9d1f819fbb | note | Frequency - 1 Test/Catchpit if Undercut required
11bfade2-10e4-5df8-a782-7f7e1df7d556 | note | Activity - H
ad79f347-8d68-53d4-8203-fd74f1958ad5 | note | By - QE
8bbc0a68-437f-5361-a976-eb875cb85fc0 | signoff | AUTHORITY HOLDPOINT
99104720-245c-5b25-8b1b-18aeffe4b9f6 | checkpoint | 3.3.3 - Bedding Compaction Testing
648a2b95-dd00-54ea-ac31-e22564f82a91 | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average98%) of MDD
5646338b-6181-5b18-b998-28102fa4c4b3 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
60218604-2f09-54fd-9073-ae1aaed2a405 | note | Verifying Document - IANZ Lab Test Report
e7c00a95-6aa8-5929-87fa-96e4a3c4dde4 | note | Frequency - 1 Test/Catchpit
f0a01638-4414-5fa4-a096-f22a36e03247 | note | Activity - H
d558e9a6-05a1-54d6-9592-b7fe56f33911 | note | By - QE
3c79a68b-3003-5e37-bd3f-e2d6d8c7e743 | signoff | AUTHORITY HOLDPOINT
8c75aa70-f4b1-5a44-b5ae-7c14fc238095 | checkpoint | 3.3.4 - Backfill Inspection
c467db57-ff4b-5807-8eee-15fae2cf0df7 | note | Acceptance / Conformance Criteria - Inspection of catchpit prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the catchpit
ffb11fbc-3b83-5abd-913a-240698c4df57 | note | Standard / Specification - Project Specification 4.3
32b11a35-8a77-5aaa-bdb1-d7cf228e6aaf | note | Verifying Document - Photographs
b6eafff6-bdea-547a-8a04-1cb3793877d3 | note | Frequency - Continuous
a1f137a5-0c59-59e3-b70b-62dc170cc355 | note | Activity - S
c9cef0a2-1b0e-535b-8f99-d8e4d17c3ecd | note | By - PE
d2e13628-b927-50fd-ad8e-db3f761f1f7d | checkpoint | 3.3.5 - Survey
7197b535-45c2-5809-829e-ebe391e834c7 | note | Acceptance / Conformance Criteria - Invert Levels The permissible deviation from the designated level of the invert at each manhole or structure shall be ± 50mm, provided that the fall between successive manholes or structures shall be at least 90% of that specified. Horizontal Alignment The permissible deviation of the horizontal alignment between manholes or structures shall be ± 100mm. Gradient For straight gradients, the permissible deviation from the specified gradient shall be ± 50mm from a straight line drawn between the inverts of successive manholes, provided that no point in the pipeline is lower than any downstream point.
a1ee0ca8-a47b-5917-bd54-f5214297b86b | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
76fa5315-b0f5-58e3-acfe-56024a1d6ac4 | note | Verifying Document - Survey Data
e150227c-5e94-5830-b10d-ea0b898175bf | note | Frequency - Continuous
5d550601-8749-5225-a5ab-5b74c1aa57c8 | note | Activity - C
16a0960f-ef12-5ca6-ba4b-afc4551b968b | note | By - SV
652c96e1-768e-5161-abb8-33857043d37c | checkpoint | 3.3.6 - Backfill Compaction Testing
eb686d29-26c4-5f20-adc9-e52220561e9e | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC.
3e46d6be-d908-593c-b47a-2cdd80cb0094 | note | Standard / Specification - Project Specification 4.3
b1763e05-12f1-56b7-8fe0-96265442db5b | note | Verifying Document - IANZ Lab Test Report
5bcd4b69-2adf-5059-bc82-158e8c321dbf | note | Frequency - 4 Density test per layer at Quarter Points around the Structure
a5f5cba0-c703-577a-af89-de2bad6a32ee | note | Activity - H
ebbf3c75-97de-50a0-b256-7d083ae04ea3 | note | By - QE
2071ec85-9200-561c-aa34-f24a7392bb50 | signoff | AUTHORITY HOLDPOINT
91838760-1f3d-5d5a-aef7-b8985744096a | section | 3.4 Riprap & Boulders Installation
bd188581-f077-5ef2-a86e-5982480525c1 | checkpoint | 3.4.1 - Rip-Rap Material
b321cd8c-5e46-5864-aba5-f794ff7ad43c | note | Acceptance / Conformance Criteria - The material shall comprise imported screened quarry blasting's and/or crushed basalt, greywacke or other angular hard rock which shall conform to Density, Crushing Resistance , Weathering Classification, Abrasion Resistance, Calcite intrusions, Grading, Shape. No rock riprap or boulders shall be placed until the Contractor has provided test results to prove compliance with the requirements and obtained approval of the Engineer.
b68f6a88-b769-531b-b43d-ea229b1af715 | note | Standard / Specification - Project Specification 4.7.1
710b49eb-0085-53e1-9708-0c05bc07c290 | note | Verifying Document - IANZ Lab Report
509fd158-cd61-5f76-9574-a828fce7ffd9 | note | Frequency - Prior to placement
c4be62b1-dd9b-5431-9751-6efbea20f7f2 | note | Activity - HP
08dd237a-e262-5a54-9704-4d1aafdb9aa1 | note | By - ENG
eaabc864-faa9-5a81-ae67-142bdcfbceef | signoff | AUTHORITY HOLDPOINT
57540095-a1da-5db5-8879-72ce52ebc6a7 | checkpoint | 3.4.2 - Soil Rip-Rap Material
ae586004-69f3-51f9-a2ab-3fb9c500fb06 | note | Acceptance / Conformance Criteria - Where soil riprap is specified on the Drawings, approved riprap rock shall be pre-mixed with topsoil from on site at a ratio of 70% riprap to 30% soil by volume.
4585a3e6-61dc-5271-b76a-4db994ee98c2 | note | Standard / Specification - Project Specification 4.7.4
5afcc23e-4686-5030-adc5-8cf217b29856 | note | Verifying Document - Dockets/Site Notes
1b6e59a7-08e6-5461-b23a-b005331f1c91 | note | Frequency - Each Batch
4f1355f3-bfa8-5d3e-95e0-b69bb3f6889a | note | Activity - R
e0e2ab75-0816-5f19-955a-022b76b98747 | note | By - PE
6f4b44e8-e52b-59c3-bfd7-07b4903aaffa | checkpoint | 3.4.3 - Void Filling Rip-Rap Material
0fb9879d-1dc8-5b88-8be9-e9d76f5bee87 | note | Acceptance / Conformance Criteria - Where void-filled riprap is specified on the Drawings, the riprap rock shall be premixed with well graded granular material with a maximum particle size of 40mm (GAP 40) at a ratio of 70% riprap to 30% GAP 40 by volume.
4cd86cc3-8c69-5de8-943f-2ea0f7b3290f | note | Standard / Specification - Project Specification 4.7.5
72cb2c30-925b-5688-bcae-53c504748bb8 | note | Verifying Document - Dockets/Site Notes
2c5fc2af-b150-58a3-871e-7fda26bfac99 | note | Frequency - Each Batch
55719c40-e0df-5036-a089-ee1c0d9c9da6 | note | Activity - R
0dc87d3c-994a-52bd-bcde-99f769a51b07 | note | By - PE
c23265cb-94ad-5549-95f2-08d7740bde24 | checkpoint | 3.4.4 - Grouted Boulder
5d119a4a-7190-56ea-a138-60a8225dc9f2 | note | Acceptance / Conformance Criteria - Boulders must be approved by the Engineer, prior to placement Grout used for grouted boulder structures shall meet the requirements of NZS 3109
e49b26c5-3d8c-535e-a12c-c23ce98772d4 | note | Standard / Specification - Project Specification 4.7.6
79b8a383-a5a9-5a06-969f-f6aba483cb0e | note | Verifying Document - Site Records Data Sheet
b03711ab-ad6c-5f3b-b345-55a98e6258f5 | note | Frequency - Prior to placement
1b8ab041-d166-5770-a6f6-2e79d7c9116c | note | Activity - HP
5191a328-e62a-5de8-9966-507dbde63370 | note | By - ENG
a1c8800a-1602-5c05-88e7-0f27fd5de5b5 | signoff | AUTHORITY HOLDPOINT
d7e3d429-5c2c-560c-a07e-a3b9ac4a87c4 | checkpoint | 3.4.5 - Achieving Required Depths
953e1403-bb20-5da8-8128-631b97ed3482 | note | Acceptance / Conformance Criteria - As per IFC Drawings
830943ec-076f-5cb7-bc84-87871c978dea | note | Standard / Specification - Project Specification
4c48f30e-2955-567f-a1dd-288e00897eac | note | Verifying Document - Photos showing thickness/depth Each Section Labelled
969c046d-ac38-5cd9-9eb3-4264be2d77bf | note | Frequency - After Placement
b22883ca-794f-5d96-a004-b5aa14482988 | note | Activity - H
dc639aaa-e29a-5d1e-a35b-050828c37bdb | note | By - PE
67469e4c-4702-511c-993c-4fd2ca883b4a | signoff | AUTHORITY HOLDPOINT
10fb46ce-e0b0-5ea6-9067-24f1b6b0b998 | section | 3.5 CCTV & Reinstatement
69f084dc-a280-5bae-885a-038ae9240059 | checkpoint | 3.5.1 - CCTV Inspection
f0fab8de-949c-5ebc-a248-d79779f581c8 | note | Acceptance / Conformance Criteria - Quality Check on New Works
18687b5c-cc85-5a1b-b730-2eb46416a2ca | note | Standard / Specification - Project Specification 4.4 NZ Pipe Inspection Manual
63f2aecc-85a2-59a9-9b6d-adc6a21fed50 | note | Verifying Document - CCTV Report
69d35b40-75fe-5dd2-b466-ea0d100bbaa8 | note | Frequency - 1 per line
66432b17-ac2c-5cfd-967e-78fc98c03e74 | note | Activity - S
488fadbe-90bf-5b0d-8b6b-8eb71925a20a | note | By - PE
f7a982c0-3823-54cd-9694-7913082459bc | checkpoint | 3.5.2 - Reinstatement
a312f052-372d-50f9-9883-57a8dbe105e1 | note | Acceptance / Conformance Criteria - Quality Check on New Works/All the MH Lids and Cespit Levels should align with the pavement specification in terms of level & alignment
7be67543-bfaa-5a20-997e-ed431314971f | note | Standard / Specification - Reinstate and Tie into existing surrounds
d1cee765-ff68-569f-93cc-97c4f195f95c | note | Verifying Document - Photographs & Level Checks
4d5922ad-a59f-5136-9229-4b0ba6edc19b | note | Frequency - Continuous
a287eccd-79c8-502e-9bf6-c7365abc4ed2 | note | Activity - S
63711978-92e4-5993-a92f-a80b22d2f3bd | note | By - PE
85475bb6-9a9c-571e-bdc0-15f2014da4d2 | section | 4. Post-construction (Final Inspection & Handover)
7ae1b87b-673c-5c28-a4bd-4b55b08e4e89 | checkpoint | 4.1 - Survey Redline Drawings
53857957-862a-5c02-affb-420f8bbcb2d4 | note | Acceptance / Conformance Criteria - Quality Check on New Works based on the tolerances in RITS
0a6e7516-d189-58bf-b63f-ed3019cfa3f0 | note | Standard / Specification - Project Specification
97975fe6-bf31-533e-aa46-c1eb07ef0da3 | note | Verifying Document - Survey Data As Built Drawings Photographs Red-Pen As Built
64440248-836a-5ff7-84fb-19292f75fdaf | note | Frequency - Post works completion
eca96e49-ee5e-5cc0-966e-5e8083612ee8 | note | Activity - H
f0c23b4c-fd20-5916-b85f-437a97b969e5 | note | By - SV
b4c049a0-485a-5f2e-99f2-48ccf99481f6 | signoff | AUTHORITY HOLDPOINT
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
c84890fb-687f-5009-8dd5-1b13a7cb0a58 | checklist | SYS - ITP - Utility Trench |  | ITP - Utility Trench
9dbf9507-d5c1-5f76-b0e9-632a875b7d7c | section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
40e50969-1ceb-5dd9-9b3c-01f7c53f618e | checkpoint | 1.1 - Extent of Line Setout
1a28f932-4256-53f4-8e4a-e589e1a2a356 | note | Acceptance / Conformance Criteria - Ensure line and level of Utility Trench has been marked out and agreed with Engineer in accordance with Utility drawings Identify any clashes before construction.
e9c10589-2e58-525d-9972-a8bb57e1b6ea | note | Standard / Specification - Design Drawings
6b76dc85-10ae-5e6b-8376-49e4b134b896 | note | Verifying Document - ITP Sign Off
f9922ebe-f7cb-5b0a-a655-f0e94ea3e5ca | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
2e5d0e79-8bb5-5576-9395-510ec96d4620 | note | Activity - M
5de18377-15ae-5482-9288-87089e16f418 | note | By - PE
d974f8f5-6fc2-53e5-bb0c-a5788cd00a86 | checkpoint | 1.2 - Construction Drawings- Berm
c9c9b3e2-adae-50ec-9477-5b9c379c72a0 | note | Acceptance / Conformance Criteria - Provide full construction drawings as agreed upon by the Service Providers including agreed Cross Sections
71ffa5a0-dba5-5cd6-b388-7cab3c17f796 | note | Verifying Document - Drawings
2733522c-3170-5982-8f04-83454cbef071 | note | Frequency - Prior to Construction
37adc687-791d-597c-82ea-c0f3e6523730 | note | Activity - HP
7b80468f-df7b-5bd0-84ed-190a83d4d579 | note | By - ENG
3b120ea3-c1aa-55eb-a5c8-3bd1aaf20868 | signoff | AUTHORITY HOLDPOINT
3830a3d7-d29c-5702-b913-96193a97db80 | checkpoint | 1.3 - Construction Drawings-Road Crossings
6ef1f90b-a514-5f74-b178-c3ca3c76b3e8 | note | Acceptance / Conformance Criteria - Provide agreed upon Cross Sections from Utility Providers for any road crossings
38a47eff-b723-55d6-88ac-a60f6c7ce80b | note | Verifying Document - Drawings
b36b68dd-ccb3-53ac-8fb5-241006f9ff6c | note | Frequency - Prior to Construction
0ddb8441-3937-525c-b62d-749ce21e391e | note | Activity - HP
cf0b9879-0582-5b3a-8fce-3437eb240640 | note | By - ENG
fc7bceba-e571-5ccf-9a9d-3c15e5c485bb | signoff | AUTHORITY HOLDPOINT
a37db132-6f29-5d4b-87fb-c7088dcbfcb7 | checkpoint | 1.4 - Environmental Protection
9e0ab3fc-be7c-5604-b9aa-51ea43847668 | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
239d1081-6c8f-595d-9a88-e7f1a434afec | note | Standard / Specification - Project ESCP Plans
cf6fdba6-58e7-5d42-b38f-fb7593b3d6e5 | note | Verifying Document - ITP Sign Off
b1795489-b8ec-5af5-b5ef-1a9532f6c47e | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
d102b365-417e-5f88-b2d1-aaec33477065 | note | Activity - M
a19d99c5-e611-5073-bbb5-e1886d74f59e | note | By - PE
1d33401d-a6f8-579f-8b2f-a0e1365abab4 | checkpoint | 1.5 - Stakeholder
14360796-9a7b-536b-9f8d-f74126ac8feb | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
fe08ae50-bd03-5b8b-af4c-0ec7f7634f81 | note | Standard / Specification - Project Stakeholder Management Plan
b1c20ff8-3e6c-5bb7-a4f5-3e1c100216d1 | note | Verifying Document - ITP Sign Off
ab6e4055-f100-52ba-b36a-6b93a14d7954 | note | Frequency - Prior to Construction with continue updates throughout the works
e6bf2580-1570-5fc8-980e-e6aa25c9ee25 | note | Activity - M
a86c2579-b1f2-5f9c-9bcb-d8f8eaae3ae8 | note | By - PE
99be0b5d-0192-5056-854d-713dca7bbecb | checkpoint | 1.6 - Permits
02ae71fd-9fe0-5153-96f8-7431f8b30552 | note | Acceptance / Conformance Criteria - Permit to Dig must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip. Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. All known services must be clearly marked on site and briefed to the workforce .
419aadfe-9db5-5cad-ab0f-e9876ebf69cc | note | Standard / Specification - Section 2.2.10 Project Specification
3765baed-457c-5b64-bc01-9488eff7b0d3 | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
c5994fec-79d5-5e19-a835-51e8ca8c6f6a | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
78f32b25-1076-51a0-bc10-c820e2403e07 | note | Activity - H
7bc7f061-bae2-50e5-8dd1-9fa1f9851eeb | note | By - PE
b2505ca3-943c-534d-afb7-23e310ef1e65 | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
254bb354-ecf8-5723-a187-916bfd4e2c3b | checkpoint | 2.1 - Duct Bedding
444cf632-a93a-5dcf-8297-b82fca3ec4eb | note | Acceptance / Conformance Criteria - Confirmation from service providers on bedding and shading material required
0a3b0101-aa8a-5c69-b05a-20ad1f3e289a | note | Standard / Specification - Section 10 PWRBSS Project Specification Sand from Source Specified by WEL
0a0c45ef-ce6f-5ab7-ac13-38b2bd1fbf36 | note | Verifying Document - Delivery Dockets
eca7e6d9-795a-56ac-a05d-de5961e268bb | note | Frequency - Every Delivery
52e259fc-94fa-5ac2-9e2c-b3df15087154 | note | Activity - S
ad6978ac-eb7d-5a81-9185-88b267694f46 | note | By - PE
057bd260-40bb-5fbd-b73e-b36b95ccbfa4 | checkpoint | 2.2 - Trench Backfill
07df4993-1ad4-5481-be9e-9f3c64467672 | note | Acceptance / Conformance Criteria - Native soil backfill must have no stones or "hard clods" of cohesive material. Max clod or particle size to be 7mm. Trench Backfill material in carriageway to be Pit Sand
9a606214-ee38-5637-808b-5b1d731ea7f1 | note | Standard / Specification - Section 10 PWRBSS Project Specification Utility Company Requirements
f299d433-7a82-57f0-9b2b-4a356b15b9d2 | note | Verifying Document - Visual Inspection/Pictures PSD and MDD
b9de21f8-0904-58d5-bdd1-49c59ed61c4b | note | Frequency - Ongoing
57b53d57-cfee-5dc1-bf7f-e32d3bdac779 | note | Activity - S
032bb84e-ae4f-5361-bcdd-2c3971ef799d | note | By - PE
29236671-2fee-5e65-a68d-5cc74cf30d0c | checkpoint | 2.3 - Duct / Pipe Material
7d4133ae-1b6d-5113-bba3-97d11bb91482 | note | Acceptance / Conformance Criteria - Obtain duct / pipe from Utility Provider Confirmation required from service providers on ducting size
e47d48e4-9a8f-51e4-9cf7-8232d79733a3 | note | Standard / Specification - Section 10 PWRBSS Project Specification Utility Company Requirements
392046a7-d9f1-57a5-9b4e-c6e930e9cf30 | note | Verifying Document - Delivery Dockets Email
b27fdf1a-8714-5c7e-9bae-2d1a3bb916ee | note | Frequency - Every Delivery
6e1de9e2-2fae-50c3-91eb-57f984033568 | note | Activity - S
750b4f6a-4226-5ce1-9da0-1ae038b7496f | note | By - PE
add8efc4-f0b3-51fa-9598-32af4435ede2 | checkpoint | 2.4 - Warning Tape & Mag Slabs
9c3d76f2-41f7-503f-a557-e5bbadbf185b | note | Acceptance / Conformance Criteria - Obtain warning tape and mag slabs from Utility Provider Confirmation required from service providers if mag slab and warning tape required.
b6618b37-a549-587e-909a-3b5acb2a9649 | note | Standard / Specification - Section 10 PWRBSS Project Specification Utility Company Requirements
e05cabbd-4118-5782-b951-d4bf9879d825 | note | Verifying Document - Delivery Dockets Email
51cbeb2d-7cb7-5b8b-9128-aceabf5907bf | note | Frequency - Every Delivery
89bc29c9-bdaa-5beb-ac6a-0ce5218ed3b4 | note | Activity - S
bffc547a-b7af-5006-b596-c230ed7ea3ad | note | By - PE
9cc06a11-17ee-5f49-ac50-31c36fc22fcb | section | SECTION 3 – CONSTRUCTION ACTIVITY
82621b46-3e0a-54f5-8fc3-d5fb2b4cb3ef | checkpoint | 3.1 - Excavate trench
ca5b4c07-7b26-58ec-ba8e-30c9c2f74bdc | note | Acceptance / Conformance Criteria - Excavate trench and stockpile excavation arisings. Visual inspection of excavation arisings to identify presence of stones / hard clods. Inspection of formation to identify any soft spots.
a6c1f659-2ed7-5ca7-8ada-98099357c35c | note | Standard / Specification - Section 10 PWRBSS Project Specification
030fc257-bb20-5c49-9ba8-25b478c38139 | note | Verifying Document - Visual Inspection
54c76830-99fb-5518-a371-d7df97efb890 | note | Frequency - Ongoing
13c504a9-9d2e-59df-a4fe-9fd8e57becc8 | note | Activity - S
24b694bf-079e-5b4b-aade-5cb8aabf0dd2 | note | By - PE
3b1267e2-dffe-5add-b50b-4dbe671cabcd | checkpoint | 3.2 - Install duct bedding
bf7a3739-d868-5588-adfc-63ab2de93d47 | note | Acceptance / Conformance Criteria - Place sand as per WEL detail
4cd8021f-35cc-5a06-8c06-546e4132a1c8 | note | Standard / Specification - Section 10 PWRBSS Project Specification
5d1f8269-de16-50bb-93ad-32496650b741 | note | Verifying Document - Visual Inspection/Pictures
b6b588eb-42b6-5e62-bb33-90827527af43 | note | Frequency - Ongoing
f377a399-92d5-51f0-8583-1b5c7d72033a | note | Activity - S
e861d23c-8062-5427-9707-75cd0a76d49c | note | By - PE
d274c796-c9a6-5cb2-ab65-32b2768101ba | checkpoint | 3.3 - Install Ducts
4dbc32a3-b84a-57dc-98da-5b40b9cdc1ed | note | Acceptance / Conformance Criteria - Place ducts to line and level shown on design drawings and in accordance with utility provider requirements
94ce0b08-8205-5e0b-9ca0-2c97f41808fd | note | Standard / Specification - Section 10 PWRBSS Project Specification
0c88a5ba-a134-5101-be66-0dc602cf86c9 | note | Verifying Document - Visual Inspection/Pictures
f9e36f3c-7cda-58c6-b1eb-647e8e775764 | note | Frequency - Ongoing
0e569a63-4871-5955-ac8a-8f07b69bbdca | note | Activity - S
34c4bae7-851e-5b52-b133-97f0373851af | note | By - PE
1becbeaa-46d9-5aa4-8937-7bf0d6434276 | checkpoint | 3.4 - Install Draw Cord
0a01dc1d-d4f5-5798-a683-21f160cd883b | note | Acceptance / Conformance Criteria - Install draw-cord to all service ducts
f175bd4a-e569-5d92-9fc3-a56848ca48a2 | note | Standard / Specification - Section 10 PWRBSS Project Specification
bf41177c-6e86-51de-a70c-c6eabc8f7ab2 | note | Verifying Document - Visual Inspection
c4efeddb-335e-5891-8d8b-5df5424422bb | note | Frequency - Ongoing
10573828-9cb6-5e52-bb4a-18e93abfa6c4 | note | Activity - S
70b47ba3-6fd1-5144-ac39-447299d2bd92 | note | By - PE
caebe6c1-f96a-5587-93f5-e5bf2f3422b7 | checkpoint | 3.5 - Install End Caps
57fa27a2-c6e1-5cbb-a097-a1b24f08367a | note | Acceptance / Conformance Criteria - Install end caps to all service ducts
414df3a8-84ae-55f3-a017-17db6429d45e | note | Standard / Specification - Section 10 PWRBSS Project Specification
a5269469-2d07-5dc2-b6d6-15cfcc39f1e9 | note | Verifying Document - Visual Inspection/Pictures
73ed089c-7649-5cf9-961d-b714e30a0b87 | note | Frequency - Ongoing
0520f1ba-2c93-5c96-90f4-c80216482e42 | note | Activity - S
8a792c63-b312-51df-98e4-7e2a75391244 | note | By - PE
85c82894-a77a-57bf-a5fe-5f9e9b9328f5 | checkpoint | 3.6 - Backfill
bbb881e7-094f-52af-b460-4c169d175b2d | note | Acceptance / Conformance Criteria - Backfill and compact with selected native soils (no stones or hard clods, max. size for all soil particles and clods is 7mm) Photos of Ducts prior to backfill
43072781-cf7a-5067-9ddc-f430181c43a6 | note | Standard / Specification - Section 10 PWRBSS Project Specification
e4f7f5f6-b92b-598c-adde-b645857dd598 | note | Verifying Document - Visual Inspection/Pictures
05313ce5-ff97-53c7-b1db-5149e5ba6337 | note | Frequency - Ongoing
4c778149-df86-58c7-8eb9-b90d6215b157 | note | Activity - S
7ef44f1e-7e46-58ed-9701-946cc3f3d646 | note | By - PE
85669d4b-4ff6-51e8-bc42-d69bf3073481 | checkpoint | 3.7 - Install Warning Tape & Mag Slabs
65648a43-d930-5e62-88da-60fdb6a41ae2 | note | Acceptance / Conformance Criteria - Install warning tapes and mag slabs to all service ducts Photos of Warning tape and Mag slabs prior to backfill
392f46e7-9361-55a4-8f16-be0ab5d8df21 | note | Standard / Specification - Section 10 PWRBSS Project Specification
a14c3b49-d5b2-5308-b18b-4cddf0ccc8d5 | note | Verifying Document - Visual Inspection/Pictures
239154e0-ed43-5bed-9b58-d0a1ba786e8e | note | Frequency - Ongoing
ce322fe5-f01b-5aa5-bf30-385cf6d073be | note | Activity - S
036e7290-08e0-5af2-9c6e-81b10789df74 | note | By - PE
6408e73c-7439-5ff5-9af9-8e36511035c3 | checkpoint | 3.8 - Trench Backfill (Berm)
86af2f05-aa5c-594a-9055-664c4f903fdf | note | Acceptance / Conformance Criteria - See below:
d991b9d2-a7a6-5c6d-887a-79eccf1f91dd | note | LOCATION: Within Road Corridor - SIL or within 1m of the base of SIL (Subgrade fill) GRANULAR FILL: NDM: 98% MDD; Scala: 5blows/100mm COHESIVE FILL: N/A
369ca596-9790-56c1-81f9-b5d09e93136f | note | LOCATION: Within Road Corridor - Deeper than 1m below base of SIL (Bulk fill) GRANULAR FILL: NDM: 95% MDD; Scala: 4blows/100mm COHESIVE FILL: Air Voids: Average 10%, single maximum of 12%; Sheer Vane: Average 120kPa, minimum single value of 110kPa
ff0b27e4-8370-58f4-b3f7-a401b25883ca | note | LOCATION: Berm - Beneath Footpath GRANULAR FILL: NDM: 98% MDD; Scala: 4blows/100mm COHESIVE FILL: N/A
8ef1d158-2321-53f9-8cf5-5cf3dda02a5d | note | LOCATION: Berm - Outside of Footpath GRANULAR FILL: Scala: 3blows/100mm COHESIVE FILL: Sheer Vane: 70kPa
a7340a2f-39c2-5ba7-9532-124d4fd062fd | note | Standard / Specification - As Per General Correspondence from BBO GCO-0072
f2bc8c5d-8642-5678-8ec5-0cbfee46ce3a | note | Verifying Document - Testing Reports
6d793839-d120-54e1-972d-352b30dd00f2 | note | Frequency - every 20m along trench 1 test every 5m² at driveways and footpaths
df92b3d8-9c08-5c78-b7ec-7c40c1d9e38c | note | Activity - S
441fb3cf-2c66-5172-a6c7-eff8dcaebfdc | note | By - PE
3be67758-191f-504f-902e-af7469e14149 | checkpoint | 3.8 - Trench Backfill (Road Crossings)
e3069caf-ac7b-5938-ba5e-b7af23e05ba1 | note | Acceptance / Conformance Criteria - See below:
64f5a35a-24fd-5b65-982e-293bb7ab9d3b | note | LOCATION: Within Road Corridor - SIL or within 1m of the base of SIL (Subgrade fill) GRANULAR FILL: NDM: 98% MDD; Scala: 5blows/100mm COHESIVE FILL: N/A
f971f735-834e-5f57-8210-d3aac1ebf2ae | note | LOCATION: Within Road Corridor - Deeper than 1m below base of SIL (Bulk fill) GRANULAR FILL: NDM: 95% MDD; Scala: 4blows/100mm COHESIVE FILL: Air Voids: Average 10%, single maximum of 12%; Sheer Vane: Average 120kPa, minimum single value of 110kPa
df159860-a002-5dfa-9c42-f60ca8545b9f | note | LOCATION: Berm - Beneath Footpath GRANULAR FILL: NDM: 98% MDD; Scala: 4blows/100mm COHESIVE FILL: N/A
15dbe736-f4fd-56c3-a62e-04748e3b5a7e | note | LOCATION: Berm - Outside of Footpath GRANULAR FILL: Scala: 3blows/100mm COHESIVE FILL: Sheer Vane: 70kPa
646446e1-42ed-5641-a553-f997e0b07cc9 | note | Standard / Specification - As Per General Correspondence from BBO GCO-0072
2ec6e3f8-a1fc-524a-a509-fadacc262ad6 | note | Verifying Document - Testing Reports
6c48dc5d-c3a7-5239-b270-9c799050ad89 | note | Frequency - Every 10m along trench
7fd95c35-09f9-51fa-a8e9-e81c379639ac | note | Activity - S
b919f3fd-1dcd-5342-9a40-fca4b36e9f95 | note | By - PE
9311d1dc-931b-50b6-b12b-cfb315c64f5c | checkpoint | 3.9 - Install Service
33c58a5f-ead1-560e-8234-9fd01dd58d82 | note | Acceptance / Conformance Criteria - Services installed in ducts by Utility Providers
8fa09378-46fa-56da-8ea1-8e25e99b2856 | note | Standard / Specification - Performed by Utility Provider under their QA / QC Systems and Controls
7b2545f6-36ec-50af-8442-0d8dbe9ae8d6 | note | Verifying Document - N/A
d067f1f0-dadd-52cc-a908-8dca32195346 | note | Frequency - N/A
47f313e2-5286-540f-acd3-58bc815b1c0d | checkpoint | 3.1 - Reinstate
ae1b20e6-8844-5778-baf8-35d5bf01eff6 | note | Acceptance / Conformance Criteria - Reinstate and tie-into to existing surrounds
9acb322c-e4b7-59ea-b319-1e3c41a5b5ca | note | Verifying Document - Visual Inspection/Pictures
f9b96b11-ccf2-5513-84d7-cc0dd1d0061e | note | Frequency - Upon Completion of Each Section
fc9bc56e-4c60-5d68-8bdd-8768a6bfe8f6 | note | Activity - S
10383bc4-81b4-5272-bad5-9684ca75a2d1 | note | By - PE
84c3283d-24bd-504e-b593-7adb2a662256 | section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
7ae1b87b-673c-5c28-a4bd-4b55b08e4e89 | checkpoint | 4.1 - Survey Redline Drawings
dc1c3dda-d46d-5493-83a4-ed992a74c7eb | note | Acceptance / Conformance Criteria - GPS Survey of every joint in every duct / 6m centres on continuous pipe. Survey point naming protocols to be agreed between subcontractor and Downer Survey Manager. Draft As Built Drawings. Photograph of formation, all ducts immediately before backfill, warning tape / mag slabs immediately before backfill.
f81e2f98-ab70-599e-8fab-14dd0ea09089 | note | Standard / Specification - Section 2.2.17 PWRBSS Specification
a7188ac8-db8a-5504-857c-c81ffc2501cc | note | Verifying Document - Survey Data As Built Drawings Photographs Red-Pen Asbuilt including Undercuts/Any changes from original design, including any change in road crossing locations
f73d8d9f-3c77-58f6-b89a-f0b8d113ae6f | note | Frequency - Post works completion
377e2c0a-cce7-5704-877f-d5cfb42a2d24 | note | Activity - H
b9d2b744-054c-52aa-b0ca-673b30e6246e | note | By - SV
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
968398e7-f34e-5403-ac6e-b739e079971f | checklist | SYS - ITP - Utility Trench - v1 |  | ITP - Utility Trench
9dbf9507-d5c1-5f76-b0e9-632a875b7d7c | section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
40e50969-1ceb-5dd9-9b3c-01f7c53f618e | checkpoint | 1.1 - Extent of Line Setout
1a28f932-4256-53f4-8e4a-e589e1a2a356 | note | Acceptance / Conformance Criteria - Ensure line and level of Utility Trench has been marked out and agreed with Engineer in accordance with Utility drawings Identify any clashes before construction.
e9c10589-2e58-525d-9972-a8bb57e1b6ea | note | Standard / Specification - Design Drawings
6b76dc85-10ae-5e6b-8376-49e4b134b896 | note | Verifying Document - ITP Sign Off
f9922ebe-f7cb-5b0a-a655-f0e94ea3e5ca | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
2e5d0e79-8bb5-5576-9395-510ec96d4620 | note | Activity - M
5de18377-15ae-5482-9288-87089e16f418 | note | By - PE
d974f8f5-6fc2-53e5-bb0c-a5788cd00a86 | checkpoint | 1.2 - Construction Drawings- Berm
c9c9b3e2-adae-50ec-9477-5b9c379c72a0 | note | Acceptance / Conformance Criteria - Provide full construction drawings as agreed upon by the Service Providers including agreed Cross Sections
71ffa5a0-dba5-5cd6-b388-7cab3c17f796 | note | Verifying Document - Drawings
2733522c-3170-5982-8f04-83454cbef071 | note | Frequency - Prior to Construction
37adc687-791d-597c-82ea-c0f3e6523730 | note | Activity - HP
7b80468f-df7b-5bd0-84ed-190a83d4d579 | note | By - ENG
3b120ea3-c1aa-55eb-a5c8-3bd1aaf20868 | signoff | AUTHORITY HOLDPOINT
3830a3d7-d29c-5702-b913-96193a97db80 | checkpoint | 1.3 - Construction Drawings-Road Crossings
6ef1f90b-a514-5f74-b178-c3ca3c76b3e8 | note | Acceptance / Conformance Criteria - Provide agreed upon Cross Sections from Utility Providers for any road crossings
38a47eff-b723-55d6-88ac-a60f6c7ce80b | note | Verifying Document - Drawings
b36b68dd-ccb3-53ac-8fb5-241006f9ff6c | note | Frequency - Prior to Construction
0ddb8441-3937-525c-b62d-749ce21e391e | note | Activity - HP
cf0b9879-0582-5b3a-8fce-3437eb240640 | note | By - ENG
fc7bceba-e571-5ccf-9a9d-3c15e5c485bb | signoff | AUTHORITY HOLDPOINT
a37db132-6f29-5d4b-87fb-c7088dcbfcb7 | checkpoint | 1.4 - Environmental Protection
9e0ab3fc-be7c-5604-b9aa-51ea43847668 | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
239d1081-6c8f-595d-9a88-e7f1a434afec | note | Standard / Specification - Project ESCP Plans
cf6fdba6-58e7-5d42-b38f-fb7593b3d6e5 | note | Verifying Document - ITP Sign Off
b1795489-b8ec-5af5-b5ef-1a9532f6c47e | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
d102b365-417e-5f88-b2d1-aaec33477065 | note | Activity - M
a19d99c5-e611-5073-bbb5-e1886d74f59e | note | By - PE
1d33401d-a6f8-579f-8b2f-a0e1365abab4 | checkpoint | 1.5 - Stakeholder
14360796-9a7b-536b-9f8d-f74126ac8feb | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
fe08ae50-bd03-5b8b-af4c-0ec7f7634f81 | note | Standard / Specification - Project Stakeholder Management Plan
b1c20ff8-3e6c-5bb7-a4f5-3e1c100216d1 | note | Verifying Document - ITP Sign Off
ab6e4055-f100-52ba-b36a-6b93a14d7954 | note | Frequency - Prior to Construction with continue updates throughout the works
e6bf2580-1570-5fc8-980e-e6aa25c9ee25 | note | Activity - M
a86c2579-b1f2-5f9c-9bcb-d8f8eaae3ae8 | note | By - PE
99be0b5d-0192-5056-854d-713dca7bbecb | checkpoint | 1.6 - Permits
02ae71fd-9fe0-5153-96f8-7431f8b30552 | note | Acceptance / Conformance Criteria - Permit to Dig must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip. Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. All known services must be clearly marked on site and briefed to the workforce .
419aadfe-9db5-5cad-ab0f-e9876ebf69cc | note | Standard / Specification - Section 2.2.10 Project Specification
3765baed-457c-5b64-bc01-9488eff7b0d3 | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
c5994fec-79d5-5e19-a835-51e8ca8c6f6a | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
78f32b25-1076-51a0-bc10-c820e2403e07 | note | Activity - H
7bc7f061-bae2-50e5-8dd1-9fa1f9851eeb | note | By - PE
b2505ca3-943c-534d-afb7-23e310ef1e65 | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
254bb354-ecf8-5723-a187-916bfd4e2c3b | checkpoint | 2.1 - Duct Bedding
444cf632-a93a-5dcf-8297-b82fca3ec4eb | note | Acceptance / Conformance Criteria - Confirmation from service providers on bedding and shading material required
0a3b0101-aa8a-5c69-b05a-20ad1f3e289a | note | Standard / Specification - Section 10 PWRBSS Project Specification Sand from Source Specified by WEL
0a0c45ef-ce6f-5ab7-ac13-38b2bd1fbf36 | note | Verifying Document - Delivery Dockets
eca7e6d9-795a-56ac-a05d-de5961e268bb | note | Frequency - Every Delivery
52e259fc-94fa-5ac2-9e2c-b3df15087154 | note | Activity - S
ad6978ac-eb7d-5a81-9185-88b267694f46 | note | By - PE
057bd260-40bb-5fbd-b73e-b36b95ccbfa4 | checkpoint | 2.2 - Trench Backfill
07df4993-1ad4-5481-be9e-9f3c64467672 | note | Acceptance / Conformance Criteria - Native soil backfill must have no stones or "hard clods" of cohesive material. Max clod or particle size to be 7mm. Trench Backfill material in carriageway to be Pit Sand
9a606214-ee38-5637-808b-5b1d731ea7f1 | note | Standard / Specification - Section 10 PWRBSS Project Specification Utility Company Requirements
f299d433-7a82-57f0-9b2b-4a356b15b9d2 | note | Verifying Document - Visual Inspection/Pictures PSD and MDD
b9de21f8-0904-58d5-bdd1-49c59ed61c4b | note | Frequency - Ongoing
57b53d57-cfee-5dc1-bf7f-e32d3bdac779 | note | Activity - S
032bb84e-ae4f-5361-bcdd-2c3971ef799d | note | By - PE
29236671-2fee-5e65-a68d-5cc74cf30d0c | checkpoint | 2.3 - Duct / Pipe Material
7d4133ae-1b6d-5113-bba3-97d11bb91482 | note | Acceptance / Conformance Criteria - Obtain duct / pipe from Utility Provider Confirmation required from service providers on ducting size
e47d48e4-9a8f-51e4-9cf7-8232d79733a3 | note | Standard / Specification - Section 10 PWRBSS Project Specification Utility Company Requirements
392046a7-d9f1-57a5-9b4e-c6e930e9cf30 | note | Verifying Document - Delivery Dockets Email
b27fdf1a-8714-5c7e-9bae-2d1a3bb916ee | note | Frequency - Every Delivery
6e1de9e2-2fae-50c3-91eb-57f984033568 | note | Activity - S
750b4f6a-4226-5ce1-9da0-1ae038b7496f | note | By - PE
add8efc4-f0b3-51fa-9598-32af4435ede2 | checkpoint | 2.4 - Warning Tape & Mag Slabs
9c3d76f2-41f7-503f-a557-e5bbadbf185b | note | Acceptance / Conformance Criteria - Obtain warning tape and mag slabs from Utility Provider Confirmation required from service providers if mag slab and warning tape required.
b6618b37-a549-587e-909a-3b5acb2a9649 | note | Standard / Specification - Section 10 PWRBSS Project Specification Utility Company Requirements
e05cabbd-4118-5782-b951-d4bf9879d825 | note | Verifying Document - Delivery Dockets Email
51cbeb2d-7cb7-5b8b-9128-aceabf5907bf | note | Frequency - Every Delivery
89bc29c9-bdaa-5beb-ac6a-0ce5218ed3b4 | note | Activity - S
bffc547a-b7af-5006-b596-c230ed7ea3ad | note | By - PE
9cc06a11-17ee-5f49-ac50-31c36fc22fcb | section | SECTION 3 – CONSTRUCTION ACTIVITY
82621b46-3e0a-54f5-8fc3-d5fb2b4cb3ef | checkpoint | 3.1 - Excavate trench
ca5b4c07-7b26-58ec-ba8e-30c9c2f74bdc | note | Acceptance / Conformance Criteria - Excavate trench and stockpile excavation arisings. Visual inspection of excavation arisings to identify presence of stones / hard clods. Inspection of formation to identify any soft spots.
a6c1f659-2ed7-5ca7-8ada-98099357c35c | note | Standard / Specification - Section 10 PWRBSS Project Specification
030fc257-bb20-5c49-9ba8-25b478c38139 | note | Verifying Document - Visual Inspection
54c76830-99fb-5518-a371-d7df97efb890 | note | Frequency - Ongoing
13c504a9-9d2e-59df-a4fe-9fd8e57becc8 | note | Activity - S
24b694bf-079e-5b4b-aade-5cb8aabf0dd2 | note | By - PE
3b1267e2-dffe-5add-b50b-4dbe671cabcd | checkpoint | 3.2 - Install duct bedding
bf7a3739-d868-5588-adfc-63ab2de93d47 | note | Acceptance / Conformance Criteria - Place sand as per WEL detail
4cd8021f-35cc-5a06-8c06-546e4132a1c8 | note | Standard / Specification - Section 10 PWRBSS Project Specification
5d1f8269-de16-50bb-93ad-32496650b741 | note | Verifying Document - Visual Inspection/Pictures
b6b588eb-42b6-5e62-bb33-90827527af43 | note | Frequency - Ongoing
f377a399-92d5-51f0-8583-1b5c7d72033a | note | Activity - S
e861d23c-8062-5427-9707-75cd0a76d49c | note | By - PE
d274c796-c9a6-5cb2-ab65-32b2768101ba | checkpoint | 3.3 - Install Ducts
4dbc32a3-b84a-57dc-98da-5b40b9cdc1ed | note | Acceptance / Conformance Criteria - Place ducts to line and level shown on design drawings and in accordance with utility provider requirements
94ce0b08-8205-5e0b-9ca0-2c97f41808fd | note | Standard / Specification - Section 10 PWRBSS Project Specification
0c88a5ba-a134-5101-be66-0dc602cf86c9 | note | Verifying Document - Visual Inspection/Pictures
f9e36f3c-7cda-58c6-b1eb-647e8e775764 | note | Frequency - Ongoing
0e569a63-4871-5955-ac8a-8f07b69bbdca | note | Activity - S
34c4bae7-851e-5b52-b133-97f0373851af | note | By - PE
1becbeaa-46d9-5aa4-8937-7bf0d6434276 | checkpoint | 3.4 - Install Draw Cord
0a01dc1d-d4f5-5798-a683-21f160cd883b | note | Acceptance / Conformance Criteria - Install draw-cord to all service ducts
f175bd4a-e569-5d92-9fc3-a56848ca48a2 | note | Standard / Specification - Section 10 PWRBSS Project Specification
bf41177c-6e86-51de-a70c-c6eabc8f7ab2 | note | Verifying Document - Visual Inspection
c4efeddb-335e-5891-8d8b-5df5424422bb | note | Frequency - Ongoing
10573828-9cb6-5e52-bb4a-18e93abfa6c4 | note | Activity - S
70b47ba3-6fd1-5144-ac39-447299d2bd92 | note | By - PE
caebe6c1-f96a-5587-93f5-e5bf2f3422b7 | checkpoint | 3.5 - Install End Caps
57fa27a2-c6e1-5cbb-a097-a1b24f08367a | note | Acceptance / Conformance Criteria - Install end caps to all service ducts
414df3a8-84ae-55f3-a017-17db6429d45e | note | Standard / Specification - Section 10 PWRBSS Project Specification
a5269469-2d07-5dc2-b6d6-15cfcc39f1e9 | note | Verifying Document - Visual Inspection/Pictures
73ed089c-7649-5cf9-961d-b714e30a0b87 | note | Frequency - Ongoing
0520f1ba-2c93-5c96-90f4-c80216482e42 | note | Activity - S
8a792c63-b312-51df-98e4-7e2a75391244 | note | By - PE
85c82894-a77a-57bf-a5fe-5f9e9b9328f5 | checkpoint | 3.6 - Backfill
bbb881e7-094f-52af-b460-4c169d175b2d | note | Acceptance / Conformance Criteria - Backfill and compact with selected native soils (no stones or hard clods, max. size for all soil particles and clods is 7mm) Photos of Ducts prior to backfill
43072781-cf7a-5067-9ddc-f430181c43a6 | note | Standard / Specification - Section 10 PWRBSS Project Specification
e4f7f5f6-b92b-598c-adde-b645857dd598 | note | Verifying Document - Visual Inspection/Pictures
05313ce5-ff97-53c7-b1db-5149e5ba6337 | note | Frequency - Ongoing
4c778149-df86-58c7-8eb9-b90d6215b157 | note | Activity - S
7ef44f1e-7e46-58ed-9701-946cc3f3d646 | note | By - PE
85669d4b-4ff6-51e8-bc42-d69bf3073481 | checkpoint | 3.7 - Install Warning Tape & Mag Slabs
65648a43-d930-5e62-88da-60fdb6a41ae2 | note | Acceptance / Conformance Criteria - Install warning tapes and mag slabs to all service ducts Photos of Warning tape and Mag slabs prior to backfill
392f46e7-9361-55a4-8f16-be0ab5d8df21 | note | Standard / Specification - Section 10 PWRBSS Project Specification
a14c3b49-d5b2-5308-b18b-4cddf0ccc8d5 | note | Verifying Document - Visual Inspection/Pictures
239154e0-ed43-5bed-9b58-d0a1ba786e8e | note | Frequency - Ongoing
ce322fe5-f01b-5aa5-bf30-385cf6d073be | note | Activity - S
036e7290-08e0-5af2-9c6e-81b10789df74 | note | By - PE
6408e73c-7439-5ff5-9af9-8e36511035c3 | checkpoint | 3.8 - Trench Backfill (Berm)
86af2f05-aa5c-594a-9055-664c4f903fdf | note | Acceptance / Conformance Criteria - See below:
d991b9d2-a7a6-5c6d-887a-79eccf1f91dd | note | LOCATION: Within Road Corridor - SIL or within 1m of the base of SIL (Subgrade fill) GRANULAR FILL: NDM: 98% MDD; Scala: 5blows/100mm COHESIVE FILL: N/A
369ca596-9790-56c1-81f9-b5d09e93136f | note | LOCATION: Within Road Corridor - Deeper than 1m below base of SIL (Bulk fill) GRANULAR FILL: NDM: 95% MDD; Scala: 4blows/100mm COHESIVE FILL: Air Voids: Average 10%, single maximum of 12%; Sheer Vane: Average 120kPa, minimum single value of 110kPa
ff0b27e4-8370-58f4-b3f7-a401b25883ca | note | LOCATION: Berm - Beneath Footpath GRANULAR FILL: NDM: 98% MDD; Scala: 4blows/100mm COHESIVE FILL: N/A
8ef1d158-2321-53f9-8cf5-5cf3dda02a5d | note | LOCATION: Berm - Outside of Footpath GRANULAR FILL: Scala: 3blows/100mm COHESIVE FILL: Sheer Vane: 70kPa
a7340a2f-39c2-5ba7-9532-124d4fd062fd | note | Standard / Specification - As Per General Correspondence from BBO GCO-0072
f2bc8c5d-8642-5678-8ec5-0cbfee46ce3a | note | Verifying Document - Testing Reports
6d793839-d120-54e1-972d-352b30dd00f2 | note | Frequency - every 20m along trench 1 test every 5m² at driveways and footpaths
df92b3d8-9c08-5c78-b7ec-7c40c1d9e38c | note | Activity - S
441fb3cf-2c66-5172-a6c7-eff8dcaebfdc | note | By - PE
3be67758-191f-504f-902e-af7469e14149 | checkpoint | 3.8 - Trench Backfill (Road Crossings)
e3069caf-ac7b-5938-ba5e-b7af23e05ba1 | note | Acceptance / Conformance Criteria - See below:
64f5a35a-24fd-5b65-982e-293bb7ab9d3b | note | LOCATION: Within Road Corridor - SIL or within 1m of the base of SIL (Subgrade fill) GRANULAR FILL: NDM: 98% MDD; Scala: 5blows/100mm COHESIVE FILL: N/A
f971f735-834e-5f57-8210-d3aac1ebf2ae | note | LOCATION: Within Road Corridor - Deeper than 1m below base of SIL (Bulk fill) GRANULAR FILL: NDM: 95% MDD; Scala: 4blows/100mm COHESIVE FILL: Air Voids: Average 10%, single maximum of 12%; Sheer Vane: Average 120kPa, minimum single value of 110kPa
df159860-a002-5dfa-9c42-f60ca8545b9f | note | LOCATION: Berm - Beneath Footpath GRANULAR FILL: NDM: 98% MDD; Scala: 4blows/100mm COHESIVE FILL: N/A
15dbe736-f4fd-56c3-a62e-04748e3b5a7e | note | LOCATION: Berm - Outside of Footpath GRANULAR FILL: Scala: 3blows/100mm COHESIVE FILL: Sheer Vane: 70kPa
646446e1-42ed-5641-a553-f997e0b07cc9 | note | Standard / Specification - As Per General Correspondence from BBO GCO-0072
2ec6e3f8-a1fc-524a-a509-fadacc262ad6 | note | Verifying Document - Testing Reports
6c48dc5d-c3a7-5239-b270-9c799050ad89 | note | Frequency - Every 10m along trench
7fd95c35-09f9-51fa-a8e9-e81c379639ac | note | Activity - S
b919f3fd-1dcd-5342-9a40-fca4b36e9f95 | note | By - PE
9311d1dc-931b-50b6-b12b-cfb315c64f5c | checkpoint | 3.9 - Install Service
33c58a5f-ead1-560e-8234-9fd01dd58d82 | note | Acceptance / Conformance Criteria - Services installed in ducts by Utility Providers
8fa09378-46fa-56da-8ea1-8e25e99b2856 | note | Standard / Specification - Performed by Utility Provider under their QA / QC Systems and Controls
7b2545f6-36ec-50af-8442-0d8dbe9ae8d6 | note | Verifying Document - N/A
d067f1f0-dadd-52cc-a908-8dca32195346 | note | Frequency - N/A
47f313e2-5286-540f-acd3-58bc815b1c0d | checkpoint | 3.1 - Reinstate
ae1b20e6-8844-5778-baf8-35d5bf01eff6 | note | Acceptance / Conformance Criteria - Reinstate and tie-into to existing surrounds
9acb322c-e4b7-59ea-b319-1e3c41a5b5ca | note | Verifying Document - Visual Inspection/Pictures
f9b96b11-ccf2-5513-84d7-cc0dd1d0061e | note | Frequency - Upon Completion of Each Section
fc9bc56e-4c60-5d68-8bdd-8768a6bfe8f6 | note | Activity - S
10383bc4-81b4-5272-bad5-9684ca75a2d1 | note | By - PE
84c3283d-24bd-504e-b593-7adb2a662256 | section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
7ae1b87b-673c-5c28-a4bd-4b55b08e4e89 | checkpoint | 4.1 - Survey Redline Drawings
dc1c3dda-d46d-5493-83a4-ed992a74c7eb | note | Acceptance / Conformance Criteria - GPS Survey of every joint in every duct / 6m centres on continuous pipe. Survey point naming protocols to be agreed between subcontractor and Downer Survey Manager. Draft As Built Drawings. Photograph of formation, all ducts immediately before backfill, warning tape / mag slabs immediately before backfill.
f81e2f98-ab70-599e-8fab-14dd0ea09089 | note | Standard / Specification - Section 2.2.17 PWRBSS Specification
a7188ac8-db8a-5504-857c-c81ffc2501cc | note | Verifying Document - Survey Data As Built Drawings Photographs Red-Pen Asbuilt including Undercuts/Any changes from original design, including any change in road crossing locations
f73d8d9f-3c77-58f6-b89a-f0b8d113ae6f | note | Frequency - Post works completion
377e2c0a-cce7-5704-877f-d5cfb42a2d24 | note | Activity - H
b9d2b744-054c-52aa-b0ca-673b30e6246e | note | By - SV
800de3dd-a2ba-5dda-990a-703c17c34469 | checklist | SYS - ITP - Wastewater-PVC - Rev F |  | ITP - Wastewater-PVC - Rev F
9dbf9507-d5c1-5f76-b0e9-632a875b7d7c | section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
40e50969-1ceb-5dd9-9b3c-01f7c53f618e | checkpoint | 1.1 - Extent of Line Setout
0d5eef49-d0fc-5a1c-8a82-fd3a74f4033f | note | Acceptance / Conformance Criteria - Ensure line and level of Wastewater has been marked out and agreed with Engineer in accordance with Wastewater drawings Identify any clashes before construction.
0d071870-11c5-5eec-84c9-292c12037ea6 | note | Standard / Specification - Design Drawings
0c26aa56-26c6-57ec-a2ad-e0bcf160427c | note | Verifying Document - ITP Sign Off
3a52920e-aaf1-52da-881b-91fe241aef3f | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
63977a38-fd54-570a-b231-ab58a3755fd8 | note | Verification Activity - M
4f7e095f-a708-5e2a-93ee-5ab5f300b976 | note | Verification Activity - By: - PE
29b93ae9-4f0f-5379-a3b9-3f819c7cf4c4 | checkpoint | 1.2 - Environmental Protection
7bc6ee02-e63f-597c-b980-314821ff6b01 | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
f3e9a12d-8c5a-5a8e-bf90-8ede8d1fa0b1 | note | Standard / Specification - Project ESCP Plans
46bfa01b-553c-5913-8caf-ebdd8474fbde | note | Verifying Document - ITP Sign Off
b29f2714-073d-5b81-bd59-5a1cbe02af26 | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
93e14ecb-207f-5822-9af8-0cdb07361ee8 | note | Verification Activity - M
3ea2dbb3-c6bf-5dc0-aa59-59f7b80d4a4e | note | Verification Activity - By: - PE
c1757774-9612-5bda-8f1b-91d1e7f574f0 | checkpoint | 1.3 - Stakeholder
afaf20fc-c54e-5524-8f33-e4380c3567a9 | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
a09a546d-55fe-5f19-b899-ae01546cb169 | note | Standard / Specification - Project Stakeholder Management Plan
967077ad-1d63-5426-901a-2aa6bc33d6d4 | note | Verifying Document - ITP Sign Off
e5e9c320-9f09-5c08-9a43-e161dbb5bf39 | note | Frequency - Prior to Construction with continue updates throughout the works
0ace0bfb-bfcd-5b85-a19a-a83a01875460 | note | Verification Activity - M
e39f3135-cafb-5b0b-b29c-fb105c9bd876 | note | Verification Activity - By: - PE
2d17bcb2-0fc6-51c9-86f5-20bc7fe95d1e | checkpoint | 1.4 - Permits
bd0fe073-cba0-5f59-a016-aeda24e18447 | note | Acceptance / Conformance Criteria - Permit to Dig must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip. Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. All known services must be clearly marked on site and briefed to the workforce .
79645441-64ea-58ef-b789-aad531bc2ad6 | note | Standard / Specification - Section 2.2.10 Project Specification
b67b4743-30a9-590a-9b37-350070f50604 | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
27583fad-0c9b-50eb-8194-8c8a1b4cadbd | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
47dad4cc-2d8d-5614-bf1e-4055e6a65556 | note | Verification Activity - H
e7cd61f0-d1fa-5369-b44a-ccc53d21f64e | note | Verification Activity - By: - PE
b2505ca3-943c-534d-afb7-23e310ef1e65 | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
405352c0-5f6d-5187-918d-a540cbfd3a1d | checkpoint | 2.1 - Pipes, Fittings and Pre-cast Structures
8380fd18-221b-5c3b-b14b-e692cc846559 | note | Acceptance / Conformance Criteria - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes/manholes are correct and in good condition and compliant.
89890d6c-4980-5009-8325-2eac61e918d2 | note | Standard / Specification - PS Appendix L
825234e5-2d1d-5fcc-bee4-6ba02fbafbc4 | note | Verifying Document - Delivery Dockets
d408a0c9-efa7-5344-8e51-029ba33d35a3 | note | Frequency - Each Delivery to site
e04f09b9-b48a-57e2-b870-52ecbafd7093 | note | Verification Activity - S
f922cdaf-e2bb-5a91-824f-41c0d5865dc0 | note | Verification Activity - By: - PE
8907bdeb-f5d3-517d-9285-d6893b320753 | checkpoint | 2.2 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
5a2cfb08-ad89-50f2-91cf-4777f1275762 | note | Acceptance / Conformance Criteria - Confirm material grading and density
08a7f806-f8b9-5dc8-8aa8-cc410ee0a080 | note | Standard / Specification - PS Appendix L
382be309-4d8d-5371-87b1-05587f94db3d | note | Verifying Document - IANZ Lab Test Report
9a444a70-31d6-5dbc-8f4c-291d55f3dc8e | note | Frequency - 1 Test per 1000m3
918e6dc4-ffed-53b9-9f63-766d42c0ad5d | note | Verification Activity - H
9bdc96f3-272f-5e88-a260-7aceb61b2360 | note | Verification Activity - By: - PE
22aee86e-39c3-5dae-b364-06afb43756dc | checkpoint | 2.3 - Undercut Backfill Material
4b89be8b-43b8-59cd-815f-9acf1c08a812 | note | Acceptance / Conformance Criteria - Engineer to Specify Material to meet specifications dependant on material selected
8097d6a7-b180-5018-87b6-12ab0464a2da | note | Standard / Specification - Engineer to Specify
eb77f4cc-821b-5bf8-856a-e20ceefb325b | note | Verifying Document - IANZ Lab Test Report
d3c2e5fa-8c1a-534e-a747-67fbeb9ed6a0 | note | Frequency - 1 Test per 1000m3
953f3b31-d3fb-5be7-b265-54d13f455913 | note | Verification Activity - HP
1ffea821-fd4e-5674-be51-72fc6127f647 | note | Verification Activity - By: - ENG
1f8d7f1f-2254-58d1-b0a1-af1db979e4f5 | checkpoint | 2.4 - Geotextile/Geogrid
b083675e-9d2f-5fed-89e2-735bd98c3563 | note | Acceptance / Conformance Criteria - NZTA F/07 Strength Class C & Filter Class 1 geotextile is to be used in the undercut. Geotextile or Geogrid that is used in the undercut is to be documented / marked up on drawing
5323cb79-91c0-54e4-ba4f-641d2790f3ee | note | Standard / Specification - Project Specification
e3b2c732-9e5e-55ec-a969-076070e60ae1 | note | Verifying Document - Certification
72b70309-dbc1-5449-ab59-d58f87e9de84 | note | Frequency - Material Used
b0cb6815-4b18-5e59-beae-9613ff549fb5 | note | Verification Activity - C
ddfd5a19-6932-5ea2-b283-6fcd127b262d | note | Verification Activity - By: - PE
e08ab34e-c80e-59c0-b450-570ddd726e9d | section | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction
6060b861-66f7-50a6-931b-1a3e09522cab | checkpoint | 3.1.1 - Foundation Compliance
f9114ed8-508c-56c9-a70c-105d2888782a | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
a805edc5-2b44-584f-9213-01a09c81f559 | note | Standard / Specification - Project Specification 4.3
e67b2dea-eeca-538c-b086-d2d763af8ade | note | Verifying Document - IANZ Scala test result
76acdc33-ead8-5322-8ee5-98920d33eb07 | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
48757397-c016-5f0b-8e74-9a848cff25f1 | note | Verification Activity - H
0302830c-7332-59de-ab66-34ab747280cf | note | Verification Activity - By: - QE
27e1b1c2-fd5c-53c7-8ab8-4e7ee944dd8d | checkpoint | 3.1.2 - Undercut Backfill Compliance
f165b5fe-6212-5080-a1c4-07cc213160c4 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average 98%) of MDD
05404d60-6262-571c-ab7f-97e9889a0080 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70% or 95% of MDD AS/NZS 2566.2/2002
ada43e11-038b-5cb0-b5ba-bf0ac6a35a16 | note | Verifying Document - IANZ Lab Test Report
9fc59673-dcbd-5795-991b-f459c7995aa9 | note | Frequency - Based on Undercut Section
457b1941-1530-51c1-bb06-563a243bd414 | note | Verification Activity - H
e347b3d0-785a-5cf7-bef9-359eb06d128f | note | Verification Activity - By: - QE
e98da528-b79e-502b-b67d-feb4cee476d0 | checkpoint | 3.1.3 - Bedding Compaction Testing
4459e1c9-44f2-5a1e-b6e6-870f04c8b5f9 | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average 98%) of MDD
9fee4cc3-00a2-53f5-b535-ebb65125d555 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
d47bb5bc-3ae8-5178-bcf3-82784e72ec0b | note | Verifying Document - IANZ Lab Test Report
d95580df-35a2-5e6a-a3da-b87260e02da5 | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
9977cecc-7656-5d5a-9b70-86e5ef67f597 | note | Verification Activity - H
e4969a6f-e491-5a9e-bd68-00560b809a5d | note | Verification Activity - By: - QE
1dccb922-3a01-5c74-b4e3-aa9d6ad2e2ae | checkpoint | 3.1.4 - Haunch/Side Zone Compaction Testing
8c6f233a-cfe9-5745-abd0-57f1e432f484 | note | Acceptance / Conformance Criteria - NDM Back Scatter Minimum Compaction 95% of MDD
078c54b1-a2cc-5641-8f40-4e135e103f94 | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS-25566.2/2002
0d979ae5-b690-5c70-8586-3dcd359bc89c | note | Verifying Document - IANZ Lab Test Report
ec877efa-f836-5fce-914d-65c42133af1d | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
355f9922-7a96-5092-a53c-a6bd5a79e540 | note | Verification Activity - H
d4d8b25b-c759-58fb-a058-5867a07868db | note | Verification Activity - By: - QE
fa07aaef-f1b2-5919-98c5-2b3d4d21dc16 | checkpoint | 3.1.5 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
d7cbb21f-3c7f-5065-be72-bf6e19634a05 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95% of MDD
c3985824-6639-5243-924a-357dafeea0e7 | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS-25566.2/2002
bdab0c55-e44f-5a38-8d40-da3eb921643f | note | Verifying Document - IANZ Lab Test Report
3a706429-ce3b-5a5c-acac-d7b3c99d521d | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
a97b6fb4-2749-5197-bfd2-9893f23d2fa3 | note | Verification Activity - H
52a59d26-f675-5687-bd40-33937c0b61d1 | note | Verification Activity - By: - QE
4bd67fc6-2248-5fa2-9103-a66716a27d00 | checkpoint | 3.1.6 - Backfill Inspection
12db7e92-b9dc-5d44-b13b-fdedc2975145 | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the pipeline.
63a956f9-715e-5e8e-a332-afe4588e4d02 | note | Standard / Specification - Project Specification 4.3
60d444b2-3c15-5124-8354-6dfaf78f9c41 | note | Verifying Document - Photographs
b1ab14f6-6ece-5cb0-adf6-9ae9ae772d75 | note | Frequency - Continuous
d54c2165-d850-5b0a-b89c-5600270b3fc1 | note | Verification Activity - S
166bcfcb-cc5e-5ab0-ac87-a2b26da10865 | note | Verification Activity - By: - PE
f0ef0e4e-6639-5d9e-992e-8e179dc580bf | checkpoint | 3.1.7 - Survey
d8b2d5c6-c725-5a65-a847-243a2bf19db2 | note | Acceptance / Conformance Criteria - The pipes shall be laid with the variation between the specified invert level and invert level laid shall not exceed 10mm. Pipe invert checks shall be carried out at least once per day with a maximum of 30m between checks.
a3f876d4-dfde-5223-aecf-28ebe92dcf94 | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
939644b9-8a94-5996-9d09-89e56788d01b | note | Verifying Document - Survey Data
ee51bd9c-6cf2-561b-82dd-22c6a02b957a | note | Frequency - Continuous
be32b652-6e68-51e1-a54e-2bfb34d520dd | note | Verification Activity - C
4617b38a-d3e0-5d7a-8052-83f11b5687f0 | note | Verification Activity - By: - SV
df69972f-e5ff-59c1-a9cb-6d29805b9c2b | checkpoint | 3.1.8 - Backfill Compaction Testing
69683509-f357-55f2-b443-9e2678eda21f | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC. Minimum Compaction 95%(Average 98%) of MDD
3132503d-6548-527d-ae32-76e55cc744cf | note | Standard / Specification - MDD Average of 98% with minimum of 95% PS 4.5
3960ff87-9875-59b6-9e35-c1e15d31c11b | note | Verifying Document - IANZ Lab Test Report
01f28adc-3ecc-512a-82d4-a6d1771e7a6c | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
3d0bf983-a5b1-5f0a-ab83-067fc76bcffe | note | Verification Activity - H
f589be2b-bdcf-5825-b553-dac0aa9a08c9 | note | Verification Activity - By: - QE
f3ef653a-c404-5084-a263-be2e2bb15cfa | checkpoint | 3.1.9 - Manhole Foundation Compliance
677d09e1-70bc-5ef1-9c4a-0ad3a5e67cd3 | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa Engineer to confirm undercut depth (If Required)
cf849772-ecad-55b4-aa02-0b5fce719a44 | note | Standard / Specification - Project Specification 4.3
5aa1ed71-ef58-55c3-983f-29ac1d35e5bc | note | Verifying Document - IANZ Scala test result
5c3f2d8c-1fcb-59cf-9887-729cde761a98 | note | Frequency - 1 Test/Manhole
97cdda2f-e76e-5655-840e-23cadfc13db6 | note | Verification Activity - H
f7a9b1b8-70e2-5f25-84bf-26b7e30c2455 | note | Verification Activity - By: - QE
3f3fc7a3-9e24-59ae-8947-8d37a1705531 | checkpoint | 3.1.10 - Undercut Backfill Compliance
f5d28d44-e770-5c37-9b43-0262b26bcf56 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average 98%) of MDD
e237cff0-422d-5a3e-b95b-96ef53bed8f3 | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 3725:2012
fd7aba61-0d96-53cc-97eb-5cde4f3d2ba1 | note | Verifying Document - IANZ Lab Test Report
6fe58900-5a8b-50d7-ab64-590c7c065ad2 | note | Frequency - 1 Test/Manhole if Undercut required
800b5487-1c28-541a-8329-d8a94d8e400c | note | Verification Activity - H
917fbdb0-418e-5466-a6fe-b12d3fa9290d | note | Verification Activity - By: - QE
56be677b-237c-52f9-9b70-a5a801cf2760 | checkpoint | 3.1.11 - Bedding Compaction Testing
2d183ad2-6329-5085-8bc5-13ac4e92f2d6 | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average 98%) of MDD
e1b29de3-a730-53c7-8d76-2d7e993deabb | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 3725:2012
aebdbf95-4e5e-5d9a-bab5-737c9a2935ba | note | Verifying Document - IANZ Lab Test Report
ccdc68b2-6f5b-5697-a585-59cc69549c59 | note | Frequency - 1 Test/Manhole
b4501a13-5213-5924-ad78-9145b0b42f90 | note | Verification Activity - H
f423f03e-2f08-5bb3-b771-74422f0c3e41 | note | Verification Activity - By: - QE
b3b65b5e-7bcb-554b-9cb8-947a4ebef121 | checkpoint | 3.1.12 - Backfill Inspection
8dacf914-9b08-546f-a9e3-9b3fe5cc4935 | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the manhole
2b084272-b8b6-5df0-84fb-13f3de659b9a | note | Standard / Specification - Project Specification 4.3
489cd81e-404c-5c4b-ba53-7198caa05a74 | note | Verifying Document - Photographs
ff693eec-23da-5e77-803d-4b7e0423c663 | note | Frequency - Continuous
fe61226b-e6d3-5623-88fe-7475c5d1ae37 | note | Verification Activity - S
9dab9a60-219b-5f79-882e-27df70458dac | note | Verification Activity - By: - PE
c8b12138-899b-5c57-b584-84dc761ac3ca | checkpoint | 3.1.13 - Backfill Testing
fd68ce07-ed6f-58e1-b85d-f91538958ac6 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC. Minimum Compaction 95%(Average 98%) of MDD
19760d10-412f-548c-9738-59448210c203 | note | Standard / Specification - MDD Average of 98% with minimum of 95% PS 4.5
05f3cf0b-31a7-5f95-8904-b79bba7c79f0 | note | Verifying Document - IANZ Lab Test Report
da9eb4b7-f5d6-5ace-ba2d-717b88dfae8f | note | Frequency - 4 Density tests per layer at Quarter Points Around Structure
3b9e8475-dca7-5e35-82ed-7a6cb0da0c7d | note | Verification Activity - H
716af32b-ddd9-52de-8389-d6cab9845209 | note | Verification Activity - By: - QE
e022f314-63cb-579e-8684-330a167a444d | checkpoint | 3.1.14 - Low Air pressure Test of Pipeline
66364606-a2c3-534e-ace6-3048f1d43445 | note | Acceptance / Conformance Criteria - Low Air Pressure Testing as per Appendix C2 NZS 4404 Refer to NZ/AS 2566.2 M5 (Constant pressure tests) "NTT 009"
de612459-5f70-5818-9692-8bde69981beb | note | Standard / Specification - Pump Air to 25kpa and maintain pressure for 3 minutes
d81c550e-1daa-5078-9784-1a7264ea80d5 | note | Verifying Document - Pressure Test Report
9e335dd2-ef48-5369-8897-e27b45acb834 | note | Frequency - 1 Per Line
f35c8c92-2a0a-5072-9fde-de6d1b2d5141 | note | Verification Activity - H
856a6127-b419-5d5b-b6e4-2b248fae3ec8 | note | Verification Activity - By: - PE
4ae69c39-52c5-59c8-8b51-32763396a1fd | checkpoint | 3.1.15 - Manhole Vacuum Test
00738fef-8cb6-51f0-87dd-c30b5c6b57c3 | note | Acceptance / Conformance Criteria - Manhole Leakage Test hold time as per Table 5-12
e87bf1ec-326e-58da-82df-2ee38be298c7 | note | Standard / Specification - Draw Vacuum of -254mm Hg
3fcacb97-bdb6-5b03-be3c-d256bf3bce66 | note | Verifying Document - Vacuum Test Report
b50aef71-5614-53b4-bc87-a8e119ba010b | note | Frequency - 1 Per Manhole
606da953-b867-5a2f-87be-2d07646604e2 | note | Verification Activity - H
1aa57890-8a66-5cb1-b2f5-79a96fc4593f | note | Verification Activity - By: - PE
af7a66f6-3592-548c-bb40-c96eb478aefa | section | SECTION 3 – CONSTRUCTION ACTIVITY - 3.2 CCTV & Reinstatement
ae4e0727-0ea0-5a5b-8cdb-39371bb338f2 | checkpoint | 3.2.1 - CCTV Inspection
49f7fb21-4d94-5678-95fe-f78b9df17770 | note | Acceptance / Conformance Criteria - Quality Check on New Works
915e5944-4095-5105-869c-b21edf93b491 | note | Standard / Specification - Project Specification 4.4 NZ Pipe Inspection Manual
9f223a2a-a09e-5164-a383-f07deaf708cc | note | Verifying Document - CCTV Report
bfc6f1be-dacf-5632-8129-6326a89ba06b | note | Frequency - 1 per line
5811b338-c224-5676-8dfd-eb01666d8fb5 | note | Verification Activity - S
d67a37a1-99ff-58c0-a5d0-99876a68a702 | note | Verification Activity - By: - PE
ff7525ea-17db-5363-91eb-cb4eb20a3429 | checkpoint | 3.2.2 - Reinstatement
d84a7d3f-8416-5520-9539-6112b4667f48 | note | Acceptance / Conformance Criteria - Quality Check on New Works/All the MH Lids and Cesspit Levels should align with the pavement specification in terms of level & alignment
e1ade64f-2cba-5b1a-b0bc-5b8923388c1a | note | Standard / Specification - Reinstate and Tie into existing surrounds
7a7a35f1-5faa-523e-b6ef-c17b9712f2e8 | note | Verifying Document - Photographs & Level Checks
2a9de3dd-83d1-5702-bc8a-b157cdfdfc7b | note | Frequency - Continuous
5e940cb0-86cd-5929-bcdd-a32bb4e182a2 | note | Verification Activity - S
861e3c21-a38e-5d21-88fb-f33e9ed47378 | note | Verification Activity - By: - PE
84c3283d-24bd-504e-b593-7adb2a662256 | section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
7ae1b87b-673c-5c28-a4bd-4b55b08e4e89 | checkpoint | 4.1 - Survey Redline Drawings
591e64be-7b5b-5756-ba5c-5c480cb802b9 | note | Acceptance / Conformance Criteria - Quality Check on New Works based on the tolerances in RITS
88b6021a-3110-5045-8d91-2e60fb1249e0 | note | Standard / Specification - Project Specification
7237c198-5606-5126-876a-6ef80ae0fee9 | note | Verifying Document - Survey Data As Built Drawings Photographs Red-Pen Asbuilt Including Undercut Sections
33e15c37-82ba-5b45-b3a6-055493fdfcdb | note | Frequency - Post works completion
394dac1e-4d42-5da3-b3eb-6cd692c55060 | note | Verification Activity - H
71d6ef71-a603-5a9e-92cb-01a6dfd75c70 | note | Verification Activity - By: - SV
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
bdc6bc56-bcba-5a64-b16f-f77cd2b8d60a | checklist | SYS - ITP - Watermain PVC |  | ITP - Watermain PVC
c3992fc7-0196-5c33-bd5f-48c26a923c63 | section | 1. Pre-construction (P&G / Establishment)
40e50969-1ceb-5dd9-9b3c-01f7c53f618e | checkpoint | 1.1 - Extent of Line Setout
2188c8af-1b0e-5f69-b95b-5375efd86476 | note | Acceptance / Conformance Criteria - Ensure line and level of Stormwater has been marked out and agreed with Engineer in accordance with Watermain drawings Identify any clashes before construction.
52de05b7-2523-5da6-8f80-d5d818ab628f | note | Standard / Specification - Design Drawings
e61c2fd1-b475-5e0b-9891-8eb078397d5c | note | Verifying Document - ITP Sign Off
4c435d60-892e-549b-ad93-35365a7448d1 | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
1b47d63b-488e-5cb4-9561-a648677e6e11 | note | Activity - M
74725284-9d13-53b3-adb8-e716dfb7ab4f | note | By - PE
29b93ae9-4f0f-5379-a3b9-3f819c7cf4c4 | checkpoint | 1.2 - Environmental Protection
2daa111b-fb92-56cb-95f0-a0893bb7d5a7 | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
90e89d68-cdce-5951-807d-af0f8df8df9d | note | Standard / Specification - Project ESCP Plans
0c7e2196-45e7-501f-b491-48fbc3679d4b | note | Verifying Document - ITP Sign Off
183c9709-e340-589b-8e50-25dde0b61fe6 | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
58063758-ff8f-5ae4-8b2f-6df8e28b5bd3 | note | Activity - M
cb9fe534-57a2-5c13-bc53-f991d52f3827 | note | By - PE
c1757774-9612-5bda-8f1b-91d1e7f574f0 | checkpoint | 1.3 - Stakeholder
9989e892-ba99-5f46-94d1-2ad757eaa13b | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
7d849347-4c2f-51c4-9572-a3141cde43c8 | note | Standard / Specification - Project Stakeholder Management Plan
92486058-ca48-5a73-8b08-5850dfbedada | note | Verifying Document - ITP Sign Off
e0d10c68-8f54-592b-ae3e-ce2b6314547a | note | Frequency - Prior to Construction with continue updates throughout the works
86e0b0bb-7529-57e6-9e4e-984c639ef986 | note | Activity - M
f0b731bf-77b1-5b67-9e5f-a719015147f2 | note | By - PE
2d17bcb2-0fc6-51c9-86f5-20bc7fe95d1e | checkpoint | 1.4 - Permits
6dc1956a-3aec-55c3-ba28-fa3b08efcdc1 | note | Acceptance / Conformance Criteria - Permit to Dig must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip. Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. All known services must be clearly marked on site and briefed to the workforce .
37f81dcf-5bd4-55f4-acf6-85e9f7454b47 | note | Standard / Specification - Section 2.2.10 Project Specification
858dc8ce-814c-557c-8854-687c8c26c1a9 | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
484256f6-9cf4-5e56-bc22-cd9ce8cca84f | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
8f71f728-3673-5fbe-9e40-0033bce41387 | note | Activity - H
c9df6b3c-5476-5a0f-a223-54b76ae6401d | note | By - PE
2b839b91-0e59-52bf-bfbc-2a6a8cc5432d | section | 2. Material, Personnel & third party approval
a01633bd-9195-57bc-b7a7-0b51939340af | checkpoint | 2.1 - Pipes & Fittings
cb6bd198-cb74-5f66-a3a6-58ecf46e544e | note | Acceptance / Conformance Criteria - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes/fittings are correct and in good condition and compliant.
25841545-1c58-586f-9e80-ecf24d1107b7 | note | Verifying Document - Delivery Dockets
0b67eb3e-77fd-5648-bc0e-f15359c84a7b | note | Frequency - Each Delivery to Site
436ec73b-2a28-5f66-a0d0-4cacba4928ce | note | Activity - S
e86680e5-61d2-5449-9f68-97554420befe | note | By - PE
16430c7e-80ff-5cf2-a225-9e09136cc5be | checkpoint | 2.2 - Bedding/Overlay
ac3ee39b-6f57-5478-a442-c7b907d45e1b | note | Acceptance / Conformance Criteria - Confirm material grading and density of pit sand or other approved material
5d3234bd-54fe-55b6-b03b-87c35187af3b | note | Verifying Document - IANZ Lab Test Reports
61ba510d-a74b-5af1-ad03-82e66121b21c | note | Frequency - 1 Test per 1000m3
f97c4424-e8b9-5ca9-a68e-bbbec2432e03 | note | Activity - H
8057e399-7390-53b4-a075-ad6c78bb59fb | note | By - PE
2934d3fb-ac0a-5be8-853d-e440230282b7 | checkpoint | 2.3 - Backfill Material Compliance
0fd748e4-0fb9-504a-adf6-f623c6b4d7af | note | Acceptance / Conformance Criteria - Confirm material grading and density of pit sand or other approved material Use selected native soils in berm
8fa15a36-e044-5740-a8a2-9311781670ef | note | Verifying Document - IANZ Lab Test Reports
77be99f0-dc14-540f-91ce-14cf9920a5d0 | note | Frequency - 1 Test per 1000m3
c80191a8-c3bd-5a2a-bc63-9e54b7a980cc | note | Activity - H
a8b7c56f-354d-5900-86a1-235d2be3eda1 | note | By - PE
92420db2-3aa9-50e5-b1d6-d56be587136a | checkpoint | 2.4 - Undercut Backfill Material
3cb47e54-1418-5622-ab41-d615c9382364 | note | Acceptance / Conformance Criteria - Engineer to Specify Material to meet specifications dependant on material selected
675eb2f7-2d4e-5dd8-9a6a-44367de039b6 | note | Verifying Document - IANZ Lab Test Reports
5c0e5624-6b46-5f4e-8374-970dee1428ec | note | Frequency - 1 Test per 1000m3
6cfa0a74-20c1-5572-80f3-2efc11be00d6 | note | Activity - HP
c075b68e-f3e8-556b-a880-b2e139659d80 | note | By - ENG
7928edd2-fe08-5f6b-ab5c-f03ae853b9da | signoff | AUTHORITY HOLDPOINT
117c1a85-87b8-5979-891c-20eb9fdb1498 | checkpoint | 2.5 - Geotextile/Geogrid
92069664-6ed8-5673-8056-9568d2bfba26 | note | Acceptance / Conformance Criteria - NZTA F/07 Strength Class C & Filter Class 1 geotextile is to be used in the undercut. Geotextile or Geogrid that is used in the undercut is to be documented / marked up on drawing
c0adf8e0-1d1f-5027-ac8a-bae157691020 | note | Standard / Specification - Project Specification
1217c2d7-7332-559c-b7f7-4a23ae4e0757 | note | Verifying Document - Certification Photos of Delivery Dockets
8ae1e8ac-9cc7-5151-a8b3-88d75e34bda1 | note | Frequency - Material Used
08f4eefd-17ae-566f-9c7a-c4931b9dc2b4 | note | Activity - C
305ec3b4-fd80-5ba6-9290-213684fa245d | note | By - PE
d947afe9-c250-55e0-9f26-e1feb944cfb2 | checkpoint | 2.6 - Warning Tape
f1e47766-a3f3-5215-a1ce-135f9e9dbb47 | note | Acceptance / Conformance Criteria - Obtain Warning Tape from supplier
b71ee51d-495e-5b89-b505-abbfb185ea0b | note | Verifying Document - Delivery Dockets
90b99526-3ed0-5be3-9aea-1e794c893eae | note | Frequency - Each Delivery to Site
c663b7c0-cb53-5627-ad7d-f5d83742f76e | note | Activity - S
1121b458-64ce-5dca-b110-8108945ceb30 | note | By - PE
249967af-1f51-5783-977d-c9f3c7c8e1d6 | section | 3. Construction Activity
7d370922-7733-519c-b084-007467ea59e9 | checkpoint | 3.1 - Trench Excavation
f12678f6-c0fd-5ed9-9d41-7545f383290c | note | Acceptance / Conformance Criteria - Excavate trench to design height, placing spoil in approved area and benching as required Visual Inspection to any hard stones or rocks to be removed Any archaeological finds to be reported Inspections to any formation of soft spots
b510b474-29a2-5d0c-81a5-9a5212a8460f | note | Standard / Specification - Project Specification 4.3
4b59d9da-33f7-53d4-8f30-f408e131b057 | note | Verifying Document - Scala test result
cda8a064-9dfd-5a8c-8458-f1134750ce46 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
78a2c85b-1eaa-5acb-bf9f-a76a82062ae1 | note | Activity - H
46695756-bbb6-58f9-8696-bed72f90f8fd | note | By - QE
01f8da51-3f6a-58b3-8693-f52e82d75129 | checkpoint | 3.2 - Foundation Compliance
276d0ce0-dfa4-5bd5-a550-9580a3b5dd3e | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
cf10a023-8a94-5086-b4a7-7c0d119805d7 | note | Standard / Specification - Project Specification 4.3
f2dc0382-c218-52d7-8977-e280dd16c5b1 | note | Verifying Document - Scala test result
d4810fc8-9e04-5194-9ec3-fc30e1853e85 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
06a8366a-dfc5-5baa-9e15-0b508bbbed80 | note | Activity - H
26295be7-846f-5ad0-9afa-1dd19a084b78 | note | By - QE
fce24abf-d983-548d-883d-e31dcfd2c304 | checkpoint | 3.3 - Undercut Backfill Compliance
34324fc7-d773-54db-8aeb-fc5b1c2f454a | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average98%) of MDD
a38999ed-4542-576e-9f74-959326a18952 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
baf96eeb-3529-5ca7-b763-cf0dfe756ffc | note | Verifying Document - IANZ Lab Test Report
1a703f4d-039c-5d00-ac58-61d47565037c | note | Frequency - Based on Undercut Section
02dcf23e-0ddf-5af9-9f2f-489a85c3bd0f | note | Activity - H
96a5d9f8-dd74-57ae-b8fd-a669eca0bac1 | note | By - QE
d0bddc7d-e5fa-5baa-94fe-1275f06be289 | checkpoint | 3.4 - Bedding Compaction Testing
08a3cf70-2b4a-517e-9869-336e34e1f911 | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average98%) of MDD
cbf448d3-5bf3-5c35-be34-24363e0e426b | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
c18f590f-57f1-5d88-b849-183772593ece | note | Verifying Document - IANZ Lab Test Report
05c60a7a-bba7-500d-bb44-44a474905a1f | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
d3c46b89-d758-5e27-b802-1ad98e98ab2b | note | Activity - H
1798524e-a004-51ef-af4b-104ac3f8c2da | note | By - QE
983a1a11-117a-5587-8e28-483d3d186c18 | checkpoint | 3.5 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
bfbf2e9a-fbc9-5fd0-973b-8095fcfb763b | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD
969fa821-e653-5c9f-8897-7ec7ae2f0083 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
028a07b5-3f8a-52e8-8de4-6fba06ab734f | note | Verifying Document - IANZ Lab Test Report
437a0105-39f6-512b-b69b-44bd64fab130 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
9260299f-8ef5-52bc-bd37-83f49bdb4e74 | note | Activity - H
a5e58f80-6f41-59e1-af0d-001fe6c370e9 | note | By - QE
d235f1f7-7d52-5cc6-838d-bb5cf530d745 | checkpoint | 3.6 - Backfill Inspection
990919b2-90bb-5bf4-bc57-bdc954877ec6 | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the pipeline.
106a340e-9051-54e1-89a9-15bf607d4d77 | note | Standard / Specification - Project Specification 4.3
7ed35f7c-4b27-5ebd-8390-370abfc9f814 | note | Verifying Document - Photographs
6b2fe735-3696-533d-bab8-16980d8f1304 | note | Frequency - Continuous
2e70d804-bb9d-5d4f-9903-b55ab30e5653 | note | Activity - S
da1687ab-91ab-58e9-91b6-1b6e97041a12 | note | By - PE
23851ce8-70e8-50f5-8a7c-b4693607ea05 | checkpoint | 3.7 - Install Warning Tape
89ad8ee1-db8e-53c5-b079-f92974f40951 | note | Acceptance / Conformance Criteria - For open trenching, detector tape shall be placed approximately 200mm below final ground level and metallic ‘detector’ tape coloured blue, stipulating ‘Danger – Water Main Below’ (or similar) shall be laid.
d0d4470d-e0c0-5649-9097-5dea6fc91f18 | note | Standard / Specification - RITS
21b7fcef-c235-5990-a6fd-f5e7757bfb27 | note | Verifying Document - Photographs
30ab73b0-3683-507d-ac37-9477ae9dc08e | note | Frequency - Continuous
1927f6e7-bf71-5f57-b600-bc4d095c4728 | note | Activity - S
ec5e7354-bd30-5124-93d6-dd96acb2018c | note | By - PE
f17dd255-5836-524d-b09e-559b70479f73 | checkpoint | 3.8 - Survey
a5d031ac-99e2-5ea8-bc94-c509b478106f | note | Acceptance / Conformance Criteria - All Water Mains shall be laid in a straight line or following street layout. The deviation from approved design alignment permitted either in plan or elevation shall be: Open Cut – ± 50mm on straight and 100mm in curves All pipes, fitting and thrust blocks to be as built prior to backfilling
681466f1-4732-5e3b-b0ea-286d982015e0 | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
2c0c5481-84e6-5bff-8007-7a844c38bedf | note | Verifying Document - Survey Data
66759fe9-2a36-5335-a22c-25c4b5dd3229 | note | Frequency - Continuous
9ba33e89-78d1-5cef-9805-8f994815413b | note | Activity - C
69778e5c-9b81-5ce5-8d17-dd4ed98cc005 | note | By - SV
b475c56c-1e51-53b0-a7b1-bcb5786f5689 | checkpoint | 3.9 - Backfill Compaction Testing
c788c146-bfb9-5a96-b95c-3518e3b3e9f7 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC.
931f3c70-962d-5967-b81f-1b19a97e7bf3 | note | Standard / Specification - RITS
c9458d99-170d-53ae-8103-b196f1f0fa35 | note | Verifying Document - IANZ Lab Test Report
e9547088-f957-51a1-8c0e-ee8a1f0b6997 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
298dad17-495a-52c9-be43-f3bbe3b937ed | note | Activity - H
c9717a72-4c7f-5c9d-a696-26defe658e28 | note | By - QE
f3176f0c-286c-506d-8552-3a9f3b62de38 | checkpoint | 3.1 - Pressure Testing
5d69a420-1957-5b1c-9290-3c51d88e388b | note | Acceptance / Conformance Criteria - At least one working day advance notice shall be given to council for pressure testing of pipelines. All pipelines shall be pressure tested and backfilled after anchor blocks, specials and fittings are completed, but with joints and connections visible. The final tests are to be witnessed by Council prior to the pipe being connected to the ‘live’ network. No further connections will be permitted after this stage. Refer to NZS 4404 Appendix C3 for the requirements or if this not available, the pipe manufacturer’s procedure.
5b2454ea-1cc6-594d-a88e-513232a2193d | note | Standard / Specification - 6.3.10 RITS
6e90bbf9-09d4-54e5-b7e6-9a44629abfc2 | note | Verifying Document - Visual Inspection & Report
f2c3c247-ebb0-5874-a6dc-294338df015c | note | Frequency - Completion of Works
5bde098e-eb81-5021-b0e8-32eedf795680 | note | Activity - S
6b55841c-7a86-5f6e-a16d-f8ba94e5ce4c | note | By - PE
682b782b-da97-511b-a451-533bb2dc1e9d | checkpoint | 3.11 - Disinfection & Flushing
a04ef4c3-e232-5cb6-bf4a-b48be7c1cbb3 | note | Acceptance / Conformance Criteria - Appendix D of NZS 4404 – Water Supply Disinfection Specification shall apply Discharge of Testing or Chlorinated Water from pipelines may require a resource consent from the regional council
72e62171-3897-5595-bacf-de1ed94ce84e | note | Standard / Specification - 6.3.11 RITS
1a077abb-5e7e-54ee-b677-bc5d79b10d96 | note | Verifying Document - Visual Inspection & Report
012e07a0-eb0d-5930-b43a-b7ed3ebb79d4 | note | Frequency - Completion of Works
480678f5-c94c-5bce-9be6-d7378074e353 | note | Activity - S
80577bfd-b617-5499-b284-b5dae1307d01 | note | By - PE
b1d7c191-8845-5cd8-bc06-9e45bfcb6347 | checkpoint | 3.12 - Bacteriological Test
ecf71ef6-9afe-54ef-b387-99bad42254b0 | note | Acceptance / Conformance Criteria - In commissioning new pipelines, Council shall be given 24 hours’ notice as to when sampling for bacteriological tests is to be carried out. Water in the pipeline shall be sampled between 12 hours and 48 hours after postchlorination flushing and the samples tested for the presence of E.coli, Coliforms and Heterotrophic Plate Count by a Ministry of Health Approved laboratory with IANZ accreditation for this type of test. The number of samples shall be at least one for projects involving less than 100m of pipe, two for projects up to 200m length, etc. “A satisfactory result is s <1 MPN/100ml for E.coli and Total Coliforms and less than 20 CFU/ml for Heterotrophic Plate Counts.” If E.coli is detected the pipeline shall be swabbed, flushed, disinfected, flushed again and then the bacteriological tests repeated. The process shall be repeated until such time a clear test is recorded. Note: There are high risks of test failure due to sample contamination so it is recommended that the testing laboratory is also involved in collecting the sample.
8458ae3b-7797-5a0a-814d-f2e6b72268ae | note | Standard / Specification - 6.3.11.2 RITS
e3bb0c54-bcd9-5b91-92e8-cb2da86ad9a5 | note | Verifying Document - Visual Inspection & Report
1c926b7a-e073-5363-94e9-287f94a4c5f7 | note | Frequency - Completion of Works
1cb5f6b7-91a6-5b74-b072-c914ba3092a9 | note | Activity - S
6a48d096-0034-56d8-868a-c78b608d8349 | note | By - PE
67389d0d-12af-5ad3-85d9-f07119c2365b | checkpoint | 3.13 - Reinstatement
8ec17bcc-d926-596a-8ec1-55e292b11670 | note | Acceptance / Conformance Criteria - Quality Check on New Works
12c240a7-5851-5a10-a894-dfc1f21a71de | note | Standard / Specification - Reinstate and Tie into existing surrounds
26665455-42e7-5cf8-af92-81a44a978efc | note | Verifying Document - Photographs
cf7cef0f-8302-5fa6-8771-1d4718d773d3 | note | Frequency - Continuous
6b0fbabb-ce6a-568c-be52-0fa22a06b6a6 | note | Activity - S
606b0568-359a-5ac7-a423-5451cf87de4f | note | By - PE
85475bb6-9a9c-571e-bdc0-15f2014da4d2 | section | 4. Post-construction (Final Inspection & Handover)
b0345a60-8f72-56e0-9331-c90c4130b0fb | checkpoint | 4.01.01 - Survey Redline Drawings
970a77da-11d9-53d6-a1c1-82d62e20424c | note | Acceptance / Conformance Criteria - Quality Check on New Works based on the tolerances in RITS
989fa426-033b-5cca-bab8-65ba09ef6e49 | note | Standard / Specification - Project Specification
f78817de-6c2e-573e-ac02-c1c19369129d | note | Verifying Document - Survey Data As Built Drawings Photographs
8c5281e5-f67d-50b7-b542-966288db2b75 | note | Frequency - Post Works Completion
45c3f513-76b5-5f0e-a367-64bc9aaa06ad | note | Activity - H
5dc829e6-c403-5afa-9d2f-41b4948b6ec6 | note | By - SV
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
a4e901b4-a1a9-544e-ba44-750ab104ee97 | checklist | SYS - ITP - Watermain-PE - Rev C |  | ITP - Watermain-PE - Rev C
9dbf9507-d5c1-5f76-b0e9-632a875b7d7c | section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
40e50969-1ceb-5dd9-9b3c-01f7c53f618e | checkpoint | 1.1 - Extent of Line Setout
0a95db99-801f-5b64-b0e4-276d1fa2e264 | note | Acceptance / Conformance Criteria - Ensure line and level of Watermain has been marked out and agreed with Engineer in accordance with Watermain drawings Identify any clashes before construction.
abc94a23-054b-5d39-b35c-be522fbf1f99 | note | Standard / Specification - Design Drawings
1e4a6c2b-0712-54b5-a084-37293bc07f79 | note | Verifying Document - ITP Sign Off
04d90d08-9c86-529d-bdc7-d7f606d767e0 | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
4e07d6b6-c8ca-5939-a4a0-b2fdc77acff1 | note | Verification Activity - M
6512d3fd-65b8-5c93-81fc-3e7f4b28fcc3 | note | Verification Activity - By: - PE
29b93ae9-4f0f-5379-a3b9-3f819c7cf4c4 | checkpoint | 1.2 - Environmental Protection
65087ed9-b989-5020-8054-6ed613639f0d | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
82587d2b-c8ca-5163-a5e7-9c3bfa2d2f18 | note | Standard / Specification - Project ESCP Plans
d5236638-585e-5e7f-9e7a-d7121a304080 | note | Verifying Document - ITP Sign Off
0fc5d5f1-98f8-5eed-b176-57002e3258b9 | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
8366b632-0a70-5798-a741-526e150ce3e0 | note | Verification Activity - M
3f118ed7-6930-568c-a87a-51e8ce7b2afa | note | Verification Activity - By: - PE
c1757774-9612-5bda-8f1b-91d1e7f574f0 | checkpoint | 1.3 - Stakeholder
a909862c-53af-5e97-a577-a7e558fc1387 | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
8b30c912-5308-515f-9011-deff2e5af2d0 | note | Standard / Specification - Project Stakeholder Management Plan
22e61624-58fb-5c44-96e6-7405784989c9 | note | Verifying Document - ITP Sign Off
56b178e3-75aa-52a2-bcd2-286ca395bd16 | note | Frequency - Prior to Construction with continue updates throughout the works
cd042eb1-e4a2-5b7f-acb5-bee68734a58c | note | Verification Activity - M
6760a1e3-a3d9-563b-b0a8-5e043a724492 | note | Verification Activity - By: - PE
2d17bcb2-0fc6-51c9-86f5-20bc7fe95d1e | checkpoint | 1.4 - Permits
bd7e3c64-3e2a-5920-be2f-4935d4539398 | note | Acceptance / Conformance Criteria - Permit to Dig must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip. Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. All known services must be clearly marked on site and briefed to the workforce .
2fdbe04a-4a53-5122-ad61-f3593e431d12 | note | Standard / Specification - Section 2.2.10 Project Specification
1d39b83d-12b7-5980-af5f-15e7f1351ef1 | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
34edf06c-9560-55bb-ad35-1bd416718184 | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
fd608052-3027-5806-80c0-b9694cfcbeb7 | note | Verification Activity - H
521e991c-018a-531f-b625-69ce492ee8b1 | note | Verification Activity - By: - PE
b2505ca3-943c-534d-afb7-23e310ef1e65 | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
b27b7bf0-a182-5300-b84a-e6d5cb49b3a5 | checkpoint | 2.1 - Pipes/Fittings/precast Units
6df1cf8d-1004-5e3d-a742-b98320906274 | note | Acceptance / Conformance Criteria - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes/fittings are correct and in good condition and compliant.
031c0d23-6b74-5de3-9375-5b4fc963eee6 | note | Standard / Specification - Project Specification
149854d4-efea-59df-8950-1b9b3855a0c5 | note | Verifying Document - Delivery Dockets
3a9c473c-e0e8-5ebb-992c-60ade1ec1262 | note | Frequency - Each Delivery to Site
45508343-caa2-5b23-9604-27047d34681d | note | Verification Activity - S
e73d70cb-5a38-5e06-b3c8-827da199cece | note | Verification Activity - By: - PE
b90ae28d-1d95-5d3e-a911-4a6a9262b7f1 | checkpoint | 2.2 - Bedding/Side/Haunch/Overlay
3a420734-f6f5-5210-bd48-c7cf30ddb976 | note | Acceptance / Conformance Criteria - Confirm material grading and density of pit sand or other approved material
75f33260-14de-5971-9893-aa995af3205e | note | Standard / Specification - AS/NZS2566
00009c7b-af45-55d2-a046-86613d201e6d | note | Verifying Document - IANZ Lab Test Reports
a99f9c72-9a71-5d7e-a194-447c96233017 | note | Frequency - 1 Test per 1000m3
681c2fad-bfa9-5648-b36c-f6de1429e902 | note | Verification Activity - H
c8944537-7fca-59e6-99ce-a66dad5e2739 | note | Verification Activity - By: - PE
2934d3fb-ac0a-5be8-853d-e440230282b7 | checkpoint | 2.3 - Backfill Material Compliance
3825299a-25b8-5dca-9c50-d60dda320558 | note | Acceptance / Conformance Criteria - Confirm material grading and density of pit sand or other approved material Use selected native soils in berm
f19d87bf-d6e5-5fa9-a4f6-2af14e24867e | note | Standard / Specification - AS/NZS2566
b6a0cd45-5a4a-5990-b006-f25f752d2a22 | note | Verifying Document - IANZ Lab Test Reports
8c338912-06e8-5281-97d2-89075e2694d6 | note | Frequency - 1 Test per 1000m3
5330899a-c227-532d-836c-d2203b881d90 | note | Verification Activity - H
f9a7db0a-0db0-52bb-9e7d-8028f23c799e | note | Verification Activity - By: - PE
92420db2-3aa9-50e5-b1d6-d56be587136a | checkpoint | 2.4 - Undercut Backfill Material
5d62f13b-d2e3-5bbe-8ebb-6190edba7f68 | note | Acceptance / Conformance Criteria - Engineer to Specify Material to meet specifications dependant on material selected
67edce20-2cbe-58dd-9fbc-e4a3dc0042fe | note | Standard / Specification - Engineer to Specify
9877596e-c4ed-50c6-a42c-cea5098163f0 | note | Verifying Document - IANZ Lab Test Reports
325f4fc4-0dcf-51e4-b273-c3021feac7ad | note | Frequency - 1 Test per 1000m3
43683a3d-d98b-5349-b20c-8bdb7293c3f8 | note | Verification Activity - HP
49593a74-948e-5827-b1fb-ad1dbd727d6a | note | Verification Activity - By: - ENG
7928edd2-fe08-5f6b-ab5c-f03ae853b9da | signoff | AUTHORITY HOLDPOINT
117c1a85-87b8-5979-891c-20eb9fdb1498 | checkpoint | 2.5 - Geotextile/Geogrid
f631587e-0e63-5d52-ae7b-6ffab6e6b11d | note | Acceptance / Conformance Criteria - NZTA F/07 Strength Class C & Filter Class 1 geotextile is to be used in the undercut. Geotextile or Geogrid that is used in the undercut is to be documented / marked up on drawing
2fa75ace-6055-55c3-a40c-3d5ec1a96d1e | note | Standard / Specification - Project Specification
32ac1128-ed5e-5ed9-9488-502f284d6511 | note | Verifying Document - Certification Photos of Delivery Dockets
2d807760-f4c3-59a1-a843-389e3e17cb23 | note | Frequency - Material Used
d41ab3eb-8b17-5d1d-b5f2-8814b53290d0 | note | Verification Activity - C
b2953535-89b8-5b39-bdfe-ffa0646ea0d4 | note | Verification Activity - By: - PE
d947afe9-c250-55e0-9f26-e1feb944cfb2 | checkpoint | 2.6 - Warning Tape
da40fc40-9a2f-5faa-b5fb-0c2ca4185b52 | note | Acceptance / Conformance Criteria - Obtain Warning Tape from supplier
1d59ac43-680f-55b0-86a5-141a8a35ca49 | note | Standard / Specification - Project Specification
6d3e8edf-e66b-5f5f-ab2a-78a7e021b887 | note | Verifying Document - Delivery Dockets
1316695c-b14e-56f8-977f-b319f1fc1d28 | note | Frequency - Each Delivery to Site
692ce30d-cceb-518e-8220-c671d05aada5 | note | Verification Activity - S
afd1ceba-7788-5d54-9c23-413cd9057004 | note | Verification Activity - By: - PE
9cc06a11-17ee-5f49-ac50-31c36fc22fcb | section | SECTION 3 – CONSTRUCTION ACTIVITY
7d370922-7733-519c-b084-007467ea59e9 | checkpoint | 3.1 - Trench Excavation
07477a63-9617-55fe-adb6-e93d735206cf | note | Acceptance / Conformance Criteria - Excavate trench to design height, placing spoil in approved area and benching as required Visual Inspection to any hard stones or rocks to be removed Any archaeological finds to be reported Inspections to any formation of soft spots
f06a3223-84cd-5d5a-9609-ec670899afad | note | Standard / Specification - Project Specification 4.3
5a7fbfbe-688e-5eeb-b7ad-2fc27a97a8fd | note | Verifying Document - Scala test result
e34b1620-5292-5b32-81ad-7a8792e3f85c | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
b0059aa8-b108-581e-b180-24bb3e22c386 | note | Verification Activity - H
fd57b629-7db9-5b42-9417-98d7db9f76de | note | Verification Activity - By: - QE
01f8da51-3f6a-58b3-8693-f52e82d75129 | checkpoint | 3.2 - Foundation Compliance
a9462c7a-cf46-5d7b-82df-bea3402e54c1 | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
6f1a316b-9b79-5dcd-999c-40cdb0a8b150 | note | Standard / Specification - Project Specification 4.3
b1d4f6de-755d-5514-a8cb-7f021fc05aa7 | note | Verifying Document - Scala test result
c28a2bf1-3c70-5baa-b8ce-f3dd98ceaa12 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
c6f79caa-eb63-5d79-b8ac-95e2d42eddc3 | note | Verification Activity - H
4028434b-9d26-5617-9fdd-438d79ac0013 | note | Verification Activity - By: - QE
fce24abf-d983-548d-883d-e31dcfd2c304 | checkpoint | 3.3 - Undercut Backfill Compliance
7289baf5-ae7e-54ed-846a-4a2383392ef2 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average 98%) of MDD
36e66f02-4614-53f2-a456-2561cb8cc4ab | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 95% of MDD AS/NZs 3725:2007
44b1bd3c-6feb-5286-881e-7f19a7d026a6 | note | Verifying Document - IANZ Lab Test Report
9f9226ea-523e-5a2b-bc38-72889a5f5bba | note | Frequency - Based on Undercut Section
035f96b5-9059-5337-a1d4-fb0b83a58c03 | note | Verification Activity - H
a2f6e221-4bf9-5a06-ba86-7797617bc26e | note | Verification Activity - By: - QE
d0bddc7d-e5fa-5baa-94fe-1275f06be289 | checkpoint | 3.4 - Bedding Compaction Testing
1df4c996-99ab-53f7-942f-6ca7ac2aff57 | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average 98%) of MDD
c28e6dab-f53d-508b-be11-e11c00e05aa9 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
f3d231c1-3db3-5089-8245-ea9d51c272f4 | note | Verifying Document - IANZ Lab Test Report
73ee2aa1-dd52-5ff3-bf59-3d7fa4631d99 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
5db05c3a-ef53-5db7-bc65-5a25040b4841 | note | Verification Activity - H
e0ef5f15-9aea-5074-a24e-658ad51bd8b1 | note | Verification Activity - By: - QE
8512aed8-c0b4-5bdd-95ca-a50815b95c66 | checkpoint | 3.5 - Haunch & Side Zone Compaction Testing
5a8cedb3-7758-52f9-ae98-349a03eb9a84 | note | Acceptance / Conformance Criteria - Side zone shall extend from top of haunch zone to 0.5 times the pipe outside diameter 100mm if >75 , <150 150mm if >150 , <300 200mm if >300 , <450 NDM DT Minimum Compaction 92% of MDD
22c67c7a-4f0f-5f27-b916-79dc9fcd70bf | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
e044652c-b18c-5d5c-97ac-f94df5e912de | note | Verifying Document - IANZ Lab Test Report
9fc2191d-c30b-56cd-b959-798fdeb8ab74 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
a7e6fd8b-8b1c-5028-b00d-f5ab364e28b8 | note | Verification Activity - H
55e5af02-e543-5e18-8b81-0f6967bb0813 | note | Verification Activity - By: - QE
e2eff8b9-7f73-518a-b234-c20b9796b76c | checkpoint | 3.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
73c47ed0-cbf2-5993-934d-120bdd476cee | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD
15511fb1-9695-53bd-88f4-1bb6eb4a68eb | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
71d57a91-6ae9-52a3-842f-a526707ddbee | note | Verifying Document - IANZ Lab Test Report
8d60ce92-fb60-5a80-b904-b95a5faaee5b | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
ef0d9e80-b8db-56c6-8afb-6cc3e21ec69d | note | Verification Activity - H
c0779ffe-29b9-5921-b18c-a5822fe94a17 | note | Verification Activity - By: - QE
0715b9f9-616e-5d14-90de-eab1faefa26e | checkpoint | 3.7 - Collection of Waipa ITPs
db16c050-4db8-553b-b5ac-c707c111faf3 | note | Acceptance / Conformance Criteria - ITP 02 Manhole and Valves ITP 04 Butt Welding ITP 05 Commissioning
a542d803-defa-5fd1-b771-2d607713ed81 | note | Standard / Specification - PWRBSS Quality Management Plan
407354aa-ee45-5aef-81cc-93cd41c63f9a | note | Verifying Document - Document Review
26782718-d70a-5d80-bd2b-82c07cf499d1 | note | Frequency - Once
0ae112fd-56f4-526f-9070-382d1a63f2a0 | note | Verification Activity - HP
8d2e5d47-b8ba-5d26-a3a6-82ce5b197b84 | note | Verification Activity - By: - ENG
0f588dd6-d4d5-57d7-b432-2e66dc5cfbf7 | signoff | AUTHORITY HOLDPOINT
4df3c69f-32d6-5ce8-9283-300b3997b531 | checkpoint | 3.8 - Backfill Inspection
dc6de0af-115b-5843-b061-6be7817ecf46 | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the pipeline.
675da3b2-fd26-56a3-a501-da6826f06731 | note | Standard / Specification - Project Specification 4.3
6965b7d0-334b-59e2-aa93-25fa3229f737 | note | Verifying Document - Photographs
e95ccae1-d1a3-52a4-9d3b-e564218e2637 | note | Frequency - Continuous
f015779c-9373-5743-a646-802c363d4478 | note | Verification Activity - S
8cf4bc20-61bc-5eeb-a074-a44f5fdd7d96 | note | Verification Activity - By: - PE
6d0efba5-6acf-5128-a807-1ab3ab9b6acf | checkpoint | 3.9 - Install Warning Tape
275cc7b9-aa03-59b1-a9ef-15d48a4251a0 | note | Acceptance / Conformance Criteria - For open trenching, detector tape shall be placed approximately 200mm below final ground level and metallic ‘detector’ tape coloured blue, stipulating ‘Danger – Water Main Below’ (or similar) shall be laid.
89fe7a2a-2b50-544d-bdad-97e00f5130ea | note | Standard / Specification - RITS
f6fa2374-a03a-5ce2-bf54-c4c85325f636 | note | Verifying Document - Photographs
afddf2df-94e0-505b-8909-48f846096047 | note | Frequency - Continuous
84edf32f-7f89-51cf-ae66-6b1336689710 | note | Verification Activity - S
f36fa6dc-2bba-5148-8f6f-6e84f2679186 | note | Verification Activity - By: - PE
76853413-39ee-5af5-afc3-fe3a4e2ceaff | checkpoint | 3.1 - Survey
a294f9b0-4c02-5c4d-a1a3-5fc5966b04b4 | note | Acceptance / Conformance Criteria - All Water Mains shall be laid in a straight line or following street layout. The deviation from approved design alignment permitted either in plan or elevation shall be: Open Cut – ± 50mm on straight and 100mm in curves All pipes, fitting and thrust blocks to be as built prior to backfilling
bd943e00-f1ef-5548-9855-abc4a6da9574 | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
e578e240-102e-52d9-8bf4-4b212aa765eb | note | Verifying Document - Survey Data
7162641a-4e07-5fd2-b4a5-1f9598843f3a | note | Frequency - Continuous
715dba86-0507-520f-9d7c-b7ff9bba058f | note | Verification Activity - C
03bed1e0-d9a5-5761-9444-e30df7766f80 | note | Verification Activity - By: - SV
b1a8a1ba-4d3e-58f2-ba0c-96893bb7956d | checkpoint | 3.11 - Backfill Compaction Testing
dcb0cf94-74d4-51d1-8687-dfbb3bd0606b | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC Average of 98%
3655ad07-7eb9-5add-99a7-f46a315bd015 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
d6ae28a0-eb28-58ef-82ea-58ef1e0541c9 | note | Verifying Document - IANZ Lab Test Report
860a494c-b3af-53b1-be11-fdc81ccaed51 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
85d03948-9207-55e4-9ec0-aeae0b9cf4a2 | note | Verification Activity - H
d5659d13-9af2-564d-b799-0641cdf4eb19 | note | Verification Activity - By: - QE
11caa917-231a-5a12-9c4b-a1cf2601809a | checkpoint | 3.12 - Manhole Foundation Compliance
d2bb9c59-ced0-5fcb-b60d-aba2e6b81c43 | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
eca8b52f-be49-5686-a1ac-7e03b5cddfd5 | note | Standard / Specification - Section 4.3 PWRBSS Project Specification
cce2838a-eb0a-530a-8a34-51b66141f36c | note | Verifying Document - IANZ Lab Test Report
f0e0bf59-c689-530f-b43b-3271b1b807bd | note | Frequency - 1Test/MH
370ed67e-4d14-5680-bfb7-0014a22de54a | note | Verification Activity - H
5c327065-fbe3-5f72-88e3-56f05f100f09 | note | Verification Activity - By: - QE
3efb3cbe-8999-5c33-8733-f7f81942565c | checkpoint | 3.13 - Undercut Backfill Compliance
69d66008-6fab-587a-9ca1-edb57a344028 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average 98%) of MDD
8989cce0-1ab5-5a3e-8bf4-8902b0256e3c | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 95% of MDD AS/NZs 3725:2007
a7b502ab-05b3-5930-8848-e1bd823626b4 | note | Verifying Document - IANZ Lab Test Report
8f433644-ef93-594d-857d-0df99d6be813 | note | Frequency - Based on Undercut Section
79b84a28-db63-5020-addd-eefa8c943bb8 | note | Verification Activity - H
975e420a-7912-5a09-be21-4e80218f9f86 | note | Verification Activity - By: - QE
f78063ed-84dd-5c6f-b9a1-849bb040c16d | checkpoint | 3.14 - Bedding Compaction Testing
38cf7141-ec8c-5604-942d-b6b72faaabbf | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average 98%) of MDD
a847bebf-1df1-581f-8304-5c4b45e6cdd7 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
1c453333-f6dd-539b-80cc-ae7863c624b9 | note | Verifying Document - IANZ Lab Test Report
1badf2d5-f6bc-57c3-aa6a-c5a45440569a | note | Frequency - 1Test/MH
627ea6e2-0f21-532f-8fe7-6770a74b9623 | note | Verification Activity - H
0d85463d-dab3-51b7-bb97-9b404dff4af2 | note | Verification Activity - By: - QE
f19695cb-1e84-53f4-b841-29cea8a6b257 | checkpoint | 3.15 - Backfill Inspection
d92fe8a3-ca3a-5430-bfc7-b1328efc2f77 | note | Acceptance / Conformance Criteria - Inspection of manhole prior to backfilling to ensure correct installation and that the joints are sealed. Check for any gaps.
0fcf5aa2-04c1-5473-8ae9-cad3834c3bb4 | note | Standard / Specification - Project Specification 4.3
71a08e1e-9f9e-5735-b9e7-974aca4bf205 | note | Verifying Document - Photographs
e1875c14-0f50-58c6-b6ef-352bf1783dad | note | Frequency - Continuous
9dcc647f-fddb-5773-90ea-778339343ecf | note | Verification Activity - S
addfe930-6991-57da-95c7-300e647696b5 | note | Verification Activity - By: - PE
f86664cc-9c9c-55e4-b8f3-2878053f2a61 | checkpoint | 3.16 - Backfill Compaction Testing
0b304461-1592-59ec-8f1c-4adbbf43cc1b | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC Average of 98%
cb84dbae-3878-5efa-8b06-b15858234554 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
97ac4fea-d9c9-5c8c-baba-96f47f0b7fde | note | Verifying Document - IANZ Lab Test Report
7fc73e23-243b-544c-a192-4cf2db61ca9a | note | Frequency - 4 Density Tests per layer at Quarter Points around structure
01211731-cc47-5c7e-9d96-455d5e38e8d5 | note | Verification Activity - H
f79276d6-10e3-52d0-80a9-20e7c5b178e5 | note | Verification Activity - By: - QE
15492269-750f-5fc1-81c3-61be85d71970 | checkpoint | 3.17 - Reinstatement
2d63696d-2d33-5c5c-ac3f-78a5a0fb3fbc | note | Acceptance / Conformance Criteria - Quality Check on New Works
a3350074-8599-5295-b334-b07bdf8c4d10 | note | Standard / Specification - Reinstate and Tie into existing surrounds
0b512309-e2c5-51c7-9586-e8a752f5e706 | note | Verifying Document - Photographs
e23e2bb4-89dc-5278-9fad-10048a6d915c | note | Frequency - Continuous
f3a7a097-a0ac-58e8-ae1b-4c6b265514b9 | note | Verification Activity - S
388eeb85-5232-5b2b-a1aa-fa731eb4176e | note | Verification Activity - By: - PE
84c3283d-24bd-504e-b593-7adb2a662256 | section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
7ae1b87b-673c-5c28-a4bd-4b55b08e4e89 | checkpoint | 4.1 - Survey Redline Drawings
fbbf0793-2870-5073-bdad-313d6c053715 | note | Acceptance / Conformance Criteria - Quality Check on New Works based on the tolerances in RITS
49d8634e-c761-5a02-8077-f2be6dbcbed0 | note | Standard / Specification - Project Specification
8f244533-d06f-5885-b00d-17430dbaf917 | note | Verifying Document - Survey Data As Built Drawings Photographs Red Pen As-Builts including Undercuts
a6bf5a44-50bf-558b-b3b2-a54478fc7244 | note | Frequency - Post Works Completion
fb594479-9802-57fc-aeed-4b92904ad9ca | note | Verification Activity - H
72121a75-77cb-536b-88c1-a40ae647a69d | note | Verification Activity - By: - SV
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cc55fd5e-aa33-557d-bf7f-0f811d993e64 | textbox | Contractor's Rep Name:
7921be36-d225-5295-ba04-205bee4975d0 | textbox | Engineer's Rep. Name:
3316de49-878a-51d9-9ab5-0136179f6cbd | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature