## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | G38-SED-ITP Erosion & Sediment Control - Public Roads Upgrade | itp |  |  |  |  | G38-SED-ITP Erosion & Sediment Control - Public Roads Upgrade
section | Details
checkpoint | 1 - Prepare Erosion & sediment Control Plan (ESCP) for the Works Under the deed
label | FREQUENCY: Once
label | ACCEPTANCE CRITERIA: The ESCP will form part of the EMP and will be incorporated in the ERA.
label | REFERENCE DOCUMENTS: G38.2.2
label | RECORD OF CONFORMITY: Verification Checklist
label | IP
label | RESPONSIBILITY: Environmental Rep.
date | Date Completed:
checkpoint | 2 - Install Erosion and Sediment Controls
label | FREQUENCY: Per Area
label | ACCEPTANCE CRITERIA: Installed in accordance to the approved progressive ESCP and guided by the BLUE BOOK.
label | REFERENCE DOCUMENTS: EMP
label | RECORD OF CONFORMITY: Verification Checklist
label | IP
label | RESPONSIBILITY: Environmental Rep.
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | R11-ODR-ITP-Open Drains - Public Roads Upgrade | itp |  |  |  |  | R11-ODR-ITP-Open Drains - Public Roads Upgrade
section | Details
checkpoint | 1 - Drain
label | FREQUENCY: Per Area
label | ACCEPTANCE CRITERIA: As indicated on design drawing
label | REFERENCE DOCUMENTS: Design DWGS
label | RECORD OF CONFORMITY: Verification Checklist
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2 - Set out the works
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: Notification that set out of drainage system has been completed. The Nominated Authority will inspect the set out prior to authorising the release of the Hold Point.
label | ○ Set out the location and level of open drains as shown on the Design Drawings.
label | REFERENCE DOCUMENTS: R11.4.1.1 Design DWGs
label | RECORD OF CONFORMITY: Hold Point
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3 - Excavation for Drainage Structures
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: Excavate to dimensions shown on drawings.
label | ○ Where dimensions are not shown, excavate to:
label | — Min 300mm depth
label | — Min waterway of 0.2 m²
label | — Batter slope ≤ 2H:1V steep
label | — Have a grade slope of ≥1%
label | — Extend open drains as necessary to natural drainage depressions or to a drainage system.
label | REFERENCE DOCUMENTS: R11.4.2.1
label | RECORD OF CONFORMITY: Verification Checklist
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 4 - Construction of open drains with grade less than 1%.
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: Notification that 1% minimum grade cannot be achieved.
label | ○ The PV will consider the matter, and will direct you further, prior to authorising the release of the Hold Point.
label | REFERENCE DOCUMENTS: R11.4.2.1
label | RECORD OF CONFORMITY: Hold Point
label | HP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Inadequate Foundation Material
label | FREQUENCY: Per lot
label | ACCEPTANCE CRITERIA: Notification to the PV that inadequate foundation material has been excavated to the extent required.
label | ○ Replace inadequate foundation material with materials from cuttings, or with other conforming material, and compact to the requirements of Clause 4.9.2 of this Specification.
label | REFERENCE DOCUMENTS: R11 4.3.3, R11 4.9.2
label | RECORD OF CONFORMITY: Witness Point
label | WP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 6 - Trim and compact open drains
label | FREQUENCY: Per Lot Q6/L.3.1
label | ACCEPTANCE CRITERIA: Trim open drains to produce a uniform surface free of irregularities.
label | REFERENCE DOCUMENTS: R11.4.2.1, R11.4.9.2
label | INSPECTION / TEST METHOD: T166
label | RECORD OF CONFORMITY: Test Report
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | R44-FIL-ITP-Select Fill - Public Roads Upgrade | itp |  |  |  |  | R44-FIL-ITP-Select Fill - Public Roads Upgrade
section | 1 - Preliminary
checkpoint | 2 - Set out the works
label | FREQUENCY: Each Section
label | ACCEPTANCE CRITERIA: Establish Pegs (or equivalent) to identify the extend of filling
label | REFERENCE DOCUMENTS: Design DWGs, Survey Management Plan
label | RECORD OF CONFORMITY: Verification Checklist
label | IP
label | RESPONSIBILITY: Surveyor
date | Date Completed:
checkpoint | 3 - Verify conformance of select fill material
label | FREQUENCY: As required
label | ACCEPTANCE CRITERIA: Imported Select Fill Material: CBR15
label | REFERENCE DOCUMENTS: Design Plans
label | INSPECTION / TEST METHOD: Verification
label | RECORD OF CONFORMITY: ITP, Material spec report
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 4 - Construction
checkpoint | 5 - Place, spread fill material (parallel to the grade), compact and test to specified densities
label | FREQUENCY: Per Lot, Q6/L3.1
label | ACCEPTANCE CRITERIA: 95% Std compaction
label | ○ Minimum layer thickness after compaction ≥ 100mm
label | ○ Maximum layer thickness after compaction <= 150mm unless otherwise approved
label | ○ Ensure insitu sampling and testing for compaction conformity is undertaken in accordance with TfNSW Q6 Annexure L
label | REFERENCE DOCUMENTS: R44.5.1.3, R44.5.2.2, R44.7.2, R44.7.3, R44.7.4, R44/A5
label | INSPECTION / TEST METHOD: T166
label | RECORD OF CONFORMITY: Test Report
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 6 - For hill side embankment foundation, terrace 1m wide of the hill side of embankment and ensure its free draining
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: Minimum Step Depth ¦¦ Slope
label | 600mm ¦¦ > 4H:1V
label | 300mm ¦¦ < 4H:1V
label | ○ Terraces not required on slopes < 10H:1V
label | REFERENCE DOCUMENTS: R44.3.3 Fig R44.4
label | RECORD OF CONFORMITY: Verification Checklist
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 7 - Conduct Deflection Testing – Proof rolling Method within 1.5m underside of SMZ
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: Must not exhibit deformation, yielding and/or show signs of distress or instability.
label | ○ All embankment layers and other surface within 1.5m of underside of SMZ
label | ○ With refer to RFI 436: Clause 3, Note B on T198 states that other equipment may be used,
label | 1. Benkelman Beam truck (as per T160)
label | 2. Loaded bogie truck
label | 3. 12M Grader (or larger
label | 4. 12t Roller (or larger)
label | REFERENCE DOCUMENTS: R44.7.6.1
label | INSPECTION / TEST METHOD: T198
label | RECORD OF CONFORMITY: Witness Point
label | WP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | R71-UCP-IPT-Unbound Pavement Course - Public Roads Upgrade | itp |  |  |  |  | R71-UCP-IPT-Unbound Pavement Course - Public Roads Upgrade
section | 1 - Preliminary
checkpoint | 2 - Set out the works
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: Establish Pegs (or equivalent) to identify the extent of pavement
label | RECORD OF CONFORMITY: Verification Checklist
label | IP
label | RESPONSIBILITY: Surveyor
date | Date Completed:
checkpoint | 3 - Check underlying lots are conforming and closed
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: Check underlying drainage and earthwork lots are conforming and closed, Hold Points released
label | REFERENCE DOCUMENTS: R44.6.1.2, R11.4
label | RECORD OF CONFORMITY: Verification Checklist
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 4 - Materials
checkpoint | 5 - Obtain material specification certificates
label | FREQUENCY: Per Stockpile
label | ACCEPTANCE CRITERIA: Verify material meets the requirements of R71 and D&C 3051. Attach NATA endorsed test results to the statement, indicate the quantity of material represented by the test results.
label | REFERENCE DOCUMENTS: R71.2.2
label | RECORD OF CONFORMITY: Hold Point
label | HP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 6 - Construction
checkpoint | 7 - Check material upon delivery
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: The material must be slightly damp and at the time of delivery
label | ○ Check delivery docket to ensure correct materials supplied
label | REFERENCE DOCUMENTS: R71.2.4
label | RECORD OF CONFORMITY: Verification Checklist
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 8 - Placing, spreading, compaction and trimming the material
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: Maintain field moisture content during placement and compaction within the target moisture content envelope
label | ○ Compacted layer to be 100-150mm thick
label | ○ For modified (sub)base, complete the construction within the Allowable Working Time
label | ○ No roller marks left after final trimming
label | ○ No delivery traffic allowed on the placed
label | ○ Trim the pavement course to design level
label | REFERENCE DOCUMENTS: R71.6.5
label | RECORD OF CONFORMITY: Verification Checklist
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 9 - Verify finished pavement properties
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: Compaction to 100% std
label | ○ Moisture content ≤70% of OMC prior to seal – as relative compaction frequency
label | ○ Level within -0/+10mm (base), or -10/+0mm (subbase) - 1 per 20 linear metres, offset as per table G71.7
label | ○ Layer thickness within -0/+20mm (base), or -/+10mm (subbase) – at least one site per 75m, with a minimum of 2 per lot
label | ○ 3m straight edge: max. 5mm – minimum 1 per 20m2
label | ○ Pavement width ≥ design width – minimum 1 per 20 linear metres.
label | ○ Unconfined compressive strength is less than 1 MPa (accordance with T116)
label | ○ Minimum frequency of testing (T116 one pair per 400 tonnes or part thereof)
label | REFERENCE DOCUMENTS: R71.8, R71.8.4.2, R44.7.4
label | INSPECTION / TEST METHOD: T116, T173, T166
label | RECORD OF CONFORMITY: Test Report
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 10 - Obtain approval for sealing of the pavement
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: Submit to the Project Verifier with test results of above pavement properties
label | REFERENCE DOCUMENTS: R71.6.8
label | RECORD OF CONFORMITY: Hold Point
label | HP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Carry out base course surface assessment
label | FREQUENCY: As directed
label | ACCEPTANCE CRITERIA: The average ball penetration value of a sample location (Pes) is ≤ 3.0 mm; and the characteristic ball penetration value is ≤ 2.5 mm.
label | REFERENCE DOCUMENTS: R71.8.10, Q6/L3.2
label | INSPECTION / TEST METHOD: T271
label | RECORD OF CONFORMITY: Test Report
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 12 - Obtain approval of treatment of non-conforming lots
label | FREQUENCY: Per Area
label | ACCEPTANCE CRITERIA: Submit to the Project Verifier a NCR and details of proposal to rectify or replace the Lot, prior to carry out the rectification works
label | REFERENCE DOCUMENTS: R71.8.12
label | INSPECTION / TEST METHOD:
label | RECORD OF CONFORMITY: Hold Point
label | HP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | R116-ASH-ITP-Asphalt Pavement - Public Roads Upgrade Upgrade | itp |  |  |  |  | R116-ASH-ITP-Asphalt Pavement - Public Roads Upgrade Upgrade
section | 1 - Preliminary
checkpoint | 2 - Confirm the type of asphalt seal to be laid against the design drawings
bool | Correction
bool | Intermediate
bool | Wearing
bool | AC20
bool | AC14
bool | AC10
bool | AR450
bool | A15E
textbox | Other:
textbox | Thickness:
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: The type and thickness of asphalt are proposed as per the details shown on pavement design drawings
label | REFERENCE DOCUMENTS: Design DWGs
label | RECORD OF CONFORMITY: Verification Checklist
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3 - Mix Temperature for Laying
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Warm Mix:
label | — To be delivered into the paver between 120C-165C. Minimum temperature before compaction of 110C.
label | ○ Hot Mix:
label | — To be delivered into the paver between 140C-175C. Minimum temperature before compaction of 120C.
label | ○ Temperature recorded by Infra-Red Temperature Gun & Probe.
label | REFERENCE DOCUMENTS: R116 and Asphalt Laying Procedure. Measure using an infrared thermometer.
label | RECORD OF CONFORMITY: Hold Point
label | HP
label | RESPONSIBILITY: Site Engineer/ Foreman
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4 - Preparation of Pavement Surface
checkpoint | 5 - Setup the working area
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: Mark-out the placement boundary, chainage and required thickness on the surface of the areas
label | ○ Ensure the mark-outs matches drainage inlets including kerb and gutters
label | REFERENCE DOCUMENTS: R116.4.3
label | RECORD OF CONFORMITY: Verification Checklist
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 6 - Preparation of pavement surface
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Prior to place asphalt, prepare the surface to a clean, no loose material, defect free and road markers removed, road services and fixtures in vicinity covered, and where required, prime sealed.
label | ○ Sweep to extend 300mm beyond each edge of area to be paved.
label | REFERENCE DOCUMENTS: R116.3.2, AS2150.10
label | RECORD OF CONFORMITY: Verification Checklist
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 7 - Check and record pavement temperature and weather conditions
label | FREQUENCY: Each lot / 1 check per 2 hours
label | ACCEPTANCE CRITERIA: With zero wind speed pavement temperature must above:
label | Binder ¦¦ Aggregate ¦¦ Temperature
label | A15E ¦¦ AC20 ¦¦ 10°C
label | A15E ¦¦ AC14 or smaller ¦¦ 15°C
label | AR450 ¦¦ AC20 ¦¦ 5°C
label | AR450 ¦¦ AC14 or smaller ¦¦ 10°C
label | ○ Add 5oC to above limits for each 5 kph of wind speed above zero
label | ○ Do not place tackcoat and/or asphalt when the pavement surface is wet and/or rain is imminent.
label | REFERENCE DOCUMENTS: R116.3.7, 3252, 3253
label | RECORD OF CONFORMITY: Asphalt Placement Record
label | IP
label | RESPONSIBILITY: Site Engineer, Subcontractor
date | Date Completed:
section | 8 - Construction
checkpoint | 9 - Construction of temporary ramps / preparation of construction joints
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Set up and prepare the temporary ramps and construction joints for safe access and protection of constructed works
label | REFERENCE DOCUMENTS: R116.3.12, AS2150.A
label | RECORD OF CONFORMITY: Verification Checklist
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 10 - Application of tack coat
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Apply Tack coat at the nominated rate, and record the rate in the Asphalt Placement Record Sheet
label | ○ The application rate is to be between 0.15-0.3 L/m2, if not otherwise specified
label | ○ Nominate in writing to the RMS rep your proposed tackcoat application rate prior to applying the tackcoat.
label | ○ Reduced application rate for tackcoat is acceptable due to the existing underlying pavement material. Comply with PV first.
label | ○ Report the application rate in terms of residual bitumen and state the percentage dilution of the tackcoat used during spraying
label | ○ Provide to RMS rep a daily record with your endorsement, of the average tackcoat application rate applied to each lot.
label | REFERENCE DOCUMENTS: R116.3.9
label | RECORD OF CONFORMITY: Asphalt Placement Record
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 11 - Check Asphalt Temperature
label | FREQUENCY: Per Delivery Load
label | ACCEPTANCE CRITERIA: Measure and monitor paving and compaction temperatures and ensure they are not fall below which nominated in item 5.
label | REFERENCE DOCUMENTS: R116.3.8
label | RECORD OF CONFORMITY: Asphalt Placement Record
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 12 - Construct joints to specified locations
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: Longitudinal joints are to be:
label | — Offset 150mm from the joint of underlying layer, within 150mm of the line of cross fall change
label | — Located out of wheel paths & in surface layers, coincident with final traffic markings.
label | ○ Transverse joint are to be:
label | — Located a min 25m apart
label | — Offset 1m from the joint in the underlying layer
label | — Formed at the commencement of each paving run
label | — Formed when a delay in paving causes asphalt temperature to fall below the initial compaction temperature nominated in Clause 3.8..
label | REFERENCE DOCUMENTS: R116.3.10
label | RECORD OF CONFORMITY: Verification Checklist
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 13 - Supervise the placement work
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: All asphalt must be homogenous in appearance. Areas of asphalt that exhibit segregation, cracking, ravelling, bony or fatty material, or damages rectified or replaced.
label | REFERENCE DOCUMENTS: R116 5.1
label | RECORD OF CONFORMITY: Verification Checklist
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 14 - Post Placement
checkpoint | 15 - Protect services
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: Immediately after the asphalt has been placed, clean & remove off waste asphalt from affected services and road fixtures
label | REFERENCE DOCUMENTS: R116.4.3
label | RECORD OF CONFORMITY: Verification Checklist
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 16 - Obtain and verify conformance records including relevant verification sheets
label | FREQUENCY: Per Lot / R116.L
label | ACCEPTANCE CRITERIA: Check conformance report against conformance criteria:
label | ○ Production test results
label | ○ Asphalt placement record with all dockets
label | ○ Field test results – insitu air void, course thickness
label | ○ Lot diagram with chainages
label | ○ 3m straight edge report
label | ○ NCRs if required
label | REFERENCE DOCUMENTS: R116.L Q6
label | RECORD OF CONFORMITY: Asphalt Placement Record
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 17 - Conformance of Levels and Thickness of Pavement
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: Level of any course placed meets table R116.9 except where tying in to existing surface where the pavement is to drain surface water and match levels of existing surface.
label | ○ Average thickness of calculated by survey consistent with average thickness calculated from cores except for wearing course which is to be within 10% of design thickness.
label | REFERENCE DOCUMENTS: R116.4.3.1
label | RECORD OF CONFORMITY: Survey Report
label | SCP
label | RESPONSIBILITY: Surveyor
date | Date Completed:
checkpoint | 18 - Submit Test results to RMS
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: To be submitted progressively
label | ○ Binder content, combined particle size distribution, air voids – within one day of mixing
label | ○ In-situ air voids, course thickness and course shape within 3 days of placing
label | REFERENCE DOCUMENTS: R116.5.3.3
label | RECORD OF CONFORMITY: Transmittal
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP