## Table 1
Lot No. |  |  | Lot Details: | [5 empty] | Lot Size/Qty: | [10 empty] | Date:
| Item No. |  | Task/Activity Description |  |  |  | Inspection/Test | [9 empty] | HP/ WP/ AP/IP TP/ SCP |  | Responsibility |  | Comments | Checked by:
[7 empty] | Frequency |  | Acceptance Criteria |  | Reference Documents |  | Inspection /Test Method |  | Conformanc e Record | [6 empty] | Client | Fulton Hogan | Date
1. Preliminaries and Submissions
1.1 |  | Check for correct documentation |  |  |  | Before commencement of activity |  | Check correct documentation is being utilized |  | Drawings |  | Current revision of drawing |  | Current revision of drawing |  | *HP |  | Fulton Hogan
1.2 |  | Ensure Safety, Traffic, Quality & Environmental management measures are in place |  |  |  | Prior to commencement of activity. |  | Safety plan, traffic management plan and environmental management plan |  | PSP, TMP, EMP |  | Ensure all measures in place as per plan |  | Inspection |  | HP |  | Fulton Hogan/Client
1.3 |  | Stockpiling |  |  |  | Prior to removing material |  | Confirmation of stockpile location approved by superintendent. |  | FH Scope document, EMP |  | Approval |  | ITP |  | WP |  | Client/ Fulton Hogan
1.4 |  | Identification of services |  |  |  | Prior to commencement |  | Any existence of underground services to be located and proven |  | BYDA Section 100.8 |  | Inspection |  | ITP |  | HP |  | Fulton Hogan
1.5 |  | Project management Plan Completed |  |  |  | Prior to commencement |  | PMP Completed |  | PMP checklist completed |  | Inspection |  | ITP |  | HP |  | Fulton Hogan/Client
1.6 |  | Site set out |  |  |  | Prior to commencement |  | Site inspection |  | Scope document Drawing 796684 |  | Site inspection |  | ITP |  | HP |  | Client/ Fulton Hogan
1.7 |  | Ground breaking |  |  |  | Prior to excavation |  | Works to be reviewed and agreed by Superintendent |  | Hold Point release for Commencement of Works Letter |  | Inspection |  | ITP |  | HP |  | Client
1.8 |  | Landowner Agreement with property owner |  |  |  | Prior to breaking ground |  | Letter to be signed |  | Signed landowner agreement |  | Hold point |  | ITP |  | HP* |  | Fulton Hogan
1.9 |  | Environmental controls |  |  |  | Prior to commencement |  | Environmental controls installed and maintained as per EMP |  | EMP |  | Inspection |  | ITP |  | HP* |  | Fulton Hogan
2. Site Access / Rock Fill / Wingwall Repairs
2.1 |  | Control of water through site |  |  |  | Prior to excavation of toe |  | Dewatering and earth bund to be confirmed on site |  | Environmental Management plan |  | Site inspection |  | ITP |  | IP |  | Client and Fulton Hogan
2.2 |  | Tree removal |  |  |  | Prior to commencement |  | Trees for removal marked out and approved for removal |  | Environmental Management plan DEECA permit |  | Site Inspection Permit |  | ITP Permit |  | HP |  | Client and Fulton Hogan
2.3 |  | Site Benching/ access track |  |  |  | Prior to commencement |  | Adequate benching and site access track constructed |  | Scope document |  | Inspection |  | ITP |  | IP |  | Fulton Hogan
2.4 |  | Fill Material |  |  |  | Prior to placement |  | Suitable Type A Fill material used for placement behind upstream wingwall |  | Scope document Drawing |  | Inspection |  | ITP |  | WP |  | Fulton Hogan/Client
2.5 |  | Geofabric |  |  |  | Prior to wingwall form and rock placement |  | Geotextile layer placed under rock beaching and behind wingwall |  | Drawing |  | Inspection |  | ITP |  | IP |  | Fulton Hogan
2.6 |  | Toe Rock Placement (downstream) |  |  |  | During the placement of the toe rock |  | Solid base, Maximum particle sizes 750-1000mm |  | N/A |  | Inspection |  | ITP |  | IP |  | Client/ Fulton Hogan
2.7 |  | Flowable grout |  |  |  | During construction |  | Flowable grout adequately placed to fill void under downstream wingwall |  | Drawing |  | Inspection |  | ITP |  | HP |  | Client
2.8 |  | Demobilisation |  |  |  | At the completion of works |  | Stockpiles and temporary works are removed. Minor defects are agreed with client |  | NA |  | Inspection |  | ITP |  | HP |  | Client
HP HP* WP AP IP TP SCP |  |  |  |  | HOLD POINT FULTON HOGAN INTERNAL HOLD POINT WITNESS POINT APPROVAL POINT INSPECTION POINT TEST POINT SURVEY CONFORMANCE POINT
FINAL INSPECT ION: |  |  |  | This is to verify that the final inspection has been carried out in accordance with the Fulton Hogan’s Quality Procedures and Project Quality Strategy and the product is hereby certified to conform with the contract specifications: Print Name: Position: Signature: Date: