## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-005 - Rock Beaching/Structures | itp |  |  |  |  | ITP-005 - Rock Beaching/Structures Rev0
section | 1 - Preliminaries and Submissions
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Before commencement of activity
label | ACCEPTANCE CRITERIA: Check correct documentation is being utilized
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Current revision of drawing
label | CONFORMANCE RECORD: Current revision of drawing
label | *HP
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
checkpoint | 1.2 - Ensure Safety, Traffic, Quality & Environmental management measures are in place
label | FREQUENCY: Prior to commencement of activity.
label | ACCEPTANCE CRITERIA: Safety plan, traffic management plan and environmental management plan
label | REFERENCE DOCUMENTS: PSP, TMP, EMP
label | INSPECTION/TEST METHOD: Ensure all measures in place as per plan
label | CONFORMANCE RECORD: Inspection
label | HP
label | RESPONSIBILITY: Fulton Hogan/Client
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Stockpiling
label | FREQUENCY: Prior to removing material
label | ACCEPTANCE CRITERIA: Confirmation of stockpile location approved by superintendent.
label | REFERENCE DOCUMENTS: FH Scope document, EMP
label | INSPECTION/TEST METHOD: Approval
label | CONFORMANCE RECORD: ITP
label | WP
label | RESPONSIBILITY: Client/ Fulton Hogan
date | Date Completed:
checkpoint | 1.4 - Identification of services
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Any existence of underground services to be located and proven
label | REFERENCE DOCUMENTS: BYDA Section 100.8
label | INSPECTION/TEST METHOD: Inspection
label | CONFORMANCE RECORD: ITP
label | HP
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Project management Plan Completed
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: PMP Completed
label | REFERENCE DOCUMENTS: PMP checklist completed
label | INSPECTION/TEST METHOD: Inspection
label | CONFORMANCE RECORD: ITP
label | HP
label | RESPONSIBILITY: Fulton Hogan/Client
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Site set out
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Site inspection
label | REFERENCE DOCUMENTS: Scope document Drawing 796684
label | INSPECTION/TEST METHOD: Site inspection
label | CONFORMANCE RECORD: ITP
label | HP
label | RESPONSIBILITY: Client/ Fulton Hogan
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Ground breaking
label | FREQUENCY: Prior to excavation
label | ACCEPTANCE CRITERIA: Works to be reviewed and agreed by Superintendent
label | REFERENCE DOCUMENTS: Hold Point release for Commencement of Works Letter
label | INSPECTION/TEST METHOD: Inspection
label | CONFORMANCE RECORD: ITP
label | HP
label | RESPONSIBILITY: Client
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.8 - Landowner Agreement with property owner
label | FREQUENCY: Prior to breaking ground
label | ACCEPTANCE CRITERIA: Letter to be signed
label | REFERENCE DOCUMENTS: Signed landowner agreement
label | INSPECTION/TEST METHOD: Hold point
label | CONFORMANCE RECORD: ITP
label | HP*
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
checkpoint | 1.9 - Environmental controls
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Environmental controls installed and maintained as per EMP
label | REFERENCE DOCUMENTS: EMP
label | INSPECTION/TEST METHOD: Inspection
label | CONFORMANCE RECORD: ITP
label | HP*
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
section | 2 - Site Access / Rock Fill / Wingwall Repairs
checkpoint | 2.1 - Control of water through site
label | FREQUENCY: Prior to excavation of toe
label | ACCEPTANCE CRITERIA: Dewatering and earth bund to be confirmed on site
label | REFERENCE DOCUMENTS: Environmental Management plan
label | INSPECTION/TEST METHOD: Site inspection
label | CONFORMANCE RECORD: ITP
label | IP
label | RESPONSIBILITY: Client and Fulton Hogan
date | Date Completed:
checkpoint | 2.2 - Tree removal
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Trees for removal marked out and approved for removal
label | REFERENCE DOCUMENTS: Environmental Management plan, DEECA permit
label | INSPECTION/TEST METHOD: Site Inspection Permit
label | CONFORMANCE RECORD: ITP Permit
label | HP
label | RESPONSIBILITY: Client and Fulton Hogan
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Site Benching/ access track
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Adequate benching and site access track constructed
label | REFERENCE DOCUMENTS: Scope document
label | INSPECTION/TEST METHOD: Inspection
label | CONFORMANCE RECORD: ITP
label | IP
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
checkpoint | 2.4 - Fill Material
label | FREQUENCY: Prior to placement
label | ACCEPTANCE CRITERIA: Suitable Type A Fill material used for placement behind upstream wingwall
label | REFERENCE DOCUMENTS: Scope document Drawing
label | INSPECTION/TEST METHOD: Inspection
label | CONFORMANCE RECORD: ITP
label | WP
label | RESPONSIBILITY: Fulton Hogan/Client
date | Date Completed:
checkpoint | 2.5 - Geofabric
label | FREQUENCY: Prior to wingwall form and rock placement
label | ACCEPTANCE CRITERIA: Geotextile layer placed under rock beaching and behind wingwall
label | REFERENCE DOCUMENTS: Drawing
label | INSPECTION/TEST METHOD: Inspection
label | CONFORMANCE RECORD: ITP
label | IP
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
checkpoint | 2.6 - Toe Rock Placement (downstream)
label | FREQUENCY: During the placement of the toe rock
label | ACCEPTANCE CRITERIA: Solid base, Maximum particle sizes 750-1000mm
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION/TEST METHOD: Inspection
label | CONFORMANCE RECORD: ITP
label | IP
label | RESPONSIBILITY: Client/ Fulton Hogan
date | Date Completed:
checkpoint | 2.7 - Flowable grout
label | FREQUENCY: During construction
label | ACCEPTANCE CRITERIA: Flowable grout adequately placed to fill void under downstream wingwall
label | REFERENCE DOCUMENTS: Drawing
label | INSPECTION/TEST METHOD: Inspection
label | CONFORMANCE RECORD: ITP
label | HP
label | RESPONSIBILITY: Client
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Demobilisation
label | FREQUENCY: At the completion of works
label | ACCEPTANCE CRITERIA: Stockpiles and temporary works are removed.
label | ○ Minor defects are agreed with client
label | REFERENCE DOCUMENTS: NA
label | INSPECTION/TEST METHOD: Inspection
label | CONFORMANCE RECORD: ITP
label | HP
label | RESPONSIBILITY: Client
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | This is to verify that the final inspection has been carried out in accordance with the Fulton Hogan’s Quality Procedures and Project Quality Strategy and the product is hereby certified to conform with the contract specifications:
textbox | Print Name:
textbox | Position:
date | Date: