## Project Structure
QA Folder Structure |  |  |  | Instructions | Checklists
Site QA
Ingrounds
Zone 1
|  |  | Pour 1 |  | Ingrounds (Zone 1)
|  |  | Pour 2 |  | Ingrounds (Zone 1)
|  |  | Pour 3 |  | Ingrounds (Zone 1)
|  |  | Pour 4 |  | Ingrounds (Zone 1)
|  |  | Pour 5 |  | Ingrounds (Zone 1)
|  |  | Pour 6 |  | Ingrounds (Zone 1)
|  |  | Pour 7 |  | Ingrounds (Zone 1)
|  |  | Pour 8 |  | Ingrounds (Zone 1)
|  |  | Pour 9 |  | Ingrounds (Zone 1)
|  |  | Pour 10 |  | Ingrounds (Zone 1)
Zone 2
|  |  | Pour 1 |  | Ingrounds (Zone 2)
|  |  | Pour 2 |  | Ingrounds (Zone 2)
|  |  | Pour 3 |  | Ingrounds (Zone 2)
|  |  | Pour 4 |  | Ingrounds (Zone 2)
|  |  | Pour 5 |  | Ingrounds (Zone 2)
|  |  | Pour 6 |  | Ingrounds (Zone 2)
|  |  | Pour 7 |  | Ingrounds (Zone 2)
|  |  | Pour 8 |  | Ingrounds (Zone 2)
|  |  | Pour 9 |  | Ingrounds (Zone 2)
|  |  | Pour 10 |  | Ingrounds (Zone 2)
Zone 3
|  |  | Pour 1 |  | Ingrounds (Zone 3)
|  |  | Pour 2 |  | Ingrounds (Zone 3)
|  |  | Pour 3 |  | Ingrounds (Zone 3)
|  |  | Pour 4 |  | Ingrounds (Zone 3)
|  |  | Pour 5 |  | Ingrounds (Zone 3)
|  |  | Pour 6 |  | Ingrounds (Zone 3)
|  |  | Pour 7 |  | Ingrounds (Zone 3)
|  |  | Pour 8 |  | Ingrounds (Zone 3)
|  |  | Pour 9 |  | Ingrounds (Zone 3)
|  |  | Pour 10 |  | Ingrounds (Zone 3)
Zone 4
|  |  | Pour 1 |  | Ingrounds (Zone 4)
|  |  | Pour 2 |  | Ingrounds (Zone 4)
|  |  | Pour 3 |  | Ingrounds (Zone 4)
|  |  | Pour 4 |  | Ingrounds (Zone 4)
|  |  | Pour 5 |  | Ingrounds (Zone 4)
|  |  | Pour 6 |  | Ingrounds (Zone 4)
|  |  | Pour 7 |  | Ingrounds (Zone 4)
|  |  | Pour 8 |  | Ingrounds (Zone 4)
|  |  | Pour 9 |  | Ingrounds (Zone 4)
|  |  | Pour 10 |  | Ingrounds (Zone 4)
Zone 5
|  |  | Pour 1 |  | Ingrounds (Zone 5)
|  |  | Pour 2 |  | Ingrounds (Zone 5)
|  |  | Pour 3 |  | Ingrounds (Zone 5)
|  |  | Pour 4 |  | Ingrounds (Zone 5)
|  |  | Pour 5 |  | Ingrounds (Zone 5)
|  |  | Pour 6 |  | Ingrounds (Zone 5)
|  |  | Pour 7 |  | Ingrounds (Zone 5)
|  |  | Pour 8 |  | Ingrounds (Zone 5)
|  |  | Pour 9 |  | Ingrounds (Zone 5)
|  |  | Pour 10 |  | Ingrounds (Zone 5)
Zone 6
|  |  | Pour 1 |  | Ingrounds (Zone 6)
|  |  | Pour 2 |  | Ingrounds (Zone 6)
|  |  | Pour 3 |  | Ingrounds (Zone 6)
|  |  | Pour 4 |  | Ingrounds (Zone 6)
|  |  | Pour 5 |  | Ingrounds (Zone 6)
|  |  | Pour 6 |  | Ingrounds (Zone 6)
|  |  | Pour 7 |  | Ingrounds (Zone 6)
|  |  | Pour 8 |  | Ingrounds (Zone 6)
|  |  | Pour 9 |  | Ingrounds (Zone 6)
|  |  | Pour 10 |  | Ingrounds (Zone 6)

## Checklist
type | name
checklist | Ingrounds (Zone 1)
Heading | Stormwater
Checkpoint | Lay bed base for preparation of pipe
checkpoint | Pipes installed as per plan
checkpoint | Pipes installed to correct levels
checkpoint | Has pipe been tested
checkpoint | Backfill
Heading | Stormwater pit 1
checkpoint | Pit installed as per manufactures instructions
checkpoint | Correct pipe sizes
checkpoint | Inlet sizes and IL's correct
checkpoint | Pump out lines to correct location
checkpoint | Electrical conduits installed
checkpoint | Correct pumpout size
Heading | Stormwater pit 19
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 20
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 21
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 22
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 23
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Sewer
Checkpoint | Lay bed base for preparation of pipe
checkpoint | Pipes installed as per plan
checkpoint | Pipes installed to correct levels
checkpoint | Has pipe been tested
checkpoint | Backfill
checklist | Ingrounds (Zone 2)
Heading | Stormwater
Checkpoint | Lay bed base for preparation of pipe
checkpoint | Pipes installed as per plan
checkpoint | Pipes installed to correct levels
checkpoint | Has pipe been tested
checkpoint | Backfill
Heading | Stormwater pit 24
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 25
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 26
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 27
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 30
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 31
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 32
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Sewer
Checkpoint | Lay bed base for preparation of pipe
checkpoint | Pipes installed as per plan
checkpoint | Pipes installed to correct levels
checkpoint | Has pipe been tested
checkpoint | Backfill
Heading | Tradewaste
Checkpoint | Lay bed base for preparation of pipe
checkpoint | Pipes installed as per plan
checkpoint | Pipes installed to correct levels
checkpoint | Has pipe been tested
checkpoint | Backfill
Heading | GIT
checkpoint | GIT installed as per manufactures instructions
checkpoint | Inlet sizes and IL's correct
checkpoint | Disconnector gully installed
checkpoint | All pipes sealed into GIT
checkpoint | Vents installed
checkpoint | Covers installed to correct level and height
checkpoint | GIT clean and clear of debris
Heading | Rainwater
Checkpoint | Lay bed base for preparation of pipe
checkpoint | Pipes installed as per plan
checkpoint | Pipes installed to correct levels
checkpoint | Has pipe been tested
checkpoint | Backfill
Heading | Rainwater Tank
checkpoint | Rainwater Tank installed as per manufactures instructions
checkpoint | Inlet sizes and IL's correct
checkpoint | All pipes sealed into Rainwater Tank
checkpoint | Pump lines and conduits installed
checkpoint | Covers installed to correct level and height
checkpoint | Rainwater Tank clean and clear of debris
Heading | Jellyfish
checkpoint | Jellyfish Tank installed as per manufactures instructions
checkpoint | Inlet sizes and IL's correct
checkpoint | All pipes sealed into Jellyfish Tank
checkpoint | Covers installed to correct level and height
checkpoint | Jellyfish Tank clean and clear of debris
checkpoint | Jellyfish filter post construction works
Heading | Water
Checkpoint | Lay bed base for preparation of pipe
checkpoint | Pipes installed as per plan
checkpoint | Pipes installed to correct levels
checkpoint | Has pipe been tested
checkpoint | Backfill
checklist | Ingrounds (Zone 3)
Heading | Stormwater
Checkpoint | Lay bed base for preparation of pipe
checkpoint | Pipes installed as per plan
checkpoint | Pipes installed to correct levels
checkpoint | Has pipe been tested
checkpoint | Backfill
Heading | Stormwater pit 3
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 4
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Sewer
Checkpoint | Lay bed base for preparation of pipe
checkpoint | Pipes installed as per plan
checkpoint | Pipes installed to correct levels
checkpoint | Has pipe been tested
checkpoint | Backfill
checklist | Ingrounds (Zone 4)
Heading | Stormwater
Checkpoint | Lay bed base for preparation of pipe
checkpoint | Pipes installed as per plan
checkpoint | Pipes installed to correct levels
checkpoint | Has pipe been tested
checkpoint | Backfill
Heading | Stormwater pit 15
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 16
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 17
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 18
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Sewer
Checkpoint | Lay bed base for preparation of pipe
checkpoint | Pipes installed as per plan
checkpoint | Pipes installed to correct levels
checkpoint | Has pipe been tested
checkpoint | Backfill
Heading | Jellyfish
checkpoint | Jellyfish Tank installed as per manufactures instructions
checkpoint | Inlet sizes and IL's correct
checkpoint | All pipes sealed into Jellyfish Tank
checkpoint | Covers installed to correct level and height
checkpoint | Jellyfish Tank clean and clear of debris
checkpoint | Jellyfish filter post construction works
checklist | Ingrounds (Zone 5)
Heading | Stormwater
Checkpoint | Lay bed base for preparation of pipe
checkpoint | Pipes installed as per plan
checkpoint | Pipes installed to correct levels
checkpoint | Has pipe been tested
checkpoint | Backfill
Heading | Stormwater pit 5
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 6
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 7
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 8
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 9
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 10
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 11
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 12
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 28
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 29
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 34
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 35
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Sewer
Checkpoint | Lay bed base for preparation of pipe
checkpoint | Pipes installed as per plan
checkpoint | Pipes installed to correct levels
checkpoint | Has pipe been tested
checkpoint | Backfill
Heading | Fire
Checkpoint | Lay bed base for preparation of pipe
checkpoint | Pipes installed as per plan
checkpoint | Pipes installed to correct levels
checkpoint | Has pipe been tested (1700kPa)
checkpoint | Backfill
checklist | Ingrounds (Zone 6)
Heading | Stormwater
Checkpoint | Lay bed base for preparation of pipe
checkpoint | Pipes installed as per plan
checkpoint | Pipes installed to correct levels
checkpoint | Has pipe been tested
checkpoint | Backfill
Heading | Stormwater pit 13
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Stormwater pit 14
checkpoint | Pit installed at correct level
checkpoint | Inlet sizes and IL's correct
checkpoint | Pipe work concreted and sealed
checkpoint | Cover setup to correct level and height
checkpoint | Pit clean and clear of debris
checkpoint | Protective mesh installed on grate
Heading | Sewer
Checkpoint | Lay bed base for preparation of pipe
checkpoint | Pipes installed as per plan
checkpoint | Pipes installed to correct levels
checkpoint | Has pipe been tested
checkpoint | Backfill
Heading | Tradewaste
Checkpoint | Lay bed base for preparation of pipe
checkpoint | Pipes installed as per plan
checkpoint | Pipes installed to correct levels
checkpoint | Has pipe been tested
checkpoint | Backfill
Heading | GIT
checkpoint | GIT installed as per manufactures instructions
checkpoint | Inlet sizes and IL's correct
checkpoint | Disconnector gully installed
checkpoint | All pipes sealed into GIT
checkpoint | Vents installed
checkpoint | Covers installed to correct level and height
checkpoint | GIT clean and clear of debris
Heading | Rainwater
Checkpoint | Lay bed base for preparation of pipe
checkpoint | Pipes installed as per plan
checkpoint | Pipes installed to correct levels
checkpoint | Has pipe been tested
checkpoint | Backfill
Heading | Rainwater Tank
checkpoint | Rainwater Tank installed as per manufactures instructions
checkpoint | Inlet sizes and IL's correct
checkpoint | All pipes sealed into Rainwater Tank
checkpoint | Pump lines and conduits installed
checkpoint | Covers installed to correct level and height
checkpoint | Rainwater Tank clean and clear of debris
Heading | Fire
Checkpoint | Lay bed base for preparation of pipe
checkpoint | Pipes installed as per plan
checkpoint | Pipes installed to correct levels
checkpoint | Has pipe been tested (1700kPa)
checkpoint | Backfill