## Project Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Name of ITP/Checklist Template Required
Site QA
boliers 1 & 2
|  | office |  |  | jacobsen vinyl installation
|  | document storage |  |  | jacobsen vinyl installation
|  | permits |  |  | jacobsen vinyl installation
|  | acc toilet |  |  | jacobsen vinyl installation
|  | wc |  |  | jacobsen vinyl installation
|  | store |  |  | jacobsen vinyl installation
|  | meeting room |  |  | jacobsen vinyl installation
|  | lab |  |  | jacobsen vinyl installation
control
boilers 4,5 & 6
|  | RM1 |  |  | jacobsen vinyl installation
|  | RM2 |  |  | jacobsen vinyl installation
|  | RM3 |  |  | jacobsen vinyl installation
|  | RM4 |  |  | jacobsen vinyl installation
|  | RM5 |  |  | jacobsen vinyl installation
|  | RM6 |  |  | jacobsen vinyl installation
|  | RM7 |  |  | jacobsen vinyl installation

## HCF Templates
Type | Name | Values
checklist | Carpet Tile Installation (Basic)
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required
checkpoint | Measure area
section | Installation
checkpoint | Confirm carpet tile pattern direction/layout
checkpoint | Glue out floors
checkpoint | Install carpet tiles
checkpoint | Install trims as applicable
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Vinyl Installation (Basic)
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor for U3 (3mm variance over 3m)
checkpoint | Check wall for smoothness where coving
checkpoint | Measure area
checkpoint | Acclimatise vinyl
section | Installation
checkpoint | Confirm vinyl layout direction
checkpoint | Confirm coving location/type
checkpoint | Glue out floors
checkpoint | Install vinyl
checkpoint | Install coving & capping/sealant as applicable
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Carpet Tile Installation
section | Details
checkpoint | 1. PRE-INSTALLATION CHECKLIST
button | CLIENT Handover of Area | YES, NO, N/A
button | Confirm materials delivered | YES, NO, N/A
button | Gather Materials and Tools | YES, NO, N/A
checkpoint | 2. SURFACE PREPARATION
button | Check Area clear of all other trades and their materials | YES, NO, N/A
button | Surface is clean, dry, and free from dust and debris. | YES, NO, N/A
button | Confirm no cracks, moisture issues, or irregularities | YES, NO, N/A
button | Clause 3.10 Humidity <75% | PASS, FAIL, N/A
button | Ambient Temperature 15.5 - 29.5 degrees | PASS, FAIL, N/A
button | Confirm 3mm tolerance in 3m or 0mm in 20cm in subfloor | PASS, FAIL, N/A
button | Assess, Discuss, Price, Confirm required works | PROCEED, NOT PROCEED, N/A
signoff | Hold works to confirm preparation required
checkpoint | 3. PREPARE CARPET TILE FOR INSTALLATION
button | Check and measure area | YES, NO, N/A
button | Acclimate the Carpet Tiles | YES, NO, N/A
checkpoint | 4. CARPET TILE INSTALLATION
button | Confirm Carpet tile layout | YES, NO, N/A
button | Set out carpet tiles | YES, NO, N/A
button | Applied Adhesive | YES, NO, N/A
button | Allow Glue to Tac-off | YES, NO, N/A
button | Install carpet tiles | YES, NO, N/A
button | Install transition strips, baseboards, or other finishing elements as needed. | YES, NO, N/A
button | Site clean up | YES, NO, N/A
checkpoint | 5. FINAL INSPECTION
button | Confirm no visible defects or issues. | PASS, FAIL, N/A
checkpoint | 6. SUBCONTRACTOR VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Subcontractor representative (Full name)
checkpoint | 7. CLIENT VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Verified by CLIENT representative (Full name)
checklist | Entry Mat Installation
section | Details
checkpoint | 1. PRE-INSTALLATION CHECKLIST
button | CLIENT Handover of Area | YES, NO, N/A
button | Confirm materials delivered | YES, NO, N/A
button | Gather Materials and Tools | YES, NO, N/A
checkpoint | 2. SURFACE PREPARATION
button | Check Area clear of all other trades and their materials | YES, NO, N/A
button | Surface is clean, dry, and free from dust and debris. | YES, NO, N/A
button | Check Recess Level meets requirements | YES, NO, N/A
button | Assess, Discuss, Price, Confirm required works | PROCEED, NOT PROCEED, N/A
signoff | Hold works to confirm preparation required
checkpoint | 3. PREPARE ENTRY MAT FOR INSTALLATION
button | Install Matwell frame | YES, NO, N/A
button | Level Floor to suit Thickness | YES, NO, N/A
button | Dimention measured on site | YES, NO, N/A
checkpoint | 4. ENTRY MAT INSTALLATION
button | Drop Entry Mat in to matwell | YES, NO, N/A
checkpoint | 5. FINAL INSPECTION
button | Confirm no visible defects or issues. | PASS, FAIL, N/A
checkpoint | 6. SUBCONTRACTOR VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Subcontractor representative (Full name)
checkpoint | 7. CLIENT VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Verified by CLIENT representative (Full name)
checklist | Jacobsens Vinyl Installation
section | Details
checkpoint | 1. PRE-INSTALLATION CHECKLIST
button | CLIENT Handover of Area | YES, NO, N/A
button | Confirm materials delivered | YES, NO, N/A
button | Gather Materials and Tools | YES, NO, N/A
checkpoint | 2. SURFACE PREPARATION
button | Check Ambient Temperature 18 – 27 degrees using Wolff V1-D4 Moisture Meter | PASS, FAIL, N/A
button | Check Area clear of all other trades and their materials | YES, NO, N/A
button | Surface is clean, dry, and free from dust and debris. | YES, NO, N/A
button | Check slab for contaminants (paint, plaster etc) as per NZS-AS 1884:2013 2.1.1 B | YES, NO, N/A
button | Confirm 3mm tolerance in 3m or 0mm in 20cm in subfloor as per NZS-AS 1884:2013 | PASS, FAIL, N/A
button | Hold works to confirm preparation required | YES, NO, N/A
button | After Grinding Check slab for Cracks as per NZS-AS 1884:2013 | YES, NO, N/A
button | If cracks are present, do they require remediation as per NZS-AS 1884:2013 Section E2.2 | YES, NO, N/A
button | Assess, Discuss, Price, Confirm required works | PROCEED, NOT PROCEED, N/A
signoff | SIGNOFF
checkpoint | 3. PREPARE VINYL FOR INSTALLATION
button | Store rolls upright in aclimatised area 24 hours prior to Use | YES, NO, N/A
button | Check and Confirm vinyl type, colour,coving height and grain direction | YES, NO, N/A
button | Check and measure area | YES, NO, N/A
button | Follow direction on approved HCF vinyl cut plans | YES, NO, N/A
button | Check Ambient Temperature 18 – 27 degrees | PASS, FAIL, N/A
button | Ensure the cuts are precise to fit the room dimensions | YES, NO, N/A
button | Wet areas: ensure joins avoid shower floor area and minimise cross joins where possible as per NZS-AS 1884:2013 5.2.1.3 which is the governing standard for NZ | YES, NO, N/A
checkpoint | 4. VINYL INSTALLATION
button | copper strip required for anti static vinyl | yes/no/na
button | capping strip. (State colour) | aluminium or PVC
button | cove fillet required (state raduis used) | YES, NO, N/A
button | Applied Adhesive in line with Green Star Requirements | YES, NO, N/A
button | Placed the vinyl onto the adhesive as per NZS-AS 1884:2013 | YES, NO, N/A
button | 68kg roller at 15min intervals as per NZS-AS 1884:2013 | YES, NO, N/A
button | Perform butterfly method to internal and external mitres as per NZS-AS 1884:2013 | YES, NO, N/A
button | Pencil cove flooring to the specified height as per NZS-AS 1884:2013 | YES, NO, N/A
button | Thermoweld all joins and mitres as per NZS-AS 1884:2013 | YES, NO, N/A
button | Install transition strips, baseboards, or other finishing elements as needed. | YES, NO, N/A
button | Allow curing time of 24 hours | YES, NO, N/A
button | Site clean up | YES, NO, N/A
checkpoint | 5. FINAL INSPECTION
button | Confirm no visible defects or issues. | PASS, FAIL, N/A
checkpoint | 6. SUBCONTRACTOR VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Subcontractor representative (Full name)
checkpoint | 7. CLIENT VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Verified by CLIENT representative (Full name)
checklist | Mapei Bulk Fill and Waterproof Membrane
section | Details
checkpoint | 1. PRE-INSTALLATION CHECKLIST
button | CLIENT Handover of Area | YES, NO, N/A
button | Confirm materials delivered | YES, NO, N/A
button | Gather Materials and Tools | YES, NO, N/A
checkpoint | 2. Substrate Moisture
button | Check Ambient Temperature 18 – 27 degrees using Wolff V1-D4 Moisture Meter | PASS, FAIL. N/A
button | Moisture test In slab method (1 test per 100m2) Clause 3.10 Humidity <75% as per Appendix A in NZS-AS 1884:2013 using Wolff V1-D4 Moisture Meter | PASS, FAIL. N/A
button | If moisture test fail add in 1K Turbo moisture barrier step after Bulk Fill/falls completed | PASS, FAIL. N/A
button | Should reading over 95% be taken, stop work to discuss options | HOLD WORKS, N/A
checkpoint | 3. Bulk Fill/Falls
button | Planicrete Slurry applied to slab Mix Ratio: 1 part Planicrete to 2 parts Mapeicem (by weight) | YES, NO, N/A
button | Install Mapeicem/Pap7 mix Fresh on slurry | YES, NO, N/A
button | Calculate required quantity for area | YES, NO, N/A
button | Measure and mix Mapeicem and Pap 7 (Gravel 0-8) Mix ratio: 350-450kg Mapeicem to 1m3 Pap 7 | YES, NO, N/A
button | Mix for max 3-4 min | YES, NO, N/A
button | Application completed within 30mins | YES, NO, N/A
button | Leave to dry 24 hours | YES, NO, N/A
checkpoint | 4. Moisture Barrier 1K turbo
button | Apply Mapei 1K Turbo 1 part polyurethane membrane neat to total bulk fill/falls areas | YES, NO, N/A
button | Apply second coat between 40min and 2 hour max. | YES, NO, N/A
button | blind kiln dry quartz 0.5mm sand to second (final) coat | YES, NO, N/A
button | Allow minimum 2 hours for drying | YES, NO, N/A
checkpoint | 5. Waterproof membrane (Aquadefence)
button | Apply first coat (approx. 0.4mm) using long haired roller, brush or trowel. | YES, NO, N/A
button | Apply Mapeband bonded in place using aquadefence to wall/floor junction and all joins in wall substrate | YES, NO, N/A
button | Allow first coat to dry making sure product becomes darker with Matt finish (approx. 1 hour at 23° C) | YES, NO, N/A
button | Apply second coat (approx.0.4mm) Diagonally to the first coat | YES, NO, N/A
button | Allow 12 hours to dry before next step | YES, NO, N/A
button | CLIENT to Book for council inspection before continuing with Polyflor Total system | YES, NO, N/A
checkpoint | 6. Primer
button | Apply Kiesel Okatmos UG30 neat | YES, NO, N/A
button | Allow to dry | YES, NO, N/A
checkpoint | 7. 3mm topping / feather
button | Mix Servo fine F333 (approx 1.3 - 1.5L/4.75kg powder) with electric mixer (approx.600RPM)till smooth | YES, NO, N/A
button | Apply 3mm to floors where Aquadefence applied to smoothe for vinyl installation | YES, NO, N/A
button | Apply 3mm to floors where Aquadefence applied to smoothe for vinyl installation | YES, NO, N/A
button | (N.B this does not level or get subfloor to a U3 finish, only smooths surface for installation) | YES, NO, N/A
checkpoint | 8. FINAL INSPECTION
button | Confirm no visible defects or issues. | PASS, FAIL. N/A
checkpoint | 9. SUBCONTRACTOR VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Subcontractor representative (Full name)
checkpoint | 10. CLIENT VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Verified by CLIENT representative (Full name)
checklist | Polyflor Vinyl Installation
section | Details
checkpoint | 1. PRE-INSTALLATION CHECKLIST
button | CLIENT Handover of Area | YES, NO, N/A
button | Confirm materials delivered | YES, NO, N/A
button | Gather Materials and Tools | YES, NO, N/A
checkpoint | 2. SURFACE PREPARATION
button | Check Ambient Temperature 18 – 27 degrees using Wolff V1-D4 Moisture Meter | PASS, FAIL, N/A
button | Check Area clear of all other trades and their materials | YES, NO, N/A
button | Surface is clean, dry, and free from dust and debris. | YES, NO, N/A
button | Confirm no cracks, moisture issues, or irregularities | YES, NO, N/A
button | Moisture test In slab method (1 test per 100m2) Clause 3.10 Humidity <75% as per Appendix A in NZS-AS 1884:2013 using Wolff V1-D4 Moisture Meter | PASS, FAIL, N/A
button | Check slab for contaminants (paint, plaster etc) as per NZS-AS 1884:2013 2.1.1 B | YES, NO, N/A
button | Store rolls upright 24 hours prior to Use | YES, NO, N/A
button | Confirm 3mm tolerance in 3m or 0mm in 20cm in subfloor as per NZS-AS 1884:2013 | PASS, FAIL, N/A
button | Assess, Discuss, Price, Confirm required works | PROCEED, NOT PROCEED, N/A
button | Hold works to confirm preparation required | YES, NO, N/A
button | After Grinding Check slab for Cracks as per NZS-AS 1884:2013 | YES, NO, N/A
button | If cracks are present, do they require remediation as per NZS-AS 1884:2013 Section E2.2 | YES, NO, N/A
button | Assess, Discuss, Price, Confirm required works | PROCEED, NOT PROCEED, N/A
signoff | SIGNOFF
checkpoint | 3. PREPARE VINYL FOR INSTALLATION
button | Store rolls upright in aclimatised area 24 hours prior to Use | YES, NO, N/A
button | Check and Confirm vinyl type, colour and grain direction | YES, NO, N/A
button | Check and measure area | YES, NO, N/A
button | Follow direction on approved HCF vinyl cut plans | YES, NO, N/A
button | Check Ambient Temperature 18 – 27 degrees using Wolff V1-D4 Moisture Meter | PASS, FAIL, N/A
button | Ensure the cuts are precise to fit the room dimensions | YES, NO, N/A
button | Wet areas: ensure joins avoid shower floor area and minimise cross joins where possible as per NZS-AS 1884:2013 5.2.1.3 which is the governing standard for NZ | YES, NO, N/A
checkpoint | 4. VINYL INSTALLATION
button | Applied Adhesive V1 Notch trowel | YES, NO, N/A
button | Placed the vinyl onto the adhesive as per NZS-AS 1884:2013 | YES, NO, N/A
button | 68kg roller to ensure adhesive transfer for floor vinyl as per NZS-AS 1884:2013/Polyflor specification | YES, NO, N/A
button | Handroller using pressure to ensure adhesive transfer for wall vinyl as per NZS-AS 1884:2013/Polyflor specification | YES, NO, N/A
button | Perform butterfly method to internal and external mitres as per NZS-AS 1884:2013/Polyflor specification | YES, NO, N/A
button | Pencil cove flooring to the specified height as per NZS-AS 1884:2013/Polyflor specification | YES, NO, N/A
button | Thermoweld all joins and mitres as per NZS-AS 1884:2013/Polyflor specification | YES, NO, N/A
button | Install transition strips, baseboards, or other finishing elements as needed as per NZS-AS 1884:2013 | YES, NO, N/A
button | Allow curing time of 24 hours | YES, NO, N/A
button | Site clean up | YES, NO, N/A
checkpoint | 5. FINAL INSPECTION
button | Confirm no visible defects or issues. | PASS, FAIL, N/A
checkpoint | 6. SUBCONTRACTOR VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Subcontractor representative (Full name)
checkpoint | 7. CLIENT VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Verified by CLIENT representative (Full name)
checklist | Rubber Tile Installation
section | Details
checkpoint | 1. PRE-INSTALLATION CHECKLIST
button | CLIENT Handover of Area | YES, NO, N/A
button | Confirm materials delivered | YES, NO, N/A
button | Gather Materials and Tools | YES, NO, N/A
checkpoint | 2. SURFACE PREPARATION
button | Check Area clear of all other trades and their materials | YES, NO, N/A
button | Surface is clean, dry, and free from dust and debris. | YES, NO, N/A
button | Moisture test In slab method (1 test per 100m2) Clause 3.10 Humidity <75% as per Appendix A in NZS-AS 1884:2013 using Wolff V1-D4 Moisture Meter | PASS, FAIL, N/A
button | Check slab for contaminants (paint, plaster etc) as per NZS-AS 1884:2013 2.1.1 B | YES, NO, N/A
button | Confirm 3mm tolerance in 3m or 0mm in 20cm in subfloor as per NZS-AS 1884:2013 | PASS, FAIL, N/A
button | Hold works to confirm preparation required | YES, NO, N/A
button | After Grinding Check slab for Cracks as per NZS-AS 1884:2013 | YES, NO, N/A
button | If cracks are present, do they require remediation as per NZS-AS 1884:2013 Section E2.2 | YES, NO, N/A
button | Assess, Discuss, Price, Confirm required works | PROCEED, NOT PROCEED, N/A
signoff | SIGNOFF
checkpoint | 3. PREPARE RUBBER TILE FOR INSTALLATION
button | Aclimatised area 24 hours prior to Use | YES, NO, N/A
button | Check and Confirm rubber type, colour and grain direction | YES, NO, N/A
button | Check and measure area | YES, NO, N/A
button | Follow direction on approved HCF vinyl cut plans | YES, NO, N/A
button | Check Ambient Temperature 18 – 27 degrees using Wolff V1-D4 Moisture Meter | PASS, FAIL, N/A
button | Ensure the cuts are precise to fit the room dimensions | YES, NO, N/A
checkpoint | 4. RUBBER TILE INSTALLATION
button | Applied Adhesive as per NZS-AS 1884:2013 | YES, NO, N/A
button | Placed the Rubber onto the adhesive as per NZS-AS 1884:2013 | YES, NO, N/A
button | Allow Glue to set as per NZS-AS 1884:2013 | YES, NO, N/A
button | Install transition strips, baseboards, or other finishing elements as needed as per NZS-AS 1884:2013 | YES, NO, N/A
button | Allow curing time of 24 hours | YES, NO, N/A
button | Site clean up | YES, NO, N/A
checkpoint | 5. FINAL INSPECTION
button | Confirm no visible defects or issues. | PASS, FAIL, N/A
checkpoint | 6. SUBCONTRACTOR VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Subcontractor representative (Full name)
checkpoint | 7. CLIENT VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Verified by CLIENT representative (Full name)
checklist | resin/epoxy application
section | Details
checkpoint | 1. PRE-INSTALLATION CHECKLIST
button | CLIENT Handover of Area | YES, NO, N/A
button | Confirm materials delivered | YES, NO, N/A
button | date concrete was poured. MPA
button | humidity in room | pass/fail
button | temperature in room | pass/fail
button | Gather Materials and Tools | YES, NO, N/A
checkpoint | 2. SURFACE PREPARATION
button | Check Area clear of all other trades and their materials | YES, NO, N/A
button | subfloor Is free from cracks, rain damage & laitence.
button | Surface is clean, dry, and free from dust and debris. | YES, NO, N/A
signoff | Hold works to confirm preparation required | YES, NO, N/A
checkpoint | 3. PREPARE RESIN/EPOXY APPLICATION
button | diamond grind sub floor to remove surface contaminants/minor undulations 1-2mm | YES, NO, N/A
button | vacuum clean substrate to remove all dust and debris | YES, NO, N/A
button | apply primer to substrate (comment for which product) | YES, NO, N/A
button | clean out saw cuts and apply sealant | YES, NO, N/A
button | apply resin/epoxy to nominal thickness. (state which product) | roll coat, 2mm,3mm,4,mm,5mm,6mm other
button | prepare coves if product has to be coved. Hight of coving | YES, NO, N/A
button | Fibre glass required (to coves or cracks) | YES, NO, N/A
button | level of aggrigate to be used/nonslip. (comment) | YES, NO, N/A
checkpoint | 5. FINAL INSPECTION
button | sealant complete (which product) | YES, NO, N/A
button | Confirm no visible defects or issues. | PASS, FAIL, N/A
checkpoint | 6. SUBCONTRACTOR VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Subcontractor representative (Full name)
checkpoint | 7. CLIENT VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Verified by CLIENT representative (Full name)
checklist | Lot Verification
section | LOT details & items
checkpoint | Details complete
dropdown | Work description | Carpet Tile Installation, Vinyl Installation
textbox | LOT number:
textbox | LOT description
checkpoint | ITP QA checksheets
textbox | Number of records required:
textbox | LOT subfolder number:
textbox | Remarks:
checkpoint | Incoming material checklist
textbox | Number of records required:
textbox | LOT subfolder number:
textbox | Remarks:
checkpoint | Photos
textbox | Number of records required:
textbox | LOT subfolder number:
textbox | Remarks:
checkpoint | Survey results
textbox | Number of records required:
textbox | LOT subfolder number:
textbox | Remarks:
checkpoint | Council reports (test results)
textbox | Number of records required:
textbox | LOT subfolder number:
textbox | Remarks:
section | Sign Offs
checkpoint | Conformance of Work Statement
signoff | SEND TO FOREMAN/SUPERVISOR FOR SIGNOFF
checkpoint | Conformance/verification of Construction LOT Statement
signoff | SEND TO PROJECT ENGINEER/SENIOR PROJECT ENGINEER FOR SIGNOFF
checkpoint | Quality Review
signoff | SEND TO QUALITY MANAGER/REP FOR SIGNOFF
checklist | Preliminary Inspection
checkpoint | ROM & Consent Approval
checkpoint | Define LOT area

## Project Structure Guide
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Name of ITP/Checklist Template Required
Site QA
Ground Floor
Unit 001
|  |  | Carpet Tile Installation |  | Carpet Tile Installation
|  |  | Vinyl Installation |  | Vinyl Installation
Unit 002
|  |  | Carpet Tile Installation |  | Carpet Tile Installation
|  |  | Vinyl Installation |  | Vinyl Installation
Level 1
Unit 101
|  |  | Carpet Tile Installation |  | Carpet Tile Installation
|  |  | Vinyl Installation |  | Vinyl Installation
Unit 102
|  |  | Carpet Tile Installation |  | Carpet Tile Installation
|  |  | Vinyl Installation |  | Vinyl Installation
Level 2
Unit 202
|  |  | Carpet Tile Installation |  | Carpet Tile Installation
|  |  | Vinyl Installation |  | Vinyl Installation
Unit 203
|  |  | Carpet Tile Installation |  | Carpet Tile Installation
|  |  | Vinyl Installation |  | Vinyl Installation
Guide: The above lets our team know that you'd like to break your project down to three areas, and have an carpet and vinyl checklist assigned in each room. Clicking the last tier laber (i.e 'Carpet Tile Installation' in Tier 4) will open the assigned checklist/ITP. The checklist contents can be found in the next tab.
NOTE: You are able to modify the structure above to include more tiers, subfolders and checklist/ITPs as required.

## Template Guide
TEMPLATE GUIDE
Type | Name | Values
checklist | Template Guide (This is where you type the name/title of your checklist)
section | Section A - This is a section which helps you split your checklist
checkpoint | This is a checkpoint (all checkpoints have the options to PASS, FAIL, N/A by default)
checkpoint | This is a checkpoint with a dropdown (you can select only one option)
dropdown | Select: | Option 1, Option 2, Option 3
checkpoint | This is a checkpoint with a textbox
textbox | Description:
checkpoint | This is a checkpoint with buttons (you can select only one option)
button | Select: | Option 1, Option 2, Option 3
section | Section B - This is a section which helps you split your checklist
checkpoint | This is a checkpoint with a note
note | This is a note
checkpoint | This is a checkpoint with tickboxes (you can select more than one option)
tickbox | White
tickbox | Grey
tickbox | Black
checkpoint | This is a checkpoint with a signoff (you can send it to anyone within or outside of CONQA)
signoff | SIGN HERE OR REQUEST SIGNOFF
NOTE: You can customise ALL wordings under the 'Name' column and the options in the 'Values' column.
PLEASE SHARE YOUR CURRENT ITP/CHECKLIST PACKS FOR US TO DIGITISE OR CREATE YOUR OWN BELOW.