## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Carpet Tile Installation (Basic)
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required
checkpoint | Measure area
section | Installation
checkpoint | Confirm carpet tile pattern direction/layout
checkpoint | Glue out floors
checkpoint | Install carpet tiles
checkpoint | Install trims as applicable
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Vinyl Installation (Basic)
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor for U3 (3mm variance over 3m)
checkpoint | Check wall for smoothness where coving
checkpoint | Measure area
checkpoint | Acclimatise vinyl
section | Installation
checkpoint | Confirm vinyl layout direction
checkpoint | Confirm coving location/type
checkpoint | Glue out floors
checkpoint | Install vinyl
checkpoint | Install coving & capping/sealant as applicable
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Carpet Tile Installation
section | Details
checkpoint | 1. PRE-INSTALLATION CHECKLIST
button | CLIENT Handover of Area | YES, NO, N/A
button | Confirm materials delivered | YES, NO, N/A
button | Gather Materials and Tools | YES, NO, N/A
checkpoint | 2. SURFACE PREPARATION
button | Check Area clear of all other trades and their materials | YES, NO, N/A
button | Surface is clean, dry, and free from dust and debris. | YES, NO, N/A
button | Confirm no cracks, moisture issues, or irregularities | YES, NO, N/A
button | Clause 3.10 Humidity <75% | PASS, FAIL, N/A
button | Ambient Temperature 15.5 - 29.5 degrees | PASS, FAIL, N/A
button | Confirm 3mm tolerance in 3m or 0mm in 20cm in subfloor | PASS, FAIL, N/A
button | Assess, Discuss, Price, Confirm required works | PROCEED, NOT PROCEED, N/A
signoff | Hold works to confirm preparation required
checkpoint | 3. PREPARE CARPET TILE FOR INSTALLATION
button | Check and measure area | YES, NO, N/A
button | Acclimate the Carpet Tiles | YES, NO, N/A
checkpoint | 4. CARPET TILE INSTALLATION
button | Confirm Carpet tile layout | YES, NO, N/A
button | Set out carpet tiles | YES, NO, N/A
button | Applied Adhesive | YES, NO, N/A
button | Allow Glue to Tac-off | YES, NO, N/A
button | Install carpet tiles | YES, NO, N/A
button | Install transition strips, baseboards, or other finishing elements as needed. | YES, NO, N/A
button | Site clean up | YES, NO, N/A
checkpoint | 5. FINAL INSPECTION
button | Confirm no visible defects or issues. | PASS, FAIL, N/A
checkpoint | 6. SUBCONTRACTOR VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Subcontractor representative (Full name)
checkpoint | 7. CLIENT VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Verified by CLIENT representative (Full name)
checklist | Entry Mat Installation
section | Details
checkpoint | 1. PRE-INSTALLATION CHECKLIST
button | CLIENT Handover of Area | YES, NO, N/A
button | Confirm materials delivered | YES, NO, N/A
button | Gather Materials and Tools | YES, NO, N/A
checkpoint | 2. SURFACE PREPARATION
button | Check Area clear of all other trades and their materials | YES, NO, N/A
button | Surface is clean, dry, and free from dust and debris. | YES, NO, N/A
button | Check Recess Level meets requirements | YES, NO, N/A
button | Assess, Discuss, Price, Confirm required works | PROCEED, NOT PROCEED, N/A
signoff | Hold works to confirm preparation required
checkpoint | 3. PREPARE ENTRY MAT FOR INSTALLATION
button | Install Matwell frame | YES, NO, N/A
button | Level Floor to suit Thickness | YES, NO, N/A
button | Dimention measured on site | YES, NO, N/A
checkpoint | 4. ENTRY MAT INSTALLATION
button | Drop Entry Mat in to matwell | YES, NO, N/A
checkpoint | 5. FINAL INSPECTION
button | Confirm no visible defects or issues. | PASS, FAIL, N/A
checkpoint | 6. SUBCONTRACTOR VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Subcontractor representative (Full name)
checkpoint | 7. CLIENT VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Verified by CLIENT representative (Full name)
checklist | Jacobsens Vinyl Installation
section | Details
checkpoint | 1. PRE-INSTALLATION CHECKLIST
button | CLIENT Handover of Area | YES, NO, N/A
button | Confirm materials delivered | YES, NO, N/A
button | Gather Materials and Tools | YES, NO, N/A
checkpoint | 2. SURFACE PREPARATION
button | Check Ambient Temperature 18 – 27 degrees using Wolff V1-D4 Moisture Meter | PASS, FAIL, N/A
button | Check Area clear of all other trades and their materials | YES, NO, N/A
button | Surface is clean, dry, and free from dust and debris. | YES, NO, N/A
button | Check slab for contaminants (paint, plaster etc) as per NZS-AS 1884:2013 2.1.1 B | YES, NO, N/A
button | Confirm 3mm tolerance in 3m or 0mm in 20cm in subfloor as per NZS-AS 1884:2013 | PASS, FAIL, N/A
button | Hold works to confirm preparation required | YES, NO, N/A
button | After Grinding Check slab for Cracks as per NZS-AS 1884:2013 | YES, NO, N/A
button | If cracks are present, do they require remediation as per NZS-AS 1884:2013 Section E2.2 | YES, NO, N/A
button | Assess, Discuss, Price, Confirm required works | PROCEED, NOT PROCEED, N/A
signoff | SIGNOFF
checkpoint | 3. PREPARE VINYL FOR INSTALLATION
button | Store rolls upright in aclimatised area 24 hours prior to Use | YES, NO, N/A
button | Check and Confirm vinyl type, colour,coving height and grain direction | YES, NO, N/A
button | Check and measure area | YES, NO, N/A
button | Follow direction on approved HCF vinyl cut plans | YES, NO, N/A
button | Check Ambient Temperature 18 – 27 degrees | PASS, FAIL, N/A
button | Ensure the cuts are precise to fit the room dimensions | YES, NO, N/A
button | Wet areas: ensure joins avoid shower floor area and minimise cross joins where possible as per NZS-AS 1884:2013 5.2.1.3 which is the governing standard for NZ | YES, NO, N/A
checkpoint | 4. VINYL INSTALLATION
button | copper strip required for anti static vinyl | yes/no/na
button | capping strip. (State colour) | aluminium or PVC
button | cove fillet required (state raduis used) | YES, NO, N/A
button | Applied Adhesive in line with Green Star Requirements | YES, NO, N/A
button | Placed the vinyl onto the adhesive as per NZS-AS 1884:2013 | YES, NO, N/A
button | 68kg roller at 15min intervals as per NZS-AS 1884:2013 | YES, NO, N/A
button | Perform butterfly method to internal and external mitres as per NZS-AS 1884:2013 | YES, NO, N/A
button | Pencil cove flooring to the specified height as per NZS-AS 1884:2013 | YES, NO, N/A
button | Thermoweld all joins and mitres as per NZS-AS 1884:2013 | YES, NO, N/A
button | Install transition strips, baseboards, or other finishing elements as needed. | YES, NO, N/A
button | Allow curing time of 24 hours | YES, NO, N/A
button | Site clean up | YES, NO, N/A
checkpoint | 5. FINAL INSPECTION
button | Confirm no visible defects or issues. | PASS, FAIL, N/A
checkpoint | 6. SUBCONTRACTOR VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Subcontractor representative (Full name)
checkpoint | 7. CLIENT VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Verified by CLIENT representative (Full name)
checklist | Mapei Bulk Fill and Waterproof Membrane
section | Details
checkpoint | 1. PRE-INSTALLATION CHECKLIST
button | CLIENT Handover of Area | YES, NO, N/A
button | Confirm materials delivered | YES, NO, N/A
button | Gather Materials and Tools | YES, NO, N/A
checkpoint | 2. Substrate Moisture
button | Check Ambient Temperature 18 – 27 degrees using Wolff V1-D4 Moisture Meter | PASS, FAIL. N/A
button | Moisture test In slab method (1 test per 100m2) Clause 3.10 Humidity <75% as per Appendix A in NZS-AS 1884:2013 using Wolff V1-D4 Moisture Meter | PASS, FAIL. N/A
button | If moisture test fail add in 1K Turbo moisture barrier step after Bulk Fill/falls completed | PASS, FAIL. N/A
button | Should reading over 95% be taken, stop work to discuss options | HOLD WORKS, N/A
checkpoint | 3. Bulk Fill/Falls
button | Planicrete Slurry applied to slab Mix Ratio: 1 part Planicrete to 2 parts Mapeicem (by weight) | YES, NO, N/A
button | Install Mapeicem/Pap7 mix Fresh on slurry | YES, NO, N/A
button | Calculate required quantity for area | YES, NO, N/A
button | Measure and mix Mapeicem and Pap 7 (Gravel 0-8) Mix ratio: 350-450kg Mapeicem to 1m3 Pap 7 | YES, NO, N/A
button | Mix for max 3-4 min | YES, NO, N/A
button | Application completed within 30mins | YES, NO, N/A
button | Leave to dry 24 hours | YES, NO, N/A
checkpoint | 4. Moisture Barrier 1K turbo
button | Apply Mapei 1K Turbo 1 part polyurethane membrane neat to total bulk fill/falls areas | YES, NO, N/A
button | Apply second coat between 40min and 2 hour max. | YES, NO, N/A
button | blind kiln dry quartz 0.5mm sand to second (final) coat | YES, NO, N/A
button | Allow minimum 2 hours for drying | YES, NO, N/A
checkpoint | 5. Waterproof membrane (Aquadefence)
button | Apply first coat (approx. 0.4mm) using long haired roller, brush or trowel. | YES, NO, N/A
button | Apply Mapeband bonded in place using aquadefence to wall/floor junction and all joins in wall substrate | YES, NO, N/A
button | Allow first coat to dry making sure product becomes darker with Matt finish (approx. 1 hour at 23° C) | YES, NO, N/A
button | Apply second coat (approx.0.4mm) Diagonally to the first coat | YES, NO, N/A
button | Allow 12 hours to dry before next step | YES, NO, N/A
button | CLIENT to Book for council inspection before continuing with Polyflor Total system | YES, NO, N/A
checkpoint | 6. Primer
button | Apply Kiesel Okatmos UG30 neat | YES, NO, N/A
button | Allow to dry | YES, NO, N/A
checkpoint | 7. 3mm topping / feather
button | Mix Servo fine F333 (approx 1.3 - 1.5L/4.75kg powder) with electric mixer (approx.600RPM)till smooth | YES, NO, N/A
button | Apply 3mm to floors where Aquadefence applied to smoothe for vinyl installation | YES, NO, N/A
button | Apply 3mm to floors where Aquadefence applied to smoothe for vinyl installation | YES, NO, N/A
button | (N.B this does not level or get subfloor to a U3 finish, only smooths surface for installation) | YES, NO, N/A
checkpoint | 8. FINAL INSPECTION
button | Confirm no visible defects or issues. | PASS, FAIL. N/A
checkpoint | 9. SUBCONTRACTOR VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Subcontractor representative (Full name)
checkpoint | 10. CLIENT VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Verified by CLIENT representative (Full name)
checklist | Polyflor Vinyl Installation
section | Details
checkpoint | 1. PRE-INSTALLATION CHECKLIST
button | CLIENT Handover of Area | YES, NO, N/A
button | Confirm materials delivered | YES, NO, N/A
button | Gather Materials and Tools | YES, NO, N/A
checkpoint | 2. SURFACE PREPARATION
button | Check Ambient Temperature 18 – 27 degrees using Wolff V1-D4 Moisture Meter | PASS, FAIL, N/A
button | Check Area clear of all other trades and their materials | YES, NO, N/A
button | Surface is clean, dry, and free from dust and debris. | YES, NO, N/A
button | Confirm no cracks, moisture issues, or irregularities | YES, NO, N/A
button | Moisture test In slab method (1 test per 100m2) Clause 3.10 Humidity <75% as per Appendix A in NZS-AS 1884:2013 using Wolff V1-D4 Moisture Meter | PASS, FAIL, N/A
button | Check slab for contaminants (paint, plaster etc) as per NZS-AS 1884:2013 2.1.1 B | YES, NO, N/A
button | Store rolls upright 24 hours prior to Use | YES, NO, N/A
button | Confirm 3mm tolerance in 3m or 0mm in 20cm in subfloor as per NZS-AS 1884:2013 | PASS, FAIL, N/A
button | Assess, Discuss, Price, Confirm required works | PROCEED, NOT PROCEED, N/A
button | Hold works to confirm preparation required | YES, NO, N/A
button | After Grinding Check slab for Cracks as per NZS-AS 1884:2013 | YES, NO, N/A
button | If cracks are present, do they require remediation as per NZS-AS 1884:2013 Section E2.2 | YES, NO, N/A
button | Assess, Discuss, Price, Confirm required works | PROCEED, NOT PROCEED, N/A
signoff | SIGNOFF
checkpoint | 3. PREPARE VINYL FOR INSTALLATION
button | Store rolls upright in aclimatised area 24 hours prior to Use | YES, NO, N/A
button | Check and Confirm vinyl type, colour and grain direction | YES, NO, N/A
button | Check and measure area | YES, NO, N/A
button | Follow direction on approved HCF vinyl cut plans | YES, NO, N/A
button | Check Ambient Temperature 18 – 27 degrees using Wolff V1-D4 Moisture Meter | PASS, FAIL, N/A
button | Ensure the cuts are precise to fit the room dimensions | YES, NO, N/A
button | Wet areas: ensure joins avoid shower floor area and minimise cross joins where possible as per NZS-AS 1884:2013 5.2.1.3 which is the governing standard for NZ | YES, NO, N/A
checkpoint | 4. VINYL INSTALLATION
button | Applied Adhesive V1 Notch trowel | YES, NO, N/A
button | Placed the vinyl onto the adhesive as per NZS-AS 1884:2013 | YES, NO, N/A
button | 68kg roller to ensure adhesive transfer for floor vinyl as per NZS-AS 1884:2013/Polyflor specification | YES, NO, N/A
button | Handroller using pressure to ensure adhesive transfer for wall vinyl as per NZS-AS 1884:2013/Polyflor specification | YES, NO, N/A
button | Perform butterfly method to internal and external mitres as per NZS-AS 1884:2013/Polyflor specification | YES, NO, N/A
button | Pencil cove flooring to the specified height as per NZS-AS 1884:2013/Polyflor specification | YES, NO, N/A
button | Thermoweld all joins and mitres as per NZS-AS 1884:2013/Polyflor specification | YES, NO, N/A
button | Install transition strips, baseboards, or other finishing elements as needed as per NZS-AS 1884:2013 | YES, NO, N/A
button | Allow curing time of 24 hours | YES, NO, N/A
button | Site clean up | YES, NO, N/A
checkpoint | 5. FINAL INSPECTION
button | Confirm no visible defects or issues. | PASS, FAIL, N/A
checkpoint | 6. SUBCONTRACTOR VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Subcontractor representative (Full name)
checkpoint | 7. CLIENT VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Verified by CLIENT representative (Full name)
checklist | Rubber Tile Installation
section | Details
checkpoint | 1. PRE-INSTALLATION CHECKLIST
button | CLIENT Handover of Area | YES, NO, N/A
button | Confirm materials delivered | YES, NO, N/A
button | Gather Materials and Tools | YES, NO, N/A
checkpoint | 2. SURFACE PREPARATION
button | Check Area clear of all other trades and their materials | YES, NO, N/A
button | Surface is clean, dry, and free from dust and debris. | YES, NO, N/A
button | Moisture test In slab method (1 test per 100m2) Clause 3.10 Humidity <75% as per Appendix A in NZS-AS 1884:2013 using Wolff V1-D4 Moisture Meter | PASS, FAIL, N/A
button | Check slab for contaminants (paint, plaster etc) as per NZS-AS 1884:2013 2.1.1 B | YES, NO, N/A
button | Confirm 3mm tolerance in 3m or 0mm in 20cm in subfloor as per NZS-AS 1884:2013 | PASS, FAIL, N/A
button | Hold works to confirm preparation required | YES, NO, N/A
button | After Grinding Check slab for Cracks as per NZS-AS 1884:2013 | YES, NO, N/A
button | If cracks are present, do they require remediation as per NZS-AS 1884:2013 Section E2.2 | YES, NO, N/A
button | Assess, Discuss, Price, Confirm required works | PROCEED, NOT PROCEED, N/A
signoff | SIGNOFF
checkpoint | 3. PREPARE RUBBER TILE FOR INSTALLATION
button | Aclimatised area 24 hours prior to Use | YES, NO, N/A
button | Check and Confirm rubber type, colour and grain direction | YES, NO, N/A
button | Check and measure area | YES, NO, N/A
button | Follow direction on approved HCF vinyl cut plans | YES, NO, N/A
button | Check Ambient Temperature 18 – 27 degrees using Wolff V1-D4 Moisture Meter | PASS, FAIL, N/A
button | Ensure the cuts are precise to fit the room dimensions | YES, NO, N/A
checkpoint | 4. RUBBER TILE INSTALLATION
button | Applied Adhesive as per NZS-AS 1884:2013 | YES, NO, N/A
button | Placed the Rubber onto the adhesive as per NZS-AS 1884:2013 | YES, NO, N/A
button | Allow Glue to set as per NZS-AS 1884:2013 | YES, NO, N/A
button | Install transition strips, baseboards, or other finishing elements as needed as per NZS-AS 1884:2013 | YES, NO, N/A
button | Allow curing time of 24 hours | YES, NO, N/A
button | Site clean up | YES, NO, N/A
checkpoint | 5. FINAL INSPECTION
button | Confirm no visible defects or issues. | PASS, FAIL, N/A
checkpoint | 6. SUBCONTRACTOR VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Subcontractor representative (Full name)
checkpoint | 7. CLIENT VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Verified by CLIENT representative (Full name)
checklist | Resin/Epoxy Application
section | Details
checkpoint | 1. PRE-INSTALLATION CHECKLIST
button | CLIENT Handover of Area | YES, NO, N/A
button | Confirm materials delivered | YES, NO, N/A
date | date concrete was poured. MPA
button | humidity in room | pass/fail
button | temperature in room | pass/fail
button | Gather Materials and Tools | YES, NO, N/A
checkpoint | 2. SURFACE PREPARATION
button | Check Area clear of all other trades and their materials | YES, NO, N/A
button | subfloor Is free from cracks, rain damage & laitence. | YES, NO, N/A
button | Surface is clean, dry, and free from dust and debris. | YES, NO, N/A
signoff | Hold works to confirm preparation required
checkpoint | 3. PREPARE RESIN/EPOXY APPLICATION
button | diamond grind sub floor to remove surface contaminants/minor undulations 1-2mm | YES, NO, N/A
button | vacuum clean substrate to remove all dust and debris | YES, NO, N/A
button | apply primer to substrate (comment for which product) | YES, NO, N/A
button | clean out saw cuts and apply sealant | YES, NO, N/A
button | apply resin/epoxy to nominal thickness. (state which product) | roll coat, 2mm,3mm,4,mm,5mm,6mm other
button | prepare coves if product has to be coved. Hight of coving | YES, NO, N/A
button | Fibre glass required (to coves or cracks) | YES, NO, N/A
button | level of aggrigate to be used/nonslip. (comment) | YES, NO, N/A
checkpoint | 5. FINAL INSPECTION
button | sealant complete (which product) | YES, NO, N/A
button | Confirm no visible defects or issues. | PASS, FAIL, N/A
checkpoint | 6. SUBCONTRACTOR VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Subcontractor representative (Full name)
checkpoint | 7. CLIENT VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Verified by CLIENT representative (Full name)
checklist | Lot Verification
section | LOT details & items
checkpoint | Details complete
dropdown | Work description | Carpet Tile Installation, Vinyl Installation
textbox | LOT number:
textbox | LOT description
checkpoint | ITP QA checksheets
textbox | Number of records required:
textbox | LOT subfolder number:
textbox | Remarks:
checkpoint | Incoming material checklist
textbox | Number of records required:
textbox | LOT subfolder number:
textbox | Remarks:
checkpoint | Photos
textbox | Number of records required:
textbox | LOT subfolder number:
textbox | Remarks:
checkpoint | Survey results
textbox | Number of records required:
textbox | LOT subfolder number:
textbox | Remarks:
checkpoint | Council reports (test results)
textbox | Number of records required:
textbox | LOT subfolder number:
textbox | Remarks:
section | Sign Offs
checkpoint | Conformance of Work Statement
signoff | SEND TO FOREMAN/SUPERVISOR FOR SIGNOFF
checkpoint | Conformance/verification of Construction LOT Statement
signoff | SEND TO PROJECT ENGINEER/SENIOR PROJECT ENGINEER FOR SIGNOFF
checkpoint | Quality Review
signoff | SEND TO QUALITY MANAGER/REP FOR SIGNOFF
checklist | Preliminary Inspection
section | Details
checkpoint | ROM & Consent Approval
checkpoint | Define LOT area