## Project Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Name of ITP/Checklist Template Required
Oaken Residences
Block A
Townhouse 1
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Townhouse 2
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Townhouse 3
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Townhouse 4
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Townhouse 5
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Block B
Townhouse 6
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Townhouse 7
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Townhouse 8
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Townhouse 9
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Townhouse 10
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Townhouse 11
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Block C
Townhouse 12
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Townhouse 13
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Townhouse 14
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Townhouse 15
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Townhouse 16
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Townhouse 17
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Block E
Townhouse 24
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Townhouse 25
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Townhouse 26
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Townhouse 27
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Townhouse 28
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Townhouse 29
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Townhouse 30
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation
Townhouse 31
|  |  | Floor Prep |  | Floor Preparation
|  |  | Vinyl Planks Installation |  | Vinyl Plank Installation
|  |  | Timber Installation |  | Timber Installation
|  |  | Carpet Installation |  | Carpet Installation
|  |  | Stairs |  | Carpet Installation
|  |  | Garage Carpet Installation |  | Garage Carpet Installation

## Checklist Templates
Type | Name | Values
checklist | Floor Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Grind Floor
checkpoint | Are there any cracks that require remediation? | Yes, No
checkpoint | Remediate cracks
checkpoint | Apply feather coat, Sanded, Edges
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Vinyl Planks Installation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required
section | Installation
checkpoint | Check floor for U3 (3mm variance over 3m)
checkpoint | Check direction
checkpoint | Check wall for smoothness where/if coving
checkpoint | Measure area
checkpoint | Acclimatise vinyl plank
checkpoint | Glue out area
checkpoint | Install vinyl plank and apply silicone/sealant if needed
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Timber Installation
checkpoint | Check installation type: floating, glue down
checkpoint | Check subfloor - level, stable and clean
section | Installation
checkpoint | Check floor for U3 (3mm variance over 3m)
checkpoint | Check if underlay or glue is required
checkpoint | Check laying your timber floor: pattern/layout as required
checkpoint | Unpack your planks and mix them up to avoid adjacent identical patterns and colour variations
checkpoint | Check for finishes with skirting boards, finishing profiles and anything else as required
checkpoint | Install Underlay/glue if required
checkpoint | Install Timber
checkpoint | Apply sealant if required
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Carpet Installation
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required
section | Installation
checkpoint | Install carpet including smoothedge and underlay as applicable
checkpoint | Check carpet direction
checkpoint | Install trims as applicable
checkpoint | Smoothedge nails not protruding through carpet
checkpoint | All temporary nails removed
checkpoint | All areas are carpeted: bedrooms, wardrobes, living, stairs, hall and nosings/trims as required
checkpoint | All strands cut off
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Garage Carpet Installation
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required
section | Installation
checkpoint | Prepare the area; sweep & vacuum the garage to start with a clean surface.
checkpoint | Check direction
checkpoint | Check if coving required
checkpoint | Measure the garage floor area, and position the roll/s in place on the floor
checkpoint | Roll up carpet to expose half the floor for gluing
checkpoint | Spread glue evenly
checkpoint | Unroll the carpet back onto the glued area and press the carpet down to the ground.
checkpoint | Trim the carpet down to fit around the outside wall and garage door edges. Check if trims/bars are required.
checkpoint | Repeat steps for the other half of the carpet
checkpoint | Press again if any bubbles or ripples
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL

## Template Guide
TEMPLATE GUIDE
Type | Name | Values
checklist | Template Guide (This is where you type the name/title of your checklist)
section | Section A - This is a section which helps you split your checklist
checkpoint | This is a checkpoint (all checkpoints have the options to PASS, FAIL, N/A by default)
checkpoint | This is a checkpoint with a dropdown (you can select only one option)
dropdown | Select: | Option 1, Option 2, Option 3
checkpoint | This is a checkpoint with a textbox
textbox | Description:
checkpoint | This is a checkpoint with buttons (you can select only one option)
button | Select: | Option 1, Option 2, Option 3
section | Section B - This is a section which helps you split your checklist
checkpoint | This is a checkpoint with a note
note | This is a note
checkpoint | This is a checkpoint with tickboxes (you can select more than one option)
tickbox | White
tickbox | Grey
tickbox | Black
checkpoint | This is a checkpoint with a signoff (you can send it to anyone within or outside of CONQA)
signoff | SIGN HERE OR REQUEST SIGNOFF
NOTE: You can customise ALL wordings under the 'Name' column and the options in the 'Values' column.
PLEASE SHARE YOUR CURRENT ITP/CHECKLIST PACKS FOR US TO DIGITISE OR CREATE YOUR OWN BELOW.