## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Floor Preparation
section | Details
checkpoint | Check area clear of all other trades and their materials
checkpoint | Grind Floor
checkpoint | Are there any cracks that require remediation?
checkpoint | Remediate cracks
checkpoint | Apply feather coat, Sanded, Edges
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Vinyl Planks Installation
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required
section | Installation
checkpoint | Check floor for U3 (3mm variance over 3m)
checkpoint | Check direction
checkpoint | Check wall for smoothness where/if coving
checkpoint | Measure area
checkpoint | Acclimatise vinyl plank
checkpoint | Glue out area
checkpoint | Install vinyl plank and apply silicone/sealant if needed
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Timber Installation
section | Preparation
checkpoint | Check installation type: floating, glue down
checkpoint | Check subfloor - level, stable and clean
section | Installation
checkpoint | Check floor for U3 (3mm variance over 3m)
checkpoint | Check if underlay or glue is required
checkpoint | Check laying your timber floor: pattern/layout as required
checkpoint | Unpack your planks and mix them up to avoid adjacent identical patterns and colour variations
checkpoint | Check for finishes with skirting boards, finishing profiles and anything else as required
checkpoint | Install Underlay/glue if required
checkpoint | Install Timber
checkpoint | Apply sealant if required
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Carpet Installation
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required
section | Installation
checkpoint | Install carpet including smoothedge and underlay as applicable
checkpoint | Check carpet direction
checkpoint | Install trims as applicable
checkpoint | Smoothedge nails not protruding through carpet
checkpoint | All temporary nails removed
checkpoint | All areas are carpeted: bedrooms, wardrobes, living, stairs, hall and nosings/trims as required
checkpoint | All strands cut off
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Garage Carpet Installation
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required
section | Installation
checkpoint | Prepare the area; sweep & vacuum the garage to start with a clean surface.
checkpoint | Check direction
checkpoint | Check if coving required
checkpoint | Measure the garage floor area, and position the roll/s in place on the floor
checkpoint | Roll up carpet to expose half the floor for gluing
checkpoint | Spread glue evenly
checkpoint | Unroll the carpet back onto the glued area and press the carpet down to the ground.
checkpoint | Trim the carpet down to fit around the outside wall and garage door edges. Check if trims/bars are required.
checkpoint | Repeat steps for the other half of the carpet
checkpoint | Press again if any bubbles or ripples
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL