## Project Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Name of ITP/Checklist Template Required
Mitre 10 Albany
Floor Plan
GF-01 Entry Lobby
|  |  | Floor Prep |  | Floor Preparation
|  |  | Waterproofing Membrane |  | Floor Preparation - Waterproofing Membrane
|  |  | Vinyl Plank Installation |  | Vinyl Planks Installation
|  |  | Carpet Tile Installation |  | Carpet Tile Installation
GF-02 Large Meeting
|  |  | Floor Prep |  | Floor Preparation
|  |  | Waterproofing Membrane |  | Floor Preparation - Waterproofing Membrane
|  |  | Vinyl Plank Installation |  | Vinyl Planks Installation
|  |  | Carpet Tile Installation |  | Carpet Tile Installation
GF-03 Open Plan
|  |  | Floor Prep |  | Floor Preparation
|  |  | Waterproofing Membrane |  | Floor Preparation - Waterproofing Membrane
|  |  | Vinyl Plank Installation |  | Vinyl Planks Installation
|  |  | Carpet Tile Installation |  | Carpet Tile Installation
GF-04 Meeting
|  |  | Floor Prep |  | Floor Preparation
|  |  | Waterproofing Membrane |  | Floor Preparation - Waterproofing Membrane
|  |  | Vinyl Plank Installation |  | Vinyl Planks Installation
|  |  | Carpet Tile Installation |  | Carpet Tile Installation
GF-05 Meeting
|  |  | Floor Prep |  | Floor Preparation
|  |  | Waterproofing Membrane |  | Floor Preparation - Waterproofing Membrane
|  |  | Vinyl Plank Installation |  | Vinyl Planks Installation
|  |  | Carpet Tile Installation |  | Carpet Tile Installation
GF-07 Breakout
|  |  | Floor Prep |  | Floor Preparation
|  |  | Waterproofing Membrane |  | Floor Preparation - Waterproofing Membrane
|  |  | Vinyl Plank Installation |  | Vinyl Planks Installation
|  |  | Carpet Tile Installation |  | Carpet Tile Installation
GF-08 Office
|  |  | Floor Prep |  | Floor Preparation
|  |  | Waterproofing Membrane |  | Floor Preparation - Waterproofing Membrane
|  |  | Vinyl Plank Installation |  | Vinyl Planks Installation
|  |  | Carpet Tile Installation |  | Carpet Tile Installation
GF-09 Office
|  |  | Floor Prep |  | Floor Preparation
|  |  | Waterproofing Membrane |  | Floor Preparation - Waterproofing Membrane
|  |  | Vinyl Plank Installation |  | Vinyl Planks Installation
|  |  | Carpet Tile Installation |  | Carpet Tile Installation
GF-10 Store
|  |  | Floor Prep |  | Floor Preparation
|  |  | Waterproofing Membrane |  | Floor Preparation - Waterproofing Membrane
|  |  | Vinyl Plank Installation |  | Vinyl Plank Installation
|  |  | Carpet Tile Installation |  | Carpet Tile Installation
GF-11 Utility
|  |  | Floor Prep |  | Floor Preparation
|  |  | Waterproofing Membrane |  | Floor Preparation - Waterproofing Membrane
|  |  | Vinyl Plank Installation |  | Vinyl Plank Installation
|  |  | Carpet Tile Installation |  | Carpet Tile Installation
GF-12 Quiet
|  |  | Floor Prep |  | Floor Preparation
|  |  | Waterproofing Membrane |  | Floor Preparation - Waterproofing Membrane
|  |  | Vinyl Plank Installation |  | Vinyl Planks Installation
|  |  | Carpet Tile Installation |  | Carpet Tile Installation
GF-13 Quiet
|  |  | Floor Prep |  | Floor Preparation
|  |  | Waterproofing Membrane |  | Floor Preparation - Waterproofing Membrane
|  |  | Vinyl Plank Installation |  | Vinyl Planks Installation
|  |  | Carpet Tile Installation |  | Carpet Tile Installation
GF-14 Service
|  |  | Floor Prep |  | Floor Preparation
|  |  | Waterproofing Membrane |  | Floor Preparation - Waterproofing Membrane
|  |  | Vinyl Plank Installation |  | Vinyl Planks Installation
|  |  | Carpet Tile Installation |  | Carpet Tile Installation

## Checklist Templates
Type | Name | Values
checklist | Floor Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Grind Floor
checkpoint | Are there any cracks that require remediation? | Yes, No
checkpoint | Remediate cracks
checkpoint | Apply feather coat, Sanded, Edges
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Floor Preparation - Waterproof Membrane
checkpoint | Check area clear of all other trades and their materials
checkpoint | Is the pH level acceptable? | Yes, No
checkpoint | Surface is clean, dry, and free from dust, debris or contaminants
checkpoint | Grind Floor
checkpoint | Does floor have U3 finish (3mm variance over 3m) | Yes, No
checkpoint | Are there any cracks that require remediation? | Yes, No
checkpoint | Remediate cracks
checkpoint | Apply Waterproof Membrane
checkpoint | Disc purged material
checkpoint | Apply Floor Levelling Compound
checkpoint | Apply feather coat, Sanded, Edges
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Vinyl Planks Installation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required
section | Installation
checkpoint | Check floor for U3 (3mm variance over 3m)
checkpoint | Check direction
checkpoint | Check wall for smoothness where/if coving
checkpoint | Measure area
checkpoint | Acclimatise vinyl plank
checkpoint | Glue out area
checkpoint | Install vinyl plank and apply silicone/sealant if needed
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Carpet Tile Installation (Basic)
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required
checkpoint | Measure area
section | Installation
checkpoint | Confirm carpet tile pattern direction/layout
checkpoint | Glue out floors
checkpoint | Install carpet tiles - ensure which carpet tile being used
checkpoint | Install trims as applicable
checkpoint | Client supplied existing carpet to patch area as per plan
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL

## Template Guide
TEMPLATE GUIDE
Type | Name | Values
checklist | Template Guide (This is where you type the name/title of your checklist)
section | Section A - This is a section which helps you split your checklist
checkpoint | This is a checkpoint (all checkpoints have the options to PASS, FAIL, N/A by default)
checkpoint | This is a checkpoint with a dropdown (you can select only one option)
dropdown | Select: | Option 1, Option 2, Option 3
checkpoint | This is a checkpoint with a textbox
textbox | Description:
checkpoint | This is a checkpoint with buttons (you can select only one option)
button | Select: | Option 1, Option 2, Option 3
section | Section B - This is a section which helps you split your checklist
checkpoint | This is a checkpoint with a note
note | This is a note
checkpoint | This is a checkpoint with tickboxes (you can select more than one option)
tickbox | White
tickbox | Grey
tickbox | Black
checkpoint | This is a checkpoint with a signoff (you can send it to anyone within or outside of CONQA)
signoff | SIGN HERE OR REQUEST SIGNOFF
NOTE: You can customise ALL wordings under the 'Name' column and the options in the 'Values' column.
PLEASE SHARE YOUR CURRENT ITP/CHECKLIST PACKS FOR US TO DIGITISE OR CREATE YOUR OWN BELOW.