## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Floor Preparation
section | Details
checkpoint | Check area clear of all other trades and their materials
checkpoint | Grind Floor
checkpoint | Are there any cracks that require remediation?
checkpoint | Remediate cracks
checkpoint | Apply feather coat, Sanded, Edges
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Floor Preparation - Waterproof Membrane
section | Details
checkpoint | Check area clear of all other trades and their materials
checkpoint | Is the pH level acceptable?
checkpoint | Surface is clean, dry, and free from dust, debris or contaminants
checkpoint | Grind Floor
checkpoint | Does floor have U3 finish (3mm variance over 3m)
checkpoint | Are there any cracks that require remediation?
checkpoint | Remediate cracks
checkpoint | Apply Waterproof Membrane
checkpoint | Disc purged material
checkpoint | Apply Floor Levelling Compound
checkpoint | Apply feather coat, Sanded, Edges
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Vinyl Planks Installation
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required
section | Installation
checkpoint | Check floor for U3 (3mm variance over 3m)
checkpoint | Check direction
checkpoint | Check wall for smoothness where/if coving
checkpoint | Measure area
checkpoint | Acclimatise vinyl plank
checkpoint | Glue out area
checkpoint | Install vinyl plank and apply silicone/sealant if needed
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Carpet Tile Installation (Basic)
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required
checkpoint | Measure area
section | Installation
checkpoint | Confirm carpet tile pattern direction/layout
checkpoint | Glue out floors
checkpoint | Install carpet tiles - ensure which carpet tile being used
checkpoint | Install trims as applicable
checkpoint | Client supplied existing carpet to patch area as per plan
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL