## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Overall Progress (Core 09)
| Scope |  |  | CORE 09
Rows
|  | CORE 09 | dynamic | CORE 09
Columns
|  | Reo |  | reo
|  | IFC Drawing |  | ifc drawing
|  | Steel Supplier | Steel Supplier | ifc drawing
|  | Other Steel Supplier | Other Steel Supplier | ifc drawing
|  | Reo Manufacture date DD/MM/YY | Reo Manufacture date DD/MM/YY | ifc drawing
|  | Cage dimensions |  | cage dimensions
|  | Fittings marked |  | fittings marked
|  | Formwork |  | formwork
|  | Formwork ready to commence - Take photos |  | formwork ready to commence - take photos
|  | Panel type | Panel type | formwork ready to commence - take photos
|  | Other Panel type | Other Panel type | formwork ready to commence - take photos
|  | Panel difficulty | Panel difficulty | formwork ready to commence - take photos
|  | Other Location | Other Location | formwork ready to commence - take photos
|  | Quantity | Quantity | formwork ready to commence - take photos
|  | Panel Weight (t) | Panel Weight (t) | formwork ready to commence - take photos
|  | Volume (m3) | Volume (m3) | formwork ready to commence - take photos
|  | Manufacture date DD/MM/YY | Manufacture date DD/MM/YY | formwork ready to commence - take photos
|  | Formwork dimensions |  | formwork dimensions
|  | Panel thickness | Panel thickness | formwork dimensions
|  | Thickness projection | Thickness projection | formwork dimensions
|  | Panel width | Panel width | formwork dimensions
|  | Width projection | Width projection | formwork dimensions
|  | Panel height | Panel height | formwork dimensions
|  | Height projection | Height projection | formwork dimensions
|  | Square |  | square
|  | Silicone Bed |  | silicone bed
|  | Edge Form/ Fillets |  | edge form/ fillets
|  | Position of reinforcement |  | position of reinforcement
|  | Fittings locations |  | fittings locations
|  | ID Tag |  | id tag
|  | Lifting devices securely/in place |  | lifting devices securely/in place
|  | Top Lifters type | Top Lifters type | lifting devices securely/in place
|  | Other Top Lifters type | Other Top Lifters type | lifting devices securely/in place
|  | Edge/Face Lifters type | Edge/Face Lifters type | lifting devices securely/in place
|  | Other Edge/Face Lifters type | Other Edge/Face Lifters type | lifting devices securely/in place
|  | Ready to pour- Take photo of QA drawing |  | ready to pour- take photo of qa drawing
|  | Notes/Changes | Notes/Changes | ready to pour- take photo of qa drawing
|  | Drafting - Missing information | Missing information | drafting
|  | Drafting - Inconsistent information | Inconsistent information | drafting
|  | Drafting - Wrong information | Wrong information | drafting
|  | Drafting - Versions | Versions | drafting
|  | Boxing - Squareness | Squareness | boxing
|  | Boxing - dimensions | dimensions | boxing
|  | Boxing - Rebate | Rebate | boxing
|  | Boxing - GT | GT | boxing
|  | Boxing - Panel Orientation | Panel Orientation | boxing
|  | Boxing - Fitments | Fitments | boxing
|  | Boxing - Tag | Tag | boxing
|  | Steel - Cover | Cover | steel
|  | Steel - Missing bars | Missing bars | steel
|  | Steel - Wrong bars | Wrong bars | steel
|  | Steel - Wrong configuration | Wrong configuration | steel
|  | Steel - Orientation | Orientation | steel
|  | Steel - Wrong projection/ embedment | Wrong projection/ embedment | steel
|  | Pre Pouring |  | pre pouring
|  | Take a picture or attach copy of concrete doc |  | take a picture or attach copy of concrete doc
|  | Concrete Supplier | Concrete Supplier | take a picture or attach copy of concrete doc
|  | Other Concrete Supplier | Other Concrete Supplier | take a picture or attach copy of concrete doc
|  | Concrete schedule docket # | Concrete schedule docket # | take a picture or attach copy of concrete doc
|  | Pouring date DD/MM/YY | Pouring date DD/MM/YY | take a picture or attach copy of concrete doc
|  | Concrete Requisition (m3) | Concrete Requisition (m3) | take a picture or attach copy of concrete doc
|  | Correct mix being used |  | correct mix being used
|  | 28 Mpa required | 28 Mpa required | correct mix being used
|  | Other Mpa required | Other Mpa required | correct mix being used
|  | Type of concrete | Type of concrete | correct mix being used
|  | Other Type of concrete | Other Type of concrete | correct mix being used
|  | Concrete strength tested | Concrete strength tested | correct mix being used
|  | Concrete - Poured with lower Mpa | Poured with lower Mpa | concrete
|  | Post Production |  | post production
|  | Post Production ready to commence - Lifting Mpa |  | post production ready to commence - lifting mpa
|  | Date panel stripped | Date panel stripped | post production ready to commence - lifting mpa
|  | Fitments removed (GT Caps, fillets, Ferrule caps) |  | fitments removed (gt caps, fillets, ferrule caps)
|  | Correct dimensions |  | correct dimensions
|  | Bulges, Dents and airholes within tolerances |  | bulges, dents and airholes within tolerances
|  | Cracks within tolerances |  | cracks within tolerances
|  | Marking |  | marking
|  | Panel conform to specifications/ tolerances |  | panel conform to specifications/ tolerances
|  | Patching/fixing required | Patching/fixing required | panel conform to specifications/ tolerances
|  | Concrete Test results |  | concrete test results
|  | Post production - Patching required | Patching required | post production
|  | On site - Squareness | Squareness | on site
|  | On site - Dimensions | Dimensions | on site
|  | On site - Rebate | Rebate | on site
|  | On site - GT | GT | on site
|  | On site - Fitments | Fitments | on site
|  | On site - Tag | Tag | on site
|  | On site - Reo | Reo | on site
|  | Storage |  | storage
|  | Inserts/Rebates removed |  | inserts/rebates removed
|  | Filling points/lifters exposed |  | filling points/lifters exposed
|  | Location (Rack #) | Location (Rack #) | filling points/lifters exposed
|  | Other Location (Rack #) | Other Location (Rack #) | filling points/lifters exposed
|  | Status | Status | filling points/lifters exposed