## Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Checklist Template
Stairs
Gridline EF and E3
Roof Part 5
SP2c/Decarb
Tier 5: VO2 Additional Stair to Bridge - STR 3.6B | VO2 Additional Stair to Bridge - STR 3.6B

## Checklists
Type | Name | Values
checklist | VO2 Additional Stair to Bridge - STR 3.6B
section | Product arrival to site
checkpoint | Check all material is as per BOM and fixings supplied are SS 316
checkpoint | Check setout location is as per drawings
checkpoint | Check fixing/fixing detail connection at the top of stairs
checkpoint | Check fixing/fixing detail connection at the bottom of stairs
checkpoint | Check Stair supports fixing/fixing details at connections
checkpoint | Check correction stanchions type and fixing details for landings
checkpoint | Check correction stanchions type and fixing details for stair flights
checkpoint | Check Top rail fixings/fixing details
checkpoint | Check Mid rail fixings/fixing details
checkpoint | Check kickboard or toe rail fixings/fixing details
checkpoint | Check endcaps on handrails
checkpoint | Final overall check of stair, clean stair and surrounding area