## Master List Templates
Id | Type | Name | Values | Prompting Name
e75fa9ec-9749-4c52-bf48-199f7aeab6c4 | checklist | General Manufacturing Template |  | General Manufacturing Template
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
83bd2d4e-0fe3-439f-86c2-c2768ee445a4 | checkpoint | Item free of defects and damages
5fd22b99-4780-43c6-ad4c-0fb51c1d1379 | checkpoint | Item is clean - No pencil marks / dirt / excessive sealant
022fbb6b-a0b9-4481-9874-92f58e3dab83 | checkpoint | Item is clearly labelled in accordance with fabrication sheets
7a8f9bfe-103e-430b-a0d6-1ab14ae785fc | checkpoint | Item is square - Frame / Sashes / Panels
5ffbc1b4-0ee6-46ed-be65-9bb4c0e10e5b | checkpoint | Sealant is correct colour
21ec308c-fb31-471c-92aa-52f970d6460e | checkpoint | Beads / Thresholds / Infills correct length
5d9c8513-2879-4860-af07-5d9448ce6e25 | checkpoint | Mitres flush
10f0cea4-e5c5-4f61-97e4-4e488cd6ccd1 | checkpoint | Drainage correct as per APL manufacturing pack and aligned
cde361a9-c03b-4620-9275-29b7d1968dac | checkpoint | Liners - TWT Measured / Correct Liner / Staples every 150 - 200mm
33435a04-bba7-4189-a3da-2e190ce103f3 | checkpoint | Rubbers continuous and free of damage - not pinched under glass / foam
bb930635-b662-42a3-8e10-43aee0db603b | checkpoint | Fin Mullions painted
4af25516-ce52-44de-a9e6-a11f4dcff239 | checkpoint | Sealant tidy on frame where sash is present
2f9938bd-984c-4b54-b40e-a20456f87fa4 | checkpoint | Glass inspection done - Clean / Correct type / No defects
ebb169bb-0cec-4538-b417-624da86a3561 | checkpoint | Glazing done correctly - No movement / correct glazing rubber
c08a92da-7e06-41f7-b6da-dee8b20a2f0b | checkpoint | Bungs / Caps fitted
5d151bf8-a07d-45b2-a6d2-eca2d09ceb32 | checkpoint | Support Blocks fitted
bc0b3aa1-cf30-4e61-9556-22604141c473 | checkpoint | Transport Blocks between panel and frame
dc1129a6-90bf-4989-933c-b196d783937e | checkpoint | Protective tape on bottom sill
41776750-e73b-470c-9bdc-9231296698b0 | checkpoint | Overall item dimensions correct
12e7851f-a3b7-40c8-9fa2-2d475a16abfd | checkpoint | Correct Windzone sticker applied
5de09a86-8ad8-4531-b97d-b6013a7edb63 | checkpoint | Item match drawing
0dfa618d-6ae0-4090-b4ec-e3ba60682f92 | checkpoint | Commenst on jobsheets followed
6dd88342-6059-408e-a00c-9c6dae71034a | checkpoint | Machining done as per assembly sheet
e251f8cc-536b-447c-b75b-499bdb6d90f9 | checkpoint | Correct Hardware fitted as per jobsheet
8ea8d0b6-ed98-443a-bf37-cc1da4bc96f6 | checkpoint | Soaker correctly fitted
e3533ec2-989b-4854-897c-cc71ec8b2715 | checkpoint | Sillsafe applied correctly
9bb04d30-a482-4f60-b67a-d8cd7f0bc0c2 | checkpoint | Soaker correctly fitted over sillsafe ends
b6fff5cf-485f-4e6f-8687-8e6e4304b090 | checkpoint | Foam tape fitted to sill fixed leg
5219d8fc-d186-4b0a-a4ac-89e322029edb | checkpoint | Top & Bottom Screws sealed
3b5a076b-c0c1-4226-bfab-d9c5b64aefb5 | checkpoint | Screws fitted to all hardware & components
a863823f-f9bf-4c1d-9177-bb3a38dfaf4b | checkpoint | Glazing Platform fitted (TH Frames)
487e8a8e-8278-43e7-b18f-34939b2203ad | checkpoint | Seal between liners - Correct application
3e60ef50-1a78-4c21-85ca-a6221847c57f | checkpoint | Tracks / Stoppers fitted correctly
7688e894-e64b-4515-a3e2-82b44ba24b50 | checkpoint | Sashes / Panels opening and closing correctly
fa453deb-b971-4e22-b80e-0113342e3c3b | checkpoint | Handles facing the right way and are not lose
263510fb-cf9c-4d6b-83e8-f4871799fba3 | checkpoint | Strikes fitted - Item locks / unlocks freely
034c87a7-8724-4c6d-8bf5-26010efc88a4 | checkpoint | All hardware operational
b2cba76e-bc18-4695-ab3b-13d9997eb5f4 | checkpoint | Protective tape on handle - Key taped to inside of handle

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
2de86dcb-a9f0-437b-b11a-9a5b2bde312e | checklist | Architectural - Install Checklist |  | Architectural - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
d4b1e726-fa24-4f8d-8911-fb4e1276a27b | checkpoint | Has the window/door installation been completed?
1921aaff-7c6e-4bee-b749-6ae313dec31c | checkpoint | Is interior sealants installation neat and continuous.
a3e65133-9247-4b67-a178-e6bc63d8a770 | checkpoint | Is exterior sealants installation neat and continuous.
0a60ed68-429d-4c90-876f-a1355fee9830 | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
235dc488-3f3e-44e5-833f-96fef24909d3 | checkpoint | Is head flashing installed per plans and as detailed in the shop drawings?
b06d9953-2a87-4d83-a329-25d213d94deb | checkpoint | Are all window and doors working?
a6813631-b76f-46ef-9b82-5a40b037c147 | checkpoint | All handles installed correctly?
7b414201-c687-4812-828b-6ea2024b325e | checkpoint | Are all the hardware installed correctly?
283d61ad-a5b2-4ced-8341-67c8d81efd84 | checkpoint | Is the joinery free of scratches?
e8dedb88-b222-46a9-b631-abbb9adeb56f | checkpoint | Is the joinery clean and tidy?
4d90dc42-b5d9-45f5-a773-b9a86b513c3b | checkpoint | Are Restrictor Stays fitted(Fully Fixed off & Silent operation)
bcc87d7e-b955-4652-b5a5-c63c49b33809 | checkpoint | Hinge doors strikes adjusted and locking easily
d220ff1e-8176-46a3-b027-151e846dd81c | checkpoint | Hinge doors 4 or 3 point lock operate easily
d1d6a8d6-2a11-44d7-853d-76d21d68e100 | checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
0801b489-8c8a-4a0d-ae9f-63e48992c98c | checkpoint | Sliding doors - panels are adjusted and locking easily
febcf5d8-eac8-48a0-be96-d86adbeaf2e7 | checkpoint | Sliding doors - Strikes are adjusted
7a441329-6699-4872-a47f-a8cecd53afc1 | checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
ecc3fcdc-05be-4d24-a450-337aa18cb340 | checkpoint | Windows open, close, and lock smoothly without excessive force.
768e00ce-4169-4222-823b-be616504756a | checkpoint | All operable windows have functional hardware (locks, latches, etc.)
107df79d-ff5f-4b52-b130-84816f107f76 | checkpoint | Proper spacing and clearances are maintained around the window units.
41a5d581-9713-4062-bf4f-4c8b2e2928b1 | checkpoint | Fasteners used are correct in type, size, and spacing
72bbf98c-8119-4937-8fae-3dda9224ba9d | checkpoint | End Caps Installed
a1c8f601-d9d1-4be0-ae18-7d7de9e733b4 | checkpoint | Frames installed correctly?
f2496434-795c-4a68-bc89-0bcc8d3fe8a4 | checkpoint | Modules installed correctly?
dcd63bba-604b-4109-8b2a-a5117b1a4713 | checkpoint | Drains are not blocked
06760dde-dd88-4109-8911-5585917a04d6 | checklist | Box Fins - Install Checklist |  | Box Fins - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
eebd0df5-3070-476e-a3c6-369f9937900c | checkpoint | Has the window/door installation been completed?
416c568a-f25f-4c89-8643-0b0e92e4f8b2 | checkpoint | Is interior sealants installation neat and continuous.
08b6dd4e-c20f-4323-b48f-aacb26075672 | checkpoint | Is exterior sealants installation neat and continuous.
5515fa8f-b943-46e5-9be5-a2b6176d3f1d | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
ecc4d773-b30f-4b53-85f4-164527c6fa40 | checkpoint | Are all window and doors working?
41295d34-9098-44d1-90ca-ecc0a32e6377 | checkpoint | Is the joinery free of scratches?
2d1e5740-a02f-4e1b-8d1d-ddfbeb97566e | checkpoint | Is the joinery clean and tidy?
a5b6b7d3-b4b1-40d9-880c-f822d13693d8 | checkpoint | Proper spacing and clearances are maintained around the window units.
ce5efa81-9f1e-4179-89ed-556a3e3e9291 | checkpoint | Fasteners used are correct in type, size, and spacing
2e5bc481-3f31-4491-a593-0de537d720df | checkpoint | End Caps Installed
ab4acc85-6b85-4f0d-bd6f-c64e93c28a2b | checkpoint | Brackets installed to modules as per Shop Drawings
d1687de7-25b8-442d-a2ae-c4a141d6efd2 | checkpoint | Brackets installed to Box fins as per Shop Drawings
27dee2a7-8ea5-4030-9afe-d693cb485e07 | checkpoint | Box Fin Spacing as per Shop Drawings
b4f74571-4cf4-4a90-80be-b04f329f3c50 | checkpoint | Box Fin Alignment completed
6165d3dc-cbd9-4382-a219-92c224e1b21a | checkpoint | Frames installed correctly?
4f911aa3-592d-400a-a370-ef44205be06b | checkpoint | Modules installed correctly?
65de735d-70a8-4ece-b267-245c63b7070b | checkpoint | Drains are not blocked
657278c2-b4ae-4cb7-adb7-52dca4ddcf55 | checklist | Centrafix - Install Checklist |  | Centrafix - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
d1ed660d-b5bb-475b-a581-85dd0b3dc658 | checkpoint | Has the window/door installation been completed?
8fef4ab2-8709-48a5-8b04-b5c2e76a9fae | checkpoint | Is Foam Seal installation neat and continuous
fd73c3ac-4770-470d-bc66-8fde83d484bf | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
0ed3c5ac-9cc2-454c-a8f6-89d00021529c | checkpoint | Are all window and doors working?
2f42d820-a6a0-4f9f-896f-a1724252da12 | checkpoint | All handles installed correctly?
a27342f4-7df7-4416-9cb2-2fbef3044432 | checkpoint | Are all the hardware installed correctly?
b41350bf-e170-4869-b7d8-198351168d7f | checkpoint | Is the joinery free of scratches?
df233d5c-7635-4ec8-b452-15c4a480191a | checkpoint | Is the joinery clean and tidy?
bddc0d56-5054-444c-bdb8-2aaf17b18dd1 | checkpoint | Are Restrictor Stays fitted(Fully Fixed off & Silent operation)
a31f43cc-cd3d-4422-b966-c8e67edde575 | checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
1b7e2a72-47db-414a-9db5-5202509ad5e5 | checkpoint | Sliding doors - panels are adjusted and locking easily
3a9c036e-d311-4121-84ac-5656bfe5da40 | checkpoint | Sliding doors - Strikes are adjusted
365c7f1a-5ea6-4486-ab3c-a12e8c6f4118 | checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
a5b54110-a2dc-42c1-8481-890d5890e997 | checkpoint | Windows open, close, and lock smoothly without excessive force.
128b6fd0-488b-4caa-9fab-b4ec62c0308a | checkpoint | All operable windows have functional hardware (locks, latches, etc.)
94d94418-79bb-4588-a756-ae1aaffa78fb | checkpoint | Proper spacing and clearances are maintained around the window units.
32ef8292-bd16-4f48-a31b-3401ddce0ff7 | checkpoint | Fasteners used are correct in type, size, and spacing
fa82180b-1474-4043-9187-b231147883e6 | checkpoint | Frames installed correctly?
81183833-6485-4627-b74c-660b65d73fa3 | checkpoint | Drains are not blocked
dcf14661-3738-4859-8aa5-5f00ba574d3e | checklist | Channel Glazing - Install Checklist |  | Channel Glazing - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
63237f2d-b90f-43f5-afe1-5abbd9a756e3 | checkpoint | Has the window/door installation been completed?
6a717b48-0c5c-4aee-adf3-b3b120ad5d41 | checkpoint | Is interior sealants installation neat and continuous.
a06ac887-9d21-48e9-9f77-c82894c97e45 | checkpoint | Is exterior sealants installation neat and continuous.
dab2bc9e-5ed0-4caf-9198-1ef94f3d236d | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
0b31a914-1523-4ba6-8e01-b501a8071b74 | checkpoint | Are all window and doors working?
bb1171e8-eb84-4b80-bf5d-51f5545e5f56 | checkpoint | Is the joinery free of scratches?
f9591f0a-f972-4877-af4a-25a4ad9780aa | checkpoint | Is the joinery clean and tidy?
b729b735-d6b2-4889-a14a-12873855ed53 | checkpoint | Proper spacing and clearances are maintained around the window units.
c260c7e0-dc93-4c58-a3a5-fd2ba7675131 | checkpoint | Fasteners used are correct in type, size, and spacing
fbf4f963-c1d4-4502-bdfb-547dd157f855 | checkpoint | Frames installed correctly?
3d25d541-f119-499b-a8d0-2654564da3e0 | checkpoint | Drains are not blocked?
c9adbf83-4a86-4a78-b807-19be6c22d1c0 | checklist | Flush Glaze - Install Checklist |  | Flush Glaze - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
48c10f70-0d4b-4a90-afbb-55fd4684f967 | checkpoint | Has the window/door installation been completed?
340d29fd-6b01-4096-b14c-d9ce3af41d1f | checkpoint | Is interior sealants installation neat and continuous.
d29f75cb-ea05-492d-8d39-27c08896e860 | checkpoint | Is exterior sealants installation neat and continuous.
d4f797f6-c3d7-45de-94ef-7666a06193a3 | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
7e9cac91-87f8-4685-bf5d-85ea53cf8406 | checkpoint | Is head flashing installed per plans and as detailed in the shop drawings?
5c406f41-6d2d-4329-8a7c-b1b87b0ba11e | checkpoint | Are all window and doors working?
b09c0a65-b29a-4786-9a94-32276b677b99 | checkpoint | All handles installed correctly?
4324a5b0-2da3-4ab3-999a-288c24ae6e01 | checkpoint | Are all the hardware installed correctly?
7cf8019e-c365-4aa5-97a9-cc6348b3fc54 | checkpoint | Is the joinery free of scratches?
6027b327-2227-4a11-93b1-68e503df9908 | checkpoint | Is the joinery clean and tidy?
87916409-3f74-4f9e-964b-be5d3fd1a384 | checkpoint | Hinge doors strikes adjusted and locking easily
1eb71b29-56f7-4e8d-a58c-b51b07a6516a | checkpoint | Hinge doors 4 or 3 point lock operate easily
4fb24d9a-9ef8-4d70-aa0e-63304c2f0597 | checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
216f5f98-f5aa-4c5c-a5a8-cd009b834074 | checkpoint | Sliding doors - panels are adjusted and locking easily
0ec769cd-ee3f-43ab-9560-8cc593991c4b | checkpoint | Sliding doors - Strikes are adjusted
4f72da1a-1cba-4a3a-a37e-b6cb3589aa7a | checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
367b0c51-b782-4609-9e94-d0df882c8710 | checkpoint | Proper spacing and clearances are maintained around the window units.
6a9c8700-df7c-4f7d-8723-b656f3da0834 | checkpoint | Fasteners used are correct in type, size, and spacing
ead71cd2-f904-4825-b72a-41197892905b | checkpoint | End Caps Installed
a92f216e-1145-4532-b15d-824731b955b2 | checkpoint | Frames installed correctly?
6cc78356-b4bc-4b8f-b7e4-2a50cc6a58f4 | checkpoint | Modules installed correctly?
2ee6f1fe-25ca-4433-b733-391ba6d27ade | checkpoint | Drains are not blocked
5648de90-9a01-4d07-a1e3-3c9c93fa988e | checklist | Glazing Checklist |  | Glazing Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
4c5c1fcd-f6c6-437c-a7af-73cda989e0ca | checkpoint | Frame installed securely
164bbf4f-0488-4fd8-84b9-e19aa68b4e8d | checkpoint | Correct glass installed
f80aa5b3-023a-4d9b-b267-eb591c2a7825 | checkpoint | Glass installed with correct face to the outside
41618874-7cb8-4d0b-9fac-1aca843cc3ec | checkpoint | Setting/location blocks correctly installed
e044dc16-ee1e-4aeb-8eb1-aaef9bd98dd6 | checkpoint | Beads installed
a3498269-12a8-4a50-bac1-cbfab2ae7b02 | checkpoint | Wedge rubber complete
221466a9-a975-4ae6-a7d4-9d5e5047ee15 | checkpoint | Trade clean
d19f209e-a969-4bda-a1c5-1af4623829aa | checklist | Handover Checklist |  | Handover Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
27380c22-3f04-4f74-a92b-9613f1302b4e | checkpoint | All works completed as per specifications
f7084266-4826-505b-b0c6-24790f3f3cc9 | date | Date:
5fbd39ca-0481-4021-80a5-175f880394e4 | checkpoint | Company Signoff
ef358f3a-a8f5-4e99-9895-b47f5340d929 | signoff | SIGN HERE
f9276116-ddf8-4f57-8ae6-b7bba8433b35 | checkpoint | Client Signoff
65597264-1723-4046-b15f-2fc2efec4a00 | signoff | SIGN HERE
e0c66102-d2fa-4367-829d-a0b894953883 | checklist | Metro-Resi - Install Checklist |  | Metro-Resi - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
825a0904-1d99-47cc-a2e0-6746c41573d3 | checkpoint | Has the window/door installation been completed?
103f1ed4-9f1e-4d3a-bb37-2e50f1941029 | checkpoint | Is interior sealants installation neat and continuous.
9bccb940-dc5d-4e12-abad-e9773eb01c82 | checkpoint | Is exterior sealants installation neat and continuous.
74d57ec0-5df8-44eb-bb6c-170d808ae4de | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
f601949b-5237-421c-9e30-ee14f04953c5 | checkpoint | Is head flashing installed per plans and as detailed in the shop drawings?
fdfedea8-8684-4044-8a48-8bb45632282c | checkpoint | Are all window and doors working?
115794d6-f1ea-4607-bb27-fc10ba2f1b66 | checkpoint | All handles installed correctly?
2a00c453-6195-4ea0-b48e-bbd4c6d596cb | checkpoint | Are all the hardware installed correctly?
3116ac17-7f93-4fd2-bc47-ad0c8f22c038 | checkpoint | Is the joinery free of scratches?
40912c60-2b8b-481a-b7b8-6159b02445df | checkpoint | Is the joinery clean and tidy?
b2dd2ae0-3193-4b16-bd3f-5a63cdf04c32 | checkpoint | Are Restrictor Stays fitted(Fully Fixed off & Silent operation)
616bad68-f82b-45b2-863a-f88d0f28839a | checkpoint | Hinge doors strikes adjusted and locking easily
2827047f-c486-48f2-ac24-d6b65eb600f8 | checkpoint | Hinge doors 4 or 3 point lock operate easily
00709556-a12b-409b-9b0d-96b745c42c04 | checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
b62e80ca-0dd9-43bc-afc3-e8d357c6fa93 | checkpoint | Sliding doors - panels are adjusted and locking easily
3aa85846-9a7a-4538-b185-1fbffbc7ca68 | checkpoint | Sliding doors - Strikes are adjusted
a93196ff-6c0f-4722-8fcf-f7a4f133c180 | checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
d7d1ce7e-ad2d-4a5e-9a1d-5472749ad38b | checkpoint | Windows open, close, and lock smoothly without excessive force.
5c5e1012-a409-4b75-b36d-12511c0fc857 | checkpoint | All operable windows have functional hardware (locks, latches, etc.)
43a79438-bb66-4d70-8557-94b0367b9783 | checkpoint | Proper spacing and clearances are maintained around the window units.
e069bf6f-3f91-4f3d-8ab1-9cdcc08c8c25 | checkpoint | Fasteners used are correct in type, size, and spacing
c28a2d7f-d2a3-402e-a347-6407c95e1d5f | checkpoint | End Caps Installed
629ad1e4-6c22-47d4-8050-b000626bb2be | checkpoint | Frames installed correctly?
2e54044c-2203-4c9c-859f-d5ae6c2122e6 | checkpoint | Drains are not blocked
5c199021-9db1-4c74-8507-6579e8f0b6d8 | checklist | Performance Tests |  | Performance Tests
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
6cec2f30-4dcd-46a8-b50d-08118a04f72a | checkpoint | Water test (if applicable) performed and passed.
84118a9f-0365-4974-91e1-3af776fc2d5c | checkpoint | Sealant Peel Test (if applicable) performed and passed
c44672c5-ef64-4d52-a58b-dd828b4093ed | checklist | Pre-Install Checklist |  | Pre-Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
cc993733-106b-4d2a-8e8c-4241fbc65b9b | checkpoint | Openings are prepared and match the dimensions specified in the drawings
0fc6e13a-bd1c-452c-8fb6-3a228690f614 | checkpoint | Waterproofing are prepared
097a7643-3873-44f5-b64b-466c49b890db | checkpoint | Windows are free from any visible damage or defects
d0a86f06-9255-45d2-b3f0-304a56e0e869 | checklist | Shopfront - Install Checklist |  | Shopfront - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
a0ad4231-771e-44d8-99ca-88da280db6a8 | checkpoint | Has the window/door installation been completed?
92c5ab18-e85b-497d-a15d-7c620d24b9c7 | checkpoint | Is interior sealants installation neat and continuous.
c26f3922-32b4-4f99-9718-c92db7e6fcd4 | checkpoint | Is exterior sealants installation neat and continuous.
bed88ea1-ef78-4198-9639-fdf7efadb7e5 | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
e023ca02-acc0-4d7c-995f-64a6bff6473a | checkpoint | Is head flashing installed per plans and as detailed in the shop drawings?
0005a4c6-e7ed-40e2-867b-10a7bae521dd | checkpoint | Are all window and doors working?
fabfddd4-2cdd-4233-9371-373636f8fbc4 | checkpoint | All handles installed correctly?
b13da429-d1b2-484f-a3dd-5d872070b419 | checkpoint | Are all the hardware installed correctly?
2fcdc4dc-d896-4ef6-8c1f-e20b72caad3f | checkpoint | Is the joinery free of scratches?
0a7d0884-ee75-4f0b-bcfe-a8ea01fcc400 | checkpoint | Is the joinery clean and tidy?
5a6360d7-f6ea-41f2-a1f8-09758670d2bb | checkpoint | Hinge doors strikes adjusted and locking easily
40294ba1-5456-4106-a2a3-36a9c420dd61 | checkpoint | Hinge doors 4 or 3 point lock operate easily
82f12a87-5492-4a57-84ba-3cc9c36d956d | checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
70a29070-7472-4f16-8ab8-82997655cf46 | checkpoint | Sliding doors - panels are adjusted and locking easily
df0f99f8-99dd-4df7-bcf6-857a3fd6e78e | checkpoint | Sliding doors - Strikes are adjusted
b47e6765-1ec0-4ab8-aa6a-df8feee9a849 | checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
066dd692-218e-4a02-8854-5c41649d3737 | checkpoint | Proper spacing and clearances are maintained around the window units.
8c40125c-b39f-4bf4-a538-e3613547eeaf | checkpoint | Fasteners used are correct in type, size, and spacing
819c2142-47ad-46ea-b5ee-c47a99733897 | checkpoint | End Caps Installed
9958ac7c-a899-43d8-a038-7c9a5f08c76f | checkpoint | Frames installed correctly?
3b01eaae-7be4-42ef-9bd2-24b48aa4232c | checkpoint | Modules installed correctly?
0f3f00c3-81ff-4244-8ad9-327da694e696 | checkpoint | Drains are not blocked
bcd54fb6-4b28-4055-bd38-bc7adfe4c242 | checklist | Structural Glaze - Install Checklist |  | Structural Glaze - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
b0280240-15b3-45e0-9ce8-8466c9b65577 | checkpoint | Has the window/door installation been completed?
bc2a0197-4f52-4728-ac01-d4e0c8d940f3 | checkpoint | Is interior sealants installation neat and continuous.
25379abb-bd6b-44c6-8f2d-fae5756e63f8 | checkpoint | Is exterior sealants installation neat and continuous.
3d0694a4-4759-4901-9424-0d1f70b0efb2 | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
7dad0b25-e96e-42c2-a959-a4dd548bf4fa | checkpoint | Is head flashing installed per plans and as detailed in the shop drawings?
cec0299f-0a91-4f2c-b905-b814e9b18f7c | checkpoint | Are all window and doors working?
5e648693-7228-4815-8922-f8c881f68172 | checkpoint | All handles installed correctly?
28ffa173-0b2d-4260-82c1-61f619c400eb | checkpoint | Are all the hardware installed correctly?
ee7a22f0-7a1b-4ca5-8337-9790c164b3cb | checkpoint | Is the joinery free of scratches?
bb8b94ae-092a-4044-a901-84565583a391 | checkpoint | Is the joinery clean and tidy?
a140e497-28e7-42ce-83e2-fab164544c58 | checkpoint | Hinge doors strikes adjusted and locking easily
9a54aa3d-8069-4087-abbb-a5492b746bd0 | checkpoint | Hinge doors 4 or 3 point lock operate easily
cd4aa98d-d371-4f21-bbe8-d0b1900eb26e | checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
dec17444-3a9b-495b-870a-1ffe763445a5 | checkpoint | Sliding doors - panels are adjusted and locking easily
b6bd8973-a421-427d-a2b3-2c449cf58066 | checkpoint | Sliding doors - Strikes are adjusted
5a4b7055-3a4d-49f6-86ed-ef39f62d1b24 | checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
9cdc40f0-cac5-420a-875e-81ac443b0167 | checkpoint | Proper spacing and clearances are maintained around the window units.
75c42c1b-0700-4419-8735-efd1268b5290 | checkpoint | Fasteners used are correct in type, size, and spacing
9527c356-e9c4-4480-8315-7f4a62f86bb9 | checkpoint | End Caps Installed
40113c46-bbec-4e71-87ec-fffe6c84c250 | checkpoint | Frames installed correctly?
7ecff598-8418-4c3c-bb50-86617b21c547 | checkpoint | Modules installed correctly?
498544d9-0a49-4d71-b5d1-13d61169c415 | checkpoint | Drains are not blocked