## Master List Templates
Id | Type | Name | Values | Prompting Name
ed5ba497-64c2-4905-85f6-5af7b6776883 | checklist | Architectural - Install Checklist |  | Architectural - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
4b749e5f-ed5e-4491-a660-59e5ae2d8b71 | checkpoint | Has the window/door installation been completed?
011f2872-23ae-40e0-ad8c-2c477d32f5a7 | checkpoint | Is interior sealants installation neat and continuous.
fb5f5b10-c67b-4312-b33b-284d63b425f8 | checkpoint | Is exterior sealants installation neat and continuous.
e943df7d-3e1a-4ee0-ac5e-5495aa90856d | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
4215faf8-2e6d-4e85-a11c-2636235fbb64 | checkpoint | Is head flashing installed per plans and as detailed in the shop drawings?
9f782d83-d9c0-4e9b-9c8e-3c8f20461f93 | checkpoint | Are all window and doors working?
c8f6d642-0f71-45d1-8ca9-ae61af3a9522 | checkpoint | All handles installed correctly?
fbd5cd23-5234-422c-af96-d5968116477a | checkpoint | Are all the hardware installed correctly?
52360ed7-30db-483d-8ca3-e670cad874a2 | checkpoint | Is the joinery free of scratches?
5d89090a-b806-4e2e-aa76-19900ef294a8 | checkpoint | Is the joinery clean and tidy?
7090f7ef-566a-421d-b6bb-ec13bae196e8 | checkpoint | Are Restrictor Stays fitted(Fully Fixed off & Silent operation)
e35d6fe5-19d4-4c41-86c4-2abeecba7e89 | checkpoint | Hinge doors strikes adjusted and locking easily
a25d8577-34d2-4950-a0a0-ee243a0c0207 | checkpoint | Hinge doors 4 or 3 point lock operate easily
96f86f0e-dadd-4161-94e6-82d9755e9d63 | checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
cec193f3-6827-4488-9e71-0a2f79691a12 | checkpoint | Sliding doors - panels are adjusted and locking easily
3ff69e39-3b88-40cf-8b81-a19d5c7c47d5 | checkpoint | Sliding doors - Strikes are adjusted
42b59d6b-30f3-44d3-b218-3a004de2197d | checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
9630a4ca-479c-4e3b-8b1d-658603c19d65 | checkpoint | Windows open, close, and lock smoothly without excessive force.
9a7f70e4-5441-430d-983d-ec3b86823500 | checkpoint | All operable windows have functional hardware (locks, latches, etc.)
fd2e4e87-935d-4a40-83b2-158176054e27 | checkpoint | Proper spacing and clearances are maintained around the window units.
bfd6c9f6-416e-4f0f-b896-301a9727121a | checkpoint | Fasteners used are correct in type, size, and spacing
6915d02c-7947-4871-bfbe-d9dc6a2df35e | checkpoint | End Caps Installed
b79edad2-42d0-4d5f-bc04-5fe3e1ccce36 | checkpoint | Frames installed correctly?
73734e08-c07a-46c0-9212-4091e3db80cb | checkpoint | Modules installed correctly?
29850021-eab2-4d98-83f5-105aa1eaca9f | checkpoint | Drains are not blocked
4c21db70-521b-4bfe-b8fb-429f0948c12c | checkpoint-no-value | The correct consumables specified were used (Sealant) - Photo of Label Required
26d4bfb6-e0cb-40cd-ae4b-c36996e827ff | checkpoint-no-value | The correct consumables specified were used (Screws) - Photo of Label Required
bf940eed-1583-444b-a88a-7fe6080bd2ec | checklist | Box Fins - Install Checklist |  | Box Fins - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
9f16cca4-1553-443a-9b99-2aed515f7a9b | checkpoint | Has the window/door installation been completed?
0984b153-3eaa-4813-9816-8eb9b589124f | checkpoint | Is interior sealants installation neat and continuous.
8428e856-68d0-476c-b582-f186a11e4dc3 | checkpoint | Is exterior sealants installation neat and continuous.
a1921991-582f-4986-b3aa-b91e0f734fa6 | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
20ab1926-e99d-4f35-8689-a94b9e691368 | checkpoint | Are all window and doors working?
a627108f-86fd-4cf8-b223-03c63b4326f8 | checkpoint | Is the joinery free of scratches?
24a7715a-c77c-4fc9-b782-f0d92bc3c5a6 | checkpoint | Is the joinery clean and tidy?
7bab1045-0600-4232-bc75-b94fab728abc | checkpoint | Proper spacing and clearances are maintained around the window units.
ca948369-328d-428b-a80c-d32bd72e81b9 | checkpoint | Fasteners used are correct in type, size, and spacing
e92e84b6-0b0a-4274-96a8-e7c951bbc9ff | checkpoint | End Caps Installed
4e3a18c8-06af-4143-b117-f6e0568067eb | checkpoint | Brackets installed to modules as per Shop Drawings
9ff05b47-9a6b-4526-97f7-1cf92d0e8033 | checkpoint | Brackets installed to Box fins as per Shop Drawings
8d8a2778-5d46-4364-9352-b5b0b2a0a01f | checkpoint | Box Fin Spacing as per Shop Drawings
1c1a3a6d-4406-438d-b6a0-25e3e6428484 | checkpoint | Box Fin Alignment completed
9769f69a-caaa-4d67-afc3-a7f9b27b4410 | checkpoint | Frames installed correctly?
dc75720c-baf6-4997-bc91-d99d9fde64f9 | checkpoint | Modules installed correctly?
23544eb9-37ca-40aa-81dd-3183db4adde2 | checkpoint | Drains are not blocked
c15efdd1-5fae-49d2-8965-28e54566368e | checkpoint-no-value | The correct consumables specified were used (Sealant) - Photo of Label Required
4a3f2adc-414e-4de3-9782-833bd2fbd759 | checkpoint-no-value | The correct consumables specified were used (Screws) - Photo of Label Required
4e4e8778-0b9e-4a42-b825-ba332a995892 | checklist | Centrafix - Install Checklist |  | Centrafix - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c8361a60-758b-4094-bb21-c97c675139df | checkpoint | Has the window/door installation been completed?
23f21a7f-a428-4d87-9c3f-21e955d920b6 | checkpoint | Is Foam Seal installation neat and continuous
ec767c97-7b43-4902-8dcc-8ed6408fedaf | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
3ce65261-116d-4805-9b73-3962ad841bbb | checkpoint | Are all window and doors working?
f4363e99-aadd-4ed7-baaf-31151c376435 | checkpoint | All handles installed correctly?
d3fd053b-dc66-4325-9a29-9de516e03c1a | checkpoint | Are all the hardware installed correctly?
f46813e4-6431-4b54-a8b5-1bb61ea82026 | checkpoint | Is the joinery free of scratches?
05cddcf4-446e-46f3-9457-8c799c40082d | checkpoint | Is the joinery clean and tidy?
e86d4ad7-c297-4356-bc91-6b45cb2af139 | checkpoint | Are Restrictor Stays fitted(Fully Fixed off & Silent operation)
8e41ff7e-cafb-45b0-8617-b4541d69294b | checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
b7f94444-1d64-4a25-9cdc-142f9e4b97ba | checkpoint | Sliding doors - panels are adjusted and locking easily
3ddd395b-7543-40a3-8bef-c56b41bdf4d0 | checkpoint | Sliding doors - Strikes are adjusted
975ac407-51f3-4d23-b551-bb8bf3db1c5d | checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
2be71943-9afa-4857-928d-0d4ed3dadc7a | checkpoint | Windows open, close, and lock smoothly without excessive force.
09b01bc4-856f-4106-a5d7-82580b129821 | checkpoint | All operable windows have functional hardware (locks, latches, etc.)
c05f16d9-20a1-40a2-8d91-ab7812f0b1b1 | checkpoint | Proper spacing and clearances are maintained around the window units.
55cc8a7d-2339-4c1c-a1cf-ed52d1d12eb6 | checkpoint | Fasteners used are correct in type, size, and spacing
c9e70d11-01a1-4bf2-8dbe-99d1045051ef | checkpoint | Frames installed correctly?
4608a93d-ba1a-47b0-94f4-32160af5debb | checkpoint | Drains are not blocked
3f752ebc-4e66-4356-80e0-16f4409a50b1 | checkpoint-no-value | The correct consumables specified were used (Sealant) - Photo of Label Required
9b0bb219-f344-4bc7-b2a6-752a427d4d82 | checkpoint-no-value | The correct consumables specified were used (Screws) - Photo of Label Required
26ebadd8-7869-48d5-8a88-80ea0b334524 | checklist | Centrafix - Manufacture Checklist |  | Centrafix - Manufacture Checklist
61afa432-93a2-4bc1-a8d9-fa67a5756702 | section | 2 sec Visual
f5d2bcc9-aa0c-497b-ac8f-f1f1a9a6b79e | checkpoint | Frame free of defects and damage
ebd4621c-402f-4e64-a19a-27a149cfb779 | checkpoint | Frame and glass clean
c6d245d0-ac42-41a4-ab8e-72829f637686 | checkpoint | Drainage in the right position
4c204538-e407-4600-8454-9342da1ba397 | checkpoint | Staples every 150 to 200mm and not sticking out
4709caa6-65d1-4844-91b1-b20a595bcc00 | checkpoint | Cleaned pencil marks under drain holes and mullions
288b680a-0591-4ea9-9daa-644d5a8621db | checkpoint | Small joint colour correct
421d631a-7da0-4264-8036-bf7605343539 | checkpoint | Beads correct length
970308e3-0b90-4dfc-916a-15dae58ab5b7 | checkpoint | Mitres flush
de06ec3b-9568-40d4-94a4-4928836f2a82 | checkpoint | Rubbers cut to correct length
3e422e35-cd03-41e4-939b-e29a7d91945f | checkpoint | Rubber not pinched under glass or GOS foam
465b89cb-af70-436d-8a16-18810b2a58b3 | checkpoint | Fin mullion painted
3a58d50d-d024-496e-9b44-b31236bde514 | section | Paperwork
f1246f06-c9df-406b-96ff-44eeef7b98c0 | checkpoint | TWT measured
c74c5093-d548-4cea-abe5-ee1527ea1b3a | checkpoint | Liners right type and groove detail
e5becb7d-47f5-4fae-a4ba-4038a9bc20b5 | checkpoint | Comments on job followed
7a7b9d33-0229-4098-86af-309849abf4d5 | checkpoint | Correct hardware and glass
4bce4c40-ae52-472a-b182-3da6c16ad8d1 | checkpoint | All the correct information has been written on liner
d5091136-7d9a-46aa-8da9-6115ffa5a36e | checkpoint | Windows made to the drawing
f184de43-49e4-4b75-92dd-c98eb36303fd | section | Handling
e620b380-58c8-402d-bca4-779f066ca154 | checkpoint | Bottom and top screws and bottom corners sealed
38f4cc3b-fe1c-4ba9-90bc-e3d4e7e8be83 | checkpoint | Sash stays and restrictors have all screws
bfe7fffe-f884-483b-9262-87d18495e5df | checkpoint | Sash opening and closing correctly
a00b5bfd-e11b-4faf-8f99-c2afbaebc299 | checkpoint | Handles facing the right way and are not loose
6776fdcd-6055-4126-9afb-61af58256904 | checkpoint | Clean seal on frame where sash is present
8b33bb4b-7427-4d17-8194-5c1a86a4addb | checkpoint | Soakers in corners (except TH and residential) and for TH drainage ramp
76b5fbe9-3289-4b92-8dfa-be7be5489382 | checkpoint | Gap fillers on residential 2019
727f7b2a-829a-48f0-876a-44de77bb37c4 | checkpoint | Correct Windzone sticker on top of fixtures
126968da-1d64-4042-9d19-27eac70154ad | checkpoint | Square frame/sash
2a4b7eb8-b072-416e-81f9-1058944143c2 | checkpoint | If glass, does it move (correct rubber)
31760796-db1d-4a15-acc2-f8ce54ff26d7 | section | Centrafix
182e810a-a50d-420d-9ea4-9cd4d9f0271d | checkpoint | Drainage correct as per APL manufacturing pack
b96d2a63-af8b-4f54-b9e2-7cae63c9bb2a | checkpoint | Sillsafe is applied correctly
d4c1948e-9d51-43d4-9ae4-6aac2496bcab | checkpoint | Soakers correctly fitted over Sillsafe ends
592e7f44-3b22-4fc1-b772-a950b6ea801f | checkpoint | Foam Tape fitted to sill fixing leg
4931285d-9a4f-42f5-b899-f4583e9922cc | checkpoint | Seal Between Liners correct application - Verified during assembly
48cfc9cd-4b73-4191-9cdc-452893427838 | checklist | Channel Glazing - Install Checklist |  | Channel Glazing - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
9decc434-3038-40b2-aea8-32661fbc4cac | checkpoint | Has the window/door installation been completed?
81ddc2c9-3817-4be3-8f4c-d4aef1e7ba87 | checkpoint | Is interior sealants installation neat and continuous.
a7334be9-b596-4659-a4a3-972992977f6e | checkpoint | Is exterior sealants installation neat and continuous.
edadd316-764b-4056-91b7-a8ba502c2e37 | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
24638af7-17d2-4d8e-85b2-33f20e93f3b0 | checkpoint | Are all window and doors working?
955f2234-6043-4577-a406-f35f142d1cb2 | checkpoint | Is the joinery free of scratches?
b3cd1466-56d8-4a03-919e-be47c2fb1bbe | checkpoint | Is the joinery clean and tidy?
25d38dbb-b2e2-496f-8374-f57649cd1367 | checkpoint | Proper spacing and clearances are maintained around the window units.
12b88cd7-66c9-4377-8c13-61dab7347f99 | checkpoint | Fasteners used are correct in type, size, and spacing
85c310de-970d-4b8c-9f5c-7f83dba150b4 | checkpoint | Frames installed correctly?
963bfe97-09b3-4ca2-abd2-3c351ffec7cc | checkpoint | Drains are not blocked?
a3735c3c-43ee-4cfe-a5b7-759e43d2a3a2 | checkpoint-no-value | The correct consumables specified were used (Sealant) - Photo of Label Required
c420144f-f907-4ec6-bd6d-11f00eda5268 | checkpoint-no-value | The correct consumables specified were used (Screws) - Photo of Label Required
96e84d49-9830-4573-8b9b-64743321174e | checklist | Flush Glaze - Install Checklist |  | Flush Glaze - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
4827c9ec-ca12-4c20-93bd-fb485f9ef6b0 | checkpoint | Has the window/door installation been completed?
4ad812e7-ad3a-41ad-97dc-0d6806f84cd7 | checkpoint | Is interior sealants installation neat and continuous.
fca26bca-b417-4924-a175-911608594313 | checkpoint | Is exterior sealants installation neat and continuous.
d1b6e121-c40f-4969-a1ad-36d8135e7a4b | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
38020422-9e64-4b11-8784-d5c519202351 | checkpoint | Is head flashing installed per plans and as detailed in the shop drawings?
bc7d0b15-ad05-43d2-8ed7-372c5f37d5b9 | checkpoint | Are all window and doors working?
e3f25dae-0e1e-45be-ba31-94420c590ade | checkpoint | All handles installed correctly?
6364639d-7461-4d50-b632-b89ee0ee959a | checkpoint | Are all the hardware installed correctly?
f3e6289f-2e22-4c6f-8982-9b75fc1278cb | checkpoint | Is the joinery free of scratches?
0e603a97-a45b-4af9-97a0-24b2af7558bc | checkpoint | Is the joinery clean and tidy?
86eb82f6-dc67-4638-8848-0fabbfb88f56 | checkpoint | Hinge doors strikes adjusted and locking easily
d5f6b887-c158-441a-89da-40c10b2a9dd7 | checkpoint | Hinge doors 4 or 3 point lock operate easily
e041b2ba-3fdb-4496-9fa0-de8aa0a2d625 | checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
578f4e7d-658a-43de-a1f9-767fe4fab19c | checkpoint | Sliding doors - panels are adjusted and locking easily
3ed17202-d703-49fb-a2d0-ee08e76166fa | checkpoint | Sliding doors - Strikes are adjusted
e6b8f241-af22-48a2-9cd6-e733cab1fe03 | checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
86b45a0b-f4af-45b9-a484-82acb5397c91 | checkpoint | Proper spacing and clearances are maintained around the window units.
c8d63ab1-1c79-45f3-9bae-4c1727acabfc | checkpoint | Fasteners used are correct in type, size, and spacing
fdbf3e3a-471d-40aa-aa47-49482f8116aa | checkpoint | End Caps Installed
97e3cbf2-3749-4a1b-b18a-ac6a6d2bdf41 | checkpoint | Frames installed correctly?
3d412e88-eedf-4a96-8262-c1d3ab64d725 | checkpoint | Modules installed correctly?
1272d03c-b5d2-4765-9e03-8551476b5c10 | checkpoint | Drains are not blocked
17a6cf65-36c8-4fa2-9a9c-1058d2202e97 | checkpoint-no-value | The correct consumables specified were used (Sealant) - Photo of Label Required
29fe7ec0-7839-45b3-b4f7-0b9146140ec5 | checkpoint-no-value | The correct consumables specified were used (Screws) - Photo of Label Required
e75fa9ec-9749-4c52-bf48-199f7aeab6c4 | checklist | General Manufacturing Template |  | General Manufacturing Template
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
83bd2d4e-0fe3-439f-86c2-c2768ee445a4 | checkpoint | Item free of defects and damages
5fd22b99-4780-43c6-ad4c-0fb51c1d1379 | checkpoint | Item is clean - No pencil marks / dirt / excessive sealant
022fbb6b-a0b9-4481-9874-92f58e3dab83 | checkpoint | Item is clearly labelled in accordance with fabrication sheets
7a8f9bfe-103e-430b-a0d6-1ab14ae785fc | checkpoint | Item is square - Frame / Sashes / Panels
5ffbc1b4-0ee6-46ed-be65-9bb4c0e10e5b | checkpoint | Sealant is correct colour
21ec308c-fb31-471c-92aa-52f970d6460e | checkpoint | Beads / Thresholds / Infills correct length
5d9c8513-2879-4860-af07-5d9448ce6e25 | checkpoint | Mitres flush
10f0cea4-e5c5-4f61-97e4-4e488cd6ccd1 | checkpoint | Drainage correct as per APL manufacturing pack and aligned
cde361a9-c03b-4620-9275-29b7d1968dac | checkpoint | Liners - TWT Measured / Correct Liner / Staples every 150 - 200mm
33435a04-bba7-4189-a3da-2e190ce103f3 | checkpoint | Rubbers continuous and free of damage - not pinched under glass / foam
bb930635-b662-42a3-8e10-43aee0db603b | checkpoint | Fin Mullions painted
4af25516-ce52-44de-a9e6-a11f4dcff239 | checkpoint | Sealant tidy on frame where sash is present
2f9938bd-984c-4b54-b40e-a20456f87fa4 | checkpoint | Glass inspection done - Clean / Correct type / No defects
ebb169bb-0cec-4538-b417-624da86a3561 | checkpoint | Glazing done correctly - No movement / correct glazing rubber
c08a92da-7e06-41f7-b6da-dee8b20a2f0b | checkpoint | Bungs / Caps fitted
5d151bf8-a07d-45b2-a6d2-eca2d09ceb32 | checkpoint | Support Blocks fitted
bc0b3aa1-cf30-4e61-9556-22604141c473 | checkpoint | Transport Blocks between panel and frame
dc1129a6-90bf-4989-933c-b196d783937e | checkpoint | Protective tape on bottom sill
41776750-e73b-470c-9bdc-9231296698b0 | checkpoint | Overall item dimensions correct
12e7851f-a3b7-40c8-9fa2-2d475a16abfd | checkpoint | Correct Windzone sticker applied
5de09a86-8ad8-4531-b97d-b6013a7edb63 | checkpoint | Item match drawing
0dfa618d-6ae0-4090-b4ec-e3ba60682f92 | checkpoint | Commenst on jobsheets followed
6dd88342-6059-408e-a00c-9c6dae71034a | checkpoint | Machining done as per assembly sheet
e251f8cc-536b-447c-b75b-499bdb6d90f9 | checkpoint | Correct Hardware fitted as per jobsheet
8ea8d0b6-ed98-443a-bf37-cc1da4bc96f6 | checkpoint | Soaker correctly fitted
e3533ec2-989b-4854-897c-cc71ec8b2715 | checkpoint | Sillsafe applied correctly
9bb04d30-a482-4f60-b67a-d8cd7f0bc0c2 | checkpoint | Soaker correctly fitted over sillsafe ends
b6fff5cf-485f-4e6f-8687-8e6e4304b090 | checkpoint | Foam tape fitted to sill fixed leg
5219d8fc-d186-4b0a-a4ac-89e322029edb | checkpoint | Top & Bottom Screws sealed
3b5a076b-c0c1-4226-bfab-d9c5b64aefb5 | checkpoint | Screws fitted to all hardware & components
a863823f-f9bf-4c1d-9177-bb3a38dfaf4b | checkpoint | Glazing Platform fitted (TH Frames)
487e8a8e-8278-43e7-b18f-34939b2203ad | checkpoint | Seal between liners - Correct application
3e60ef50-1a78-4c21-85ca-a6221847c57f | checkpoint | Tracks / Stoppers fitted correctly
7688e894-e64b-4515-a3e2-82b44ba24b50 | checkpoint | Sashes / Panels opening and closing correctly
fa453deb-b971-4e22-b80e-0113342e3c3b | checkpoint | Handles facing the right way and are not lose
263510fb-cf9c-4d6b-83e8-f4871799fba3 | checkpoint | Strikes fitted - Item locks / unlocks freely
034c87a7-8724-4c6d-8bf5-26010efc88a4 | checkpoint | All hardware operational
b2cba76e-bc18-4695-ab3b-13d9997eb5f4 | checkpoint | Protective tape on handle - Key taped to inside of handle
d900dd32-9eba-4297-b27f-6d98c6558780 | checklist | Glazing Checklist |  | Glazing Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
b68e0248-2936-43d7-a39e-425796453601 | checkpoint | Frame installed securely
4bc74dd1-2c26-42fc-9240-efb1d4d8f31f | checkpoint | Correct glass installed
144ce542-9dd8-46db-a99b-ae5c872b169e | checkpoint | Glass installed with correct face to the outside
8c042754-d45b-443d-bc5b-2c4227aa0c59 | checkpoint | Setting/location blocks correctly installed
e8d93361-bb58-40fb-8648-db2f0fd7cc49 | checkpoint | Beads installed
e2f364df-c5f6-4d6b-91f5-e4a855a0b7dd | checkpoint | Wedge rubber complete
c710226e-2ed1-4c58-b052-4585b0c112f8 | checkpoint | Trade clean
93754c40-d751-4f62-8952-dbb6fe743baa | checklist | Handover Checklist |  | Handover Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
f5319e7d-c1f3-4777-b3a2-6b94f57a4313 | checkpoint | All works completed as per specifications
7b05e090-6935-5526-a050-1202c0b658f4 | date | Date:
bcb80f05-b1a1-4cf1-9660-fa74a8d7790f | checkpoint | Company Signoff
6307ad26-9f46-4bae-a376-4475c7e744f8 | signoff | SIGN HERE
a79b18ad-d9c6-44cf-af9b-3a0634994635 | checkpoint | Client Signoff
3117845b-52e4-4056-b6ac-4dfcbd0ec98b | signoff | SIGN HERE
fabab1f4-499c-4d74-a3b4-74898b14a941 | checklist | Performance Tests |  | Performance Tests
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
02e033c7-3388-461a-9334-681086727aa0 | checkpoint | Water test (if applicable) performed and passed.
883761d8-e44d-4bec-a7e5-84ca8536b1c4 | checkpoint | Sealant Peel Test (if applicable) performed and passed
5a22953a-90a7-43f1-bf68-3ca12e772e78 | checklist | Pre-Install Checklist |  | Pre-Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
b00b5a77-ad76-45b6-b3ad-2731c8def02a | checkpoint | Openings are prepared and match the dimensions specified in the drawings
0f1896aa-38e6-449b-83dc-81b006266aa3 | checkpoint | Waterproofing are prepared
09275694-954a-46dc-87cb-d8c38a7c6214 | checkpoint | Windows are free from any visible damage or defects
9832d90a-3eff-4b2e-80a3-cc32c5805580 | checklist | Shopfront - Install Checklist |  | Shopfront - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
0700aeb0-3f45-4ff4-86b6-ab6c0cca4433 | checkpoint | Has the window/door installation been completed?
22636621-414f-4893-805e-6546b06e46a3 | checkpoint | Is interior sealants installation neat and continuous.
96bda80c-2631-46dd-b88a-8700430c61af | checkpoint | Is exterior sealants installation neat and continuous.
1eaae647-cd3a-495c-bfaf-d343f4748ed0 | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
0e43a742-3a62-4536-bba5-6531d0c7cc38 | checkpoint | Is head flashing installed per plans and as detailed in the shop drawings?
a0ec81ba-aad0-45a3-b1ee-18c2bcb2a02b | checkpoint | Are all window and doors working?
42c68b8c-0e27-4059-bef0-6566302122e5 | checkpoint | All handles installed correctly?
379cee60-3b3c-467d-bcaa-bcba2e9568df | checkpoint | Are all the hardware installed correctly?
417260e6-16f7-45c1-a701-98c28a5bdc41 | checkpoint | Is the joinery free of scratches?
8cfd618e-f177-497b-a8be-9c4d39b0f6fd | checkpoint | Is the joinery clean and tidy?
e6c1ed45-68bd-4f4e-9bf1-0b59885eddfd | checkpoint | Hinge doors strikes adjusted and locking easily
a0daa382-e0e6-48da-8217-402769e86259 | checkpoint | Hinge doors 4 or 3 point lock operate easily
822dd074-b742-42db-827e-3571d39ed6ab | checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
666f9ec9-82dd-4103-9aa8-5929c3ee6e2f | checkpoint | Sliding doors - panels are adjusted and locking easily
50d83164-a9e4-4566-9e3b-901f3c128573 | checkpoint | Sliding doors - Strikes are adjusted
c056892f-b32d-4cb0-9f45-9f419004a094 | checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
26957168-637e-4581-8159-c74e9bc1ae3f | checkpoint | Proper spacing and clearances are maintained around the window units.
ba37aef7-e674-4dae-91a7-b9772dfcabb5 | checkpoint | Fasteners used are correct in type, size, and spacing
3effd75a-f577-4aea-b04b-33c7c876f7af | checkpoint | End Caps Installed
266b9389-c9ca-4e57-a127-9692e9ba0d65 | checkpoint | Frames installed correctly?
103a2da0-4f87-42d6-bda7-f4838b94b6a3 | checkpoint | Modules installed correctly?
06602471-2c7a-4dbe-ae01-a26237ed3225 | checkpoint | Drains are not blocked
95001876-e7ce-4ab4-aecf-028c4d0fc456 | checkpoint-no-value | The correct consumables specified were used (Sealant) - Photo of Label Required
ddea2775-bac3-48d4-a371-53570906f5cb | checkpoint-no-value | The correct consumables specified were used (Screws) - Photo of Label Required
498451fa-4c5c-4493-bf45-2aa8240fd71d | checklist | Structural Glaze - Install Checklist |  | Structural Glaze - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
a6202c1a-9c75-45da-a7c8-ccfc043b41f5 | checkpoint | Has the window/door installation been completed?
9fee5fee-7e56-46a6-88fd-b338d4c3ec96 | checkpoint | Is interior sealants installation neat and continuous.
4cbb0e8d-4f4e-42e2-8ff3-bedbd52e203b | checkpoint | Is exterior sealants installation neat and continuous.
0376e0c5-35ed-48bd-8f19-41fa56d3f04a | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
05ad11a6-49e8-46a3-be38-348225650450 | checkpoint | Is head flashing installed per plans and as detailed in the shop drawings?
97243724-972f-4547-9c8e-7f73539e74ba | checkpoint | Are all window and doors working?
88435f8a-0f42-4cd3-ad70-8b3aa6902004 | checkpoint | All handles installed correctly?
894c7133-66a1-4306-85fe-6682a0e3a3f8 | checkpoint | Are all the hardware installed correctly?
d2bc6cb7-003b-489a-bd87-1c05e5b360a5 | checkpoint | Is the joinery free of scratches?
797af926-95d9-4274-8060-87005ff313bf | checkpoint | Is the joinery clean and tidy?
1084587b-8fe8-412c-9c62-dabdb51524f8 | checkpoint | Hinge doors strikes adjusted and locking easily
39f25609-dc9d-49de-9171-9a5ca9d832bb | checkpoint | Hinge doors 4 or 3 point lock operate easily
1f531f2c-debf-4f11-bd51-531b52f107a7 | checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
787bb37f-5f97-47d4-819c-3c66ea9cd595 | checkpoint | Sliding doors - panels are adjusted and locking easily
22f65642-8ba8-4803-b604-3ef3b34921d8 | checkpoint | Sliding doors - Strikes are adjusted
f7f999bc-7bbb-49d0-b610-b7de4afca181 | checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
3f174e56-5da8-4cc3-8ecc-45f6da79cc76 | checkpoint | Proper spacing and clearances are maintained around the window units.
b6805a9f-92bb-48bc-b931-fc0934f76ace | checkpoint | Fasteners used are correct in type, size, and spacing
afabb51f-106a-41fb-a75e-e2a166b56a26 | checkpoint | End Caps Installed
fa1811a2-5f98-416f-acbb-cae7e2184665 | checkpoint | Frames installed correctly?
6cfc2547-36f3-450b-963d-e9b0ddb415b4 | checkpoint | Modules installed correctly?
08848229-d398-4494-a945-75f3eab64de7 | checkpoint | Drains are not blocked
cd3dac97-f843-4108-90d4-d2f9b1a11fc8 | checkpoint-no-value | The correct consumables specified were used (Sealant) - Photo of Label Required
06be6f18-2455-4d2c-a5fe-fd795fcb83ef | checkpoint-no-value | The correct consumables specified were used (Screws) - Photo of Label Required
f1bf969b-4a44-462a-821e-bcc16fa6d5a2 | checklist | Ω (DEPRECATED) Architectural - Install Checklist (v0) |  | Architectural - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
4b749e5f-ed5e-4491-a660-59e5ae2d8b71 | checkpoint | Has the window/door installation been completed?
011f2872-23ae-40e0-ad8c-2c477d32f5a7 | checkpoint | Is interior sealants installation neat and continuous.
fb5f5b10-c67b-4312-b33b-284d63b425f8 | checkpoint | Is exterior sealants installation neat and continuous.
e943df7d-3e1a-4ee0-ac5e-5495aa90856d | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
4215faf8-2e6d-4e85-a11c-2636235fbb64 | checkpoint | Is head flashing installed per plans and as detailed in the shop drawings?
9f782d83-d9c0-4e9b-9c8e-3c8f20461f93 | checkpoint | Are all window and doors working?
c8f6d642-0f71-45d1-8ca9-ae61af3a9522 | checkpoint | All handles installed correctly?
fbd5cd23-5234-422c-af96-d5968116477a | checkpoint | Are all the hardware installed correctly?
52360ed7-30db-483d-8ca3-e670cad874a2 | checkpoint | Is the joinery free of scratches?
5d89090a-b806-4e2e-aa76-19900ef294a8 | checkpoint | Is the joinery clean and tidy?
7090f7ef-566a-421d-b6bb-ec13bae196e8 | checkpoint | Are Restrictor Stays fitted(Fully Fixed off & Silent operation)
e35d6fe5-19d4-4c41-86c4-2abeecba7e89 | checkpoint | Hinge doors strikes adjusted and locking easily
a25d8577-34d2-4950-a0a0-ee243a0c0207 | checkpoint | Hinge doors 4 or 3 point lock operate easily
96f86f0e-dadd-4161-94e6-82d9755e9d63 | checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
cec193f3-6827-4488-9e71-0a2f79691a12 | checkpoint | Sliding doors - panels are adjusted and locking easily
3ff69e39-3b88-40cf-8b81-a19d5c7c47d5 | checkpoint | Sliding doors - Strikes are adjusted
42b59d6b-30f3-44d3-b218-3a004de2197d | checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
9630a4ca-479c-4e3b-8b1d-658603c19d65 | checkpoint | Windows open, close, and lock smoothly without excessive force.
9a7f70e4-5441-430d-983d-ec3b86823500 | checkpoint | All operable windows have functional hardware (locks, latches, etc.)
fd2e4e87-935d-4a40-83b2-158176054e27 | checkpoint | Proper spacing and clearances are maintained around the window units.
bfd6c9f6-416e-4f0f-b896-301a9727121a | checkpoint | Fasteners used are correct in type, size, and spacing
6915d02c-7947-4871-bfbe-d9dc6a2df35e | checkpoint | End Caps Installed
b79edad2-42d0-4d5f-bc04-5fe3e1ccce36 | checkpoint | Frames installed correctly?
73734e08-c07a-46c0-9212-4091e3db80cb | checkpoint | Modules installed correctly?
29850021-eab2-4d98-83f5-105aa1eaca9f | checkpoint | Drains are not blocked
5b0e6534-a66c-4b8e-b48c-32ce48a81c57 | checklist | Ω (DEPRECATED) Box Fins - Install Checklist (v0) |  | Box Fins - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
9f16cca4-1553-443a-9b99-2aed515f7a9b | checkpoint | Has the window/door installation been completed?
0984b153-3eaa-4813-9816-8eb9b589124f | checkpoint | Is interior sealants installation neat and continuous.
8428e856-68d0-476c-b582-f186a11e4dc3 | checkpoint | Is exterior sealants installation neat and continuous.
a1921991-582f-4986-b3aa-b91e0f734fa6 | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
20ab1926-e99d-4f35-8689-a94b9e691368 | checkpoint | Are all window and doors working?
a627108f-86fd-4cf8-b223-03c63b4326f8 | checkpoint | Is the joinery free of scratches?
24a7715a-c77c-4fc9-b782-f0d92bc3c5a6 | checkpoint | Is the joinery clean and tidy?
7bab1045-0600-4232-bc75-b94fab728abc | checkpoint | Proper spacing and clearances are maintained around the window units.
ca948369-328d-428b-a80c-d32bd72e81b9 | checkpoint | Fasteners used are correct in type, size, and spacing
e92e84b6-0b0a-4274-96a8-e7c951bbc9ff | checkpoint | End Caps Installed
4e3a18c8-06af-4143-b117-f6e0568067eb | checkpoint | Brackets installed to modules as per Shop Drawings
9ff05b47-9a6b-4526-97f7-1cf92d0e8033 | checkpoint | Brackets installed to Box fins as per Shop Drawings
8d8a2778-5d46-4364-9352-b5b0b2a0a01f | checkpoint | Box Fin Spacing as per Shop Drawings
1c1a3a6d-4406-438d-b6a0-25e3e6428484 | checkpoint | Box Fin Alignment completed
9769f69a-caaa-4d67-afc3-a7f9b27b4410 | checkpoint | Frames installed correctly?
dc75720c-baf6-4997-bc91-d99d9fde64f9 | checkpoint | Modules installed correctly?
23544eb9-37ca-40aa-81dd-3183db4adde2 | checkpoint | Drains are not blocked
98501ad7-dd18-4648-9f7d-0e18a94191e1 | checklist | Ω (DEPRECATED) Centrafix - Install Checklist (v0) |  | Centrafix - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c8361a60-758b-4094-bb21-c97c675139df | checkpoint | Has the window/door installation been completed?
23f21a7f-a428-4d87-9c3f-21e955d920b6 | checkpoint | Is Foam Seal installation neat and continuous
ec767c97-7b43-4902-8dcc-8ed6408fedaf | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
3ce65261-116d-4805-9b73-3962ad841bbb | checkpoint | Are all window and doors working?
f4363e99-aadd-4ed7-baaf-31151c376435 | checkpoint | All handles installed correctly?
d3fd053b-dc66-4325-9a29-9de516e03c1a | checkpoint | Are all the hardware installed correctly?
f46813e4-6431-4b54-a8b5-1bb61ea82026 | checkpoint | Is the joinery free of scratches?
05cddcf4-446e-46f3-9457-8c799c40082d | checkpoint | Is the joinery clean and tidy?
e86d4ad7-c297-4356-bc91-6b45cb2af139 | checkpoint | Are Restrictor Stays fitted(Fully Fixed off & Silent operation)
8e41ff7e-cafb-45b0-8617-b4541d69294b | checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
b7f94444-1d64-4a25-9cdc-142f9e4b97ba | checkpoint | Sliding doors - panels are adjusted and locking easily
3ddd395b-7543-40a3-8bef-c56b41bdf4d0 | checkpoint | Sliding doors - Strikes are adjusted
975ac407-51f3-4d23-b551-bb8bf3db1c5d | checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
2be71943-9afa-4857-928d-0d4ed3dadc7a | checkpoint | Windows open, close, and lock smoothly without excessive force.
09b01bc4-856f-4106-a5d7-82580b129821 | checkpoint | All operable windows have functional hardware (locks, latches, etc.)
c05f16d9-20a1-40a2-8d91-ab7812f0b1b1 | checkpoint | Proper spacing and clearances are maintained around the window units.
55cc8a7d-2339-4c1c-a1cf-ed52d1d12eb6 | checkpoint | Fasteners used are correct in type, size, and spacing
c9e70d11-01a1-4bf2-8dbe-99d1045051ef | checkpoint | Frames installed correctly?
4608a93d-ba1a-47b0-94f4-32160af5debb | checkpoint | Drains are not blocked
d4e010ca-b147-4503-b6b7-aa04508d9526 | checklist | Ω (DEPRECATED) Channel Glazing - Install Checklist (v0) |  | Channel Glazing - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
9decc434-3038-40b2-aea8-32661fbc4cac | checkpoint | Has the window/door installation been completed?
81ddc2c9-3817-4be3-8f4c-d4aef1e7ba87 | checkpoint | Is interior sealants installation neat and continuous.
a7334be9-b596-4659-a4a3-972992977f6e | checkpoint | Is exterior sealants installation neat and continuous.
edadd316-764b-4056-91b7-a8ba502c2e37 | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
24638af7-17d2-4d8e-85b2-33f20e93f3b0 | checkpoint | Are all window and doors working?
955f2234-6043-4577-a406-f35f142d1cb2 | checkpoint | Is the joinery free of scratches?
b3cd1466-56d8-4a03-919e-be47c2fb1bbe | checkpoint | Is the joinery clean and tidy?
25d38dbb-b2e2-496f-8374-f57649cd1367 | checkpoint | Proper spacing and clearances are maintained around the window units.
12b88cd7-66c9-4377-8c13-61dab7347f99 | checkpoint | Fasteners used are correct in type, size, and spacing
85c310de-970d-4b8c-9f5c-7f83dba150b4 | checkpoint | Frames installed correctly?
963bfe97-09b3-4ca2-abd2-3c351ffec7cc | checkpoint | Drains are not blocked?
68093a7e-0bd3-42aa-babb-03e57aefa3d0 | checklist | Ω (DEPRECATED) Flush Glaze - Install Checklist (v0) |  | Flush Glaze - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
4827c9ec-ca12-4c20-93bd-fb485f9ef6b0 | checkpoint | Has the window/door installation been completed?
4ad812e7-ad3a-41ad-97dc-0d6806f84cd7 | checkpoint | Is interior sealants installation neat and continuous.
fca26bca-b417-4924-a175-911608594313 | checkpoint | Is exterior sealants installation neat and continuous.
d1b6e121-c40f-4969-a1ad-36d8135e7a4b | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
38020422-9e64-4b11-8784-d5c519202351 | checkpoint | Is head flashing installed per plans and as detailed in the shop drawings?
bc7d0b15-ad05-43d2-8ed7-372c5f37d5b9 | checkpoint | Are all window and doors working?
e3f25dae-0e1e-45be-ba31-94420c590ade | checkpoint | All handles installed correctly?
6364639d-7461-4d50-b632-b89ee0ee959a | checkpoint | Are all the hardware installed correctly?
f3e6289f-2e22-4c6f-8982-9b75fc1278cb | checkpoint | Is the joinery free of scratches?
0e603a97-a45b-4af9-97a0-24b2af7558bc | checkpoint | Is the joinery clean and tidy?
86eb82f6-dc67-4638-8848-0fabbfb88f56 | checkpoint | Hinge doors strikes adjusted and locking easily
d5f6b887-c158-441a-89da-40c10b2a9dd7 | checkpoint | Hinge doors 4 or 3 point lock operate easily
e041b2ba-3fdb-4496-9fa0-de8aa0a2d625 | checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
578f4e7d-658a-43de-a1f9-767fe4fab19c | checkpoint | Sliding doors - panels are adjusted and locking easily
3ed17202-d703-49fb-a2d0-ee08e76166fa | checkpoint | Sliding doors - Strikes are adjusted
e6b8f241-af22-48a2-9cd6-e733cab1fe03 | checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
86b45a0b-f4af-45b9-a484-82acb5397c91 | checkpoint | Proper spacing and clearances are maintained around the window units.
c8d63ab1-1c79-45f3-9bae-4c1727acabfc | checkpoint | Fasteners used are correct in type, size, and spacing
fdbf3e3a-471d-40aa-aa47-49482f8116aa | checkpoint | End Caps Installed
97e3cbf2-3749-4a1b-b18a-ac6a6d2bdf41 | checkpoint | Frames installed correctly?
3d412e88-eedf-4a96-8262-c1d3ab64d725 | checkpoint | Modules installed correctly?
1272d03c-b5d2-4765-9e03-8551476b5c10 | checkpoint | Drains are not blocked
de2b93ea-22bb-47c6-ade9-73d333e1ad6e | checklist | Ω (DEPRECATED) Shopfront - Install Checklist (v0) |  | Shopfront - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
0700aeb0-3f45-4ff4-86b6-ab6c0cca4433 | checkpoint | Has the window/door installation been completed?
22636621-414f-4893-805e-6546b06e46a3 | checkpoint | Is interior sealants installation neat and continuous.
96bda80c-2631-46dd-b88a-8700430c61af | checkpoint | Is exterior sealants installation neat and continuous.
1eaae647-cd3a-495c-bfaf-d343f4748ed0 | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
0e43a742-3a62-4536-bba5-6531d0c7cc38 | checkpoint | Is head flashing installed per plans and as detailed in the shop drawings?
a0ec81ba-aad0-45a3-b1ee-18c2bcb2a02b | checkpoint | Are all window and doors working?
42c68b8c-0e27-4059-bef0-6566302122e5 | checkpoint | All handles installed correctly?
379cee60-3b3c-467d-bcaa-bcba2e9568df | checkpoint | Are all the hardware installed correctly?
417260e6-16f7-45c1-a701-98c28a5bdc41 | checkpoint | Is the joinery free of scratches?
8cfd618e-f177-497b-a8be-9c4d39b0f6fd | checkpoint | Is the joinery clean and tidy?
e6c1ed45-68bd-4f4e-9bf1-0b59885eddfd | checkpoint | Hinge doors strikes adjusted and locking easily
a0daa382-e0e6-48da-8217-402769e86259 | checkpoint | Hinge doors 4 or 3 point lock operate easily
822dd074-b742-42db-827e-3571d39ed6ab | checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
666f9ec9-82dd-4103-9aa8-5929c3ee6e2f | checkpoint | Sliding doors - panels are adjusted and locking easily
50d83164-a9e4-4566-9e3b-901f3c128573 | checkpoint | Sliding doors - Strikes are adjusted
c056892f-b32d-4cb0-9f45-9f419004a094 | checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
26957168-637e-4581-8159-c74e9bc1ae3f | checkpoint | Proper spacing and clearances are maintained around the window units.
ba37aef7-e674-4dae-91a7-b9772dfcabb5 | checkpoint | Fasteners used are correct in type, size, and spacing
3effd75a-f577-4aea-b04b-33c7c876f7af | checkpoint | End Caps Installed
266b9389-c9ca-4e57-a127-9692e9ba0d65 | checkpoint | Frames installed correctly?
103a2da0-4f87-42d6-bda7-f4838b94b6a3 | checkpoint | Modules installed correctly?
06602471-2c7a-4dbe-ae01-a26237ed3225 | checkpoint | Drains are not blocked
3d535cfb-bc36-4f94-9bb8-4e326e6213f4 | checklist | Ω (DEPRECATED) Structural Glaze - Install Checklist (v0) |  | Structural Glaze - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
a6202c1a-9c75-45da-a7c8-ccfc043b41f5 | checkpoint | Has the window/door installation been completed?
9fee5fee-7e56-46a6-88fd-b338d4c3ec96 | checkpoint | Is interior sealants installation neat and continuous.
4cbb0e8d-4f4e-42e2-8ff3-bedbd52e203b | checkpoint | Is exterior sealants installation neat and continuous.
0376e0c5-35ed-48bd-8f19-41fa56d3f04a | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
05ad11a6-49e8-46a3-be38-348225650450 | checkpoint | Is head flashing installed per plans and as detailed in the shop drawings?
97243724-972f-4547-9c8e-7f73539e74ba | checkpoint | Are all window and doors working?
88435f8a-0f42-4cd3-ad70-8b3aa6902004 | checkpoint | All handles installed correctly?
894c7133-66a1-4306-85fe-6682a0e3a3f8 | checkpoint | Are all the hardware installed correctly?
d2bc6cb7-003b-489a-bd87-1c05e5b360a5 | checkpoint | Is the joinery free of scratches?
797af926-95d9-4274-8060-87005ff313bf | checkpoint | Is the joinery clean and tidy?
1084587b-8fe8-412c-9c62-dabdb51524f8 | checkpoint | Hinge doors strikes adjusted and locking easily
39f25609-dc9d-49de-9171-9a5ca9d832bb | checkpoint | Hinge doors 4 or 3 point lock operate easily
1f531f2c-debf-4f11-bd51-531b52f107a7 | checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
787bb37f-5f97-47d4-819c-3c66ea9cd595 | checkpoint | Sliding doors - panels are adjusted and locking easily
22f65642-8ba8-4803-b604-3ef3b34921d8 | checkpoint | Sliding doors - Strikes are adjusted
f7f999bc-7bbb-49d0-b610-b7de4afca181 | checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
3f174e56-5da8-4cc3-8ecc-45f6da79cc76 | checkpoint | Proper spacing and clearances are maintained around the window units.
b6805a9f-92bb-48bc-b931-fc0934f76ace | checkpoint | Fasteners used are correct in type, size, and spacing
afabb51f-106a-41fb-a75e-e2a166b56a26 | checkpoint | End Caps Installed
fa1811a2-5f98-416f-acbb-cae7e2184665 | checkpoint | Frames installed correctly?
6cfc2547-36f3-450b-963d-e9b0ddb415b4 | checkpoint | Modules installed correctly?
08848229-d398-4494-a945-75f3eab64de7 | checkpoint | Drains are not blocked

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
c41960ff-8759-4060-a148-eacff8c4ef39 | checklist | Liners |  | Liners
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
27bf5284-fc84-45e5-8a48-e02327b65c0d | checkpoint | Primed liners
be8ddaa9-da64-4509-b9bc-d2b3d9aa7095 | checkpoint | Sealant between the liners & frame
e1bd8eb4-5b7a-41d6-a493-827d02ff8e6c | checkpoint | Staple distance
f1de1d64-f0cc-4a02-bc72-4cd9c70058ba | checklist | Manufacturing |  | Manufacturing
c1c1b930-9b27-401c-beee-d5650ffa14b1 | section | Details
d6ad0ddc-ed9d-4d58-95fb-12e0ffa48b37 | checkpoint | Manufacturing Complete
223be225-1539-5814-9d0f-37185df91192 | button | Item free of defects and damages | PASS,FAIL,N/A
f97463e1-81f4-555a-a76e-853dddff9752 | button | Item is clean - No pencil marks / dirt / excessive sealant | PASS,FAIL,N/A
e872bae2-8287-593c-899a-f19c9e25c551 | button | Item is clearly labelled in accordance with fabrication sheets | PASS,FAIL,N/A
28ac2dc1-02b6-5075-882e-234c90e14024 | button | Item is square - Frame / Sashes / Panels | PASS,FAIL,N/A
029493af-023f-419f-b311-272f26c83d30 | checkpoint | Sealant is correct colour
1b079fa2-06ab-4b69-b3a0-7373454504a8 | checkpoint | Beads / Thresholds / Infills correct length
efcd4967-5075-430d-8de4-f32b8e17bffc | checkpoint | Mitres flush
9d81ea38-4c5d-4bda-8e52-4b42d9923f0b | checkpoint | Drainage correct as per APL manufacturing pack and aligned
c5bff0ce-77f1-5f10-bfb2-e565231d4e5f | button | Liners - TWT Measured / Correct Liner / Staples every 150 - 200mm | PASS,FAIL,N/A
84143131-f70d-4afd-886a-13f4942b3fc4 | checkpoint | Rubbers continuous and free of damage - not pinched under glass / foam
c5e2a167-2dcd-56e1-a925-928802a7e5b3 | button | Fin Mullions painted | PASS,FAIL,N/A
8d79e3cf-2c89-5844-ae45-1e8505e2cfd1 | button | Sealant tidy on frame where sash is present | PASS,FAIL,N/A
d1b632f4-5f21-57a5-b1aa-e37b4d520dc5 | button | Glass inspection done - Clean / Correct type / No defects | PASS,FAIL,N/A
a645e4b1-7f2b-5f19-9e93-4022a7c599ce | button | Glazing done correctly - No movement / correct glazing rubber | PASS,FAIL,N/A
04bf48cf-06a9-58cf-bfdb-9f367e844616 | button | Bungs / Caps fitted | PASS,FAIL,N/A
c323b1cb-245e-516b-a7d5-08b923247f05 | button | Support Blocks fitted | PASS,FAIL,N/A
12e8a50a-ed4b-559f-aed7-841a4fefb04e | button | Transport Blocks between panel and frame | PASS,FAIL,N/A
52109fd5-ee01-5fd9-a7ec-56c988b710a5 | button | Protective tape on bottom sill | PASS,FAIL,N/A
0195f25a-b06b-5fc8-902f-ad8cec44f140 | button | Overall item dimensions correct | PASS,FAIL,N/A
50e86fac-d844-48d5-950d-9c3cac8430e1 | checkpoint | Correct Windzone sticker applied
87736ec4-51a5-568b-8225-3d1c26c824ed | button | Item match drawing | PASS,FAIL,N/A
a98b7d14-af15-5c3b-ae03-d4fd199b5a6f | button | Commenst on jobsheets followed | PASS,FAIL,N/A
446d4093-257c-509c-94dd-520fe2b8e27d | button | Machining done as per assembly sheet | PASS,FAIL,N/A
c39867c9-554d-5210-a132-e5a00227446a | button | Correct Hardware fitted as per jobsheet | PASS,FAIL,N/A
f796dd1e-9c5c-42ca-8a13-23ca3c63c6ce | checkpoint | Soaker correctly fitted
cf79fc62-6a85-4951-a604-08504cb1e75d | checkpoint | Sillsafe applied correctly
89e33519-43f5-56a2-9534-5616164f428e | button | Soaker correctly fitted over sillsafe ends | PASS,FAIL,N/A
9cc45f57-d4ec-4fa7-a6b2-c8bb60952b7d | checkpoint | Foam tape fitted to sill fixed leg
7153cdbc-6924-5e03-b9c0-b99dafa04503 | button | Top & Bottom Screws sealed | PASS,FAIL,N/A
af219e47-1478-57ed-b812-61d92a8764db | button | Screws fitted to all hardware & components | PASS,FAIL,N/A
ef773e3f-79e1-584f-b4b6-165901e0d03d | button | Glazing Platform fitted (TH Frames) | PASS,FAIL,N/A
e25c0629-4b2a-5fa1-8f06-f072ac7783fe | button | Seal between liners - Correct application | PASS,FAIL,N/A
8c08b59a-6979-5b8b-87ba-4549064e1487 | button | Tracks / Stoppers fitted correctly | PASS,FAIL,N/A
76a95d22-45d6-5c9e-9cab-58412fb69bc5 | button | Sashes / Panels opening and closing correctly | PASS,FAIL,N/A
ddadb77f-d449-573c-97f2-854ff36d6b1a | button | Handles facing the right way and are not lose | PASS,FAIL,N/A
52c91d44-e24f-5439-a685-9907d7d55403 | button | Strikes fitted - Item locks / unlocks freely | PASS,FAIL,N/A
7b3e6f0b-5916-5149-b708-d1843f5a4106 | button | All hardware operational | PASS,FAIL,N/A
fc3588f5-57be-4cf5-b571-bcb176c16d16 | checkpoint | Protective tape on handle - Key taped to inside of handle
931865be-c19e-4525-bd10-5aa458e73725 | checklist | Ω (DEPRECATED) Metro-Resi - Install Checklist (Proposed Remedial Works) (v1) |  | Metro-Resi - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
1e38e5d1-a940-4d30-9d04-d3d0944b3049 | checkpoint | Has the window/door installation been completed?
63fd56ea-52ea-4539-b89a-8c8cf4a54aa9 | checkpoint | Fixings & Centres as per the PS1 requirements
15d86b81-22b1-40bb-b363-78bcf5251bdd | checkpoint | Is interior sealants installation neat and continuous.
734c4d01-1eb6-4703-a72c-c0676b893938 | checkpoint | Is exterior sealants installation neat and continuous.
e95fdb1b-5f5d-4e02-bfde-a577e80406b3 | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
05062682-c46c-4aa6-9691-a66883b08e60 | checkpoint | Is head flashing installed per plans and as detailed in the shop drawings?
1ac637c8-42e4-4250-a2c0-69f666aa3ca3 | checkpoint | Are all window and doors working?
64a780c2-a706-4c42-acae-45d5d2bff3a0 | checkpoint | All handles installed correctly?
02289cc4-6145-4d39-9770-36a0e2cc761e | checkpoint | Are all the hardware installed correctly?
613555d4-3e95-4638-ad39-12254cb24c1b | checkpoint | Is the joinery free of scratches?
d03bcce2-498f-4eef-bf7f-3025eb56dd2a | checkpoint | Is the joinery clean and tidy?
aa554910-b46f-46a6-805a-213fbc0be141 | checkpoint | Are Restrictor Stays fitted(Fully Fixed off & Silent operation)
f86b558b-0027-4be9-b6f7-9d3186865540 | checkpoint | Hinge doors strikes adjusted and locking easily
f0847ce3-462a-4375-926b-9e66e06636ef | checkpoint | Hinge doors 4 or 3 point lock operate easily
1f8bc687-2964-4f76-ad06-bf5f6f0bbe78 | checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
b370a481-cb6d-4d73-8d26-4348047986d8 | checkpoint | Sliding doors - panels are adjusted and locking easily
b2a3284f-8780-43c5-ba75-a64fc0303673 | checkpoint | Sliding doors - Strikes are adjusted
2483bfed-b334-456d-80c4-9830797fce2a | checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
9e049ba8-74b8-44b6-bf94-4a1b582c311a | checkpoint | Windows open, close, and lock smoothly without excessive force.
ee6a584c-a1e1-4e11-8bae-8514cf53cc1d | checkpoint | All operable windows have functional hardware (locks, latches, etc.)
c2e3e616-8256-4f2d-b286-0839b26f480a | checkpoint | Proper spacing and clearances are maintained around the window units.
1feca60b-b419-4e9f-8d10-f1fc00485b1d | checkpoint | Fasteners used are correct in type, size, and spacing
5c35c7db-7c8d-4f3a-b5ba-f602486cc2d0 | checkpoint | End Caps Installed
05ae1412-e741-433b-b5f6-e748f23d3445 | checkpoint | Frames installed correctly?
ea22cfcb-e6e9-4489-8e68-a5dd90034e40 | checkpoint | Drains are not blocked
22ab04d3-ff51-43af-a23e-7d6d1b2eedc7 | checklist | Ω (DEPRECATED) Metro-Resi - Install Checklist (Stage 1-3) (v1) |  | Metro-Resi - Install Checklist
755e85d5-2589-476b-8e54-5853a61e61ad | section | Details
54c9f95a-7308-4943-aae2-e30561317ecf | checkpoint | Has the window/door installation been completed?
b8cfe6c2-6353-4899-b236-c2855f5dd3ee | checkpoint | Fixings & Centres as per the PS1 requirements
9acd8c5c-a49e-4214-8f4b-3a224482b729 | checkpoint | Is interior sealants installation neat and continuous.
ed377c18-f19e-4c1a-a5f6-e93c3bd2ae22 | checkpoint | Is exterior sealants installation neat and continuous.
f45f757c-6faa-488e-ae62-e65feb48850f | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
b06f6f8d-8af3-493e-8179-5951048a7f12 | checkpoint | Is head flashing installed per plans and as detailed in the shop drawings?
40654a6a-c98a-454e-a35c-cb456c5dd551 | checkpoint | Are all window and doors working?
46b959fb-8858-4569-9352-b1ca2f38997e | checkpoint | All handles installed correctly?
acedbeb7-7cee-4142-b50f-df03ec44d71c | checkpoint | Are all the hardware installed correctly?
f25936a2-e1a7-40d0-b623-803ffaf54d73 | checkpoint | Is the joinery free of scratches?
9e1eddf3-d0da-4f97-9688-eb820abe8e4b | checkpoint | Is the joinery clean and tidy?
ffbe10d9-01c9-4fcf-8ed0-d3e15514cfe1 | checkpoint | Are Restrictor Stays fitted(Fully Fixed off & Silent operation)
d9a3f23e-186b-4cd9-a499-284424e06436 | checkpoint | Hinge doors strikes adjusted and locking easily
eda24a77-8785-4e60-b391-a7353bd3bc16 | checkpoint | Hinge doors 4 or 3 point lock operate easily
5dc691b0-f2d3-4bd9-9774-9df6a281a77f | checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
c70e1b19-6cf6-4169-946e-cd67a55e72cd | checkpoint | Sliding doors - panels are adjusted and locking easily
23613ccf-a259-4ffa-8b35-8ca141e5b3fd | checkpoint | Sliding doors - Strikes are adjusted
06318e87-ec16-4447-b0b3-124317ac3f9f | checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
35439dbb-d017-4710-948e-3bb6812f5ceb | checkpoint | Windows open, close, and lock smoothly without excessive force.
a19fbf32-7fc0-44bb-a8c0-a69d4c9901b3 | checkpoint | All operable windows have functional hardware (locks, latches, etc.)
759a6ef0-c4fe-405a-8206-dfd0bce29e78 | checkpoint | Proper spacing and clearances are maintained around the window units.
30e99728-b9d9-4520-afe7-7eb1a825bd18 | checkpoint | Fasteners used are correct in type, size, and spacing
d7de0464-2e43-4ef2-aebb-4d8d1cf3fae1 | checkpoint | End Caps Installed
9820b70a-4455-493b-b875-4dfc24f4eb46 | checkpoint | Frames installed correctly?
abe57fd8-5e80-4ee6-a49f-6b4ba96c5be3 | checkpoint | Drains are not blocked