## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-124-STR-BRUNT-Waterproofing - Bridge Deck CJ
ITP Description: |  | Waterproofing - Bridge Deck CJ
Discipline (e.g. CIV/STR/RAIL: |  | STR
Revision Number: |  | 0
Revision Date: |  | 2024-01-24
ITP created by: |  | Yasna Naicker
ITP approved for use by: |  | Jon De Castro
Special Notes to ConQA Team : |  | ITP for Brunt Road Project Only
Inspection & Test Plan - Waterproofing - Bridge Deck CJ
|  |  | Doc No.: ITP-124-STR-BRUNT-Waterproofing - Bridge Deck CJ | [5 empty] | Revision: | 0
[9 empty] | Date: | 2024-01-24
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 660 January 2018 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VicRoads Section 691 November 2018 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | AC-AR Installation Guide | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries-Materials
2.1 | Waterproofing Membrane System Materials | VR 691.05 VR 691.07 | Certificate from the manufacturer in the form of a guarantee confirming that the waterproofing system and materials comply with the requirements of this section, including a guaranteed in-service performance of not less than ten (10) years from the date of installation. Submit Certificate of Conformity, including all relevant test results shown in Table 691.071 and Table 691.072, verifying conformity of the supplied materials for every lot/batch delivered, to be submitted for review to the Nominated Authority. Enter: Teambinder Approval Number [free text box] | Document Review | Prior installation | HP | Nominated Authority | ConQA HP Release
3 | Preliminaries-Procedures
3.1 | Waterproofing System installation Procedures | VR 691.04 | Details of proposed procedures and surface preparation in accordance with clause 691.08 to be submitted for review to the Nominated Authority. Waterproofing works shall not take place until the Contractor's proposed materials and procedures and surface preparation in accordance with clause 691.08 have been reviewed and accepted by the Superintendent. Enter: Teambinder Approval Number [free text box] | Document Review | Prior installation | HP | Nominated Authority | ConQA HP Release
4 | Pre-construction Activities
4.1 | Material Handling and storage | VR 691.15 | Where applicable the joint material including joint sealant shall match the drawings or be an equivalent product All material shall be brought to site in the original preformed rolls or unopened cans clearly labelled with the manufacturer’s name, product type, reference and batch numbers. The Contractor shall provide a certificate from the manufacturer for each batch of waterproofing membrane and primer material confirming: (a) manufacturer’s name and address (b) product reference (c) batch number of identification (d) quantity manufactured in the batch (e) date of manufacture. All waterproofing membrane materials to be used on the works shall be free from contamination, gelling, drying out, heavy skin formation and severe segregation of ingredients. Attach Delivery dockets/Proof of purchase | Document Review/ Inspection | When applicable | IP | PE/SPE | This ITP Signed Off
5 | Construction Activities
5.1 | Surface Preparation | 691.08 (a) and(b) | The surface preparation shall be in accordance with the manufacturer’s recommendations for the waterproofing membrane system to be applied and as specified in this section. Concrete surfaces to which the waterproof membranes are applied shall be dry, clean, sound and free of dust or loose particles. | Visual Inspection | Befor Primerbeing applied | IP | SE/PE | This ITP Signed Off
5.2 | Primer application | 691.08 (c ) | Primers shall be applied by brush, mop, broom or spray in accordance with the manufacturer's recommendations. | Visual Inspection | When applicable | IP | SE/PE | This ITP Signed Off
5.3 | Environmental Conditions | 691.14 | Waterproofing systems shall not be applied under any of the following conditions: (a)windy conditions where over spray and/or spatter may be generated (b)when wind-borne debris is likely to contaminate the uncured surface of the freshly applied membrane (c)when the ambient temperature exceeds 35°C or is below 10°C unless otherwise expressed in writing by the manufacturer (d)when the relative humidity exceed 85% or where it may be expected to exceed 85% during the subsequent 12 hour curing period (e)when rain spatter contaminating the surface and adversely affecting the adhesion to the substrate (f)when the substrate surface is wet or damp, (g)the surface temperature of the substrate exceeds 40°C. | Visual Inspection Measure | Prior installation | IP | SE/PE | This ITP Signed Off
5.4 | Waterproofing membrane application | 691.09 (a) | All concrete surfaces to receive a waterproofing membrane shall be dry at the time of application. The waterproofing membrane system shall be applied within 24 hours unless otherwise expressed in writing by the manufacturer after the preparation of the concrete surface. The prepared surface shall be protected against contamination and rain or expected rain if the waterproofing is not undertaken within 24 hours. | Visual Inspection | Prior installation | IP | SE/PE | This ITP Signed Off
5.5 | Waterproofing membrane application | 691.09 (c ) | Placement of preformed sheets shall commence at the lowest section and proceed to higher sections, so that water does not flow into any joints during service. The Contractor shall ensure compliance with the manufacturer's recommendations for heating method, duration of heating and temperature of oxidised bitumen adhesives. | Visual Inspection | When applicable | IP | SE/PE | This ITP Signed Off
5.6 | Waterproofing membrane application | 691.09 (c ) | Self-adhesive membranes shall be rolled out and manual pressure applied immediately to ensure satisfactory adherence to the concrete deck. | Visual Inspection | When applicable | IP | SE/PE | This ITP Signed Off
5.7 | Waterproofing membrane coverage | 691.09 (d) | Coverage of the waterproofing membrane must be continuous over the entire deck area, including service bays, between parapets, medians and kerbs. The layout of the waterproofing membrane shall be detailed such that water seepage beneath the membrane is prevented, | Visual Inspection | When applicable | IP | SE/PE | This ITP Signed Off
5.8 | Waterproofing membrane coverage | 691.09 (d ) | At the junction with vertical concrete surfaces, the membrane shall continue up the vertical concrete surface, terminating at a level 10 mm below the top level of the proposed asphalt surface. | Visual Inspection | When applicable | IP | SE/PE | This ITP Signed Off
5.9 | Waterproofing membrane coverage | 691.09 (d ) | The waterproofing membrane shall be applied with minimum side and end overlaps of 100 mm and 150 mm respectively. | Visual Inspection | When applicable | IP | SE/PE | This ITP Signed Off
5.10 | Tack Coat | 691.05 (f) | Tack coat shall be applied as required, in accordance with the manufacturer’s recommendations to provide adequate adhesion of asphalt to the waterproofing membrane over its service life. The tack coat shall be applied uniformly to the waterproofing membrane | Visual Inspection | When applicable | IP | SE/PE | This ITP Signed Off
5.11 | Drying and curing | 691.13 | The Contractor shall adhere to the manufacturer’s instructions regarding drying and curing requirements, and overcoating time intervals, for the prevailing weather conditions. | Inspection | When applicable | IP | SE/PE | This ITP Signed Off
6 | Post-construction Activities
6.1 | Subcontractor Product warranties obtained | 691.05 | Product warranties obtained and are compliant with 691.05 Attach: Copies of product warranties | Inspection Document Review | Once per Lot | WP | SE/PE | This ITP Signed Off
6.2 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP Signed Off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /