## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-130-CIV-BRUNT-Guard Rail Supply and Installation Rev.0 | itp |  |  |  | Yes | ITP-130-CIV-BRUNT-Guard Rail Supply and Installation Rev.0
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-130-CIV-BRUNT-Guard Rail Supply and Installation
label | ITP Description: Guard Rail Supply and Installation
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 25/01/2024
label | ITP created by: Yasna Naicker
label | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Non Dependent
label | Reference - VicRoads Section 708 July 2023
checkpoint | 1.2 - Non Dependent
label | Reference - VicRoads Section 703 Aug 2021
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Accepted Products and material confirmation
label | Reference - VicRoads Spec. Cl.708.04
label | Acceptance Criteria - Only safety barrier products listed in VicRoads Road Design Note 06-04 shall be used.
label | ○ Check design drawing for correct type of barrier, transitions and/or end connection and any additional material component requirements
label | Attach: TeamBinder HP Reference No.
label | Method - Document Review
label | Frequency - Each member material component
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Obtain and submit Material Test Certificate of Compliance for the barrier systems
label | Reference - VicRoads Spec. Cl.708.05(b & c) and Cl.708.10 AS/NZS 1594, AS1627, AS 4680 ISO/IEC 17025 a
label | Acceptance Criteria - The properties of all steel for the Works shall be evidenced by test certificates
label | ○ Laboratories that perform tests required by this Section shall meet the requirements of AS ISO/IEC 17025
label | ○ W-beams and terminal sections shall comply with AS/NZS1594 Grade HA350.
label | ○ Steel posts and blocks shall comply with AS/NZS1594 Grade HA250. Treated in accordance with AS1627- Parts 1 & 4. All test reports shall be endorsed in accordance with the AS ISO/IEC 17025 accreditation for that laboratory.
label | Attach: TeamBinder HP Reference No.
label | Method - Document Review
label | Frequency - Min 14 days prior to commencing, 1 per 1000m of material
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - CERTIFICATE OF COMPLIANCE
label | Reference - VicRoads Spec. Cl.708.10
label | Acceptance Criteria - July 2023 individuals which install, repair, and maintain road safety barriers and terminals, and are accredited under the Austroads Safety Hardware Training and Accreditation Scheme (ASHTAS). July 2024 all barrier and terminal installations, maintenance and repairs must be done by an Austroads Safety Hardware Training and Accreditation Scheme (ASHTAS) accredited individual. Individuals shall be accredited under the ASHTAS and for the product which is being installed, repaired or maintained.
label | Attach: TeamBinder HP Reference No.
label | Method - Document Review
label | Frequency - Min 14 days prior to commencing, 1 per 1000m of material
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Verification of Protective treament/ galvanisation records
label | Reference - VicRoads Spec. Cl.708.05(d)
label | Acceptance Criteria - Unless stated otherwise in the manufacturer’s recommendations, the surfaces of all ferrous metal components including posts, blocks, beam elements, anchor plates, connectors and end treatment pieces must, after fabrication, be treated in accordance with the requirements of AS 16–7 Parts 1 and 4, and finished by hot-dipped galvanising in accordance with AS/NZS 4680.All galvanised coatings shall be smooth, adherent and free from stains, gross surface imperfections, markings, brand names and/or inclusions.
label | ○ Hot-dipped galvanised coating on bolts, nuts and washers shall comply with AS 1214.
label | ○ Where the galvanising on guard rail or associated fittings has been damaged, the coating shall be repaired by regalvanising or by painting with a minimum of two coats of a zinc rich inorganic paint in accordance with AS/NZS 3750.9 and one coat of aluminium paint.
label | Attach: TeamBinder HP Reference No.
label | Method - Document Review
label | Frequency - Min 14 days prior to commencing, 1 per 1000m of material
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Concrete mix design
label | Reference - VicRoads Spec. Cl.703, Cl.708.05(g) AS1379
label | Acceptance Criteria - Concrete to comply with the requirements of AS 1379 and VicRoads Section 703, for either:
label | (i) Portland cement-based concrete, N20 strength grade, or
label | (ii) Geopolymer binder-based concrete, 20 MPa strength grade.
label | The use of chemical admixtures shall comply with the requirements of Section 703.
label | Attach: TeamBinder HP Reference No.
label | Method - Document Review
label | Frequency - Min 14 days prior to commencing, 1 per 1000m of material
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Identification of guard fence components
label | Reference - VicRoads Spec. Cl.708.05 (a)
label | Acceptance Criteria - Mark on any steel w-beams, posts at both ends and all plastic components of proprietary end treatments unobtrusively and permanently in text not more than 20 mm high, the following information:
label | (i) name of the manufacturer
label | (ii) batch number, or date of manufacture
label | (iii) strength grade and base metal thickness of the steel w-beams.
label | Method - Visual
label | Frequency - Each member material component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
section | 3. Preliminaries - Documents & Procedures
checkpoint | 3.1 - Subcontractor Installation Procedure and Inspection & Test Plan (where applicable)
label | Reference - IFC Drawings
label | Acceptance Criteria - Subcontractor Installation Procedure and ITP shall conform with the IFC Drawings & Relevant Standards & Specifications.
label | Attach: Approved Subcontractor Work Procedure and ITP
label | Method - Document Review
label | Frequency - Each Lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQa HP Release
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-Construction Activities
checkpoint | 4.1 - Survey Set-out
label | Reference - IFC Drawings
label | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table VR610.464 (February 2020) / 610.473
label | Attach: Survey As-builts / Survey Report
label | Method - Measure, Visual
label | Frequency - Prior to Commencing Excavation
label | Category - HP*
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
section | 5. Construction Activities
checkpoint | 5.1 - Obtain approval of location and length
label | Reference - VicRoads Spec. Cl.708.08 IFC Drawings
label | Acceptance Criteria - The required location and length of all guard fence shall be confirmed with the Superintendent.
label | Attach: TeamBinder HP Reference No.
label | Method - Measure, Visual
label | Frequency - Prior to Installation
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - W-beam barrier system where non standard post lengths are used
label | Reference - VicRoads Spec. Cl.708.08 IFC Drawings
label | Acceptance Criteria - Prior to installation of any w-beam barrier system where non-standard post lengths are required or shallow concrete foundations are proposed to be used, the Contractor shall provide details of the measures proposed and evidence that the effectiveness of the barrier system will be maintained.
label | ○ Where shallow foundations that require a concrete ground beam are proposed to be constructed, the design shall be proof engineered by a Department of Transport and Planning appropriately prequalified consultant.
label | Attach: TeamBinder HP Reference No.
label | Method - Document Review
label | Frequency - Prior to Installation
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Install posts, rails and terminations
label | Reference - IFC Drawings VicRoads Spec. Cl.708 .07(a & d ) IFC Drawings
label | Acceptance Criteria - Posts shall be installed to the depth, line and spacing shown on the drawings, and to the tolerances in clause 708.08(d).
label | Posts shall be installed by driving, provided there is no distortion or damage which may reduce their effectiveness. The installation must not cause any damage to the pavement beyond 100 mm from any part of any post
label | If posts cannot be driven, then the posts shall be installed in holeswith a 75 mm minimum clearance from the back of the post to the face of the hole.
label | Post holes in rock shall be backfilled with granular material, that is firmly compacted in layers not exceeding 100 mm compacted thickness. Where posts are located in areas to be paved, the backfilling of the post holes shall be finished 50 mm below the underside of such paving and the remaining depth of the holes compacted with material similar to the surrounding material.
label | W-beam guard fence shall be erected to the following tolerances:
label | (i) Variation from true plan position of posts ±20 mm
label | (ii) Variation of line of w-beams from specified vertical profile ±10 mm
label | (iii) Variation of w-beams from specified horizontal alignment ±20 mm
label | (iv) Variation of posts from vertical (measured at top of the post) ±15 mm
label | (v) Orientation of block and/or post to w-beam +0 mm, -15 mm (measured at the point of greatest offset between the block or post to the w-beam)
label | (vi) Dimension of holes -0 mm, +50 mm
label | (vii) Top of bolt head relative to w-beam -0 mm, +5 mm
label | ○ After installation the top of the rail shall be within 25 mm of the specified level and 50 mm of the specified line. Variations from specified line and level shall not occur at a rate exceeding 15 mm in any 5 m length.
label | ○ Guard fence shall be installed at the offsets shown on Standard Drawing SD 3502. The desirable level shall be adopted unless otherwise approved by the Superintendent. Posts shall be installed such that the back of post is not less than 500 mm from hinge point
label | Method - Measure, Visual
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.4 - Construct crushed rock base for maintenance strip
label | Reference - VicRoads Spec. Cl.708 .11, Cl.812
label | Acceptance Criteria - All bedding material used for cast in place concrete construction works shall be in accordance with Section 812 for Class 3 Crushed Rock.
label | Method - Measure, Visual
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.5 - Construct concrete maintenance strip
label | Reference - VicRoads Spec. Cl.708.12a, Cl.708.5g, Cl.703.11
label | Acceptance Criteria - The concrete maintenance strip shall be placed parallel to the barrier, such that it extends a minimum of 300 mm clear of the rear of the post and 300 mm clear from the face of w beam. It shall be constructed with minimum 2% crossfall away from the road
label | ○ The concrete maintenance strip shall consist of 75 mm depth of N20 strength grade portland cement-based concrete or 20 MPa geopolymer binder-based concrete conforming to the requirements of clause 708.05(g), on 75 mm of compacted Class 3 crushed rock.
label | Method - Measure, Visual
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
section | 6. Post-construction Activities
checkpoint | 6.1 - Delineators
label | Reference - VicRoads Spec. Cl.708.11, Cl.703.12
label | Acceptance Criteria - The Contractor shall supply and fasten delineators to the top of the w-beam, comprising flexible plastic mounting brackets fitted with 100 cm2 of Class 1A retro-reflective material, as defined in AS/NZS 1906.2. These shall be installed in accordance with VicRoads Traffic Engineering Manual Volume 2.
label | Red delineators on the left side of one-way and two-way roadways;
label | ○ white delineators on the right side of two-way roadways; and
label | ○ yellow delineators on the right side of one-way roadways.
label | – Delineators shall not be installed on guard fence when the barrier offset is greater than 4 m from the traffic lane. White guide posts with delineators shall be installed in accordance with VicRoads Traffic Engineering Manual Volume 2 Part 2.02 clause 4.2.4 – Guide Posts (TEM Vol 2 Part 2.02).
label | Method - Visual, Document Review
label | Frequency - Once, immediately following the installation and prior to any Work commencing on the members
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | 6.2 - Existing Sign & markings Reinstatement
label | Reference - VicRoads Spec. Cl.708.17 IFC Drawings
label | Acceptance Criteria - The Contractor shall reinstate all signs to a standard not less than the pre-existing condition and to the satisfaction of the Superintendent
label | Method - Document Review
label | Frequency - Each element
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | 6.3 - Compliance Audit of Safety Barrier System Installation
label | Reference - VicRoads Spec. Cl.708.10
label | Acceptance Criteria - A safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract shall be undertaken and a report prepared by the Australian Licensed Supplier of the safety barrier system.
label | ○ A Certificate of Compliance(CoC) shall be provided certifying that the products have installed in accordance with the manufactures installation Manual and specifiction for each end treatment installed.
label | ○ A signed copy of the manufacturer’s Installation Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual shall be completed and submitted to the Superintendent..
label | Method - Visual, Document Review
label | Frequency - Each bridge beam
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.4 - Survey data captured for as-built purposes
label | Reference - IFC Drawings VicRoads Spec. Cl.708
label | Acceptance Criteria - As-built Drawings Tolerances as per VicRoads Specifications, Clause 708.
label | Method - Visual, Document Review
label | Frequency - Where applicable
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | 6.5 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP