## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-131-STR-BRUNT-Waterproofing - Bridge Deck CJ Rev.0 | itp |  |  |  | Yes | ITP-131-STR-BRUNT-Waterproofing - Bridge Deck CJ Rev.0
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-131-STR-BRUNT-Waterproofing - Bridge Deck CJ
label | ITP Description: Waterproofing - Bridge Deck CJ
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 0
label | Revision Date: 24/01/2024
label | ITP created by: Yasna Naicker
label | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Non Dependent
label | Reference - VicRoads Section 660 January 2018
checkpoint | 1.2 - Non Dependent
label | Reference - VicRoads Section 691 November 2018
checkpoint | 1.3 - Non Dependent
label | Reference - AC-AR Installation Guide
section | 2. Preliminaries-Materials
checkpoint | 2.1 - Waterproofing Membrane System Materials
label | Reference - VR 691.05, VR 691.07
label | Acceptance Criteria - Certificate from the manufacturer in the form of a guarantee confirming that the waterproofing system and materials comply with the requirements of this section, including a guaranteed in-service performance of not less than ten (10) years from the date of installation.
label | ○ Submit Certificate of Conformity, including all relevant test results shown in Table 691.071 and Table 691.072, verifying conformity of the supplied materials for every lot/batch delivered, to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval Number
label | Method - Document Review
label | Frequency - Prior installation
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA HP Release
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries-Procedures
checkpoint | 3.1 - Waterproofing System installation Procedures
label | Reference - VR 691.04
label | Acceptance Criteria - Details of proposed procedures and surface preparation in accordance with clause 691.08 to be submitted for review to the Nominated Authority.
label | ○ Waterproofing works shall not take place until the Contractor's proposed materials and procedures and surface preparation in accordance with clause 691.08 have been reviewed and accepted by the Superintendent.
textbox | Enter: Teambinder Approval Number
label | Method - Document Review
label | Frequency - Prior installation
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA HP Release
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-construction Activities
checkpoint | 4.1 - Material Handling and storage
label | Reference - VR 691.15
label | Acceptance Criteria - Where applicable the joint material including joint sealant shall match the drawings or be an equivalent product
label | ○ All material shall be brought to site in the original preformed rolls or unopened cans clearly labelled with the manufacturer’s name, product type, reference and batch numbers.
label | ○ The Contractor shall provide a certificate from the manufacturer for each batch of waterproofing membrane and primer material confirming:
label | (a) manufacturer’s name and address
label | (b) product reference
label | (c) batch number of identification
label | (d) quantity manufactured in the batch
label | (e) date of manufacture.
label | ○ All waterproofing membrane materials to be used on the works shall be free from contamination, gelling, drying out, heavy skin formation and severe segregation of ingredients.
label | ○ Attach Delivery dockets/Proof of purchase
label | Method - Document Review/Inspection
label | Frequency - When applicable
label | Category - IP
label | Responsibility - PE/SPE
label | Verifying Documents - This ITP Signed Off
section | 5. Construction Activities
checkpoint | 5.1 - Surface Preparation
label | Reference - 691.08 (a) and (b)
label | Acceptance Criteria - The surface preparation shall be in accordance with the manufacturer’s recommendations for the waterproofing membrane system to be applied and as specified in this section.
label | ○ Concrete surfaces to which the waterproof membranes are applied shall be dry, clean, sound and free of dust or loose particles.
label | Method - Visual Inspection
label | Frequency - Before Primerbeing applied
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.2 - Primer application
label | Reference - 691.08 (c )
label | Acceptance Criteria - Primers shall be applied by brush, mop, broom or spray in accordance with the manufacturer's recommendations.
label | Method - Visual Inspection
label | Frequency - When applicable
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.3 - Environmental Conditions
label | Reference - 691.14
label | Acceptance Criteria - Waterproofing systems shall not be applied under any of the following conditions:
label | (a) windy conditions where over spray and/or spatter may be generated
label | (b) when wind-borne debris is likely to contaminate the uncured surface of the freshly applied membrane
label | (c) when the ambient temperature exceeds 35°C or is below 10°C unless otherwise expressed in writing by the manufacturer
label | (d) when the relative humidity exceed 85% or where it may be expected to exceed 85% during the subsequent 12 hour curing period
label | (e) when rain spatter contaminating the surface and adversely affecting the adhesion to the substrate
label | (f) when the substrate surface is wet or damp,
label | (g) the surface temperature of the substrate exceeds 40°C.
label | Method - Visual Inspection, Measure
label | Frequency - Prior installation
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.4 - Waterproofing membrane application
label | Reference - 691.09 (a)
label | Acceptance Criteria - All concrete surfaces to receive a waterproofing membrane shall be dry at the time of application.
label | ○ The waterproofing membrane system shall be applied within 24 hours unless otherwise expressed in writing by the manufacturer after the preparation of the concrete surface.
label | ○ The prepared surface shall be protected against contamination and rain or expected rain if the waterproofing is not undertaken within 24 hours.
label | Method - Visual Inspection
label | Frequency - Prior installation
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.5 - Waterproofing membrane application
label | Reference - 691.09 (c)
label | Acceptance Criteria - Placement of preformed sheets shall commence at the lowest section and proceed to higher sections, so that water does not flow into any joints during service.
label | ○ The Contractor shall ensure compliance with the manufacturer's recommendations for heating method, duration of heating and temperature of oxidised bitumen adhesives.
label | Method - Visual Inspection
label | Frequency - When applicable
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.6 - Waterproofing membrane application
label | Reference - 691.09 (c)
label | Acceptance Criteria - Self-adhesive membranes shall be rolled out and manual pressure applied immediately to ensure satisfactory adherence to the concrete deck.
label | Method - Visual Inspection
label | Frequency - When applicable
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.7 - Waterproofing membrane coverage
label | Reference - 691.09 (d)
label | Acceptance Criteria - Coverage of the waterproofing membrane must be continuous over the entire deck area, including service bays, between parapets, medians and kerbs.
label | ○ The layout of the waterproofing membrane shall be detailed such that water seepage beneath the membrane is prevented,
label | Method - Visual Inspection
label | Frequency - When applicable
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.8 - Waterproofing membrane coverage
label | Reference - 691.09 (d )
label | Acceptance Criteria - At the junction with vertical concrete surfaces, the membrane shall continue up the vertical concrete surface, terminating at a level 10 mm below the top level of the proposed asphalt surface.
label | Method - Visual Inspection
label | Frequency - When applicable
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.9 - Waterproofing membrane coverage
label | Reference - 691.09 (d)
label | Acceptance Criteria - The waterproofing membrane shall be applied with minimum side and end overlaps of 100 mm and 150 mm respectively.
label | Method - Visual Inspection
label | Frequency - When applicable
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.10 - Tack Coat
label | Reference - 691.05 (f)
label | Acceptance Criteria - Tack coat shall be applied as required, in accordance with the manufacturer’s recommendations to provide adequate adhesion of asphalt to the waterproofing membrane over its service life. The tack coat shall be applied uniformly to the waterproofing membrane
label | Method - Visual Inspection
label | Frequency - When applicable
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.11 - Drying and curing
label | Reference - 691.13
label | Acceptance Criteria - The Contractor shall adhere to the manufacturer’s instructions regarding drying and curing requirements, and overcoating time intervals, for the prevailing weather conditions.
label | Method - Inspection
label | Frequency - When applicable
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
section | 6. Post-construction Activities
checkpoint | 6.1 - Subcontractor Product warranties obtained
label | Reference - 691.05
label | Acceptance Criteria - Product warranties obtained and are compliant with 691.05
label | Attach: Copies of product warranties
label | Method - Inspection Document Review
label | Frequency - Once per Lot
label | Category - WP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 6.2 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP