## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation | itp |  |  |  |  | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0
checkpoint-no-status | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation
label | Document Title: CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation
label | ITP Description: RSS Walls - Panel Installation
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 06/11/2023
label | ITP created by: Matthew Dib/Jason Quan
label | ITP approved for use by: Pradeep Talasila
checkpoint | 1 - Panels-survey set out-Tolerance
label | Reference: VR 682.20 IFC Drawings MRP-080-C-RFL-DRG-33-CPV-CSW-1001 and 1202 to 1205
label | Acceptance Criteria: Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
label | Method: Measure
label | Frequency: Base course panels
label | Category: IP
label | Responsibility: Surveyor/PE
label | Verifying Documents: This Checklist Signed-off
date | Date Completed:
checkpoint | 2 - Mark-up panel for construction team
label | Reference: Construction Manual
label | Acceptance Criteria: Mark number of strips per row on the back of each panel. Mark design location (Wall number, row and column) as per elevation drawings on the back of each panel
label | Method: Visual
label | Frequency: Each panel
label | Category: IP
label | Responsibility: SE
label | Verifying Documents: This Checklist Signed-off
date | Date Completed:
checkpoint | 3 - Panel installation
label | Reference: IFC Drawing:
label | ○ Instructions: MRP-080-C-RFL-DRG-33-CPV-CSW-2003
label | ○ Weephole Locations: MRP-080-C-RFL-DRG-33-CPV-CSW-1401, 1402, 1501, 1601 and 1701
label | ○ Archtectural pattern drawings: MRP-080-C-RFL-DRG-33-CPV-CSW-1404 ,1503, 1603 and 1703
label | Acceptance Criteria: RSS Panels are to be installed as per IFC Drawings and specified schedule.
label | – Check for correct architectural pattern
label | – Check for Weephole Locations
label | – Check the 1 in 40 slope is to be maintained
label | Method: Visual, Measure
label | Frequency: Each panel
label | Category: WP
label | Responsibility: SE
label | Verifying Documents: This Checklist Signed-off
date | Date Completed:
checkpoint | 4 - Bearing Pad Installation
label | Reference: IFC Drawing: Instructions: MRP-080-C-RFL-DRG-33-CPV-CSW-2003
label | Acceptance Criteria: 3X19mm bearing pads must be installed per panel - Centre of the outer bearing pads must be 200mm+/-10mm from the edge of the panel
label | – Check the 19mm nominal gap to be maintained
label | – Install 3 Bearing Pads at rear on top of panels
label | – Above must be checked with Surveyor prior to backfill
label | – Note bearing pads shall not be installed under base row panels
label | Method: Visual
label | Frequency: Each panel
label | Category: WP
label | Responsibility: SE
label | Verifying Documents: This Checklist Signed-off
date | Date Completed:
checkpoint | 5 - Panel installation-Abutment interfaces
label | Reference: IFC Drawings MRP-080-C-RFL-DRG-33-CPV-CSW-1106, MRP-080-C-SME-DRG-34-CPV-CSF-3023 and 3024
label | Acceptance Criteria: Panel installation and abutment interfaces
label | – 20mm nominal gap between panels and Abutment wall is to be mainatined
label | – 150mm wide x 6mm Folded Galvanized plates (Grade 250) drill and fix to as per IFC drawings with Galvanized M12x75 Long Excalibur screwbolts at 500 CTRS Typical each wall.
label | – 600mm wide BITAC tape installed
label | Method: Measure
label | Frequency: Where applicable
label | Category: IP
label | Responsibility: SE/PE
label | Verifying Documents: This Checklist Signed-off
date | Date Completed:
checkpoint | 6 - Filter fabric -Installation
label | Reference: IFC Drawings MRP-080-C-SME-DRG-34-CPV-CSF-2003 VR682.11
label | Acceptance Criteria: Install Filter Fabric against all vertical and horizontal joints
label | Method: Visual
label | Frequency: Each course of panel installation
label | Category: IP
label | Responsibility: SE
label | Verifying Documents: This Checklist Signed-off
date | Date Completed:
checkpoint | 7 - Drainage-Strip Drain
label | Reference: VR682.11
label | Acceptance Criteria: Install 300mm wide strip drain between precast wall panel vertical joints. Strip drain to be encapsulated by nonwoven geotextile in accordance with section 682.11 At every vertival joint between panels in RSS wall, ensure no gap is formed bewteen strip drian and RSS panels
label | Method: Visual
label | Frequency: Each course of panel installation
label | Category: IP
label | Responsibility: SE
label | Verifying Documents: This Checklist Signed-off
date | Date Completed:
checkpoint | 8 - Panel installation-Survey reference points
label | Reference: VR 682.20
label | Acceptance Criteria: To ensure compliance with the tolerances specified in clause 682.20, the Contractor shall install stable and permanent survey reference points on a not more than 5 m (horizontal) by 2 m (vertical) grid covering the whole face of the RSS
label | Method: Visual
label | Frequency: Each course of panel installation
label | Category: IP
label | Responsibility: Surveyor/SE
label | Verifying Documents: This Checklist Signed-off
date | Date Completed:
checkpoint | 9 - Traceability of precast units and records
label | Reference: VR 620.09
label | Acceptance Criteria: Unique ID of precast panel is recorded.
label | – ATTACH: marked-up elevation drawings or installation record with reference to panel ID
label | Method: Visual
label | Frequency: Each panel
label | Category: IP
label | Responsibility: SE/PE
label | Verifying Documents: This Checklist Signed-off
date | Date Completed:
checkpoint | 10 - Panels installation-Conformance Survey
label | Reference: IFC Drawings VR 682.06, VR 682.17, VR 682.20
label | Acceptance Criteria: The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The
label | ○ Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
label | – Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall
label | – Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm
label | – Variation in gap width between facing panels shall not exceed 5mm per meter length and 10mm over the full length of the gap
label | – The wall level shall not deviate from the specified level by more than ±20mm
label | – The tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height
label | – The verticality of the RSS wall facing shall lean backward at a minimum slope of 1(H) in 40 (V)
label | Attach: Survey Report
label | Method: Survey, Measure
label | Frequency: Each course of panel installation
label | Category: HP*
label | Responsibility: Surveyor/PE
label | Verifying Documents: This Checklist Signed-off
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP