## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | CHK-009-CIV-CPD-RSS Walls-Fill Placement | itp |  |  |  |  | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 0
checkpoint-no-status | CHK-009-CIV-CPD-RSS Walls-Fill Placement
label | Document Title: CHK-009-CIV-CPD-RSS Walls-Fill Placement
label | ITP Description: RSS Walls-Fill Placement
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 06/11/2023
label | ITP created by: Matthew Dib/Jason Quan
label | ITP approved for use by: Pradeep Talasila
checkpoint | 1 - Soil reinforcement-Straps
label | Reference: VR682.08, VR682.17 IFC Drawings
label | Acceptance Criteria: Reinforcing elements shall be placed on top of the compacted fill material and connected to the wall panels. Any twists, kinks, sags or deviations in the reinforcing elements shall be removed prior to the placement of fill material on the reinforcing.
label | Method: Visual
label | Frequency: Each strap
label | Category: IP
label | Responsibility: SE/PE
label | Verifying Documents: This Checklist
date | Date Completed:
checkpoint | 2 - Soil reinforcement-Straps
label | Reference: Installation manual
label | Acceptance Criteria: Correct number of reinforcing element shall be attached to each panel
label | Method: Visual
label | Frequency: Each panel
label | Category: IP
label | Responsibility: SE/PE
label | Verifying Documents: This Checklist
date | Date Completed:
checkpoint | 3 - Soil reinforcements-Bolts Connections
label | Reference: IFC Drawings
label | ○ Schedule of lengths: MRP-080-C-RFL-DRG-33-CPV-CSW-1403, 1502, 1602, 1702, 1803.
label | ○ Connections arrangement: MRP-080-C-RFL-DRG-33-CPV-CSW-2101
label | Acceptance Criteria: Grid Strips are to be installed at the back of each panel in correct length and to the correct anchors at the back of each panel. Finger tight nut or use a wrench so thread emerges from top of nut
label | Method: Visual
label | Frequency: Each Fill Layer
label | Category: IP
label | Responsibility: SE/PE
label | Verifying Documents: This Checklist
date | Date Completed:
checkpoint | 4 - Soil reinforcements-Plan arrangement
label | Reference: IFC Drawings
label | ○ Arrangements: MRP-080-C-RFL-DRG-33-CPV-CSW-1101 to 1105 VR682.06\
label | Acceptance Criteria: Plan positions of Grid Strips are to be as IFC Drawings.
label | – Grid Strips to be placed perpendicular to back of panel where possible.
label | Method: Visual
label | Frequency: Where applicable
label | Category: IP
label | Responsibility: SE/PE
label | Verifying Documents: This Checklist
date | Date Completed:
checkpoint | 5 - Soil reinforcements-vertical/horizontal deviation
label | Reference: IFC Drawings MRP-080-C-RFL-DRG-33-CPV-CSW-1101, 1901 and 1904
label | Acceptance Criteria: Skew grid strips as required to achieve 100mm clearence from pile sleeves. Where grid strips are in the same horizontal plane, ensure 75mm Min horizontal clearance between grid strips
label | Method: Measure, Survey
label | Frequency: Each fill Layer
label | Category: IP
label | Responsibility: Surveyoe/SE
label | Verifying Documents: This Checklist
date | Date Completed:
checkpoint | 6 - Soil reinforcements-clash with drainage
label | Reference: IFC Drawings MRP-080-C-RFL-DRG-33-CPV-CSW-1109, 1901 and 1904
label | Acceptance Criteria: Avoid clash with stormawater pipe as per IFC drawings
label | – RW02 column 1-27 and 30-41: Top layer of grid strips to pass over stormwater pipe. Other locations to pass underneath.
label | – RW03 column 1-23 Deflect top layers of grid-strips below stormwater pipe at maxmum 1:3 slope, column 24 pass over stormwater pipe.
label | – Set Out invert levels of stormwater pipe before commencing straps and fill placement for RW02 and RW03.
label | Method: Visual
label | Frequency: RW02 and RW03 stormwater and grid-strip interface
label | Category: IP
label | Responsibility: SE/PE
label | Verifying Documents: This Checklist
date | Date Completed:
checkpoint | 7 - Fill-Placement
label | Reference: VR204.10
label | Acceptance Criteria: Select backfill shall be placed in accordance with Vicroads section 204. Fill layers to be spread and compacted in layers not exceeding a compacted thickness of 200mm. Fill dispensation to be granted by superintendent to increase thickness layers.
label | Method: Measure, Visual
label | Frequency: Each fill layer
label | Category: IP
label | Responsibility: SE/PE
label | Verifying Documents: This Checklist
date | Date Completed:
checkpoint | 8 - Fill-Placement compaction
label | Reference: 204.111
label | Acceptance Criteria: 0 - 0.15 m Light weight hand operated DPU
label | ○ 0.15 - 0.30 m Less than 5T Roller
label | ○ 0.3 - 1.2 m Less than 10T Roller
label | ○ >1.2 m Less than 35T Roller
label | Method: Visual
label | Frequency: Each fill layer
label | Category: IP
label | Responsibility: SE/PE
label | Verifying Documents: This Checklist
date | Date Completed:
checkpoint | 9 - Fill Test roll
label | Reference: VR 204.12
label | Acceptance Criteria: All layers of fill shall be test rolled in accordance with VR 173. The contractor Shall provide for the superintendent to be present during all test rolling
label | ○ Static Smooth drum roller with a mass >12T; or
label | ○ Tandem truck or water cart with a mass >20T.
label | ○ No visible deformation or springing during test roll.
label | ○ Unstable areas rectified as per agreed method.
label | Method: Visual
label | Frequency: Every Fill Layer
label | Category: HP
label | Responsibility: Nominated Authority
label | Verifying Documents: This Checklist
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Select back fill-Compaction Testing
label | Reference: IFC Drawings VR 204.14, VR 682.16
label | Acceptance Criteria: Testing frequency shall be in accordance with Vicroad Specification section 204.14
label | ○ Moisture content shall achieve minimum characteristic value of density ratio: 98%
label | ○ Moisture content of backfill shall be maintained evenly at all times. Moisture content shall be +0%/-2% of the optimum moisture content. Any backfill material exceeding the optimum moisture content must be allowed to dry.
label | Attach: Compaction test results
label | Method: Documet review
label | Frequency: Each Fill Layer or every second layer as agreed
label | Category: IP
label | Responsibility: Nominated Authority/PE
label | Verifying Documents: Attached Test Results
date | Date Completed:
checkpoint | 11 - Select back fill-Test frequency
label | Reference: IFC Drawings VR 204.14, VR 682.16
label | Acceptance Criteria: After three consecutive lots of like material have achieved the specified requirement, reduce frequency of testing of subsequent lots to the minimum requirement specified in table 204.142:
label | Method: Document review
label | Frequency: Each Fill Layer or every second layer as agreed
label | Category: IP
label | Responsibility: Nominated Authority/PE
label | Verifying Documents: Referenced Lots in This Checklist
date | Date Completed:
checkpoint | 12 - Survey Conformance Asbuilt
label | Reference: Section 204.03 (d, g & h), 206.16
label | Acceptance Criteria: Scale B: Min. No. of Measurements Per Lot: 40
label | ○ Tolerance: mean value of readings +5mm to -25mm and Maximum Standard Deviation to be 15mm
label | Method: Review
label | Frequency: Each lot
label | Category: IP
label | Responsibility: SE
label | Verifying Documents: This ITP, Attach: Survey Conformance As Built
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP