## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | Bunnings Entranceway ITP | itp |  |  |  | Yes | Bunnings Entranceway ITP
checkpoint | 1. Set-out for earthworks and project boundaries
label | When Required - Prior to earthworks
label | By - Contractor or surveyor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2. Pre-construction meeting: review Resource Consent, construction plans and confirm construction methodology with Engineer
label | When Required - Prior to works starting
label | By - NCE / Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3. Sediment control
label | When Required - Prior to works starting
label | By - NCE / Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4. Fill undercut subgrade
label | When Required - Prior to placing any fill material
label | By - NCE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5. Certified fill testing
label | When Required - Ongoing during construction
label | By - Testing Lab / NCE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6. Footpath subgrade
label | When Required - Prior to placement of base coarse
label | By - NCE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7. Installation and connection of stormwater system, and other services
label | When Required - Prior to trench reinstatement, as appropriate.
label | By - NCE, NCC and others as required
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8. Entrance subgrade - excluding services trenches designed by others
label | When Required - Prior to placement of subbase and kerbs
label | By - NCE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9. Pavement density, saturation, beam testing and surface mosaic
label | When Required - Prior to sealing
label | By - NCE / NCC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10. Subgrade and reinforcing for concrete threshold strip
label | When Required - Prior to placing formwork or reinforcing
label | By - NCE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11. As built survey of works
label | When Required - Prior to completion
label | By - Surveyor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12. Final Inspection
label | When Required - At completion of works
label | By - NCE
holdpoint | AUTHORITY HOLDPOINT