## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 1630-P200-SYM-QAC-ITP-0056 Pavement Base Course (Crushed Rock) | itp |  |  |  |  | 1630-P200-SYM-QAC-ITP-0056 Pavement Base Course (Crushed Rock)
section | ITP Details
checkpoint | ITP Details
label | ITP No. - 1630-P200-SYM-QAC-ITP-0056
label | Rev No. - 00
label | Date of Issue - 09/01/2024
label | ITP Type - New
section | 1.0 Pre-start activities
checkpoint | 1.1 - Check Survey Set-out and TCM’s
label | Acceptance criteria - Record existing TCM’s on TCM offset sheet. Survey set out including frame, benchmark, and recovery points in place.
label | Freq - Prior to start of Works
label | Key - H
label | Resp - SE
checkpoint | 1.2 - Crushed Rock Mix Registration
label | Ref docs - DoT812.04, DoT304.03
label | Acceptance criteria - HP: Crushed rock proposed is a current registered mix in accordance with VR500.02 and conforms to the specified requirements for that class.
label | ○ Mix is registered by VicRoads as ‘General’.
label | Freq - Prior to start of works
label | Key - H
label | Resp - SE
label | SI Key - H
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | Crushed Rock Mix Registration | Yes,No
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Addition of Water
label | Ref docs - DoT304.03
label | Acceptance criteria - Water added to the pavement will be clean and suitable for construction and substantially free from detrimental impurities such as oils, salts, acids, alkalis, and vegetable substances, and have no more 1000 mg/L of suspended solids.
label | Freq - Each Lot
label | Key - I
label | Resp - SE
section | 2.0 Installation of Layer
checkpoint | 2.1 - Maximum allowable lot size for a single layer of work.
label | Ref docs - DoT304.06(b) T.304.111
label | Acceptance criteria - Each lot is a single layer of work, and its size is lesser of 4000m2 or one day’s production.
label | Freq - Each Lot
label | Key - I
label | Resp - SE
checkpoint | 2.2 - Delivery Dockets
label | Ref docs - DoT304.05
label | Acceptance criteria - Delivery dockets of the material supplier conform to the requirements outlined in specification VR304.05: Name of supplier, docket number, project name, nature and source of material, and supplier’s stockpile identification number.
label | Freq - Each Lot
label | Key - I
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | Delivery Dockets | Yes,No
checkpoint | 2.3 - Conformity with Drawings
label | Ref docs - DoT304.06
label | Acceptance criteria - Pavement course after compaction is smooth and uniform, and free of segregated areas and any water ponding.
label | Width
label | ○ Width of each side of pavement is not less than specified offset width or more than 50mm outside specified offset width when measured at right angles from centre line or design line.
label | Surface Level
label | ○ Pavement constructed to the lip level of kerb and channel is flush with the lip of the channel or not more than 5mm above.
label | Shape
label | ○ No point on the layer is >8mm from a 3m straight edge or >10mm from a 6m straight edge. Placed in any direction.
label | Freq - Each Lot
label | Key - W
label | Resp - SE
checkpoint | 2.4 - Conformity with Drawings
label | Ref docs - DoT304.06
label | Acceptance criteria - W: Any material compacted and then trimmed from the compacted surface to conform to the correct level or thickness as shown on the drawings shall not be re-used in the pavement construction without Superintendent approval.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | SI Key - W
checkpoint | 2.5 - Construction - Jointing
label | Ref docs - DoT304.07
label | Acceptance criteria - Material has been spread to minimise joints.
label | ○ Transverse joints are offset from one layer to the next by not less than 2m.
label | ○ Longitudinal joints are offset from one layer to the next by not less than 150mm and located within 300mm of planned position of traffic lines or within 300mm of centre of traffic lane.
label | ○ Exposed lot and edge each lot of any part of jointing is kept moist until spreading and compaction is complete over entire layer.
label | Freq - Each Lot
label | Key - I
label | Resp - SE
checkpoint | 2.6 - Protection of compacted layer
label | Ref docs - DoT304.09
label | Acceptance criteria - Surface of each compacted layer is in good order/condition & free from contamination until the subsequent pavement work is to commence.
label | Freq - Each Lot
label | Key - I
label | Resp - SE
section | 3.0 Testing
checkpoint | 3.1 - Testing – Stability (Proof Roll)
label | Ref docs - DoT304.08(b), DoT173.03(ii), DoT173.03(b)
label | Acceptance criteria - HP: The contractor has provided for the Superintendent to attend all test rolling.
label | ○ Contact pressure of test vehicle is min. 450kPa/tyre during test over an area of min. 0.035m2/tyre. The layer doesn’t show visible deformation or springing.
label | Freq - Each Lot
label | Key - H
label | Resp - SE
label | SI Key - H
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | Proof Roll Checklist | Yes,No
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Unstable Area Rectification
label | Ref docs - DoT304.08(b), DoT173.03(b)
label | Acceptance criteria - Unstable areas identified during the proof roll have been rectified. Prior to any successive layer, the superintendent has required further test rolling to confirm the layer is sound.
label | ○ Contact pressure of test vehicle is min. 450kPa/tyre during test over an area of min. 0.035m2/tyre. Layer doesn’t show visible deformation or springing.
label | Freq - Each Lot
label | Key - I
label | Resp - SE
label | SI Key - R
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | Proof Roll Checklist (Post Rectification) | Yes,No
checkpoint | 3.3 - Testing – Compaction
label | Ref docs - DoT304 T.304.081, DoT173.04(d)
label | Acceptance criteria - Scale A
label | ○ Characteristic Density Ratio % (six tests):
label | ○ Greater than 100.0% Modified Compaction.
label | ○ Moisture content is at least 85% of optimum until test request is completed.
label | ○ Initial testing frequency: 1 test per lot.
label | ○ Reduced Testing: Once 3 consecutive lots of like material and/or work is passing, test 1 per 2 lots. If one lot fails, resume 1 test per lot.
label | ○ Small Lot: Lots <500m2 can be CDR 3-Lot and accepted if 3-lot mean value is at least 102.0%. Small lots can’t qualify for reduced testing.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | SI Key - R
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | NATA Test Report: Compaction | Yes,No
textbox | Prev. Tested Lot No. (If reduced frequency)
checkpoint | 3.4 - Post Compaction Grading (Nominal Size = 20mm)
label | Ref docs - DoT304.10(a) T.304.101 T.304.111
label | Acceptance criteria - Sieve Size ¦ % Passing by Mass
label | 26.5 mm – 100%
label | 19.0 mm – 95 - 100%
label | 13.2 mm – 78 – 92%
label | 9.5 mm – 63 - 83%
label | 4.75 mm – 44 - 64%
label | 2.36 mm – 30 - 49%
label | 0.425 mm – 14 - 23%
label | 0.075 mm – 6 - 12%
label | Minimum testing frequency: 1 test per 2 lots.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | SI Key - R
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | NATA Test Report: Grading | Yes,No
checkpoint | 3.5 - Post Compaction - Plasticity Index
label | Ref docs - DoT304.10(b) T.304.111, T.304.103
label | Acceptance criteria - PI: 2 – 6 (Class 1) Minimum testing frequency: 1 test per 4 lots.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | SI Key - R
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | NATA Test Report: Atterberg Limits | Yes,No
checkpoint | 3.6 - Scale A Requirements for Post Compaction Grading and PI Testing
label | Ref docs - DoT304.11(c)(i)
label | Acceptance criteria - The first lot of each pavement layer shall be tested for post- compaction grading and PI.
label | ○ Any reworked lot is re-tested for compliance.
label | Freq - Each Lot
label | Key - H
label | Resp - SE
label | SI Key - R
section | 4.0 Completion
checkpoint | 4.1 - Survey as built
label | Ref docs - DoT304.06 T. 304.061, T. 304.062
label | Acceptance criteria - Surface is smooth, uniform, free of segregation, conforming to grade, thickness, and drawing section. Each measurement is taken at random locations in accordance with the VicRoads Test Method.
label | ○ Scale A: 80 measurements per lot are taken.
label | ○ Mean Range: +5mm to -5mm.
label | ○ Max Stnd. Deviation: 8mm.
label | Surface out of tolerance is rectified and re-surveyed.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | Survey Conformance Certificate | Yes,No
checkpoint | 4.2 - Thickness of Pavement Layers
label | Ref docs - DoT304.06 (c) DoT304.08(v)
label | Acceptance criteria - Base course is not less than specified thickness by more than 10mm and average thickness of base over every 100m section over full carriageway width is not less than specified thickness.
label | ○ Combined thickness of subbase and base courses is not less than specified thickness by more than 15mm.
label | ○ Maximum base layer thickness is 150mm.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | Survey Conformance Certificate | Yes,No
section | 5.0 Work Lot Close Out
checkpoint | 5.1 - Test Reports
label | Ref docs - VIC Roads Specifications
label | Acceptance criteria - All Test reports received and reviewed.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | NATA Endorsed Tests | Yes,No
checkpoint | 5.2 - Product Non-Conformance
label | Ref docs - CQMP
label | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | NCR reports | Yes,No
checkpoint | 5.3 - Quality Representative to check the above criteria and records to confirm.
label | Ref docs - CQMP Lot Records
label | Acceptance criteria - All above criteria met, and records identified attached.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | Completed Checklist (if applicable). reports and other compliance records attached. | Yes,No