## Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier6 | Instruction to CONQA | Checklist Name
SP2A - L2 Lounge Extension & Fire Egress Stairs
Grids 34A-36A
Grids 34A-35A
Grids 35A-32
Grids 32-36A

## Resources
type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist | Steel Member Checklist |  |  |  |  | Yes | Steel Member Checklist | 24b4adbb-f9eb-44ef-adab-6ca79fbfd5a2
checkpoint | Batch numbers photographed
checkpoint | Area first application complete and visual check completed
checkpoint | Proile substrate for adhesion sanded
checkpoint | Solvent clean of substrate performed to remove contamination
checklist | ST - S - Intumescent Painting - Pre-Commencement |  |  |  |  | Yes | ST - S - Intumescent Painting - Pre-Commencement | 39df253a-8f0f-4334-9fdd-fc9185c10a29
section | Pre-site visit
checkpoint | Fabrication Drawings received
checkpoint | Carboline schedule received and attached/uploaded
checkpoint | Sealer schedule received and attached/uploaded
checkpoint | Fire engineer report received and attached/uploaded
textbox | Fire rating specified | 60FRR
textbox | Fire limiting temperature specified | 550
checkpoint | QA documentation from blast and prime received
signoff | Raise remedial/ sign-off request
section | Pre-Paint Site Visit
checkpoint | Supports removed
checkpoint | No timber attached
checkpoint | Concrete splatters removed
checkpoint | All area and substrate checkpoints passed and area acceptable for painting
signoff | Raise remedial/ sign-off request
checkpoint | Inspections completed and issued to Foreman
signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist | Area Checklist |  |  |  |  | Yes | Area Checklist | 422fa8f6-f8a6-48bb-890f-326c2b796c10
checkpoint | All area and substrate checkpoints passed and area acceptable for painting
checkpoint | Average ambient conditions photographed and site conditions acceptable for painting
checkpoint | Positector activated to gauge weather elements
checkpoint | No timber attached
checkpoint | Concrete splatters removed
checkpoint | Inspections completed and issued to Foreman
checklist | CST - S - Completion Documents |  |  |  |  | Yes | CST - S - Completion Documents | bc9797a9-a87e-4c43-bbb0-17f26d13fd8e
checkpoint | All relevant Compliance Documentation completed and attached above
tickbox | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
signoff | Request Signoff
checkpoint | Inspections completed and issued to Foreman
signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist | ST - S - Intumescent Painting - QA |  |  |  |  | Yes | ST - S - Intumescent Painting - QA | fb65c9ca-305e-4e15-978e-b2be384d0123
section | Preparation
checkpoint | Area for preparation and application input:
textbox | Area / Grids:
checkpoint | Solvent clean of substrate performed to remove contamination
checkpoint | Proile substrate for adhesion sanded
tickbox | Abrasive blast
tickbox | Vapour blast
tickbox | Bristle blast
tickbox | Scotch sand
checkpoint | All area and substrate checkpoints passed and area acceptable for painting
section | Application
checkpoint | Positector activated to gauge weather elements
checkpoint | Average ambient conditions photographed and site conditions acceptable for painting
checkpoint | Batch numbers photographed
checkpoint | Area first application complete and visual check completed
checkpoint | Inspections completed and issued to Foreman
signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist | Application |  |  |  |  | Yes | Application | 172e9c72-2c60-4bfb-86da-0aa30a39d6da
checkpoint | All area substrates passed and area acceptable for painting
textbox | Area / Grids:
checkpoint | Batch numbers photographed