## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Excavation for Area: |  |  |  |  | Yes | QA - Excavation | 07a6ecc9-184b-4e6c-a390-0f9a7f647f40
checkpoint-status |  |  | checkpoint | Location accurate
checkpoint-status |  |  | checkpoint | Depth correct (allow for site concrete if required)
checkpoint-status |  |  | checkpoint | Width correct (allow for boxing if required)
checkpoint-status |  |  | checkpoint | Any relevant excavation for services is completed and accurate (use underground services checklist to QA service install)
checkpoint-status |  |  | checkpoint | General Photos / Comments / Observations during excavation
boolean | 31e1b45c-583a-57eb-89ef-dea8f8f3d7a8 |  | tickbox | Trades QA received & attached as applicable
checklist-flat |  |  | checklist | RS-01: Membrane Roof - Asphaltech IKO Armourplan: |  |  |  |  | Yes | RS-01: Membrane Roof - Asphaltech IKO Armourplan: | 13bee9d7-0693-4d6b-a2f8-c9bc04272f18
checkpoint-status |  |  | checkpoint | Framing complete
checkpoint-status |  |  | checkpoint | Plywood installed
checkpoint-status |  |  | checkpoint | Membrane installed
checkpoint-status |  |  | checkpoint | Penetrations through roof installed
checkpoint-status |  |  | checkpoint | Flashings installed
checkpoint-status |  |  | checkpoint | Roof/gutter testing witnessed by Inhabit
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checklist-flat |  |  | checklist | Consultant Inspection - |  |  |  |  | Yes | Add - Consultant Inspection Checklist (V3) | 1a39894f-1959-48ce-a38c-c424149ab37d
checkpoint-status |  |  | checkpoint | Consultant inspection completed, attached and any relevant observations closed out
text | 7b7a025d-81fa-4409-9ef9-3281b2d64523 |  | textbox | Date of Inspection
text | dd36bd0b-3ee0-4704-912f-3f8f961a2cb6 |  | textbox | Type of Inspection
text | da74bdd5-b086-41a1-94ef-12814f41c3f5 |  | textbox | Area inspection relates to
boolean | e495e118-490c-453e-af9d-13b99904e2dc |  | tickbox | Consultant Inspection attached
button | 0f8e78cc-ac2e-4458-b897-ef644c2cb994 |  | button | All Relevant Observation Closeout evidence attached here if applicable (Pass once completed) | PASS, N/A
label | 1f26a12b-97a7-4354-afab-298bf48ac079 |  | note | "PASS" once corrective closeout evidence has been attached
label | 5b90254d-0b5f-40ab-b626-60f2f7e09379 |  | note | If there are no corrective action requirements select "N/A"
text | 3d06351b-6af4-431a-909b-5a78ef041b49 |  | textbox | Corrective Actions (listed here if required)
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Council Inspection - |  |  |  |  | Yes | Add - Council Inspection Checklist (V3) | 1a732614-648c-4004-b460-d06c77a7584c
checkpoint-status |  |  | checkpoint | Council inspection completed, attached and any relevant observations closed out
label | 3444c651-e5e2-4a4d-87f9-f06b48de741d |  | note | PASS once all information is attached including Observations/Failed comments with evidence of closeout
text | dc83a024-74b8-4254-9ddd-e5098acc1bd8 |  | textbox | Date of Inspection:
text | 9078e12c-052d-4e8e-aaa0-bf0ee4a8e674 |  | textbox | Type of Inspection:
text | 52f91732-bf1d-45c6-bd07-b9da5bc92d07 |  | textbox | Area inspection relates to
select | b4da29de-ea63-439e-a19e-c0f75d938880 |  | dropdown | Inspection Outcome | Pass, Fail, Partial Pass,Completed, N/A
boolean | e163160e-48f6-4a1e-925a-fc9517380516 |  | tickbox | Council Inspection attached
text | 202aee45-e7db-4a11-a3cd-d58c1ed02669 |  | textbox | Failed Comment(s) & Required Action
label | 3c7bfeb2-48cc-4c75-8c53-db434c64e996 |  | note | Select N/A if there are no Observations/Failures requiring closeout
button | 5fc35eaa-61ff-4a6a-85df-bfb72c73a67d |  | button | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed) | Pass, N/A
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Underslab Services for Area: |  |  |  |  | Yes | QA - Underslab Services | 227b882c-60d5-48b0-bbaf-b0d64f4d2734
checkpoint-status |  |  | checkpoint | ELECTRICAL services/ conduits installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | HYDRAULIC services installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | GAS services installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | MECHANICAL services installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | DATA/COMMS services installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | Any other services installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | Underslab Services completed correctly to specification & within tolerance in respective area(s) (photographic evidence provided below)
boolean | cf084637-b161-5f5a-a470-9dbcc8b5e5a8 |  | tickbox | Trades QA received & attached as applicable
checklist-flat |  |  | checklist | Apartment Preline: |  |  |  |  | Yes | QA - Apartment Preline | 27cb5ca1-ebb3-4dce-bfeb-459c06b8c954
checkpoint-status |  |  | checkpoint | IT Bulkheads complete
checkpoint-status |  |  | checkpoint | Steel stud installed
checkpoint-status |  |  | checkpoint | Plumbing first fix complete
checkpoint-status |  |  | checkpoint | Mechanical first fix complete
checkpoint-status |  |  | checkpoint | Sprinkler first fix complete
checkpoint-status |  |  | checkpoint | Passive fire complete
checkpoint-status |  |  | checkpoint | Nogs installed
checkpoint-status |  |  | checkpoint | Insulation installed
checkpoint-status |  |  | checkpoint | GIB installed
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Council / Consultant inspections complete
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checklist-flat |  |  | checklist | FS-01: Aluminium Joinery: |  |  |  |  | Yes | FS-01: Aluminium Joinery: | 6ea8abe8-10a5-4ef4-b370-9d0b7c41902c
checkpoint-status |  |  | checkpoint | Substrate acceptable
checkpoint-status |  |  | checkpoint | Openings sealed
checkpoint-status |  |  | checkpoint | General install photos
checkpoint-status |  |  | checkpoint | Fixings correct
checkpoint-status |  |  | checkpoint | Windows sealed
checkpoint-status |  |  | checkpoint | Glazing installed
checkpoint-status |  |  | checkpoint | Rainshield angle installed
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checklist-sectioned |  |  | checklist | Precast Panels for Area: |  |  |  |  | Yes | QA - Precast Panels | 73928117-945b-4c61-bd1a-e93ec35bb30a
checkpoint-group |  |  | section | Pre installation
checkpoint-status |  |  | checkpoint | Precast elements inspected, correct and damage free before placement
checkpoint-status |  |  | checkpoint | All pre installation work completed
boolean | 8866ab0d-0674-5ad8-913c-16c47f89c2db |  | tickbox | Site set-out completed
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Alignment and levels of the panel checked/correct
checkpoint-status |  |  | checkpoint | Panel propping checked
checkpoint-status |  |  | checkpoint | Panel brackets installed
checkpoint-status |  |  | checkpoint | Drypacking / grouting complete
checkpoint-status |  |  | checkpoint | Sealant complete
checkpoint-status |  |  | checkpoint | Flashings installed
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Panel installation completed within tolerance in respective area
boolean | 6adc1e10-3160-5264-8602-77ffd22effb4 |  | tickbox | Trades QA received, reviewed, attached and approved
checklist-flat |  |  | checklist | FS-05: Aluminium Panels: |  |  |  |  | Yes | FS-05: Aluminium Panels: | 7b89ca15-443e-4309-b915-81babe412ec5
checkpoint-status |  |  | checkpoint | Nib installed
checkpoint-status |  |  | checkpoint | Framing complete
boolean | 411dfc1d-09a2-5a0e-ba25-d7eeae5201ba |  | tickbox | Correct grade timber used
boolean | 090c155f-2181-5457-ae08-c77612bdcf6b |  | tickbox | Set-out correct
boolean | 4c4d6ffe-42b8-55ec-9045-4a56765e48c9 |  | tickbox | Fixings correct
checkpoint-status |  |  | checkpoint | Framing sealed
checkpoint-status |  |  | checkpoint | Waterproofing membrane lapped up nib
checkpoint-status |  |  | checkpoint | RAB installed
checkpoint-status |  |  | checkpoint | Self adhesive membrane installed
boolean | edb7dadb-c3d8-5d0f-9778-1c99cd2d01ab |  | tickbox | Penetrations sealed
checkpoint-status |  |  | checkpoint | Flashing tape installed
checkpoint-status |  |  | checkpoint | Extrusions and underflashings installed
checkpoint-status |  |  | checkpoint | Panels installed
boolean | ef48aba0-7853-51f3-bae5-a3b3efbb6c6b |  | tickbox | Fixings correct
checkpoint-status |  |  | checkpoint | Panels sealed
checkpoint-status |  |  | checkpoint | Additional flashings installed
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checklist-sectioned |  |  | checklist | Shotcrete for Area: |  |  |  |  | Yes | QA - Shotcrete | 7ff4aff2-6271-4067-b928-0eb275487388
checkpoint-group |  |  | section | Shotcrete Pre-pour
checkpoint-status |  |  | checkpoint | Drainage installed and aligning with design
checkpoint-status |  |  | checkpoint | Waterproofing installed and aligning with design
checkpoint-status |  |  | checkpoint | Reinforcing checked and correct
button | c130dac0-33f0-5ea0-99bd-9d8ee2b68a24 |  | button | Size and type correct to specification | Yes, N/A
boolean | 737e6547-2707-5ec4-bae0-0182d5aaeac5 |  | tickbox | Reinforcing spacing and location correct
boolean | 4b24a13c-760e-52f8-b93a-a0c04aa80878 |  | tickbox | Specified covers checked/correct
boolean | 325afaaa-72f6-5346-bcd2-1af225e972b5 |  | tickbox | Splice laps checked/correct
boolean | bdc800fb-3df2-586e-a463-882129fa7a04 |  | tickbox | Any starter bars are installed correctly (location, size and spacing )
boolean | 3c18fbb2-66a4-5da4-ba58-d4b12e4e4529 |  | tickbox | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Shotcrete Pour
checkpoint-status |  |  | checkpoint | General photos/comments/observations
boolean | 6aa6e9bd-70b0-5634-a284-78168162cc08 |  | tickbox | All concrete dockets photographed/attached here
boolean | c37c96d0-1c2d-51a1-be38-e51b5a8f584b |  | tickbox | Trades QA received & attached as applicable
checklist-sectioned |  |  | checklist | Blockwork for Area: |  |  |  |  | Yes | QA - Blockwork | 8a0303fa-4a64-4552-88d1-bf3d7a2b5d78
checkpoint-group |  |  | section | Blockwall Pre-pour
checkpoint-status |  |  | checkpoint | Set-out correct
checkpoint-status |  |  | checkpoint | Reinforcing checked and correct
button | f7586310-fc3b-5658-92c3-0d0cea4c317e |  | button | Size and type correct to specification | Yes, N/A
boolean | 1fc40f0f-711b-5395-909c-5ebde9a2f166 |  | tickbox | Reinforcing spacing and location correct
boolean | cc2480f0-f0d8-530b-9399-0639187cbf96 |  | tickbox | Specified covers checked/correct
boolean | 835d02c7-3dc6-5b06-ba6a-e04340a4f1b7 |  | tickbox | Splice laps checked/correct
boolean | ad88c3b3-8140-5228-93dc-4833a7f40456 |  | tickbox | Any starter bars are installed correctly (location, size and spacing )
boolean | 110cffa5-c7b7-54b9-b4ae-dd7bc999dd32 |  | tickbox | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Openings checked and correct - location, height and width
boolean | bacdfe6d-4a64-5468-8d70-a317a6ffffd4 |  | tickbox | Lintels / bond beams formed correctly
checkpoint-status |  |  | checkpoint | Any/All cast in items checked / correct (location and size)
checkpoint-status |  |  | checkpoint | Penetrations correctly formed/located, checked and accurate
checkpoint-status |  |  | checkpoint | Ties / Control joints installed as required
checkpoint-status |  |  | checkpoint | Wall built within tolerance - straight, level and to the correct height
checkpoint-status |  |  | checkpoint | Engineer informed of pour checks completed (see consultant folder and ensure observations are closed out)
checkpoint-group |  |  | section | Blockwall Pour
checkpoint-status |  |  | checkpoint | General photos/comments/observations
boolean | 82a3590f-81db-5ef5-b5c6-355c721b26c5 |  | tickbox | All concrete dockets photographed/attached here
boolean | 5b90492c-04c4-586b-8b7e-ee4c22eb90cb |  | tickbox | Trades QA received & attached as applicable
checklist-sectioned |  |  | checklist | Structural Steel for Area: |  |  |  |  | Yes | QA - Structural Steel | a76dc7c3-3a6e-4bf2-afe8-fc3519a71d25
checkpoint-group |  |  | section | Pre installation
checkpoint-status |  |  | checkpoint | Structural steel items checked
boolean | 88bdc03d-e52a-5cb7-992c-85f91130a672 |  | tickbox | Type/Size Checked
boolean | ee6898f1-e970-5644-b091-f11820056761 |  | tickbox | Finishing checked (ie. Painted, Galvanised, etc)
checkpoint-status |  |  | checkpoint | Cast in/anchor bolts and plates installed
checkpoint-status |  |  | checkpoint | All pre installation work completed
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Alignment and levels checked/correct
checkpoint-status |  |  | checkpoint | All dry packing / grouting completed
checkpoint-status |  |  | checkpoint | Passive fire works completed
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Structural steel work completed within tolerance in respective area
boolean | 56e950a9-968a-52bc-acf0-afd140d4f249 |  | tickbox | Trades QA received, reviewed, attached and approved
checklist-flat |  |  | checklist | Drawings & Programme |  |  |  |  | Yes | Add Drawings & Programme Checklist (V1) | ba496c6a-d1a4-45ed-8dba-ed2acabf5615
checkpoint-status |  |  | checkpoint | Relevant Drawings Uploaded
checkpoint-status |  |  | checkpoint | Construction Programme Uploaded
checklist-sectioned |  |  | checklist | Precast Floor Units for Area: |  |  |  |  | Yes | QA - Precast Floors | bf97e2f8-3052-4ed3-804a-40c0a76a9f3d
checkpoint-group |  |  | section | Pre installation
checkpoint-status |  |  | checkpoint | Precast elements inspected, correct and damage free before placement
checkpoint-status |  |  | checkpoint | All pre installation work completed
boolean | b0cd75d9-f909-5f55-9612-157de0abc38b |  | tickbox | Site set-out completed
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Alignment and levels of the unit checked/correct
checkpoint-status |  |  | checkpoint | Propping checked
checkpoint-status |  |  | checkpoint | Bearing strips installed
checkpoint-status |  |  | checkpoint | Seating correct
checkpoint-status |  |  | checkpoint | Drypacking / grouting complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Panel installation completed within tolerance in respective area
boolean | de8b1597-587b-5ee1-ba59-ff309a756f96 |  | tickbox | Trades QA received, reviewed, attached and approved
checklist-flat |  |  | checklist | Blank Checklist |  |  |  |  | Yes | Blank Checklist | d01769cc-3cb8-420b-9181-82dab49241c3
checkpoint-status |  |  | checkpoint | General photos/comments/observations
checklist-flat |  |  | checklist | Waterproofing for Area: |  |  |  |  | Yes | QA - Waterproofing | d5a07195-22c5-498d-83bf-338ca9c9ffd4
checkpoint-status |  |  | checkpoint | Preparation / Substrate acceptable
checkpoint-status |  |  | checkpoint | Correct product delivered and checked - approval given to install
checkpoint-status |  |  | checkpoint | General photos/comments during install
checkpoint-status |  |  | checkpoint | Any inspections / observations documented, reviewed and closed out
checkpoint-status |  |  | checkpoint | Waterproofing install completed, reviewed and approved to meet required specifications
label | 991b4660-642d-5ee3-9f56-f272eb589ce7 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
boolean | dabfd03e-d97f-59fd-8234-aacf5c17935a |  | tickbox | Trades QA received & attached as applicable
checklist-sectioned |  |  | checklist | Concrete Pour for Area: |  |  |  |  | Yes | QA - Concrete Pour | deccf201-2d52-4b0e-aa99-380d6472752e
checkpoint-group |  |  | section | Concrete Pre-pour
checkpoint-status |  |  | checkpoint | Set-out correct
checkpoint-status |  |  | checkpoint | Any/All cast in items checked / correct (location and size)
checkpoint-status |  |  | checkpoint | Penetrations correctly formed / located, checked and accurate
checkpoint-status |  |  | checkpoint | Reinforcing checked and correct
button | 0b8b12f4-7aec-564f-adb6-923ede08c7fb |  | button | Size and type correct to specification | Yes, N/A
boolean | 5a1a1978-5513-52bb-a763-305e1fb16372 |  | tickbox | Reinforcing spacing and location correct
boolean | 8ef410a8-1bf3-5b47-a654-628373862bf0 |  | tickbox | Specified covers checked / correct
boolean | 36b77f08-c984-5546-88a3-4a1667147e5c |  | tickbox | Splice laps checked/correct
boolean | ec071fad-d9c3-53c6-a0af-eebcb51685f6 |  | tickbox | Any starter bars are installed correctly (location, size and spacing )
boolean | 654ba5e5-0dc2-52c6-b7e1-019d6011808d |  | tickbox | Any additional items installed / completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Waterproofing (checked and correct)
checkpoint-status |  |  | checkpoint | Bottom of concrete pour is clean and free of debris / roughened
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Engineer informed of pour checks completed (see consultant folder and ensure observations are closed out)
checkpoint-group |  |  | section | Concrete Pour /Post Pour
checkpoint-status |  |  | checkpoint | General photos/comments/observations
boolean | 5a059e79-6052-56c2-b453-7ded34f80758 |  | tickbox | All concrete dockets photographed/attached here
boolean | e289c314-c718-56fa-a76b-5e0a821b2216 |  | tickbox | Trades QA received & attached as applicable
checklist-flat |  |  | checklist | Backfill for Area: |  |  |  |  | Yes | QA - Backfill | e421c3da-91ab-4fdd-a281-bd48af4e0e87
checkpoint-status |  |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status |  |  | checkpoint | General photos and observations during backfill
checkpoint-status |  |  | checkpoint | Backfill completed correctly and heights checked/ correct - desired compaction achieved
label | f2b4da8e-a831-5390-abbd-99edf9ee0689 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
boolean | 46b5ca41-d911-52ce-a905-02a9a40e8d8c |  | tickbox | Trades QA received & attached as applicable
checklist-flat |  |  | checklist | MS-01: Balcony Membrane - Asphaltech IKO Permatec: |  |  |  |  | Yes | MS-01: Balcony Membrane - Asphaltech IKO Permatec: | e79f8488-0e37-44b4-940a-d7850a7df186
checkpoint-status |  |  | checkpoint | Substrate acceptable
checkpoint-status |  |  | checkpoint | Membrane installed
checkpoint-status |  |  | checkpoint | Transition waterproofing installed
checkpoint-status |  |  | checkpoint | Flashings installed
checkpoint-status |  |  | checkpoint | Deck tiles installed
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checklist-flat |  |  | checklist | FS-02/3: Precast Concrete Panels: |  |  |  |  | Yes | FS-02/3: Precast Concrete Panels: | f03028de-2972-4c69-877c-849d4ba40b32
checkpoint-status |  |  | checkpoint | General install photos
checkpoint-status |  |  | checkpoint | Lifting eye flashings installed and grouted
checkpoint-status |  |  | checkpoint | Joint flashings installed
checkpoint-status |  |  | checkpoint | Expansion tape installed at inaccessible locations
checkpoint-status |  |  | checkpoint | Horizontal joints sealed
checkpoint-status |  |  | checkpoint | Vertical joints sealed
checkpoint-status |  |  | checkpoint | Panel brackets installed
boolean | 1ae932ca-aed6-5df4-8021-ca9135e79e49 |  | tickbox | Washers welded where required
boolean | 844a1539-58b7-541b-a615-6d9b19029c4f |  | tickbox | Bracket grouted
boolean | cf770f4e-8b62-5446-99c5-434ae1c77ace |  | tickbox | Intumescent paint applied
checkpoint-status |  |  | checkpoint | Window opening sealed
checkpoint-status |  |  | checkpoint | Panels painted / sealed
checkpoint-status |  |  | checkpoint | Additional flashings installed
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checklist-sectioned |  |  | checklist | Panel Brackets: |  |  |  |  | Yes | QA - Panel Bracket | f96b6bb8-3534-4d16-a7b1-7ed50fd0fe57
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Installation and welding complete
checkpoint-status |  |  | checkpoint | Intumescent paint complete
checkpoint-status |  |  | checkpoint | All dry pack / grouting completed
checkpoint-status |  |  | checkpoint | Engineer's inspection notes closed out
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Structural steel work completed within tolerance in respective area
boolean | db2db7bd-101b-5097-9fe3-9c486090c1b2 |  | tickbox | Trades QA received, reviewed, attached and approved