## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP020 - AGL Precast Pits | itp |  |  |  | Yes | ITP020 - AGL Precast Pits | 55a1460b-774a-402d-b298-38b0b78d26d5
section | 1.0 Preliminary Works
checkpoint | 1.1 - Check for Correct Documentation
note | Frequency: Prior to commencing activity
note | Acceptance Criteria: Ensure that all employees and subcontractors are:
note | – using the correct and complete set of drawings
note | – all drawings are the latest revision
note | Reference Documents: Drawings / Aconex Register
note | Inspection/ Test Method: Verify
note | Record of conformity: Drawings and drawing registers
note | HP*
note | Responsibility: Site Engineer
textbox | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
note | Frequency: Prior to commencing activity
note | Acceptance Criteria: All necessary measures and controls being implemented, that is PSP, EMP, TMP, SWMS & WP
note | Reference Documents: PSP, EMP, TMP, JSEA, SWMS, WP
note | Inspection/ Test Method: Visual Inspection
note | Record of conformity: This ITP signed
note | HP*
note | Responsibility: Site Engineer
textbox | Date Completed:
checkpoint | 1.3 - Definition of the work Area & Survey check
note | Frequency: Prior to commencing activity
note | Acceptance Criteria: Work area has been cleared and surveyed (marked on site). Work area to be clearly defined as per For Construction drawings prior to trenching and install.
note | Reference Documents: IFC Drawings 12554937-E014 to E028
note | Inspection/ Test Method: Verify
note | Record of conformity: This ITP Signed & Sub-contractor ITC
note | SCP
note | Responsibility: Site Engineer / Site Supervisor
textbox | Date Completed:
checkpoint | 1.4 - Excavation Works
note | Frequency: Prior to commencing activity
note | Acceptance Criteria: Location of services to be found and marked on the ground within the works;
note | • Obtain excavation permit from APAM prior to any excavation works.
note | • Services located within the works area to be exposed/proven, recorded as survey data and also on a service plan which is to be attached to the Excavation Permit.
note | Reference Documents: APAM- DBYD Job:32711991 Seq:215891341
note | • FH Permit
note | • Appendix K- Technical Specifications Cl.3.9.3
note | Inspection/ Test Method: Verify
note | Record of conformity: Melbourne Airport Excavation Permit
note | HP*
note | Responsibility: Site Engineer / Surveyor
textbox | Date Completed:
checkpoint | 1.5 - Native Grass Protection
note | Frequency: Prior to commencing activity
note | Acceptance Criteria: Native grass protection installed. As per native grass model, 8m wide corridor delineated by bollards/ fencing.
note | Reference Documents: Relevant Native Grass Permit
note | Inspection/ Test Method: Visual Inspection
note | Record of conformity: This ITP signed
note | IP
note | Responsibility: Site Engineer/Site Supervisor
textbox | Date Completed:
checkpoint | 1.6 - Service Locating/Proving
note | Frequency: Prior to commencing Excavation Works
note | Acceptance Criteria: Location of services to be found and marked on the ground within the works;
note | • Obtain excavation permit from APAM prior to any demolition works.
note | • Services located within the works area to be exposed/proven, recorded as survey data and also on a service plan which is to be attached to the Excavation Permit.
note | Reference Documents: APAM- DBYD Job:32711991 Seq:215891341
note | • FH Permit
note | • Appendix K- Technical Specifications Cl.3.9.3
note | Inspection/ Test Method: Verify
note | Record of conformity: Melbourne Airport Excavation Permit
note | HP*
note | Responsibility: Site Engineer / Surveyor
textbox | Date Completed:
section | 2.0 Supply of Materials
checkpoint | 2.1 - Materials & source Approval
note | Frequency: Pre-commencement
note | Acceptance Criteria: Provide full details of pit types to the Contract administrator including, but not limited to:
note | – Manufacturer
note | – Model Number
note | – External Dimensions
note | – Internal Dimensions
note | – Maximum number of penetrations of each conduit size for each pit wall
note | – Depth of penetrations
note | – Label recess dimensions
note | – SIT tray details/ installation details
note | – Installation requirements
note | – Lid details including
note | o Model Number
note | o Dimensions
note | o Materials
note | o Lifting points / mechanism
note | o Load rating
note | o Removal tools
note | Reference Documents: Appendix K- Technical Specifications - Section 2.7
note | Inspection/ Test Method: Verify
note | Record of conformity: Aconex correspondence Reference Approval
note | AP
note | Responsibility: Site Engineer and Principal’s Representative
textbox | Date Completed:
section | 3.0 Excavation
checkpoint | 3.1 - Excavation Obstruction
note | Frequency: Each lot
note | Acceptance Criteria: Any rock found to impose significantly on excavations (i.e. rock that cannot be excavated by means of a Rock Saw, Caterpillar D7 with single tyne ripper or similar suitably equipped machine) must be brought to the attention of the Contract Administrator
note | • Cable pits must be relocated as necessary to avoid significant areas of rock that cannot be excavated. Provide details of proposed pit relocations to the Contract Administrator for approval.
note | Reference Documents: Appendix K- Technical Specifications) 3.9.7, AGL Conduit Install ITC
note | Inspection/ Test Method: Visual Inspection
note | Record of conformity: This ITP signed
note | HP
note | Responsibility: Site Engineer / Foreman/ Principal’s Representative
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Confirm Ground
note | Frequency: Each Lot
note | Acceptance Criteria: Pits shall be constructed on firm subgrade as per methods listed in item 3.3, in accordance with manufacturer’s instructions
note | Reference Documents: IFC Drawings, Manufacturer installation guide
note | Inspection/ Test Method: Verify
note | Record of conformity: This ITP signed
note | HP*
note | Responsibility: Site Engineer / Foreman/
textbox | Date Completed:
checkpoint | 3.3 - Blinding
note | Frequency: Each Lot
note | Acceptance Criteria: Blinding to be installed in either of the following methods:
note | – 50mm 20Mpa Concrete
note | – 100mm Class 2 Wet Mix Crushed Rock – Compacted to refusal using handheld mechanical aid (DPU / Wacker Plate).
note | – 5% Stabilised Sand dry mix Min. 50mm depth
note | • Installed blinding layer is to be stable and level to ensure the precast pit is vertical
note | Reference Documents: IFC Drawings, Manufacturer installation guide BecaCPL-RTRFI-000280
note | Inspection/ Test Method: Verify
note | Record of conformity: This ITP signed
note | IP
note | Responsibility: Site Engineer
textbox | Date Completed:
section | 4.0 Precast Pit Fabrication & Delivery
checkpoint | 4.1 - Pit Delivery
note | Frequency: Each Lot
note | Acceptance Criteria: Ensure each pit component is inspected upon arrival ensuring:
note | – Dimensions are as shown on manufacturer drawings
note | – All blockouts in correct positions and to dimensions.
note | – No damage to any pit component to the satisfaction of Site Engineer
note | • No modifications to the pits are to be made without written approval from manufacturer.
note | • Conduit entries to be drilled on site, with defined area defined by pit manufacturer.
note | Reference Documents: Appendix K- Technical Specifications
note | Inspection/ Test Method: Visual Inspection
note | Record of conformity: This ITP Signed
note | HP*
note | Responsibility: Site Engineer
textbox | Date Completed:
section | 5.0 Pit Installation
checkpoint | 5.1 - Positioning Pit Components
note | Frequency: Each Lot
note | Acceptance Criteria: Pits must be constructed at the locations shown on the drawings.
note | Reference Documents: IFC Drawings
note | Inspection/ Test Method: Verify
note | Record of conformity: This ITP Signed
note | HP*
note | Responsibility: Surveyor
textbox | Date Completed:
checkpoint | 5.2 - Construction / Levels
note | Frequency: Each Lot
note | Acceptance Criteria: Install new pits as shown on drawings such that its collar and lid is level and at the same level as the finished adjacent surface.
note | Reference Documents: Appendix K- Technical Specifications - Section 3.8
note | Inspection/ Test Method: Verify
note | Record of conformity: This ITP Signed
note | HP*
note | Responsibility: Site Engineer
textbox | Date Completed:
checkpoint | 5.3 - Pit Entries
note | Frequency: Each Lot
note | Acceptance Criteria: Seal buried entries to all pits with a waterproof compound where necessary to prevent the ingress of soil and mud after backfill. Seal spare pit entries immediately after installation with a temporary cap.
note | Reference Documents: Appendix K- Technical Specifications - Section 3.8
note | Inspection/ Test Method: Verify
note | Record of conformity: This ITP Signed
note | HP*
note | Responsibility: Site Engineer / Site Supervisor
textbox | Date Completed:
checkpoint | 5.5 - Earth Pit Installation
note | Frequency: Each Lot
note | Acceptance Criteria: Install earth pit next to AGL pit as shown in IFC drawing.
note | Reference Documents: IFC Drawing 12554937-E050
note | Inspection/ Test Method: Visual Inspection
note | Record of conformity: This ITP Signed
note | IP
note | Responsibility: Site Engineer
textbox | Date Completed:
section | 6.0 Post Installation
checkpoint | 6.1 - As-built Documentation
note | Frequency: Prior to Practical Completion
note | Acceptance Criteria: Record the location of all new pits, as well as any existing pits utilised by the works. Prior to backfilling accurately record the location of routes of underground cables.
note | Reference Documents: Appendix K- Technical Specifications 3.18
note | Inspection/ Test Method: Verify
note | Record of conformity: As-built Survey Report
note | SCP
note | Responsibility: Site Engineer
textbox | Date Completed:
checkpoint-status | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: