## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 0a69f1b6-4419-4e3a-82d9-9e926efe991b |  | checklist | Wet Area Floor |  |  |  |  | Yes | Wet Area Floor | 7daa03fc-bea4-4c1b-ab1e-7924ece44039
checkpoint-status | 50898d3b-043f-4c49-a98d-d1562bda02d2 |  | checkpoint | Confirm if Waterproofing Contractors ITP’s have been received and confirms substrate is ready to receive tiles.
checkpoint-status | b8592097-4ae7-437b-9d6e-cea391789bfa |  | checkpoint | Visual Inspection shows that membrane has no signs of obvious surface damage.
checkpoint-status | ced4d4a4-a619-475d-ab18-e018ea30dfd4 |  | checkpoint | Confirm all falls to drain in wet area are minimum 1:100
checkpoint-status | deb6be5c-3bbf-479a-8f1b-8205a4f60eab |  | checkpoint | Confirm all falls to drain in shower are minimum 1:80
checkpoint-status | 3a2c21e7-59ea-42ec-9ba1-f9181a818c98 |  | checkpoint | Check finish floor level is at meter mark
checkpoint-status | 90f495b1-2a4e-4eb3-a61c-8ad8539b7628 |  | checkpoint | Confirm floor wastes are free of debris at tiling completion.
checklist-flat | b97e91ca-4282-4d02-905b-553998d34c4d |  | checklist | Wet Area Walls |  |  |  |  | Yes | Wet Area Walls | f01e663f-6170-4a56-86f6-626b30dd0eec
checkpoint-status | dedfbfce-89e3-48a8-bf23-45795c19c1cd |  | checkpoint | Confirm if Waterproofing Contractors ITP’s have been received and confirms substrate is ready to receive tiles.
checkpoint-status | 18925d70-1e15-441b-8ae6-8d0e65b19035 |  | checkpoint | Visual Inspection shows that membrane has no signs of obvious surface damage.
checkpoint-status | 84b96a57-6c31-4ffe-9cea-ceac308e0952 |  | checkpoint | Confirm all wall tiles are trowelled and not spot fixed
checkpoint-status | ba8fd488-870a-499b-b780-0f0bb33a590c |  | checkpoint | Check wall tiles are plumb and straight at tiling completion.