## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP Structure - Structural Steel - Column and Beams |  |  |  |  | Yes | ITP Structure - Structural Steel - Column and Beams | 0a17e8aa-8714-45cf-8930-c3656c254b63
checkpoint-group |  |  | section | Pre-Start
checkpoint-status |  |  | checkpoint | RL for support beams/ Plinth
checkpoint-status |  |  | checkpoint | Plate support/ bolts surveyed and checked as built
checkpoint-status |  |  | checkpoint | Slab QA received
checkpoint-status |  |  | checkpoint | checked tolerances, packing space
checkpoint-status |  |  | checkpoint | Area clean/clear for access equipment
checkpoint-group |  |  | section | Safety
checkpoint-status |  |  | checkpoint | review weights and lifting gears inspected
checkpoint-status |  |  | checkpoint | taglines secured
checkpoint-status |  |  | checkpoint | Work space demarcation
checkpoint-group |  |  | section | Erection
checkpoint-status |  |  | checkpoint | GN inspection
boolean | d5e46124-5087-5abb-a7e7-b9289c4e2258 |  | tickbox | i. Welds, bolts, plumb, alignment, etc. as per design
boolean | 2062daf2-f74a-5bc5-b458-2ffc50f7d9d5 |  | tickbox | ii. QA test requirements such as Torque test, Welding test (NDT - UT/MPI)
checkpoint-status |  |  | checkpoint | Structural Eng inspection report received and close-out
checkpoint-status |  |  | checkpoint | Council inspection report received and close-out
checkpoint-group |  |  | section | Post erection
checkpoint-status |  |  | checkpoint | Propping where required
checkpoint-status |  |  | checkpoint | Spot check RL’s and plumb
checkpoint-status |  |  | checkpoint | Primer touch-ups
checkpoint-status |  |  | checkpoint | Steel QA received
checkpoint-status |  |  | checkpoint | Grout under columns
checklist-sectioned |  |  | checklist | Civil - Drainage |  |  |  |  | Yes | Civil - Drainage Checklist | 124d2cb2-dde2-42b4-b954-8e1ca2a4c11d
checkpoint-group |  |  | section | Pre-start
checkpoint-status |  |  | checkpoint | Locates done on site – confirm no clash with pre-existing underground services
checkpoint-status |  |  | checkpoint | Appropriate permits in place
checkpoint-status |  |  | checkpoint | GL and datum provided
checkpoint-status |  |  | checkpoint | Upload drawings / check services depths, confirm location, filling/digging
checkpoint-status |  |  | checkpoint | Clear work area
checkpoint-group |  |  | section | Trenching
checkpoint-status |  |  | checkpoint | Delineation of area
checkpoint-status |  |  | checkpoint | Benching appropriate for ground conditions
checkpoint-status |  |  | checkpoint | Safety of trenching conditions and edge protection
checkpoint-status |  |  | checkpoint | Civil Eng inspection report received and close-out if unsuitable subgrade conditions exist
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Confirm correct bedding material being used and spot check RL’s
checkpoint-status |  |  | checkpoint | Manhole installation
boolean | 6cd6e903-e416-4d0c-ad82-38ffba52e1ff |  | tickbox | Confirm MH diameter
boolean | b20e33ff-fc40-4a16-8b7c-42ee5e2617e2 |  | tickbox | Reo
boolean | e2f4d1fa-78bc-40c5-9bec-31016f9be862 |  | tickbox | Joint sealing (if precast)
boolean | 7add8d48-662a-43f2-befd-1db905d9cf23 |  | tickbox | Invert level
boolean | 523ada56-529e-428b-8752-17e6d2d0b8e3 |  | tickbox | Confirm concrete grade
checkpoint-status |  |  | checkpoint | Pipes installed and correct junctions/connections
checkpoint-status |  |  | checkpoint | Civil Eng inspection report received and close-out for first pipe run
checkpoint-status |  |  | checkpoint | Council inspection report received and close-out
checkpoint-group |  |  | section | Backfilling
checkpoint-status |  |  | checkpoint | Appropriate backfill material
checkpoint-status |  |  | checkpoint | Backfill at 150mm lifts and compact as per Civil spec
checkpoint-group |  |  | section | Post Backfilling
checkpoint-status |  |  | checkpoint | Internal manhole works
boolean | c86e0894-36d8-5186-a72f-a7a7428cfd3e |  | tickbox | Civil Eng Splitter weir manholes – weir pre-pour inspection (first manhole)
boolean | c3a67ff4-f316-5eb8-94c4-e8e2570875ab |  | tickbox | Splitters and benching completed
checkpoint-status |  |  | checkpoint | Soakholes
boolean | 48fd210a-d850-52e2-942a-7ba870883371 |  | tickbox | Civil Eng Inspection of selection of rock bore installation report received and close-out
boolean | 4a6d677c-9c3b-5c2a-8e83-9eba1b8a40c8 |  | tickbox | Civil Eng inspection of selected of soakage testing
boolean | 51f0e36e-6c5e-5e7c-8c74-38d8b2b34328 |  | tickbox | Council inspection report received and close-out – as-built plan required
checkpoint-status |  |  | checkpoint | Drainage QA received and as built
checklist-sectioned |  |  | checklist | Structure – Structural Steel - Roof, Mezzanine & Shopfront |  |  |  |  | Yes | Structure – Structural Steel - Roof, Mezzanine & Shopfront | 20ab7197-068e-4285-9dcf-b94a9cc9f84c
checkpoint-group |  |  | section | Pre-Start
checkpoint-status |  |  | checkpoint | Panel sign-off/QA received
checkpoint-status |  |  | checkpoint | Check shopfront opening with Lancom - Key members location
checkpoint-status |  |  | checkpoint | Slab QA received (not required for roof steel install)
checkpoint-status |  |  | checkpoint | GL and datum provided
checkpoint-status |  |  | checkpoint | Area clean/clear for access equipment
checkpoint-group |  |  | section | Erection
checkpoint-status |  |  | checkpoint | GN inspection
boolean | 00ed825a-c6f5-5270-bf27-1e7703c2fc11 |  | tickbox | Welds, bolts, tensioning, etc. as per design
checkpoint-status |  |  | checkpoint | Structural Eng inspection report received and close-out
checkpoint-status |  |  | checkpoint | Council inspection report received and close-out
checkpoint-group |  |  | section | Post Erection
checkpoint-status |  |  | checkpoint | Propping where required
checkpoint-status |  |  | checkpoint | Spot check RL’s and plumb
checkpoint-status |  |  | checkpoint | Primer touch-ups
checkpoint-status |  |  | checkpoint | Steel QA received
checkpoint-status |  |  | checkpoint | Grout under columns
checklist-sectioned |  |  | checklist | Structure – Retaining Wall |  |  |  |  | Yes | Structure – Retaining Wall | 2b812d04-680a-4d7d-a098-f5d27f7be596
checkpoint-group |  |  | section | Pre-start
checkpoint-status |  |  | checkpoint | Foundation QA
checkpoint-status |  |  | checkpoint | GL and datum provided
checkpoint-status |  |  | checkpoint | Check starters
checkpoint-status |  |  | checkpoint | Clean work area
checkpoint-status |  |  | checkpoint | Confirm expansion joints
checkpoint-group |  |  | section | During works
checkpoint-status |  |  | checkpoint | Check reo details
checkpoint-status |  |  | checkpoint | Expansion joints
checkpoint-status |  |  | checkpoint | Bottom clean-outs for inspection
checkpoint-status |  |  | checkpoint | Check set-out
checkpoint-status |  |  | checkpoint | Pointing of joints
checkpoint-group |  |  | section | Pre-pour (blocks infill)
checkpoint-status |  |  | checkpoint | Reo sign off/QA
checkpoint-status |  |  | checkpoint | GN inspection
boolean | 1733e04a-f19f-5584-a5a9-7eb75ff06c37 |  | tickbox | Details checked
boolean | d8c18b7e-707b-5a67-afe9-58da36c6cba6 |  | tickbox | Any CANs
boolean | 982c83d1-b708-5ac3-b00c-ed885b316b9b |  | tickbox | Starters, cover checked
boolean | f8b24e9c-b2d0-5f99-a8cd-42c63a3a96da |  | tickbox | Clean-outs free of debris and ready to inspect/pour
checkpoint-status |  |  | checkpoint | Structural Eng inspection report received and close-out
checkpoint-status |  |  | checkpoint | Council inspection report received and close-out
checkpoint-status |  |  | checkpoint | Form work and clean-out covers in place
checkpoint-status |  |  | checkpoint | Pour sequence mark-up
checkpoint-status |  |  | checkpoint | Max 2.4m lifts
checkpoint-group |  |  | section | Access/Safety
checkpoint-status |  |  | checkpoint | Clear access for trucks/pump
checkpoint-status |  |  | checkpoint | Exposed reo capped
checkpoint-status |  |  | checkpoint | Safe access to all areas of pour
checkpoint-group |  |  | section | Post pour
checkpoint-status |  |  | checkpoint | Checks
boolean | 27c6c37a-5ec7-5664-87ab-a652d1114885 |  | tickbox | Finish
boolean | 034ad420-9149-5e49-b324-c847c9642e0e |  | tickbox | Levels
boolean | 32270be0-e164-556a-93f8-2b51de5a11b4 |  | tickbox | Starters
checkpoint-status |  |  | checkpoint | Block and pour QA received
checklist-sectioned |  |  | checklist | Toe Footings |  |  |  |  | Yes | QA - Toe Footings Checklist | 315e1716-cf52-4aa5-a3d6-e5ed632c234e
checkpoint-group |  |  | section | Pre-start
checkpoint-status |  |  | checkpoint | Panel QA received
checkpoint-status |  |  | checkpoint | GL and datum provided
checkpoint-status |  |  | checkpoint | Backfill to foundation level completed
checkpoint-status |  |  | checkpoint | Clean work area
checkpoint-group |  |  | section | Pre-Pour
checkpoint-status |  |  | checkpoint | Service trade sign off/QA
checkpoint-status |  |  | checkpoint | Formwork signoff/QA
checkpoint-status |  |  | checkpoint | Waterproof sign off/QA
checkpoint-status |  |  | checkpoint | Photo of water bar installed (TBC if required)
checkpoint-status |  |  | checkpoint | DPM where required
checkpoint-status |  |  | checkpoint | Reo sign off/QA
checkpoint-status |  |  | checkpoint | GN inspection
checkpoint-status |  |  | checkpoint | Details checked
checkpoint-status |  |  | checkpoint | Any CANs
checkpoint-status |  |  | checkpoint | Starters, scabbling, cover checked
checkpoint-status |  |  | checkpoint | Clean formwork and ready to pour
checkpoint-status |  |  | checkpoint | Structural Eng inspection report received and close-out
checkpoint-status |  |  | checkpoint | Council inspection report received and close-out
checkpoint-status |  |  | checkpoint | Pour sequence mark-up
checkpoint-group |  |  | section | Access/Safety
checkpoint-status |  |  | checkpoint | Clear access for trucks/pump
checkpoint-status |  |  | checkpoint | Exposed reo capped
checkpoint-status |  |  | checkpoint | Safe access to all areas of pour
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | Confirm mix
checkpoint-status |  |  | checkpoint | Confirm concrete is being tested (slump and cylinders)
checkpoint-status |  |  | checkpoint | Weather recorded
checkpoint-group |  |  | section | Post Pour
checkpoint-status |  |  | checkpoint | Finish
checkpoint-status |  |  | checkpoint | Levels
checkpoint-status |  |  | checkpoint | Starters
checkpoint-status |  |  | checkpoint | Pour QA received including dockets
checklist-sectioned |  |  | checklist | ITP Structure - Suspended Slab |  |  |  |  | Yes | ITP Structure - Suspended Slab | 3cc12c14-c9fe-4949-8901-403ced61ee78
checkpoint-group |  |  | section | Pre-start
checkpoint-status |  |  | checkpoint | Beam/Precast/Steel QA/ signoff
checkpoint-status |  |  | checkpoint | Edge protection in place
checkpoint-status |  |  | checkpoint | Access provided
checkpoint-status |  |  | checkpoint | GL and datum provided
checkpoint-status |  |  | checkpoint | Clean work area
checkpoint-group |  |  | section | Pre-pour
checkpoint-status |  |  | checkpoint | Propping sign-off/QA received
checkpoint-status |  |  | checkpoint | Services marked out and double mesh
checkpoint-status |  |  | checkpoint | Waterproofing sign-off/QA
boolean | 1caa78bc-8ed9-557b-8f33-1ec4503824f2 |  | tickbox | i. DPM including tapes and laps
checkpoint-status |  |  | checkpoint | Formwork signoff/QA
boolean | 4b9b77da-c578-5a93-adee-3a3e1885bd45 |  | tickbox | i. Step down/ falls
boolean | 855ba951-2aa7-5f5f-aa2a-8b0a785a5985 |  | tickbox | ii. Ties, propping, seal formworks
boolean | f3290555-49ca-5b51-8fcc-13585372ce5b |  | tickbox | iii. Seismic gap/expansion joints
checkpoint-status |  |  | checkpoint | Reo sign-off/QA received
checkpoint-status |  |  | checkpoint | GN inspection
boolean | a21af35b-d2f6-5044-94b3-f053e1cf4cb4 |  | tickbox | i. Details checked
boolean | 2ed8943e-837f-5cf8-9056-06772db590c6 |  | tickbox | ii. Openings checked
boolean | 17a02416-3245-5104-8fb5-04b101f39fab |  | tickbox | iii. Starters, cover, Trimmer installed, Hangers, saddle bars, Nib Reo location
boolean | 9b619e67-ccb0-5e99-abc8-014d903de047 |  | tickbox | iv. Clean and ready to pour
checkpoint-status |  |  | checkpoint | Structural Eng inspection report received and close-out
checkpoint-status |  |  | checkpoint | Council inspection report received and close-out
checkpoint-group |  |  | section | Access/Safety
checkpoint-status |  |  | checkpoint | Clear access for trucks/pump
checkpoint-status |  |  | checkpoint | Safe access to all areas of pour
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | Confirm mix
checkpoint-status |  |  | checkpoint | Confirm concrete is being tested (slump and cylinders)
checkpoint-status |  |  | checkpoint | Weather recorded
checkpoint-group |  |  | section | Post pour
checkpoint-status |  |  | checkpoint | Finish
checkpoint-status |  |  | checkpoint | Levels
checkpoint-status |  |  | checkpoint | Curing agent and canvas protection (standby)
checkpoint-status |  |  | checkpoint | Pour QA and dockets received
checklist-sectioned |  |  | checklist | Facade - Below Ground Waterproofing |  |  |  |  | Yes | Facade - Below Ground Waterproofing | 450919e1-d57a-4d4d-962b-9d92d78c1874
checkpoint-group |  |  | section | Pre-start
checkpoint-status |  |  | checkpoint | Panel QA received
checkpoint-status |  |  | checkpoint | Block wall QA received
checkpoint-status |  |  | checkpoint | Panel joints grouted/sealed
checkpoint-status |  |  | checkpoint | GL and datum provided
checkpoint-status |  |  | checkpoint | Clean work area
checkpoint-status |  |  | checkpoint | Safe access
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Waterproofing as per architectural drawings
checkpoint-status |  |  | checkpoint | Council inspection report received and close-out
checkpoint-group |  |  | section | Post install
checkpoint-status |  |  | checkpoint | Protective layers
checkpoint-status |  |  | checkpoint | Tanking QA received
checklist-sectioned |  |  | checklist | ITP Structure - Pre-cast Beams |  |  |  |  | Yes | ITP Structure - Pre-cast Beams | 51099cd6-4aac-48d6-8d06-67f04d1e2db0
checkpoint-group |  |  | section | Pre-start
checkpoint-status |  |  | checkpoint | GL and datum provided
checkpoint-status |  |  | checkpoint | Clean work area
checkpoint-status |  |  | checkpoint | Propping onsite and in place
checkpoint-group |  |  | section | Delivery Inspection
checkpoint-status |  |  | checkpoint | Check for damage/defects on arrival
checkpoint-status |  |  | checkpoint | Measurement checks in line w/ IFC dwg
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Check alignment and leveling meet specs. before placement
checkpoint-status |  |  | checkpoint | Ensure proper connection and anchoring
checkpoint-status |  |  | checkpoint | Check positioning and orientation
checkpoint-status |  |  | checkpoint | Structural Eng inspection report received and close-out
checkpoint-group |  |  | section | Post installation
checkpoint-status |  |  | checkpoint | Verify final positioning and alignment
checkpoint-status |  |  | checkpoint | Check for damage to the beams
checkpoint-status |  |  | checkpoint | Monitor and control grouting/backfilling processes
checkpoint-status |  |  | checkpoint | Beam installation QA
checklist-sectioned |  |  | checklist | Structure – In Situ Concrete |  |  |  |  | Yes | Structure – In Situ Concrete | 5438386e-45fe-4a16-8fa7-0f0eb8198930
checkpoint-group |  |  | section | Pre-start
checkpoint-status |  |  | checkpoint | Toe footing sign-off/QA received
checkpoint-status |  |  | checkpoint | GL and datum provided
checkpoint-status |  |  | checkpoint | Clean work area
checkpoint-status |  |  | checkpoint | Formwork signoff/QA
checkpoint-status |  |  | checkpoint | Reo sign off/QA
checkpoint-status |  |  | checkpoint | GN inspection
boolean | f4afdd8a-c977-5bbd-b2ce-5603d1cb8cd5 |  | tickbox | Details checked
boolean | cf7a75f9-6ea0-5598-ae03-be89634b63a1 |  | tickbox | Starters, scabbling, cover checked
boolean | efc2b0ba-3b9a-5e7e-b881-f150eed948f2 |  | tickbox | Clean formwork and ready to pou
checkpoint-status |  |  | checkpoint | Structural Eng inspection report received and close-out
checkpoint-status |  |  | checkpoint | Council inspection report received and close-out
checkpoint-status |  |  | checkpoint | Pour sequence mark-up
checkpoint-group |  |  | section | Access/safety
checkpoint-status |  |  | checkpoint | Access for sprayer/pump
checkpoint-status |  |  | checkpoint | Check TA
checkpoint-status |  |  | checkpoint | Safe access to all areas of spray
checkpoint-status |  |  | checkpoint | Exposed reo capped
checkpoint-group |  |  | section | Spray / Pour
checkpoint-status |  |  | checkpoint | Confirm mix
checkpoint-status |  |  | checkpoint | Confirm concrete is being tested (slump and cylinders)
checkpoint-status |  |  | checkpoint | Weather recorded
checkpoint-group |  |  | section | Post spray / pour
checkpoint-status |  |  | checkpoint | Checks
boolean | ce5936fb-8e0e-5442-9801-fffd5c95e226 |  | tickbox | Finish
boolean | 992922c9-907d-5778-9509-70522abec791 |  | tickbox | Levels
checkpoint-status |  |  | checkpoint | Pour QA received including concrete dockets
checklist-sectioned |  |  | checklist | Civil - Roads V2 |  |  |  |  | Yes | Civil - Roads | 59a6e795-9b21-4190-b83d-0ac4478999c7
checkpoint-group |  |  | section | Pre-Hand Over
checkpoint-status |  |  | checkpoint | In ground services QA and testing received
boolean | 42a61e44-440d-5a1e-8068-c1e9e48ae635 |  | tickbox | Electrical
boolean | c68df2b7-adde-5b3a-871a-292154477b66 |  | tickbox | Hydraulic
boolean | 41cee28b-f4b3-51ac-9062-3d755d000c7f |  | tickbox | Coms, Chorus
boolean | 854c83c4-5873-545f-8281-2e122731b927 |  | tickbox | Façade works completed
checkpoint-status |  |  | checkpoint | Drainage works complete
boolean | 3f8ea192-45de-53b4-86d1-d3de021e33b9 |  | tickbox | Cess pits, manhole benching and final RL, all ORG installed
checkpoint-status |  |  | checkpoint | Road clear and ready for hand over
checkpoint-group |  |  | section | Road Build-Up
checkpoint-status |  |  | checkpoint | Ensure road is built up in GP65
checkpoint-status |  |  | checkpoint | Ensure testing is completed.
boolean | 5a09b68e-2b8f-53da-9a15-a11867047b21 |  | tickbox | CRB 6 and proof rolled
checkpoint-group |  |  | section | Channel Drains Install
checkpoint-status |  |  | checkpoint | Correct RL to slab
checkpoint-status |  |  | checkpoint | Sumps installed
checkpoint-status |  |  | checkpoint | Channel drains QA
checkpoint-status |  |  | checkpoint | Channel drains encased on concrete
checkpoint-group |  |  | section | Kerb Install
checkpoint-status |  |  | checkpoint | Layout/pre-pour
boolean | a3fd0010-c33f-53e3-8302-9d006e7704fc |  | tickbox | Spot Check RL’s
boolean | 935bd2ec-153b-5ab7-8887-048730a75c82 |  | tickbox | Confirm mix
boolean | ad61d071-1033-5b5b-a8c6-fe63e323d767 |  | tickbox | Check kerb location
boolean | 80f1a504-1b67-5992-9f12-cd9d1cf99401 |  | tickbox | Check kerb type
checkpoint-status |  |  | checkpoint | Saw cuts 4m spacing
checkpoint-status |  |  | checkpoint | Chip/cracks
checkpoint-group |  |  | section | Concrete Loading Bays
checkpoint-status |  |  | checkpoint | Build Up
boolean | 32257c5f-a1f3-501d-b026-6a7135041c38 |  | tickbox | 100mm GP40
boolean | 033f8ade-ee8f-551f-9de5-385cab926729 |  | tickbox | Sand/fines
checkpoint-status |  |  | checkpoint | 1 layer 661 mesh 60mm top cover
checkpoint-status |  |  | checkpoint | Trimmer bars at corners 2*D16 1200mm long
boolean | ab0bf92e-decc-51a5-90b7-49c07d569f45 |  | tickbox | Unless corner coincides with sawcut
checkpoint-status |  |  | checkpoint | Trimmers around manholes
checkpoint-status |  |  | checkpoint | Refer Civil drawing 115
checkpoint-status |  |  | checkpoint | 175mm 30MPa
checkpoint-status |  |  | checkpoint | Chamfer at asphalt transition asphalt to sit 5mm proud.
checkpoint-status |  |  | checkpoint | Broom finish
checkpoint-status |  |  | checkpoint | Saw cuts
checkpoint-group |  |  | section | Walkway Install
checkpoint-status |  |  | checkpoint | Water cure 7 days
checkpoint-status |  |  | checkpoint | Chorus Tuds
boolean | 69b3d83d-440c-5d71-84a3-d0f9fd1c77e4 |  | tickbox | Set out to correct height and slope
checkpoint-status |  |  | checkpoint | Build Up/Falls
boolean | 8c3f67fa-10b2-548d-9d8a-99d03e7592b3 |  | tickbox | 150mm GP40 or 200mm GP65 and 100mm GP40
boolean | 1618d43a-cad7-525f-93f2-4013179c6ac0 |  | tickbox | Check RL’s at critical points
boolean | c242b2c7-f965-50de-a6ab-67a15fba6772 |  | tickbox | 25mm asphalt thickness
checkpoint-status |  |  | checkpoint | Lay Walkway
boolean | 7bef1887-1151-5472-8988-40fb83664587 |  | tickbox | Visual check finish/transitions
checkpoint-group |  |  | section | Manhole Lids Install
checkpoint-status |  |  | checkpoint | Set to proper RL and grade
checkpoint-group |  |  | section | Road Install
checkpoint-status |  |  | checkpoint | 100mm GP 40
boolean | 02eb2810-ff33-5624-9420-eaa67a0206f4 |  | tickbox | 3% slope from crown
boolean | 4972956e-2b55-537e-a605-fe849f6e775c |  | tickbox | 35mm Asphalt thickness
checkpoint-group |  |  | section | Line Marking
checkpoint-status |  |  | checkpoint | Layout as per Drawings
checklist-sectioned |  |  | checklist | Insitu Piles |  |  |  |  | Yes | Insitu Piles | 6c8786c0-c580-4d09-8ca4-5921f832d21b
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Pile location marked and confirmed
checkpoint-status |  |  | checkpoint | Pile Cage dimension and specification checked
label | 1ebc5b73-a0a5-50a2-b26f-fa90f8f31aac |  | note | Attach Docket
checkpoint-status |  |  | checkpoint | Pile drilling Card - refer details with the approved pile schedule
checkpoint-status |  |  | checkpoint | Engineer Inspection
checkpoint-status |  |  | checkpoint | Concrete pour & docket received
checkpoint-status |  |  | checkpoint | Mill Certificate received
checkpoint-status |  |  | checkpoint | Surveyworks Asbuilt check
checklist-sectioned |  |  | checklist | Fitout - Installation |  |  |  |  | Yes | Fitout - Installation | 6cf7a78b-9d80-4611-b8a1-b48b3df71d34
checkpoint-group |  |  | section | Mezzanine
checkpoint-status |  |  | checkpoint | Balustrade measure
checkpoint-status |  |  | checkpoint | Stairwell opening and location as per arch dwg 1701
checkpoint-status |  |  | checkpoint | Order stairwell
checkpoint-status |  |  | checkpoint | Check detail for balustrade (3302 – interior details)
checkpoint-status |  |  | checkpoint | Stair details as per arch and SD
checkpoint-status |  |  | checkpoint | Handrail site measure
checkpoint-status |  |  | checkpoint | Install eco-ply ceiling
holdpoint |  |  | signoff | Line/stop internal service penetration prior to eco ply
checkpoint-group |  |  | section | Bathroom Walls/Ceilings
checkpoint-status |  |  | checkpoint | Bathroom Lining
holdpoint |  |  | signoff | Bathroom are lined and fire stopped before bathroom framing
checkpoint-group |  |  | section | High Level Services
checkpoint-status |  |  | checkpoint | Services sign-off
checkpoint-status |  |  | checkpoint | Pre-line photos
holdpoint |  |  | signoff | Council Pre-Line Inspection
checkpoint-group |  |  | section | Set / Sand / Paint
checkpoint-status |  |  | checkpoint | Plasterboard fixings as per requirements (aqualine x standard)
checkpoint-group |  |  | section | Tiling and Waterproofing
checkpoint-status |  |  | checkpoint | Stopping complete
checkpoint-status |  |  | checkpoint | Sealants installed
checkpoint-status |  |  | checkpoint | Waterproofing QA
checkpoint-status |  |  | checkpoint | Tiling QA
checklist-sectioned |  |  | checklist | ITP - Structure - Slab on Grade |  |  |  |  | Yes | ITP - Structure - Slab on Grade | 701beb82-28f0-45b9-a79f-b3685dc5afa0
checkpoint-group |  |  | section | Pre-start
checkpoint-status |  |  | checkpoint | Columns/GB sign-off/QA received
checkpoint-status |  |  | checkpoint | Services sign-off
boolean | 2db17213-52f0-5fcf-82fe-bac71a4e8033 |  | tickbox | i. Electrical
boolean | 5dafd3d9-ca0f-5e88-95c1-1b002d6ef3a0 |  | tickbox | ii. Fire
boolean | 7a5cb49b-941c-5367-9781-1d50b178e975 |  | tickbox | iii. Hydraulic
boolean | bbb45f58-32b2-5d21-ad4d-ac5a73bc5821 |  | tickbox | iv. Comms and Fibre
checkpoint-status |  |  | checkpoint | Subgrade sign-off/QA received
boolean | b8181f2e-bd2c-5271-a8e7-38744f074124 |  | tickbox | i. Backfill and blinding
checkpoint-status |  |  | checkpoint | GL and datum provided
checkpoint-status |  |  | checkpoint | Clean work area
checkpoint-group |  |  | section | Pre-Pour
checkpoint-status |  |  | checkpoint | Waterproofing sign-off/QA
boolean | 2da6d233-ca40-5197-b8b3-6a70ba58b2f4 |  | tickbox | i. DPM including tapes and laps
boolean | 26241039-dfa7-5037-8cf3-fd1b17fff318 |  | tickbox | ii. Waterstop where applicable
checkpoint-status |  |  | checkpoint | Formwork signoff/QA
boolean | d8bc15f1-9368-533a-b4de-67dc94a2345c |  | tickbox | i. Step down/ falls
boolean | 0c082847-d6dd-5e98-a5a9-c2f4481df9bf |  | tickbox | ii. Ties, propping, seal formworks
boolean | 01bbc981-d2d5-58cc-9b04-bbb0fc919928 |  | tickbox | iii. Seismic gap/expansion joints
checkpoint-status |  |  | checkpoint | Reo sign off/QA
checkpoint-status |  |  | checkpoint | GN inspection
boolean | af1066b9-f756-508b-b045-1a1110ff77b2 |  | tickbox | i. Details checked
boolean | c328f3ae-58d7-55bf-97b8-881d55c3cffe |  | tickbox | ii. Any CANs
boolean | 600c7ed6-7566-55fe-8c80-fe17623ba846 |  | tickbox | iii. Check starters, scabbling, cover checked, thickenings
boolean | 732e662e-c306-5272-9f02-7beb1257f24b |  | tickbox | iv. Reinforcement size, spacing, supports.
boolean | 1b8ababd-265e-5b51-babf-f0b8eb13583e |  | tickbox | v. Clean formwork and ready to pour
checkpoint-status |  |  | checkpoint | Structural Eng inspection report received and close-out
checkpoint-status |  |  | checkpoint | Council inspection report received and close-out
checkpoint-group |  |  | section | Access/safety/protection
checkpoint-status |  |  | checkpoint | Clear access for trucks/pump
checkpoint-status |  |  | checkpoint | Safe access to all areas of pour
checkpoint-status |  |  | checkpoint | Panel and steel protection
checkpoint-status |  |  | checkpoint | Skip clean and ready
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | Confirm mix
checkpoint-status |  |  | checkpoint | Confirm concrete is being tested (slump and cylinders)
checkpoint-status |  |  | checkpoint | Weather recorded
checkpoint-group |  |  | section | Post pour
checkpoint-status |  |  | checkpoint | Finish
checkpoint-status |  |  | checkpoint | Levels
checkpoint-status |  |  | checkpoint | Curing agent
checkpoint-status |  |  | checkpoint | Saw cuts within 24h of pour and slurry removed
checkpoint-status |  |  | checkpoint | Pour QA received including concrete dockets
checklist-sectioned |  |  | checklist | Council Inspection |  |  |  |  | Yes | Council Inspection | 799e78b0-0f0a-4cc9-8f0f-6cd2d91081f2
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Inspection completed, attached and any relevant observations closed out
text | a811dc5b-ac83-5470-8e22-e6605df80fcd |  | textbox | Date of inspection
text | eaa36b12-dd05-5534-9855-79c4bd6c0898 |  | textbox | Type of inspection
text | bc8f8242-678a-5cb5-861d-6fb07e05967b |  | textbox | Area of inspection
boolean | 46b42bf2-dfd2-563b-b4d1-592bae41d634 |  | tickbox | Inspection report attached
select | bd8c65cf-b0da-509c-8292-66c15022fdc4 |  | dropdown | Inspection outcome | Fail, Partial Pass, Pass
holdpoint |  |  | signoff | Sign off
checkpoint-status |  |  | checkpoint | All relevant observation closeout evidence attached here if applicable
text | 747abae4-11b7-5603-bb0c-287329ec618b |  | textbox | Corrective action required
checklist-sectioned |  |  | checklist | ITP Structure - In Situ Concrete (RC beam) |  |  |  |  | Yes | ITP Structure - In Situ Concrete (RC beam) | 7a5e815d-937f-46f2-9114-3a1446ce3438
checkpoint-group |  |  | section | Pre-start
checkpoint-status |  |  | checkpoint | GL and datum provided
checkpoint-status |  |  | checkpoint | Clean work area
checkpoint-group |  |  | section | 2. Pre-pour
checkpoint-status |  |  | checkpoint | Formwork signoff/QA
boolean | ef670c48-dd41-58db-8dbc-dd945f5516a5 |  | tickbox | i. Check RL levels
boolean | 59eddef0-00da-5f22-a2ab-30a529c82e76 |  | tickbox | ii. Check Dimensions and alignment
boolean | bdefe7ea-878a-596b-aeb3-149950ee53bf |  | tickbox | iii. Check form ties and propping as per design
boolean | 80b1ee4d-6fd6-57a1-9ced-097408f47914 |  | tickbox | iv. Overall Cleanliness and Seals and ready to Pour
checkpoint-status |  |  | checkpoint | Reo sign off/QA
checkpoint-status |  |  | checkpoint | GN inspection
boolean | 4e5d82a3-f934-5139-8283-73ce2bc1f737 |  | tickbox | i. Details checked
boolean | 73f10c1c-277e-5c04-a6a9-7e931fee4a14 |  | tickbox | ii. Scabbling, Starters/ embedment depth, cover checked
boolean | f5731e97-5ca3-56f6-8c3c-6af68c52ff6f |  | tickbox | iii. Check reinforcements size, spacing and cleanliness
checkpoint-status |  |  | checkpoint | Structural Eng inspection report received and close-out
checkpoint-status |  |  | checkpoint | Council inspection report received and close-out
checkpoint-group |  |  | section | Access/safety
checkpoint-status |  |  | checkpoint | Access for sprayer/pump
checkpoint-status |  |  | checkpoint | Safe access to all areas of pour
checkpoint-status |  |  | checkpoint | Exposed reo capped
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | Confirm mix
checkpoint-status |  |  | checkpoint | Confirm concrete is being tested (slump and cylinders)
checkpoint-status |  |  | checkpoint | Weather recorded
checkpoint-group |  |  | section | Post pour
checkpoint-status |  |  | checkpoint | Checks
boolean | 96130089-885a-5f11-b19d-965309b31ae8 |  | tickbox | i. Finish
boolean | 70429381-23b3-5218-8f98-dc19683a3743 |  | tickbox | ii.Levels
checkpoint-status |  |  | checkpoint | Pour QA received including concrete dockets
checklist-sectioned |  |  | checklist | Civil – Buildings Subgrade |  |  |  |  | Yes | Civil – Buildings Subgrade | 89ad418b-6828-4f01-ac3c-f092ee049816
checkpoint-group |  |  | section | Subgrade base
checkpoint-status |  |  | checkpoint | Geotech Eng inspection report received- and close-out
checkpoint-status |  |  | checkpoint | Geotech Eng Inspection of subgrade and proof rolling prior to filling
checkpoint-group |  |  | section | Building Subgrade build-up
checkpoint-status |  |  | checkpoint | GL and datum provided
checkpoint-status |  |  | checkpoint | Placement of hardfill layer compacted as per design
checkpoint-status |  |  | checkpoint | Drainage piping installed under foundation level
checkpoint-status |  |  | checkpoint | Platforms spot checks heights and location
checkpoint-group |  |  | section | Subgrade Sign-off
checkpoint-status |  |  | checkpoint | Subgrade QA and test results received
checkpoint-status |  |  | checkpoint | Geotech Eng Inspection of subgrade and proof rolling report received and close-out
checklist-flat |  |  | checklist | Fitout - Prestart |  |  |  |  | Yes | Fitout - Prestart | 8b6081c1-5601-4967-a12b-c1d415cf113f
checkpoint-status |  |  | checkpoint | Slab poured and curing complete
checkpoint-status |  |  | checkpoint | Mezzanine steel QA/Sign-off
checkpoint-status |  |  | checkpoint | Intumescent paint to mezzanine steel (beams and posts)
checkpoint-status |  |  | checkpoint | GL and datum provided
checkpoint-status |  |  | checkpoint | Sealant complete between precast panels
checklist-sectioned |  |  | checklist | Structure – Pre-cast Panels |  |  |  |  | Yes | Structure – Pre-cast Panels | 8d6fdf3c-5718-4919-aac9-5044a68cc761
checkpoint-group |  |  | section | Pre-start
checkpoint-status |  |  | checkpoint | GL and datum provided
checkpoint-status |  |  | checkpoint | Timber guides installed – including spacers
checkpoint-status |  |  | checkpoint | Clean work area
text | 12a56350-744f-5467-9068-838ec0843b58 |  | textbox | Min days/MPa since pour
checkpoint-status |  |  | checkpoint | Propping onsite
checkpoint-status |  |  | checkpoint | Deadmen on site and in position
checkpoint-group |  |  | section | Delivery
checkpoint-status |  |  | checkpoint | Check for damage/defects on arrival
checkpoint-status |  |  | checkpoint | Measurement checks in line w/ IFC SD
checkpoint-status |  |  | checkpoint | Panels unloaded correctly
checkpoint-group |  |  | section | Installed in correct location as per SD
checkpoint-status |  |  | checkpoint | Measure internal dimensions
checkpoint-status |  |  | checkpoint | Sample vertical check
checkpoint-group |  |  | section | Propping completed
checkpoint-status |  |  | checkpoint | Hit/miss and deadmen as per propping design.
checkpoint-status |  |  | checkpoint | Check for damage to panels
checkpoint-status |  |  | checkpoint | Panel installation QA - (Packer, verticality, positioning…)
checklist-sectioned |  |  | checklist | Civil – Footpath In Ground Services |  |  |  |  | Yes | Civil – Footpath In Ground Services | 935eee73-0071-4b5d-9fc2-aefe02fd9712
checkpoint-group |  |  | section | Pre-start
checkpoint-status |  |  | checkpoint | Stormwater laterals exposed and extended to sump locations
checkpoint-status |  |  | checkpoint | Trench formed and sand bed completed
checkpoint-status |  |  | checkpoint | Conduits underslab completed
checkpoint-group |  |  | section | Services trench
checkpoint-status |  |  | checkpoint | Electrical cables running from DB location to each unit
checkpoint-status |  |  | checkpoint | Electrical cables top covered and cable slab installed and covered
checkpoint-status |  |  | checkpoint | Hydraulic service joined and water tested
checkpoint-status |  |  | checkpoint | Chorus pits & tuds located and levels agreed
checkpoint-status |  |  | checkpoint | Fire alarms conduits and cables completed
checkpoint-status |  |  | checkpoint | Conduits crossing roads where required
checkpoint-group |  |  | section | Post-services
checkpoint-status |  |  | checkpoint | Fines cover
checkpoint-status |  |  | checkpoint | Chorus pits to final RL
checkpoint-status |  |  | checkpoint | Final backfill & compacted
checklist-sectioned |  |  | checklist | Structure – Suspended Slab |  |  |  |  | Yes | Structure – Suspended Slab | 9a8071b7-6694-4e0f-a335-284031bea95a
checkpoint-group |  |  | section | Pre-start
checkpoint-status |  |  | checkpoint | Toe footing sign-off/QA received
checkpoint-status |  |  | checkpoint | Roof Steel sign-off – all bracings completed
checkpoint-status |  |  | checkpoint | Panel props removed
checkpoint-status |  |  | checkpoint | Retaining wall sign-off/QA received
checkpoint-status |  |  | checkpoint | Steel sign-off/QA received
checkpoint-status |  |  | checkpoint | Services sign-off/QA received
boolean | 369e5a55-3ba4-5d2c-915d-ba9815563899 |  | tickbox | Electrical
boolean | ec9f13b7-84d0-5c69-931d-83b6c537a458 |  | tickbox | Fire
boolean | 45ff9656-1859-52c5-94dd-fc28ad626e95 |  | tickbox | Hydraulic
boolean | 05171d84-a2bf-5c30-bbfe-f64d806c9e5c |  | tickbox | Comms and Fibre
checkpoint-status |  |  | checkpoint | Sacrificial timber propping installed
checkpoint-status |  |  | checkpoint | GL and datum provided
checkpoint-status |  |  | checkpoint | Clean work area
checkpoint-group |  |  | section | Pre-pour
checkpoint-status |  |  | checkpoint | Flat slab sign-off/QA received
checkpoint-status |  |  | checkpoint | Formwork sign-off/QA received
boolean | d232d833-e57b-542f-bd1f-45ebfd9e8096 |  | tickbox | Seal perimeter and services penetration
checkpoint-status |  |  | checkpoint | Services sign-off/QA received
checkpoint-status |  |  | checkpoint | Reo sign-off/QA received
checkpoint-status |  |  | checkpoint | GN inspection
boolean | e0ca422d-cda2-5b59-adc2-b0300fbdc4f0 |  | tickbox | Details checked
boolean | 9233c1c3-97de-5ea2-a2b9-3332f995e06a |  | tickbox | Starters, scabbling, cover checked
boolean | 5dd8af4b-521c-55ed-bf3e-d038d05b4aee |  | tickbox | Clean formwork and ready to pour
checkpoint-status |  |  | checkpoint | Structural Eng inspection report received and close-out
checkpoint-status |  |  | checkpoint | Council inspection report received and close-out
checkpoint-status |  |  | checkpoint | Pour sequence mark-up
checkpoint-group |  |  | section | Access/Safety
checkpoint-status |  |  | checkpoint | Clear access for trucks/pump
checkpoint-status |  |  | checkpoint | Safe access to all areas of pour
checkpoint-status |  |  | checkpoint | Panel and steel protection
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | Confirm mix
checkpoint-status |  |  | checkpoint | Confirm concrete is being tested (slump and cylinders)
checkpoint-status |  |  | checkpoint | Weather recorded
checkpoint-status |  |  | checkpoint | Screed to falls in bathroom
checkpoint-group |  |  | section | Post pour
checkpoint-status |  |  | checkpoint | Finish
checkpoint-status |  |  | checkpoint | Levels
checkpoint-status |  |  | checkpoint | Curing agent
checkpoint-status |  |  | checkpoint | Saw cuts within 24h of pour and slurry removing
checkpoint-status |  |  | checkpoint | Pour QA received
checklist-sectioned |  |  | checklist | Insitu Piles | itp |  |  |  | Yes | Insitu Piles Checklist | a88129a9-94f4-4f1a-bac4-b416889401c8
checkpoint-group |  |  | section | Preliminary Tasks
checkpoint-status |  |  | checkpoint | Confirm Pile installation plan including methodology, material and equipment submitted
label | aad92bda-2664-5684-85d8-ac46105d5e3f |  | note | Sub-Contract signing
checkpoint-group |  |  | section | Site Start Up Tasks
checkpoint-status |  |  | checkpoint | Confirm full services and utilities check by subcontractor. Permit to work in place
label | 1ff69a78-304f-5ff1-bef9-2327ab135518 |  | note | Prior to mobilization
checkpoint-status |  |  | checkpoint | Confirm an adequate site surface has been established for a safe working platform and check periodically once installation is underway.
label | 274e4199-4609-5c0e-bcf0-af268e3c000a |  | note | 1 week prior and intermittently after
checkpoint-status |  |  | checkpoint | Confirm all piles to be set out in accordance with design requirements and appropriate procedures taken to protect adjacent services, structures etc.
label | 39b65b1d-06eb-5451-9329-ee7c0c1ba814 |  | note | Prior to installation of 1st pile
checkpoint-group |  |  | section | Construction Tasks
checkpoint-status |  |  | checkpoint | Confirm correct equipment is in place to check the verticality and position of rig, and that the mast is vertical in both axes prior to construction of each pile
label | 8f90764a-26a5-54fd-ad0e-41520fa86710 |  | note | Prior to installation of 1st pile and periodically after
checkpoint-status |  |  | checkpoint | Confirm pile construction has not been carried out within the specified distance of newly cast piles until concrete has attained the strength specified. Refer to installation methodology provided.
label | 70b4018e-e24d-5d43-afcf-77c7e21de1c2 |  | note | Each pile
checkpoint-status |  |  | checkpoint | Confirm that pile depth has been checked at completion of boring. Toe level to at or below target depth
text | 1d929ece-f6f1-5a54-b680-7583325fbe41 |  | textbox |  |  |  | m depth
label | 31fa7856-713f-5a2e-8d38-fd9bc67d051c |  | note | Each pile
checkpoint-status |  |  | checkpoint | Sight delivery dockets to confirm all in accordance with engineers specification.
label | 5b01ba3e-dffa-5ac4-a11f-64a1cae3968d |  | note | Each concrete delivery
checkpoint-status |  |  | checkpoint | Confirm that subcontractor has checked that steel is not excessively rusted, cage has been sturdily constructed and that the correct cage has been installed for each pile.
label | 7af01921-38cc-575c-8eb4-2f2e9815a008 |  | note | Each reinf. Cage batch
checkpoint-status |  |  | checkpoint | Dimensional check, length, bar diameter, nr of bars. Make sure compliant with technical package.
label | 61f8d457-3081-5c32-935f-e095776a9b7f |  | note | Random control check
checkpoint-status |  |  | checkpoint | Check cage has been installed at the correct level and is centralised, ensure cover requirements are met. All as per specification and documents.
label | c9a27d0a-9e00-544c-af03-c5f0e10465a1 |  | note | Random control check
checkpoint-status |  |  | checkpoint | Obtain Engineers site reports and signoff as required.
label | a8d66440-d4f6-56dc-ac2c-85f4087b08a3 |  | note | As per Contract
checkpoint-status |  |  | checkpoint | Confirm top of piles have been trimmed to elevations indicated on design drawings prior to construction of pile caps.
label | a1f5f14b-1587-5c9c-84f9-c2d8b78ae80c |  | note | After completion of installation
checkpoint-group |  |  | section | Post Construction Tasks
checkpoint-status |  |  | checkpoint | Obtain as-built drawings to confirm grid layout is completely in accordance with all drawings and specifications (all within tolerance)
label | 937c4592-d188-5c57-9c64-385a32ef5100 |  | note | After completion
checkpoint-status |  |  | checkpoint | All data and records required provided to Structural Engineer after completion of pile installation (as per required contract specification). Include any Engineer’s site reports and sign off.
label | 157dad8c-3e70-5546-b991-bcbd5b78a21e |  | note | After completion of works
checkpoint-status |  |  | checkpoint | Dynamic pile testing (if required by the contract) carried out as per specification requirements. Written pile test results submitted for acceptance. Obtain sign off from Structural Engineer. (Attach certificate)
label | 269a9bb3-f1c9-5664-a58f-17b5ac3698af |  | note | As per contract requirements
checkpoint-status |  |  | checkpoint | Confirm all inspections as identified on the cover page have been undertaken
label | 06600b44-5607-5b42-b8d8-ad2c9d51181e |  | note | After Completion
checkpoint-status |  |  | checkpoint | Subcon QA received including pilecards and dockets
checklist-sectioned |  |  | checklist | Facade – Shop Front |  |  |  |  | Yes | Facade – Shop Front | aaedfc85-0acc-4cdf-b0bc-498b79bff4ca
checkpoint-group |  |  | section | Pre-start
checkpoint-status |  |  | checkpoint | Site measure complete
checkpoint-status |  |  | checkpoint | Steel QA received
checkpoint-status |  |  | checkpoint | Carpentry sign-off received
checkpoint-status |  |  | checkpoint | GL and datum provided
checkpoint-status |  |  | checkpoint | Clean work area
checkpoint-status |  |  | checkpoint | Waterproofing sign off as per details
checkpoint-group |  |  | section | Install
checkpoint-status |  |  | checkpoint | Prime surfaces
checkpoint-status |  |  | checkpoint | Seismic frames
checkpoint-status |  |  | checkpoint | Inserts
checkpoint-status |  |  | checkpoint | Glazing
checkpoint-status |  |  | checkpoint | Air seals completed
checkpoint-status |  |  | checkpoint | Bespoke flashings measured
checkpoint-group |  |  | section | Post install
checkpoint-status |  |  | checkpoint | Protection 1.5m high
checkpoint-status |  |  | checkpoint | AAMA 501 water test completed and passed – results received
checkpoint-status |  |  | checkpoint | QA subby and consultant (inspection requirements?)
checklist-sectioned |  |  | checklist | ITP Structure - In Situ Concrete (RC Column) |  |  |  |  | Yes | ITP Structure - In Situ Concrete (RC Column) | b6b283c2-7f31-40da-9bfd-0103cd1d2e9d
checkpoint-group |  |  | section | Pre-start
checkpoint-status |  |  | checkpoint | Footing sign-off/QA received
checkpoint-status |  |  | checkpoint | GL and datum provided
checkpoint-status |  |  | checkpoint | Clean work area
checkpoint-group |  |  | section | Pre-pour
checkpoint-status |  |  | checkpoint | GN inspection
boolean | 8685dbce-2133-5d07-8902-bf433aa93781 |  | tickbox | i. Details checked
boolean | 4aa88abf-c69b-52a2-bdfa-35c68e892550 |  | tickbox | ii. Scabbling, Starters/ embedment depth, cover checked and cast in items
boolean | 1902df8e-3afa-5e19-98df-9adcf3cb7f9b |  | tickbox | iii. Check reinforcements size, spacing and cleanliness
checkpoint-status |  |  | checkpoint | Formwork signoff/QA
boolean | 8300dac9-f555-52cb-a65e-86f5edebee79 |  | tickbox | i. Check RL levels and benchmarks
boolean | 09c13d34-cb05-5209-aef2-cdcf91e72529 |  | tickbox | ii. Check Dimensions and alignment
boolean | ea780471-ca3d-5fad-b208-36d8c3777237 |  | tickbox | iii. Check form ties and propping
boolean | 125efa4b-7a4d-5650-8cc1-1622edd5f5a0 |  | tickbox | iiii. Overall Cleanliness and Seals and ready to Pour
checkpoint-status |  |  | checkpoint | Reo sign off/QA
checkpoint-status |  |  | checkpoint | Structural Eng inspection report received and close-out
checkpoint-status |  |  | checkpoint | Council inspection report received and close-out
checkpoint-group |  |  | section | Access/safety
checkpoint-status |  |  | checkpoint | Access for sprayer/pump
checkpoint-status |  |  | checkpoint | Safe access to all areas of spray
checkpoint-status |  |  | checkpoint | Exposed reo capped
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | Confirm mix
checkpoint-status |  |  | checkpoint | Confirm concrete is being tested (slump and cylinders)
checkpoint-status |  |  | checkpoint | Weather recorded
checkpoint-group |  |  | section | Post pour
checkpoint-status |  |  | checkpoint | Checks
boolean | 8b38a299-6686-54d9-b015-fa67395355b5 |  | tickbox | i. Finish
boolean | b522fb61-afcb-571e-bf33-915efc435e9e |  | tickbox | ii.Levels
checkpoint-status |  |  | checkpoint | Pour QA received including concrete dockets
checklist-sectioned |  |  | checklist | ITP Structure - Suspended Slab - comflor |  |  |  |  | Yes | ITP Structure - Suspended Slab - comflor | bf23e088-91d7-4158-a380-84a33bacb782
checkpoint-group |  |  | section | Pre-start
checkpoint-status |  |  | checkpoint | Beam QA/ signoff
checkpoint-status |  |  | checkpoint | Edge protection in place
checkpoint-status |  |  | checkpoint | Access provided
checkpoint-status |  |  | checkpoint | GL and datum provided
checkpoint-status |  |  | checkpoint | Clean work area
checkpoint-group |  |  | section | Pre-pour
checkpoint-status |  |  | checkpoint | Comflor sign-off/QA received
boolean | d3910e96-7c62-5bd0-b1e2-e015d3c01040 |  | tickbox | i. Stud testing completed
checkpoint-status |  |  | checkpoint | Propping sign-off/QA received
checkpoint-status |  |  | checkpoint | Services marked out and double mesh
checkpoint-status |  |  | checkpoint | Formwork signoff/QA
boolean | 82d8dbd1-2a07-57ad-8159-dad012c040e7 |  | tickbox | i. Step down/ falls
boolean | 19f28f3b-ec5c-5841-84ac-a88deb13f20a |  | tickbox | ii. Ties, propping, seal formworks
checkpoint-status |  |  | checkpoint | Reo sign-off/QA received
checkpoint-status |  |  | checkpoint | GN inspection
boolean | d1542daf-d937-5502-a197-deb99b3d7e66 |  | tickbox | i. Details checked
boolean | 22227eb9-bf7f-56e8-8da3-62a88b5829d4 |  | tickbox | ii. Openings checked
boolean | 2f2e36ca-b90e-55e0-9539-6d4ecfdfb2af |  | tickbox | iii. Starters, cover, Trimmer installed, Hangers, saddle bars, Nib Reo location
boolean | 4a43084e-b270-544f-9f77-a82293ef9f96 |  | tickbox | iv. Clean and ready to pour
checkpoint-status |  |  | checkpoint | Structural Eng inspection report received and close-out
checkpoint-status |  |  | checkpoint | Council inspection report received and close-out
checkpoint-group |  |  | section | Access/Safety
checkpoint-status |  |  | checkpoint | Clear access for trucks/pump
checkpoint-status |  |  | checkpoint | Safe access to all areas of pour
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | Confirm mix
checkpoint-status |  |  | checkpoint | Confirm concrete is being tested (slump and cylinders)
checkpoint-status |  |  | checkpoint | Weather recorded
checkpoint-group |  |  | section | Post pour
checkpoint-status |  |  | checkpoint | Finish
checkpoint-status |  |  | checkpoint | Levels
checkpoint-status |  |  | checkpoint | Curing agent and canvas protection (standby)
checkpoint-status |  |  | checkpoint | Pour QA and dockets received
checklist-sectioned |  |  | checklist | Façade – Eave and Roof |  |  |  |  | Yes | Façade – Eave and Roof | cc471d2d-f573-4042-92f3-c435598922f3
checkpoint-group |  |  | section | Pre-start
checkpoint-status |  |  | checkpoint | Steel QA received
checkpoint-status |  |  | checkpoint | GL and datum provided
checkpoint-status |  |  | checkpoint | Clean work area
checkpoint-status |  |  | checkpoint | Safe access
checkpoint-group |  |  | section | Eaves
checkpoint-status |  |  | checkpoint | Framing - DPC between timber and steel
checkpoint-status |  |  | checkpoint | Framing -Timber frame fixings to steel frame/purlins
checkpoint-group |  |  | section | Services
checkpoint-status |  |  | checkpoint | Services signoff/QA including nogs
checkpoint-group |  |  | section | RAB
checkpoint-status |  |  | checkpoint | HOLD POINT - Council pre-line inspection report received and close-out
checkpoint-status |  |  | checkpoint | RAB signoff/QA
checkpoint-group |  |  | section | ACP
checkpoint-status |  |  | checkpoint | ACP installed as per shop drawings
checkpoint-status |  |  | checkpoint | Services cables pulled through – check builders work
checkpoint-status |  |  | checkpoint | Sealants
checkpoint-status |  |  | checkpoint | ACP signoff/QA
checkpoint-group |  |  | section | Roof
checkpoint-status |  |  | checkpoint | Framing - DPC between timber and steel
checkpoint-status |  |  | checkpoint | Framing - Timber frame fixings to steel frame/purlins
checkpoint-status |  |  | checkpoint | Gutter waterproofing sign-off/QA
checkpoint-status |  |  | checkpoint | ILD Testing
checkpoint-status |  |  | checkpoint | Mesh and underlay installed
checkpoint-status |  |  | checkpoint | Check roof sheets fixings
checkpoint-status |  |  | checkpoint | Service penetrations installed
checkpoint-status |  |  | checkpoint | Proper septation
checkpoint-status |  |  | checkpoint | Roof finishes
checkpoint-status |  |  | checkpoint | Painting panels
checkpoint-status |  |  | checkpoint | Cap flashings
checkpoint-status |  |  | checkpoint | Apron flashings
checkpoint-status |  |  | checkpoint | Services penetrations
checkpoint-status |  |  | checkpoint | EPDM tape / termination bar and sealants installed
checkpoint-status |  |  | checkpoint | Gutter and downpipe installed
checkpoint-status |  |  | checkpoint | Roof signoff/QA
checkpoint-group |  |  | section | Roof safety anchors
checkpoint-status |  |  | checkpoint | Check layout (positioning)
checkpoint-status |  |  | checkpoint | Roof anchors tagged
checkpoint-status |  |  | checkpoint | Roof anchors signoff/QA
checklist-sectioned |  |  | checklist | ITP Structure - Lift Pit |  |  |  |  | Yes | ITP Structure - Lift Pit | d22ba7ea-f017-4e3c-bf45-6a376e3c8ec7
checkpoint-group |  |  | section | 1. Pre-start
checkpoint-status |  |  | checkpoint | Clear work Area
checkpoint-status |  |  | checkpoint | QA for sub-grade and relevant services received (if applicable)
checkpoint-status |  |  | checkpoint | GL and datum provided
checkpoint-status |  |  | checkpoint | Geotechnical Eng inspection report received and closed-out
checkpoint-group |  |  | section | 2. Pre-pour
checkpoint-status |  |  | checkpoint | Waterproof sign off/QA
boolean | 92757ad1-c7d4-5289-93e1-b6ca644f4f95 |  | tickbox | i. DPM including tapes and laps
checkpoint-status |  |  | checkpoint | Formwork signoff/QA
boolean | 5c0b3054-469b-5a0e-852a-4dfcd210ec41 |  | tickbox | i. Check RL levels
boolean | 484ccc91-c87a-5d5a-852a-6ff7ab5f7053 |  | tickbox | ii. Check Dimensions and alignment
boolean | e1fa039b-647d-5d68-bba0-cc1bf9ffdaa7 |  | tickbox | iii. Check form ties and propping
boolean | 07fe1de6-af71-50d4-aa88-4dbb505d32ce |  | tickbox | iv. Overall Cleanliness and Seals and ready to Pour
checkpoint-status |  |  | checkpoint | Reo sign off/QA
checkpoint-status |  |  | checkpoint | GN inspection
boolean | 8e58b85f-60d0-5646-885f-7cfd1888f2d9 |  | tickbox | i. Details checked and shop drawings
boolean | 9fdc42d8-3094-5449-b9ac-8a92ce69478a |  | tickbox | ii. Scabbling, Starters/ embedment depth, cover checked
boolean | e38adc7c-ab46-5e17-a5b8-78140768f6c8 |  | tickbox | iii. Check reinforcements size, spacing and cleanliness
checkpoint-status |  |  | checkpoint | Structural Eng inspection report received and close-out
checkpoint-status |  |  | checkpoint | Council inspection report received and close-out
checkpoint-group |  |  | section | 3. Access/Safety
checkpoint-status |  |  | checkpoint | Clear access for trucks/pump
checkpoint-status |  |  | checkpoint | Safe access to all areas of pour
checkpoint-group |  |  | section | 4. Pour
checkpoint-status |  |  | checkpoint | Confirm mix
checkpoint-status |  |  | checkpoint | Confirm concrete is being tested (slump and cylinders)
checkpoint-status |  |  | checkpoint | Weather recorded
checkpoint-group |  |  | section | 5. Post pour
checkpoint-status |  |  | checkpoint | Checks
boolean | 99706468-0534-5ca0-941b-8e2c2bc50909 |  | tickbox | i. Finish
boolean | 1f07d691-ac0a-5ce2-a552-485cc3bdba43 |  | tickbox | ii. Levels
checkpoint-status |  |  | checkpoint | Pour QA received including dockets
checkpoint-status |  |  | checkpoint | Starters
checkpoint-status |  |  | checkpoint | Pour QA received including dockets
checklist-sectioned |  |  | checklist | ITP Structure - Pre-cast Panels |  |  |  |  | Yes | ITP Structure - Pre-cast Panels | dae1c41f-75c5-4f63-be1c-97d7ada58487
checkpoint-group |  |  | section | Pre-start
checkpoint-status |  |  | checkpoint | GL and datum provided
checkpoint-status |  |  | checkpoint | Timber guides installed - including spacers
checkpoint-status |  |  | checkpoint | Waterstop Installed
checkpoint-status |  |  | checkpoint | Clear work area for delivery and Install
checkpoint-status |  |  | checkpoint | Ground Beams QA received
checkpoint-status |  |  | checkpoint | Min days/MPa since pour
checkpoint-status |  |  | checkpoint | Propping onsite
checkpoint-group |  |  | section | Delivery Inspection
checkpoint-status |  |  | checkpoint | Check for damage/defects on arrival
checkpoint-status |  |  | checkpoint | Measurement checks in line w/ IFC dwg
checkpoint-status |  |  | checkpoint | Panels unloaded correctly
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Installed in correct location as per Dwg
checkpoint-status |  |  | checkpoint | Check temporary bracing as per requirements
checkpoint-status |  |  | checkpoint | Sample verticality check
checkpoint-group |  |  | section | Post Installation
checkpoint-status |  |  | checkpoint | As per propping design.
checkpoint-status |  |  | checkpoint | Check for damage to panels
checkpoint-status |  |  | checkpoint | Confirm all Grouting completed
checkpoint-status |  |  | checkpoint | Panel installation QA
checklist-sectioned |  |  | checklist | Structure – Slab on Grade |  |  |  |  | Yes | Structure – Slab on Grade | de2d0bf2-e5ca-4331-b87c-6f56fe534347
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Toe footing sign-off/QA received
checkpoint-status |  |  | checkpoint | Services sign-off
boolean | 3cacbbe6-deed-56ef-9a96-182b249c4a69 |  | tickbox | Electrical
boolean | c5b5b5ad-c847-5cc0-b6c5-dd7bc5ebb9ec |  | tickbox | Fire
boolean | ca4dcabf-ea4d-5cdb-b88d-028e128c4428 |  | tickbox | Hydraulic
boolean | 017a6fab-94f8-57d2-95e3-2047cfab7b82 |  | tickbox | Comms and Fibre
checkpoint-status |  |  | checkpoint | Subgrade sign-off/QA received
boolean | c79730fe-7111-52bd-beff-8b3b78c2f39a |  | tickbox | Backfill and blinding
checkpoint-status |  |  | checkpoint | Roof Steel sign-off – all bracings completed
checkpoint-status |  |  | checkpoint | Panel props removed
checkpoint-status |  |  | checkpoint | GL and datum provided
checkpoint-status |  |  | checkpoint | Clean work area
checkpoint-group |  |  | section | Pre-Pour
checkpoint-status |  |  | checkpoint | Service trades sign-off/QA
checkpoint-status |  |  | checkpoint | Waterproofing sign-off/QA
boolean | a18eb022-c736-58a0-b4b3-005a71c1af66 |  | tickbox | DPM including tapes and laps
boolean | 974b6530-07d5-5f33-b7fa-ce89f8ee5661 |  | tickbox | Waterstop where applicable
checkpoint-status |  |  | checkpoint | Formwork signoff/QA
boolean | 748055f6-8ecf-5b95-a742-773f20525f73 |  | tickbox | Entrance set-downs
boolean | 6f5ed65b-e067-57a2-a053-771d446ba17a |  | tickbox | Shower set-downs
checkpoint-status |  |  | checkpoint | Reo sign off/QA
checkpoint-status |  |  | checkpoint | GN inspection
boolean | 846fe06b-0f13-53b1-929b-2932d75195fe |  | tickbox | Details checked
boolean | 15e0b0b8-72f5-5411-91dd-138fb885c0ac |  | tickbox | Any CANs
boolean | 71a9b94d-2d04-5265-b1fb-c3fb0c869b04 |  | tickbox | Starters, scabbling, cover checked, thickenings
boolean | a689524a-4708-5075-a16f-0bfc26a49f8c |  | tickbox | Clean formwork and ready to pour
checkpoint-status |  |  | checkpoint | Structural Eng inspection report received and close-out
checkpoint-status |  |  | checkpoint | Council inspection report received and close-out
checkpoint-status |  |  | checkpoint | Pour sequence mark-up
checkpoint-group |  |  | section | Access/safety/protection
checkpoint-status |  |  | checkpoint | Clear access for trucks/pump
checkpoint-status |  |  | checkpoint | Safe access to all areas of pour
checkpoint-status |  |  | checkpoint | Panel and steel protection
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | Confirm mix
checkpoint-status |  |  | checkpoint | Confirm concrete is being tested (slump and cylinders)
checkpoint-status |  |  | checkpoint | Weather recorded
checkpoint-status |  |  | checkpoint | Screed to falls in bathroom
checkpoint-group |  |  | section | Post Pour
checkpoint-status |  |  | checkpoint | Finish
checkpoint-status |  |  | checkpoint | Levels
checkpoint-status |  |  | checkpoint | Curing agent
checkpoint-status |  |  | checkpoint | Saw cuts within 24h of pour and slurry removed
checkpoint-status |  |  | checkpoint | Pour QA received
checklist-sectioned |  |  | checklist | Fitout - Carpentry Framing |  |  |  |  | Yes | Fitout - Carpentry Framing | e8ced4e5-c36a-43b0-9cc4-927b8c90733f
checkpoint-group |  |  | section | Mezzanine
checkpoint-status |  |  | checkpoint | Framing complete as per Arch details
checkpoint-status |  |  | checkpoint | DPM between timber and beam
checkpoint-status |  |  | checkpoint | Balustrade 150x150mm 19mm packer.
checkpoint-status |  |  | checkpoint | Framing/beam packing continuous to receive the Balustrade posts
checkpoint-status |  |  | checkpoint | Stair measure complete
checkpoint-status |  |  | checkpoint | Stairs received on site and installed
checkpoint-status |  |  | checkpoint | 70mm min width of stringer against precast
checkpoint-status |  |  | checkpoint | Inside stringer notching clear
checkpoint-status |  |  | checkpoint | Base of stair detail correct
checkpoint-status |  |  | checkpoint | Battens to receive Fireline installed correctly
checkpoint-status |  |  | checkpoint | All nails flush within framing to receive GIB
checkpoint-status |  |  | checkpoint | Fireline installed as per Spec
checkpoint-status |  |  | checkpoint | AC inspection No.1 Post line Fireline
checkpoint-group |  |  | section | Bathroom
checkpoint-status |  |  | checkpoint | DPC between timber and concrete
checkpoint-status |  |  | checkpoint | Framing as per Arch drawings
checkpoint-status |  |  | checkpoint | Fixings to concrete panel and slab correct
checkpoint-status |  |  | checkpoint | Door opening Correct
checkpoint-status |  |  | checkpoint | Service nogs / stud exclusion zones
checkpoint-status |  |  | checkpoint | Set out confirmed by EXP and accepted by ZYJ
checkpoint-status |  |  | checkpoint | All nails flush within framing
checkpoint-status |  |  | checkpoint | AC inspection No.1 Pre-line inspection
checkpoint-status |  |  | checkpoint | GIB install to walls
checkpoint-status |  |  | checkpoint | Ceiling Grid installed – services accounted.
checkpoint-status |  |  | checkpoint | Services installed – TRF, AM, TC
checkpoint-status |  |  | checkpoint | Ceiling GIB installed
checkpoint-status |  |  | checkpoint | AC inspection No.2 Post line
checklist-sectioned |  |  | checklist | Footings |  |  |  |  | Yes | QA - Footings Checklist | ea26c85e-080a-4f7c-a162-ea32d6cc37dc
checkpoint-group |  |  | section | Pre-start
checkpoint-status |  |  | checkpoint | QA for sub-grade and relevant services received
boolean | de78e993-f115-4c39-b510-f89d2481a6c8 |  | tickbox | Site concrete allowed for in cut
checkpoint-status |  |  | checkpoint | GL and datum provided
checkpoint-status |  |  | checkpoint | Clear work area
checkpoint-status |  |  | checkpoint | Geotechnical Eng inspection report received and closed-out
checkpoint-group |  |  | section | Pre-Pour
checkpoint-status |  |  | checkpoint | Service trade sign off/QA
checkpoint-status |  |  | checkpoint | Waterproof sign off/QA
checkpoint-status |  |  | checkpoint | Formwork signoff/QA
checkpoint-status |  |  | checkpoint | Check levels
checkpoint-status |  |  | checkpoint | Check foundation width for propping
checkpoint-status |  |  | checkpoint | Sump position check and block-off foundation if clash
checkpoint-status |  |  | checkpoint | Reo sign off/QA
checkpoint-status |  |  | checkpoint | GN inspection
boolean | cd7866fe-0b96-4141-be80-6968f9d662ca |  | tickbox | Details checked
boolean | b88df18d-5e7a-4f82-9cc4-a5bb84fbc013 |  | tickbox | Starters, scabbling, cover checked
boolean | 3378105b-1ca7-4407-9c0b-cd274393cad6 |  | tickbox | Clean formwork and ready to pour
checkpoint-status |  |  | checkpoint | Structural Eng inspection report received and close-out
checkpoint-status |  |  | checkpoint | Council inspection report received and close-out
checkpoint-group |  |  | section | Access/Safety
checkpoint-status |  |  | checkpoint | Clear access for trucks/pump
checkpoint-status |  |  | checkpoint | Exposed reo capped
checkpoint-status |  |  | checkpoint | Safe access to all areas of pour
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | Confirm mix
checkpoint-status |  |  | checkpoint | Confirm concrete is being tested (slump and cylinders)
checkpoint-status |  |  | checkpoint | Weather recorded
checkpoint-group |  |  | section | Post Pour
checkpoint-status |  |  | checkpoint | Finish
checkpoint-status |  |  | checkpoint | Levels
checkpoint-status |  |  | checkpoint | Starters
checkpoint-status |  |  | checkpoint | Pour QA received including dockets
checklist-sectioned |  |  | checklist | Consultant Inspection |  |  |  |  | Yes | Consultant Inspection | f4453121-a2db-4f7b-966a-44b91112b9b7
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Inspection completed, attached and any relevant observations closed out
text | 85d5c57f-5087-594a-9409-ad4a5f8cf854 |  | textbox | Date of inspection
text | d22c574d-b540-5c25-bcde-870e97bc0a2b |  | textbox | Type of inspection
text | 056b2541-4a8b-5b2c-9acb-bfec89374578 |  | textbox | Area of inspection
boolean | 540522ff-0a02-5422-9757-c4e19e4bf71c |  | tickbox | Inspection report attached
holdpoint |  |  | signoff | Sign off
checkpoint-status |  |  | checkpoint | All relevant observation closeout evidence attached here if applicable
text | 88bdd135-f1c4-58ad-8725-aad5bdc3811f |  | textbox | Corrective action required
checklist-sectioned |  |  | checklist | ITP Structure - shotcrete |  |  |  |  | Yes | ITP Structure - shotcrete | fe568e6f-031f-44b2-ad74-2beb40b09cfa
checkpoint-group |  |  | section | Pre-start
checkpoint-status |  |  | checkpoint | Review IFC dwgs
checkpoint-status |  |  | checkpoint | GL and datum provided
checkpoint-status |  |  | checkpoint | Clean work area
checkpoint-group |  |  | section | Pre-pour
checkpoint-status |  |  | checkpoint | Check surface preparations (adjacent wall protection)
checkpoint-status |  |  | checkpoint | Reo sign off/QA
checkpoint-status |  |  | checkpoint | GN inspection
boolean | a053b812-1f9a-5567-891f-0856b5eb84b9 |  | tickbox | i. Details checked
boolean | 0297003d-fcce-59ed-8be7-4876944fbc9c |  | tickbox | ii. Any CAN, Engr requirements
boolean | 5a82d12c-dcaf-5106-b87e-fda684f23168 |  | tickbox | iii. Scabbling, support bars, reinforcement quality
boolean | 3e5ecf69-6791-58ec-a4e5-9c43f2683c19 |  | tickbox | iv. Check reinforcements size, lapping, covers and starters
boolean | 5a0ee8e1-8fec-5550-8b20-0e61e012f745 |  | tickbox | v. confirm waterstop
checkpoint-status |  |  | checkpoint | Structural Eng inspection report received and close-out
checkpoint-status |  |  | checkpoint | Council inspection report received and close-out
checkpoint-group |  |  | section | Access/safety
checkpoint-status |  |  | checkpoint | Access for sprayer/pump
checkpoint-status |  |  | checkpoint | Safe access to all areas of spray
checkpoint-group |  |  | section | Spray
checkpoint-status |  |  | checkpoint | Confirm mix
checkpoint-status |  |  | checkpoint | Confirm concrete is being tested (slump and cylinders)
checkpoint-status |  |  | checkpoint | shotcrete placement timing (within 90 mins)
checkpoint-group |  |  | section | Post spray
checkpoint-status |  |  | checkpoint | Checks
boolean | e52b6789-823d-5af1-b530-ec7c2ebf4452 |  | tickbox | i. Finish
boolean | dba42595-6eef-5ed9-bfc5-9adb4a7da99c |  | tickbox | ii. Levels
checkpoint-status |  |  | checkpoint | Pour QA received including concrete dockets