## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Incident Reports |  |  |  |  | Yes | Incident Reports | 0606e89c-f856-4c16-af66-6d6090875466
checkpoint-group |  |  | section | Details of accident/incident
checkpoint-status |  |  | checkpoint | Please attach any relevant photos & documents
text | 3d842218-184d-508d-ba74-fcd27bbc95ee |  | textbox | Date of incident
text | 1d43f17a-cc63-5c8c-8202-54535de16955 |  | textbox | Time of incident:
text | ec8b877d-3086-565b-addf-00098a5262bd |  | textbox | Time of report:
checkpoint-status |  |  | checkpoint | Nature of incident
boolean | ffcc64b2-1396-545d-a3cf-9b6c8f24d772 |  | tickbox | injury (attach completed WHSE Form 01 Injury report)
boolean | f3783988-5ba3-5864-bb6f-3a9b48488954 |  | tickbox | environmental (pollution)
boolean | ecec5d4a-76e2-5eee-86ea-1d31364ad1ed |  | tickbox | damage to property/assets/services
boolean | df2dc992-3f6e-5eda-91b6-c178842f2e36 |  | tickbox | incident
checkpoint-group |  |  | section | Names of person(s) involved
checkpoint-status |  |  | checkpoint | Please attach any relevant photos & documents
text | 290379eb-52a2-5552-b78d-f757166861e2 |  | textbox | Name
text | 66c5b580-7f53-5a78-8cdc-50de3f3d3db8 |  | textbox | Phone Number
label | 2888649b-af0b-5531-acb0-7b6f4062672e |  | note | (home, mobile & work)
text | c3102656-8950-573c-8ade-481eb526d8b1 |  | textbox | Address
text | 2659392c-4e38-5475-81f9-5baea1e3a394 |  | textbox | D.O.B
text | d69ee093-b5e1-5028-9847-000aff8691ba |  | textbox | Email
text | a9fdca2d-bd82-5d9d-aa1a-42d128c039b5 |  | textbox | Activity in which the person(s) was engaged at the time:
text | fb41d4d6-8559-579e-aae9-0a8a90f1ff04 |  | textbox | Exact site location where injury/incident occurred:
text | f3c4345e-acf7-513f-9725-0fa046d8c7d9 |  | textbox | Type of injury/pollution/damage/ incident:
text | a6b88299-222c-551d-bbb1-12aede5a600e |  | textbox | Describe the accident/incident in detail:
checkpoint-group |  |  | section | Witness to incident (each witness may need to provide an account of what happened
checkpoint-status |  |  | checkpoint | Please attach any relevant photos & documents
text | c93aedc4-011e-5a7c-9543-c571eaabe8d0 |  | textbox | Witness Name
text | 60244696-804c-56a7-a557-c5053fb7d912 |  | textbox | Witness Contact
text | 288bc978-4bf2-5d17-b981-f69e62635c8c |  | textbox | Witness Name
text | 48e7fb5b-3785-5c8f-85cf-d5aacee2dd91 |  | textbox | Witness Contact
checkpoint-group |  |  | section | Are there any notable/significant factors relevant to the accident/incident?
checkpoint-status |  |  | checkpoint | Please attach any relevant photos & documents
text | 90f6237c-8dd1-5c2b-ab8d-b495c427a0bb |  | textbox | Details
checkpoint-group |  |  | section | Arrangements made to store any equipment that believed to have contributed to injury/incident?
checkpoint-status |  |  | checkpoint | Please attach any relevant photos & documents
text | 5e8f330f-be78-585a-87a2-4c4ce547db62 |  | textbox | Details
checkpoint-group |  |  | section | Did any third parties (subcontractors, visitors, etc.,) contribute to the incident? If so, how?
checkpoint-status |  |  | checkpoint | Please attach any relevant photos & documents
text | 4fe201a6-b77b-5a3d-bb0c-f2c111bafa90 |  | textbox | Details
checkpoint-group |  |  | section | Immediate corrective actions taken? (e.g., works ceased, area made safe, barriers erected, etc.,)
checkpoint-status |  |  | checkpoint | Please attach any relevant photos & documents
text | dda1ac0b-4a31-5051-9e0f-4d4f19025c48 |  | textbox | Details
checkpoint-group |  |  | section | Future actions taken (e.g., engineering solutions, training, toolbox talk, etc.,)
checkpoint-status |  |  | checkpoint | Please attach any relevant photos & documents
text | 9fdba0fc-211e-519b-919e-fb5295e33564 |  | textbox | Details
checkpoint-group |  |  | section | Review & Sign off
checkpoint-status |  |  | checkpoint | Have all actions been completed and reviewed as effective?
checkpoint-status |  |  | checkpoint | Have all documents relating to the incident, including corrective action evidence been completed
holdpoint |  |  | signoff | Signed Off
checklist-flat |  |  | checklist | Fire Extinguishers/Blankets |  |  |  |  | Yes | Fire Extinguishers/Blankets | 1bb90598-a438-496e-b9e6-a263dc69d304
checkpoint-status |  |  | checkpoint | Install Extinguishers
checkpoint-status |  |  | checkpoint | Install appropiate signage
checkpoint-status |  |  | checkpoint | Install Fire Blankets
checkpoint-status |  |  | checkpoint | Fire Hose Reel signs
checklist-flat |  |  | checklist | Sprinkler Fit Off Checklist |  |  |  |  | Yes | Sprinkler Fit Off Checklist | 1e0f18d3-0783-46bb-b86f-004e41e0e6d3
checkpoint-status |  |  | checkpoint | Fit Off: Check all sprinklers have been fit off
checkpoint-status |  |  | checkpoint | Check sprinkler heights pre paint
checkpoint-status |  |  | checkpoint | Fit off Escutcheon plates
checkpoint-status |  |  | checkpoint | Air Test: Pressurized air test for a period of 30 mins (if applicable)
text | 84f4fb22-8552-5052-8313-7c39c13df6d5 |  | textbox | Start time:
text | f04ae3a8-b492-5403-b2c2-7294801f2008 |  | textbox | Completion time:
checkpoint-status |  |  | checkpoint | Water Test: Pressure test to 1600Kpa for duration of 2 hours
text | 9564164c-a162-5677-863f-6dbeb85bc04b |  | textbox | Start time:
text | 5bba66df-b590-56cf-bb27-e881b5cc3eec |  | textbox | Completion time:
checkpoint-status |  |  | checkpoint | PFP Foreman signature
checklist-flat |  |  | checklist | Commissioning |  |  |  |  | Yes | Commissioning | 2df32243-02a8-4b18-bb5c-724aa17ee04c
checkpoint-status |  |  | checkpoint | SCV-Locks/chain/labels/pipework stickers/sprinkler spares & spanner/block plans
checkpoint-status |  |  | checkpoint | Booster Cupboard-Signage/Locks/chain/labels/plan sleeve+block plans label/block plans
checkpoint-status |  |  | checkpoint | Hydrant Mains/Isolation Valves-Locks/chain/labels/pipework stickers
checkpoint-status |  |  | checkpoint | Water Meter Assembly-Locks/chain/labels
checkpoint-status |  |  | checkpoint | Check sluice valves & water meter valves are open
checkpoint-status |  |  | checkpoint | Fire Pump/Tank-Fuel full, Exhaust piped, Mains power, Drains/Relief Valve piped, Water Supply on, Locks/chain/labels/pipework stickers
checkpoint-status |  |  | checkpoint | Adjust Bermads & float Valves to fire tanks
checkpoint-status |  |  | checkpoint | Pump Room-Block Plans
checkpoint-status |  |  | checkpoint | FIP-Block plans/test all alarm devices
checkpoint-status |  |  | checkpoint | Test all Valves & Flow switches to ensure correct operation
checkpoint-status |  |  | checkpoint | Set Pressure switches to Jacking pump & alarm line
checkpoint-status |  |  | checkpoint | Block plans/Tactical Fire plans/FRV way finding plan
checkpoint-status |  |  | checkpoint | FRV Shortfall drawings & FRV stat signage ie: x2 30m hose
checkpoint-status |  |  | checkpoint | Individual Floor Block plans (If applicable)
checklist-flat |  |  | checklist | Fire Penetrations Checklist |  |  |  |  | Yes | Fire Penetrations Checklist | 363c0d9e-cadb-475c-a520-107c5d4f42cd
checkpoint-status |  |  | checkpoint | Fire Penetration labelled & caulked in accordance with AS 4072.1 Drawing Reference No.
checklist-sectioned |  |  | checklist | Variations |  |  |  |  | Yes | Variations | 36c9625f-ec13-47a5-b338-b86018f11ea0
checkpoint-group |  |  | section | Payer Details
checkpoint-status |  |  | checkpoint | Payer Details entered below
text | eab047e9-f63d-5add-97ec-9dadc0edd07c |  | textbox | Contact
text | 5005b495-7445-5d3d-94de-14f6e337dc22 |  | textbox | Company
text | 0e56e228-b99d-51dc-848d-05bc9cf248fc |  | textbox | Contact No.
checkpoint-group |  |  | section | Variation Details
checkpoint-status |  |  | checkpoint | Variation Details Entered
text | 607cd55b-0587-5d86-8f3b-df7cab34481a |  | textbox | Description of work
text | 27e04e0b-48f9-50b9-aaf1-ad23eb9f4400 |  | textbox | Reason for variation (unless stated in instruction)
text | ca8ff66e-f7d2-5f80-84a8-d682109fb9c4 |  | textbox | Area/Location
text | 254dde7b-6cb1-56d3-bb76-58a77a6624c1 |  | textbox | As directed and requested by
text | d3a8711d-454e-5061-88ac-2ac6b12ae763 |  | textbox | Date
text | 62857e94-44bf-53af-8896-bc533e306b9b |  | textbox | Normal Hours
text | 701bdf83-91c5-5eb0-a282-ac62cb3a78f9 |  | textbox | Overtime Hours
text | 7c6e915e-a1b8-5ade-b360-7ff506118128 |  | textbox | Material used to complete task
checkpoint-status |  |  | checkpoint | Variation Completed
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Variation signed
label | a8ff315b-1d5d-5d17-b48d-5402393ac36c |  | note | I hereby authorise you to carry out the extra work detailed above and I agree that the same shall be paid as an addition to your original contract order
holdpoint |  |  | signoff | Builder / Client signature
checklist-sectioned |  |  | checklist | Toolbox Meeting Checklist |  |  |  |  | Yes | Toolbox Meeting Checklist | 4c485904-7d63-4469-94dd-64acaca104cd
checkpoint-group |  |  | section | Attendance
checkpoint-status |  |  | checkpoint | Attendance - list of attendees added below
checkpoint-group |  |  | section | Minutes
checkpoint-status |  |  | checkpoint | Actions from last meeting
checkpoint-status |  |  | checkpoint | Safety: (including hazards / near misses / controls / site specific)
checkpoint-status |  |  | checkpoint | Plant, tools & Equipment all in good working order?
checkpoint-status |  |  | checkpoint | PPE-ensure everyone has PPE
checkpoint-status |  |  | checkpoint | Housekeeping to be maintained
checkpoint-status |  |  | checkpoint | Ensure Electrical equipment test and tagged
checkpoint-group |  |  | section | New Business / Other
checkpoint-status |  |  | checkpoint | Any new business / other comments added below
checkpoint-group |  |  | section | Meeting Closure
checkpoint-status |  |  | checkpoint | Meeting Closed
text | a415b8ee-e716-5683-90bd-3214f9148904 |  | textbox | Meeting Closed time
text | d90b1408-c93d-5607-8712-33cf7e8a1423 |  | textbox | Minutes taken by (Name)
checkpoint-status |  |  | checkpoint | Employee sign off
checklist-flat |  |  | checklist | Fire Booster Cupboard Checklist |  |  |  |  | Yes | Fire Booster Cupboard Checklist | 4cf8387b-a5c6-4cab-9b09-1d8108d928b4
checkpoint-status |  |  | checkpoint | Install Suction/ Millcocks & Hydrant, Sprinkler Boosters
checklist-flat |  |  | checklist | Sprinkler Control Valves Checklist |  |  |  |  | Yes | Sprinkler Control Valves Checklist | 64683fd7-4313-40ff-956e-251abe5ba846
checkpoint-status |  |  | checkpoint | Install Sprinkler Control Valves/ Jacking Pump
checkpoint-status |  |  | checkpoint | Test full operation of Control Valves
checkpoint-status |  |  | checkpoint | Install Sprinkler Spares box, spare sprinklers & spanner
checkpoint-status |  |  | checkpoint | Set Jacking Pump pressure switch min 150 kPa above towns main/manifold pressure
checkpoint-status |  |  | checkpoint | Install Gong/Electric Bell & test operation
checkpoint-status |  |  | checkpoint | Check for adequate drainage and test
checklist-flat |  |  | checklist | Project Drawings |  |  |  |  | Yes | Project Drawings | 70e3bf18-b38c-48e4-b9b8-a0333631aafd
checkpoint-status |  |  | checkpoint | Upload project drawings
checklist-flat |  |  | checklist | Hydrant/Sprinkler Mains/Risers/Hose Reel Checklist |  |  |  |  | Yes | Hydrant/Sprinkler Mains/Risers/Hose Reel Checklist | 77f73d3c-7978-4144-bb09-725be43d4ef5
checkpoint-status |  |  | checkpoint | Rough In: All Mains & isolation valves installed
checkpoint-status |  |  | checkpoint | Install Hydrant/ Sprinkler/Test Drain Risers & Mill Cocks
checkpoint-status |  |  | checkpoint | Sprinkler Floor Control Valves installed and secured
checkpoint-status |  |  | checkpoint | Fit Off: Check all millcock clearances/angles/Mill cocks in closed position & Install 2400kPa pressure gauge to top of risers
checkpoint-status |  |  | checkpoint | Install Fire Hose Reels & pipework
checkpoint-status |  |  | checkpoint | Air Test: Pressurized air test for a period of 30 mins (if applicable)
text | 90a050b4-c3e7-5eb8-a108-4fc689d8d8e2 |  | textbox | Start time:
text | 47f96094-f824-5aca-ad32-c7a32af5c4da |  | textbox | Completion time:
checkpoint-status |  |  | checkpoint | Water Test: Pressure test to 1700Kpa for duration of 2 hours
text | 7c8d4160-2af8-5667-a513-e65e4728c337 |  | textbox | Start time:
text | 8ee8df67-8cf8-5a63-9896-c16bc798d0bd |  | textbox | Completion time:
checkpoint-status |  |  | checkpoint | FHR: All FHR been bled from excess air & proof of water
checkpoint-status |  |  | checkpoint | PFP Foreman signature
checklist-flat |  |  | checklist | Site Diary Checklist |  |  |  |  | Yes | Site Diary Checklist | 85f80362-2fd5-4d2d-8c96-d346c30a51d2
checkpoint-status |  |  | checkpoint | Comment/notes
checklist-flat |  |  | checklist | Fire Pumps/Tanks Checklist |  |  |  |  | Yes | Fire Pumps/Tanks Checklist | 878798f0-ec18-41a7-9fc8-5ec1edd67455
checkpoint-status |  |  | checkpoint | Install Plinth & secure
checkpoint-status |  |  | checkpoint | Install Pumps & secure to plinths
checkpoint-status |  |  | checkpoint | Install all pipework/isolation valves to pumps
checkpoint-status |  |  | checkpoint | Install Annubar/coolant drains
checkpoint-status |  |  | checkpoint | Install Pump Exhaust to designated point
checkpoint-status |  |  | checkpoint | Water Test all Pipework to pumps
checkpoint-status |  |  | checkpoint | Install all Pipework and Valves to Fire Tank
checkpoint-status |  |  | checkpoint | Water test all pipework to and from Water Tank
checklist-flat |  |  | checklist | Sprinkler Rough In Checklist |  |  |  |  | Yes | Sprinkler Rough In Checklist | 8ea7c330-f092-47a7-ab50-4e469c403727
checkpoint-status |  |  | checkpoint | Rough In: All Mains, range pipes, clips installed & secured
checkpoint-status |  |  | checkpoint | Concealed Space Sprinklers & Flexible droppers Installed
checkpoint-status |  |  | checkpoint | Arm pieces / Under Duct pipework installed and secured
checkpoint-status |  |  | checkpoint | Balcony Sprinklers installed
checkpoint-status |  |  | checkpoint | Car Park Sprinklers Installed
checkpoint-status |  |  | checkpoint | Car Stackers pipework installed & secured (if applicable)
checkpoint-status |  |  | checkpoint | Install Remote Test drain pipework
checkpoint-status |  |  | checkpoint | Air Test: Pressurized air test for a period of 30 mins (if applicable)
text | 8d6a18a9-346c-5ef3-8004-e9221b93e7c5 |  | textbox | Start time:
text | 13822ffc-58f9-50b2-936c-cf863fe0051f |  | textbox | Completion time:
checkpoint-status |  |  | checkpoint | Water Test: Pressure test to 1600Kpa for duration of 2 hours
text | b383d6c7-7ee0-5a34-9866-9117d90fa1f9 |  | textbox | Start time:
text | 7c67ab08-d90c-526a-b015-431d59e18c52 |  | textbox | Completion time:
checkpoint-status |  |  | checkpoint | PFP Foreman signature
checklist-flat |  |  | checklist | Undocumented Variations |  |  |  |  | Yes | Undocumented Variations | b4665017-8507-4b8f-a1bf-6e2df1df2f38
checkpoint-status |  |  | checkpoint | Attach relevant details