## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | 02.01 - Traffic Management | itp
section | Details
checkpoint | The Contractor's Nominated Traffic Officer submitted to the Administrator and meets the requirements as specified
label | Acceptance Criteria and Frequency (Project Specific) - Accreditation Supplied to Administrator
label | Check Item - Check Item
label | Reference - MRTS02 Cl. 5.2
checkpoint | No traffic rearrangements shall be carried out until after the Administrator has advised the Contractor that the submitted, and amended as directed, TMP is approved and suitable for use.
label | Acceptance Criteria and Frequency (Project Specific) - Approval via Contract Notice - Per NTO
label | Check Item - Hold Point 1
label | Reference - MRTS02 Cl. 5.3
holdpoint | Hold Point
checkpoint | All traffic control devices inspected and records kept in accordance with the specification
label | Acceptance Criteria and Frequency (Project Specific) - Site Records - Daily
label | Check Item - Check Item
label | Reference - MRTS02 Cl. 5.6.4
checkpoint | In the event of a traffic crash/incident within the site, the Contractor shall record the date and take time and date stamped photographs of the signs/devices in the vicinity of the crash.
label | Acceptance Criteria and Frequency (Project Specific) - Incident Report - Per incident
label | Check Item - Check Item
label | Reference - MRTS02 Cl. 5.6.5
checkpoint | All TGS's prepared by a suitably qualified person and submitted to the Administrator for review and shall be accompanied with a specific risk assessment, as required. Innovations, alternatives and departures from standards shall be certified by a RPEQ.
label | Acceptance Criteria and Frequency (Project Specific) - TMD sign off of TGS and, RPEQ Risk Assessment as required
label | Check Item - Hold Point 2
label | Reference - MRTS02 Cl. 6.2
holdpoint | Hold Point
checkpoint | The Traffic Management Inspection report to the Contractor for action, together with documentation of any actions taken in regard to findings.
label | Acceptance Criteria and Frequency (Project Specific) - Submission of report to Administrator - Per inspection
label | Check Item - Milestone
label | Reference - MRTS02 Cl. 7.5
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 03.09 - Removal of Existing Drainage Structures and Concrete Slabs | itp
section | Details
checkpoint | Culverts and culvert end structures shall be removed or demolished where specified in the drawings.
label | Acceptance Criteria and Frequency (Project Specific) - Culvert Removal - Per Culvert
label | Check Item - Check Item
label | Reference - MRTS03 Cl 9.2
checkpoint | If existing culvert components are to be removed and re-used, they shall be removed and stacked in a manner which avoids damaging the components.
label | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
label | Check Item - Check Item
label | Reference - MRTS03 Cl 9.2
checkpoint | Removed components which are not to be salvaged, nor reused, shall be removed from the Site and disposed.
label | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
label | Check Item - Check Item
label | Reference - MRTS03 Cl 9.2
checkpoint | Excavations carried out and the void left by the removed culvert or end structure shall be backfilled to reinstate the area to a safe and free draining state.
label | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
label | Check Item - Check Item
label | Reference - MRTS03 Cl 9.2
checkpoint | Existing kerbs, channels, kerbs and channels, kerb crossings and concrete slabs shall be removed or demolished where specified in the drawings.
label | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Kerb
label | Check Item - Check Item
label | Reference - MRTS03 Cl 9.4
checkpoint | Any Kerb and Channel or concrete slab to be removed is saw cut at removal extents or removed to existing joint (or removed in its entirety) where specified in the drawings and no damage shall occur to adjacent work
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl. 9.4
checkpoint | Kerb excavations shall be backfilled to flush with the surrounding area.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl. 9.4
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 03.10 - Supply and Installation of Precast Concrete Culverts | itp
section | Details
checkpoint | Maximum Lot Size - 1 Culvert
label | Acceptance Criteria and Frequency (Project Specific) - Lot size </= 1 Culvert - Per lot
label | Check Item - Check Item
label | Reference - MRTS04 Table A.2
checkpoint | Concrete Pipe culvert components comply with MRTS25/26, FRCP with Slotted Drain Insert Complies with MRTS26
label | Acceptance Criteria and Frequency (Project Specific) - Manufacture and Test Certificates
label | Check Item - Check Item
label | Reference - MRTS03 Cl10.2
checkpoint | All pipes of diameter 800 mm or less shall have spigot and socket joints with rubber sealing rings. Joints for other sizes shall be as specified on the drawings.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl10.2
checkpoint | Component size, wall thickness and class is as specified in the drawings
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl10.2
checkpoint | Bandage Covers are a Proprietary Product, either: Synthetic or Rubber Band, samples inspected by administrator
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 1
label | Reference - MRTS03 Cl11.2
holdpoint | Hold Point
checkpoint | Culvert Construction Procedures to be accepted prior to commencement of Installation
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS03 Cl11.3.1
holdpoint | Hold Point
checkpoint | Load testing of non standard pipes ordered for specific projects shall be a witness point
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Witness Point
label | Reference - Annexure MRTS26.1 Cl 2
section | Excavation
checkpoint | Excavations shall be carried out in accordance with Clause 13 of MRTS04 General Earth works
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl.11.3.1
checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially unsuitable Material is encountered on site the contactor shall, before proceding with removal, shall notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl. 9.3 and CL.11.3
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 4
label | Reference - MRTS04 Cl. 9.4
holdpoint | Hold Point
checkpoint | Bottom of excavation compaction tested. 0 - 150mm below foundation -RDD Q140A
label | Acceptance Criteria and Frequency (Project Specific) - Cl 15, Table 15.3(b), CV 95% minimum (1 tests / 50m2 - min 2 / lot)
label | Check Item - Test results
label | Reference - MRTS04 Table A.2
section | Culvert Installation
checkpoint | Components are assembled as per manufaturers specifications, and if possible, contruction commenced at outlet
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl11.3.3, Cl11.3.4
checkpoint | Pipes shall be placed with their external grooved ends or spigot ends facing the culvert outlet
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl11.3.5
checkpoint | The pipes shall be laid with the lifting hole or "TOP" marking uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl11.3.5
checkpoint | Placed with external groove or spigot end facing outlet with minimum of 50mm bedding material
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl11.3.5
checkpoint | The horizontal alignment of culverts shall not vary from the location specified in the Drawings by more than ± 100 mm
label | Acceptance Criteria and Frequency (Project Specific) - ± 100mm (All points shown on drawings - min 1 per 20m or 2 points)
label | Check Item - Survey Results
label | Reference - MRTS03 Cl.8.2
checkpoint | The invert heights of culverts shall not vary from those specified by more than ± 10 mm and nowhere shall the grades of culverts depart from those specified by more than 1%
label | Acceptance Criteria and Frequency (Project Specific) - ± 10mm, ± 1% grade (All points shown on drawings - min 1 per 20m or 2 points)
label | Check Item - Survey Results
label | Reference - MRTS03 Cl.8.3
section | FRCP with Slotted Drain Installation
checkpoint | Fibre-reinforced concrete pipes shall be designed for installation in accordance with AS/NZS 3725. Construction load cases shall be considered in accordance with Clause 5.5.1. Designs already completed to AS 5100.2 shall be deemed to comply with these requirements.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS26.1 Cl 2, MRTS26 5.5
checkpoint | FRCP: The maximum angle of deflection of joints for pipes is two degrees
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS26.1 Cl 2, MRTS26 11
checkpoint | For the specified pipe class and size, the contractor shall progressively backfill the pipe using the fill depth and construction equipment permissible in Table B1 of AS/NZS 3725.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS26.1 Cl 2, MRTS26 11
section | Backfill
checkpoint | Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met and notice of such works provided to the Administrator
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 4
label | Reference - MRTS03 11.3.10
holdpoint | Hold Point
checkpoint | Backfill material shall not be placed until culverts, structures, pipes, conduits, pits, etc have been completed and inspected, and any specified curing periods have elapsed.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 14
label | Reference - MRTS04 Cl.19.3.3
holdpoint | Hold Point
checkpoint | Overlay material within 300 mm of the structure, culvert, pipe, etc shall be general back fill Class A1, A2 or B material conforming to MRTS04 Cl.19.2.2 excep 100% material shall pass 25.0mm test sieve.
label | Acceptance Criteria and Frequency (Project Specific) - Class A1:
label | ○ Class A2:
label | ○ Class B:
label | ○ Except: 100% passing 25mm
label | Check Item - Witness Point
label | Reference - MRTS04 19.3.1, 19.2.2 Table 14.2.2
checkpoint | Compaction - Q142A, Q141B
label | Acceptance Criteria and Frequency (Project Specific) - Top 300mm below Subgrade Level ≥97%
label | ○ Greater than 300mm below Subgrade Level ≥95% (1 test / 50m3, min 1 per lot)
label | Check Item - Test results
label | Reference - MRTS04 Table 15.3(b)
checkpoint | Moisture content within ranges specified Rainfall Zone: HIGH
label | Acceptance Criteria and Frequency (Project Specific) - Class A1/A2: 70-100%
label | ○ Class B: 80-110%
label | Check Item - Test results
label | Reference - MRTS04 Table 15.3(c)
section | Completion
checkpoint | CCTV inspection undertaken, report submitted and accepted by administrator. Visual inspection may be approved by the Administrator in lieu of CCTV inspection.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 3
label | Reference - MRTS03 Cl11.3.5
holdpoint | Hold Point
checkpoint | Final Verification
label | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 03.11 - Installation of Culvert Components and Structures - Precast or In-Situ | itp
section | Details
checkpoint | Maximum Lot Size - 1 Culvert
label | Acceptance Criteria and Frequency (Project Specific) - Lot size </= 1 Culvert - Per lot
label | Check Item - Check Item
label | Reference - MRTS04 Table A.2
checkpoint | Culvert Construction Procedures accept prior to commencement of Installation
label | Acceptance Criteria and Frequency (Project Specific) - Administrator Approval - Per Project
label | Check Item - Hold Point 2
label | Reference - MRTS03 Cl 11.3.1
holdpoint | Hold Point
section | Excavation
checkpoint | Excavations shall be carried out in accordance with Clause 13 of MRTS04 General Earthworks.
label | Acceptance Criteria and Frequency (Project Specific) - Visual - Per lot
label | Check Item - Check Item
label | Reference - MRTS03 Cl 12.3.1
checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially unsuitable Material is encountered on site the contactor shall, before proceding with removal, shall notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl. 9.2 and CL.11
textbox | Reference Unsuitable Lot No. :
label | Acceptance Criteria and Frequency (Project Specific) - Visual - Per lot
label | Check Item - Hold Point 4
label | Reference - MRTS04 Cl 9.4
holdpoint | Hold Point
checkpoint | Bottom of excavation compaction tested. 0 - 150mm below foundation - AS 1289.5.4.1 or AS1289.5.7.1
label | Acceptance Criteria and Frequency (Project Specific) - Cl 15, Table 15.3(b)
label | ○ CV 95% minimum (1 tests / 50m2 - min 2 / lot)
label | Check Item - Test results
label | Reference - MRTS04 Table A.2
section | Installation
checkpoint | Cast In Situ material: In accordance with MRTS03 Cl.6.1, MRTS 70 & MRTS71
label | Acceptance Criteria and Frequency (Project Specific) - MRTS03
label | ○ Cl.15: End Structures
label | ○ Cl.21: Gullies
label | ○ Cl.21: Access Chambers
label | Check Item - Check Item
label | Reference - MRTS03 Cl.6.1
checkpoint | Precast: Installed in accordance with MRTS03 - Components shall be laid on a foundation bedding which provides continuous even support to the structures.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | ○ Cl.19: Precast End Structures
label | ○ Cl.21: Precast Gullies
label | ○ Cl.21.5.1 Precast Access Chamber
label | Check Item - Check Item
label | Reference - MRTS03
label | ○ Cl. 16
label | ○ Cl. 21
label | ○ Cl. 21.5.1
checkpoint | Precast: Culverts shall be joined to shafts/pits to form watertight joints using cement mortar. Cement mortar shall be used within one hour of mixing and shall not be re-tempered. The joints shall be finished to given smooth surfaces which are uniform with the surfaces of the shafts.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl. 21.3
section | Tolerances
checkpoint | Gullies/Chambers: Vertical Tolerances: Invert heights shall not vary from those specified by the Drawings by more than ± 50 mm
label | Acceptance Criteria and Frequency (Project Specific) - ±50mm (All points specified on drawings)
label | Check Item - Survey Results
label | Reference - MRTS03 Cl.21.4.2
checkpoint | Gullies/Chambers: Vertical Tolerances: The heights of the tops of back-units, grates and frames shall not vary from those described in the Drawings by more than ± 10 mm
label | Acceptance Criteria and Frequency (Project Specific) - ±10mm (All points specified on drawings)
label | Check Item - Survey Results
label | Reference - MRTS03 Cl.21.4.2
checkpoint | Horizontal tolerances: Gullies: shall not vary from those specified in the Drawings by more than ± 100 mm in the direction of the construction centre line and ± 50 mm in the direction at right angles to the construction centre line. Access Chambers: shall not vary from those specified in the Drawings by more than ±100mm
label | Acceptance Criteria and Frequency (Project Specific) - Gullies:
label | ○ ±100mm in road direction
label | ○ ±50mm perpendicular to road
label | Access Chambers:
label | ○ ±100mm (All points specified on drawings)
label | Check Item - Survey Results
label | Reference - MRTS03 Cl.21.4.1
checkpoint | Gullies/Chambers: join neatly to existing drainage structures, do not pond water unnecessarily and are at heights compatible with other adjacent structures.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl.21.4.2
checkpoint | Gullies/Chambers: Grates on gullies or Concrete top slabs on precast concrete access chambers shall not be installed until all the surveying requirements have been met and notice of such works provided to the Administrator
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 5, Hold Point 6
label | Reference - MRTS03 Cl.21.3
holdpoint | Hold Point
section | Backfill
checkpoint | Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met and notice of such works provided to the Administrator
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 4
label | Reference - MRTS03 11.3.10
holdpoint | Hold Point
checkpoint | Prior to incorporating any Backfill material into the Works, the Contractor shall submit stockpile or source tests results as specified in Appendix A which demonstrate the source meets the specified material requirements
label | Acceptance Criteria and Frequency (Project Specific) - Quarry Material Test Results
label | Check Item - Hold Point 8
label | Reference - MRTS04 Cl. 14.2.1
holdpoint | Hold Point
checkpoint | Material for backfill shall be as shown on the drawings or as specified elsewhere in the ContractEarth Backfill Material shall comply with the requirements of Earth Fill Material Class A1, Class A2 or Class B specified in Clause 14.2.2 except that 100% of the material shall pass 25.0 mm test sieve.
label | Acceptance Criteria and Frequency (Project Specific) - Test Results
label | Check Item - Witness Point 5
label | Reference - MRTS04 Cl. 19.3.1
checkpoint | Hold Point 12
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 12
label | Reference - MRTS04 Cl.19.3.3
holdpoint | Hold Point
checkpoint | Overlay material within 300 mm of the structure, culvert, pipe, etc shall be general back fill Class A1, A2 or B material conforming to MRTS04 Cl.19.2.2 except 100% material shall pass 25.0mm test sieve. Else where material may contain stone sized up to 150mm maximum dimension
label | Acceptance Criteria and Frequency (Project Specific) - Class A: WPI < 1200, PI > 7,
label | ○ % passing 0.075mm: 15 - 30
label | ○ Class B: 1200 < WPI < 2200
label | ○ Class A/B: 100% passing 25mm
label | Check Item - Witness Point
label | Reference - MRTS04 19.3.1, 19.2.2
checkpoint | Compaction - Q142A, Q141B
label | Acceptance Criteria and Frequency (Project Specific) - Top 300mm below Subgrade Level ≥97%
label | ○ Greater than 300mm below Subgrade Level ≥95% (1 test / 50m3, min 1 per lot)
label | Check Item - Test results
label | Reference - MRTS04 Table 15.3(b), MRTS03.1 Cl.1
checkpoint | Moisture content within ranges specified Rainfall Zone: HIGH
label | Acceptance Criteria and Frequency (Project Specific) - Class A: 70-100%
label | ○ Class B: 80-110%
label | Check Item - Test results
label | Reference - MRTS04 Table 15.3(c)
section | Completion
checkpoint | A water test on a side inlet gully shall be carried out where the longitudinal grade is less than 1%. Water shall be discharged into the side inlet gully to check uniformity of flow. After the flow has ceased, water shall not pond to a depth of more than 5 mm in any section of the channel.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Witness Point
label | Reference - MRTS03 Cl. 21.6.2
checkpoint | CCTV inspection undertaken, report submitted and accepted by administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 3
label | Reference - MRTS03 Cl11.3.5
holdpoint | Hold Point
checkpoint | Final Verification
label | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 03.22 - Subsoil Drainage | itp
section | Details
checkpoint | Subsoil Drains constructed to appropriate dimensions, inspect trench prior to backfill
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
checkpoint | Backfill materialshall be damp when placed in trench. Material shall be carefully placed in layers not exceeding 200mm loose thickness. Shall be compacted to achieve effective mechanical interlock between particles.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl 22.3
checkpoint | Subsoil Drains shall be constructed in the locations and in accordance to the drawings. Subsoil Drains shall be installed to the grades specified in the drawings. Where the grades are not specified, the bottom of trenches shall be trimmed to provide not less that 0.5% longitudinal fall towards outlets for pipe type drains and not less that 1% longitudinal fall towards outlets for strip filter type drains.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl 22.3
checkpoint | Cleanout and outlet pipes, Geotextiles, trench backfill, concrete for headwalls and surrounds, marker posts shall be as per specification
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl22.2
checkpoint | Clean-outs shall be located at the heads of all subsoil drains and at subsequent spacings not exceeding 60m for Type B subsoil drains and 50m for Type D subsoil drains. Cleanouts shall be constructed in accordance with the details shown on Standard Drawings 1116.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl22.3 TMR SD 1116
checkpoint | Marker posts installed where and when required as shown in the project drawings or standard drawings.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl22.2.7 TMR SD 1116
checkpoint | Where directed by Administrator, drains shall be flushed until outlet water is clean and flows consistently
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Witness Point
label | Reference - MRTS03 Cl22.3
checkpoint | As Constructed drawings prepared
label | Acceptance Criteria and Frequency (Project Specific) - As constructed drawings submitted to administrator
label | Check Item - Witness Point
checkpoint | All geometric tolerance requirements met
label | Acceptance Criteria and Frequency (Project Specific) - Survey
label | Check Item - Check Item
checkpoint | Final Verification
label | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 03.35 - Rock Protection | itp
section | Details
checkpoint | Rock employed as per drawings. If not specified, between 150 - 500mm, with at least 50% larger than twice the minimum size
label | Acceptance Criteria and Frequency (Project Specific) - Visual Inspection
label | Check Item - Check Item
label | Reference - MRTS03 Cl 35.2
checkpoint | Uniform appearance overall, and shall not have noticeable overall irregularities in horizontal and vertical alignments. The layers of placed rock shall be of even thickness and of even grading
label | Acceptance Criteria and Frequency (Project Specific) - Visual Inspection
label | Check Item - Check Item
label | Reference - MRTS03 Cl 35.3
checkpoint | Ordering Geotextile - Documentation which demonstrates that the design of the geotextile is in accordance with MRTS27 Cl. 6 submitted to the administrator and accepted prior to ordering.
label | Acceptance Criteria and Frequency (Project Specific) - Written Approval
label | Check Item - Hold Point 1
label | Reference - MRTS27 Cl 8.1
holdpoint | Hold Point
checkpoint | Geotextile - Inspection of product to be incorporated into works. Where Lot sites are greater than 5000m2, a representative sample covering approximately 15 m² of geotextile shall be cut from each sampled roll but not within two metres of the start or end of the roll. Where directed by the Administrator, samples shall also be cut and supplied to the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Visual Inspection
label | Check Item - Witness Point 1
label | Reference - MRTS27 Cl 10.2
checkpoint | Compliance of delivered Geotextile - Geotextile shall not be placed prior to acceptance of the test results by the Administrator
label | Acceptance Criteria and Frequency (Project Specific) - Visual Inspection
label | Check Item - Hold Point 2
label | Reference - MRTS27 Cl 10.4
holdpoint | Hold Point
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 04.07 - Clear and Grub | itp
section | Details
checkpoint | Any trees, shrubs and overhanging branches to be left undisturbed shall be clearly marked prior to clearing operations reaching the areas concerned.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS04 Cl. 7.2.2
holdpoint | Hold Point
checkpoint | Any trees required by the Administrator for use as marketable timber shall be as nominated in Clause 1.3 of Annexure MRTS04.1. Such trees shall be clearly marked by the Contractor prior to clearing operations reaching the areas concerned
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 3
label | Reference - MRTS04 Cl. 7.2.3
holdpoint | Hold Point
checkpoint | As soon as practicable and prior to initial earthworks operations (clearing and grubbing) for any stage or section of the Works, erosion and sediment controls associated with drainage paths flowing through the Works area shall be installed.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS52 Cl. 7.1
holdpoint | Hold Point
checkpoint | Hollow timber which is identified as being suitable for fauna habitat logs relocated to areas clear of construction activities
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 7.2.5
checkpoint | Surplus topsoil material and material considered not suitable for use as planting media in accordance with Cl. 8.3 shall be assessed for suitability for use as fill or deemed as unsuitable and disposed in accordance with Cl. 11
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 8.4.2
checkpoint | The scope of clearing and grubbing shall include the items as per Annexure MRTS04.1 Cl. 1.2 & Cl. 1.4
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 7.2.8, MRTS04.1 Cl 1.2, Cl 1.4
checkpoint | The additional width for clearing (no grubbing) is 3.0m as per Annexure MRTS04.1
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - Annexure MRTS04.1
checkpoint | Material not to be removed from within drip lines of existing plants to be retained except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retained are preserved where practical.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 8.4.3
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off