## SAC Rehab ITP
| Site Name | Ford Street | [6 empty] | Development Date:01/08/2024
| Carriageway width (m) | 8.1 |  |  | Target CBR value for subgrade | 3 |  |  | Role | Name |  | Acronym
| Surfacing Type | Chipseal |  |  | Scala - Minimum blows per 100mm | 2 |  |  | Foreman |  |  | FM
| Kerb and Channel | No |  |  | Scala - Minimum blows per 300mm |  |  |  | Quality Technician |  |  | QA
| ESA (Million ESA) | ` |  |  | Clegg - Minimum CIV value | >35 |  |  | Site Engineer |  |  | SE
|  | From design report |  |  | Material used for Subbase | WAP65 |  |  | Site Supervisor |  |  | SS
| Does design align with RITs standards | No |  |  | Target MDD value for subbase |  |  |  | Project Engineer |  |  | PE
| Theoretical max deflection on Basecourse (mm) |  |  |  | Material used for Basecourse | EME2 |  |  | Project Manager |  |  | PM
Target MDD value for basecourse
[9 empty] | Engineers Representative |  |  | ER
STRUCTURAL REHAB INSPECTION TESTING PLAN
Item No | Material Type | Typical Use | Item ID | Lab, PQE or Field, SE | Material Properties Required for Acceptability for Permanent Works |  |  |  |  | link | Action Point Records required | Responsibility
[5 empty] | Material Test Method Requirement | Reference Documents | Material Acceptance Criteria (Method) | Material Test Frequency* | Target Criteria
1 | Subgrade |  | 1.01 | Field | Scala Penetrometer Cohesive soils only | RITS Table 3-20 | NZS 4402.6.5.2:1988 | 1m inside of edge of seal and along centerline, Both lanes, at 10m spacing Minimum of 10 tests and/or at a frequency of 2 test per 10m chainage, whichever qty is greater | Confirm design assumptions - Scalar reaches minimum 2 blows/100mm |  | Test Record | QA / SE
|  |  | 1.02 | Field | Surface Level, Shape, and crossfall | RITS Table 3.24 | TNZ B/02:2005 Section 5 Fig 1 | 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal | +0mm/-30m from design or nominated level No more than 15mm deviation from a 3m straight edge |  | Survey record | QA / SE
|  |  | 1.03 | Field | Geogrid and Geofabric (cloth) installation | ISO:G 032 Version 2 | Manufracture installation instructions | 100% of Surface | Maintain minimum 300mm overlap between each roll on longitudinal and transverse joints. Geogrid and Geofabric shall be neatly installed without creases or folds. |  | Site Record | QA / SE
|  | Compliance | 1.04 | PE | Is the layer closed out ? | See PQE | See PQE | 100% of Surface Prior to placement of material | PQE Approval All testing record & reviewed as comliant. Available Documents: Test records Survey records Hold Point Records |  | Hold Point | PM
2 | Subbase | Compliance | 2.01 | PE | Has the material used in this layer been formally accepted for use? | Insert Material Testing link | See PQE | Prior to construction commencing | Material meets project requirements |  | Hold Point | QA / SE
|  |  | 2.02 | Field | Plateau Density Test | TNZ B/02: 2005 | TNZ B/02: 2005 | Minimum of 1 test per to determine obtainable MDD target for Compliance NDM testing Target to be approved by Engineer | N/A |  | Hold Point Test Record | QA / SE
|  |  | 2.03 | Field | Clegg Hammer | RITS Table 3-21 | RITS 3.8.3.3 ASTM D5874-16 | Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater | CIV ≥ 35 |  | Test Record | QA / SE
|  |  | 2.04 | Field | Compaction NDM Back Scatter | RITS Table 3-22 | RITS 3.8.3.4 4407:2015 test 4.3 | Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater | Mean ≥ 95 % MDD Minimum ≥ 92% MDD |  | Test Record | QA / SE
|  |  | 2.05 | Field | Surface Level, Shape, and crossfall | RITS Table 3.24 | TNZ B/02:2005 Section 5 Fig 1 | 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal | +5mm/-25m from design or nominated level No more than 15mm deviation from a 3m straight edge |  | Survey record | QA / SE
|  | Compliance | 2.06 | PE | Is the layer closed out ? | See PQE | See PQE | 100% of Surface Prior to placement of material | PQE Approval All testing record & reviewed as comliant. Available Documents: Test records Survey records Hold Point Records |  | Hold Point | PM
3 | Membrane | Compliance | 3.01 | PE | Seal Design | INSERT SEAL DESIGN | TNZ M/1 Table 1 Tests | Prior to sealing commencing (Minimum 1 week prior to application) | Meets project requirements |  | Hold Point | QA / SE
|  | Compliance | 3.02 | PE | Bitumen Sprayer | TNZ P3 | Certification provided | Prior to starting | Current E/2 Certificate |  | Certificate Sheet | QA / SE
|  | Compliance | 3.03 | PE | Has the material used in this layer been formally accepted for use? | Insert Material Testing | See PQE | Prior to construction commencing | Material meets project requirements |  | Hold Point | QA / SE
|  |  | 3.04 | Field | Preseal Inspection | TNZ B/02: 2005 | TNZ B/02: 2005 | 100% of Surface Prior to sealing of surface | All loose aggregate, dirt, dust, silt and deleterious matter has been removed. |  | Test Record | QA / SE
|  |  | 3.05 | Field | GO/NO GO Survey | Downers processes | Downer survey sealing GO/NO GO,Road science Zeus app & Downer Iris app | Prior to sealing on each site | Pass on GO/NO GO ,Marginal & discussion with contract Manager or Written approval from Rehab manager |  | Survey record | QA / SE
|  |  | 3.06 | Field | Application Rate | TNZ P/3 : 1995.18 | Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer | Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling | binder application rate is +/-50ltrs + 4% of the application rate |  | Spray Sheet | QA / SE
|  |  | 3.07 | Field | Post Seal Inspection | TNZ P3: 1995 | Engineers Inspection | After sealing | The chip is embedded, uniformily placed and chipseal is fit for purpose |  | Witness Point | QA / SE
4 | EME2 Mix NZTA M32:2021 | Compliance | 4.01 | PE | Has the material used in this layer been formally accepted for use? | Insert Asphalt Design & Material Records NZTA -M32 Specification for high modulus asphalt EME 2) | Approved Treatment Design | Prior to paving works commencing | Treatment Design validation |  | Hold Point | QA / SE
|  | Production Testing and Cores | 4.02 | Lab | In-situ mat density calibration cores | NZTA M32: 2021, 9.8.1 | ASTM D5361 | 1 test per 300m² per layer (Min 8 / Construction lot) 1 test per 100m per layer length (min 3 / Construction lot) | Characteristic value - mix design air void +3% -2% |  | Hold Point | QA / SE
|  |  | 4.03 | Lab | Grading (Particle Size Distribution) | NZTA M32: 2021, 5.3 | NZS 4407:2015 test 3.8 | One test per 200 tonnes of production | Tolerance from nominated JMF grading as per NZTA M32: 2021, Table 5.3 |  | Test record | QA / SE
|  |  | 4.04 | Lab | Binder content | NZTA M32: 2021, 5.3 | ASTM D2172 | One test per 200 tonnes of production | Tolerance on JMF Individual ±0.5 Rolling Average of 3 ±0.3% |  | Test record | QA / SE
|  |  | 4.05 | Lab | Maximum Theoratical Specific Gravity | NZTA M32: 2021, 5.3 | ASTM D2041 | One test per 200 tonnes of production | Report Value |  | Test record | QA / SE
|  |  | 4.06 | Lab | Air Voids | NZTA M32: 2021, 5.3 | ASTM D3203-22 | One test per 600 tonnes of production | As specified for each mix type |  | Test record | QA / SE
|  |  | 4.07 | Field | Load Locate | Downer Procedures | Each load can be indentified to a location. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth | Every Load | All data is collected |  | QA Sheet | QA / SE
|  |  | 4.08 | Field | NDM Density Testing On-Site Mat and Joint | NZTA M32: 2021, 9.8 Table 9.2 | ASTM D2950 ASTM D5361 | 1 test per 300m² per layer (Min 8 / Construction lot) 1 test per 100m per layer length (min 3 / Construction lot) | Mat: Mean air voids JMF +3,-2 Join: Mean air voids JMF +5,-2 |  | Test record | QA / SE
|  |  | 4.09 | Field | Plateau Density Test | TNZ B/02: 2005 | TNZ B/02: 2005 | 1 test per site | N/A |  | Test Record | QA / SE
|  |  | 4.1 | Field | Surface Level- Stringline checks for validation | NZTA M32:2021 10.2 and 10.3 Downer Procedures | Contract Specifications | 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal | +15mm/-5mm from design or nominated level No more than 8mm deviaton from a 3m straight edge |  | Survey record | QA / SE
|  |  | 4.11 | Field | Post Surfacing Inspection | CCA Procedures | Contract Specifications | 100% of site After surfacing (within 5 days) | Line marking has been reinstated All excess material has been removed from site All CPs are clear from filter fabric and any excess material removed from on top service covers |  | Survey record | PM
5 | First Coat Seal | Compliance | 5.01 | PE | Seal Design | INSERT SEAL DESIGN | TNZ M/1 Table 1 Tests | Prior to sealing commencing (Minimum 1 week prior to application) | Meets project requirements |  | Hold Point | QA / SE
|  | Compliance | 5.02 | PE | Bitumen Sprayer | TNZ P3 | Certification provided | Prior to starting | Current E/2 Certificate |  | Certificate Sheet | QA / SE
|  | Compliance | 5.03 | PE | Has the material used in this layer been formally accepted for use? | Insert Material Testing | See PQE | Prior to construction commencing | Material meets project requirements |  | Hold Point | QA / SE
|  |  | 5.04 | Field | Preseal Inspection | TNZ B/02: 2005 | TNZ B/02: 2005 | 100% of Surface Prior to sealing of surface | All loose aggregate, dirt, dust, silt and deleterious matter has been removed. |  | Test Record | QA / SE
|  |  | 5.05 | Field | Degree of Saturaton | TNZ B/02: 2005 | TNZ B/02: 2005 | 1 set of 5 per 1000m² - then 1 per 200m² | < 80 % Completed Max 48hrs before sealing |  | Test Record | QA / SE
|  |  | 5.06 | Field | GO/NO GO Survey | Downers processes | Downer survey sealing GO/NO GO,Road science Zeus app & Downer Iris app | Prior to sealing on each site | Pass on GO/NO GO ,Marginal & discussion with contract Manager or Written approval from Rehab manager |  | Survey record | QA / SE
|  |  | 5.07 | Field | Road temp | TNZ P3:1995.18 | Temperature recorded on site prior to sealing commencing | Once per day of sealing prior to sealing commencing | Air temp >10°C |  | Spray sheet | QA / SE
|  |  | 5.08 | Field | Application Rate | TNZ P/3 : 1995.18 | Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer | Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling | binder application rate is +/-50ltrs + 4% of the application rate |  | Spray Sheet | QA / SE
|  |  | 5.09 | Field | Chip spread rate | TNZ P3: 1995.21 | area sealed (m2) to be divided by the volume of chip spread (m3) Chipsealing in New Zealand (pg 435) | Total amount of chip used to be calculated at end of days sealing | Visual checks meets seal design requirements |  | Witness Point/Spray sheet | QA / SE
|  |  | 5.1 | Field | Rolling Checks | TNZ P3: 1995.22 | Sealing Record | for each sealing site per day | As per rolling requirements defined in TNZ P3: 1995.22. |  | Witness Point/Spray sheet | QA / SE
|  |  | 5.11 | Field | Post Seal Inspection | TNZ P3: 1995 | Engineers Inspection | After sealing | The chip is embedded, uniformily placed and chipseal is fit for purpose |  | Witness Point | QA / SE
6 | Post Construction | Compliance | 6.01 | PE | Asbuilt and RAMM Data | RAMM Update sheet | Asset Management Information Plan | After works complete | RAMM sheet 100% complete and accurate . |  | RAMM Asset Update sheet | PM
|  | Compliance | 6.02 | Field | Site Safety Audit | [5 empty] | Test Record | PM

## Sheet2
ASTM D3203-22
ASTM D2041

## Full ITP (hidden)
REHAB INSPECTION TESTING PLAN
Item No | Material Type | Typical Use | Item ID | CEA Lab, Supplier or Field | Material Properties Required for Acceptability for Permanent Works | [7 empty] | NOTES
[5 empty] | Material Test Method Requirement | Reference Documents | Material Acceptance Criteria (Method) | Material Test Frequency* | Target Criteria | link | Action Point Records required | Responsibility
1 | sub grade layer | Onsite Testing | 1.01 | Field | checking for CBR | RITS Table 3.20 | NZS 4402.6.5.2:1988 | at every 10m alternating or staggered intervals depending on the width of carriageway | 3 minimum blows/100mm or CBR 7 |  | Survey record | site engineer / Project Engineer/PQE
|  |  | 1.02 | Field | Surface Level, Shape, and crossfall | RITS Table 3.24 | TNZ B/02:2005 Section 5 Fig 1 | 5 points every 10 m | Tolerence -30 to 0 mm |  | Survey record | site engineer / Project Engineer/PQE
|  |  | 1.03 | Field | Tenser Triaxial Geogrid and Geofabric (cloth) installation | Tensar construction sequence CS_TriAx/30.04.08 | Maintain minimum 300mm overlap between each roll on longitudinal and transverse joints. Geogrid and Geofabric shall be neatly installed without creases or folds. | For full length pavement. |  |  |  | site engineer / Project Engineer/PQE
2 | sub base testing | Compliance | 2.01 | PQE | Has the material used in this layer been formally accepted for use? | Insert Material Testing link | See PQE | Prior to construction commencing | Material meets project requirements |  | Hold Point | site engineer / Project Engineer/PQE
|  | Onsite Testing | 2.02 | Lab | Plateau Density Test | TNZ B/02: 2005 | TNZ B/02: 2005 | 1 test per 5,000m² | N/A |  | Test record | site engineer / Project Engineer/PQE
|  |  | 2.03 | Field | Surface Level, Shape, and crossfall | RITS Table 3.24 | TNZ B/02:2005 | 2 points (per shoulder and median) at a 20m frequency | tolerence -25 to +5 mm |  | Survey record | site engineer / Project Engineer/PQE
3 | Basecourse Placement | Compliance | 3.01 | PQE | Has the material used in this layer been formally accepted for use? | See PQE | See PQE | Prior to construction commencing | Material meets project requirements |  | Test record | site engineer / Project Engineer/PQE
4 | stabilized basecourse | Onsite Testing | 4.01 | Field | Visual Inspection of previous layer | See PQE | See PQE | 100% of Surface Prior to placement of material | Engineers Approval (The larger aggregate is held in place by with a matrix of smaller aggregates, the smaller aggregate is held firmly in place by cemented fine material, and the matrix does not displace under normal trafficking or sweeping No evidence of rutting in surface of Hi Lab) |  | Hold Point | site engineer / Project Engineer/PQE
|  |  | 4.02 | Field | Stinging for basecourse layer | RITS : Table 3.24 | See PQE | at every 10m alternating or staggered intervals depending on the width of carriageway | Tolerence -5mm to +15mm |  |  | site engineer / Project Engineer/PQE
|  |  | 4.03 | Field | Plateau Test | To achieve the OWC and MDD of the basecourse | TRANSIT TNZ B/5: 2008 7.7 | once for specified material | N/A |  |  | site engineer / Project Engineer/PQE
|  |  | 4.04 | Field | Clegg Hammer | RITS Table 3.21 | RITS 3.8.3.3 | At 10 m Alternating or staggered intervals depending on the width of carriageway | For clegg 40 CIV minimum |  |  | site engineer / Project Engineer/PQE
|  |  | 4.05 | Field | NDM | RITS Table 3.22 | 4407:2015 test 4.3 | At 10 m Alternating or staggered intervals depending on the width of carriageway | NDM minimum 92% MDD and 95% MDD average |  |  | site engineer / Project Engineer/PQE
|  |  | 4.06 | Field | BEAMS | RITS Table 3.23 | TNZ T/1 June 1977 | At 10 m Alternating or staggered intervals depending on the width of carriageway | depending on traffic |  |  | site engineer / Project Engineer/PQE
5 | Stabilisation | Onsite Testing | 5.01 | Field | Cement application Mat test | TNZ B/5:2008 | TNZ B/5:2008 | 1 test per 400m² (minimum 2 per run) | ±0.50kg/m² of specified rate |  | Stabilisation QA sheet | site engineer / Project Engineer/PQE
|  |  | 5.02 | Field | Stabilisation Depth | TNZ B/5:2008 | TNZ B/5:2008 | 1 test hole every 50m staggered between left-and right-hand edges of the run | Visual check to confirm that cement has been mixed to the correct depth, and as near as possible to full depth without mixing into the previous layer |  | Stabilisation QA sheet | site engineer / Project Engineer/PQE
|  |  | 5.03 | Field | Surface Level, Shape, and Crossfall | RITS table 3-24 | TNZ B/5:2008 | 5 points per 2 lanes (+1 point per add. Lane) at a 20m frequency | +15mm/-5mm no point in the surface varies more than 12 mm from a 3.0m straight edge placed on the road |  | Survey record | site engineer / Project Engineer/PQE
6 | pre seal inspection | Compliance | 6.01 | PQE | Has the Basecourse been given Approval to Proceed | Insert Approval to Proceed Documents Number | Approval to Proceed process | 1 document per lot | Available Documents: Test records Survey records Site Obs records Witness Points |  | Hold Point | site engineer / Project Engineer/PQE
|  |  | 6.02 | PQE | stone mosaic | TNZ B/2 | NZTA Chapter -07 Preseal preaparation Cl 7.2.1 | Throughout the surface | Clean stone mosaic surface that will not ravel as a result of sweeping |  |  | site engineer / Project Engineer/PQE
|  |  | 6.03 | PQE | straight edge | RITS Table 3-24 | within 12mm deviation from 3m staight edge | Throughout the surface |  |  |  | site engineer / Project Engineer/PQE
|  |  | 6.04 |  | client approval |  | Complaince with item ID 6.01, 6.02, 6.03 |  |  |  |  | site engineer / Project Engineer/PQE
7 | wearing surface First Coat Application | For Compliance | 7.01 | PQE | Seal Design | INSERT SEAL DESIGN | TNZ M/1 Table 1 Tests | Prior to sealing commencing (Minimum 1 week prior to application) | Meets project requirements |  | Hold Point | site engineer / Project Engineer/PQE
|  |  | 7.02 | PQE | Has the material used in this layer been formally accepted for use? | Insert Material Testing | See PQE | Prior to construction commencing | Material meets project requirements |  | Hold Point | site engineer / Project Engineer/PQE
|  |  | 7.03 |  | GO/NO GO Survey | Downer survey sealing GO/NO GO,Road science Zeus app & Downer Iris app |  | Prior to sealing on each site | Pass on GO/NO GO ,Marginal & discussion with contract Manager or Written approval from Rehab manager |  |  | site engineer / Project Engineer/PQE
|  | On Site Testing | 7.04 | Field | Road temp | TNZ P3:1995.18 | Temperature recorded on site prior to sealing commencing | Once per day of sealing prior to sealing commencing | Air temp >10°C |  | Spray Sheet | site engineer / Project Engineer/PQE
|  |  | 7.05 | Field | Application Rate | TNZ P/3 : 1995.18 | Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer | Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling | binder application rate is +/-50ltrs + 4% of the application rate |  | Spray Sheet | site engineer / Project Engineer/PQE
|  |  | 7.06 | Field | Chip spread rate | TNZ P3: 1995.21 | area sealed (m2) to be divided by the volume of chip spread (m3) Chipsealing in New Zealand (pg 435) | Total amount of chip used to be calculated at end of days sealing | Visual checks meets seal design requirements |  | Witness Point/Spray sheet | site engineer / Project Engineer/PQE
|  |  | 7.07 | Field | Rolling Checks | TNZ P3: 1995.22 | Sealing Record | for each sealing site per day | As per rolling requirements defined in TNZ P3: 1995.22. |  | Witness Point/Spray sheet | site engineer / Project Engineer/PQE
|  |  | 7.08 | Field | Post Seal Inspection | TNZ P3: 1995 | Engineers Inspection | After sealing | The chip is embedded, uniformily placed and chipseal is fit for purpose |  | Witness Point | site engineer / Project Engineer/PQE
|  |  | 7.09 |  | High speed Rutting & NAASRA - Road Roughness | CCA DOC | Laser Profilometer Survey | After first coat sealing and prior to final surfacing with either EMOGPA, OGPA, SMA, or second coat sealing; After 12 months of trafficking; End of defects liability All lanes at 20m intervals in each wheel path and staggered by 10m between wheel paths | High Speed Rutting: > 5mm Report to Designer NAASRA reading:Shall not exceed 70 counts/km as a 95th percentile value |  | Test Record | site engineer / Project Engineer/PQE
8

## Sheet1
Yes
No
Frequency
|  | CBR and Deflection testing | Compaction testing | Surface Level, Shape, and crossfall
| Carriageway 4.0m wide and less | Along centerline, at 15m spacing (no greater than 30m between tests) Minimum of 10 tests and/or at a frequency of 1 test per 15m chainage, whichever qty is greater | Scattered across carriageway width, at 30m spacing (no greater than 60m between tests, no closer than 15m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater | 3 Points across full width of carriageway at 10m frequency Edge of Seal, Centerline, Edge of Seal
| Carriageways between 4.0m and 8.0m | 1m inside of edge of seal, on alternating lanes, at 10m spacing (no greater than 20m between tests) Minimum of 10 tests and/or at a frequency of 1 test per 10m chainage, whichever qty is greater | Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater | 5 Points across full width of carriageway at 10m frequency Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
| Carriageways greater than 8.0m in width | 1m inside of edge of seal and along centerline, staggered across lanes, at 10m spacing (no greater than 20m between tests) Minimum of 10 tests and/or at a frequency of 1 test per 10m chainage, whichever qty is greater | Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater | 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal
|  | Chipseal | Asphalt
| Residential cul-de-sacs and private ways <40 units | Average: 1.50mm 90th %ile: 1.80mm Max: 2.40mm | Average: 1.30mm 90th %ile: 1.60mm Max: 2.10mm
| Carriageways less than a million ESAs | Average: 1.25mm 90th %ile: 1.50mm Max: 1.80mm | Average: 1.10mm 90th %ile: 1.35mm Max: 1.80mm
| Carriageways greater than a million ESAs | Average: 1.00mm 90th %ile: 1.20mm Max: 1.60mm | Average: 1.00mm 90th %ile: 1.20mm Max: 1.60mm
| Cohesive Soils |  |  | Granular
CBR | Penetration per blow (mm) | Min blows/100mm | Min blows/300mm | CIV
1 | 109.5 | n/a | 3 | n/a
2 | 65 | n/a | 5 | n/a
3 | 47.2 | n/a | 7 | n/a
4 | 36 | n/a | 9 | n/a
5 | 30.5 | n/a | 10 | n/a
6 | 27.5 | n/a | 11 | n/a
7 | 24.6 | n/a | 13 | n/a
8 | 22 | n/a | 14 | n/a
9 | 20 | n/a | 15 | n/a
10 | 18.7 | 6 | n/a | n/a
11 | 17 | 6 | n/a | n/a
12 | 17.5 | 6 | n/a | n/a
13 | 16.7 | 6 | n/a | n/a
14 | 15.5 | 7 | n/a | n/a
15 | 13.7 | 8 | n/a | 15
20 | 11 | 10 | n/a | 28
30 | 8.5 | 12 | n/a | 63
40 | 7 | 15 | n/a | 112
50 | 5.5 | 19 | n/a | 175