## ITP Cover Page
Pavement Type 9 - Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 031 - Rev 0
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project |  |  |  |  | ITP Number: |  |  | 031
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  |  | Draft For Approval
ITP Description: |  |  | Pavement Type 9 Inspection and Test Plan |  |  |  |  | Revision: | 1000 |  | 0
Contract Number: |  |  | NZTA8287 |  |  |  |  | Drawing Sets: |  |  | 232735.02-WSP-DR-PVS
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Contract specification
Quality Specified: |  |  | ISO 9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 2024-11-15 | [7 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | Chris Benson | [5 empty] | Downer PM
Downer QM |  | Cordelia Girdler-Brown |  |  |  |  | 18/11/2024 | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Pavement Type 9 - Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 031 - Rev 0
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 1 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
1.1 | Imported hard fill - GAP20 SOURCE MATERIAL TESTING - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
1.1.1 | Material grading:PSD Materials GAP20 | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Sieve Size % Passing 19.0mm 100% passing 9.5mm 52-76% passing 4.75mm 33-57% passing 2.36mm 20-44% passing 1.18mm 12-35% passing 0.600mm 7-25% Passing 0.300mm 4-20%Passing 0.150mm 0-12% passing 0.075mm 0-8% passing | NZS4407:2015 Test 3.10 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.1.2 | Weathering index: Materials GAP20 | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | CB,CC,CA. | NZS4407:2015 Test 3.11 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.1.3 | Crushing Resistance: Materials GAP20 | Pavement layer on top of underpass | Engineers Approval >100kN | PS-21.7.2 | IANZ Accredited Report | 2 test per source | HP | ENG
1.1.4 | Maximum Dry Density and Optimum Water Content | NZS4402:1986, Test 4.1.2 - Heavy Compaction Test | Report Value Only | NZS4402:1986 Test 4.1.2 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.1.5 | Geogrid | Triaxial geogrid to be laid on top of the sand layer extending it 1m on both sides | Engineers Apprvoal | WSP-DR-PVS-0401 | Engineers Apprvoal | Once before works commence | HP | ENG
1.1.6 | Mix Design | Concrete Mix Design needs to be Sumbiited to an Engineer. | Engineers Apprvoal | WSP-DR-PVS-0401 | Engineers Apprvoal | Once before works commence | HP | ENG
SECTION 2 - CONSTRUCTION OF UNBOUND AP20 LAYER
2.1 | Finished Level - Stringline or Equivalent
2.1.1 | Install 2 layer of polythene sheet on top of underpass | Installation of Polythene to be directly on top of underpass precast unit 2 layers of polythene to be laid to prevent the puncture of the water seal during compaction | Visual Inspection | WSP-DR-PVS-0401 | Visual Inspection | During Construction | I | SE
2.1.2 | Sand Layer | 20mm sand layer to cushion the polythene layer | Visual Inspection | WSP-DR-PVS-0401 | Visual Inspection | During Construction | I | SE
2.1.3 | Place Triaxial Geogrid over underpass extending 1m on both sides | Triaxial geogrid T600 to be laid on top of the sand layer extending it 1m on both sides | Visual Inspection | WSP-DR-PVS-0401 | Visual Inspection | During Construction | I | SE
2.1.4 | Stringlines or equivalent | Stringlines or equivalent to check finished height of surface | -0mm + 20mm | NZTA B/06 8.2.2 | Check Sheet | During Construction | I | SE
2.2 | Compaction - NDM
2.2.1 | Compaction - NDM of AP 20 layer | NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode) | Min >92% of MDD | NZTA B/06 8.1 | IANZ Accredited Report | 1 set (5 tests) 1000m2 | I | SE
SECTION 3 – CONSTRUCTION - 10Mpa LEAN MIX CONCRETE
3.1 | Finished Level - Stringline or Equivalent
3.1.1 | Stringlines or equivalent | Stringlines or equivalent to check height of surface prep | +/-5mm | PS 21.7.6 | Check Sheet | 1 Test along kerb line @ 20m centres | I | SE
3.1.2 | Pre pour inspection to be done before concrete pour, Check delivery dockets | Pre pour inspection with designer to verify the surface is clean and all works has been finished before pour which will stop concrete from flowing outside the pouring area | Visual Inspection | WSP-DR-PVS 0401 Rev 3 | Pre-pour Check Sheet 'Visual Inspection | Each pour | HP | ENG
3.1.3 | Slump test and compressive strength test of concrete | Ensure lean mix concrete with slump 40-80mm and take samples for compressive strength test | within tolerence: +20mm for slump test and minimum compressive strength of 10MPA @28 days | WSP-DR-PVS 0401 Rev 3 | IANZ Accredited Report/ Concrete delivery docket | Each pour | I | SE
3.1.4 | Stringlines or equivalent | Stringlines or equivalent to check finished height of surface. 235mm Below | (-15mm +0mm) | NZTA B/06 8.2.2 | Check Sheet | During Construction | I | SE
SECTION 4 – KERB & CHANNEL PREPARATION
4.1 | Finished Level - Stringline or Equivalent
4.1.1 | Stringlines or equivalent | Stringlines or equivalent to check height of surface prep | +/-5mm | PS 21.7.6 | Check Sheet | 1 Test along kerb line @ 20m centres | I | SE
4.2 | Compaction - Clegg Hammer
4.2.1 | Compaction - Clegg Hammer | ASTM D5874-16:2016 Clegg Hammer Testing | Min 25 CIV |  | Clegg Hammer Report | 1 Test along kerb line @ 20m centres | I | SE
SECTION 5 – AS-BUILTS / REDPEN MARKUPS
4.1 | As-Builts/ Red pen markup | As-Built records and drawings shall accurately record the layout and extents of all the work including all the changes been made different from design. | Red pen markups | PS 16.7.6 | Red pen markups | During Construction | D | SV