## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-031 ITP Pavements Type 09 | itp |  |  |  |  | DN1210-031 ITP Pavements Type 09 Rev 0
section | SECTION 1 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
checkpoint | 1.1.1 - Material grading: PSD Materials GAP20
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 19.0mm ¦¦ 100% passing
label | 9.5mm ¦¦ 52-76% passing
label | 4.75mm ¦¦ 33-57% passing
label | 2.36mm ¦¦ 20-44% passing
label | 1.18mm ¦¦ 12-35% passing
label | 0.600mm ¦¦ 7-25% Passing
label | 0.300mm ¦¦ 4-20%Passing
label | 0.150mm ¦¦ 0-12% passing
label | 0.075mm ¦¦ 0-8% passing
label | Standard / Specification - NZS4407:2015 Test 3.10
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source, Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.2 - Weathering index: Materials GAP20
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - CB,CC,CA.
label | Standard / Specification - NZS4407:2015 Test 3.11
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source, Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.3 - Crushing Resistance: Materials GAP20
label | Detail - Pavement layer on top of underpass
label | Acceptance / Conformance Criteria - Engineers Approval >100kN
label | Standard / Specification - PS-21.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 test per source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.4 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4402:1986 Test 4.1.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source, Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.5 - Geogrid
label | Detail - Triaxial geogrid to be laid on top of the sand layer extending it 1m on both sides
label | Acceptance / Conformance Criteria - Engineers Apprvoal
label | Standard / Specification - WSP-DR-PVS-0401
label | Verifying Document - Engineers Apprvoal
label | Testing Quantity Required (based from schedule qtys) - Once before works commence
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.6 - Mix Design
label | Detail - Concrete Mix Design needs to be Sumbiited to an Engineer.
label | Acceptance / Conformance Criteria - Engineers Apprvoal
label | Standard / Specification - WSP-DR-PVS-0401
label | Verifying Document - Engineers Apprvoal
label | Testing Quantity Required (based from schedule qtys) - Once before works commence
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 2 - CONSTRUCTION OF UNBOUND AP20 LAYER
checkpoint | 2.1.1 - Install 2 layer of polythene sheet on top of underpass
label | Detail - Installation of Polythene to be directly on top of underpass precast unit 2 layers of polythene to be laid to prevent the puncture of the water seal during compaction
label | Acceptance / Conformance Criteria - Visual Inspection
label | Standard / Specification - WSP-DR-PVS-0401
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.1.2 - Sand Layer
label | Detail - 20mm sand layer to cushion the polythene layer
label | Acceptance / Conformance Criteria - Visual Inspection
label | Standard / Specification - WSP-DR-PVS-0401
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.1.3 - Place Triaxial Geogrid over underpass extending 1m on both sides
label | Detail - Triaxial geogrid T600 to be laid on top of the sand layer extending it 1m on both sides
label | Acceptance / Conformance Criteria - Visual Inspection
label | Standard / Specification - WSP-DR-PVS-0401
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.1.4 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface
label | Acceptance / Conformance Criteria - -0mm + 20mm
label | Standard / Specification - NZTA B/06 8.2.2
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.2.1 - Compaction - NDM of AP 20 layer
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Min >92% of MDD
label | Standard / Specification - NZTA B/06 8.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) 1000m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 3 – CONSTRUCTION - 10Mpa LEAN MIX CONCRETE
checkpoint | 3.1.1 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check height of surface prep
label | Acceptance / Conformance Criteria - +/-5mm
label | Standard / Specification - PS 21.7.6
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Test along kerb line @ 20m centres
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.1.2 - Pre pour inspection to be done before concrete pour, Check delivery dockets
label | Detail - Pre pour inspection with designer to verify the surface is clean and all works has been finished before pour which will stop concrete from flowing outside the pouring area
label | Acceptance / Conformance Criteria - Visual Inspection
label | Standard / Specification - WSP-DR-PVS 0401 Rev 3
label | Verifying Document - Pre-pour Check Sheet, Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Each pour
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.3 - Slump test and compressive strength test of concrete
label | Detail - Ensure lean mix concrete with slump 40-80mm and take samples for compressive strength test
label | Acceptance / Conformance Criteria - within tolerence: +20mm for slump test and minimum compressive strength of 10MPA @28 days
label | Standard / Specification - WSP-DR-PVS 0401 Rev 3
label | Verifying Document - IANZ Accredited Report/ Concrete delivery docket
label | Testing Quantity Required (based from schedule qtys) - Each pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.1.4 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface. 235mm Below
label | Acceptance / Conformance Criteria - (-15mm +0mm)
label | Standard / Specification - NZTA B/06 8.2.2
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 4 – KERB & CHANNEL PREPARATION
checkpoint | 4.1.1 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check height of surface prep
label | Acceptance / Conformance Criteria - +/-5mm
label | Standard / Specification - PS 21.7.6
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Test along kerb line @ 20m centres
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2.1 - Compaction - Clegg Hammer
label | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Min 25 CIV
label | Standard / Specification -
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test along kerb line @ 20m centres
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 5 – AS-BUILTS / REDPEN MARKUPS
checkpoint | 5.1 - As-Builts/ Red pen markup
label | Detail - As-Built records and drawings shall accurately record the layout and extents of all the work including all the changes been made different from design.
label | Acceptance / Conformance Criteria - Red pen markups
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Red pen markups
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature