## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | RR-SEPD-BESS-FIC-002-00 - Concrete slabs - | itp |  |  |  |  | RR-SEPD-BESS-FIC-002-00 - Concrete slabs
section | Part 1 – Preliminaries (photos where applicable)
checkpoint | Review of approved construction drawings and specifications
label | All drawings and specifications approved and up to date
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-007
checkpoint | Verification of permits
label | All relevant permits (GDA/GDP) in place
label | Specifications/Drawings Reference - GDA/GDP
checkpoint | Site access and safety preparation
label | Site access cleared and made safe
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-007
checkpoint | Safety inductions and toolbox talks
label | All personnel inducted; safety briefings completed
label | Specifications/Drawings Reference - Induction record
checkpoint | Environmental controls in place
label | Dust, noise, and sediment barriers installed and functioning
label | Specifications/Drawings Reference - SEPD environmental requirements
section | Part 2 – Survey (photos where applicable)
checkpoint | Set-out of slab location
label | Slab set-out conforms to approved design coordinates
label | Specifications/Drawings Reference - Site Layout Drawings, Survey Plan
checkpoint | Level and alignment check
label | Levels and alignment of formwork and slab position verified
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-0007, Survey Report
checkpoint | As-built survey after formwork and reinforcement
label | Survey to confirm reinforcement cover and formwork position
label | Specifications/Drawings Reference - As-Built Drawings, Survey Report
section | Part 3 – Pre-pour inspection (photos where applicable)
checkpoint | Review of approved concrete mix design
label | Mix design approved P3220100
label | Specifications/Drawings Reference - AS 1379, WBS-SS-CI-SPC-0007
checkpoint | Formwork installation
label | Formwork aligned, clean, and secure; dimensions correct
label | Specifications/Drawings Reference - AS 3610, WBS-SS-CI-SPC-0007
checkpoint | Reinforcement placement
label | Reinforcement size, placement, spacing and cover as per drawings
label | Specifications/Drawings Reference - AS 4671, WBS-SS-CI-SPC-0007
checkpoint | Reinforcement ties
label | Reinforcement securely tied in place, no loose bars
label | Specifications/Drawings Reference - AS 4671
checkpoint | Installation of dowels
label | Correct placement of all embedded items, dowels aligned
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-0007
checkpoint | Waterproofing membrane
label | Membrane installed per design; overlaps secured
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-0007
checkpoint | Crack control joints
label | Joints placed and cut as per drawings and specifications
label | Specifications/Drawings Reference - AS 3600, WBS-SS-CI-SPC-0007
checkpoint | Construction joints
label | Joints placed and prepared as per drawings and specifications
label | Specifications/Drawings Reference - AS 3600, WBS-SS-CI-SPC-0007
checkpoint | Site safety inspection prior to pour
label | Site clear, access routes checked, and emergency plans in place
label | Specifications/Drawings Reference - Safety Plan, WBS-SS-CI-SPC-0007
section | Part 4 – Concrete pouring and compaction (photos where applicable)
checkpoint | Concrete delivery
label | Delivery in line with approved mix design
label | Specifications/Drawings Reference - AS 1379, Delivery dockets
checkpoint | Slump test
label | Slump within specified range (e.g., 100mm +/- 20mm)
label | Specifications/Drawings Reference - AS 1012, Slump Test Results
checkpoint | Concrete placement
label | Concrete placed within formwork without segregation or delays
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-0007
checkpoint | Compaction of concrete
label | Concrete compacted using vibrators, no visible voids or honeycombing
label | Specifications/Drawings Reference - AS 3600, WBS-SS-CI-SPC-0007
checkpoint | Cylinder sampling for compressive strength
label | Cylinder samples taken for 7, 14, 28-day tests
label | Specifications/Drawings Reference - AS 1012, Sample Register
checkpoint | Concrete temperature monitoring (if required)
label | Temperature recorded during pouring
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-0007, Pour record
section | Part 5 – Post-pour inspection (photos where applicable)
checkpoint | Surface finish
label | Class 5
label | Specifications/Drawings Reference - AS 3610, WBS-SS-CI-SPC-0007
checkpoint | Curing method
label | Curing compound or wet curing applied as per requirements
label | Specifications/Drawings Reference - AS 3799, WBS-SS-CI-SPC-0007
checkpoint | Formwork stripping
label | Formwork removed after concrete reaches required strength
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-0007
checkpoint | Compressive strength testing
label | Compressive strength results meet >32 MPa at 28 days
label | Specifications/Drawings Reference - AS 1012, Test Results
checkpoint | Inspection of surface cracks and defects
label | No major cracks or surface defects observed
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-0007
section | Part 5 – Final survey and as-built verification (photos where applicable)
checkpoint | As-built survey verification
label | As-built levels and layout match design
label | Specifications/Drawings Reference - As-Built Drawings, Survey Report
checkpoint | Final inspection sign-off
label | Final approval of the slab surface, dimensions, and finish
label | Specifications/Drawings Reference - FIC sign-off
section | Document Sign-off
checkpoint | Prepared by:
textbox | SEPD (Engineer) - Name:
date | SEPD (Engineer) - Date:
signoff | Add Signature